LENDER’S INDEPENDENT ENGINEER REPORT

(3rd Report)

Details of the property under consideration:

Name of Project: Poddar Riviera Phase - 1

Residential project on Plot Bearing Survey No. 9, Hissa No. 1B, 2 & 3, Survey No. 10 and 11, Hissa No. 1 & 2 of Village – Mharal, Taluka – Kalyan, District – Thane, Pin Code – 421 103, State - Maharashtra, Country – India

Latitude Longitude: 19°15'01.3"N 73°10'33.8"E

Valuation Prepared for:

STCI FINANCE LIMITED

A/B 1-802, A Wing, 8th Floor, Marathon Innova, Marathon Nextgen Compound,

Off. Ganpatrao Kadam Marg, Lower Parel (West), Mumbai – 400 013,

State – Maharashtra, Country – India

Vastu/STCI/ Mumbai/07/2023/2781/2301775

26/2-400-PY

Date: - 26.07.2023

THIRD LENDER’S INDEPENDENT ENGINEER REPORT

To,

STCI FINANCE LIMITED

A/B 1-802, A Wing, 8th Floor,

Marathon Innova, Marathon Nextgen Compound,

Off. Ganpatrao Kadam Marg,

Lower Parel (West), Mumbai – 400 013,

State – Maharashtra, Country – India

Subject: Construction of Residential project on Plot Bearing Survey No. 9, Hissa No. 1B, 2 & 3, Survey No. 10 and 11, Hissa No. 1 & 2 of Village – Mharal, Taluka – Kalyan, District – Thane, Pin Code – 421 103, State - Maharashtra, Country – India.

Ref: You’re Request for Lenders Independent Engineer Report of under Construction Building.

Dear Sir,

The Construction work as per approved plan was in progress during the site visit on 10th March 2023. Total expenditure occurred as on 31/12/2022 on this project by M/s. Poddar Housing and Development Ltd. is                      ` 104.74 Cr. & as per CA Certificate actual total expenditure occurred as on 31/12/2022 is ` 95.01 Cr. Hence, release of Balance Amount as requested by M/s. Poddar Housing and Development Ltd. is hereby recommended. As per plinth area calculation 12.00% construction work is completed and cost incurred till 31.12.2022 is 44.62%.

DECLARATION

- The information furnished in the report is based on our site visit Dated 10/03/2023 & Documents Provided by the client.

- I have no direct and indirect interest in the property examined for report.

- I have not been found guilty of misconduct in my professional capacity.

Manoj B. Chalikwar

Registered Valuer

Chartered Engineer (India)

Reg. No. IBBI/RV/07/2018/10366

# Purpose & Methodology

• STCI Finance Limited and financial institutions require monitoring & an independent review of the progress of the sanctioned projects

VCIPL undertakes such study to independently review the progress of the project and put forward a comprehensive analysis

# Advantages:

- Assurance on present practices

- Identification of risk

- Analyzing the performance of third parties

- Recommendations

# The Methodology

THIRD LENDER’S INDEPENDENT ENGINEER REPORT

OF

"Poddar Riviera Phase - 1"

Residential project on Plot Bearing Survey No. 9, Hissa No. 1B, 2 & 3, Survey No. 10 and 11, Hissa No. 1 & 2 of Village – Mharal, Taluka – Kalyan, District – Thane, Pin Code – 421 103, State - Maharashtra, Country – India

Latitude Longitude: 19°15'01.3"N 73°10'33.8"E

NAME OF DEVELOPER:  M/s. Poddar Housing and Development Ltd.

Pursuant to instructions from STCI Finance Limited, Lower Parel Branch, Mumbai we have duly visited, inspected, surveyed & assessed the above said property on 10th March 2023 to determine the work progress report of the said property/project as on Quarter ending 31st December 2022 for LIE purpose. 1. Location Details: The property is situated on Plot Bearing Survey No. 9, Hissa No. 1B, 2 & 3, Survey No. 10 and 11, Hissa No. 1 & 2 of Village – Mharal, Taluka – Kalyan, District – Thane, Pin Code – 421 103, State - Maharashtra, Country - India. It is about 3.0 Km distance from Shahad Railway Station of Central Railway line. Surface transport to the property is by buses, Auto, taxis & private vehicles. The property is in developed locality. All the amenities like shops, banks, hotels, markets, schools, hospitals, etc. are all available in the nearby locality. The locality is higher middle class & developed.

- Developer Details:

| Name of builder | M/s. Poddar Housing and Development Ltd. |
| --- | --- |
| Project Rera Registration Number | P51700023508 |
| Registered office address | Unit No. 3-6, Neeru Silk Mill, Mathuradas Mill compound, 126, N. M. Joshi Marg, Lower Parel (West), Mumbai - 400 013, State - Maharashtra, Country - India |
| Contact details | Contact Person: Umesh Sawant - (Company staff - Mobile No. 91673 99723) |
| E – mail ID and website |  |

3. 	Boundaries of the Property:

| Direction | Particulars |
| --- | --- |
| On or towards North | Ulhas River |
| On or towards South | Bhiwandi - Murbad Road |
| On or towards East | Konark Meadows |
| On or towards West | Open Plot |

# Introduction

As per Information on site M/s. Poddar Housing and Development Ltd. has acquired land by conveyance deed Date 17.12.2016 admeasuring area is 7 Hectare i.e., 70,000.00 Sq. M. bearing on Plot Bearing Survey No. 9, Hissa No. 1B, 2 & 3, Survey No. 10 and 11, Hissa No. 1 & 2 of Village – Mharal, For the development of residential Building.

# Area Statement:

# Land:

- As per Conveyance deed, total land area is 7 Hectare i.e., 70,000.00 Sq. M.

- As the project under reference finance by STCI Finance Limited is for Phase I only, land area under phase I is 16,054.00 Sq. M.

# List of Approvals:

- Copy of Mharal Collector order for construction consent dated 25.03.2022.

- Copy of Approved Layout Plan as per details below:

# LEVEL OF COMPLETION:

# Sale Building (Wing A1)

| Sr. No. | Floor | Construction Area in Sq. M. | Completed Area in Sq. M. | Work Completed As on 12.10.2022 |
| --- | --- | --- | --- | --- |
| 1 | Excavation Work | - |  | Excavation work is completed |
| 2 | Stilt Floor | 171.95 | 171.95 | Slab work is completed |
| 3 | 1st Floor (Podium) | 1,009.24 |  |  |
| 4 | 2nd Floor (Podium) | 1,009.24 |  |  |
| 5 | 1st Floor (Resi.) | 263.67 | 263.67 | Slab work is completed |
| 6 | 2nd Floor (Resi.) | 300.73 |  |  |
| 7 | 3rd Floor | 470.99 |  |  |
| 8 | 4th Floor | 470.99 |  |  |
| 9 | 5th Floor | 470.99 |  |  |
| 10 | 6th Floor | 470.99 |  |  |
| 11 | 7th Floor | 470.99 |  |  |
| 12 | 8th Floor | 470.99 |  |  |
| 13 | 9th Floor | 470.99 |  |  |
| 14 | 10th Floor | 470.99 |  |  |
| 15 | 11th Floor | 470.99 |  |  |
| 16 | 12th Floor | 470.99 |  |  |
| 17 | 13th Floor | 395.56 |  |  |
| 18 | 14th Floor | 470.99 |  |  |
| 19 | 15th Floor | 470.99 |  |  |
| 20 | 16th Floor | 470.99 |  |  |
| 21 | 17th Floor | 470.99 |  |  |
| 22 | 18th Floor | 395.56 |  |  |
| 23 | 19th Floor | 470.99 |  |  |
| 24 | 20th Floor | 470.99 |  |  |
| 25 | 21st Floor | 470.99 |  |  |
| 26 | 22nd Floor | 470.99 |  |  |
| 27 | 23rd Floor | 470.99 |  |  |
| TOTAL |  | 12,494.76 | 435.62 |  |

# Sale Building (Wing A2)

| Sr. No. | Floor | Construction Area in Sq. M. | Completed Area in Sq. M. | Work Completed As on 12.10.2022 |
| --- | --- | --- | --- | --- |
| 1 | Excavation Work | - |  | Excavation work is completed |
| 2 | Stilt Floor | 171.95 | 171.95 | Slab work is completed |
| 3 | 1st Floor (Podium) | 1,009.24 | - |  |
| 4 | 2nd Floor (Podium) | 1,009.24 | - |  |
| 5 | 1st Floor (Resi.) | 263.67 | 263.67 | Slab work is completed |
| 6 | 2nd Floor (Resi.) | 300.73 |  |  |
| 7 | 3rd Floor | 470.99 |  |  |
| 8 | 4th Floor | 470.99 |  |  |
| 9 | 5th Floor | 470.99 |  |  |
| 10 | 6th Floor | 470.99 |  |  |
| 11 | 7th Floor | 470.99 |  |  |
| 12 | 8th Floor | 470.99 |  |  |
| 13 | 9th Floor | 470.99 |  |  |
| 14 | 10th Floor | 470.99 |  |  |
| 15 | 11th Floor | 470.99 |  |  |
| 16 | 12th Floor | 470.99 |  |  |
| 17 | 13th Floor | 395.56 |  |  |
| 18 | 14th Floor | 470.99 |  |  |
| 19 | 15th Floor | 470.99 |  |  |
| 20 | 16th Floor | 470.99 |  |  |
| 21 | 17th Floor | 470.99 |  |  |
| 22 | 18th Floor | 395.56 |  |  |
| 23 | 19th Floor | 470.99 |  |  |
| 24 | 20th Floor | 470.99 |  |  |
| 25 | 21st Floor | 470.99 |  |  |
| 26 | 22nd Floor | 470.99 |  |  |
| 27 | 23rd Floor | 470.99 |  |  |
| TOTAL |  | 12,494.76 | 435.62 |  |

# Sale Building (Wing A3)

| Sr. No. | Floor | Construction Area in Sq. M. | Completed Area in Sq. M. | Work Completed As on 12.10.2022 |
| --- | --- | --- | --- | --- |
| 1 | Excavation Work | - |  | Excavation work is completed |
| 2 | Stilt Floor | 171.95 | 171.95 | Slab work is completed |
| 3 | 1st Floor (Podium) | 1,009.24 | - |  |
| 4 | 2nd Floor (Podium) | 1,009.24 | - |  |
| 5 | 1st Floor (Resi.) | 263.67 | 263.67 | Slab work is completed |
| 6 | 2nd Floor (Resi.) | 300.73 | 300.73 | Slab work is completed |
| 7 | 3rd Floor | 470.99 | 470.99 | Slab work is completed |
| 8 | 4th Floor | 470.99 |  |  |
| 9 | 5th Floor | 470.99 |  |  |
| 10 | 6th Floor | 470.99 |  |  |
| 11 | 7th Floor | 470.99 |  |  |
| 12 | 8th Floor | 470.99 |  |  |
| 13 | 9th Floor | 470.99 |  |  |
| 14 | 10th Floor | 470.99 |  |  |
| 15 | 11th Floor | 470.99 |  |  |
| 16 | 12th Floor | 470.99 |  |  |
| 17 | 13th Floor | 395.56 |  |  |
| 18 | 14th Floor | 470.99 |  |  |
| 19 | 15th Floor | 470.99 |  |  |
| 20 | 16th Floor | 470.99 |  |  |
| 21 | 17th Floor | 470.99 |  |  |
| 22 | 18th Floor | 395.56 |  |  |
| 23 | 19th Floor | 470.99 |  |  |
| 24 | 20th Floor | 470.99 |  |  |
| 25 | 21st Floor | 470.99 |  |  |
| 26 | 22nd Floor | 470.99 |  |  |
| 27 | 23rd Floor | 470.99 |  |  |
| TOTAL |  | 12,494.76 | 1,207.34 |  |

# Sale Building (Wing A4)

| Sr. No. | Floor | Construction Area in Sq. M. | Completed Area in Sq. M. | Work Completed As on 12.10.2022 |
| --- | --- | --- | --- | --- |
| 1 | Excavation Work | - |  | Excavation work is completed |
| 2 | Stilt Floor | 229.97 | 229.97 | Slab work is completed |
| 3 | 1st Floor (Podium) | 1,009.24 | - |  |
| 4 | 2nd Floor (Podium) | 1,009.24 | - |  |
| 5 | 1st Floor (Resi.) | 322.82 | 322.82 | Slab work is completed |
| 6 | 2nd Floor (Resi.) | 377.21 | 377.21 | Slab work is completed |
| 7 | 3rd Floor | 595.81 | 595.81 | Slab work is completed |
| 8 | 4th Floor | 595.81 | 595.81 | Slab work is completed |
| 9 | 5th Floor | 595.81 |  |  |
| 10 | 6th Floor | 595.81 |  |  |
| 11 | 7th Floor | 595.81 |  |  |
| 12 | 8th Floor | 595.81 |  |  |
| 13 | 9th Floor | 595.81 |  |  |
| 14 | 10th Floor | 595.81 |  |  |
| 15 | 11th Floor | 595.81 |  |  |
| 16 | 12th Floor | 595.81 |  |  |
| 17 | 13th Floor | 595.81 |  |  |
| 18 | 14th Floor | 595.81 |  |  |
| 19 | 15th Floor | 595.81 |  |  |
| 20 | 16th Floor | 595.81 |  |  |
| 21 | 17th Floor | 595.81 |  |  |
| 22 | 18th Floor | 595.81 |  |  |
| 23 | 19th Floor | 595.81 |  |  |
| 24 | 20th Floor | 595.81 |  |  |
| 25 | 21st Floor | 595.81 |  |  |
| 26 | 22nd Floor | 595.81 |  |  |
| 27 | 23rd Floor | 595.81 |  |  |
| TOTAL |  | 15,460.49 | 2,121.62 |  |

# Sale Building (Wing C1)

| Sr. No. | Floor | Construction Area in Sq. M. | Completed Area in Sq. M. | Work Completed As on 12.10.2022 |
| --- | --- | --- | --- | --- |
| 1 | Excavation Work | - |  | Excavation work is completed |
| 2 | Stilt Floor | 142.78 |  |  |
| 3 | 1st Floor (Podium) | 1,009.24 |  |  |
| 4 | 2nd Floor (Podium) | 1,009.24 |  |  |
| 5 | 1st Floor (Resi.) | 241.37 |  |  |
| 6 | 2nd Floor (Resi.) | 284.96 |  |  |
| 7 | 3rd Floor | 288.79 |  |  |
| 8 | 4th Floor | 284.96 |  |  |
| 9 | 5th Floor | 288.79 |  |  |
| 10 | 6th Floor | 284.96 |  |  |
| 11 | 7th Floor | 288.79 |  |  |
| 12 | 8th Floor | 284.96 |  |  |
| 13 | 9th Floor | 288.79 |  |  |
| 14 | 10th Floor | 284.96 |  |  |
| 15 | 11th Floor | 288.79 |  |  |
| 16 | 12th Floor | 284.96 |  |  |
| 17 | 13th Floor | 288.79 |  |  |
| 18 | 14th Floor | 284.96 |  |  |
| 19 | 15th Floor | 288.79 |  |  |
| 20 | 16th Floor | 284.96 |  |  |
| 21 | 17th Floor | 288.79 |  |  |
| 22 | 18th Floor | 276.17 |  |  |
| 23 | 19th Floor | 288.79 |  |  |
| 24 | 20th Floor | 284.96 |  |  |
| 25 | 21st Floor | 288.79 |  |  |
| 26 | 22nd Floor | 284.96 |  |  |
| 27 | 23rd Floor | 288.79 |  |  |
| TOTAL |  | 8,705.09 | - |  |

# Details of the Project:

# Project Cost: (as per C.A. Certificate – M/s. M. S. Bajaj & Co. dated 14.06.2023)

| Particulars | Incurred Cost in Cr. till 31.12.2022 issued by M/s. M. S. Bajaj & Co. | Incurred Cost in Cr. till 30.09.2022 issued by M/s. M. S. Bajaj & Co. | Net |
| --- | --- | --- | --- |
| Land Cost & Brokeage | 13.99 | 13.99 | - |
| Approval Cost | 3.45 | 3.28 | 0.17 |
| Construction cost | 35.84 | 34.60 | 1.24 |
| On- site expenditure for development / Professional / Advance for Project/ Administrative Cost/ Fixed Assets | 8.40 | 8.18 | 0.22 |
| Marketing and brokerage | 19.91 | 19.82 | 0.09 |
| Interest Cost | 13.42 | 11.48 | 1.94 |
| TOTAL | 95.01 | 91.35 | 3.66 |

# Project Cost: (as per Bills):

| Particulars | Incurred Cost (in ` Cr.) |  |  |
| --- | --- | --- | --- |
|  | 31.12.2022 as per Bill (Inclusive GST) | 30.09.2022 as per Bill (Inclusive GST) | Net |
| Land Cost & Brokeage | 13.99 | 13.99 | - |
| Approval Cost | 3.45 | 3.28 | 0.17 |
| Construction cost | 41.44 | 40.34 | 1.10 |
| On- site expenditure for development / Professional / Advance for Project/ Administrative Cost/ Fixed Assets | 12.89 | 12.54 | 0.36 |
| Marketing and brokerage | 19.85 | 19.82 | 0.03 |
| Interest Cost | 13.12 | 11.18 | 1.94 |
| Total | 104.74 | 101.14 | 3.60 |

# Land Cost

| Particulars | Cost in Cr. (`) |
| --- | --- |
| The Ravalgaon Sugar farm Limited and SDR | 15.75 |
| Brokerage to Land parcel | 0.95 |
| Deshpande and other Families | 8.41 |
| Acquisition Cost of Land | 25.11 |
| Cost towards Clearance of Land | 13.62 |
| Total Land Cost payments | 38.73 |
| Proportionate Land Cost for 5 buildings | 13.99 |

- As per information provided by the client

# Approval Cost

| Sr No | Description | Area | Rate | % | Total |
| --- | --- | --- | --- | --- | --- |
| 1 | DEVELOPMENT CHARGES |  |  |  |  |
| a | Development Charges on Land | 70,120 | 3,590 | 0.50% | 12,58,654 |
| b | Development Charges on Residential Built-up |  |  |  |  |
| b1 | Residential Built-up - Phase I | 1,41,259 | 3,590 | 2.00% | 1,01,42,416 |
| b2 | Residential Built-up - Phase II | 1,12,024 | 3,590 | 2.00% | 80,43,305 |
| b3 | Residential Built-up - Phase III | - | 3,590 | 2.00% | - |
|  | Total of Development Charges |  |  |  | 1,94,44,375 |
| 2 | TDR AND PREMIUM PAYMENTS |  |  |  |  |
| a | Ancillary FSI - Phase I | 56,989 | 3,590 | 10% | 2,04,58,935 |
|  | Ancillary FSI - Phase II | 37,992 | 3,590 | 10% | 1,36,39,290 |
| b | Premium FSI - Phase II | 30,510 | 3,590 | 35% | 3,83,35,815 |
| c | TDR | 45,309 | 3,590 | 50% | 8,13,29,756 |
|  | TDR | 7,354 | 3,590 | 50% | 1,32,00,023 |
|  | Total of Ancillary FSI and Premium FSI |  |  |  | 16,69,63,821 |
| 3 | FEES |  |  |  |  |
| a | Scrutiny fees - Built-up area - Phase I | 1,41,259 | 4 |  | 5,65,037 |
|  | Scrutiny fees - Built-up area - Phase II | 1,12,024 | 4 |  | 4,48,095 |
| b | Tree Plantation (Rs 5,000 per 25 units) - Phase I | 2,754 | 200 |  | 5,50,800 |
|  | Tree Plantation (Rs 5,000 per 25 units) - Phase II | 571 | 200 |  | 1,14,200 |
| c | Drainage Connection (Rs 2000 per unit) - Phase I - NA | - | 2,000 |  | - |
|  | Drainage Connection (Rs 2000 per unit) - Phase II - NA | - | 2,000 |  | - |
| d | Stacking charges - Phase I | 1,41,259 | 10 |  | 14,12,593 |
|  | Stacking charges - Phase II | 1,12,024 | 10 |  | 11,20,237 |
| e | Compound Wall | 1 | 100 |  | 100 |
|  | Total of other Fees |  |  |  | 42,11,062 |
| 4 | LABOUR CESS |  |  |  |  |
|  | Labour Cess - Built-up area - Phase I | 2,94,559 | 21,296 | 1.00% | 6,27,29,344 |
|  | Labour Cess - Built-up area - Phase II | 90,024 | 21,296 | 1.00% | 1,91,71,456 |
|  | Total of Labour Cess |  |  |  | 8,19,00,800 |
|  | Add Past Approvals cost paid for PMAY |  |  |  | 96,83,530 |
|  | Grand Total of Approval Cost |  |  |  | 28,22,03,588 |
|  | Proportionate Estimate Approval Cost for 5 Buildings |  |  |  | 8,02,26,125 |
|  | Incurred Cost for Approval Cost of 5 Building in Cr. |  |  |  | 3.45 Cr. |

- As per information provided by the client

# Estimated Cost of Construction as on 31st December 2022:

| Sr. No. | Floor | Construction Area in Sq. M. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Wing A1 | Wing A2 | Wing A3 | Wing A4 | Wing C1 | Total |
| 1 | Stilt Floor | 171.95 | 171.95 | 171.95 | 229.97 | 142.78 | 888.60 |
| 2 | 1st Floor (Podium) | 1,009.24 | 1,009.24 | 1,009.24 | 1,009.24 | 1,009.24 | 5,046.20 |
| 3 | 2nd Floor (Podium) | 1,009.24 | 1,009.24 | 1,009.24 | 1,009.24 | 1,009.24 | 5,046.20 |
| 4 | 1st Floor (Resi.) | 263.67 | 263.67 | 263.67 | 322.82 | 241.37 | 1,355.20 |
| 5 | 2nd Floor (Resi.) | 300.73 | 300.73 | 300.73 | 377.21 | 284.96 | 1,564.36 |
| 6 | 3rd Floor | 470.99 | 470.99 | 470.99 | 595.81 | 288.79 | 2,297.57 |
| 7 | 4th Floor | 470.99 | 470.99 | 470.99 | 595.81 | 284.96 | 2,293.74 |
| 8 | 5th Floor | 470.99 | 470.99 | 470.99 | 595.81 | 288.79 | 2,297.57 |
| 9 | 6th Floor | 470.99 | 470.99 | 470.99 | 595.81 | 284.96 | 2,293.74 |
| 10 | 7th Floor | 470.99 | 470.99 | 470.99 | 595.81 | 288.79 | 2,297.57 |
| 11 | 8th Floor | 470.99 | 470.99 | 470.99 | 595.81 | 284.96 | 2,293.74 |
| 12 | 9th Floor | 470.99 | 470.99 | 470.99 | 595.81 | 288.79 | 2,297.57 |
| 13 | 10th Floor | 470.99 | 470.99 | 470.99 | 595.81 | 284.96 | 2,293.74 |
| 14 | 11th Floor | 470.99 | 470.99 | 470.99 | 595.81 | 288.79 | 2,297.57 |
| 15 | 12th Floor | 470.99 | 470.99 | 470.99 | 595.81 | 284.96 | 2,293.74 |
| 16 | 13th Floor | 395.56 | 395.56 | 395.56 | 595.81 | 288.79 | 2,071.28 |
| 17 | 14th Floor | 470.99 | 470.99 | 470.99 | 595.81 | 284.96 | 2,293.74 |
| 18 | 15th Floor | 470.99 | 470.99 | 470.99 | 595.81 | 288.79 | 2,297.57 |
| 19 | 16th Floor | 470.99 | 470.99 | 470.99 | 595.81 | 284.96 | 2,293.74 |
| 20 | 17th Floor | 470.99 | 470.99 | 470.99 | 595.81 | 288.79 | 2,297.57 |
| 21 | 18th Floor | 395.56 | 395.56 | 395.56 | 595.81 | 276.17 | 2,058.66 |
| 22 | 19th Floor | 470.99 | 470.99 | 470.99 | 595.81 | 288.79 | 2,297.57 |
| 23 | 20th Floor | 470.99 | 470.99 | 470.99 | 595.81 | 284.96 | 2,293.74 |
| 24 | 21st Floor | 470.99 | 470.99 | 470.99 | 595.81 | 288.79 | 2,297.57 |
| 25 | 22nd Floor | 470.99 | 470.99 | 470.99 | 595.81 | 284.96 | 2,293.74 |
| 26 | 23rd Floor | 470.99 | 470.99 | 470.99 | 595.81 | 288.79 | 2,297.57 |
| TOTAL |  | 12,494.76 | 12,494.76 | 12,494.76 | 15,460.49 | 8,705.09 | 61,649.86 |

# Sale Building (Wing A1)

| Plinth Area Calculation of Wing A1 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sr. No. | Floor | Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value After Completion | Percentage work completed | Actual Expenditure till date in ` |
| 1 | Excavation Work | - |  |  | 2,49,89,520.00 | 100% | 2,49,89,520.00 |
| 2 | Stilt Floor | 171.95 | 171.95 | 20,000.00 | 34,39,000.00 | 40% | 13,75,600.00 |
| 3 | 1st Floor (Podium) | 1,009.24 |  | 20,000.00 | 2,01,84,800.00 | 0% | - |
| 4 | 2nd Floor (Podium) | 1,009.24 |  | 20,000.00 | 2,01,84,800.00 | 0% | - |
| 5 | 1st Floor (Resi.) | 263.67 | 263.67 | 20,000.00 | 52,73,400.00 | 40% | 21,09,360.00 |
| 6 | 2nd Floor (Resi.) | 300.73 |  | 20,000.00 | 60,14,600.00 | 0% | - |
| 7 | 3rd Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 8 | 4th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 9 | 5th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 10 | 6th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 11 | 7th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 12 | 8th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 13 | 9th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 14 | 10th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 15 | 11th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 16 | 12th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 17 | 13th Floor | 395.56 |  | 20,000.00 | 79,11,200.00 | 0% | - |
| 18 | 14th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 19 | 15th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 20 | 16th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 21 | 17th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 22 | 18th Floor | 395.56 |  | 20,000.00 | 79,11,200.00 | 0% | - |
| 23 | 19th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 24 | 20th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 25 | 21st Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 26 | 22nd Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 27 | 23rd Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| TOTAL |  | 12,494.76 | 435.62 |  | 27,48,84,720.00 | 10% | 2,84,74,480.00 |

# Sale Building (Wing A2)

| Plinth Area Calculation of Wing A2 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sr. No. | Floor | Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value After Completion | Percentage work completed | Actual Expenditure till date in ` |
| 1 | Excavation Work | - |  |  | 2,49,89,520.00 | 100% | 2,49,89,520.00 |
| 2 | Stilt Floor | 171.95 | 171.95 | 20,000.00 | 34,39,000.00 | 40% | 13,75,600.00 |
| 3 | 1st Floor (Podium) | 1,009.24 | - | 20,000.00 | 2,01,84,800.00 | 0% | - |
| 4 | 2nd Floor (Podium) | 1,009.24 | - | 20,000.00 | 2,01,84,800.00 | 0% | - |
| 5 | 1st Floor (Resi.) | 263.67 | 263.67 | 20,000.00 | 52,73,400.00 | 40% | 21,09,360.00 |
| 6 | 2nd Floor (Resi.) | 300.73 | - | 20,000.00 | 60,14,600.00 | 0% | - |
| 7 | 3rd Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 8 | 4th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 9 | 5th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 10 | 6th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 11 | 7th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 12 | 8th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 13 | 9th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 14 | 10th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 15 | 11th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 16 | 12th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 17 | 13th Floor | 395.56 |  | 20,000.00 | 79,11,200.00 | 0% | - |
| 18 | 14th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 19 | 15th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 20 | 16th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 21 | 17th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 22 | 18th Floor | 395.56 |  | 20,000.00 | 79,11,200.00 | 0% | - |
| 23 | 19th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 24 | 20th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 25 | 21st Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 26 | 22nd Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 27 | 23rd Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| TOTAL |  | 12,494.76 | 435.62 |  | 27,48,84,720.00 | 10% | 2,84,74,480.00 |

# Sale Building (Wing A3)

| Plinth Area Calculation of Wing A3 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sr. No. | Floor | Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value After Completion | Percentage work completed | Actual Expenditure till date in ` |
| 1 | Excavation Work | - |  |  | 2,49,89,520.00 | 100% | 2,49,89,520.00 |
| 2 | Stilt Floor | 171.95 | 171.95 | 20,000.00 | 34,39,000.00 | 50% | 17,19,500.00 |
| 3 | 1st Floor (Podium) | 1,009.24 | - | 20,000.00 | 2,01,84,800.00 | 0% | - |
| 4 | 2nd Floor (Podium) | 1,009.24 | - | 20,000.00 | 2,01,84,800.00 | 0% | - |
| 5 | 1st Floor (Resi.) | 263.67 | 263.67 | 20,000.00 | 52,73,400.00 | 40% | 21,09,360.00 |
| 6 | 2nd Floor (Resi.) | 300.73 | 300.73 | 20,000.00 | 60,14,600.00 | 40% | 24,05,840.00 |
| 7 | 3rd Floor | 470.99 | 470.99 | 20,000.00 | 94,19,800.00 | 40% | 37,67,920.00 |
| 8 | 4th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 9 | 5th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 10 | 6th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 11 | 7th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 12 | 8th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 13 | 9th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 14 | 10th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 15 | 11th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 16 | 12th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 17 | 13th Floor | 395.56 |  | 20,000.00 | 79,11,200.00 | 0% | - |
| 18 | 14th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 19 | 15th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 20 | 16th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 21 | 17th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 22 | 18th Floor | 395.56 |  | 20,000.00 | 79,11,200.00 | 0% | - |
| 23 | 19th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 24 | 20th Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 25 | 21st Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 26 | 22nd Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| 27 | 23rd Floor | 470.99 |  | 20,000.00 | 94,19,800.00 | 0% | - |
| TOTAL |  | 12,494.76 | 1,207.34 |  | 27,48,84,720.00 | 13% | 3,49,92,140.00 |

# Sale Building (Wing A4)

| Plinth Area Calculation of Wing A4 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sr. No. | Floor | Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value After Completion | Percentage work completed | Actual Expenditure till date in ` |
| 1 | Excavation Work | - |  |  | 3,09,20,980.00 | 100% | 3,09,20,980.00 |
| 2 | Stilt Floor | 229.97 | 229.97 | 20,000.00 | 45,99,400.00 | 50% | 22,99,700.00 |
| 3 | 1st Floor (Podium) | 1,009.24 | - | 20,000.00 | 2,01,84,800.00 | 0% | - |
| 4 | 2nd Floor (Podium) | 1,009.24 | - | 20,000.00 | 2,01,84,800.00 | 0% | - |
| 5 | 1st Floor (Resi.) | 322.82 | 322.82 | 20,000.00 | 64,56,400.00 | 40% | 25,82,560.00 |
| 6 | 2nd Floor (Resi.) | 377.21 | 377.21 | 20,000.00 | 75,44,200.00 | 40% | 30,17,680.00 |
| 7 | 3rd Floor | 595.81 | 595.81 | 20,000.00 | 1,19,16,200.00 | 40% | 47,66,480.00 |
| 8 | 4th Floor | 595.81 | 595.81 | 20,000.00 | 1,19,16,200.00 | 40% | 47,66,480.00 |
| 9 | 5th Floor | 595.81 |  | 20,000.00 | 1,19,16,200.00 | 0% | - |
| 10 | 6th Floor | 595.81 |  | 20,000.00 | 1,19,16,200.00 | 0% | - |
| 11 | 7th Floor | 595.81 |  | 20,000.00 | 1,19,16,200.00 | 0% | - |
| 12 | 8th Floor | 595.81 |  | 20,000.00 | 1,19,16,200.00 | 0% | - |
| 13 | 9th Floor | 595.81 |  | 20,000.00 | 1,19,16,200.00 | 0% | - |
| 14 | 10th Floor | 595.81 |  | 20,000.00 | 1,19,16,200.00 | 0% | - |
| 15 | 11th Floor | 595.81 |  | 20,000.00 | 1,19,16,200.00 | 0% | - |
| 16 | 12th Floor | 595.81 |  | 20,000.00 | 1,19,16,200.00 | 0% | - |
| 17 | 13th Floor | 595.81 |  | 20,000.00 | 1,19,16,200.00 | 0% | - |
| 18 | 14th Floor | 595.81 |  | 20,000.00 | 1,19,16,200.00 | 0% | - |
| 19 | 15th Floor | 595.81 |  | 20,000.00 | 1,19,16,200.00 | 0% | - |
| 20 | 16th Floor | 595.81 |  | 20,000.00 | 1,19,16,200.00 | 0% | - |
| 21 | 17th Floor | 595.81 |  | 20,000.00 | 1,19,16,200.00 | 0% | - |
| 22 | 18th Floor | 595.81 |  | 20,000.00 | 1,19,16,200.00 | 0% | - |
| 23 | 19th Floor | 595.81 |  | 20,000.00 | 1,19,16,200.00 | 0% | - |
| 24 | 20th Floor | 595.81 |  | 20,000.00 | 1,19,16,200.00 | 0% | - |
| 25 | 21st Floor | 595.81 |  | 20,000.00 | 1,19,16,200.00 | 0% | - |
| 26 | 22nd Floor | 595.81 |  | 20,000.00 | 1,19,16,200.00 | 0% | - |
| 27 | 23rd Floor | 595.81 |  | 20,000.00 | 1,19,16,200.00 | 0% | - |
| TOTAL |  | 15,460.49 | 2,121.62 |  | 34,01,30,780.00 | 14% | 4,83,53,880.00 |

# Sale Building (Wing C1)

| Plinth Area Calculation of Wing C1 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sr. No. | Floor | Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value After Completion | Percentage work completed | Actual Expenditure till date in ` |
| 1 | Excavation Work | - |  |  | 1,74,10,180.00 | 100% | 1,74,10,180.00 |
| 2 | Stilt Floor | 142.78 |  | 20,000.00 | 28,55,600.00 | 0% | - |
| 3 | 1st Floor (Podium) | 1,009.24 |  | 20,000.00 | 2,01,84,800.00 | 0% | - |
| 4 | 2nd Floor (Podium) | 1,009.24 |  | 20,000.00 | 2,01,84,800.00 | 0% | - |
| 5 | 1st Floor (Resi.) | 241.37 |  | 20,000.00 | 48,27,400.00 | 0% | - |
| 6 | 2nd Floor (Resi.) | 284.96 |  | 20,000.00 | 56,99,200.00 | 0% | - |
| 7 | 3rd Floor | 288.79 |  | 20,000.00 | 57,75,800.00 | 0% | - |
| 8 | 4th Floor | 284.96 |  | 20,000.00 | 56,99,200.00 | 0% | - |
| 9 | 5th Floor | 288.79 |  | 20,000.00 | 57,75,800.00 | 0% | - |
| 10 | 6th Floor | 284.96 |  | 20,000.00 | 56,99,200.00 | 0% | - |
| 11 | 7th Floor | 288.79 |  | 20,000.00 | 57,75,800.00 | 0% | - |
| 12 | 8th Floor | 284.96 |  | 20,000.00 | 56,99,200.00 | 0% | - |
| 13 | 9th Floor | 288.79 |  | 20,000.00 | 57,75,800.00 | 0% | - |
| 14 | 10th Floor | 284.96 |  | 20,000.00 | 56,99,200.00 | 0% | - |
| 15 | 11th Floor | 288.79 |  | 20,000.00 | 57,75,800.00 | 0% | - |
| 16 | 12th Floor | 284.96 |  | 20,000.00 | 56,99,200.00 | 0% | - |
| 17 | 13th Floor | 288.79 |  | 20,000.00 | 57,75,800.00 | 0% | - |
| 18 | 14th Floor | 284.96 |  | 20,000.00 | 56,99,200.00 | 0% | - |
| 19 | 15th Floor | 288.79 |  | 20,000.00 | 57,75,800.00 | 0% | - |
| 20 | 16th Floor | 284.96 |  | 20,000.00 | 56,99,200.00 | 0% | - |
| 21 | 17th Floor | 288.79 |  | 20,000.00 | 57,75,800.00 | 0% | - |
| 22 | 18th Floor | 276.17 |  | 20,000.00 | 55,23,400.00 | 0% | - |
| 23 | 19th Floor | 288.79 |  | 20,000.00 | 57,75,800.00 | 0% | - |
| 24 | 20th Floor | 284.96 |  | 20,000.00 | 56,99,200.00 | 0% | - |
| 25 | 21st Floor | 288.79 |  | 20,000.00 | 57,75,800.00 | 0% | - |
| 26 | 22nd Floor | 284.96 |  | 20,000.00 | 56,99,200.00 | 0% | - |
| 27 | 23rd Floor | 288.79 |  | 20,000.00 | 57,75,800.00 | 0% | - |
| TOTAL |  | 8,705.09 | - |  | 19,15,11,980.00 | 9% | 1,74,10,180.00 |

| Summary of Plinth Area Calculation of Sale Building |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sr. No. | Wing | Construction Area in Sq. M. | Completed Area in Sq. M. | Full Value After Completion | Percentage work completed | Actual Expenditure till date in ` |
| 1 | Wing A1 | 12,494.76 | 435.62 | 27,48,84,720.00 | 10% | 2,84,74,480.00 |
| 2 | Wing A2 | 12,494.76 | 435.62 | 27,48,84,720.00 | 10% | 2,84,74,480.00 |
| 3 | Wing A3 | 12,494.76 | 1,207.34 | 27,48,84,720.00 | 13% | 3,49,92,140.00 |
| 4 | Wing A4 | 15,460.49 | 2,121.62 | 34,01,30,780.00 | 14% | 4,83,53,880.00 |
| 5 | Wing C1 | 8,705.09 | - | 19,15,11,980.00 | 9% | 1,74,10,180.00 |
| TOTAL |  | 61,649.86 | 4,200.20 | 1,35,62,96,920.00 | 12% | 15,77,05,160.00 |

##### Note: Details of work completion stage is as per site visit dated 10.03.2023 but report is prepared as on 31st December 2022.

##### As per plinth area calculation 12.00% construction work is completed. Value for the same amounts to ` 15.77 Cr. However, company has incurred cost of  ` 41.44 Cr. Which is inclusive of Infrastructure & Site developemnts and cost on construction related materials on site.

| Particulars | Estimated Cost (In Cr.) | Incurred Cost (in Cr.) |  |  | Net of both Bills |
| --- | --- | --- | --- | --- | --- |
|  |  | Issued dated 14.06.2023 as per CA till 31.12.2022 | As per Bills upto 31.12.2022 | As per Bills upto 30.09.2022 |  |
| Land Cost & Brokeage | 13.99 | 13.99 | 13.99 | 13.99 | - |
| Approval Cost | 8.02 | 3.28 | 3.45 | 3.28 | 0.17 |
| Construction cost | 135.34 | 34.60 | 41.44 | 40.34 | 1.10 |
| On- site expenditure for development / Professional / Advance for Project/ Administrative Cost/ Fixed Assets | 16.24 | 8.18 | 12.89 | 12.54 | 0.36 |
| Marketing and brokerage | 25.53 | 19.82 | 19.85 | 19.82 | 0.03 |
| Interest Cost | 35.61 | 11.48 | 13.12 | 11.18 | 1.94 |
| Total | 234.73 | 91.35 | 104.74 | 101.14 | 3.60 |

Note:

- As there is variation of 9.73 Cr. between bills & CA certificate, the same  is balance payable amount to different vendors.

- As per plinth area calculation 12.00% construction work is completed. Value for the same amounts to ` 15.77 Cr. However, company has incurred cost of  ` 41.44 Cr. Which is inclusive of Infrastructure & Site developemnts and cost on construction related materials on site.

# Comparison of Cost incurred on dated 31.12.2022 & 30.09.2022

| Particulars | 30.09.2022 as per Bill | 31.03.2022 as per Bill | Difference in Cr. | % Weightage of Total Difference |
| --- | --- | --- | --- | --- |
| Land Cost & Brokeage | 13.99 | 13.99 | - | 0.00% |
| Approval Cost | 3.45 | 3.28 | 0.17 | 4.72% |
| Construction cost | 41.44 | 40.34 | 1.10 | 30.56% |
| On- site expenditure for development / Professional / Advance for Project/ Administrative Cost/ Fixed Assets | 12.89 | 12.54 | 0.36 | 10.00% |
| Marketing and brokerage | 19.85 | 19.82 | 0.03 | 0.83% |
| Interest Cost | 13.12 | 11.18 | 1.94 | 53.89% |
| Total | 104.74 | 101.14 | 3.60 | 100.00% |

# % of Fund Utilised till 31st December 2022

| Particulars | Estimated Project Cost (in Cr.) | Incurred cost as on 30.09.2022 | % of Incurred Cost | % of Estimated Project Cost |
| --- | --- | --- | --- | --- |
| Land Cost & Brokeage | 13.99 | 13.99 | 99.98% | 5.96% |
| Approval Cost | 8.02 | 3.45 | 43.01% | 1.47% |
| Construction cost | 135.34 | 41.44 | 30.62% | 17.65% |
| On- site expenditure for development / Professional / Advance for Project/ Administrative Cost/ Fixed Assets | 16.24 | 12.89 | 79.39% | 5.49% |
| Marketing and brokerage | 25.53 | 19.85 | 77.76% | 8.46% |
| Interest Cost | 35.61 | 13.12 | 36.85% | 5.59% |
| Total | 234.73 | 104.74 | 44.62% | 44.62% |

Based on above Calculation it is found that till date Project Incurred Cost is 44.62% of the Total Project Cost.

# Means of Finance:

| Sr. No. | Particulars | Exp. Cumulative (Cr.) |
| --- | --- | --- |
|  | Promoter Contribution / Unsecured Loan | 25.83 |
|  | Sales (Advance from customer) | 65.38 |
|  | Loan | 13.75 |
|  | Total | 104.96 |

The Details of the Means of Finance are provided by Client as on 31.12.2022.

# Mandatory Arrangements:

| Sr. No. | Particulars | Status |
| --- | --- | --- |
|  | Rainwater Harvesting | To be executed after RCC Structure |
|  | Firefighting System | To be executed after RCC Structure |
|  | Solid Waste Management | To be executed after RCC Structure |

# Quality of Construction:

| Sr. No. | Particulars | Status |
| --- | --- | --- |
|  | Soundness of Structures | Executing as per approved Structural Design |
|  | Look of Structures | Good |
|  | Quality of Material Used | Good |
|  | Safety Measures for Construction/labour | Taken Care by Contractor |

# Schedule V/s. Actual Progress:

# Sale Building (Wing A1)

| Activity | Date of Implementation | Date of Completion | Status |
| --- | --- | --- | --- |
| Land |  |  | Completed |
| Development of Land |  |  | Completed |
| Foundation Work |  |  | Completed |
| Ground Floor Slab | 10-Jun-22 | 05-Jul-22 | Completed |
| 1st Floor Podium Slab | 05 Jul '22 | 22 Jul '22 |  |
| 2nd Floor Podium Slab | 17 Aug '23 | 11 Sep '23 |  |
| 1st Floor Resi. Slab | 12 Sep '23 | 22 Sep '23 |  |
| 2nd Floor Resi. Slab | 23 Sep '23 | 03 Oct '23 |  |
| 3rd Floor Slab | 04 Oct '23 | 12 Oct '23 |  |
| 4th Floor Slab | 13 Oct '23 | 21 Oct '23 |  |
| 5th Floor Slab | 23 Oct '23 | 01 Nov '23 |  |
| 6th Floor Slab | 02 Nov '23 | 10 Nov '23 |  |
| 7th Floor Slab | 11 Nov '23 | 20 Nov '23 |  |
| 8th Floor Slab | 21 Nov '23 | 29 Nov '23 |  |
| 9th Floor Slab | 30 Nov '23 | 08 Dec '23 |  |
| 10th Floor Slab | 09 Dec '23 | 18 Dec '23 |  |
| 11th Floor Slab | 19 Dec '23 | 27 Dec '23 |  |
| 12th Floor Slab | 28 Dec '23 | 06 Jan '24 |  |
| 13th Floor Slab | 08 Jan '24 | 16 Jan '24 |  |
| 14th Floor Slab | 17 Jan '24 | 25 Jan '24 |  |
| 15th Floor Slab | 27 Jan '24 | 05 Feb '24 |  |
| 16th Floor Slab | 06 Feb '24 | 14 Feb '24 |  |
| 17th Floor Slab | 15 Feb '24 | 23 Feb '24 |  |
| 18th Floor Slab | 24 Feb '24 | 04 Mar '24 |  |
| 19th Floor Slab | 05 Mar '24 | 13 Mar '24 |  |
| 20th Floor Slab | 14 Mar '24 | 23 Mar '24 |  |
| 21st Floor Slab | 25 Mar '24 | 02 Apr '24 |  |
| 22nd Floor Slab |  |  |  |
| 23rd Floor Slab |  |  |  |
| Block work / Internal Plaster work | 04 Oct '23 | 07 Aug '24 |  |
| Terrace Parapet wall / Overhead water tank / Lift Machine room / compound wall / External Plaster work | 09 Nov '23 | 19 Aug '24 |  |
| Electric Work | 20 Jul '22 | 04 Jan '25 |  |
| Water Proofing | 16 Oct '23 | 12 Sep '24 |  |
| Plumbing Work | 10 Oct '23 | 03 Dec '24 |  |
| Tiling / Marble Flooring | 09 Nov '23 | 07 Oct '24 |  |
| Door Frames | 02 Dec '23 | 12 Sep '24 |  |
| Window Installation | 02 Dec '23 | 12 Sep '24 |  |
| Staircase Flooring | 22 Jun '24 | 07 Oct '24 |  |
| Staircase Railing | 22 Jun '24 | 07 Oct '24 |  |
| Refuge Area Flooring | 22 Jun '24 | 07 Oct '24 |  |
| Internal Painting | 12 Dec '23 | 01 Feb '25 |  |
| External Painting | 20 Aug '24 | 12 Oct '24 |  |
| Lift Work | 15 Nov '23 | 31 Oct '24 |  |
| Fire Fighting Installation | 24 Apr '24 | 01 Nov '24 |  |
| Stack Parking |  |  |  |
| CP Fitting & Sanitary Work | 05 Oct '24 | 03 Dec '24 |  |
| Final Finishing & Fitting | 03 Feb '25 | 08 Mar '25 |  |

# Sale Building (Wing A2)

| Activity | Date of Implementation | Date of Completion | Status |
| --- | --- | --- | --- |
| Land |  |  | Completed |
| Development of Land |  |  | Completed |
| Foundation Work |  |  | Completed |
| Ground Floor Slab | 01 Mar '22 | 30 Jun '22 | Completed |
| 1st Floor Podium Slab | 30 Jun '22 | 20 Jul '22 |  |
| 2nd Floor Podium Slab | 01 Oct '22 | 05 Nov '22 |  |
| 1st Floor Resi. Slab | 07 Nov '22 | 17 Nov '22 |  |
| 2nd Floor Resi. Slab | 18 Nov '22 | 29 Nov '22 |  |
| 3rd Floor Slab | 30 Nov '22 | 10 Dec '22 |  |
| 4th Floor Slab | 12 Dec '22 | 22 Dec '22 |  |
| 5th Floor Slab | 23 Dec '22 | 03 Jan '23 |  |
| 6th Floor Slab | 04 Jan '23 | 14 Jan '23 |  |
| 7th Floor Slab | 16 Jan '23 | 27 Jan '23 |  |
| 8th Floor Slab | 28 Jan '23 | 08 Feb '23 |  |
| 9th Floor Slab | 09 Feb '23 | 20 Feb '23 |  |
| 10th Floor Slab | 21 Feb '23 | 03 Mar '23 |  |
| 11th Floor Slab | 04 Mar '23 | 15 Mar '23 |  |
| 12th Floor Slab | 16 Mar '23 | 28 Mar '23 |  |
| 13th Floor Slab | 29 Mar '23 | 08 Apr '23 |  |
| 14th Floor Slab | 10 Apr '23 | 20 Apr '23 |  |
| 15th Floor Slab | 21 Apr '23 | 03 May '23 |  |
| 16th Floor Slab | 04 May '23 | 15 May '23 |  |
| 17th Floor Slab | 16 May '23 | 26 May '23 |  |
| 18th Floor Slab | 27 May '23 | 07 Jun '23 |  |
| 19th Floor Slab | 08 Jun '23 | 19 Jun '23 |  |
| 20th Floor Slab | 20 Jun '23 | 30 Jun '23 |  |
| 21st Floor Slab | 01 Jul '23 | 12 Jul '23 |  |
| 22nd Floor Slab |  |  |  |
| 23rd Floor Slab |  |  |  |
| Block work / Internal Plaster work | 30 Nov '22 | 04 Oct '23 |  |
| Terrace Parapet wall / Overhead water tank / Lift Machine room / compound wall / External Plaster work | 04 Jan '23 | 16 Oct '23 |  |
| Electric Work | 18 Jul '22 | 01 Mar '24 |  |
| Water Proofing | 12 Dec '22 | 09 Nov '23 |  |
| Plumbing Work | 06 Dec '22 | 30 Jan '24 |  |
| Tiling / Marble Flooring | 04 Jan '23 | 02 Dec '23 |  |
| Door Frames | 28 Jan '23 | 09 Nov '23 |  |
| Window Installation | 28 Jan '23 | 09 Nov '23 |  |
| Staircase Flooring | 17 Aug '23 | 02 Dec '23 |  |
| Staircase Railing | 17 Aug '23 | 02 Dec '23 |  |
| Refuge Area Flooring | 17 Aug '23 | 02 Dec '23 |  |
| Internal Painting | 07 Feb '23 | 30 Mar '24 |  |
| External Painting | 17 Oct '23 | 08 Dec '23 |  |
| Lift Work | 24 Feb '23 | 10 Feb '24 |  |
| Fire Fighting Installation | 03 Aug '23 | 12 Feb '24 |  |
| Stack Parking |  |  |  |
| CP Fitting & Sanitary Work | 01 Dec '23 | 30 Jan '24 |  |
| Final Finishing & Fitting | 01 Apr '24 | 06 May '24 |  |

# Sale Building (Wing A3)

| Activity | Date of Implementation | Date of Completion | Status |
| --- | --- | --- | --- |
| Land |  |  | Completed |
| Development of Land |  |  | Completed |
| Foundation Work |  |  | Completed |
| Ground Floor Slab |  |  | Slab work is completed |
| 1st Floor Podium Slab | 23 Feb '22 | 14 Jul '22 |  |
| 2nd Floor Podium Slab | 02 Aug '22 | 26 Aug '22 |  |
| 1st Floor Resi. Slab | 26 Aug '22 | 08 Sep '22 | Slab work is completed |
| 2nd Floor Resi. Slab | 08 Sep '22 | 20 Sep '22 | Slab work is completed |
| 3rd Floor Slab | 20 Sep '22 | 01 Oct '22 | Slab work is completed |
| 4th Floor Slab | 01 Oct '22 | 13 Oct '22 |  |
| 5th Floor Slab | 13 Oct '22 | 25 Oct '22 |  |
| 6th Floor Slab | 25 Oct '22 | 07 Nov '22 |  |
| 7th Floor Slab | 07 Nov '22 | 18 Nov '22 |  |
| 8th Floor Slab | 18 Nov '22 | 30 Nov '22 |  |
| 9th Floor Slab | 30 Nov '22 | 12 Dec '22 |  |
| 10th Floor Slab | 12 Dec '22 | 23 Dec '22 |  |
| 11th Floor Slab | 23 Dec '22 | 04 Jan '23 |  |
| 12th Floor Slab | 04 Jan '23 | 16 Jan '23 |  |
| 13th Floor Slab | 16 Jan '23 | 28 Jan '23 |  |
| 14th Floor Slab | 28 Jan '23 | 09 Feb '23 |  |
| 15th Floor Slab | 09 Feb '23 | 21 Feb '23 |  |
| 16th Floor Slab | 21 Feb '23 | 04 Mar '23 |  |
| 17th Floor Slab | 04 Mar '23 | 16 Mar '23 |  |
| 18th Floor Slab | 16 Mar '23 | 29 Mar '23 |  |
| 19th Floor Slab | 29 Mar '23 | 10 Apr '23 |  |
| 20th Floor Slab | 10 Apr '23 | 21 Apr '23 |  |
| 21st Floor Slab | 21 Apr '23 | 04 May '23 |  |
| 22nd Floor Slab |  |  |  |
| 23rd Floor Slab |  |  |  |
| Block work / Internal Plaster work | 20 Sep '22 | 04 Dec '23 |  |
| Terrace Parapet wall / Overhead water tank / Lift Machine room / compound wall / External Plaster work | 12 Nov '22 | 15 Dec '23 |  |
| Electric Work | 13 Jun '22 | 27 Dec '23 |  |
| Water Proofing | 07 Oct '22 | 09 Jan '24 |  |
| Plumbing Work | 01 Oct '22 | 25 Nov '23 |  |
| Tiling / Marble Flooring | 12 Nov '22 | 23 Aug '23 |  |
| Door Frames | 24 Nov '22 | 05 Sep '23 |  |
| Window Installation | 24 Nov '22 | 05 Sep '23 |  |
| Staircase Flooring | 14 Jun '23 | 28 Sep '23 |  |
| Staircase Railing | 14 Jun '23 | 28 Sep '23 |  |
| Refuge Area Flooring | 14 Jun '23 | 28 Sep '23 |  |
| Internal Painting | 03 Dec '22 | 25 Jan '24 |  |
| External Painting | 15 Dec '23 | 08 Feb '24 |  |
| Lift Work | 15 Dec '22 | 01 Dec '23 |  |
| Fire Fighting Installation | 25 May '23 | 02 Dec '23 |  |
| Stack Parking |  |  |  |
| CP Fitting & Sanitary Work | 26 Sep '23 | 25 Nov '23 |  |
| Final Finishing & Fitting | 08 Feb '24 | 14 Mar '24 |  |

# Sale Building (Wing A4)

| Activity | Date of Implementation | Date of Completion | Status |
| --- | --- | --- | --- |
| Land |  |  | Completed |
| Development of Land |  |  | Completed |
| Foundation Work |  |  | Completed |
| Ground Floor Slab |  |  | Slab work is completed |
| 1st Floor Podium Slab |  |  |  |
| 2nd Floor Podium Slab |  | 02 Jul '22 |  |
| 1st Floor Resi. Slab | 02 Jul '22 | 20 Jul '22 | Slab work is completed |
| 2nd Floor Resi. Slab | 20 Jul '22 | 06 Aug '22 | Slab work is completed |
| 3rd Floor Slab | 06 Aug '22 | 24 Aug '22 | Slab work is completed |
| 4th Floor Slab | 24 Aug '22 | 12 Sep '22 | Slab work is completed |
| 5th Floor Slab | 12 Sep '22 | 29 Sep '22 |  |
| 6th Floor Slab | 29 Sep '22 | 17 Oct '22 |  |
| 7th Floor Slab | 17 Oct '22 | 04 Nov '22 |  |
| 8th Floor Slab | 04 Nov '22 | 22 Nov '22 |  |
| 9th Floor Slab | 22 Nov '22 | 09 Dec '22 |  |
| 10th Floor Slab | 09 Dec '22 | 27 Dec '22 |  |
| 11th Floor Slab | 27 Dec '22 | 13 Jan '23 |  |
| 12th Floor Slab | 13 Jan '23 | 01 Feb '23 |  |
| 13th Floor Slab | 01 Feb '23 | 18 Feb '23 |  |
| 14th Floor Slab | 18 Feb '23 | 08 Mar '23 |  |
| 15th Floor Slab | 08 Mar '23 | 27 Mar '23 |  |
| 16th Floor Slab | 27 Mar '23 | 13 Apr '23 |  |
| 17th Floor Slab | 13 Apr '23 | 02 May '23 |  |
| 18th Floor Slab | 02 May '23 | 19 May '23 |  |
| 19th Floor Slab | 19 May '23 | 06 Jun '23 |  |
| 20th Floor Slab | 06 Jun '23 | 23 Jun '23 |  |
| 21st Floor Slab | 23 Jun '23 | 11 Jul '23 |  |
| 22nd Floor Slab |  |  |  |
| 23rd Floor Slab |  |  |  |
| Block work / Internal Plaster work | 24 Aug '22 | 14 Nov '23 |  |
| Terrace Parapet wall / Overhead water tank / Lift Machine room / compound wall / External Plaster work | 19 May '23 | 24 Jan '24 |  |
| Electric Work | 29 Jan '22 | 20 Jul '24 |  |
| Water Proofing | 23 Sep '22 | 19 Dec '23 |  |
| Plumbing Work | 17 Sep '22 | 19 Jun '24 |  |
| Tiling / Marble Flooring | 17 Oct '22 | 23 Apr '24 |  |
| Door Frames | 17 Jun '23 | 30 Mar '24 |  |
| Window Installation | 17 Jun '23 | 30 Mar '24 |  |
| Staircase Flooring | 06 Jan '24 | 23 Apr '24 |  |
| Staircase Railing | 06 Jan '24 | 23 Apr '24 |  |
| Refuge Area Flooring | 06 Jan '24 | 23 Apr '24 |  |
| Internal Painting | 27 Jun '23 | 17 Aug '24 |  |
| External Painting | 18 Mar '24 | 11 May '24 |  |
| Lift Work | 21 Feb '23 | 08 Feb '24 |  |
| Fire Fighting Installation | 01 Aug '23 | 10 Feb '24 |  |
| Stack Parking |  |  |  |
| CP Fitting & Sanitary Work | 20 Apr '24 | 19 Jun '24 |  |
| Final Finishing & Fitting | 17 Aug '24 | 23 Sep '24 |  |

# Sale Building (Wing C1)

| Activity | Date of Implementation | Date of Completion | Status |
| --- | --- | --- | --- |
| Land |  |  | Completed |
| Development of Land |  |  | Completed |
| Foundation Work | 02 Mar ‘23 | 18 Apr ‘23 | Excavation work is Completed |
| Ground Floor Slab | 19 Apr ‘23 | 11 Oct ‘23 |  |
| 1st Floor Podium Slab |  |  |  |
| 2nd Floor Podium Slab |  | 02 Jul '22 |  |
| 1st Floor Resi. Slab | 23 Sep ‘23 | 23 Oct ‘23 |  |
| 2nd Floor Resi. Slab | 24 Oct ‘23 | 16 Nov ‘23 |  |
| 3rd Floor Slab | 17 Nov ‘23 | 04 Dec ‘23 |  |
| 4th Floor Slab | 05 Dec ‘23 | 21 Dec ‘23 |  |
| 5th Floor Slab | 22 Dec ‘23 | 09 Jan ‘24 |  |
| 6th Floor Slab | 10 Jan ‘24 | 27 Jan ‘24 |  |
| 7th Floor Slab | 29 Jan ‘24 | 14 Feb ‘24 |  |
| 8th Floor Slab | 15 Feb ‘24 | 02 Mar ‘24 |  |
| 9th Floor Slab | 04 Mar ‘24 | 20 Mar ‘24 |  |
| 10th Floor Slab | 22 Mar ‘24 | 08 Apr ‘24 |  |
| 11th Floor Slab | 09 Apr ‘24 | 25 Apr '24 |  |
| 12th Floor Slab | 26 Apr '24 | 14 May '24 |  |
| 13th Floor Slab | 15 May '24 | 31 May '24 |  |
| 14th Floor Slab | 01 Jun '24 | 18 Jun '24 |  |
| 15th Floor Slab | 19 Jun '24 | 05 Jul '24 |  |
| 16th Floor Slab | 06 Jul '24 | 23 Jul '24 |  |
| 17th Floor Slab | 24 Jul '24 | 09 Aug '24 |  |
| 18th Floor Slab | 10 Aug '24 | 27 Aug '24 |  |
| 19th Floor Slab | 28 Aug '24 | 14 Sep '24 |  |
| 20th Floor Slab | 16 Sep '24 | 03 Oct '24 |  |
| 21st Floor Slab | 04 Oct '24 | 21 Oct '24 |  |
| 22nd Floor Slab | 22 Oct ‘24 | 08 Nov ‘24 |  |
| 23rd Floor Slab | 09 Nov ‘24 | 26 Nov ‘24 |  |
| Block work / Internal Plaster work | 10 Jan '25 | 17 May '25 |  |
| Terrace Parapet wall / Overhead water tank / Lift Machine room / compound wall / External Plaster work | 27 Nov ‘24 | 10 Jun '25 |  |
| Electric Work | 21 Oct '23 | 05 Dec '25 |  |
| Water Proofing | 09 Feb ‘24 | 06 May ‘25 |  |
| Plumbing Work | 03 Feb '24 | 04 Nov '25 |  |
| Tiling / Marble Flooring | 04 Mar ‘24 | 06 Sep ‘25 |  |
| Door Frames | 09 Feb ‘24 | 15 Nov ‘25 |  |
| Window Installation | 04 Nov ‘24 | 13 Aug ‘25 |  |
| Staircase Flooring | 06 Jan '24 | 23 Apr '24 |  |
| Staircase Railing | 06 Jan '24 | 23 Apr '24 |  |
| Refuge Area Flooring | 06 Jan '24 | 23 Apr '24 |  |
| Internal Painting | 13 Nov '24 | 02 Jan '26 |  |
| External Painting | 02 Aug '25 | 24 Sep ‘25 |  |
| Lift Work | 09 Jul '24 | 24 Jun ‘25 |  |
| Fire Fighting Installation | 18 Dec '24 | 26 Jun '25 |  |
| Stack Parking |  |  |  |
| CP Fitting & Sanitary Work | 03 Feb '24 | 04 Nov '25 |  |
| Final Finishing & Fitting | 03 Jan '26 | 06 Feb ‘26 |  |

# Action initiated to complete the project in time:

Status as on date:

For Sale Buildings:

- For A1 – wing: 1st floor Resi. slab work is completed

- For A2 – wing: 1st floor Resi. slab Work is completed

- For A3 – wing: 3rd floor Resi. slab work is completed

- For A4 – wing: 4th floor Resi. slab work is completed

- For A2 – wing: Excavation work is completed

Actionable:

Multiple construction activities need to be performed simultaneously for achieving the timely completion.

# Comments related to cost overrun if any:

The cost of Sales Building is ` 234.73 Cr. The cost incurred till date is ` 101.14 Cr. There is no cost overrun observed till date.

# Balance investment required for completion of project:

As per our opinion the amount of ` 133.59 Cr. will be required to complete the Project.

# Mandatory Approval Status:

| Sr. No. | Particulars | Name of Department | Status | Order Details |
| --- | --- | --- | --- | --- |
| 1 | N. A. Order | Collector of Thane | Obtained and available at site |  |
| 2 | Approved Plan | Collector of Thane | Obtained and available at site |  |
| 3 | C.C. | Collector of Thane | Obtained and available at site |  |
| 4 | Occupancy |  | Pending (Project is not completed) |  |

## Note:-

# Assumptions & Remarks:

- The adequacy of Engineering / Structural design is beyond the scope of our assignment.

- Estimated project completion date as per RERA Certificate is 30/09/2025.

- The cost is certified based on the assumptions that the project will be completed within stipulated period.

- Few assumptions were made considering expected inflation & cost rise etc. during construction period.

Manoj B. Chalikwar

Registered Valuer

Chartered Engineer (India)

Reg. No. IBBI/RV/07/2018/10366

About the Project:

| 1. Introduction |  |  |
| --- | --- | --- |
| a) | Project Name (With Address & Phone Nos.) | Poddar Riviera Phase - 1, Plot Bearing Survey No. 9, Hissa No. 1B, 2 & 3, Survey No. 10 and 11, Hissa No. 1 & 2 of Village – Mharal, Taluka – Kalyan, District – Thane, Pin Code – 421 103, State - Maharashtra, Country – India. Contact Person: Umesh Sawant - (Company staff - Mobile No. 91673 99723) |
| b) | Purpose of Valuation | As per request from STCI Finance Limited, Lower Parel Branch to assess fair market value of the Project for LIE purpose. |
| c) | Date of Inspection of Property | 10.03.2023 |
| d) | Date of LIE Report | 26.07.2023 |
| e) | Name of the Developer of Property (in case of developer built properties) | M/s. Poddar Housing and Development Ltd. Address: Unit No. 3-6, Neeru Silk Mill, Mathuradas Mill compound, 126, N. M. Joshi Marg, Lower Parel (West), Mumbai - 400 013, State - Maharashtra, Country - India |
| 2. Physical Characteristics of the Property |  |  |
| a) | Location of the Property | Poddar Riviera Phase - 1, Plot Bearing Survey No. 9, Hissa No. 1B, 2 & 3, Survey No. 10 and 11, Hissa No. 1 & 2 of Village – Mharal, Taluka – Kalyan, District – Thane, Pin Code – 421 103, State - Maharashtra, Country – India. |
|  | Brief description of the property |  |
|  | TYPE OF THE BUILDING - Sales Building (Wing A1, A2, A3, A4 & C1) No. of Floors; Stilt floor + 1st & 2nd Podium floor + 3rd to 23rd Residential Upper floors. Building type; Residential sale building. Sales Building work is given on contract based for labour contract. Developer has grant to the labour contractor do the work of construction and completion includes Concrete work, Reinforcement work, Masonry, Internal Plaster, External Plaster and other miscellaneous work such as repairing, joints b/w concrete and masonry surface, etc. Bill must be paid on measurement of construction area. All the material requires for construction are provided by the Developer. Lift & lift installation contract is not finalized till now. PROPOSED DATE OF COMPLETION & FUTURE LIFE: Expected completion date as per RERA is 30th September 2025. About Poddar Riviera Project: Poddar Riviera by Poddar Housing is one of the most sought-after new projects in Kalyan (West) for those who are looking for low-cost apartments. It is a new launch project. The possession will begin in June 2026. There are 1BHK and 2BHK apartments for sale, coming up in this project. Poddar Riviera is a RERA-registered project. Poddar Riviera Kalyan (West) has 19 towers, with 22 floors each and 1412 units on offer. Spread over an area of 18.8 acres, Poddar Riviera is one of the spacious projects in the Mumbai Beyond Thane region. With all the basic amenities available, Poddar Riviera fits into your budget and your lifestyle. It has a thoughtful design and is well equipped with all basic facilities. The project is well equipped with modern amenities and has excellent connectivity by public and private transport. There are restaurants and hotels close by to the project. It is well-connected to other parts of the city through road and rail public transports. The amenities available in the project include a modern gymnasium along with all the basic facilities to assist the daily requirements of the residents. The interiors of Poddar Riviera are designed using vitrified tile flooring, large sliding windows, designer doors and branded hardware fittings. |
|  | Postal Address of the Property | Poddar Riviera Phase - 1, Plot Bearing Survey No. 9, Hissa No. 1B, 2 & 3, Survey No. 10 and 11, Hissa No. 1 & 2 of Village – Mharal, Taluka – Kalyan, District – Thane, Pin Code – 421 103, State - Maharashtra, Country – India. |
|  | Area of the plot/land | Plot Area: 16,054.00 Sq. M. |
|  | Type of Land: Solid, Rocky, Marsh land, reclaimed land, Water-logged, Land locked. | Solid land |
|  | Independent access/approach to the property etc. | Yes |
|  | Google Map Location of the Property with a neighborhood layout map | Provided |
|  | Details of roads abutting the property | 20.00 Mt. wide Road |
|  | Description of adjoining property | Located in Middle-class locality |
|  | Plot No. Survey No. | Survey No. 9, Hissa No. 1B, 2 & 3, Survey No. 10 and 11, Hissa No. 1 & 2 |
|  | Ward/Village/Taluka | Village – Mharal, Taluka – Kalyan |
|  | Sub-Registry/Block | Kalyan |
|  | District | Thane |
| b) | Boundaries of the Plot |  |
|  | As per Agreement; As per RERA Certificate; Actual. North; Ulhas River; Survey No 10 Hissa No 1; Ulhas River. South; Kalyan-Murbad Road; Survey No 11 Hissa No 2; Bhiwandi - Murbad Road. East; Seema Resort; Boundary Of Village Varap; Konark Meadows. West; Property of Shri Panvelkar; S No 9 H No 1 Of B 2 3 And S No 11 H No 2; Open Plot. |

| 4. Document Details and Legal Aspects of Property: |  |
| --- | --- |
| a) | Ownership Documents (Building Permission, Commencement Certificate & Status of Plan) |
|  | Sale Deed, Gift Deed, Lease Deed |
|  | - Copy of Registered Conveyance Deed (Indenture) No. 7489/2016 dated 13.12.2016. |
|  | - Copy of Registered Conveyance Deed No. 7604/2016 dated 17.12.2016 between M/s. Ravalgaon Sugar Farms Ltd. and M/s. Poddar Housing and Development Ltd. |
|  | - Copy of Registered Deed of Rectification No. 1492/2018 dated 07.02.2018 between M/s. Ravalgaon Sugar Farms Ltd. and M/s. Poddar Housing and Development Ltd. |
|  | - Copy of Power of Attorney No. 7490/2016 dated 13.12.2016 |
|  | - Copy of 7/12 Extract. |
|  | - Copy of Mharal Collector order for construction consent dated 25.03.2022. |
|  | - Copy of Approved Layout Plan as per details below: |
|  | - Copy of RERA Certificate MAHRERA No. P51700023508 dated 08.09.2021 issued by Maharashtra Real Estate Regulatory Authority (MAHRERA) |
|  | - Copy of Bills |
|  | - Copy of CA Certificate dated 03.06.2022 issued by M/s. M.S. Bajaj & Co. |
|  | - Copy of Bills from 01.04.2022 to 30.09.2022 |
|  | - Copy of CA Certificate dated 28.10.2022 issued by M/s. M. S. Bajaj & Co. |

| b) | Documents verified for present LIE report |
| --- | --- |
|  | - Copy of Bills from 01.10.2022 to 31.12.2022 |
|  | - Copy of CA Certificate dated 14.06.2023 issued by M/s. M. S. Bajaj & Co. |

Actual Site Photographs

Wing – A1

Actual Site Photographs

Wing – A2

Actual Site Photographs

Wing – A3

Actual Site Photographs

Wing – A4

Actual Site Photographs

Wing – A4

Actual Site Photographs

Wing – C1

Actual Site Photographs

External Photos

Route Map of the property

Site u/r

## Latitude Longitude: 19°15'05.1"N 73°10'35.3"E

Note: The Blue line shows the route to site from nearest railway station (Shahad Station –3.0 KM.)

CA Certificate dated 14.06.2023 till 31.12.2022