Name of Owner: M/s. Mahi Terry Cot LLP

Plant Location: - Plot No. T-24, Additional Amravati Textile Park, MIDC Nandgaon Peth, Amravati, PIN Code-444 901, State- Maharashtra, County-India.

Report Prepared For

State Bank of India

Diamond Garden Chembur Branch

Unit No. 11, Ground Floor, Corporate Park, Sion -Trombay Road, Chembur,

Mumbai – 400 071, State – Maharashtra, Country – India

INDEX

| CHAPTER | NAME | PAGE NO. |
| --- | --- | --- |
| 1 | PREAMBLE | 03 |
| 2 | ASSIGNMENT OVERVIEW | 04 |
| 3 | ABOUT COMPANY & THE PROJECT | 09 |
| 4 | PROJECT EXECUTION | 33 |
| 5 | PHOTOGRAPHS | 63 |
| 6 | NOTES, LIMITATIONS, DISCLAIMERS & CAVEATS | 90 |
| 7 | SUMMARY | 92 |
| 8 | OPINION | 99 |

- PREAMBLE

State of India, SME Chembur Branch Unit No. 11, Building No. 11, Ground Floor, Corporate Park, Sion-Trombay Road, Chembur, Mumbai- 400 071 has appointed M/s Vastukala Consultants (I) Pvt. Ltd. (VCIPL) as Lender’s Independent Engineers vide letter Ref. No. SBI/SMEC/SME/ST/2023-24/207 dated 13.07.2023 for inspection and monitoring the progress of proposed 9.5 MTPD Terry Towel manufacturing facility of Rs. 4,811.82 Lakhs by M/s Mahi Teryy Cot LLP, (hereinafter referred to as either “MTC or “the borrower” or “the company”) on behalf of lenders. M/s Mahi Terry Cot LLP is the borrower and the project is financed by State Bank of India as per the table mentioned below: -

(Rs in Cr)

| S. No | Particular | Proposed |
| --- | --- | --- |
| 1 | Term Loan from State of India, SME Chembur Branch | 28.00 |
|  | Total | 28.00 |

Pursuant to instructions from Relationship Manager of State of India, SME Chembur Branch Unit No. 11, Building No. 11, Ground Floor, Corporate Park, Sion-Trombay Road, Chembur, Mumbai- 400 071, as appointment of Lender’s Independent Engineer, our Engineer visited 2nd time on 23.10.2023 at the project site 9.5 MTPD Terry Towel manufacturing facility at Plot No. T-24, Additional Amravati Textile Park, MIDC Nandgaon Peth, Amravati, PIN Code-444 901, State- Maharashtra, County-India with a view to ascertain and certify the quantity and amount of work progressively undertaken by the borrower.

- ASSIGNMENT OVERVIEW

#### 2.1 NATURE OF ASSIGNMENT

To review the status of the 9.5 MTPD Terry Towel manufacturing facility at Plot No. T-24, Additional Amravati Textile Park, MIDC Nandgaon Peth, Amravati, PIN Code-444 901, State- Maharashtra, County-India on behalf of State of India, SME Chembur Branch Unit No. 11, Building No. 11, Ground Floor, Corporate Park, Sion-Trombay Road, Chembur, Mumbai- 400 071 (Lender’s).

#### 2.2 SCOPE OF WORK: -

#### The scope of work is as per work order provided by the company is under: -

- Executive Summary, Brief Profile/ Basic information of the applicant Company.

- Periodic Progress Monitoring Report.

- Financial Progress.

- Project Cost, Means of Finance details and Expenses.

- Bank related details.

- Physical Progress.

- Site Visit.

- Present Physical Status of the Project.

- Land Acquisition

- Building & Civil Work

- Status of Plant & Machinery and Miscellaneous Fixed Assets.

- Verification of Invoice/ Purchase Orders received for Civil construction work.

- Details of Plant & Machinery Installed.

- Statutory Approvals for the Projects

- Monitoring of obtainment of the statutory approvals, clearances from appropriate authorities.

- Monitoring of the actuals with the timelines initially set for different stages of implementation for monitoring the time over run if any.

- Review of the production capacity (In Capacity terms and Volume) via-a-vis the original projections.

- Monitoring of the disbursement made viz-a-vis the original schedule and ensuring infusion of margins.

- Monitoring of the purchase of assets from the related parties/group companies and payments made thereof.

- Verification of the invoices and validation of the rates/commercial terms and conditions thereof vis-a-viz the original projections.

- Monitoring of the payments made to the suppliers, contractors, vendors etc.

- Monitoring changes in the external factors vis-a-viz the original estimates- government policies, policy changes.

- Monitoring of arrangement for continuous power and water supply, availability of labour.

- Environmental Clearances.

- Monitoring of logistics and infrastructure.

#### 2.3 DATE OF VISIT: -

- VCIPL’s Engineer has visited the project site 2nd time on 23.10.2023.

#### 2.4 DOCUMENTS PROVIDED FOR VALUATION: -

The following documents were perused during the said assignment:

- Letter for Appointment of Lenders Independent Engineer (LIE) issued by Relationship Manager, State Bank of India vide No. SBI/SMEC/SME/ST/2023-24/207 dated 13.07.2023.

- Layout Plan.

- Sanction for the allotment of land admeasuring 40000 Sq. M issued by Area Manager, MIDC, Amravati vide Letter No. MIDC/RO(AMR)/NAN/LMS-701/00143 dated 15.11.2017.

- Agreement dated 12.03.2018 made between Maharashtra Industrial Development Corporation (“Grantor”) and M/s. Mahi Terry Cot LLP (Licensees”) for the lease of Land admeasuring 40000 Sq. M.

- Pre-determined Lease dated 06.09.2022 made between Maharashtra Industrial Development Corporation (MIDC) (“the Lessor”) and M/s. Mahi Terry Cot LLP (“the Licensee”) for the lease of Land admeasuring 40000 Sq. M. for the period of 95 years computed from 01.12.2017.

- Punjab National Bank Statement of Account No. 3737002101015170 from 01.04.2022 to 22.09.2022

- Organization Chart.

- Audited Balance Sheet for the year ended at 31.03.2022.

- Marine Cargo Open Policy inland issued by Liberty General Insurance Limited valid till 08.03.2024.

- Erection All Risk Policy issued by Liberty General Insurance Limited valid till 24.04.2023.

- Arrangement Letter SME-1 for sanction of Credit facilities dated 09.09.2022 made between M/s. Mahi Terry Cot LLP and Relationship Manager, SBI, Diamon Garden Branch, Chembur, Mumbai-400 071 vide Letter No. SME/DGC/22-23/128.

- Pan Card of Mahi Terry Cot LLP.

- Project report.

- Annexure-1 for Project Report.

- Implementation schedule.

- Certificate of Importer-Exporter issued by Directorate General of Foreign Trade, Ministry of Commerce and Industry, Government of India dated 24.04.2017.

- GST registration certificate issued by Government of India dated 01.07.2017.

- Certificate of Incorporation issued by Registrar, Mumbai, Ministry of Corporate Affairs, Government of India dated 21.06.2016.

- Yes Bank Statement of Account No. 007863700002690 from 01.05.2022 to 30.09.2022.

- Udyam Registration Certificate dated 06.12.2021.

- Sanction Letter for Temporary IP connection having load 90 KW in r/o. M/s. Mahi Terry Cot LLP under Amravati Rural Sub Division under DDF 1.3% Scheme issued Executive Engineer, CCO & M Rural division, Amravati vide No. EE/Amt./T/0961 dated 18.02.2022.

- Sanction of 80.00 mm dia water Connection issued by Deputy Engineer, Sub Div Amaravati (E&M), Maharashtra Industrial Development Corporation vide No. MIDC/IFMS/AMR/E&MD/SDAMRVTE&M/2022/A42678 dated 10.02.2022.

- Application for Consent to Operate vide UAN No. MPCB-CONSENT-0000170771 dated 13.05.2023.

- The agreement of Limited Liability Partnership dated 22.06.2016 made between 
Mr. Sorabh Agarwal and Mrs. Ruchika Agarwal and Master Aditya Agarwal.

- Sanctioning of New contract demand 1150 KVA and connected load 920 KW issued Superintending Engineer, O&M Circle, M.S.E.D.C. Ltd., Amravati vide No. SE/O&M/Amt/Tech/No. 00518 dated 24.01.2023.

- Estimation for giving Power supply to 1 No. New HT connection for contract demand 1150 KVA & connected load 920 KW issued Superintending Engineer, O&M Circle, Amravati vide No. SE/O&M/Amt/Tech/Estt/DDF1.2%/519 dated 24.01.2023.

- Land Possession receipt issued by Surveyor, MIDC, Amravati dated 14.12.2017.

- Consent to Establish issued by Member Secretary, Maharashtra Pollution Control Board vide Consent No. Format 1.0/BO/CAC-Cell/CAC-UAN No. 37617/CAC1810000566 dated 12.10.2018.

- Layout Plan approved by Executive Engineer, MIDC Division, Amravati dated 15.02.2019.

- Letter for Building Plan Approval issued by Executive Engineer, (Special Planning Authority), MIDC Division, Amravati vide No. EE/DB/A63695/ of 2019 dated 15.02.2019.

- Email from MIDC for the Demand Note Revised Layout Plan approval dated 08.06.2023.

- Application for Registration of Boiler/Economiser.

- Current Account Statement of State Bank of India for A/c No. 00000038033132201 from 01.09.2022 to 30.06.2023.

- Term Loan Account Statement of State Bank of India for A/c No. 00000041264242092 from 01.10.2022 to 30.06.2023.

- Purchase Order/Work Order.

- Invoice Copies.

- Draw Down Schedule.

- C.A Certificate for the cost incurred till 30.06.2023 certified by M/s. V.B Goel & Co., Chartered Accountant dated 27.07.2023.

- Ledger for the Project till 23.10.2023.

- Electrical Load List.

- C.A Certificate for the cost incurred till 23.10.2023 certified by M/s. V.B Goel & Co., Chartered Accountant dated 31.10.2023.

- Letter for Discharge of treated Effluent to CETP for the trail production run issued by Regional Officer, MPC Board, Amravati dated 10.10.2023.

- Email dated 11.10.12023 by Executive Engineer, MIDC Div. Amravati for confirmation for discharge of treated Effluent.

- Application for Consent/ Authorization dated 13.05.2023.

- Provisional Order under section 9 of the Boilers Act of 1923 for the use of Boiler issued by Joint Director, Directorate of Stem Boilers dated 03.10.2023 valid till 27.01.2024.

- Layout Plan approved by Executive Engineer, MIDC Division, Amravati vide Letter No. I/17583/2023 dated 12.09.2023.

- Letter for Building Plan Approval issued by Executive Engineer, (Special Planning Authority), MIDC Division, Amravati vide No. I/17583/2023 dated 12.09.2023.

- Electricity Bill for the month of August-2023 & September-2023.

- Letter for Machinery Layout Approval issued by Joint Director, Industrial Safety and Health dated 05.10.2023.

- Standard Fire and Special Perils Policy issued By Bajaj Allianz General Insurance Company Limited valid till 22.10.2023.

- Manpower Details.

- Water Bill for the Month of September 2023.

#### 2.5 METHODOLOGY ADOPTED

- LIE visit to the project site 2nd time on 23.10.2023.

- Perusal of documents and information provided by the Company.

- Physical verification of the project site with the following executives of the Company: -

- Mr. Abhishek Srivastava, Project Head of MTC.

- Explanations and information given by the following executives of the Company,

- Mr. Abhishek Srivastava, Project Head of MTC.

- Mr. Girish Rathod, Executive-Accounts & Finance of MTC.

- Examinations of documents provided by the Company.

- Selective photographs of the project site are enclosed.

- Finalization of LIE Report.

- ABOUT COMPANY & THE PROJECT

#### 3.1. ABOUT COMPANY: -

M/s. Mahi Terry Cot LLP (“MTC” or ‘Company”) is a Limited Liability Partnership firm incorporated on 21st June 2016. It is registered at Registrar of Companies, Mumbai. Its total obligation of contribution is Rs. 100,000. Designated Partners of MTC are Shri Sorabh Kishan Agarwal and Smt. Ruchika Agarwal. MTC's LLP Identification Number is (LLPIN)AAG-7383. Its registered address is Office No. 116, 1st Floor, Ackruti Star, Central Road, MIDC Pkt 5, Near-Marol Telephone Exchange, Andheri-East Mumbai-400 093.

MTC proposes to set up Terry Towel manufacturing facility with dyeing, stitching, and packing at Plot No. T-24, Additional Amravati Textile Park, MIDC Nandgaon Peth, Amravati, PIN Code-444 901, State- Maharashtra, County-India. MTC had applied and has been allotted Leasehold Land admeasuring 40000 Sq. M. at Plot No. T-24, Addl Amaravati Textile Park, MIDC, Amravati, Maharashtra. This is an MIDC land where infrastructure is readily available as per Textile requirement.

M/s. Mahi Exports, a partnership firm, having common partners is already in the business of export of terry towel since 2008 and is a Government recognized star export house. At present Mahi Exports are sourcing terry towel from other manufacturers and also getting it done on job work from different manufacturer. Hence, they are setting up proposed terry towel manufacturing facility to have stability in supply of terry towel and reduce dependency on the external source.

Promoters

The present partners of the firm comprise of the following:

1. Shri Sorabh Agarwal:-

Shri Sorabh Agarwal aged 38 years is a Commerce Graduate. He is into the family business since the age of 20. In the year 2008 he came to Mumbai to start a new venture. He started with Mahi Exports. The said firm is engaged into the business of trading and export of Terry Towel. In a span of 10 years the firm has established itself in this market. The firm has achieved a turnover of Rs 34 Cr. in the year 2020-21.

2. Smt. Ruchika Agarwal

Smt. Ruchika Agarwal is also a commerce graduate from Rajasthan. She will be assisting 
Shri. Sorabh Agarwal in the accounts and administration.

3.2. ORGANISATION CHART: -

3.3) ABOUT THE PROJECT

MTC is proposes to set-up a terry towel manufacturing facility with a capacity of 9.5 ton per day at Plot No. T-24, Additional Amravati Textile Park, MIDC Nandgaon Peth, Amravati, PIN Code-444 901, State- Maharashtra, County-India. MIDC has allotted the Leasehold Land admeasuring 40,000.00 Sq. M at Plot No. T-24, Additional Amravati Textile Park, MIDC Nandgaon Peth, Amravati, PIN Code-444 901, State- Maharashtra, County-India. Total estimated project cost is Rs. 4,811.82 Lakhs as indicated in table provided below for ready reference.

| S. No | Particular of Project | Estimated Project Cost (Rs. in Lakhs) |
| --- | --- | --- |
| 1. | Land & Development | 0* |
| 2. | Buildings | 0** |
| 3. | Plant & Machinery | 3,995.90 |
| 4. | Miscellaneous Fixed Asset | 100.00 |
| 5. | Electrical Fittings | 112.10 |
| 6. | Contingencies | 210.40 |
| 7. | Preoperative Expenses | 393.42 |
|  | Total | 4,811.82 |

NOTE:-

- *The Company has already acquired a land of 40,000 m².

- ** The expenses for the civil work of the factory building will be borne by the company from its own sources.

- Cost of Land and Buildings are not considered in the project cost.

MEANS OF FINANCE

| S. No | Particular of Project | Estimated Project Cost (Rs. in Lakhs) |
| --- | --- | --- |
| 1. | Promoter Capital | 2,011.82 |
| 2. | Term Loan | 2,800.00 |
|  | Total | 4,811.82 |

OBSERVATIONS:-

- State Bank of India, SME, Dimond Garden Branch has sanctioned Term Load of Rs 28.00 Crores vide as per Arrangement Letter SME-1 for sanction of Credit facilities dated 09.09.2022 made between M/s. Mahi Terry Cot LLP and Relationship Manager, SBI, Diamon Garden Branch, Chembur, Mumbai-400 071 vide Letter No. SME/DGC/22-23/12.

3.4) APPOINTMENT OF CONSULTANT & CONTRACTORS: -

The consultant and contractor appointed for execution of proposes to set-up a terry towel manufacturing facility with a capacity of 9.5 ton per day at Plot No. T-24, Additional Amravati Textile Park, MIDC Nandgaon Peth, Amravati, PIN Code-444 901, State- Maharashtra, County-India are as under:-

| S. No | Particular | Name of Contractor/ Consultant |
| --- | --- | --- |
| 1 | Soil Investigation | M.K. Welankar & Associates, Mumbai |
| 2 | General Layout Plan | M.K. Welankar & Associates, Mumbai |
| 3 | WBM Road Work | M.K. Welankar & Associates, Mumbai |
| 4 | Civil Contractor | Amarshakti Techno-Estate Pvt. Ltd., Vapi |
| 5 | PMC | Forbes Marshall Pvt. Ltd., Pune |
| 6 | ETP & STP | Konark Fixtures Ltd., Mumbai |
| 7 | Boiler | Alfa-Therm Engineers, Pune |
| 8 | Machinery Erection | Aswad Engineering, Ahmedabad |
| 9 | Fire Hydrant System | Vaidyanath Fire Services Pvt. Ltd., Pune |
| 10 | Electrical Installation | Choudhary Electricals, Nagpur. |

OBSERVATIONS: -

- Company has appointed the Consultants & Contractors for the proposed project.

- Project activity is going on.

3.5) LAND FOR THE PROJECT:-

The company is already in possession of the MIDC Leasehold Land admeasuring 40,000 Sq. M. Company has provided following documents for the Leasehold Land: -

- Sanction for the allotment of land admeasuring 40000 Sq. M issued by Area Manager, MIDC, Amravati vide Letter No. MIDC/RO(AMR)/NAN/LMS-701/00143 dated 15.11.2017.

- Agreement dated 12.03.2018 made between Maharashtra Industrial Development Corporation (“Grantor”) and M/s. Mahi Terry Cot LLP (Licensees”) for the lease of Land admeasuring 40000 Sq. M.

- Pre-determined Lease dated 06.09.2022 made between Maharashtra Industrial Development Corporation (MIDC) (“the Lessor”) and M/s. Mahi Terry Cot LLP (“the Licensee”) for the lease of Land admeasuring 40000 Sq. M. for the period of 95 years computed from 01.12.2017.

OBSERVATIONS: -

- MIDC has allotted Leasehold Land admeasuring 40,000 Sq. M to M/s. Mahi Terry Cot LLP. Project activity is going on.  It is observed that the land cost is not included in the project cost. 
As per CA Certificate, the cost incurred towards Land as on 30.06.2023 is Rs. 94,30,580/-.

3.6) BUILDINGS FOR THE MANUFACTURING PROJECT: -

The buildings for proposes terry towel manufacturing facility with a capacity of 9.5 ton per day at Plot No. T-24, Additional Amravati Textile Park, MIDC Nandgaon Peth, Amravati, PIN Code-444 901, State- Maharashtra, County-India are as under: -

| S. No | Building | Proposed FSI Area (sq. M) | Double Height FSI Area (Sq. M) | Stair (Sq. M) | Total FSI Area (Sq. M) |
| --- | --- | --- | --- | --- | --- |
| 1 | Boilers-1 (B) | 769.41 | 384.71 | - | 1,154.12 |
| 2 | Ladies-1 (Quarter) (G+2) | 1,069.98 | - | 107.79 | 1,069.98 |
| 3 | Male-1 (Quarters) (G+2) | 1,268.44 | - | 62.52 | 1,268.44 |
| 4 | Pump-1 (Room) | 475.14 | - | - | 475.14 |
| 5 | Warehouse-1 (Main Plant Building) (B) (G+ Part 1st Floor) | 10,160.23 | 4,184.79 | 156.46 | 14,345.02 |
|  | Total | 13,743.20 | 4,569.50 | 326.77 | 18,312.70 |

OBSERVATIONS: -

- As per Initial approved Plan vide letter No. EE/DB/A63695 dated 15.02.2019 approved by Executive Engineer, MIDC Division, Amravati, the total Proposed Built-up Area is 14,373.54 Sq. M.

- Later Company had submitted the revised Plan with few additional areas and the Approval for the same was received vide Letter No. I/17583/2023 dated 12.09.2023 for the total built-up area is 18,312.70 Sq. M.

- Building & Civil cost of the project includes cost of construction of Boilers-1 (B), Ladies-1 (Quarter) (G+2), Male-1 (Quarters) (G+2), Pump-1 (Room), Warehouse-1 (B) (G+ Part 1st Floor), Road and infrastructure etc & is estimated at Rs. 11.00 Crores. It is observed that the land cost is not included in the project cost.

- M/s. Amarshakti Techno-Estate Pvt. Ltd., Vapi has mobilized the site and commenced the construction of main plant building. The construction work is in Progress.

3.7) PLANT & MACHINERY FOR THE PROJECT:-

The plant & machinery includes both imported as well as indigenous machineries for 9.5 ton per day at Plot No. T-24, Additional Amravati Textile Park, MIDC Nandgaon Peth, Amravati, PIN Code-444 901, State- Maharashtra, County-India. The total cost of plant & machinery is estimated at Rs. 3,995.90 Lakhs which includes core plant and machinery as well as other allied machineries. The cost of imported plant and machinery is estimated at Rs. 3,022.00 Lakhs (inclusive of C&F+ Erection Expenses 1.5%) and cost of indigenous plant and machinery is estimated around 973.90 Lakhs inclusive of taxes.

Breakup of Imported Plant & Machinery is as under:-

| S No. | Machine Name | Supplier | Qty. (No.) | Net Value (₹) | C&F + Erection Exp 1.5% (₹) | Total Value (₹) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Terry Airjet Looms - Dobby type - 340 cm Wide | Tsudakoma/Toyota / Picanol | 24 | 1440.00 | 21.60 | 1461.60 |
| 2 | Beam knotting machine | Staubli / Groz-Beckert / Todo | 1 | 13.00 | 0.20 | 13.20 |
| 3 | Pile Beam Trolley for 340 cm Loom width | Genkinger / Prashant Ferber / Rabatex | 1 | 50.00 | 0.75 | 50.75 |
| 4 | Fabric Dyeing Machine (800 Kg) | Thies / Fongs / Sclavos | 1 | 165.00 | 2.48 | 167.48 |
| 5 | Fabric Dyeing Machine (1200 Kg) | Thies / Fongs / Sclavos | 1 | 205.00 | 3.08 | 208.08 |
| 6 | Fabric Dyeing Machine (1600 Kg) | Thies / Fongs / Sclavos | 1 | 265.00 | 3.98 | 268.98 |
| 7 | Auto Chemical Supply System - 20 products | Thies / Fongs / Sclavos | 1 | 65.00 | 0.98 | 65.98 |
| 8 | Dyestuff Dissolving System | Thies / Fongs / Sclavos | 1 | 45.00 | 0.68 | 45.68 |
| 9 | Orgatex - Overhead system for machine controller | Thies / Fongs / Sclavos | 1 | 24.00 | 0.36 | 24.36 |
| 10 | Rope Opener for Fabric - 340 cm working width | Corino / Bianco / Swastik | 1 | 90.00 | 1.35 | 91.35 |
| 11 | Tumble Dryer | Biancalani / Penninsula | 1 | 100.00 | 1.50 | 101.50 |
| 12 | Length hemming machine | Texpa / Schmale | 3 | 225.00 | 3.38 | 228.38 |
| 13 | Semi Automatic Cross cutting machine | Texpa / Schmale | 2 | 30.00 | 0.45 | 30.45 |
| 14 | Fully Automatic Cross Hemming machine | Texpa / Schmale | 1 | 250.00 | 3.75 | 253.75 |
| 15 | Juki single needle lockstitch machine | IIGM, India | 5 | 2.00 | 0.03 | 2.03 |
| 16 | 3/4 thread overlock machine | IIGM, India | 2 | 1.30 | 0.02 | 1.32 |
| 17 | Needle detector system | CEIA SpA, Italy | 1 | 7.50 | 0.11 | 7.61 |
|  |  |  | Total | 2,977.80 | 44.67 | 3,022.47 |

Breakup of Indigenous Plant & Machinery is as under: -

| S No. | Machine Name | Supplier | Qty. (No.) | Net Value (₹) | GST 18% | Total Value (₹) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Weaver's beam (Pile) - 1.5 No. / loom | Bharat Beams / Dharmshil | 36 | 22.72 | 4.09 | 26.80 |
| 2 | Weaver's beam (Ground) - 1.5 No. / loom | Bharat Beams / Dharmshil | 36 | 12.38 | 2.23 | 14.61 |
| 3 | Cloth Roll - 1.5 No. / loom | Bharat Beams / Dharmshil | 36 | 2.88 | 0.52 | 3.40 |
| 4 | Flat heald, Riderless C type, 331 X 5.5 X 0.38 mm 9000/loom | Royal Industries / Dharmshil | 216000 | 6.22 | 1.12 | 7.34 |
| 5 | Drop pins (Ground - 0.2 mm) - 4500 No. / loom | Pradeep Industries / Dharmshil | 108000 | 1.56 | 0.28 | 1.84 |
| 6 | Drop pins (Pile - 0.3 mm) - 4500 No. / loom | Pradeep Industries / Dharmshil | 108000 | 1.47 | 0.26 | 1.73 |
| 7 | Loom Cloth Batching Motion | New Bhagwati / Prashant Ferber / I Shree | 24 | 42.00 | 7.56 | 49.56 |
| 8 | Warp Beam Trolley | Rabatex / Prashant Ferber / Tech-Mech | 1 | 1.80 | 0.32 | 2.12 |
| 9 | Empty Beam Trolley | Rabatex / Prashant Ferber / Tech-Mech | 1 | 0.80 | 0.14 | 0.94 |
| 10 | Cloth Doffing Trolley | Rabatex / Prashant Ferber / Tech-Mech | 1 | 2.25 | 0.41 | 2.66 |
| 11 | Motorized Beam Stocker System - 48 Beams | Rabatex | 1 |  |  |  |
| 12 | Guide roll for weaving looms | Rabatex | 24 |  |  |  |
| 13 | Material Pallet Trolley - 2 MT capacity | Tech Mech, India | 2 | 0.50 | 0.09 | 0.59 |
| 14 | Humidification Plant for Weaving + Warping | Batliboi / Luwa | 1 | 24.00 | 4.32 | 28.32 |
| 15 | Sectional Warping with Swivel Creel - 340 cm wide | Rabatex / Prashant Gamatex | 1 | 55.00 | 9.90 | 64.90 |
| 16 | Direct Warping with 'H' type 672 ends Creel | Jupiter / Prashant Gamatex | 1 | 40.00 | 7.20 | 47.20 |
| 17 | Multi cylinder Sizing machine | Jupiter / Prashant Gamatex | 1 | 135.00 | 24.30 | 159.30 |
| 18 | SS Size Cooking Vessel - 1500 Litres | Jupiter / Prashant Gamatex | 1 | 2.65 | 0.48 | 3.13 |
| 19 | SS Size Storage Vessel - 1500 Litres | Jupiter / Prashant Gamatex | 1 | 2.55 | 0.46 | 3.01 |
| 20 | 2 Tons Electrical Hoist | Mechatronics Engg, India | 1 | 1.00 | 0.18 | 1.18 |
| 21 | Warpers beam (24 nos) | Jupiter / Bharat Beam | 24 | 14.40 | 2.59 | 16.99 |
| 22 | Fabric Inspection Machine | New Bhagwati, India | 1 | 6.50 | 1.17 | 7.67 |
| 23 | Cone winding machine (60 drums x 1 = 60 drums) | SMEW,/ Peass / KTM | 1 | 9.00 | 1.62 | 10.62 |
| 24 | Plastic storage boxes for yarn / chemicals |  | 1 | 0.50 | 0.09 | 0.59 |
| 25 | Material stacking system for Main stores |  | 1 | 1.00 | 0.18 | 1.18 |
| 26 | Laboratory Equipments | Paramount / Presto | 1 | 12.00 | 2.16 | 14.16 |
| 27 | Fabric Dyeing Machine (50 Kg) | Penninsula, India | 1 | 9.00 | 1.62 | 10.62 |
| 28 | HDPE chemical tanks (H2O2, Acetic acid, HCL etc) - total 80 KL approx. |  | 80 | 9.60 | 1.73 | 11.33 |
| 29 | Fabric Hydroextractor (400 kg/Batch) | Swastik, India | 1 | 28.00 | 5.04 | 33.04 |
| 30 | MS Trolley with Plastic Crates (Dyeing) 2.54 x 0.87 x 0.77 m |  | 25 | 3.75 | 0.68 | 4.43 |
| 31 | SS Trollies (Dyeing) 3.4 x 1.2 x 0.78 m |  | 20 | 8.00 | 1.44 | 9.44 |
| 32 | Weighing Balances of Misc. Capacity |  | 1 | 1.50 | 0.27 | 1.77 |
| 33 | Length cutting machine | Penninsula / OTS | 1 | 20.00 | 3.60 | 23.60 |
| 34 | Butt Jointing machine |  | 1 | 0.15 | 0.03 | 0.18 |
| 35 | Stitching - Checking - Packing Tables |  | 40 | 1.60 | 0.29 | 1.89 |
| 36 | Stitched Material Trolley (4' x 4') |  | 60 | 4.80 | 0.86 | 5.66 |
| 37 | Computers & peripherals |  | 15 | 4.50 | 0.81 | 5.31 |
| 38 | Integrated ERP Software System |  | 1 | 30.00 | 5.40 | 35.40 |
| 39 | Servers |  | 1 | 20.00 | 3.60 | 23.60 |
| 40 | Power back up for Computer, servers & emergency lights |  | 1 | 0.75 | 0.14 | 0.89 |
| 41 | Ware house racking system |  | 1 | 15.00 | 2.70 | 17.70 |
| 42 | Forklift |  | 1 | 12.00 | 2.16 | 14.16 |
| 43 | Office Equipments (Tables & chairs) - 20 sets |  | 1 | 2.00 | 0.36 | 2.36 |
| 44 | Air compressor (770 CFM) - VFD | Kaeser / Atlas copco | 1 | 24.00 | 4.32 | 28.32 |
| 45 | Air compressor (745 CFM) - Fixed | Kaeser / Atlas copco | 1 | 15.00 | 2.70 | 17.70 |
| 46 | Air compressor (745 CFM) - Fixed | Kaeser / Atlas copco | 1 | 15.00 | 2.70 | 17.70 |
| 47 | Refrigerated Air Dryer | Kaeser / Atlas copco | 3 | 16.50 | 2.97 | 19.47 |
| 48 | Air compressor Microfilter | Kaeser / Atlas copco | 3 | 2.10 | 0.38 | 2.48 |
| 49 | Air compressor activated carbon filter | Kaeser / Atlas copco | 3 | 2.10 | 0.38 | 2.48 |
| 50 | Air Management system with accessories | Kaeser / Atlas copco | 1 | 2.75 | 0.50 | 3.25 |
| 51 | Vertical Air receiver - 5 cubic meter / 8 bar | Kaeser / Atlas copco | 1 | 2.00 | 0.36 | 2.36 |
| 52 | Compressed Air Piping & Distribution |  | 1 | 12.00 | 2.16 | 14.16 |
| 53 | Coal Fired FBC Steam Bolier | Thermax / IBL / Heatex | 1 | 40.00 | 7.20 | 47.20 |
| 54 | Boiler accessories (chimney, platform, fuel feeding system, bag filters etc.) |  | 1 | 45.00 | 8.10 | 53.10 |
| 55 | Pipes & fittings (Water / steam) |  | 1 | 35.00 | 6.30 | 41.30 |
| 56 | Fire fighting system (smoke detectors, hydrant, extingushers & alarms) |  | 1 | 20.00 | 3.60 | 23.60 |
| 57 | Effluent Treatment Plant |  | 1 | 25.00 | 4.50 | 29.50 |
|  |  |  | Total | 825.27 | 148.55 | 973.82 |

The cost of Plant & Machinery is as under:-

| S No. | Description of Machinery | Estimated Project Cost (Rs. in Lakhs) |
| --- | --- | --- |
| 1 | Imported Machinery | 3,022.47 |
| 2 | Indigenous Machinery | 973.82 |
|  | Total | 3,996.29 |

OBSERVATIONS:-

- The Company has finalized the machines for the project. However, change of supplier may take place while making final deal with the supplier. The status of plant & machinery is discussed in next section.

3.8) MISCELLANEOUS FIXED ASSET: -

The Miscellaneous Fixed Assets consist of Furniture/ Office Equipments, Air Conditioners, Vehicles and Others.  The total cost of miscellaneous fixed assets estimated by the company is Rs. 100.00 Lakhs.

| S No. | Machine Name | Total Value (₹) |
| --- | --- | --- |
| 1. | Furniture / Office Equipments | 10.00 |
| 2. | Air Conditioners | 50.00 |
| 3. | Vehicles | 25.00 |
| 4. | Others | 15.00 |
|  | Total | 100.00 |

3.9) ELECTRICAL FITTINGS: -

The Electrical fittings consist of Transformer 33kV / 2000 KVA, VCB 2000 KVA, Servo stabilizers,

Electrical Panels & Distribution board and Electrical cables, fittings, lighting fixtures.  The total cost of Electrical fittings estimated by the company is Rs. 112.10 Lakhs.

| S No. | Electrical Equipments | Qty. (No.) | Net Value (₹) | GST 18% | Total Value (₹) |
| --- | --- | --- | --- | --- | --- |
| 1 | Transformer 33kV / 2000 KVA | 1 | 35.00 | 6.30 | 41.30 |
| 2 | VCB 2000 KVA | 1 | 5.00 | 0.90 | 5.90 |
| 3 | Servo stabilizers | 1 | 10.00 | 1.80 | 11.80 |
| 4 | Electrical Panels & Distribution board | 1 | 15.00 | 2.70 | 17.70 |
| 5 | Electrical cables, fittings, lighting fixtures | 1 | 30.00 | 5.40 | 35.40 |
|  | Total |  | 95.00 | 17.10 | 112.10 |

OBSERVATIONS:-

- The Company has finalized the machines for the project. However, change of supplier may take place while making final deal with the supplier. The status of Electrical Installation is discussed in next section.

3.10) CONTINGENCY: -

The cost estimate is based on the budgetary quotations for most of the capital Equipments and no major change in the cost is expected. Considering these factors, provision for contingency has been estimated at @5% of total Project Hard Cost i.e., Cost of Plant & Machinery, Electrical Installation and Miscellaneous Fixed Assets (i.e., Rs. 3,995.90 Lakhs+ Rs. 100.00 Lakhs + 
Rs. 112.10 Lakhs = Rs. 4,208.3 Lakhs). Therefore, the estimated cost for contingency is Rs. 210.40 Lakh.

3.11) PRE-OPERATIVE EXPENDITURE: -

Preoperative expenditure for the proposed project estimated by the company is Rs. 393.02 Lakh and the break-up of the same is as under: -

| S No. | Machine Name | Total Value (₹) |
| --- | --- | --- |
| 1. | Interest During Construction @ 10.50% p.a. | 293.42 |
| 2. | Up-Front fee to lenders, documentation charges and other related expenses | 50.00 |
| 3. | Miscellaneous | 50.00 |
|  | Total | 393.42 |

3.12) POWER & WATER REQUIREMENT: -

The total connected load for the company would be around 1599.07 KW and the contract demand would be 1150 KW. The power breakup is as given under:

| S No. | Machine / Building Name | Qty. (Nos.) | Rating (KW) | Total Load (KW) |
| --- | --- | --- | --- | --- |
| 1 | Sectional Warping with Swivel Creel - 340 cm wide | 1 | 30.2 | 30.2 |
| 2 | Direct Warping with ’H' type 672 ends Creel | 1 | 30.2 | 30.2 |
| 3 | Cone winding machine (60 drums x 1 = 60 drums) | 1 | 5.76 | 5.76 |
| 4 | Multi cylinder Sizing machine | 1 | 80 | 80 |
| 5 | SS Size Cooking Vessel - 1500 Litres | 1 | 2 | 2 |
| 6 | SS Size Storage Vessel - 1500 Litres | 1 | 2 | 2 |
| 7 | 2 Tons Electrical Hoist | 3 | 2.5 | 7.5 |
| 8 | Weaver's Beam stacker | 1 | 7.5 | 7.5 |
| 9 | Terry Airjet Looms - Dobby type - 340 cm Wide | 24 | 10 | 240 |
| 10 | Loom Cloth Batching Motion | 24 | 1.5 | 36 |
| 11 | Beam knotting machine | 1 | 0.52 | 0.52 |
| 12 | Pile Beam Trolley for 340 cm Loom width (Battery operated) | 1 | 0.69 | 0.69 |
| 13 | Fabric Inspection Machine | 1 | 8.2 | 8.2 |
| 14 | Butt jointing machine | 1 | 0.32 | 0.32 |
| 15 | Fabric Dyeing Machine (800 Kg) | 1 | 39.43 | 39.43 |
| 16 | Fabric Dyeing Machine (1200 Kg) | 1 | 63.6 | 63.6 |
| 17 | Fabric Dyeing Machine (1600 Kg) | 1 | 77.42 | 77.42 |
| 18 | Liquid chemical & auxiliaries’ dosing / distribution 14 P + 1 OBA (DLV-PS) | 1 | 4 | 4 |
| 19 | Powder dye stuff storage/weighing/ PESMAN2) | 1 | 0.13 | 0.13 |
| 20 | Powder dye stuff dissolution / distribution (SCL1AN360) | 1 | 6 | 6 |
| 21 | Powder chemical weighing / dissolution / distribution (Salt & Soda) - DAP.360 | 1 | 12 | 12 |
| 22 | Rope Opener for Fabric - 340 cm working width | 1 | 10 | 10 |
| 23 | Tumble Dryer | 1 | 119 | 119 |
| 24 | Length cutting machine | 1 | 4.5 | 4.5 |
| 25 | Length hemming machine | 2 | 6.6 | 13.2 |
| 26 | Length hemming machine | 1 | 5.5 | 5.5 |
| 27 | Semi-Automatic Cross cutting machine | 2 | 1.5 | 3 |
| 28 | Juki single needle lockstitch machine | 25 | 0.32 | 8 |
| 29 | 3/4 thread overlock machine | 2 | 0.32 | 0.64 |
| 30 | Needle detector system | 1 | 2.62 | 2.62 |
| 31 | Warehouse storage & retrieval system | 1 | 10 | 10 |
| 32 | Laboratory Equipments | 1 | 15 | 15 |
| 33 | Humidification Plant for Weaving | 1 | 91.4 | 91.4 |
| 34 | Humidification Plant for Warping | 1 | 16.5 | 16.5 |
| 35 | Air compressor (499 CFM) - VFD | 1 | 75 | 75 |
| 36 | Air compressor (745 CFM) - Fixed | 1 | 110 | 110 |
| 37 | Air compressor (745 CFM) - Fixed | 1 | 110 | 110 |
| 38 | Refrigerated Air Dryer | 2 | 2.87 | 5.74 |
| 39 | Coal Fired FBC Steam Boiler | 1 | 70 | 70 |
| 40 | Weighing Balances of Misc. capacity | 1 | 5 | 5 |
| 41 | Computers & peripherals | 20 | 0.25 | 5 |
| 42 | CL IV cameras / access control | 150 | 0.01 | 1.5 |
| 43 | Firefighting system (smoke detectors, hydrant, extinguishers & alarms) | 1 | 120 | 120 |
| 44 | Effluent Treatment Plant (600 KLD) | 1 | 35 | 35 |
| 45 | Sewerage Treatment plant (50 KLD) | 1 | 10 | 10 |
| 46 | Supply water pumps (1 w + 1 s) | 1 | 9 | 9 |
| 47 | Water Softening Plant | 1 | 5 | 5 |
| 48 | Ceiling fans for Office / Factory | 1 |  | 10 |
| 49 | Indoor Office & Factory Lighting | 1 |  | 10 |
| 50 | Water and air coolers | 1 |  | 5 |
| 51 | Air Conditioners | 1 |  | 15 |
| 52 | Worker’s Housing (G+2) | 1 |  | 15 |
| 53 | Staff Quarters (G+2) | 1 |  | 15 |
| 54 | Ladies Worker’s Quarters (G+2) | 1 |  | 15 |
|  |  |  | Total | 1599.07 |

| S No. | Machine / Building Name | Unit | Load |
| --- | --- | --- | --- |
| 1 | Total Connected load | KW | 1599.07 |
| 2 | Total connected Load ON Transformer | KW | 1599.07 |
| 3 | Considering U.F 70%, i.e 0.70 | KW | 1,119.35 |
| 4 | Considering 0.98% Power Factor | KVA | 1,142.19 |
| 5 | Therefore for 1,142.19 KVA Contract Demand | KVA | 1,150 |
| 6 | Considering 75% Loading of transformer | KVA | 1,522.92 |
| 7 | Hence Proposed Rating Of transformer | KVA | 1,600.00 |

The total connected load for the company would be around 1599.07 KW and the contract demand would be 1150 KW.

The total water requirement as estimated is 800 KL per Day and the sane will be provided by MIDC. Water will be required for sizing, dyeing etc.

Observations:-

- MTC has applied for the 1150 KVA (Contact Demand) and received the sanction letter Sanctioning of New contract demand 1150 KVA and connected load 920 KW issued Superintending Engineer, O&M Circle, M.S.E.D.C. Ltd., Amravati vide No. SE/O&M/Amt/Tech/No. 00518 dated 24.01.2023. This will meet the requirement of the company.

- Water will be supplied by MIDC. Company required of 800 KL of Water per day. The said requirement will be sufficient for overall activity of the company.

3.14) STATUTORY CLEARANCES AND APPROVALS: -

Status of Approvals and clearances is as under: -

| S. No. | Approvals / Certifications | Approving / Sanctioning Authority | Status |
| --- | --- | --- | --- |
| 1 | Date of Incorporation | Registrar, Mumbai, Ministry of Corporate Affairs, GOI | Incorporated on 21.06.2016. |
| 2 | PAN Card | Income Tax, GOI | PAN Number-ABDFM1686N |
| 3 | GST Certificate | GOI | Registered on 01.07.2017, GSTN Number- 27ABDFM1686N1ZQ |
| 4 | Udyam Registration Certificate | MSME, GOI | Registered on 06.12.2021, Registration No. UDYAM-MH-18-0113799 |
| 5 | Certificate of Importer - Exporter Code | Directorate General of Foreign Trade | Obtained. Importer - Exporter Code 0317507605. |
| 6 | Land Possession | Provided vide possession receipt issued by MIDC dated 14.12.2017 |  |
| 7 | Building Plan approval | MIDC | Obtained |
| 8 | Consent to establish | Maharashtra Pollution Control Board | Obtained vide Consent No. Format 1.0/BO/CAC-Cell/CAC-UAN No. 37617/ CAC1810000566 dated 12.10.2018 valid till commission of the unit or 5 years whichever is earlier. |
| 9 | Provisional Fire NOC | MIDC | Obtained |
| 10 | Temporary Power Connection | MSEDCL | Obtained |
| 11 | Temporary Water Connection | MIDC | Obtained |
| 12 | Machinery Layout Plan | Director of Industrial Safety & Health | Obtained. |
| 13 | Permanent Electricity Connection | MSEDCL | Obtained |
| 14 | Drainage completion certificate | MIDC | Pending |
| 15 | Building Completion Certificate | MIDC | Pending |
| 16 | IBR Approvals | Directorate of Boilers | Obtained |
| 17 | Final Fire Department NOC | MIDC | Fire-fighting installation work in progress. NOC Pending |
| 18 | Consent to Operate | MPCB | Pending |
| 19. | Factory License | Director of Industrial Safety & Health | Pending |

OBSERVATIONS: -

- BCC, Drainage Completion Certified, Fire NOC, Consent to Operate and Factory License are pending.

3.15) IMPLEMENTATION SCHEDULE: -

Implementation Schedule for 9.5 ton per day at Plot No. T-24, Additional Amravati Textile Park, MIDC Nandgaon Peth, Amravati, PIN Code-444 901, State- Maharashtra, County-India is as under:-

| S. No. | Activity | Original Date as per Project Report |  | Revised date as per Company | Remark |
| --- | --- | --- | --- | --- | --- |
|  |  | Start Date | Completion Date | Completion Date |  |
| 1 | Procurement of Land |  | Acquired | Done | Acquired |
| 2 | Land Development | Jan-22 | Jan-22 | Done | Drainage, Road and Compound Wall work in Progress |
| 3 | Foundation of Building | Jan-2022 | April-2022 | Done | Completed |
| 4 | Construction of Building | April-2022 | July-2022 | Done | Finishing Work Balance |
| 5 | Machines Orders | March-2022 | July-2022 | Done | Completed |
| 6 | Receipt of Equipments | July-2022 | October-2022 | Done | Received |
| 7 | Assembling Fittings | Sept-2022 | Feb-2023 | Jul-23 | Fire Hydrant Line, Weighbridge Installation and Data Colour Kitchen equipment installation is pending |
| 8 | Trail Run |  | March-2023 | July + Aug 23 | Completed |
| 9 | Commercial Production | April-2023 |  | Aug-23 | Started |

OBSERVATIONS: -

- During the Date and time of Visit the Commercial Production is going on.

- Fire Hydrant Line, Weighbridge Installation and Data Colour Kitchen equipment installation is progress.

3.16) INSURANCE: -

Company has taken the insurance policy for 9.5 ton per day at Plot No. T-24, Additional Amravati Textile Park, MIDC Nandgaon Peth, Amravati, PIN Code-444 901, State- Maharashtra, County-India is as under:-

| S. No. | Type of Policy | Policy Period | Sum Insured (₹) | Policy Issuer |
| --- | --- | --- | --- | --- |
| 1 | Standard Fire and Special Perils Policy | 23.10.2023 to 22.10.2024 | 95,00,00,000 | Bajaj Allianz General Insurance Company Limited |

OBSERVATIONS: -

- Company has taken the Standard Fire and Special Perils Policy.

3.17) MANUFACTURING PROCESS: -

A terry towel is described as a textile product which is made with loop pile on one or both sides generally covering the entire surface or forming strips, checks, or other patterns (with end hems or fringes and side hems or selvages). A woven towel consists of five parts. These are the pile area, fringes, beginning and end part, selvedge, and border.

Part of a Terry Towel

Classification of Terry Towels according to Weight, Production Style, Finishing, Weft Count Per Pile Loop and Pile Presence on Fabric Surfaces

| S. No. | Weight | Production | Finishing | Weft Pick Count per Pile Loop | Pile Presence on Fabric Surfaces |
| --- | --- | --- | --- | --- | --- |
| 1 | Very heavy (>550 g/m2) | Woven | Velour Towel | Two-Pick Terry | One side pile |
| 2 | Heavy (450-550 g/m2) | Weft Knitted | Printed Towel | Three – Pick Terry | Both sides pile |
| 3 | Medium (350-450 g/m2) | Warp Knitted | Towel with Embroidery | Four – Pick Terry |  |
| 4 | Light (250-350 g/m2) |  | Towel with appliqués | Five – Pick Terry Six – Pick Terry Seven (or more) pick Terry |  |

Terry towel production processes include spinning, weaving, dyeing and finishing, and cutting as general steps. Shearing and embroidery are also regarded as necessary sub steps to obtain the final product of a terry woven towel.

The project will purchase yarn. Hence spinning will not be required.

Weaving :

The production of terry fabrics is a complex process and is only possible on specially equipped weaving machines. Three yarn systems are woven in the terry loom compared to the two system types of traditional weaving: Ground warp, pile warp and weft. The two warps are processed simultaneously: the ground warp, with tightly tensioned ends and the pile warp with lightly tensioned ends. A special weaving method enables loops to be handled with the lightly tensioned warp ends on the surface. Ground warps and pile warps are unwound separately, warped onto two different section beams and sized separately. The processes they undergo show some differences from each other. Weft or filling yarns are wound onto bobbins in required softness and lengths. In Figure, the flow chart of terry weaving process is shown. In drafting or drawing in, ground and pile warps are passed through heddle eyes in the heald frames or harnesses, through ground and pile drop wires and through special terry reeds which have double teeth. Warps are fed into the loom from two beams: The ground and pile warp beams. The tension of the pile warp beam is lower than that of the ground warp beam; therefore the pile warp beam delivers higher length of warps than does the ground warp beam does. A special reed motion lets this extra length of pile warp form loops. Terry weaving is described as “slack tension warp method” by Humpries. Weaving preparation consists of procedures which are carried out before weaving in order to obtain good quality fabric by ensuring warp and weft performance.

Warping

Warp ends should be wound onto the section beam in accordance with the required weave, total number of ends, length and the required warp density (epi) of the fabric. By setting the yarn tension consistently during warping throughout the warp beam, the sizing may be applied in a more homogenous manner throughout the beam. The objective of the warping systems is to present a continuous length of yarn to the succeeding process with all the ends continuously present and with the integrity and elasticity of the yarn as wound; fully preserved.

Sizing

Terry toweling is formed from cotton yarns, and as described earlier these yarns are produced by gathering cotton fibers together and twisting them. Some of the fibers in the yarn are totally in contact with other fibers, while some fibers are loose and protruding. Fibers of the latter type do not contribute to the strength of yarn totally and form a rough yarn surface. Warp ends should be able to withstand great tension and friction forces during shedding and beat-up in the weaving process. As the number of end breakages increase so will the total cost and number of fabric defects increase. Sizing is a pretreatment for yarns to be processed as warps for weaving into textile fabrics. Sizing protects the yarns against mechanical stresses in the weaving process by the application of a film of sizing agent which envelopes the yarn and which subsequently must be removed in finishing. Weaving efficiency is highly dependent on sizing. The sizing agents which are used today can be either natural sizing agents (starches, starch derivatives, cellulosic sizing agents) or manmade sizing agents (polyvinyl alcohol, acrylic).

Drafting for Terry Weaving

Drafting or drawing-in is the process of passing the warp ends through drop wires, heald or heddle eyes and reed dents in the designated order. With this step the warp ends are arranged in the required order, prevented from crossing over each other, and warp density is set. It is one of the most laborious of all textile processes, however, most weaving mills throughout the world continues to do this process by hand.

It is quite common practice to shear the terry loops after manufacture in order to create a cut-pile effect. Shearing is applied to the pile fabric, by passing it over a cylinder with blades like a giant cylindrical lawnmower. The velour fabric is then brushed with bristles set in a cylinder to remove cut bits of fiber. Brushing leaves the surface fiber lying in one direction so care must be taken to have all the fabrics in the same batch laid out in the same direction, or light will reflect off various pieces differently.

Dyeing and Finishing of Terry Towels

The main fiber which is used in towels is cotton. As cotton fiber is not sensitive to alkali or chlorine bleach but is to acids, all the dyeing and finishing processes are planned with these conditions. Like other textile materials the dyeing and finishing stage of terry towels generally follow the workflow shown below:-

a) Pretreatment

Fiber preparation ordinarily involves scouring to remove foreign material and thus ensures even access to dye liquor from the dye bath. Cotton must be boiled and bleached to remove pectin and cotton seeds. Sizing substances also must be eliminated. The steps of pretreatment are shown below:

➢Desizing

➢Scouring

➢Bleaching

b) Coloration (Dyeing or Printing)

Coloration of towels can be achieved in three ways as follow:

➢ Fabric Dyeing

The process of dye application involves the transfer of dye from a solution in a dye bath to the fiber. Additives such as wetting agents, salts and others are added to the dye bath along with the dye in order to facilitate the dyeing process.

➢Printing

Printing is local dyeing in zones according to patterns. Thickeners ensure that these zones defined by the engraved pattern are adhered to. The type and size of the artistic design determine the printing process and method of dye paste application

➢Package Dyeing

For package dyeing, yarn is wound on dye tubes as packages, each with a hollow center that allows liquid to flow through it. The packages are stacked on perforated, hollow posts, and dye liquor is pumped through these.

c) Finishing

Final finishing includes all the finishing treatments applied to the fabric after dyeing and printing. It can be divided into two:

➢Chemical (or Wet) Treatments

➢Mechanical (or Decorative) Treatments

Softening, hydrophilling and antimicrobial treatments are among the chemical finishing processes of terry towels.

The main aims of dry treatments are to give the towels fuller volume, and dimensional stability and dryness.

In Cutting and Sewing, Towels pass through four steps.

➢Longitudinal Cutting

➢Longitudinal Hemming - Cross Cutting

➢Cross Hemming

These processes are achieved by scissors and standard sewing machines by workers or by machines specialized in towel cutting or sewing or even by automatic machines which can carry out some of or all the mentioned processes.

- PROJECT EXECUTION

#### 4.1) SITE SETUP: -

The project site setup is as under: -

| S. No | Particular | Status as on LIE 2nd Visit |
| --- | --- | --- |
| 1 | Power | Available for construction |
| 2 | Water | Available for construction |
| 3 | Project Team | Available |
| 4 | Timing | 8.00 a.m to 6.00 p.m |
| 5 | Project Office Setup | Furniture and office Equipments etc. |
| 6 | Staff | Recruitment ongoing |
| 7 | Lighting | Flood Lights |
| 8 | Labour Camp | Available |
| 9 | Canteen | Available |

OBSERVATIONS:-

The site setup is satisfactory. The photographs of site setup are provided for ready reference in Photograph Section.

#### 4.2) MANPOWER: -

The recruitment for the project execution is as under: -

| S. No | Particular | Staff | Worker | Nos. |
| --- | --- | --- | --- | --- |
| 1 | Plant Head | 1 | 0 | 1 |
| 2 | Engineering Staff | 5 | 6 | 11 |
| 3 | Accounts & Stores | 3 | 0 | 3 |
| 4 | HR & Admin | 2 | 0 | 2 |
| 5 | Designing | 1 | 0 | 1 |
| 6 | Preparatory | 3 | 14 | 17 |
| 7 | Weaving | 3 | 25 | 28 |
| 8 | Grey Folding | 0 | 3 | 3 |
| 9 | Dyeing & Processing | 2 | 9 | 11 |
| 10 | Finishing | 3 | 25 | 28 |
|  | Total | 23 | 82 | 105 |

#### OBSERVATIONS: -

The project team is experienced to handle the day-to-day operations of the project.

#### 4.3) COST OF THE PROJECT: -

MTC is proposes to set-up a terry towel manufacturing facility with a capacity of 9.5 ton per day at Plot No. T-24, Additional Amravati Textile Park, MIDC Nandgaon Peth, Amravati, PIN Code-444 901, State- Maharashtra, County-India. MIDC has allotted the Leasehold Land admeasuring 40,000.00 Sq. M at Plot No. T-24, Additional Amravati Textile Park, MIDC Nandgaon Peth, Amravati, PIN Code-444 901, State- Maharashtra, County-India. Total estimated project cost is Rs. 4,811.82 Lakhs as indicated in table provided below for ready reference.

| S. No | Particular of Project | Estimated Project Cost (Rs. in Lakhs) |
| --- | --- | --- |
| 1. | Land & Development | 0 |
| 2. | Buildings | 0 |
| 3. | Plant & Machinery | 3,995.90 |
| 4. | Miscellaneous Fixed Asset | 100.00 |
| 5. | Electrical Fittings | 112.10 |
| 6. | Contingencies | 210.40 |
| 7. | Preoperative Expenses | 393.42 |
|  | Total | 4,811.82 |

Note:-

- The Company has already acquired a land of 40,000 m².

- The expenses for the civil work of the factory building will be borne by the company from its own sources and Cost for the same was not considered in project cost.

MEANS OF FINANCE

| S. No | Particular of Project | Estimated Project Cost (Rs. in Lakhs) |
| --- | --- | --- |
| 1. | Promoter Capital | 2,011.82 |
| 2. | Term Loan | 2,800.00 |
|  | Total | 4,811.82 |

#### 4.4) EXPENDITURE ON PROJECT: -

The expenditure on Cost on Project as on 23.10.2023 as per CA Certificate is as under: -

The expenditure on Cost on Project as on 23.10.2023 as per CA Certificate is as under: -

#### 4.5) STATUS OF LAND: -

MIDC has allotted Leasehold Land admeasuring 40,000.00 Sq. M. The Cost incurred towards Land is as under: -

| S. No. | Particular | Details | Date | Cost Incurred (₹) |
| --- | --- | --- | --- | --- |
| 1 | Being amount paid for land purchased. CHRQUE NO. 696857 | Punjab National Bank A/c No. 3737002101015170 | 16/10/2017 | 23,50,000 |
| 2 | Being amount paid for land purchased. CHEQUE NO. 696861. | Punjab National Bank A/c No. 3737002101015170 | 11/12/2017 | 70,50,000 |
| 3 | being exp paid by sorabh sir for Visit at Amravati. (REGISTRATION CHARGES) | Cash | 13/03/2018 | 30,580 |
|  |  |  | Total | 94,30,580 |

OBSERVATIONS: -

- Land Cost is not considered in the cost of Project.

#### 4.6) COST INCURRED TOWARD BUILDING: -

As per C.A Certificate, the Cost incurred towards Building till 23.10.2023 is Rs. 20,33,70,952/- (i.e Factory Premises and Building CWIP). The Status of Building Completed is as under:-

| S. No | Building | Total FSI Area (Sq. M) | % of Work Completed |
| --- | --- | --- | --- |
| 1 | Boilers-1 (B) | 1,154.12 | 100% |
| 2 | Ladies-1 (Quarter) (G+2) | 1,069.98 | 90% |
| 3 | Male-1 (Quarters) (G+2) | 1,268.44 | 90% |
| 4 | Pump-1 (Room) | 475.14 | 90% |
| 5 | Warehouse-1 (Main Plant Building) (B) (G+ Part 1st Floor) | 14,345.02 | 90% |

OBSERVATIONS: -

- On Average Building is 92% Completed.

- Work related to Compound wall, road, drainage is in progress.

- Finishing work related to Ladies-1 (Quarter) (G+2), Male-1 (Quarters) (G+2), Pump-1 (Room), Warehouse-1 (Main Plant Building) (B) and (G+ Part 1st Floor) is in progress.

- Weigh Bridge foundation work is in progress.

#### 4.7) COST INCURRED TOWARDS PLANT & MACHINERY: -

The plant & machinery includes both imported as well as indigenous machineries for 9.5 ton per day at Plot No. T-24, Additional Amravati Textile Park, MIDC Nandgaon Peth, Amravati, PIN Code-444 901, State- Maharashtra, County-India. The total cost of plant & machinery is estimated at Rs. 3,995.90 Lakhs which includes core plant and machinery as well as other allied machineries. The cost of imported plant and machinery is estimated at Rs. 3,022.00 Lakhs (inclusive of C&F+ Erection Expenses 1.5%) and cost of indigenous plant and machinery is estimated around Rs. 973.90 Lakhs inclusive of taxes. The Cost incurred toward Plant & Machinery till 30.06.2023 is as under:-

#### 4.7.1 COST INCURRED TOWARDS PLANT & MACHINERY-INDIGENOUS: -

The Cost incurred toward Plant & Machinery- Indigenous till 23.10.2023 is as under:-

| S. No. | Particulars | Supplier | Qty | Date | Invoice No. | Basic Invoice Value (₹) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 470 KLPL Effluent Treatment Plant having 400 KLPD Non Dye Bath Strem & 70 KLPD Dye Bath Stream (Part Supply) | Konark Fixtures Ltd | Lot | 18/03/2023 | 23ININ000519 | 6,50,000 |
| 2 | 470 KLPL Effluent Treatment Plant having 400 KLPD Non Dye Bath Strem & 70 KLPD Dye Bath Stream (Part Supply) | Konark Fixtures Ltd | Lot | 23/03/2023 | 23ININ000525 | 18,80,000 |
| 3 | 470 KLPL Effluent Treatment Plant having 400 KLPD Non Dye Bath Strem & 70 KLPD Dye Bath Stream (Part Supply) | Konark Fixtures Ltd | Lot | 23/03/2023 | 23ININ000527 | 3,10,000 |
| 4 | 470 KLPL Effluent Treatment Plant having 400 KLPD Non Dye Bath Strem & 70 KLPD Dye Bath Stream (Part Supply) | Konark Fixtures Ltd | Lot | 30/03/2023 | 23ININ000544 | 20,10,000 |
| 5 | 470 KLPL Effluent Treatment Plant having 400 KLPD Non Dye Bath Strem & 70 KLPD Dye Bath Stream (Part Supply) | Konark Fixtures Ltd | Lot | 04/05/2023 | IIN2300015 | 16,50,000 |
| 6 | 470 KLPL Effluent Treatment Plant having 400 KLPD Non Dye Bath Strem & 70 KLPD Dye Bath Stream (Part Supply) | Konark Fixtures Ltd | Lot | 30/05/2023 | IIN2300046 | 11,50,000 |
| 7 | 470 KLPL Effluent Treatment Plant having 400 KLPD Non Dye Bath Strem & 70 KLPD Dye Bath Stream (Part Supply) | Konark Fixtures Ltd | Lot | 19/06/2023 | IIN2300094 | 1,05,000 |
| 8 | 470 KLPL Effluent Treatment Plant having 400 KLPD Non Dye Bath Strem & 70 KLPD Dye Bath Stream (Part Supply) | Konark Fixtures Ltd | Lot | 27/06/2023 | IIN2300099 | 2,10,000 |
| 9 | 470 KLPL Effluent Treatment Plant having 400 KLPD Non Dye Bath Strem & 70 KLPD Dye Bath Stream (Part Supply) | Konark Fixtures Ltd | Lot | 25/07/2023 | IIN2300153 | 35,000 |
| 10 | 50 KLD Sewerage Treatment Plant (Part Supply) | Konark Fixtures Ltd | Lot | 18/03/2023 | 23ININ000520 | 2,50,000 |
| 11 | 50 KLD Sewerage Treatment Plant (Part Supply) | Konark Fixtures Ltd | Lot | 21/03/2023 | 23ININ000526 | 3,20,000 |
| 12 | 50 KLD Sewerage Treatment Plant (Part Supply) | Konark Fixtures Ltd | Lot | 23/03/2023 | 23ININ000528 | 85,000 |
| 13 | 50 KLD Sewerage Treatment Plant (Part Supply) | Konark Fixtures Ltd | Lot | 30/03/2023 | 23ININ000545 | 1,35,000 |
| 14 | 50 KLD Sewerage Treatment Plant (Part Supply) | Konark Fixtures Ltd | Lot | 04/05/2023 | IIN2300016 | 1,71,000 |
| 15 | 50 KLD Sewerage Treatment Plant (Part Supply) | Konark Fixtures Ltd | Lot | 30/05/2023 | IIN2300047 | 50,000 |
| 16 | Air Receiver 1 m3 8bar Vert.Ungal | Kaeser Compressors (India) Pvt.Ltd. | 1 | 20/05/2023 | PI1000039992 | 70,000 |
| 17 | Air Receiver 5 m3 | Kaeser Compressors (India) Pvt.Ltd. | 1 | 20/05/2023 | PI1000039990 | 2,15,000 |
| 18 | All Flue Gas ducting and combustion air ducting with structurals | Alfa Therm Engineers | 1 | 12/03/2023 | ATE/2022-23/024 | 8,00,000 |
| 19 | Ash Handling System- Supply of Grate Ash Scew Conveyor (ASC 1) with Drive Unit (1 No.) & CI Rotary Scew Valve, 8" with Drive Unit | Decon Equipments and Systems Private Limited | Set | 08/05/2023 | 62/23-24 | 4,00,000 |
| 20 | Bag Closer Sewing Machine | Shyam Agencies | Set | 28/09/2023 | 98/2023-24 | 25,000 |
| 21 | Sewing Thread | Shyam Agencies | Set | 28/09/2023 | 99/2023-24 | 536 |
| 22 | BATCHING DEVICE For Weaving Machine Suitable For 340 CM | Rabatex Industries | 24 | 11/04/2023 | 36-23/24 | 32,64,000 |
| 23 | Battery Operated Top Beam Warp Beam Carrier -Eco Sup 1100 | Rabatex Industries | 1 | 11/04/2023 | 36-23/24 | 44,55,000 |
| 24 | Bearing 6215 2 Rs | Bharat Beams Pvt Ltd | 70 | 13/05/2023 | BBPL/2023-24/045 | 2,03,000 |
| 25 | Bearing | BHARAT BEAMS PVT LTD | 26 | 25/07/2023 | BBPL/2023-24/131 | 75,400 |
| 26 | Boiler Accesories Piping & Fittings | Alfa Therm Engineers | Set | 23/05/2023 | ATE/2023-24/05 | 22,53,974 |
| 27 | Uloading Of Material , Erection & Commissioning & Instalation Of Boiler | Alfa Therm Engineers |  | 04/10/2023 | ATE/2023-24/34 | 15,00,000 |
| 28 | Ecomak Make Online Bag Filter, Model:- EXC-154-455 | ECOMAK SYSTEMS PVT LTD | 1 | 10/04/2023 | 2324006 | 18,00,000 |
| 29 | Boiler Capacity 5500kg/Hr With Accessories | Forbe Svyncke Pvt Ltd | Lot | 22/03/2023 | 853501985 | 1,41,00,000 |
| 30 | Boiler Flow Meter & Accesories | Forbes Marshall Pvt. Ltd. (Goods) | Lot | 27/05/2023 | 6004500739 | 5,00,000 |
| 31 | Boiler Pipes & Fitting (Water/Steam) & Accesories | Forbes Marshall Pvt. Ltd. (Goods) | Lot | 02/05/2023 | 5545000932 | 1,10,00,000 |
| 32 | Boiler Accessories | Forbes Marshall Pvt. Ltd. (Goods) | Lot | 17/07/2023 | 5545003283 | 62,57,389 |
| 33 | Boiler Accessories | Forbes Marshall Pvt. Ltd. (Goods) | Lot | 11/09/2023 | 6004502301 | 94,425 |
| 34 | Boiler Accessories | Forbes Marshall Pvt. Ltd. (Goods) | Lot | 20/09/2023 | 6004502332 | 1,38,950 |
| 35 | C3a-Solenoid230-Wsm0140410 Forbes Marshall Steam Ancillary Equipments | Forbes Marshall Pvt. Ltd. (Goods) | Lot | 23/09/2023 | 6004502433 | 12,250 |
| 36 | Material Returned | Forbes Marshall Pvt. Ltd. (Goods) | Lot | 27/09/2023 | 003/23-24 | - 1,37,500 |
| 37 | Chain Pulley Block 1ton Indef Make | Gode Engineering Pvt Ltd | 1 | 30/03/2023 | GST/2223/01232 | 13,464 |
| 38 | Chain Pulley Block 3ton Indef Make | Gode Engineering Pvt Ltd | 1 | 30/03/2023 | GST/2223/01232 | 23,706 |
| 39 | Chemical Tank .75kl Envisol-15 | Arvind Envisol Ltd | 15 | 21/06/2023 | S402300015 | 87,345 |
| 40 | Chimney Template With Foundation | ALFA THERM ENGINEERS | Journal | 09/12/2022 | ATE/2022-23/018 | 40,000 |
| 41 | Cloth Inspection Cum Rolling Machine, Mode Nb-105 | New Bhagwati Vijay Engg.Works | 1 | 21/06/2023 | T-04 | 7,60,000 |
| 42 | Cloth Roll Doffer Carrier Model No.Vm-502c(Cradle Type) | Rabatex Industries | 1 | 11/04/2023 | 36-23/24 | 2,92,000 |
| 43 | Compressed Air Filter E320KA | Kaeser Compressors (India) Pvt.Ltd. | Set | 05/10/2023 | PI1000041311 | 50,907 |
| 44 | Diameter Axial Floe Fan For Comressor Drayer | Yesha Enterprises | Set | 12/08/2023 | YE/12/23-24 | 64,000 |
| 45 | Cross Cutting Machine For Towel | Om Textile Solution | Set | 13/09/2023 | 42 | 12,00,000 |
| 46 | Df25 Hand Pallet Truck 1 | Toyota Material Handling India Pvt Ltd | 1 | 26/12/2022 | 22GEQ00484 | 35,000 |
| 47 | Df25 Hand Pallet Truck 2 | Toyota Material Handling India Pvt Ltd | 1 | 26/12/2022 | 22GEQ00484 | 35,000 |
| 48 | Hermetically Sealed Distribution Transformer-1600 Kva (Oltc Indoor), Sr. No. Di-31803 | Digvijay Industries | 1 | 13/06/2023 | 506 | 24,50,000 |
| 49 | Drop Pins For Weaving Looms | Saifee Enterprises | Lot | 20/09/2023 | A000423 | 6,400 |
| 50 | 165 X 11 X 0.30 Mm Open Ele. (SS)- Drop Wire-108000 Nos. 165 X 11 X 0.20 Mm Open Ele. (SS)- Drop Wire-40,000 Nos. | Pradeep Industries | Lot | 15/06/2023 | GST-56/23-24 | 2,65,800 |
| 51 | 165 X 11 X 0.20 Mm Open Ele. (SS)- Drop Wire | Pradeep Industries | 68000 | 19/06/2023 | GST-57/23-24 | 1,12,200 |
| 52 | Electronic Weighing Machine, Dx-451, 1500 Kg | Essae-Teraoka Pvt Ltd | 1 | 05/06/2023 | 11022402586 | 64,800 |
| 53 | Electronic Weighing Machine, Dx-852, 1 Kg | Essae-Teraoka Pvt Ltd | 1 | 14/06/2023 | 12022401933 | 13,935 |
| 54 | Electronic Weighing Machine, Dx-451, 100 Kg | Essae-Teraoka Pvt Ltd | 4 | 20/06/2023 | 11022403248 | 99,812 |
| 55 | Electronic Weighing Machine- Dx-451, 300 Kg | Essae-Teraoka Pvt Ltd | 2 | 20/06/2023 | 11022403249 | 66,946 |
| 56 | Electronic Weighing Machine, Dx-451, 15 Kg | Essae-Teraoka Pvt Ltd | 1 | 22/06/2023 | 11022403391 | 22,328 |
| 57 | Electronic Weighing Machine, Ax-620g | Essae-Teraoka Pvt Ltd | 1 | 24/06/2023 | 11022403472 | 25,313 |
| 58 | Weighing Scale Capacity 3000kg | Mettler -Toledo India Pvt Ltd | 1 | 15/07/2023 | F24023003828 | 1,58,740 |
| 59 | Empty Beam Carrier Model No Vm-501 | Rabatex Industries | 1 | 11/04/2023 | 36-23/24 | 1,03,000 |
| 60 | Samcrete-Ep-848 Kgs & Samsol-Ep-5 Kg | Murexin Chemicals Pvt Ltd | Lot | 28/04/2023 | GSTBT/7 | 1,88,660 |
| 61 | Erection & Commission | Hilti India Pvt Ltd | Journal | 29/04/2023 | HI27-5187-2023 | 95,426 |
| 62 | Erection & Commission- Bolt, Hammer Drill, Plum Bob | Saifee Enterprises | Lot | 08/05/2023 | A000088 | 1,230 |
| 63 | Erection & Commission- Safety Helmet White & Blue | Saifee Enterprises | 25 | 11/05/2023 | A000096 | 3,000 |
| 64 | Erection & Commission- Nylone Line Dori Blue, Wire Rope, Level Pipe, Ms Hex Bolt | Taherali Fidahusain & Co | Lot | 15/05/2023 | TFC/23-24/122 | 2,550 |
| 65 | Application Of Core Cutting Work On Floor, Dia Of Core 60 Mm, Depth-200 Mm | Labhesh Construction | 232 | 16/05/2023 | 12 | 2,20,400 |
| 66 | Erection & Commission | Murexin Chemicals Pvt Ltd | Journal | 23/05/2023 | GSTBT/11 | 1,18,460 |
| 67 | Samcrete-Ep | Murexin Chemicals Pvt Ltd | 224 Kg | 01/06/2023 | SR/1 | - 49,280 |
| 68 | Erection & Commission- Lock, Sand Paper, Fan Rod, Cutte, Hammer Drill | Saifee Enterprises | Lot | 01/06/2023 | A000165 | 2,128 |
| 69 | Erection & Commission | Murexin Chemicals Pvt Ltd | Journal | 01/06/2023 | J/10 | 69,120 |
| 70 | Erection & Commission- Nut & Bolt | Saifee Enterprises | Lot | 10/06/2023 | A000203 | 7,100 |
| 71 | Erection & Commission- High Tensil Hex Bolt, Nut, Wedge Anchor | Taherali Fidahusain & Co | Lot | 10/06/2023 | TFC/23-24/214 | 20,000 |
| 72 | Erection & Commission- Gi Hex Bolt, Washer, Wedge Anchor | Taherali Fidahusain & Co | Lot | 15/06/2023 | TFC/23-24/221 | 4,949 |
| 73 | Erection & Commission- Nut & Bolt | Saifee Enterprises | Lot | 19/06/2023 | A000234 | 6,550 |
| 74 | Erection & Commission | Taherali Fidahusain & Co | Journal | 25/06/2023 | TFC/23-24/244 | 10,950 |
| 75 | Erection & Commission- Nut & Bolt | Saifee Enterprises | Lot | 26/06/2023 | A000255 | 4,045 |
| 76 | Erection & Commission- Rubber Hose Assembly, Adaptors, | Techmark Corporation | Lot | 26/06/2023 | M-652 | 754 |
| 77 | Erection & Commission- Rivets | Saifee Enterprises | 4.2 Pkt | 27/06/2023 | A000259 | 630 |
| 78 | Erection & Commission | Saifee Enterprises | Lumpsum | 01/07/2023 | A000047 | 9,471 |
| 79 | Erection & Commission | Taherali Fidahusain & Co | Lumpsum | 03/07/2023 | TFC/23-24/272 | 4,464 |
| 80 | Erection & Commission | Techmark Corporation | Lumpsum | 04/07/2023 | M-691 | 758 |
| 81 | Purchase Of Bolt 16x150 | Saifee Enterprises | Lumpsum | 06/07/2023 | A000287 | 5,250 |
| 82 | Purchase Of Electrical Parts | Taherali Fidahusain & Co | Lumpsum | 07/07/2023 | TFC/23-24/287 | 4,237 |
| 83 | Purchase Of Ms Bolt 12x50mm | Saifee Enterprises | Lumpsum | 07/07/2023 | A000293 | 1,208 |
| 84 | Erection & Commission | Fong's Technical Services Pvt Ltd | Lumpsum | 08/07/2023 | 23070072 | 11,986 |
| 85 | Chemical Anchorning Bolt For Rope Opener Machine | Hilti India Pvt Ltd | Lumpsum | 13/07/2023 | HI27-16681- 2023 | 31,456 |
| 86 | Ppr Line Support | Taherali Fidahusain & Co | Lumpsum | 17/07/2023 | TFC/23-24 /331 | 1,610 |
| 87 | Ss Fittings For Sizing Machine Piping | Saraswati Metal And Fittings | Lumpsum | 17/07/2023 | 2358/2023-24 | 56,866 |
| 88 | Boiler & Ppr Line Mechanical Work | Taherali Fidahusain & Co | Lumpsum | 18/07/2023 | TFC/23-24 /337 | 5,813 |
| 89 | Erection & Commission | Chandiram Tractor Agency | Lumpsum | 21/07/2023 | 2955 | 3,559 |
| 90 | Erection & Commission | Techmark Corporation | Lumpsum | 22/07/2023 | M-840 | 1,866 |
| 91 | Erection & Commission | Techmark Corporation | Lumpsum | 25/07/2023 | M-848 | 5,000 |
| 92 | Erection & Commission | Taherali Fidahusain & Co | Lumpsum | 01/08/2023 | TFC/23-24 /353 | 1,750 |
| 93 | Erection & Commission | Techmark Corporation | Lumpsum | 01/08/2023 | M-892 | 34,300 |
| 94 | Erection & Commission | Taherali Fidahusain & Co | Lumpsum | 09/08/2023 | TFC/23-24 /373 | 27,492 |
| 95 | Erection Of Warping, Looms, Sizing Bian Calani, Fongs Dying, Bianco Rop Opener Machineries | Aswad Engineering Pvt Ltd | Lumpsum | 10/08/2023 | 295/23-24 | 11,77,966 |
| 96 | Core Cutting Work & Saw Cutting Work | Labhesh Construction | Lumpsum | 12/08/2023 | 27 | 28,000 |
| 97 | Welding Electrodes & Rubber Sheet | Saifee Enterprises | Lumpsum | 12/08/2023 | A000350 | 2,332 |
| 98 | Bolts | Taherali Fidahusain & Co | Lumpsum | 14/08/2023 | TFC/23-24 /391 | 1,175 |
| 99 | Connectors For Erection & Commissioning For Fongs & Color Service Machinery | Techmark Corporation | Lumpsum | 18/08/2023 | M-1029 | 17,675 |
| 100 | Nut & Bolts | Taherali Fidahusain & Co | Lumpsum | 23/08/2023 | TFC/23-24 /412 | 20,728 |
| 101 | Flange Connector For Erection & Commissioning For Fongs & Color Service Machinery | Techmark Corporation | Lumpsum | 24/08/2023 | M-1072 | 32,228 |
| 102 | Erection & Commission | Gode Engineering Pvt Ltd | Lumpsum | 24/08/2023 | 2324/SHELL /0633 | 1,52,629 |
| 103 | Erection & Commission | Gurudeo Sales Corporation | Lumpsum | 24/08/2023 | MOB232 400328 | 94,784 |
| 104 | Erection & Commission | Techmark Corporation | Lumpsum | 31/08/2023 | M-1127 | 10,224 |
| 105 | Erection & Commission | Techmark Corporation | Lumpsum | 31/08/2023 | M-1128 | 8,937 |
| 106 | Grease Gc | Kanak Intratrade | Lumpsum | 31/08/2023 | KI/I/23-24 /0122 | 23,100 |
| 107 | Smps For Humidification Plant | Patel Sale Corp. | Lumpsum | 13/09/2023 | 743 | 564 |
| 108 | Erection & Commission | Gode Engineering Pvt Ltd | Lumpsum | 17/09/2023 | 2324/SHELL /0742 | 3,700 |
| 109 | Erection & Commission | Taherali Fidahusain & Co | Lumpsum | 19/09/2023 | TFC/23-24/490 | 7,894 |
| 110 | Erection & Commission | Techmark Corporation | Lumpsum | 22/09/2023 | M-1249 | 4,750 |
| 111 | Erection & Commission | Techmark Corporation | Lumpsum | 22/09/2023 | M-1258 | 9,900 |
| 112 | Erection & Commission | Saifee Enterprises | Lumpsum | 30/09/2023 | A000445 | 9,926 |
| 113 | Erection & Commission | Fong's Technical Services Pvt Ltd | Lumpsum | 01/10/2023 | 23090114 | 9,192 |
| 114 | Professional Fees For Erection & Commisionering | Fong's Technical Services Pvt Ltd | Lumpsum | 01/10/2023 | 23090119 | 10,112 |
| 115 | Erection & Commission | Gurudeo Sales Corporation | Lumpsum | 04/10/2023 | MOB/23 2400420 | 85,752 |
| 116 | Erection & Commission | Taherali Fidahusain & Co | Lumpsum | 04/10/2023 | TFC/23-24 /530 | 18,954 |
| 117 | Professional Fees For Erection & Commisionering | Fong's Technical Services Pvt Ltd | Lumpsum | 04/10/2023 | M-23090119 | 6,695 |
| 118 | Erection & Commission | Taherali Fidahusain & Co | Lumpsum | 12/10/2023 | TFC/23-24 /555 | 1,864 |
| 119 | Erection & Commission | Oriental Enterise Pvt Ltd | Lumpsum | 12/10/2023 |  | 13,000 |
| 120 | Erection & Commission | Taherali Fidahusain & Co | Lumpsum | 20/10/2023 | TFC/23-24 /594 | 2,332 |
| 121 | Feed Water Tank & LP Chemical Dosing System | Alfa Therm Engineers | Set | 10/04/2023 | ATE/2023- 24/01 | 9,10,000 |
| 122 | Fire Extinguishers | Ceasfire Industries Pvt Ltd | 14 | 20/08/2023 | DL092324 TIAR2250 | 6,54,492 |
| 123 | Floor Clearing Machine | Clicktech Retail Private Limited |  | 05/08/2023 | HYD8-464186 | 4,092 |
| 124 | Floor Clearing Machine | SA Field Marketing & Services |  | 12/08/2023 | KAR/VD/23- 24/037 | 1,70,000 |
| 125 | Flushing Tank 2 KL Envisol-2 | Arvind Envisol Ltd | 2 | 21/06/2023 | S402300015 | 20,223 |
| 126 | Flushing Tank 5 KL Envisol-2 | Arvind Envisol Ltd | 2 | 21/06/2023 | S402300015 | 50,580 |
| 127 | Fuel Handling System- Impact Crusher With Drive Unit, Fuel Screw Conveyor (Fsc 1) With Drive Unit- 1 No.; Fuel Bucket Elevator (Be 1) With Drive Unit- 1 No.; Storage Hopper 4 m3 With Level Sensor & With Short Support; Extra For Supporting Structure From Ground; Supply of Pin Gate; Fuel Screw Feeder (Fsc 2) With Drive Unit- 1 No. | Decon Equipments And Systems Private Limited | Set | 08/05/2023 | 62/23-24 | 27,00,000 |
| 128 | Geared Trolley 1 Ton Indef Make | Gode Engineering Pvt Ltd | 1 | 30/03/2023 | GST/2223/ 01232 | 8,462 |
| 129 | Geared Trolley 3 Ton Indef Make | Gode Engineering Pvt Ltd | 1 | 30/03/2023 | GST/2223/ 01232 | 12,325 |
| 130 | Ground Warp Beams (Q2 Quality) Having 800mm Dia | Bharat Beams Pvt Ltd | 24 | 17/05/2023 | BBPL/2023- 24/044 | 15,18,240 |
| 131 | Ground Warp Beams (Q2 Quality) Having 800mm Dia | Bharat Beams Pvt Ltd | 12 | 25/07/2023 | BBPL/2023- 24/127 | 7,59,120 |
| 132 | Groz Heavy Duty 6 Kg Grease Pump | Groz Net Industries | 1 | 26/04/2023 | GNYS- 1822 | 5,214 |
| 133 | Groz V Series Bucket Grease Pump | Sankalp | Journal | 20/05/2023 | GJ-2204366 495-2324 | 5,324 |
| 134 | Guide Roll with Mounting Assembly For 340 CM Wide Toyota JAT810 Airjet Terry Loom | Rabatex Industries | 24 | 11/04/2023 | 36-23/24 | 10,44,000 |
| 135 | HD Spiral Tank-2 Kl-3 Nos. 1.5 Kl-3 Nos. & 1 Kl- 2 Nos. | Arvind Envisol Ltd | 8 | 21/06/2023 | S402300014 | 2,67,688 |
| 136 | HD Spiral Tank- 25 Kl | Arvind Envisol Ltd | 2 | 21/06/2023 | S402300013 | 7,61,194 |
| 137 | High Speed Section Warping Machine- 672 Ends, Model JSW- Dia. 1250 Mm, Sr. No. JSS-001 | Jupiter Machineries | 1 | 20/05/2023 | JM/M/23- 24/014 | 45,00,000 |
| 138 | High Speed Direct Warping Machine- 672 Ends, Model J- 1250 Mm, Sr. No. JBW-379 | Jupiter Machineries | 1 | 13/06/2023 | JM/M/23- 24/016 | 45,00,000 |
| 139 | Hot Air Oven & Infra Color Dyeing Machine | R.B. Electronics And Engineering Pvt Ltd | 1 | 25/07/2023 | D747 | 1,32,000 |
| 140 | Hot Water Storage Tank 20 KL | Alfa Therm Engineers | 2 | 21/08/2023 | ATE/2023- 24/24 | 14,50,000 |
| 141 | Luwa Auto Control Type Humidification Plant for Weaving and Warping parts thereof with standard and essential accessories (Partial Shipment 1st Lot) | Luwa India Pvt Ltd | 1 | 28/07/2022 | 22-23/1371 | 2,10,000 |
| 142 | Humidification Plant | Site Visit | Journal | 10/08/2022 | 9 | 2,650 |
| 143 | Tadpatri 60 X 60- 111.35 Kg & 50 X 50- 80.6 Kg | Sagar Plastic | Lot | 24/01/2023 | 458 | 25,913 |
| 144 | HUMIDIFICATION PLANT- Rivets | Saifee Enterprises | 17 Pkt | 06/03/2023 | A000382 | 5,610 |
| 145 | HUMIDIFICATION PLANT- Threded Rod- 12 mm, Hex Nut, Bolt | Saifee Enterprises | Lot | 25/03/2023 | A000416 | 14,420 |
| 146 | Luwa Auto Control Type Humidification Plant for Weaving and Warping partss therof with standard and essential accessories (Partial Shipment 1st Lot) | Luwa India Pvt Ltd | 1 | 31/03/2023 | 22-23/4233 | 22,90,000 |
| 147 | HUMIDIFICATION PLANT- Nitrile Rubber Sheet 13 mm Class O Plain 53 Rools X 16.80 Sq. M Each & Adhesive K-414 (30 Ltr Pack) 4 Drum X 30 Ltr each | Velocityinsulation Solutions | Lot | 11/04/2023 | VIS/2023- 24/004 | 2,11,353 |
| 148 | Luwa Auto Control Type Humidification Plant for Weaving and Warping parts thereof with standard and essential accessories (Partial Shipment 2nd Lot) | Luwa India Pvt Ltd | 1 | 12/04/2023 | 23-24/0107 | 14,75,000 |
| 149 | Plant Room GI Door Masonry | Luwa India Pvt Ltd | 1 | 22/04/2023 | 23-24/0252 | 19,179 |
| 150 | Humidification Plant- Hex Nut, Bolt, Drill Bit | Saifee Enterprises | Lot | 02/05/2023 | A000067 | 23,990 |
| 151 | Humidification Plant- Threding Tap, Screw, Core Bit, Drill | Saifee Enterprises | Lot | 05/05/2023 | A000078 | 1,768 |
| 152 | Luwa Auto Control Type Humidification Plant for Weaving and Warping partss therof with standard and essential accessories (Partial Shipment 3rd Lot) | Luwa India Pvt Ltd | 1 | 23/05/2023 | 23-24/0657 | 25,000 |
| 153 | Hyundai Hand Pallet Truck- 2.5 Ton | Gode Engineering Pvt Ltd | 2 | 17/04/2023 | GST/2324/058 | 41,000 |
| 154 | Industrial Butterfly Valves | Sa Field Marketing & Services | 62 | 23/06/2023 | CRA/VD/23- 24/014 | 3,79,130 |
| 155 | Industrial Compressed Air Piping | KPT Piping Systems Pvt Ltd | Lot | 24/05/2023 | GST/0476/ 23-24 | 11,11,000 |
| 156 | Industrial Compressed Air Piping | KPT Piping Systems Pvt Ltd | Lot | 06/06/2023 | GST/0607/ 23-24 | 33,97,840 |
| 157 | Water Piping | KPT Piping Systems Pvt Ltd | Journal | 10/07/2023 | GST/0843/ 23-24 | 59,911 |
| 158 | Industrial Compressed Air Piping | Sigma Airtech Engineers | Journal | 12/07/2023 | SAE/23-24/ 0198 | 52,157 |
| 159 | Industrial Compressed Air Piping | Sigma Airtech Engineers | Journal | 13/07/2023 | SAE/23-24/ 0199 | 40,613 |
| 160 | Industrial Compressed Air Piping | KPT Piping Systems Pvt Ltd | Journal | 17/07/2023 | GST/0968/ 23-24 | 28,851 |
| 161 | Industrial Compressed Air Piping | KPT Piping Systems Pvt Ltd | Journal | 22/07/2023 | GST/1017/ 23-24 | 1,19,100 |
| 162 | Industrial Compressed Air Piping | Sigma Airtech Engineers | Journal | 24/07/2023 | SAE/23-24/ 0227 | 4,644 |
| 163 | Industrial Compressed Air Piping | Sigma Airtech Engineers | Journal | 28/07/2023 | SAE/23-24/ 0236 | 8,613 |
| 164 | Industrial Compressed Air Piping | KPT Piping Systems Pvt Ltd | Journal | 07/08/2023 | GST/1165/ 23-24 | 1,49,705 |
| 165 | Industrial Compressed Air Piping | KPT Piping Systems Pvt Ltd | Journal | 07/08/2023 | GST/1148/ 23-24 | 1,17,850 |
| 166 | Gasket For Industrial Compressed Piping | S.N.K. Enterprises | Journal | 16/08/2023 | 17195 | 23,381 |
| 167 | Material Returned | KPT Piping Systems Pvt Ltd | Journal | 11/09/2023 | 002/23-24 | - 3,28,165 |
| 168 | Industrial Compressed Air Piping | Taherali Fidahusain & Co | Journal | 14/09/2023 | TFC/23-24/ 475 | 9,559 |
| 169 | Installation of Insustrial Compressed Air Piping | KPT Piping Systems Pvt Ltd | Journal | 27/09/2023 | GST/1739/ 23-24 | 10,00,000 |
| 170 | Industrial Compressed Air Pipings Materials | KPT Piping Systems Pvt Ltd | Journal | 30/09/2023 | GST/1698/ 23-24 | 19,490 |
| 171 | Industrial Compressed Air Piping | Kpt Piping Systems Pvt Ltd | Journal | 01/10/2023 | GST/1447/ 23-24 | 6,22,821 |
| 172 | Industrial Compressed Air Piping | Kpt Piping Systems Pvt Ltd | Journal | 01/10/2023 | GST/1393/ 23-24 | 1,56,786 |
| 173 | Pump House | S.N.K. Enterprises | Journal | 10/10/2023 | 17396 | 4,201 |
| 174 | Industrial Compressed Air Piping | Jalgaon Gas Agency | Journal | 02/09/2023 | 2023-24/ JGA-0262 | 1,94,931 |
| 175 | Industrial Compressed Air Piping | Jalgaon Gas Agency | Journal | 02/09/2023 | 2023-24/ JGA-0263 | 81,475 |
| 176 | Industrial Compressed Air Piping | Jalgaon Gas Agency | Journal | 25/09/2023 | 2023-24/ JGA-0311 | 1,613 |
| 177 | Industrial Compressed Air Piping | Jalgaon Gas Agency | Journal | 04/10/2023 | 2023-24/ JGA-0337 | 7,563 |
| 178 | Industrial Compressed Air Piping | Jalgaon Gas Agency | Journal | 18/10/2023 | 2023-24/ JGA-0324 | 7,840 |
| 179 | Industrial Compressed Air Piping | Jalgaon Gas Agency | Journal | 20/10/2023 | 2023-24/ JGA-0366 | 975 |
| 180 | Industrial Valves:- 15 mm - (1/2) - 7 Nos. 25 mm - (1) - 23 Nos. 40 mm - (1-1/2) - 9 Nos. 50 mm - (2) - 26 Nos. 65 mm - (2-1/2) - 3 Nos. 80 mm - (3) - 2 Nos. 25 mm - (1) - 2 Nos. | Gupta Machinery Stores | Set | 19/06/2023 | 23GBI1313 | 4,76,500 |
| 181 | Industrial Valves:- 50 mm - (2) - 4 Nos. 200 mm - (8) - 3 Nos. 100 mm - (4) - 4 Nos. 20 mm - (3/4) - 17 Nos. 25 mm - (1) - 24 Nos. 65 mm - (2-1/2) - 5 Nos. | Gupta Machinery Stores | Set | 27/06/2023 | 23GBI1465 | 4,55,479 |
| 182 | Industrial Valves | Gupta Machinery Stores |  | 08/09/2023 | 23GBI2675 | 17,334 |
| 183 | Industrial Valves | Gupta Machinery Stores |  | 01/10/2023 | 23GBI2929 | 680 |
| 184 | Industrial Valves | Gupta Machinery Stores |  | 01/10/2023 | 23GBI2930 | 17,593 |
| 185 | Industrial Valves | Gupta Machinery Stores |  | 04/10/2023 | 23GBI3008 | 20,120 |
| 186 | Hot Air Oven & Infra Color Dyeing Machine | R.B. Electronics and Engineering Pvt Ltd |  | 25/07/2023 | D747 | 1,98,000 |
| 187 | SS 316 Grade Pipes for Dyeing Machines Connection | Ronak Tubes |  | 08/08/2023 | RT/228/2023 -24 | 2,28,500 |
| 188 | SS Pipes & Fittings for Dyeing Machines Connection | Bheema Engineering Company |  | 12/08/2023 | BEC/2022- 23/46 | 98,240 |
| 189 | SS Pipes & Fittings for Dyeing Machines Connection | Bheema Engineering Company |  | 19/08/2023 | BEC/2022- 23/47 | 2,11,992 |
| 190 | ISMB for Boiler | Agrawal Hardware Stores | 432.6 Kg | 14/06/2023 | AHS/23-24 /592 | 26,393 |
| 191 | Hydraulic Jack V5 | Gode Engineering Pvt Ltd | 1 | 31/03/2023 | GST/2223 /01238 | 46,670 |
| 192 | Laboratory Accessories | Dange Trading Co |  | 11/09/2023 | 513 | 1,831 |
| 193 | Laboratory Accessories | Dange Trading Co |  | 15/09/2023 | 529 | 2,624 |
| 194 | Laboratory Accessories | Dange Trading Co |  | 16/09/2023 | 531 | 312 |
| 195 | Laboratory Equipments | Paramount Instruments Pvt Ltd |  | 31/08/2023 | PIPL/23-24 /0270 | 7,50,000 |
| 196 | Length Cutting Machine | Om Textile Solution |  | 13/09/2023 | 42 | 28,00,000 |
| 197 | Length Hemming Machine | Om Textile Solution |  | 13/09/2023 | 42 | 33,00,000 |
| 198 | Machine & Tools | M.K. Machinery Corporation | Journal | 18/11/2022 | 469 | 1,475 |
| 199 | Machine & Tools | H H Tools Centre | Journal | 06/03/2023 | HHTC/22- 23/5336 | 73,069 |
| 200 | Angel Grinder, Chopsaw, Drill Machine, Grinding Wheel, Heat Gun, Rotary Hammer | N Deep & Sons | Set | 11/04/2023 | 14 | 24,352 |
| 201 | Machine & Tools | Rangoon Auto Parts | Journal | 11/04/2023 | RAP/23- 24-037 | 13,214 |
| 202 | Machine & Tools | Skyking Instruments | Journal | 19/04/2023 | 26876 | 49,950 |
| 203 | Vernier And Other Tools | Skyking Instruments |  | 16/08/2023 | 17216 | 15,700 |
| 204 | Machine & Tools | Taherali Fidahusain & Co |  | 19/09/2023 | TFC/23- 24/490 | 665 |
| 205 | Man Hole 600 Dia X 300lg | Vinay Industries | 1 | 16/03/2023 | VI/39/ 2022-23 | 18,000 |
| 206 | Man Hole 600 Dia X 500 Lg | Vinay Industries | 1 | 16/03/2023 | VI/39/ 2022-23 | 20,500 |
| 207 | Man Hole 900 Dia X 500lg | Vinay Industries | 1 | 16/03/2023 | VI/39/ 2022-23 | 29,000 |
| 208 | Motorised Beam Stocker Model Vm-401 | Rabatex Industries | 1 | 11/04/2023 | 36- 23/24 | 66,53,000 |
| 209 | MS Self Supported Chimney with Accessories | ALFA THERM ENGINEERS | 1 Set | 12/03/2023 | ATE/2022- 23/025 | 13,00,000 |
| 210 | MS Self Supported Chimney with Accessories (Total Height-38 Mtrs) | ALFA THERM ENGINEERS | 1 | 12/03/2023 | ATE/2022- 23/024 | 18,50,000 |
| 211 | MS Trolley 3000x1570 Qty.1 @22325 & SS Trolley 1800x1200 Qty 3 @55100 | Nimisha Engineering Works | - | 21/08/2023 | 83 | 22,325 |
| 212 | MS Trolley 3000x1570 Qty.1 @22325 & SS Trolley 1800x1200 Qty 3 @55100 | Nimisha Engineering Works | - | 24/08/2023 | 86 | 22,325 |
| 213 | Purchase of MS Trolley 3000x1570 Qty.1 @22325 & SS Trolley 1800x1200 Qty 3 @55100 | Nimisha Engineering Works | - | 05/10/2023 | 110 | 44,650 |
| 214 | MS Trolley Qty 2 | Nimisha Engineering Works | - | 11/10/2023 | 114 | 44,650 |
| 215 | MS Trolly 3000 x 1570 Qty 2, Sintex Box Trolly Qty2 | Nimisha Engineering Works | - | 15/10/2023 | 115 | 44,650 |
| 216 | MS Trolly 3000 x 1570 Qty 2, Sintex Box Trolly Qty2 | Nimisha Engineering Works | - | 19/10/2023 | 123 | 44,650 |
| 217 | Muti-Tier Storage Systems | Nilkamal Limited | Set | 08/06/2023 | 6105121693 | 8,65,000 |
| 218 | Pile Warp Beams (Q2 Quality) Having 1250mm Dia | BHARAT BEAMS PVT LTD | 24 | 17/05/2023 | BBPL/2023- 24/044 | 20,84,400 |
| 219 | Pile Warp Beams (Q2 Quality) Having 1250mm Dia | BHARAT BEAMS PVT LTD | 12 | 25/07/2023 | BBPL/2023- 24/127 | 10,42,200 |
| 220 | Pile Warp Beams (Q2 Quality) Having 1250mm Dia | BHARAT BEAMS PVT LTD | 12 | 27/08/2023 | BBPL/2023- 24/180 | 12,48,000 |
| 221 | Plc Base A.C. Servo Drive High Speed Sizing Machine, Model J-Dia. 1250, Sr. No. JKS-061 | Jupiter Machineries | 1 | 05/05/2023 | JM/M/23- 24/011 | 1,45,00,000 |
| 222 | 64 Spdls Rewinder Model (Double Sided ) M/C. Sr. No. 5256 | Peass Industrial Engineers Pvt Ltd | 1 | 18/07/2023 | A01/INM/47 | 13,25,000 |
| 223 | Rotary Screw Compressor Csdx 140 F/ 8.5 Bar, Sr. No. 3269 | Kaeser Compressors (India) Pvt.Ltd. | 1 | 20/05/2023 | PI10000 39990 | 21,20,000 |
| 224 | Roto Crates | Nilkamal Limited | 16 | 31/08/2023 | 61083 70785 | 1,52,000 |
| 225 | Roto Crates | Nilkamal Limited | 3 | 11/09/2023 | 61083 70920 | 28,500 |
| 226 | Electrical Hoist for Sizing Machine | Gode Engineering Pvt Ltd | 1 | 03/06/2023 | GST/23 24/0231 | 8,800 |
| 227 | Safetrack Bar Gi | Gode Engineering Pvt Ltd | 16 Mtrs | 02/06/2023 | GST/23 24/0231 | 25,600 |
| 228 | Ms Trolley 3000x1570 Qty.1 @22325 & Ss Trolley 1800x1200 Qty 3 @55100 | Nimisha Engineering Works |  | 05/10/2023 | 110 | 35,150 |
| 229 | Ms Trolly 3000x 1570 Qty 2, Sintex Box Trolly Qty2 | Nimisha Engineering Works |  | 15/10/2023 | 115 | 35,150 |
| 230 | Ms Trolly 3000x 1570 Qty 2, Sintex Box Trolly Qty2 | Nimisha Engineering Works |  | 19/10/2023 | 123 | 35,150 |
| 231 | Sludge Volute Press Of Capacity 20-25kg | Konark Fixtures Ltd | 1 | 04/05/2023 | IIN2300017 | 12,50,000 |
| 232 | Soft Starter | Vijay Engineering And Machinery Co |  | 30/08/2023 | SNP/1276 | 3,15,553 |
| 233 | Soft Starter Qty 2 | Vijay Engineering And Machinery Co |  | 06/09/2023 | SNP/1456 | 1,94,448 |
| 234 | MS Trolley 3000x1570 Qty.1 @22325 & Ss Trolley 1800x1200 Qty 3 @55100 | Nimisha Engineering Works |  | 21/08/2023 | 83 | 1,65,300 |
| 235 | MS Trolley 3000x1570 Qty.1 @22325 & Ss Trolley 1800x1200 Qty 3 @55100 | Nimisha Engineering Works |  | 24/08/2023 | 86 | 1,65,300 |
| 236 | Ss Trolley Qty 4 @55100/- | Nimisha Engineering Works |  | 08/09/2023 | 98 | 2,20,400 |
| 237 | SS Trolley Qty 4 @55100/- | Nimisha Engineering Works |  | 28/09/2023 | 106 | 2,20,400 |
| 238 | SS Trolley Qty 4 @55100/- | Nimisha Engineering Works |  | 28/09/2023 | 108 | 2,20,400 |
| 239 | Standard 5.5 Tph MDC and Aph with 150 Square Rav | Omkar Industries | 1 | 10/04/2023 | 5 | 8,00,000 |
| 240 | Thread Winding Machine | Fablook International Pvt Ltd | 1 | 14/09/2023 | 2023- 2024/500 | 11,500 |
| 241 | Transport Trolley F6 | Gode Engineering Pvt Ltd | 1 | 31/03/2023 | GST/22 23/01238 | 26,670 |
| 242 | Transport Trolley L6 | Gode Engineering Pvt Ltd | 1 | 31/03/2023 | GST/22 23/01238 | 34,670 |
| 243 | Transport Trolley Tl6 | Gode Engineering Pvt Ltd | 1 | 31/03/2023 | GST/22 23/01238 | 46,670 |
| 244 | Trolly 6 Mm Wire Guage with Wheels With Wire Mesh Cage | Nilkamal Limited |  | 16/10/2023 | 614559 6418 | 2,50,000 |
| 245 | Warp Beam Carrier Moel No VM-502 | Rabatex Industries | 1 | 11/04/2023 | 36- 23/24 | 2,33,000 |
| 246 | Warper Beam | Bharat Beams Pvt Ltd | 12 | 11/07/2023 | BBPL/2023 -24/114 | 12,48,000 |
| 247 | Water Pump | Sa Field Marketing & Services |  | 06/07/2023 | GRD/VD/23 -24/056 | 14,39,954 |
| 248 | Hydro Multi Water Pump | Sa Field Marketing & Services |  | 03/08/2023 | GRD/VD/23 -24/069 | 12,05,046 |
| 249 | Water Purifier Qty 7 | Ion Exchange India Ltd |  | 08/09/2023 | INVCMH12 31733 | 92,400 |
| 250 | Water Soften Plant 700kld | Konark Fixtures Ltd |  | 25/07/2023 | IIN2300154 | 10,01,000 |
| 251 | Water Tank Envisol-2 Kl | Arvind Envisol Ltd | 2 | 21/06/2023 | S402300 015 | 28,214 |
| 252 | Welding Machine Arc 200i | Alps Trading Co | 1 | 11/04/2023 | ATC/0088 /23-24 | 12,750 |
| 253 | Welding Machine Arc 400i | Alps Trading Co | 1 | 11/04/2023 | ATC/0088 /23-24 | 43,500 |
| 254 | Wire Rope Hoist 2 Ton | Gode Engineering Pvt Ltd | 1 | 02/06/2023 | GST/2324 /0231 | 2,20,000 |
| 255 | Kitchen Equipment | Shankar Refrigeration & Engineering | 12/08/2023 | Set | SRE/2324/205 | 7,32,450.00 |
| 256 | Dining Table for Canteen | Shankar Refrigeration & Engineering | 28/08/2023 | Set | SRE/2324/233 | 2,77,200.00 |
| 257 | Dish Washer Water Cooler & Gas Tilting Pan | Shankar Refrigeration & Engineering | 28/08/2023 | Set | SRE/2324/226 | 4,93,825.00 |
| 258 | Dining Table for Canteen | Shankar Refrigeration & Engineering | 30/08/2023 | Set | SRE/2324/236 | 2,26,800.00 |
|  |  |  |  |  | Total | 14,93,92,853 |

OBSERVATIONS: -

- During the date and time of our visit, the commercial production is going on.

- Installation of Fire Hydrant Line, Fire Pumps is in progress.

- Based on Site Visit the On Average work related to Plant & Machinery- Indigenous is 94% Completed.

- Total Cost incurred towards Plant & Machinery- Indigenous is Rs. 14,93,92,853/-.

#### 4.7.2 COST INCURRED TOWARDS PLANT & MACHINERY-IMPORTED: -

The Cost incurred toward Plant & Machinery- Imported till 23.10.2023 is as under: -

| S. No. | Particulars | Supplier | Qty | Date | Invoice No. | Basic Invoice Value (₹) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | AlROo24 continuous open-width airflow drying and softening machine (WORKING WIDTH 320 CM) | Biancalani SRL | 1 | 06/01/2023 | 21 | 1,75,51,800 |
|  |  | LC Charges |  | 31/03/2023 |  | 7,78,939 |
| 2 | Autolab Tubeless Robotic Dispenser | Data Color Asia Pacific (HK) Ltd. | Set | 22/07/2023 | SO677962 | 33,30,000 |
|  |  | LC Charges |  | 01/10/2023 |  | 4,17,354 |
| 3 | Compressed Air Filter F320KE 2NO | Kaeser Compressors (India) Pvt. Ltd. | 2 | 18/03/2023 | PI10000 38910 | 1,96,000 |
|  |  | Shipping & Clearing Charges |  | 31/03/2023 |  | 5,431 |
| 4 | Compressed air filter KF4 F320KA 2NO | Kaeser Compressors (India) Pvt. Ltd. | 2 | 18/03/2023 | PI10000 38910 | 1,96,000 |
|  |  | Shipping & Clearing Charges |  | 31/03/2023 |  | 5,431 |
| 5 | Condensate Drain ECO-Drain 13 for Air Compressors | Kaeser Compressors (India) Pvt.Ltd. | 1 | 18/03/2023 | PI10000 38910 | 33,000 |
|  |  | Shipping & Clearing Charges | Journal | 31/03/2023 |  | 914 |
| 6 | Fabric Dyeing Machine 1200KG, Model- TOWELTEC3-3T, Sr. No. 47040853 | Fongs National Dyeing and Finishing Machinery Co. Ltd | 1 | 25/04/2023 | FM-IN- 02740 | 1,51,16,451 |
|  |  | LC Charges | Journal | 30/06/2023 |  | 3,67,612 |
| 7 | Fabric Dyeing Machine 1600KG, Model- TOWELTEC3-4T, Sr. No. 47040854 | Fongs National Dyeing and Finishing Machinery Co. Ltd | 1 | 25/04/2023 | FM-IN- 02740 | 1,80,70,269 |
|  |  | LC Charges | Journal | 30/06/2023 |  | 4,39,445 |
| 8 | Fabric Dyeing Machine 800KG, Model- TOWELTEC3-2T, Sr. No. 47040852 | Fongs National Dyeing and Finishing Machinery Co. Ltd | 1 | 25/04/2023 | FM-IN- 02740 | 1,16,20,350 |
|  |  | LC Charges | Journal | 30/06/2023 |  | 2,82,592 |
| 9 | Flat Steel Healds 5.5 x 0.30 x 331 mm, Optifil eye 6.5 x 1.8 mm | GROZ-BECKERT ASIA PRIVATE LIMITED | 220000 Pcs | 12/12/2022 | 43900 00661 | 17,63,690 |
|  |  | Shipping & Clearing Charges | Journal | 31/03/2023 |  | 96,681 |
| 10 | Fongs Smart Centre Systems | Fongs National Dyeing and Finishing Machinery Co. Ltd | 1 | 25/04/2023 | FM-IN- 02740 | 26,73,930 |
|  |  | LC Charges | Journal | 30/06/2023 |  | 65,026 |
| 11 | KNOTMASTER AS/3 230V Universal Tying Machine for Tying all natural, Synthetic and Mixed Yarn with computer, Sr. No. 10171 | GROZ-BECKERT KG | 1 | 18/04/2023 | 11411 58764 | 25,24,500 |
|  |  | Shipping & Clearing Charges | Journal | 30/06/2023 |  | 65,978 |
| 12 | Schmaledura 510 Automatic Double Sided Sewing Installation for Home Textile- Max. Working Width Approx 120 CM, 2 Needle Chain Stitch Sewing Heads (2 X Stitch Type E 401) | CARL SCHMALE GmbH & Co. | 2 | 21/02/2023 | L202109281- IC001 | 1,59,93,650 |
|  |  | LC Charges | Journal | 30/06/2023 |  | 1,89,579 |
| 13 | PLC Based Open width / rope and squeezing machine with detwister | Bianco S.P.A. | 1 | 03/02/2023 | 119 | 1,47,75,750 |
|  |  | LC Charges | Journal | 31/03/2023 |  | 3,68,892 |
| 14 | PLC Controlled Dye Kitchen Management System | Color Service S R L | 1 | 24/02/2023 | 2023-FV2C 0000186 | 3,04,51,500 |
|  |  | LC Charges | Journal | 30/06/2023 |  | 5,54,639 |
|  |  | Color Service S R L |  | 29/09/2023 |  | 4,26,525 |
|  |  | Shipping & Clearing Charges | Journal | 01/10/2023 |  | 41,121 |
| 15 | Refrigeration Dryer SECOTEC TF 340 400/3/50 , Model TF 340, Sr. No. 1631 & 1632) | Kaeser Compressors (India) Pvt.Ltd. | 2 | 18/03/2023 | PI1000 038910 | 16,00,000 |
|  |  | Shipping & Clearing Charges | Journal | 31/03/2023 |  | 44,338 |
| 16 | Rotary Screw Compressor, Model DSD 205, (Sr. No. 4971 & 4972) | Kaeser Compressors (India) Pvt.Ltd. | 2 | 18/03/2023 | PI1000 038910 | 38,60,000 |
|  |  | Shipping & Clearing Charges | Journal | 31/03/2023 |  | 1,06,966 |
| 17 | Single Needle Locksmit | Toyotsu Machinery Corporation | Set | 08/09/2023 | S221482 | 12,18,228 |
|  |  | Shipping & Clearing Charges | Journal | 01/10/2023 |  | 1,22,524 |
| 18 | Toyota Airjet Shuttleless Loom Model 340 ES-EH-810 - 4 Colour Qty. 20. | Toyotsu Machinery Corporation | 20 | 10/11/2022 | S221482 | 11,78,45,000 |
|  |  | Shipping & Clearing Charges | Journal | 31/03/2023 |  | 22,14,282 |
| 19 | Toyota Airjet Shuttleless Loom Model 340 ES-EH-810 - 6 Colour Qty. 4 | Toyotsu Machinery Corporation | 4 | 10/11/2022 | S221482 | 2,43,33,400 |
|  |  | Shipping & Clearing Charges | Journal | 31/03/2023 |  | 4,57,219 |
| 20 | Two Thread Overlook Machine | Juki Singapore PTE Ltd. | Set |  | JIN/23-154RZ | 1,59,410 |
|  |  | Bank Charges | Journal |  |  | 16,033 |
|  |  |  |  |  | Total | 29,03,80,452 |

OBSERVATIONS: -

- During the date and time of our visit, the commercial production is going on.

- Installation of PLC Controlled Dye Kitchen Management System is pending.

- Based on Site Visit the On Average work related to Plant & Machinery- Imported is 95% Completed.

- Total Cost incurred towards Plant & Machinery- Imported is Rs. 29,03,80,452/-.

#### 4.8) COST INCURRED TOWARDS MISCELLANEOUS FIXED ASSET: -

The Cost incurred toward Miscellaneous Fixed Asset till 23.10.2023 is as under:-

| S No. | Machine Name | Qty. (No.) | Estimated Net Value (₹) | Basic Invoice Value (₹) | Remark |
| --- | --- | --- | --- | --- | --- |
| 1 | Furniture & Fixture | 1 | 10,00,000 | 34,09,685 | Ordered |
| 2 | Office Equipment |  |  | 8,16,570 |  |
| 3 | Air Conditioners | 1 | 50,00,000 |  | Ordered |
| 4 | Vehicles | 1 | 25,00,000 | 19,61,039 | Not ordered |
| 5 | Computer | 1 | 15,00,000 | 32,57,544 | Being taken as per requirement |
| 6 | Computer Software | 1 |  | 1,35,594 |  |
| 7 | Water Connection Charges | 1 |  | 1,65,586 |  |
|  |  | Total | 1,00,00,000 | 97,46,018 |  |

OBSERVATIONS: -

- Total Cost incurred towards Miscellaneous Fixed Asset is Rs. 97,46,018/-.

#### 4.9) COST INCURRED TOWARDS ELECTRICAL FITTINGS: -

The Cost incurred toward Electrical Fittings till 23.10.2023 is as under:-

| S. No. | Particulars | Supplier | Qty | Date | Invoice No. | Basic Invoice Value (₹) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Electrical Materials | Opening Balance | Lot | 01/04/2022 |  | 15,835 |
| 2 | PCC Outdoor type, double door Panel & Metering Panel along with MCCB 250A TP | Kothari Power Solutions Pvt Ltd | Set | 02/04/2022 | KPSPL/22-23/17 | 1,20,000 |
| 3 | Journal | TDS on Contract @2% | - | 05/04/2022 | W/22-23/1 | 40,000 |
| 4 | Electrical Materials | Shri Swami Samarth Traders | Lot | 21/10/2022 | 8967 | 3,664 |
| 5 | Electrical Materials | Shri Swami Samarth Traders | Lot | 07/11/2022 | 8988 | 4,829 |
| 6 | Supply, Installation, Testing, Comm. | Kothari Power Solutions Pvt Ltd | LS | 10/11/2022 | KPSPL/22-23/2140 | 1,45,572 |
| 7 | MCB 32 A DP 7.5 KA C Curve-10 Nos.; MCB Channel-2 Mtrs; Wire 4 Sq. mm- 100 Mtrs; Copper Flexible Cable 4 C X 10 Sq. mm - 200 Mtrs | Kothari Power Solutions Pvt Ltd | LS | 17/11/2022 | KPSPL/22-23/2217 | 81,980 |
| 8 | Electrical Materials | Shri Swami Samarth Traders | Lot | 22/11/2022 | 9011 | 5,193 |
| 9 | Sigma 200 W V1 LED Floodlight 5700K | Kothari Power Solutions Pvt Ltd | 3 | 29/11/2022 | KPSPL/22-23/2442 | 13,500 |
| 10 | PVC Pipes, Bend etc | Shri Swami Samarth Traders | Lot | 08/12/2022 | 43 | 15,204 |
| 11 | Capacitor | Subodhan Engineers (Pune) Pvt Ltd | 3 | 27/12/2022 | 2021/22-23 | 6,750 |
| 12 | Sigma 200 W V1 LED Floodlight 5700K | Kothari Power Solutions Pvt Ltd | 1 | 01/01/2023 | KPSPL/22-23/2443 | 4,500 |
| 13 | Venia Switch, LED Bulb, PVC tape, Batten Holder, Cables, etc | Kothari Power Solutions Pvt Ltd | Lot | 01/01/2023 | KPSPL/22-23/3033 | 12,522 |
| 14 | Al Feruls 120 Sq. mm & 70 Sq. mm and PVC Tape | Kothari Power Solutions Pvt Ltd | 16 | 08/01/2023 | KPSPL/22-23/3139 | 215 |
| 15 | Building CWIP | Being CGST & SGST Amount for Building Material Transferred to Building CWIP. (Steel - GST Block Credit as Per Section 17 (5)) for the Period 01/10/2022 to 31/12/2022 |  | 31/03/2023 |  | -28,890 |
| 16 | Electrical Materials | Gopal Sales Corporation | Lot | 04/04/2023 | CR-0014/23-24 | 71,222 |
| 17 | Precision 25 mm Bend | Gopal Sales Corporation | 105 | 10/04/2023 | CR-0064/23-24 | 766 |
| 18 | Polycab Wire | Concept Incorporation | Lot | 11/04/2023 | CI/23-24/43 | 78,150 |
| 19 | 2.5 Sq. mm Wire 100 M Red Polycab | Concept Incorporation | 3 Coils | 12/04/2023 | CI/23-24/44 | 6,228 |
| 20 | Cables | Concept Incorporation | 1825 Mtrs | 13/04/2023 | CI/23-24/78 | 4,79,695 |
| 21 | BRP333 LED84-46 Pcs & BN 021 LED-101 Pcs | Premiere Electrical Solutions LLP | 147 | 14/04/2023 | PESL/023/23-24 | 1,79,070 |
| 22 | Armd Cables | Concept Incorporation | 564 Mtrs | 14/04/2023 | CI/23-24/79 | 1,69,593 |
| 23 | Cables | Concept Incorporation | Lot | 14/04/2023 | CI/23-24/80 | 1,64,929 |
| 24 | Precision 25 mm Saddle | Gopal Sales Corporation | 200 | 15/04/2023 | CR-0098/23-24 | 940 |
| 25 | Precision PWM Line Conditioner | TSI Power Pvt Ltd | 7 | 20/04/2023 | 2324TSI0074 | 26,00,000 |
| 26 | LED Tube & Bulbs | Premiere Electrical Solutions Llp | 1020 Pcs | 21/04/2023 | PESL/047/23-24 | 3,48,310 |
| 27 | GI Perforated Cable Tray | Hutaib Electricals | 1250 Mtrs | 21/04/2023 | HE/56/23-24 | 6,99,392 |
| 28 | PCC Panel Joint 1 & 2, By pass Changeover Switch-1 & 2, 5 to 7 | Tenco Systems & Switchgears Pvt Ltd | 6 | 21/04/2023 | TSSG/23-24/8 | 18,05,749 |
| 29 | PDB-1 to 7, By Pass Changeover Switch-3 & 4, ATS Panel | Tenco Systems & Switchgears Pvt Ltd | 10 | 21/04/2023 | TSSG/23-24/7 | 8,94,524 |
| 30 | 11 kV VCB Panel, Indoor, Sr. No. 36 & 37 | Power Control Electro Systems Pvt Ltd | 2 | 22/04/2023 | GST/23-24/38 | 8,15,000 |
| 31 | BY225P LED100S CW WB PSU FG GR V1 | Premiere Electrical Solutions Llp | 42 | 27/04/2023 | PESL/070/23-24 | 1,97,400 |
| 32 | Polycab Wire | Concept Incorporation | 30 Coils | 28/04/2023 | CI/23-24/271 | 76,187 |
| 33 | PVC Tapes | Concept Incorporation | 60 Nos. | 28/04/2023 | CI/23-24/272 | 534 |
| 34 | Cu & Al Armd Cables | Concept Incorporation | 1760 Mtrs | 29/04/2023 | CI/23-24/282 | 11,25,517 |
| 35 | Aluminium Flat armd Cable 3C X 185 Sqmm (Polycab make) | Concept Incorporation | 295 Mtrs | 03/05/2023 | CI/23-24/311 | 2,84,233 |
| 36 | Aluminium Flat armd Cable 3C X 185 Sqmm (Polycab make) | Concept Incorporation | 355 Mtrs | 03/05/2023 | CI/23-24/312 | 3,42,043 |
| 37 | 1200 mm Spido ES Brown | Concept Incorporation | 24 | 03/05/2023 | CI/23-24/324 | 31,176 |
| 38 | Electrical Materials | Jyoti Enterprises | Lot | 04/05/2023 | J-ENT/275 | 1,74,285 |
| 39 | Fast Electrode Earthing | Fast Electrode | 107 | 05/05/2023 | 23-24/0017 | 3,57,200 |
| 40 | ESE Lighting Arrestor, 2 Digit Transeient Event | Fast Electrode | Set | 09/05/2023 | 23-24/0018 | 2,40,000 |
| 41 | Electrical Materials | Gopal Sales Corporation | Lot | 09/05/2023 | CR-0283/23-24 | 52,578 |
| 42 | Electrical Materials | Gopal Sales Corporation | Lot | 09/05/2023 | CR-0284/23-24 | 1,08,524 |
| 43 | Cables | Concept Incorporation | Lot | 10/05/2023 | CI/23-24/428 | 3,70,623 |
| 44 | ABB VTPN 4 Way, ABB SP MCB 2 Amp, ABB DP, ABB MCCB | Jyoti Enterprises | Lot | 10/05/2023 | J-ENT/337 | 1,18,841 |
| 45 | Plug & Socket DB 20 amp Legrand 507811 | Gopal Sales Corporation | 53 | 18/05/2023 | CR-0393/23-24 | 56,816 |
| 46 | Gland, Lugs, Electrical Fittings | Concept Incorporation | Lot | 19/05/2023 | CI/23-24/474 | 36,239 |
| 47 | Polycab Wire | Concept Incorporation | 41 Coils | 19/05/2023 | CI/23-24/473 | 88,869 |
| 48 | Cable Tie & PVC Tape | Gopal Sales Corporation | Lot | 22/05/2023 | CR-0433/23-24 | 4,118 |
| 49 | ABB TP MCB 50 A | Jyoti Enterprises | 15 | 30/05/2023 | J-ENT/544 | 14,175 |
| 50 | Garware Screw, Nut, Thread Locker & Welding Goggles | Taherali Fidahusain & Co | Lot | 01/06/2023 | TFC/23-24/179 | 2,036 |
| 51 | Gland & Lugs | Concept Incorporation | Lot | 02/06/2023 | CI/23-24/648 | 15,095 |
| 52 | Cables | Concept Incorporation | Lot | 02/06/2023 | CI/23-24/647 | 13,44,356 |
| 53 | Legrand 3 Mod. & 6 Mod. & Mylinc USB Charges | Gopal Sales Corporation | 232 | 02/06/2023 | CR-0532/23-24 | 51,780 |
| 54 | Gland & Lugs | Concept Incorporation | 812 Nos. | 03/06/2023 | CI/23-24/664 | 1,16,846 |
| 55 | DN296B LED-131 Pcs & SP780P LED-4 Pcs | Premiere Electrical Solutions LLP | 135 | 06/06/2023 | PESL/158/23-24 | 1,12,250 |
| 56 | GI Flat 50 X 5 - 4040 Kg & Copper Strip 25 X 3- 129 Kg | Jyoti Radio & Electricals | Lot | 07/06/2023 | JRE-2512 | 3,80,911 |
| 57 | BGP300 LED28 757 PSU PC IN S1 | Premiere Electrical Solutions LLP | 5 | 10/06/2023 | PESL/180/23-24 | 36,000 |
| 58 | ABB Spreader Kit XT1 3P 6 Pcs | Jyoti Enterprises | 3 | 13/06/2023 | J-ENT/656 | 3,144 |
| 59 | Gland, Lugs, Electrical Fittings | Concept Incorporation | 328 Nos. | 15/06/2023 | CI/23-24/801 | 7,696 |
| 60 | Glands | Concept Incorporation | 12 Nos. | 24/06/2023 | CI/23-24/891 | 8,169 |
| 61 | Mylinc USB Charges | Gopal Sales Corporation | 50 | 26/06/2023 | CR-0761/23-24 | 15,400 |
| 62 | PVC Tape, Fan Clamp. Precision 25 mm Bend | Gopal Sales Corporation | 140 | 29/06/2023 | CR-0814/23-24 | 1,728 |
| 63 | Journal | INPUT CGST | - | 30/06/2023 | 30.6.2023 | 12,03,212 |
| 64 | Material Returned | Concept Incorporation | Set | 04/07/2023 | CN/23-24/235 | -570 |
| 65 | Electrical Materials | Concept Incorporation | Set | 05/07/2023 | CI/23-24/985 | 28,579 |
| 66 | Electrical Materials | Concept Incorporation | Set | 05/07/2023 | CI/23-24/986 | 15,372 |
| 67 | Electrical Materials | Concept Incorporation | Set | 11/07/2023 | CI/23-24/1042 | 48,912 |
| 68 | Hybrid APFC Panel 500 KVAR | Subodhan Engineers (Pune) Pvt Ltd | Set | 16/07/2023 | 23-24/532 | 9,00,000 |
| 69 | Electrical Cables | Concept Incorporation | Set | 19/07/2023 | CI/23-24/1127 | 1,07,504 |
| 70 | Gland | Concept Incorporation | Set | 19/07/2023 | CI/23-24/1128 | 6,189 |
| 71 | Cables | Concept Incorporation | Set | 19/07/2023 | CI/23-24/1129 | 68,432 |
| 72 | Cables | Concept Incorporation | Set | 19/07/2023 | CI/23-24/1130 | 860 |
| 73 | Electrical Materials | Gopal Sales Corporation | Set | 27/07/2023 | CR-1087/23-24 | 6,695 |
| 74 | cable marker | Vardayani Enterprises | Set | 31/07/2023 | MH-598065275-2324 | 420 |
| 75 | 2.2 mm Insulating Mat Size 1 mtr X 10 mtr X 7 nos Qty 70 mtr | Vardhman Hoses Pvt Ltd | Set | 05/08/2023 | VHPL/23-24/1449 | 35,000 |
| 76 | Supplies And Installation Work at Amravati Site | Panchal Switchgears Pvt Ltd | Set | 05/08/2023 | PSPL/23-24/115 | 78,773 |
| 77 | Switchboard Panel Lt Schneider Make 2500A Bbt Qty. 1 | Panchal Switchgears Pvt Ltd | Set | 07/08/2023 | PSPL/23-24/114 | 5,20,000 |
| 78 | Cables | Concept Incorporation | Set | 11/08/2023 | CI/23-24/1399 | 40,096 |
| 79 | Shock Treatment Chart Qty 5 & Hand Glowa 11 kV Qty 2 | Metro Electrical & Industrial Agencies | Set | 11/08/2023 | CM-02054 | 2,200 |
| 80 | Solar Modem | Shubh Enterprises | Set | 11/08/2023 | M29 | 15,500 |
| 81 | Electrical Installations | Concept Incorporation | Set | 18/08/2023 | CI/23-24/1449 | 35,470 |
| 82 | Electrical Installations | Concept Incorporation | Set | 18/08/2023 | CI/23-24/1450 | 10,557 |
| 83 | MCBS | Jyoti Enterprises | Set | 25/08/2023 | J-ENT/1316 | 18,456 |
| 84 | Electrical Installations | Concept Incorporation | Set | 26/08/2023 | CI/23-24/1519 | 6,458 |
| 85 | Electrical Installations | Gopal Sales Corporation | Set | 31/08/2023 | CR-1418/23-24 | 50,790 |
| 86 | HT 11 kV Overhead Line & Two Polls Structure Installation Work | Rachit Enterprises | Set | 01/09/2023 | REA/B/23/16 | 2,50,000 |
| 87 | Electrical Parts | Taherali Fidahusain & Co | Set | 02/09/2023 | TFC/23-24/431 | 13,934 |
| 88 | Electrical Installations Lab Canteen & Dyeing | Gopal Sales Corporation | Set | 06/09/2023 | CR-1454/23-24 | 15,768 |
| 89 | Camera Cable Installations | Gopal Sales Corporation | Set | 08/09/2023 | CR-1484/23-24 | 6,089 |
| 90 | Electrical Installations | S.N.K. Enterprises | Set | 09/09/2023 | 17327 | 1,850 |
| 91 | Electrical Installations For Biancalani Dyeing , Compressor, ETP & Lab | Gopal Sales Corporation | Set | 12/09/2023 | CR-1527/23-24 | 5,514 |
| 92 | Electrical Installations | Concept Incorporation | Set | 15/09/2023 | CI/23-24/1731 | 1,29,555 |
| 93 | Electrical Installations | Gopal Sales Corporation | Set | 21/09/2023 | CR-1589/23-24 | 17,136 |
| 94 | Electrical Installations | Taherali Fidahusain & Co | Set | 23/09/2023 | TFC/23-24/508 | 5,021 |
| 95 | Electrical Installations | Concept Incorporation | Set | 01/10/2023 | CI/23-24/1819 | 45,830 |
| 96 | 160 KVA DG Set with Auto Logic Panel | Sreeja Engineering Services | Set | 04/10/2023 | 59 | 10,55,085 |
| 97 | Electrical Installations | Concept Incorporation | Set | 08/10/2023 | CI/23-24/1978 | 12,000 |
| 98 | Electrical Installations | Concept Incorporation | Set | 14/10/2023 | CI/23-24/2068 | 40,770 |
| 99 | Electrical Installations | Gopal Sales Corporation | Set | 15/10/2023 | CR-1733/23-24 | 39,384 |
| 100 | CC Camera & Accessories | Ahdityaa Enterprises | Set | 19/10/2023 | AE/SL/23-24/833 | 25,65,665 |
| 101 | Electrical Installations | Concept Incorporation | Set | 19/10/2023 | CI/23-24/2118 | 27,498 |
| 102 | Electrical Installations | Gopal Sales Corporation | Set | 20/10/2023 | CR-1909/23-24 | 12,302 |
|  |  |  |  |  | Total | 2,19,71,514 |

OBSERVATIONS: -

- Based on Site Visit the on Average work related to Electrical Fittings is 95% Completed.

- Total Cost incurred towards Electrical is Rs. 2,19,71,514/-.

#### 4.10) ADVANCE PAID TO SUPPLIER: -

The advance paid to supplier till 23.10.2023 as per CA Certificate is Rs. 1,87,38,182/-.

#### 4.11) PREOPERATIVE EXPENSES: -

The Preoperative Expenses as per CA Certificate till 23.10.2023 is ₹ 3,81,40,944/-

#### 4.12) GST: -

As per CA Certificate and Ledger provided by Company the GST paid till 23.10.2023 is 
₹ 3,98,45,786/-

#### 4.13) SUMMARY OF TOTAL COST INCURRED TOWARDS PROJECT: -

Summary for Cost incurred toward project till 23.10.2023 is as under:-

| S. No | Particular of Project | Estimated Project Cost (Rs. in Lakhs) | Cost incurred till 30.06.2023 (Rs. in Lakhs) |
| --- | --- | --- | --- |
| 1 | Land & Development | 0* | 94.31 |
| 2 | Buildings | 0** | 2,033.71 |
| 3 | Plant & Machinery-Indigenous | 973.90 | 1,493.92 |
| 4 | Plant & Machinery-Imported | 3,022.00 | 2,903.80 |
| 5 | Miscellaneous Fixed Asset | 100 | 97.46 |
| 6 | Electrical Fittings | 112.1 | 219.71 |
| 7 | Contingencies | 210.4 | - |
| 8 | Preoperative Expenses | 393.42 | 381.41 |
| 9 | Advance Paid to Supplier | - | 187.38 |
| 10 | GST | - | 398.46 |
|  | Total | 4,811.82 | 7,810.16 |

OBSERVATIONS: -

- The expenses for the civil work of the factory building will be borne by the company from its own sources and Cost for the same was not considered in project cost.

- Cost of Plant & Machinery- Indigenous & Imported and Electrical Installation is increased due to reason mention in our previous LIE report for the quarter ended at 30.06.2023.

- Cost incurred toward total project is Rs. 7,810.16 Lakhs.

- PHOTOGRAPHS

- NOTES, LIMITATIONS, DISCLAIMERS & CAVEATS

#### Notes, Limitations, Disclaimers & Caveats forms important part of the report.

- The Lender’s independent engineer report is made to review the progress of project activities and to prepare the detail report outlining all activities completed along with the status.

- Our Engineer has visited the project site 2nd Time on 23.10.2023 with a view to ascertain and certify the quantity and amount of work progressively undertaken by the borrower till 23.10.2023.

- LIE progress report is based on the physical verification of the site on 23.10.2023, invoices provided, discussions held with the Plant Head of the Company and information and explanation given & documents provided. Accordingly, the percentage of work of completion of project activities is worked out. The photographs are enclosed.

- The Company has provided the necessary documents. LIE has referred the same for preparation of report.

- During the date and time of our visit to the project site, Commercial Production is going on. The execution of project activities like construction of Drainage, Compound Wall, finishing work of Male and Female Quarters, Installation of Data Colour Kitchen, Fire Hydrant System and Weighbridge was going on and it can be clearly seen from the photographs enclosed.

- The Credit details in other bank accounts are not verified by us and we have relied on documents issued by the party.

- Our report does not cover verification of ownership, title clearance, or legality and subject to adequacy of engineering / structural design.

- Our report does not cover verification of ownership, title clearance, or legality and subject to adequacy of engineering / structural design. The report is delayed as compared with the visit date because of delay in receipt of documents.

- It should be noted that VCIPL’s project progress assessments are based upon the facts and evidence available at the time of assessment and the documents provided.  The lenders should do the progress assessment from time to time.

- The legal documents pertaining to the ownership of the properties has been referred to on its face value and that is presumed that Bank /financer have got the same verified through its legal counsel. We do not certify the veracity of the documents. This report does not certify valid or legal or marketable title of any of the parties over the property. Our report does not cover verification of ownership, title clearance, or legality and subject to adequacy of engineering / structural design.

- Our report is only for the use of the party to whom it is addressed, and no responsibility is accepted to any third party for the whole or any part of its contents.

- It is presumed that the soft copies of documents are taken from the originals duly tested and verified at the party’s end.

- The progress report is made based on our visit, information furnished, discussions, documents made available at the time of visit. We presume optimistically that the project assessed by us will be a top success project.  In case on a future date if the project does not come up to an expectation of the lenders and borrowers, due to various factors i.e., socio, economic and political factors in this region and country, any decrease in projections, profits, non-repayment of regular installments of loan and interest thereon, the VCIPL should not be held responsible on a future date. The market scenario in India at particular and the whole world at large is at volatile trend since last many months and future cannot be anticipated as of date.

- Our report should be read along with disclaimers. We have given our opinion as the percentage of work completion of the project as on date of visit to the project site.

- SUMMARY

#### 7.1) WORK COMPLETION FOR THE PROJECT: -

Location wise the progress of the project is as under: -

| S. No. | Activities | % of Work Completion |
| --- | --- | --- |
|  | Project Documentation |  |
| 1 | Detailed Project Report | 100% |
|  | Statutory Clearances |  |
| 2 | Building Plan (initial approval) | 100% |
| 3 | Pollution Control Board - Consent to establish | 100% |
| 4 | Pollution Control Board - Consent to operate | 50% |
| 5 | Power Sanction | 100% |
| 6 | Insurance | 100% |
| 7 | Bank Loan Sanction | 100% |
| 8 | Disbursement – Term loan (Fund + non-Fund) | 94% |
|  | Site Setup |  |
| 9 | Start of Payments | 100% |
| 10 | Registrations PAN Card, GST, IEC, IEM, etc. | 100% |
| 11 | Power –for construction purpose | 100% |
| 12 | Water - for construction purpose | 100% |
| 13 | Bore Well | 100% |
| 14 | Office setup at Site | 80% |
| 15 | Recruitment | Ongoing |
|  | Civil Work |  |
|  | Boiler-1 (B) |  |
| 16 | Foundation | 100% |
| 17 | Flooring Work | 100% |
| 18 | Brick Work | 100% |
| 19 | Roof | 100% |
| 20 | Finishing | 100% |
|  | Ladies-1 (Quarter) (G+2) |  |
| 21 | Foundation | 100% |
| 22 | Flooring Work | 100% |
| 23 | Brick Work | 100% |
| 24 | Roof | 100% |
| 25 | Finishing | 80% |
|  | Male-1 (Quarter) (G+2) |  |
| 26 | Foundation | 100% |
| 27 | Flooring Work | 100% |
| 28 | Shed Erection | 100% |
| 29 | Roof | 100% |
| 30 | Finishing | 70% |
|  | Pump-1 (Room) |  |
| 31 | Foundation | 100% |
| 32 | Flooring Work | 100% |
| 33 | Brick Work | 100% |
| 34 | Roof | 100% |
| 35 | Finishing | 80% |
|  | Warehouse-1 (B) (G+ Part 1st Floor) |  |
| 36 | Foundation | 100% |
| 37 | Flooring Work | 100% |
| 38 | Brick Work | 100% |
| 39 | Roof | 100% |
| 40 | Finishing | 90% |
|  | Misc. Civil Work |  |
| 41 | Compound Wall | 80% |
| 42 | Road | 50% |
| 43 | Infrastructure | 50% |
| 44 | Drainage | 60% |
|  | Plant & Machinery |  |
|  | Imported Plant & Machinery |  |
| 45 | Vendor Selection | 100% |
| 46 | Purchase Order/ Contract | 100% |
| 47 | Delivery | 100% |
| 48 | Erection | 95% |
| 49 | Installation | 95% |
| 50 | Electrification | 95% |
| 51 | Trials & Commissioning | 95% |
|  | Indigenous Plant & Machinery |  |
| 52 | Vendor Selection | 100% |
| 53 | Purchase Order/ Contract | 100% |
| 54 | Delivery | 100% |
| 55 | Erection | 90% |
| 56 | Installation | 90% |
| 57 | Electrification | 90% |
| 58 | Trials & Commissioning | 90% |
|  | Miscellaneous Fixed Asset |  |
| 59 | Vendor Selection | 100% |
| 60 | Purchase Order/ Contract | 80% |
| 61 | Delivery | 80% |
| 62 | Erection | 80% |
| 63 | Installation | 80% |
| 64 | Electrification | 80% |
| 65 | Trials & Commissioning | 80% |
|  | Electrical Fittings |  |
| 66 | Vendor Selection | 100% |
| 67 | Purchase Order/ Contract | 100% |
| 68 | Delivery | 100% |
| 69 | Erection | 95% |
| 70 | Installation | 95% |
| 71 | Electrification | 95% |
| 72 | Trials & Commissioning | 95% |
|  | Total Work Completed | 92% |

#### 7.2) DCCO: -

During the date and time of our Site visit on 23.10.2023, we observed that the Commercial Production is going on at the rate of 60 to 50% of Installed Capacity.

During the date and time of our site visit on 23.10.2023, following work related to Project is balance: -

- Finishing Work related for Ladies-1 (Quarter), Male-1 (Quarter), Pump-1 (Room), Warehouse-1 (Main Plant Building), Drainage, Road, and Compound Wall.

- Installation of PLC Controlled Dye Kitchen Management System and Fire Fighting Equipment is pending.

- Internal Fining work of Admin Block in main Plant Building is still pending.

- Weigh Bridge (Addition in the Project).

STATUS OF STATUTORY CLEARANCES AND APPROVALS: -

Status of Approvals and clearances is as under: -

| S. No. | Approvals / Certifications | Approving / Sanctioning Authority | Status |
| --- | --- | --- | --- |
| 1 | Date of Incorporation | Registrar, Mumbai, Ministry of Corporate Affairs, GOI | Incorporated on 21.06.2016. |
| 2 | PAN Card | Income Tax, GOI | PAN Number-ABDFM1686N |
| 3 | GST Certificate | GOI | Registered on 01.07.2017, GSTN Number- 27ABDFM1686N1ZQ |
| 4 | Udyam Registration Certificate | MSME, GOI | Registered on 06.12.2021, Registration No. UDYAM-MH-18-0113799 |
| 5 | Certificate of Importer - Exporter Code | Directorate General of Foreign Trade | Obtained. Importer - Exporter Code 0317507605. |
| 6 | Land Possession | Provided vide possession receipt issued by MIDC dated 14.12.2017 |  |
| 7 | Consent to establish | Maharashtra Pollution Control Board | Obtained vide Consent No. Format 1.0/BO/CAC-Cell/CAC-UAN No. 37617/ CAC1810000566 dated 12.10.2018 valid till commission of the unit or 5 years whichever is earlier. |
| 8 | Provisional Fire NOC | MIDC | Obtained |
| 9 | Temporary Power Connection | MSEDCL | Obtained |
| 10 | Temporary Water Connection | MIDC | Obtained |
| 11 | Permanent Electricity Connection | MSEDCL | Obtained |
| 12 | Building Plan approval | MIDC | Revised Plan approval is pending |
| 13 | Machinery Layout Plan | Director of Industrial Safety & Health | Pending |
| 14 | Drainage completion certificate | MIDC | Pending |
| 15 | Building Completion Certificate | MIDC | Pending |
| 16 | IBR Approvals | Directorate of Boilers | Pending |
| 17 | Final Fire Department NOC | MIDC | Pending |
| 18 | Consent to Operate | MPCB | Pending |
| 19. | Factory License | Director of Industrial Safety & Health | Pending |
| 20. | Insurance |  | Pending |
| 21 | Weigh Bridge |  | Pending |

OBSERVATIONS: -

- We are at opinion that, the Company must take the pending approval for the continuous operation of the Plant.

We are at option the Company has started the Commercial Operation and the Date of Commencement of Commercial Operation (DCCO) is 25.09.2023 subjected to getting the pending statutory Approval and Clearances.

- OPINION

Based on the physical inspection and verification of project site, information and explanation given to us and the documents referred by us; we are of the opinion that the progress of 9.5 MTPD Terry Towel manufacturing facility at Plot No. T-24, Additional Amravati Textile Park, MIDC Nandgaon Peth, Amravati, PIN Code-444 901, State- Maharashtra, County-India belonging to M/s. Mahi Terry Cot LLP is 92 % completed till 23.10.2023 as per our information provided by the party, observation made during LIE 2nd visit to the project site on 23.10.2023 subject to observations made in the main report.

Date:-03.01.2024

Place:- Mumbai

For Vastukala Consultants (I) Pvt. Ltd.

Umang A Patel

Registered Valuer Chartered Engineer (India) Reg. No. IBBI/RV/04/2019/10803