## Sheet1
|  | As per approved Plan |  |  |  |  | As per Site Inspection
Name of Strucutre | Floor | Width | Length | Area in Sq. M. | Area in Sq. Ft. | Name of Strucutre | Width | Length | Area in Sq. Ft. | Area in Sq. M. | Difference in Sq. M. | Difference in Sq. Ft. | Roofing | Work progress Status | Remarks
Layour Shed | Ground Floor | 11.58 | 99.085 | 1147.4043 | 12351 | Tin Shed 1 | 42 | 325 | 13650 | 1268.1159 | 120.7116 | 1299 | R.C.C Slab | Old | Additional Area Difference
| First Floor | 11.58 | 99.085 | 1147.4043 | 12351 |  | 42 | 325 | 13650 | 1268.1159 | 120.7116 | 1299 | A.C. Sheet | Old | Additional Area Difference
Layour Shed | Ground Floor | 11.58 | 99.085 | 1147.4043 | 12351 | Tin Shed 2 | 42 | 325 | 13650 | 1268.1159 | 120.7116 | 1299 | R.C.C Slab | Old | Additional Area Difference
| First Floor | 11.58 | 99.085 | 1147.4043 | 12351 |  | 42 | 325 | 13650 | 1268.1159 | 120.7116 | 1299 | A.C. Sheet | Old | Additional Area Difference
Layour Shed | Ground Floor | 11.58 | 99.085 | 1147.4043 | 12351 | Tin Shed 3 | 42 | 325 | 13650 | 1268.1159 | 120.7116 | 1299 | R.C.C Slab | New | Additional Area Difference
| First Floor | 11.58 | 99.085 | 1147.4043 | 12351 |  | 42 | 325 | 13650 | 1268.1159 | 120.7116 | 1299 | A.C. Sheet | New | Additional Area Difference
Layour Shed | Ground Floor | 11.58 | 99.085 | 1147.4043 | 12351 | Tin Shed 4 | 42 | 325 | 13650 | 1268.1159 | 120.7116 | 1299 | R.C.C Slab | New | Additional Area Difference
| First Floor | 11.58 | 99.085 | 1147.4043 | 12351 |  | 42 | 325 | 13650 | 1268.1159 | 120.7116 | 1299 | A.C. Sheet | Under Construction | Additional Area Difference | Brick work is in progress
Feed Godown | Ground Floor | 15.24 | 30.48 | 464.5152 | 5000 | Feed Godown & Plant Tin Shed | 60 | 80 | 4800 | 445.9309 | -18.5843 | -200 | A.C. Sheet | Old | Less Area Difference
Electric Room | Ground Floor | 6.1 | 6.1 | 37.21 | 401 | [9 empty] | Not Constructed on Site
Power House | Ground Floor | 9.14 | 9.14 | 83.5396 | 899 | [9 empty] | Not Constructed on Site
Generator Room | Ground Floor | 6.1 | 9.14 | 55.754 | 600 | [9 empty] | Not Constructed on Site
Store Room | Ground Floor | 9.14 | 9.14 | 83.5396 | 899 | Store Room | 14 | 27 | 378 | 35 | -48.5396 | -521 | A.C. Sheet | Old | Location and Additional Area Difference |  | Photo
Photo
Cold Room (Eggs) | Ground Floor | 6.1 | 4.57 | 27.877 | 300 | A part of Labour Room | 20 | 115 | 2300 | 214 |  |  |  |  | Constructed as a part of Labour Room at differanct location |  | Photo
Photo
Office & Manager Room | Ground Floor | 6.1 | 9.14 | 55.754 | 600 | Office | 38 | 20 | 760 | 71 | 15.246 | 160 | R.C.C Slab | Old | Additional Area Difference |  | Photo
| First Floor | 6.1 | 9.14 | 55.754 | 600 | [9 empty] | Not Constructed |  | Photo
Photo
Feed Shed | Ground Floor | 10.06 | 109.75 | 1104.085 | 11884 | Hatchery Building | 235 | 33 | 7755 | 720 | -384.085 | -4129 | R.C.C Slab |  | Less Area Difference |  | Photo
Grower Shed | Ground Floor | 11.58 | 143.29 | 1659.2982 | 17861 | Grower Shed | 38 | 235 | 8930 | 830 | -829.2982 | -8931 | R.C.C Slab |  | Constructed in two parts - Part 1 |  | Photo
| First Floor | [5 empty] | 38 | 235 | 8930 | 830 | 830 | 8930 | A.C. Sheet |  | Not in the approved Plan |  | Photo
[6 empty] | Grower Shed | 44 | 173 | 7612 | 707 | 707 | 7612 | R.C.C Slab |  | Part 2 |  | Photo
25472
Photo
Chick Shed | Ground Floor | 10.06 | 109.75 | 1104.085 | 11884 | Brooder Shed | 33 | 180 | 5940 | 552 | -552.085 | -5944 | A.C. Sheet |  | Location and Less Area Difference |  | Photo
Photo
Workers Residence | Ground Floor | 12.19 | 33 | 402.27 | 4330 |  | 80 | 40 | 3200 | 297 | -105.27 | -1130 | R.C.C Slab |  | Less Area Difference |  | Photo
| First Floor | [5 empty] | 80 | 40 | 3200 | 297 | 297 | 3200 | A.C. Sheet |  | Not in the approved Plan |  | Photo
Photo
Toilets for Workers | Ground Floor | 19.14 | 3.05 | 58.377 | 628 |  | 23 | 20 | 460 | 43 | -15.377 | -168 | A.C. Sheet |  | Location and Less Area Difference |  | Photo
Photo
Super Visor Residence | Ground Floor | 9.14 | 36.58 | 334.3412 | 3599 |  | 25 | 80 | 2000 | 186 | -148.3412 | -1599 | R.C.C Slab | New | Location and Less Area Difference |  | Photo
| First Floor | 9.14 | 36.58 | 334.3412 | 3599 |  | 25 | 80 | 2000 | 186 | -148.3412 | -1599 | R.C.C Slab | Under Construction | Location and Less Area Difference | Brick work is in progress | Photo
Canteen | Ground Floor | 9 | 6 | 54 | 581 | [9 empty] | Not Constructed |  |  | 378
[6 empty] | Generator Room | 25 | 80 | 2000 | 186 |  |  | A.C. Sheet | New
Wash room Dress Cleaning
bathroom for workers
Mess
Coldroom

## Additional Area
As per Site Inspection
Name of Strucutre | Width | Length | Area in Sq. Ft. | Area in Sq. M.
D.G. Room | 15 | 20 | 300 | 27.8707