## Sheet1
As On Site Work in Progress.
Sr No. | Building Name | Floor Name | Gross Built Up Area | % Work Completed | Decreption | Height - As Per Actual
1 | F.G. Store & Admin Block | Basement | 183.65 | 100% | RCC Framed Structure, BBM Wall with Both Side Plaster, Kota Stone Flooring, MS Rolling Shutters, Aluminium Sliding Windows, Concealed Ele. Fittings | 5.85
|  | Ground | 324.5 | 100% |  | 4.7 |  | 855
2 | Coal Storage - Boiler Room | Ground | 789.52 | 80% | RCC Work Completed | As Per Plan |  | 855
|  | Floor -1 | 78.08 |  |  |  |  | 855
|  | Floor - 2 | 78.07 |  |  |  | 5328.94 | 855
|  | Floor - 3 | 78.07 |  |  |  |  | 3420
3 | Poductiong Block
| Reduction & Sulphonation | Ground | 855 | 90% | RCC Framed Structure, BBM Wall with Both Side Plaster, Rajasthani Stone Flooring, MS Rolling Shutters, | 5.68
|  | Floor -1 | 855 | 90% |  | 6.25 | 1776.32 | 855
|  | Floor - 2 | 855 | 90% |  | 6.75 | 1776.3 | 855
|  | Floor - 3 | 855 | 90% |  | 5.25 | 1776.32 | 855
| Oxidation | Ground | 782.89 | 90% | RCC Framed Structure, BBM Wall with Both Side Plaster, Rajasthani Stone Flooring, MS Rolling Shutters, | 4.75 | 1776.32 | 855
|  | Floor -1 | 782.89 | 90% |  | 4.75 | 317.67 | 782.89
|  | Floor - 2 | 782.89 | 90% |  | 5.75 | 386.33 | 782.89
|  | Floor - 3 | 782.89 | 90% |  | 4.75 | 495.37 | 782.89
4 | DG + Panel Room | Ground | 279 | 100% | RCC Framed Structure, BBM Wall with Both Side Plaster, Kota Stone Flooring, MS Rolling Shutters, Aluminium Sliding Windows, Concealed Ele. Fittings | 5.9 | 279 | 782.89
|  | Floor -1 | 279 | 100% |  | 5.3 |  | 279
5 | Time Office | Ground | 41.925 | 100% |  | 3.5 | 8583.63 | 279
6 | ETP Plant | Ground | 556.31 | 80% | RCC Work Completed | As Per Plan |  | 41.925
|  | Floor -1 | 406.45 | 80% | RCC Work Completed |  |  | 7151.485
|  | Floor - 2 | 406.45 | 80% | RCC Work Completed
|  | Floor - 3 | 232.3 | 80% | RCC Work Completed
7 | TANK FARM | TANK Foundation & Tank As On Date
|  |  | 60 K Ltr | 4 Tanks
|  |  | 2 Lac Ltr | 1 Tank
|  |  | 12 K Ltr | 1 Tank
8 | Water Tank - 1 |  | 2 Lac Ltr | RCC UG Tank
| Water Tank - 2 |  | 6 Lac LTr | RCC UG Tank
9 | Compound Wall & MS Gate | All Side | 602.43 | Plaster Yet to be done | UCRS Foundation, AAC Block Compound With MS Gate
10 | Fire Fighting System | All Internal Primises & All Constructed Area
Note on G2: Author:

## Sheet2
Sr. No. | Building Name | Floor Name | Gross Built Up Area | Total Deduction | Industrial Net FS Area | Excess FS Area Hardship | Room Area Deviation Details Hardship
1 | FG STORE & ADMIN | Basement | 183.65 | 183.65 | 0 | 0 | 0
|  | Ground Floor | 324.5 | 14.63 | 309.87 | 0 | 222.94
2 | COAL STORAGE- BOILER | Ground Floor | 789.82 | 0 | 789.82 | 213.59 | 427.18
|  | Ground Floor | 0 | 0 | 0 | 161.24 | 322.49
|  | Floor 1 | 78.08 | 0 | 78.08 | 0 | 0
|  | Floor 2 | 78.07 | 0 | 78.07 | 0 | 0
|  | FLloor 3 | 78.07 | 0 | 78.07 | 0 | 0
3 | Production Block | Floor Ground | 1776.32 | 279.14 | 1497.18 | 0 | 1363.74
|  | Floor 1 | 1776.3 | 636.31 | 1139.99 | 0 | 1005.85
|  | Floor 2 | 1776.32 | 493.48 | 1282.84 | 0 | 1144.12
|  | Floor 3 | 1776.32 | 526.57 | 1249.75 | 0 | 1109.29
4 | RM Storage Tank Farm | Ground Floor | 317.67 | 19.8 | 297.87 | 0 | 212.31
|  | Floor 1 | 386.33 | 19.8 | 366.53 | 0 | 282.91
5 | Time Office & Utility | Ground Floor | 495.37 | 18.9 | 476.47 | 0 | 363.16
|  | Floor 1 | 279 | 18.9 | 260.1 | 0 | 241.69
6 | Effluent Tretment Plant | Ground Floor | 556.31 | 556.31 | 0 | 0 | 0
|  | Floor 1 | 406.45 | 406.45 | 0 | 0 | 0
|  | Floor 2 | 406.45 | 406.45 | 0 | 0 | 0
|  | Floor 2 | 232.3 | 232.3 | 0 | 0 | 0
| Total |  | 11717.33 | 3812.69 | 7904.64 | 374.83 | 6695.68