## Sheet1
As On Site Work in Progress.
Sr No. | Building Name | Floor Name | Gross Built Up Area | % Work Completed | Decreption | Height - As Per Actual
1 | F.G. Store & Admin Block | Basement | 183.65 | 100% | RCC Framed Structure, BBM Wall with Both Side Plaster, Kota Stone Flooring, MS Rolling Shutters, Aluminium Sliding Windows, Concealed Ele. Fittings | 5.85
|  | Ground | 324.5 | 100% |  | 4.7
2 | Coal Storage - Boiler Room | Ground | 789.52 | 80% | RCC Work Completed | As Per Plan
|  | Floor -1 | 78.08
|  | Floor - 2 | 78.07
|  | Floor - 3 | 78.07
3 | Poductiong Block
| Reduction & Sulphonation | Ground | 855 | 90% | RCC Framed Structure, BBM Wall with Both Side Plaster, Rajasthani Stone Flooring, MS Rolling Shutters, | 5.68
|  | Floor -1 | 855 | 90% |  | 6.25
|  | Floor - 2 | 855 | 90% |  | 6.75
|  | Floor - 3 | 855 | 90% |  | 5.25
| Oxidation | Ground | 782.89 | 90% | RCC Framed Structure, BBM Wall with Both Side Plaster, Rajasthani Stone Flooring, MS Rolling Shutters, | 4.75
|  | Floor -1 | 782.89 | 90% |  | 4.75
|  | Floor - 2 | 782.89 | 90% |  | 5.75
|  | Floor - 3 | 782.89 | 90% |  | 4.75
4 | DG + Panel Room | Ground | 279 | 100% | RCC Framed Structure, BBM Wall with Both Side Plaster, Kota Stone Flooring, MS Rolling Shutters, Aluminium Sliding Windows, Concealed Ele. Fittings | 5.9
|  | Floor -1 | 279 | 100% |  | 5.3
5 | Time Office | Ground | 41.925 | 100% |  | 3.5
6 | ETP Plant | Ground | 556.31 | 80% | RCC Work Completed | As Per Plan
|  | Floor -1 | 406.45 | 80% | RCC Work Completed
|  | Floor - 2 | 406.45 | 80% | RCC Work Completed
|  | Floor - 3 | 232.3 | 80% | RCC Work Completed
7 | TANK FARM | TANK Foundation & Tank As On Date
|  |  | 60 K Ltr | 4 Tanks
|  |  | 2 Lac Ltr | 1 Tank
|  |  | 12 K Ltr | 1 Tank
8 | Water Tank - 1 |  | 2 Lac Ltr | RCC UG Tank
| Water Tank - 2 |  | 6 Lac LTr | RCC UG Tank
9 | Compound Wall & MS Gate | All Side | 602.43 | Plaster Yet to be done | UCRS Foundation, AAC Block Compound With MS Gate
10 | Fire Fighting System | All Internal Primises & All Constructed Area
Note on G2: Author: