Vastu/Mumbai /SBI/SME/04/2024/8080/2305867

02/5-6-APU

Date: 02-04-2024

## ADDENDUM TO LIE REPORT

To,

## The Branch Manager,

## State of India, SME Chembur Branch,

## Unit No. 11, Building No. 11, Ground Floor,

## Corporate Park, Sion-Trombay Road,

## Chembur, Mumbai- 400 071.

## Sub: Addendum to LIE Report dated 03.01.2024 of M/s Mahi Teryy Cot LLP.

Ref: LIE Report dated 03.01.2024.

Dear Sir,

With reference to our LIE Report dated 03.01.2024 for the progress of 9.5 MTPD Terry Towel manufacturing facility at Plot No. T-24, Additional Amravati Textile Park, MIDC Nandgaon Peth, Amravati, PIN Code-444 901, State- Maharashtra, County-India belonging to M/s. Mahi Terry Cot LLP till 23.10.2023, following Approvals and clearances is pending: -

- BCC

- Drainage Completion Certified

- Fire NOC

- Consent to Operate

- Factory License.

- Insurance

- Weigh Bridge

Later, Company has obtained the pending approvals from the concerned authority, the Current Status of Approvals and clearances is as under: -

| S. No. | Approvals / Certifications | Approving / Sanctioning Authority | Status |
| --- | --- | --- | --- |
| 1 | Date of Incorporation | Registrar, Mumbai, Ministry of Corporate Affairs, GOI | Incorporated on 21.06.2016. |
| 2 | PAN Card | Income Tax, GOI | PAN Number-ABDFM1686N |
| 3 | GST Certificate | GOI | Registered on 01.07.2017, GSTN Number- 27ABDFM1686N1ZQ |
| 4 | Udyam Registration Certificate | MSME, GOI | Registered on 06.12.2021, Registration No. UDYAM-MH-18-0113799 |
| 5 | Certificate of Importer - Exporter Code | Directorate General of Foreign Trade | Obtained. Importer - Exporter Code 0317507605. |
| 6 | Land Possession | Provided vide possession receipt issued by MIDC dated 14.12.2017 |  |
| 7 | Consent to establish | Maharashtra Pollution Control Board | Obtained vide Consent No. Format 1.0/BO/CAC-Cell/CAC-UAN No. 37617/ CAC1810000566 dated 12.10.2018 valid till commission of the unit or 5 years whichever is earlier. |
| 8 | Provisional Fire NOC | MIDC | Obtained |
| 9 | Temporary Power Connection | MSEDCL | Obtained |
| 10 | Temporary Water Connection | MIDC | Obtained |
| 11 | Permanent Electricity Connection | MSEDCL | Obtained |
| 12 | Building Plan approval | MIDC | Obtained |
| 13 | Machinery Layout Plan | Director of Industrial Safety & Health | Obtained |
| 14 | Drainage completion certificate | MIDC | Obtained vide No. EE/DB/ A16901 / of 2024 dated 28.03.2024. |
| 15 | Building Completion Certificate | MIDC | Received vide No. MIDC/EE/SPA/ A15922 /2024 dated 22.03.2024. |
| 16 | IBR Approvals | Directorate of Boilers | Obtained |
| 17 | Final Fire Department NOC | MIDC | Obtained vide No. MIDC/FIRE/IFMS/ A14255 dated 14.03.2024. |
| 18 | Consent to Operate | MPCB | Obtained vide No. Format1.0/CC/UAN No.0000170771/CO/2312000556 dated 06.12.2023 valid till 31.008.2028. |
| 19. | Factory License | Director of Industrial Safety & Health | Obtained vide No. 1203013999000M dated 28.12.2023 valid till 31.12.2024. |
| 20. | Insurance |  | Obtained Standard Fire and Special Perils Policy valid till 22.10.2024. |
| 21. | Weigh Bridge |  | Pending |

OBSERVATIONS: -

- Company has obtained all the necessary Approval and Clearance to run the Factory.

- Original the Weigh Bridge is not the part of the project.

- Currently the installation of Weigh Bridge is in progress as informed by the Party and the weighments of Trucks are done from outside.

We are at option the Company has obtained all the necessary Approval and Clearance to run the Factory.

Hence Certified.

This Certificate is prepared for State Bank of India, SME Chembur Branch.

We further declare that: --

### In the preparation of the Addendum to LIE Report, we have relied on the information provided by the client.

### The information furnished in this Certificate is true and correct to the best of our knowledge and belief.

### We have no direct or indirect interest in the Unit.

For Vastukala Consultants (I) Pvt. Ltd.

Date: - 02.04.2024

Place: - Mumbai

Umang Ashwin Patel

Regd. Valuer

Chartered Engineer (India)

Reg. No. IBBI/RV/04/2019/10803