## Final Summary
Project expenses | Estimated Cost as per Cost Vetting | Incurred Cost as per Bill till 31.03.2024 | Incurred Cost as per CA till 31.03.2024 | Incurred Cost as per Bill till 31.12.2023 | Incurred Cost as per CA till 31.12.2023 | Difference between the Bills & CA | Difference between both the Bills | Difference between both CA | Remark
Land Cost | 0.34 | 0.33572 | 0.34 | 0.33572 | 0.34 | -0.0042775 | 0 | 0
Rent Cost | 1.84 | 1.5537 | 1.55 | 1.3695 | 1.36 | 0.0036746 | 0.18421 | 0.19
TDR Cost | 0.61 | 1.0817 | 1.08 | 1.0817 | 1.08 | 0.0016961 | 0 | 0
Construction Cost of Sale Building | 11.41 | 9.834 | 11.5 | 6.014 | 8.61 | -1.666 | 3.82 | 2.89 | Justification required
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 4.5 | 5.6997 | 4.6 | 5.6927 | 4.6 | 1.0997 | 0.007 | 0
Architect Cost, RCC & other Professional fees | 0.34 | 0.59608 | 0.98 | 0.59608 | 0.91 | 0.036014 | 0 | 0.07 | Security Charges, water charges, Bank processing charges & insurance cost is considered in Admin Cost
Administrative Expenses | 0.46 | 0.39312 |  | 0.35118 |  |  | 0.041936
Marketing Expences | 0.55 | 0.02681 |  | 0.01681 |  |  | 0.01
Interest Cost | 0.85 | 0.2232 | 0.27 | 0.17952 | 0.27 | -0.046797 | 0.043688 | 0 | CA has considered the bank processing charges & insurance cost in interest cost
Contingency Cost | 0.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost | 21.13 | 19.744 | 20.32 | 15.6372 | 17.17 | -0.57599 | 4.1068 | 3.15
|  | 1.386 | 0.57599
Particulars | Revised Estimated Cost (in Cr.) | 31.03.2024 as per Bill Tally (inclusive of GST) | Cost incurred as %age total cost of that Component | Cost incurred as %age of cost incurred as on 31.12.2023
Land Cost | 0.34 | 0.33572 | 98.74% | 1.589%
Rent Cost | 1.84 | 1.5537 | 84.44% | 7.353%
TDR Cost | 0.61 | 1.0817 | 177.3% | 5.119%
Construction Cost of Sale Building | 11.41 | 9.834 | 86.19% | 46.54%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 4.5 | 5.6997 | 126.7% | 26.97%
Architect Cost, RCC & other Professional fees | 0.34 | 0.59608 | 175.3% | 2.821%
Administrative Expenses | 0.46 | 0.39312 | 85.46% | 1.86%
Marketing Expences | 0.55 | 0.02681 | 4.875% | 0.1269%
Interest Cost | 0.85 | 0.2232 | 26.26% | 1.056%
Contingency Cost | 0.23 | 0 | 0% | 0%
Total | 21.13 | 19.744 | 93.44% | 93.44%
Pariculars | 31.03.2024 as per Bill Tally (inclusive of GST) | 31.12.2023 as per Bill Tally (inclusive of GST) | Difference b/w bills of 31.07.2023 & CA Certificate | Difference of Cost incurred as %age of cost incurred as on 31.07.2023 & 31.12.2023
Land Cost | 0.33572 | 0.33572 | 0 | 0%
Rent Cost | 1.5537 | 1.3695 | 0.18 | 0.9117%
TDR Cost | 1.0817 | 1.0817 | 0 | 0%
Construction Cost of Sale Building | 9.834 | 6.014 | 3.82 | 19.35%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 5.6997 | 5.6927 | 0.01 | 0.05065%
Architect Cost, RCC & other Professional fees | 0.59608 | 0.59608 | 0 | 0%
Administrative Expenses | 0.39312 | 0.35118 | 0.04 | 0.2026%
Marketing Expences | 0.02681 | 0.01681 | 0.01 | 0.05065%
Interest Cost | 0.2232 | 0.17952 | 0.04 | 0.2026%
Contingency Cost | 0 | 0 | 0 | 0%
Total | 19.744 | 15.6372 | 4.11 | 20.82%

## Summary Sheet
Sr. No. | Particulars | Incurred Cost in ` till 31.03.2024 | Incurred Cost in ` Cr. Till 31.03.2024 | Incurred Cost in ` till 31.12.2023 | Incurred Cost in ` Cr. Till 31.12.2023 | Balance | Balance in Cr.
1 | Land Cost | 3357225 | 0.33572 | 3357225 | 0.33572 | 0 | 0
2 | Rent Cost | 15536746 | 1.5537 | 13694653 | 1.3695 | 1842093 | 0.18421
3 | TDR Cost | 10816961.5 | 1.0817 | 10816961.5 | 1.0817 | 0 | 0
4 | Construction Cost | 98340427 | 9.834 | 60140336 | 6.014 | 38200091 | 3.82 | 127278700 | 30.0129
5 | Approval Cost & Stamp Duty | 56996599.3 | 5.6997 | 56926599.3 | 5.6927 | 70000 | 0.007
6 | Professional Cost | 5960850 | 0.59608 | 5960850 | 0.59608 | 0 | 0
7 | Admin Cost | 3931187.16 | 0.39312 | 3511823.88 | 0.35118 | 419363.28 | 0.041936
8 | Marketing Cost | 268100 | 0.02681 | 168100 | 0.01681 | 100000 | 0.01
9 | Interest Cost | 2232034 | 0.2232 | 1795155 | 0.17952 | 436879 | 0.043688
| Total | 197440129.96 | 19.744 | 156371703.68 | 15.6372 | 41068426.28 | 4.1068
8500000
6267966

## Land, Rent, TDR, Approval
Land Cost Description | [7 empty] | TDR Cost
Sr. No. | Date | Document Name | Description | Total Cost | Incurred Cost |  | Sr. No. | Description | Incurred Cost
1 | 16.02.2022 | Developer Agreement | Stamp Duty | 3325725 | 3325725 |  |  | TDR PURCHASE | 10238932
2 |  |  | Reg. Fees | 30000 | 30000 |  | 2 | Stamp Duty | 578029.5
3 |  | Power Attorney |  | 1500 | 1500
Total |  |  |  | 3357225 | 3357225 |  | Total |  | 10816961.5
Sr. No. | 6. MCGM Approval Costs |  | 5. Premium Costs
| Plot Size (sq Mt) | 868.17 | Plot Size (sq Mt) | 868.17
| FSI | 2.2 | FSI | 0.5 | 67145
| Net Area | 1909.974 | Net Area | 434.085
| Net Area (sq Mt i.e. *10.764) | 20558.9601 | Premium Factor | 0.5
| Rate per Sft (Rs.) | 2000 | Land Rate (Rs.) | 49200
| Total Approval Cost | 41117920.272 | Total Premium Cost | 10678491
45000000
2188.8267
Sr. No. | Tenant No. | Old Carpet Area in Sq. Ft. | New Carpet Area in Sq. Ft. | Rate per Sq. Ft. on CA | Rent per Month | Rent per Year | Rate per Sq. Ft. on CA | Rent per Month | Shifting Charges | Brokerage Charges | Total
1 | Resi 1 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
2 | Resi 2 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
3 | Resi 3 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
4 | Resi 4 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
5 | Resi 5 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
6 | Resi 6 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
7 | Resi 7 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
8 | Resi 8 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
9 | Resi 9 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
10 | Resi 10 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
11 | Resi 11 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
12 | Resi 12 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
13 | Resi 13 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
14 | Resi 14 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
15 | Resi 15 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
16 | Resi 16 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
17 | Resi 17 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
18 | Resi 18 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
19 | Comm 1 | 295 | 359.9 | 90 | 26550 | 318600 | 99 | 29205 | 20000 | 26550 | #REF!
20 | Comm 2 | 295 | 359.9 | 90 | 26550 | 318600 | 99 | 29205 | 20000 | 26550 | #REF!
21 | Comm 3 | 295 | 359.9 | 90 | 26550 | 318600 | 99 | 29205 | 20000 | 26550 | #REF!
22 | Comm 4 | 295 | 359.9 | 90 | 26550 | 318600 | 99 | 29205 | 20000 | 26550 | #REF!
23 | Comm 5 | 109 | 132.98 | 90 | 9810 | 117720 | 99 | 10791 | 20000 | 9810 | #REF!
24 | Comm 6 | 385 | 0 | 90 | 34650 | 415800 | 99 | 38115 | 20000 | 34650 | #REF!
|  | 9774 | 11454.58 |  | 596160 | 7153920 |  | 655776 | 480000 | 596160 | #REF!
[6 empty] | 7153920 |  |  |  |  | #REF! | 240000 | 596160
#REF!

## Rent Cost
RENT PAID-COMMERCIAL to Tenant | 1662138
RENT PAID- RESIDENTIAL to Tenant | 6869250
Brokerage Paid To Tenant (To take Flat on rent) | 534960
CORPUS FUND -PAID to Tenant | 1100000
TRANSPORT CHARGES PAID TO TENENT | 440000
RENT PAID-COMMERCIAL to Tenant | 665280
RENT PAID- RESIDENTIAL to Tenant | 2423025
RENT PAID-COMMERCIAL to Tenant | 399168
RENT PAID- RESIDENTIAL to Tenant | 1442925
15536746

## TDR & Approval
SR.NO | PARTICULARS | TOTAL AMOUNT
| BMC PAYMENT-CFO PAYMENT | 385236
| FUNGIBLE PREMIUM PAID | 7100
| HE NOC /PCO NOC | 94200
| M.C.G.M DD/ORDER PAY | 48386911.5
| PROPERTY TAX PAID | 497391
| REVALIDATION CHARGES | 22800
| REVISED CONCESSION CHARGES-SCRUTINY FEES | 19400
| SWM NOC | 26500
| Scrutiny Fees for TDR & ACCOMODATION | 16016
| Roc Expenses | 10000
| Survay Remark Fees | 11048
| LAXMAN SUTHAR (PARKING REMARK) NOC | 9900
| FUNGIBLE PREMIUM PAID | 1208441.8
| HE NOC /PCO NOC | 67065
| M.C.G.M DD/ORDER PAY | 6164590
| M.C.G.M DD/ORDER PAY | 70000
56996599.3

## Material & Labour
Date | Particulars | Amount
2023-05-15 | Suman Kanoria | 2500000 | Date | Particulars | Gross Total
2023-04-10 | Narottam Granites Pvt Ltd | 1000000 |  | Construction Cost-Advance to Contractor (J.R Infra) | 2640000
2023-06-20 | Anjaneya Star India Pvt Ltd | 3100000 |  | Building Material Purchase | 3521729.32
2023-06-05 | Narottam Granites Pvt Ltd | 376000 |  | BOREWELL WORK | 161908
2023-06-03 | Magnium Steel Company | 1716197 |  | ELECTRIC WORK | 27625
2023-06-05 | Narottam Granites Pvt Ltd | 184305 |  | Water Licencing & Plumber Contract Work | 182500
2023-07-15 | Narottam Granites Pvt Ltd | 25050000
2023-06-24 | Shreenanth Plywood | 63026
2023-06-20 | Shreenanth Plywood | 143724 |  |  | 6533762.32
2023-07-01 | Shreenanth Plywood | 38477
| Building Material Purchase | 2905899
| BOREWELL WORK | 53293
| BUILDING MATERIAL PURCHASE | 1227240
| Construction Cost | 20621263
| ELECTRIC WORK | 89040
| LABOUR CHARGES | 1005610
| Payment to Electric Contractor | 38262
| Water Licencing & Plumber Contract Work | 28000
| Building Material Purchase | 2537902
| BUILDING MATERIAL PURCHASE | 164643
| LABOUR CHARGES | 1117764
| LIFT CONTARCT | 2315160
| MATERIAL WITH LABOUR CHARGES | 678571
| R.C.C. Work ( Construction Expenses) | 30639819
| Tower Car Parking- Material | 746232
98340427
0

## Professional
SR.NO | PARTICULARS | TOTAL AMOUNT
1 | Civil Aviation Noc | 81420
4 | CONSULTANCY FEES PAID | 1902550
5 | PROFESSIONAL FEES EXPENSES | 3861580
6 | PROFESSIONAL FEES EXPENSES | 115300
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
32
TOTAL |  | 5960850

## MArketing
SR.NO | PARTICULARS | TOTAL AMOUNT
| STAMP DUTY AND REGISTRATION CHARGES | 91100
| Advertising Charges | 2000
| Brokerage | 75000
| BROKERAGE PAID- BUSINESS LEAD | 100000
TOTAL |  | 268100

## Admin
SR.NO | PARTICULARS | TOTAL AMOUNT
| Horticulture Expenses | 10000
| MCGM WATER CHARGES | 107100
| Payment to Electric Contractor | 52156
| SECURITY SERVICE CHARGE | 263045
| STAFF SALARY | 753149
| ACCOUNTING CHARGES | 12500
| Advertising Charges | 22619
| AUDIT FEES | 8850
| Bank Charges | 32171.64
| DONATION PAID | 9000
| Electricity Charges (Site) | 98560
| Expenses for Project | 34870
| INTEREST PAID ON TDS | 6241
| JANTA INSURANCE POLICY | 36155
| MEMBERSHIP FEES PAID | 76700
| Office Exp | 3200
| PRINTING & STATIONERY | 238550
| REPAIRS & MAINTENANCE | 5000
| Rera Registration Fees and Other Charges | 18292.8
| ROUNDING OFF | 435.5
| Staff Salary | 143276
| STAFF WELFARE | 5248
| Sundry Expenses | 40725.55
| COMMISSION PAID ON SBI LOAN PROCESS | 781986
| Staff Salary | 294437
| Bank Charges | 1697.39
| Electricity Charges (Site) | 115600
| INTEREST PAID ON TDS | 316
| PRINTING & STATIONERY | 12966
| MCGM WATER CHARGES | 23800
| SECURITY SERVICE CHARGE | 90000
| Insurance | 213177
| STAFF SALARY | 150945
| Bank Charges | 31911.28
| Electricity Charges (Site) | 106210
| MEMBERSHIP FEES PAID | 11800
| PRINTING & STATIONERY | 10729
| Roc Expenses | 3068
| Survay Remark Fees | 15000
| SECURITY SERVICE CHARGE | 54000
| MCGM WATER CHARGES | 35700
TOTAL |  | 3931187.16

## Interest
Sr. No. | Month | Interest Amount
| 2023-06-01 | 9357
| 2023-07-01 | 291649
| 2023-08-01 | 322489
| 2023-09-01 | 343268
| 2023-10-01 | 343288
| 2023-11-01 | 238412
| 2023-12-01 | 246692
| 2024-03-01 | 436879
2232034

## Construction Area Statement
Sr. No. | Floor | Total Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | Percentage of work completed | Actual Expenditure till date in ` | Work Completion status as on 31.12.2023
1 | Excavation Cost |  |  |  |  | 100% | 0 | Completed
2 | Basement | 51.85 | 51.85 | 30000 | 1555500 | 70% | 1088850 | Slab work, block work, plaster work is completed
3 | Ground | 246.44 | 246.44 | 30000 | 7393200 | 75% | 5544900 | Slab work, block work, plaster work, Door and window frame work is completed
4 | 1st | 241.65 | 241.65 | 30000 | 7249500 | 75% | 5437125 | Slab work, block work, plaster work, Door and window frame work, flooring & tiling work, Gypsum work is completed
5 | 2nd | 241.65 | 241.65 | 30000 | 7249500 | 75% | 5437125 | Slab work, block work, plaster work, Door and window frame work, Gypsum work is completed
6 | 3rd | 241.65 | 241.65 | 30000 | 7249500 | 75% | 5437125 | Slab work, block work, plaster work, Door and window frame work, Gypsum work is completed
7 | 4th | 241.65 | 241.65 | 30000 | 7249500 | 75% | 5437125 | Slab work, block work, plaster work, Door and window frame work, Gypsum work is completed
8 | 5th | 241.65 | 241.65 | 30000 | 7249500 | 75% | 5437125 | Slab work, block work, plaster work, Door and window frame work, Gypsum work is completed
9 | 6th | 241.65 | 241.65 | 30000 | 7249500 | 75% | 5437125 | Slab work, block work, plaster work, Door and window frame work, Gypsum work is completed
10 | 7th | 241.65 | 241.65 | 30000 | 7249500 | 75% | 5437125 | Slab work, block work, plaster work, Door and window frame work, Gypsum work is completed
11 | 8th | 241.67 | 241.67 | 30000 | 7250100 | 75% | 5437575 | Slab work, block work, plaster work, Door and window frame work, Gypsum work is completed
12 | 9th | 241.65 | 241.65 | 30000 | 7249500 | 75% | 5437125 | Slab work, block work, plaster work, Door and window frame work is completed & 60% gyspum work is completed
13 | 10th | 241.65 | 241.65 | 30000 | 7249500 | 75% | 5437125 | Slab work, block work, plaster work, Door and window frame work is completed
14 | 11th | 241.65 | 241.65 | 30000 | 7249500 | 70% | 5074650 | Slab work, block work, plaster work, Door and window frame work is completed
15 | 12th | 241.65 | 241.65 | 30000 | 7249500 | 70% | 5074650 | Slab work, block work, plaster work, Door and window frame work is completed
16 | Terrace | 38.89 | 38.89 | 30000 | 1166700 | 70% | 816690 | Slab work, block work, plaster work, Door and window frame work is completed
Sub - Total (A) |  | 3237 | 3237 |  | 97110000 |  | 71971440
STACK PARKING Nos. |  | 34 |  | 500000 | 17000000 |  | 0
TOTAL COST OF CONSTRUCTION (A + B) |  |  |  |  | 114110000 | 63.07% | 71971440