## Final Summary
Project expenses | Estimated Cost as per Cost Vetting | Incurred Cost as per CA till 31.03.2024 | Incurred Cost as per CA till 31.12.2023 | Difference between both CA | Remark
Land Cost | 0.77724 | 0.7769 | 0.7769 | 0
Construction Cost of Sale Building | 28.4353 | 8.6506 | 5.9539 | 2.6967
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 0.7867 | 0.6367 | 0.6367 | 0
Admin, Professional & Marketing Cost | 1.575 | 0.36822 | 0.1577 | 0.21052
Interest Cost | 3.85 | 0 | 0 | 0
Contingency Cost | 1.7005 | 0 | 0 | 0
Total Cost | 37.1247 | 10.4324 | 7.5252 | 2.9072
26.6924
Particulars | Estimated Cost (in Cr.) | Incurred Cost as per CA till 31.03.2024 | Cost incurred as %age total cost of that Component | Cost incurred as %age of cost incurred as CA Certificate
Land Cost | 0.77724 | 0.7769 | 99.96% | 2.093%
Construction Cost of Rehab cum Sale Building | 28.4353 | 8.6506 | 30.42% | 23.3%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 0.7867 | 0.6367 | 80.93% | 1.715%
Architect Cost, RCC & other Professional fees | 1.575 | 0.36822 | 23.38% | 0.9918%
Interest Cost | 3.85 | 0 | 0% | 0%
Contingency Cost | 1.7005 | 0 | 0% | 0%
Total | 37.1247 | 10.4324 | 28.1% | 28.1%

## Plinth Area Calculation
Sr. | Floor | Built Up Area In Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | % of work completed | Actual Expenditure till date in `
1 | Ground Floor | 208.96 | 208.96 | 30000 | 6268800 | 80% | 5015040
2 | 1st Floor | 557.71 | 557.71 | 30000 | 16731300 | 75% | 12548475
3 | 2nd Floor | 589.66 | 589.66 | 30000 | 17689800 | 75% | 13267350
4 | 3rd Floor | 589.66 | 589.66 | 30000 | 17689800 | 75% | 13267350
5 | 4th Floor | 589.66 | 589.66 | 30000 | 17689800 | 75% | 13267350
6 | 5th Floor | 589.66 | 589.66 | 30000 | 17689800 | 70% | 12382860
7 | 6th Floor | 589.66 | 589.66 | 30000 | 17689800 | 70% | 12382860
8 | 7th Floor | 589.66 | 589.66 | 30000 | 17689800 | 70% | 12382860
9 | 8th Floor | 558.03 | 558.03 | 24000 | 13392720 | 70% | 9374904
10 | 9th Floor | 589.66 | 589.66 | 30000 | 17689800 | 55% | 9729390
11 | 10th Floor | 589.66 | 589.66 | 30000 | 17689800 | 55% | 9729390
12 | 11th Floor | 589.66 | 589.66 | 30000 | 17689800 | 55% | 9729390
13 | 12th Floor | 589.66 | 589.66 | 30000 | 17689800 | 50% | 8844900
14 | 13th Floor | 558.03 |  | 24000 | 13392720
15 | 14th Floor | 589.66 |  | 30000 | 17689800
16 | 15th Floor | 589.66 |  | 30000 | 17689800
17 | 16th Floor | 589.66 |  | 30000 | 17689800
TOTAL |  | 9548.31 | 7221.3 |  | 279752940 | 50.73% | 141922119