## Final Summary
Project expenses | Estimated Cost as per Cost Vetting | Incurred Cost as per Bill till 31.03.2024 | Incurred Cost as per CA till 31.03.2024 | Incurred Cost as per Bill till 31.12.2022 | Incurred Cost as per CA till 31.12.2022 | Difference between the Bills & CA | Difference between both the Bills | Difference between both CA | Remark
Land Cost | 12.5 | 12.5 | 12.5 |  |  | 4.3e-05
Construction Cost of Sale Building | 55.81 | 8.1212 | 8.13 |  |  | -0.0087834
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 13.02 | 10.6006 | 10.6 |  |  | 0.0006165
Architect Cost, RCC & other Professional fees | 0.56 | 0.26089 | 0.26 |  |  | 0.000887
On- site expenditure for development / Advance for Project / Administrative Cost / Fixed Assets | 3.07 | 0.27637 | 0 |  |  | 0.27637 |  |  | .
Marketing Expenses | 5.35 | 0.3698 | 0.64 |  |  | -0.2702
Interest Cost | 6.91 | 0 | 0 |  |  | 0
Total Cost | 97.22 | 32.1289 | 32.13 | 0 | 0 | -0.0010641 | 0 | 0
65.0911
Particulars | Revised Estimated Cost (in Cr.) | 31.03.2024 as per Bill Tally (inclusive of GST) | Cost incurred as %age total cost of that Component | Cost incurred as %age of cost incurred as on 31.03.2024
Land Cost | 12.5 | 12.5 | 100% | 12.86%
Construction Cost | 55.81 | 8.1212 | 14.55% | 8.353%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 13.02 | 10.6006 | 81.42% | 10.9%
Architect Cost, RCC & other Professional fees | 0.56 | 0.26089 | 46.59% | 0.2683%
On- site expenditure for development / Advance for Project/ Administrative Cost/ Fixed Assets | 3.07 | 0.27637 | 9.002% | 0.2843%
Marketing Expenses | 5.35 | 0.3698 | 6.912% | 0.3804%
Interest Cost | 6.91 | 0 | 0% | 0%
Total | 97.22 | 32.1289 | 33.05% | 33.05%
Pariculars | 31.03.2024 as per Bill Tally (inclusive of GST) | CA Certificate till 31.03.2024 | Difference b/w bills of 31.03.2024 & CA Certificate | Difference of Cost incurred as %age of cost incurred as on 31.03.2024 & CA Certificate
Land Cost | 12.5 | 12.5 | 0 | 0%
Construction Cost | 8.1212 | 8.13 | -0.01 | -0.03112%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 10.6006 | 10.6 | 0 | 0%
Architect Cost, RCC & other Professional fees | 0.26089 | 0.26 | 0 | 0%
On- site expenditure for development / Advance for Project/ Administrative Cost/ Fixed Assets | 0.27637 | 0 | 0.28 | 0.8715%
Marketing Expenses | 0.3698 | 0.64 | -0.27 | -0.8404%
Interest Cost | 0 | 0 | 0 | 0%
Total | 32.1289 | 32.13 | 0 | #DIV/0!

## Summary Sheet
Sr. No. | Particulars | Incurred Cost in ` till 31.08.2022 | Incurred Cost in ` Cr. Till 30.06.2022 | Incurred Cost in ` till 31.03.2022 | Incurred Cost in ` Cr. Till 31.03.2022 | Balance | Balance in Cr.
1 | Land Cost | 125000430 | 12.5 |  |  | 125000430 | 12.5
3 | Construction Cost | 81212166.44 | 8.1212 |  |  | 81212166.44 | 8.1212
4 | Approval Cost & Stamp Duty | 106006165 | 10.6006 |  |  | 106006165 | 10.6006
5 | Professional Cost | 2608870 | 0.26089 |  |  | 2608870 | 0.26089
6 | Admin Cost | 2763700 | 0.27637 |  |  | 2763700 | 0.27637
7 | Marketing Cost | 3698028 | 0.3698 |  |  | 3698028 | 0.3698
8 | Interest Cost | 0 | 0 |  |  | 0 | 0
| Total | 321289359.44 | 32.1289 | 0 | 0 | 321289359.44 | 32.1289

## Land
S.No | Land Cost: | Amount (in Rs.)
1 | Payment to Land Owners | 437153000
2 | Payment to Tenants | 304088299
741241299
3 | Stamp Duty | 38602044
68564179
| Total Land Cost | 848407522
Note: | The Stamp duty at 5% of total cost incurred i.e. 74.12 cr is approx 3.86 crs which has been paid.
S.No | Particulars | Land Cost (in Rs.) | BUA | % of Land Covered
1 | Arena ( Commercial ) | 219607901.47 | 16122.03 | 28.16%
2 | One Meraki -Wing A & B | 198240325.86 | 14171.63 | 24.75%
3 | One Meraki -Wing C | 125000430.49 | 7223.11 | 12.62%
| One Meraki -Wing D) | 135144430.49 | 7223.11 | 12.62%
4 | One Meraki -Wing E | 79841530.97 | 5861.39 | 10.24%
4 | Platina | 90572902.7 | 6649.21 | 11.61%
|  | 848407521.98 | 57250.48 | 100%
Additional Stamp Duty Cost inccured for One Meraki -Wing A & B = 52,00,000
So the total land cost = 19,30,40,325/- + 52,00,000/- = Rs. 19,82,00,000/-
| One Meraki | 198240325.86
| Stamp Duty | 5200000
| Total Land Cost | 125000430.49

## Approval Cost Details
Cost of Approvals/Liaisioning (Rs. 13.02 crore):
Sr. No. | Nature of Charges | Estimated Cost (Rs.) | Estimated Cost (Rs. In crs )
1 | Scrutiny Fees (New Proposals U/S 337 & 342 | 1400000 | 0.14
2 | Development Cess 33(7) | 42500000 | 4.25
3 | Premium for Staircase, Lift, Lift Lobby area | 10000000 | 1
4 | Premium for .50 % Addition F.S.I | 2700000 | 0.27
5 | Premium for Fungible F.S.I | 14000000 | 1.4
6 | I.O.D Deposit | 100000 | 0.01
7 | Premium for deficiency in Open Space | 300000 | 0.03
8 | Labour Welfare Cess (ADM -1% ) | 300000 | 0.03
9 | Other deficiency Premium | 3500000 | 0.35
10 | Miscellaneous | 37500000 | 3.75
11 | 5% Premium for TDR Utilizations | 2000000 | 0.2
12 | Labour Welfare Cess (Tax/Fund - 99% ) | 2800000 | 0.28
13 | Permissible additional 0.50 F.S.I Dharavi redevelopment project (DRP) | 100000 | 0.01
14 | Premium for paved/ perforated RG | 5000000 | 0.5
15 | Premium for conversion of zone from I to R/ C reg 14 B | 5500000 | 0.55
16 | MSRDC share towards Fungible FSI reg 31(3) | 2500000 | 0.25
17 | MSRDC Share towards 0.50 Addi. FSI reg 30 | 1400000 | 0.14
| Total cost of Approval / Liaisioning | 130200000 | 13.02
| Cost Inccured till 31.03.2024 | 106006165

## 04T2 CONSTRUCTION COST
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
04T2 CONSTRUCTION COST
Group Summary
1-Apr-01 to 31-Mar-24
Particulars | Amount
4T2 ANCHOR WORK & LABOUR CHGS | 2761550
4T2 CEMENT | 2639142.84
4T2 CEMENT BLOCKS | 104893
4T2 CHEMICAL MATERIAL | 437650
4T2 ELECTRIC MATERIAL | 587736.74
4T2 EXCAVATION LABOUR CHARGES | 2000000
4T2 FABRICATION MATERAILS | 852487
4T2 FIRE FITTING EQUIPMENTS | 39482
4T2 FREIGHT - W/O GST | 4000
4T2 GRILL & FABRICATION LABOUR | 357790
4T2 HARDWARE | 22778
4T2 LABOUR CHARGES | 20806105
4T2 MARBLE | 338050
4T2 MIVAN MATERIAL | 2496188
4T2 PLUMBING MATERIAL | 1161736.02
4T2 READY MIX | 1301470.69
4T2 REPAIRS & SERVICES | 212164
4T2 SAFETY NET EXPS | 769660
4T2 SAND | 1452918.15
4T2 STEEL | 16415503
PO-HITACHI BUILDING SYSTEMS CO. LTD.-PO- WORK ORDER | 17095680
S- FORM INDIA PVT LTD | 6311962
KDM CHEMICALS AND RESEARCH PVT LTD | 594720
PUTZMEISTER INDIA PVT LTD | 2448500
Grand Total | 81212166.44

## 4T2 ANCHOR WORK & LABOUR CHGS
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 ANCHOR WORK & LABOUR CHGS
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2022-12-06 | ZC TOTAL FOUNDATION(AEUPP8891C) | Pur - T2 | 099/TF/22-23 | 793750
2022-12-06 | ZC TOTAL FOUNDATION(AEUPP8891C) | Pur - T2 | 100/TF/22-23 | 191250
2023-03-20 | ZC TOTAL FOUNDATION(AEUPP8891C) | Pur - T2 | 142/TF/22-23 | 495000
2023-03-20 | ZC TOTAL FOUNDATION(AEUPP8891C) | Pur - T2 | 141/TF/22-23 | 488300
2023-04-26 | ZC TOTAL FOUNDATION(AEUPP8891C) | Pur - T2 | 009/TF/23-24 | 454750
2023-06-12 | ZC TOTAL FOUNDATION(AEUPP8891C) | Pur - T2 | TF/23-24/029 | 338500
2761550

## 4T2 CEMENT
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 CEMENT
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2024-02-05 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310930491 | 87000
2024-03-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310939438 | 116000
2024-03-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310939450 | 29000
2024-03-09 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2303166795 | 116071.42
2024-03-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310940800 | 58000
2024-03-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310940799 | 87000
2024-03-15 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310941204 | 145000
2024-03-19 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2303172385 | 116071.42
2024-03-19 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310942851 | 145000
2024-03-19 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310942826 | 145000
2024-03-20 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310942897 | 145000
2024-03-22 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310943578 | 87000
2024-03-22 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310943600 | 58000
2024-03-24 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310944362 | 145000
2024-03-24 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310944183 | 145000
2024-03-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310945295 | 87000
2024-03-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310945294 | 58000
2024-03-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310945293 | 87000
2024-03-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310945296 | 58000
2024-03-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310945420 | 145000
2024-03-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310945484 | 145000
2024-03-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310945496 | 145000
2024-03-31 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310946406 | 72500
2024-03-31 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310946187 | 145000
2024-03-31 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310946405 | 72500
2639142.84

## 4T2 CEMENT BLOCKS
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 CEMENT BLOCKS
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2023-04-03 | K N CONCEPTS(APAPS8825E) | Pur - T2 | 002-23/24 | 104893
104893

## 4T2 CHEMICAL MATERIAL
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 CHEMICAL MATERIAL
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2023-08-23 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T2 | VM/23-24/1394 | 93600
2023-10-12 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T2 | VM/23-24/1911 | 187200
2024-02-19 | KAVLES PRESSURE CONCRETE PVT LTD(AABCK8239K) | Pur - T2 | KPC/MEJ1/23-24 | 88900
2024-03-16 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T2 | VM/23-24/3523 | 38250
2024-03-27 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T2 | VM/23-24/3612 | 29700
437650

## 4T2 ELECTRIC MATERIAL
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 ELECTRIC MATERIAL
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2023-04-21 | N.K.TRADING CO.(AJEPP2160M) | Pur - T2 | 10753 | 3250
2023-07-18 | EAGLE SALES CORPORATION(AAAFE2557J) | Pur - T2 | 2/795-23/24 | 33040.74
2023-12-16 | N.K.TRADING CO.(AJEPP2160M) | Pur - T2 | 11399 | 46630
2024-02-06 | EAGLE SALES CORPORATION(AAAFE2557J) | Pur - T2 | 1/16880-23/24 | 107131.2
2024-02-16 | BHARAT ENGINEERS | Pur - T2 | 2657/2023-2024 | 100800
2024-02-16 | BHARAT ENGINEERS | Pur - T2 | 2658/2023-2024 | 68780
2024-02-17 | BHARAT ENGINEERS | Pur - T2 | 2673/2023-2024 | 43700
2024-02-20 | EAGLE SALES CORPORATION(AAAFE2557J) | Pur - T2 | 1/17708-23/24 | 11604.8
2024-03-23 | N.K.TRADING CO.(AJEPP2160M) | Pur - T2 | 11634 | 172800
587736.74

## 4T2 EXCAVATION LABOUR CHARGES
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 EXCAVATION LABOUR CHARGES
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2024-03-09 | ZC SEVEN HILLS CONSTRUCTIONS - GARDENS(ALFPR2696M) | Pur - T2 | 025/23-24 | 2000000
2000000

## 4T2 FABRICATION MATERAILS
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 FABRICATION MATERAILS
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2023-08-24 | ZC PARMAR KHIMJI MAVJI & CO(AALPP8208L) | Pur - T2 | 50/23-24 | 106401
2024-03-26 | ZC PARMAR KHIMJI MAVJI & CO(AALPP8208L) | Pur - T2 | 168-23-24 | 746086
852487

## 4T2 FIRE FITTING EQUIPMENTS
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 FIRE FITTING EQUIPMENTS
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2024-03-06 | ARYAN FIRE SAFETY AND SOLUTIONS | Pur - T2 | 171 | 39482
39482 |  |  |  | 39482

## 4T2 FREIGHT - W O GST
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 FREIGHT - W/O GST
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2023-05-09 | REAL INDUSTRIES(ACGPM3884J) | Pur - T2 | 0028/23-24 | 4000
4000 |  |  |  | 4000

## 4T2 GRILL & FABRICATION LABOUR
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 GRILL & FABRICATION LABOUR
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date | Particulars |  | Vch Type | Vch No. | Bank Date | Debit | Credit
2023-04-26 | Cr | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 186 |  | 87820
2023-04-26 | Cr | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 187 |  | 39150
2023-11-01 | Cr | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 221 |  | 22800
2024-03-02 | Cr | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 239 |  | 19600
2024-03-02 | Cr | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 240 |  | 26520
2024-03-02 | Cr | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 241 |  | 25500
2024-03-02 | Cr | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 242 |  | 36700
2024-03-02 | Cr | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 243 |  | 21500
2024-03-02 | Cr | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 244 |  | 47800
2024-03-02 | Cr | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 245 |  | 23500
2024-03-02 | Cr | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 246 |  | 6900
357790 | [5 empty] | 357790

## 4T2 HARDWARE
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 HARDWARE
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date | Particulars |  | Vch Type | Vch No. | Bank Date | Debit | Credit
2023-05-18 | Cr | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T2 | 72 |  | 1510
2023-07-21 | Cr | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T2 | 168 |  | 2998
2023-10-16 | Cr | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T2 | 288 |  | 1725
2023-10-17 | Cr | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T2 | 289 |  | 4710
2023-10-17 | Cr | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T2 | 290 |  | 700
2023-10-19 | Cr | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T2 | 295 |  | 4435
2023-10-22 | Cr | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T2 | 305 |  | 3140
2023-10-26 | Cr | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T2 | 309 |  | 2130
2024-02-29 | Cr | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T2 | 471 |  | 1430
22778 | [5 empty] | 22778

## 4T2 LABOUR CHARGES
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 LABOUR CHARGES
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date | Particulars |  | Vch Type | Vch No. | Bank Date | Debit | Credit
2023-04-05 | Cr | ZC UTRACON STRUCTURAL SYSTEMS PVT LTD - ONE MERAKI(AAACU6685L-M) | Pur - T2 | MH/2324/M012 |  | 58000
2023-04-24 | Cr | ZC ATRI BUILDTECH - RESI -T2 | Pur - T2 | CD/001 |  | 2500000
2023-05-23 | Cr | ZC ATRI BUILDTECH - RESI -T2 | Pur - T2 | CD/002 |  | 9082700
2023-08-02 | Cr | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T2 | 215 |  | 56672
2023-08-02 | Cr | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T2 | 214 |  | 56672
2023-08-21 | Cr | ZC UCON PT STRUCTURAL SYSTEM PVT LTD | Pur - T2 | MH/2324/M356 |  | 18000
2023-08-31 | Dr | ZC ATRI BUILDTECH - RESI -T2 | Debit Note | CD/002 |  | -9082700 | 9082700
2023-08-31 | Cr | ZC ATRI BUILDTECH - RESI -T2 | Pur - T2 | CD/002 |  | 9082700
2023-08-31 | Cr | ZC ATRI BUILDTECH - RESI -T2 | Pur - T2 | CD/003 |  | 8823100
2023-09-26 | Cr | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T2 | 224 |  | 64050
2023-10-12 | Cr | ZC UCON PT STRUCTURAL SYSTEM PVT LTD | Pur - T2 | MH/2324/264 |  | 13000
2023-10-30 | Cr | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T2 | 234 |  | 64050
2023-10-30 | Cr | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T2 | 233 |  | 64050
2023-12-01 | Dr | ZC ATRI BUILDTECH - RESI -T2 | Debit Note | T2/CD/002 |  | -5850 | 5850
2023-12-01 | Dr | ZC ATRI BUILDTECH - RESI -T2 | Debit Note | T2/CD/003 |  | -19067 | 19067
2023-12-01 | Dr | ZC ATRI BUILDTECH - RESI -T2 | Debit Note | T2/CD/004 |  | -25000 | 25000
2023-12-01 | Dr | ZC ATRI BUILDTECH - RESI -T2 | Debit Note | T2/CD/005 |  | -3417 | 3417
2023-12-04 | Dr | ZC ATRI BUILDTECH - RESI -T2 | Debit Note | T2/CD/0016 |  | -12500 | 12500
2024-02-28 | Dr | ZC ATRI BUILDTECH - RESI -T2 | Debit Note | T2/CD/0017 |  | -4230 | 4230
2024-02-28 | Dr | ZC ATRI BUILDTECH - RESI -T2 | Debit Note | T2/CD/0018 |  | -3350 | 3350
2024-02-28 | Dr | ZC ATRI BUILDTECH - RESI -T2 | Debit Note | T2/CD/0019 |  | -12500 | 12500
2024-02-28 | Dr | ZC ATRI BUILDTECH - RESI -T2 | Debit Note | T2/CD/0020 |  | -30850 | 30850
2024-03-12 | Cr | ZC JSA CONSTRUCTION(BHSPM4751L-P) | Pur - T2 | 03 |  | 122575
20806105

## 4T2 MARBLE
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 MARBLE
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date | Particulars |  | Vch Type | Vch No. | Bank Date | Debit | Credit
2024-03-01 | Cr | CHIMAN GRANITE MARBLE | Pur - T2 | 105 |  | 189050
2024-03-11 | Cr | CHIMAN GRANITE MARBLE | Pur - T2 | 126 |  | 149000
338050 | [5 empty] | 338050

## 4T2 MIVAN MATERIAL
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 MIVAN MATERIAL
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date | Particulars |  | Vch Type | Vch No. | Bank Date | Debit | Credit
2024-02-01 | Cr | DEEPSHIKHA ENTERPRISES | Pur - T2 | 398 |  | 972370
2024-02-01 | Cr | DEEPSHIKHA ENTERPRISES | Pur - T2 | 399 |  | 620365
2024-02-01 | Cr | DEEPSHIKHA ENTERPRISES | Pur - T2 | 400 |  | 29696
2024-02-09 | Cr | DEEPSHIKHA ENTERPRISES | Pur - T2 | 412 |  | 118132
2024-02-19 | Cr | DEEPSHIKHA ENTERPRISES | Pur - T2 | 417 |  | 333800
2024-02-19 | Cr | DEEPSHIKHA ENTERPRISES | Pur - T2 | 423 |  | 174200
2024-02-20 | Cr | DEEPSHIKHA ENTERPRISES | Pur - T2 | 424 |  | 247625
2496188 | [5 empty] | 2496188

## 4T2 PLUMBING MATERIAL
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 PLUMBING MATERIAL
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date | Particulars |  | Vch Type | Vch No. | Bank Date | Debit | Credit
2023-05-09 | Cr | REAL INDUSTRIES(ACGPM3884J) | Pur - T2 | 0028/23-24 |  | 285090
2023-05-09 | Cr | REAL INDUSTRIES(ACGPM3884J) | Pur - T2 | 0029/23-24 |  | 44275
2023-10-14 | Cr | A.B. AJMERA & CO(AAVFA0036B) | Pur - T2 | 105/2023-24 |  | 80617.22
2023-12-16 | Cr | KANERIA PLAST PVT LTD(AAFCK1826N) | Pur - T2 | KP/7917/23-24 |  | 155700
2023-12-20 | Cr | KANERIA PLAST PVT LTD(AAFCK1826N) | Pur - T2 | KP/8040/23-24 |  | 130500
2023-12-22 | Cr | KANERIA PLAST PVT LTD(AAFCK1826N) | Pur - T2 | KP/8104/23-24 |  | 121500
2023-12-22 | Cr | KANERIA PLAST PVT LTD(AAFCK1826N) | Pur - T2 | KP/8084/23-24 |  | 156600
2023-12-24 | Cr | KANERIA PLAST PVT LTD(AAFCK1826N) | Pur - T2 | KP/8151/23-24 |  | 160200
2024-03-30 | Cr | LIDCO BUILDING TECHNOLOGIES LLP | Pur - T2 | LIDCO/1310/23-24 |  | 27253.8
1161736.02 | [5 empty] | 1161736.02

## 4T2 READY MIX
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 READY MIX
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date | Particulars |  | Vch Type | Vch No. | Bank Date | Debit | Credit
2023-05-20 | Cr | BNC EQUIPMENT INDIA PVT.LTD | Pur - T2 | 1000/23-24-142 |  | 4350
2024-02-22 | Cr | BNC EQUIPMENT INDIA PVT.LTD | Pur - T2 | 1000/23-24-1009 |  | 8387.67
2024-02-22 | Cr | BNC EQUIPMENT INDIA PVT.LTD | Pur - T2 | 1000/23-24-1010 |  | 20989.17
2024-03-19 | Cr | NEEV ENTERPRISE(AAQFN6654B) | Pur - T2 | NE/0096/23-24 |  | 1249144.78
2024-03-21 | Cr | BNC EQUIPMENT INDIA PVT.LTD | Pur - T2 | 1000/23-24-1132 |  | 13195.77
2024-03-27 | Cr | BNC EQUIPMENT INDIA PVT.LTD | Pur - T2 | 1000/23-24-1160 |  | 5403.3
1301470.69 | [5 empty] | 1301470.69

## 4T2 REPAIRS & SERVICES
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 REPAIRS & SERVICES
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date | Particulars |  | Vch Type | Vch No. | Bank Date | Debit | Credit
2023-08-05 | Cr | MAURYA ELECTRICAL WORKS | Pur - T2 | 3487 |  | 15800
2023-08-18 | Cr | MAURYA ELECTRICAL WORKS | Pur - T2 | 3497 |  | 4650
2023-08-25 | Cr | MAURYA ELECTRICAL WORKS | Pur - T2 | 3500 |  | 7500
2023-08-29 | Cr | MAURYA ELECTRICAL WORKS | Pur - T2 | 3504 |  | 12500
2023-11-02 | Cr | MAURYA ELECTRICAL WORKS | Pur - T2 | 3526 |  | 19067
2023-11-02 | Cr | MAURYA ELECTRICAL WORKS | Pur - T2 | 3527 |  | 25000
2023-11-02 | Cr | MAURYA ELECTRICAL WORKS | Pur - T2 | 3528 |  | 3417
2023-11-06 | Cr | MAURYA ELECTRICAL WORKS | Pur - T2 | 3536 |  | 8650
2023-11-17 | Cr | MAURYA ELECTRICAL WORKS | Pur - T2 | 3539 |  | 5850
2023-11-26 | Cr | MAURYA ELECTRICAL WORKS | Pur - T2 | 3550 |  | 12500
2023-11-27 | Cr | MAURYA ELECTRICAL WORKS | Pur - T2 | 3551 |  | 28800
2023-11-29 | Cr | AQUARIUS ENGINEERS PVT LTD(AACCA2748L) | Pur - T2 | 2301S0496 |  | 5000
2023-12-04 | Cr | MAURYA ELECTRICAL WORKS | Pur - T2 | 3553 |  | 12500
2024-02-28 | Cr | MAURYA ELECTRICAL WORKS | Pur - T2 | 3571 |  | 3350
2024-02-28 | Cr | MAURYA ELECTRICAL WORKS | Pur - T2 | 3572 |  | 4230
2024-02-28 | Cr | MAURYA ELECTRICAL WORKS | Pur - T2 | 3573 |  | 30850
2024-02-28 | Cr | MAURYA ELECTRICAL WORKS | Pur - T2 | 3574 |  | 12500
212164 | [5 empty] | 212164

## 4T2 SAFETY NET EXPS
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 SAFETY NET EXPS
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date | Particulars |  | Vch Type | Vch No. | Bank Date | Debit | Credit
2023-04-03 | Cr | TUSHAR STEEL(AAEPK3479R) | Pur - T2 | TS/003 |  | 57786
2023-04-24 | Cr | TUSHAR STEEL(AAEPK3479R) | Pur - T2 | TS/022 |  | 34794
2024-01-12 | Cr | G.R. ENTERPRISE | Pur - T2 | 256/23-24 |  | 2600
2024-03-13 | Cr | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T2 | K16989 |  | 198730
2024-03-18 | Cr | G.R. ENTERPRISE | Pur - T2 | 327 |  | 4600
2024-03-27 | Cr | G.R. ENTERPRISE | Pur - T2 | 340 |  | 83000
2024-03-27 | Cr | G.R. ENTERPRISE | Pur - T2 | 341 |  | 82360
2024-03-28 | Cr | G.R. ENTERPRISE | Pur - T2 | 342 |  | 82160
2024-03-28 | Cr | G.R. ENTERPRISE | Pur - T2 | 343 |  | 86200
2024-03-29 | Cr | G.R. ENTERPRISE | Pur - T2 | 344 |  | 59420
2024-03-29 | Cr | G.R. ENTERPRISE | Pur - T2 | 345 |  | 78010
769660 | [5 empty] | 769660

## 4T2 SAND
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 SAND
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date | Particulars |  | Vch Type | Vch No. | Bank Date | Debit | Credit
2023-05-02 | Cr | NEEV ENTERPRISE(AAQFN6654B) | Pur - T2 | NE/0006/23-24 |  | 96449.2
2023-06-30 | Cr | NEEV ENTERPRISE(AAQFN6654B) | Pur - T2 | NE/0029/23-24 |  | 131457.42
2024-01-15 | Cr | NEEV ENTERPRISE(AAQFN6654B) | Pur - T2 | NE/0076/23-24 |  | 1225011.53
1452918.15 | [5 empty] | 1452918.15

## 4T2 STEEL
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 STEEL
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date | Particulars |  | Vch Type | Vch No. | Bank Date | Debit | Credit
2023-04-06 | Cr | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B60 |  | 2362258
2023-04-08 | Cr | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B84 |  | 2308680
2023-04-15 | Cr | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B157 |  | 801450
2023-04-15 | Cr | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B156 |  | 1214460
2023-05-09 | Cr | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T2 | K9300 |  | 1052940
2023-10-14 | Cr | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B1659 |  | 1739820
2024-02-23 | Cr | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B2716 |  | 2068580
2024-03-01 | Cr | BAKKA STEEL(AYMPK4501E) | Pur - T2 | B2B1014 |  | 99300
2024-03-07 | Cr | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B2859 |  | 2109975
2024-03-12 | Cr | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T2 | K16929 |  | 425830
2024-03-22 | Cr | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B3001 |  | 2095830
2024-03-23 | Cr | BAKKA STEEL(AYMPK4501E) | Pur - T2 | BS1065 |  | 136380
16415503 | [5 empty] | 16415503

## Summary Professional
Sr. No. | Particulars | Amount
1 | Professional | 661270
2 | Architect | 1934400
3 | Soil testing | 13200
TOTAL |  | 2608870

## 4T2 PROFESSIONAL FEES
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 PROFESSIONAL FEES
Ledger Account
( 09T2 LAISONING & PROFESSIONAL FEES )
1-Apr-22 to 31-Mar-24
Date | Particulars |  | Vch Type | Vch No. | Bank Date | Debit | Credit
2023-05-04 | Cr | ZP KAPURE & KAPURE(AAPFK3547F) | Pur - T2 | KK/2023/24/35 |  | 20000
2024-01-22 | Cr | ZP P R CONSULTANTS(AAHFP1742P) | Pur - T2 | PRC/2023-24/149 |  | 266270
2024-03-01 | Cr | ZPL VASMUM LEGAL(AAPFV6380F) | Pur - T2 | SBI/MHL/001 |  | 175000
2024-03-14 | Cr | ZPL SNG & PARTNERS(ACUPG6247R) | Pur - T2 | RE/303/23-24 |  | 200000
661270 | [5 empty] | 661270

## 4T2 SOIL TESTING
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 SOIL TESTING
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date | Particulars |  | Vch Type | Vch No. | Bank Date | Debit | Credit
2023-06-25 | Cr | ZP F M TESTING LAB(AOMPP6000R) | Pur - T2 | 0864 |  | 13200
13200 | [5 empty] | 13200

## 4T2 ARCHITECT & ENGG FEES
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 ARCHITECT & ENGG FEES
Ledger Account
( 09T2 LAISONING & PROFESSIONAL FEES )
1-Apr-22 to 31-Mar-24
Date | Particulars |  | Vch Type | Vch No. | Bank Date | Debit | Credit
2023-06-26 | Cr | ZP SHANGHVI & ASSOCIATES CONSULTANTS PVT LTD(AALCS3411K) | Pur - T2 | SACPL/095/22-23 |  | 1934400
1934400 | [5 empty] | 1934400

## Summary Admin
Sr. No. | Particulars | Amount
1 | Water Charges | 43200
2 | Bank Processing Fees | 2720500
3
TOTAL |  | 2763700

## 4T2 WATER CHARGES
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 WATER CHARGES
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date | Particulars |  | Vch Type | Vch No. | Bank Date | Debit | Credit
2024-01-08 | Cr | ASHTA VINAYAK WATER SUPPLIERS | Pur - T2 | 1520 |  | 43200
43200 | [5 empty] | 43200
2024-03-30 | Cr | 2Z STATE BANK OF INDIA - 6965-ESCROW ACCOUNT ONE MERAKI WING C & WING D -30%(42038426965) | Payment | ESBTER | 2024-03-31 | 1355500
E-STAMP PAPER 1355500/- FOR MORTGAGE CUM LOAN AGREEMENT WITH STATE BANK OF INDIA FOR 45 Cr PAID 1 Loan agreement Rs.600/- 2 Guarantee Agreement Rs.600/- 3 Hypothecation Agreement Rs.13,51,500/-(0.3% of loan amount+1500) 4 Escrow agreement Rs.200/- 5 Arrangement letter Rs.500/- 6 Memorandum of Understanding Rs.500/- 7 Security Trustee Agreement Rs.1600/- TOTAL Rs.13,55,500/-
2024-03-31 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129(0077002102302129) | Payment | STAMP DUTY +REG | 2024-03-31 | 1365000
STAMP DUTY 1350000/- + REGISTRATION 15000/- FOR MORTGAGE CUM LOAN AGREEMENT WITH STATE BANK OF INDIA FOR 45 Cr PAID
2720500

## Marketing
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 STAMP DUTY & REGISTRATION CHARGES
Ledger Account
( 01T2 LAND COST )
1-Apr-01 to 31-Mar-24
Date | Particulars |  | Vch Type | Vch No. | Bank Date | Debit | Credit
2023-03-25 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2023-03-25 | 30000
REG.FEES 30,000 PAID FOR SALE DEED - VINODKUMAR TANDEL ON OUR BEHALF
2023-03-25 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2023-03-25 | 698000
FOR REG.FEES 30,0000 & STAMP DUTY 6,68,000/- PAID FOR SURRENDER OF TENANCY - VINODKUMAR TANDEL ON OUR BEHALF
2023-03-31 | Cr | ZP AMIN R RATNANI | Pur - T2 | R/44/22-23 |  | 10000
TOWARDS REGISTRATION OF AGREEMENT ON ALLOTMENT BASIS BETWEEN MERAKI HABITATS LLP & M/S. BHAYANI INVESTMENTS, REGISTERES UNDER KRL5-6513-2023
2023-03-31 | Cr | AMIN R RATNANI | Pur - T2 | R/44/22-23 |  | 2800
TOWARDS REGISTRATION OF AGREEMENT ON ALLOTMENT BASIS BETWEEN MERAKI HABITATS LLP & M/S. BHAYANI INVESTMENTS, REGISTERES UNDER KRL5-6513-2023 DEBIT NOTE
2023-03-31 | Cr | AMIN R RATNANI | Pur - T2 | R/41/22-23 |  | 1000
TOWARDS DOCUMENTS HANDLING CHARGES ACTUAL FOR REGISTRATION OF SURRENDER OF LEASE BETWEEN MEARKI HABITATS LLP & MR . VINODKUMAR DAHYABHAI TANDEL , REGISTERED UNDER KRL5-6395-2023
2023-03-31 | Cr | ZP AMIN R RATNANI | Pur - T2 | R/41/22-23 |  | 10000
TOWARDS REGISTRATION OF SURRENDER OF LEASE BETWEEN MEARKI HABITATS LLP & MR . VINODKUMAR DAHYABHAI TANDEL , REGISTERED UNDER KRL5-6395-2023
2023-03-31 | Cr | ZP AMIN R RATNANI | Pur - T2 | R/43/22-23 |  | 5000
TOWARDS REGISTRATION OF SALE DEED BETWEEN MR. SHEETAL ANIL GANDHI & MR. VINODKUMAR DAHYABHAI TANDEL , REGISTERED UNDER KRL5-6392-2023
2023-03-31 | Cr | AMIN R RATNANI | Pur - T2 | R/43/22-23 |  | 520
TOWARDS DOCUEMENTS HANDLING CHARGES AS ACTUAL SALE DEED BETWEEN MR. SHEETAL ANIL GANDHI & MR. VINODKUMAR DAHYABHAI TANDEL , REGISTERED UNDER KRL5-6392-2023 DEBIT NOTE
2023-03-31 | Dr | 22 WORK IN PROGRESS - TOWER - 2 | Journal |  |  |  | 757320
TRFD & CLOSED
2023-04-27 | Cr | ZP AMIN R RATNANI | Pur - T2 | R/01/23-24 |  | 5000
TOWARDS REGISTRATION OF DEED OF RECTIFICATION BETWEEN MR SHEETAL ANI GANDHI & VINOD KUMAR DAHYABHAI TANDEL REGISTERED UNDER KRL5 -8263-2023
2023-04-27 | Cr | AMIN R RATNANI | Pur - T2 | R/01/23-24 |  | 800
TOWARDS REGISTRATION OF DEED OF RECTIFICATION BETWEEN MR SHEETAL ANI GANDHI & VINOD KUMAR DAHYABHAI TANDEL REGISTERED UNDER KRL5 -8263-2023 DEBIT NOTE
2023-08-07 | Cr | ZS VISHAL MAHADU TAPAL | Journal | REG FEES + STAMP DUTY |  | 96000
FOR STAMP DUTY 80,000/- & REGS.FEES 16,000 PAID FOR SURRENDER OF TENANCY - JAYSAWAR FULCHAND ON OUR BEHALF
2023-08-11 | Cr | AMIN R RATNANI | Pur - T2 | R/22/23-24 |  | 4240
DEBIT NOTE RS.4241/-, TOWARDS DOCUMENTS HANDELING CHARGES AS ACTUAL OF REGISTRATION OF FOUR NOS. SURRENDER OF TENANCY BETWEEN MERAKI AND MR BABLU JAYSWAR
2023-08-21 | Cr | ZP AMIN R RATNANI | Pur - T2 | R/22/23-24 |  | 20000
TOWARDS REGISTRATION OF SURRENDER OF TENANCY BETWEEN MR.BABLU JAYSAWAR, MR LUCKY JAYASWAR & MR MANJU JAISWAL UNDER KRL1-16590-20236, KRL1-16591-2023, KRL1-16595-2023 & KRL1-16593-2023
2023-08-22 | Cr | ZS VISHAL MAHADU TAPAL | Journal | REG FEES + STAMP DUTY |  | 30012
FOR STAMP DUTY 25,000/- & REGS.FEES 5,000 PAID FOR SURRENDER OF TENANCY - SHAIKH RUBINA MOHSIN ON OUR BEHALF ( BK CHGS 12)
2023-08-22 | Cr | ZS VISHAL MAHADU TAPAL | Journal | REG FEES + STAMP DUTY |  | 30012
FOR STAMP DUTY 25,000/- & REGS.FEES 5,000 PAID FOR SURRENDER OF TENANCY - SHABANA RAFIQ KHAN ON OUR BEHALF ( BK CHGS 12)
2023-08-23 | Cr | ZP AMIN R RATNANI | Pur - T2 | R/23/23-24 |  | 10000
TOWARDS REGISTRATION OF SURRENDER OF TENANCY , CONSULTATION FEES , KRL5-17860-2023, KRL5-117858-2023
2023-08-24 | Cr | ZS VISHAL MAHADU TAPAL | Journal | REG FEES + STAMP DUTY |  | 330012
FOR STAMP DUTY 3,00,000/- & REGS.FEES 30,000 PAID FOR SURRENDER OF TENANCY - BADRUNISHA YASIN CHAVAN & AKRAM YASIN CHAVAN ON OUR BEHALF ( BK CHGS 12)
2023-08-29 | Cr | ZP AMIN R RATNANI | Pur - T2 | R/24/23-24 |  | 5000
BILL NO - R/24/23-24, CONSULTATION FEES TOWARDS REGISTERATION OF TWO NO.S AGREEMENT FOR SALE BETWEEN MERAKI HABITATS LLP AND MRS BANDRUNISHA YASIN CHAVAN & MR AKRAM YASIN CHAVAN REGISTERED UNDER KRL5-181172-2023
2023-08-29 | Cr | AMIN R RATNANI | Pur - T2 | R/24/23-24 |  | 960
DEBIT NOTE FOR DOCUMNET HANDLING CHARGES OF REGISTRATION FOR ONE MERAKI C & D WING
2023-10-20 | Cr | ZS VISHAL MAHADU TAPAL | Journal | REG FEES + STAMP DUTY |  | 280012
FOR STAMP DUTY 2,50,000/- & REGS.FEES 30,000 PAID FOR SURRENDER OF TENANCY - AYUB KHAN ON OUR BEHALF ( BK 12)
2024-01-11 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2024-01-11 | 500000
FOR STAMP DUTY 4,70,000/- & REGS.FEES 30,000 PAID FOR SURRENDER OF TENANCY - HAFIJA ABBAS KHAN ON OUR BEHALF
2024-01-30 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2024-01-30 | 90000
FOR STAMP DUTY 75,000/- & REGS.FEES 15,000 PAID FOR SURRENDER OF TENANCY - SHAQUIB SHAFIQUE SHAIKH ON OUR BEHALF
2024-01-30 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2024-01-30 | 90000
FOR STAMP DUTY 75,000/- & REGS.FEES 15,000 PAID FOR SURRENDER OF TENANCY - SHAHBAZ SHAFIQUE SHAIKH ON OUR BEHALF
2024-01-30 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2024-01-30 | 90000
FOR STAMP DUTY 75,000/- & REGS.FEES 15,000 PAID FOR SURRENDER OF TENANCY - SHAHNAWAZ SHAFIQUE SHAIKH ON OUR BEHALF
2024-01-30 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2024-01-30 | 90000
FOR STAMP DUTY 75,000/- & REGS.FEES 15,000 PAID FOR SURRENDER OF TENANCY - ASMABI SHAFIQUE SHAIKH ON OUR BEHALF
2024-02-01 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2024-02-01 | 150000
FOR STAMP DUTY 125,000/- & REGS.FEES 25,000 PAID FOR SURRENDER OF TENANCY - JAVED NASRUBHAI SAYED ON OUR BEHALF
2024-02-01 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2024-02-01 | 150000
FOR STAMP DUTY 125,000/- & REGS.FEES 25,000 PAID FOR SURRENDER OF TENANCY - IMARAN NASRUBHAI SAYED ON OUR BEHALF
2024-02-01 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2024-02-01 | 150000
FOR STAMP DUTY 125,000/- & REGS.FEES 25,000 PAID FOR SURRENDER OF TENANCY - MOSIM NASRUBHAI SAYED ON OUR BEHALF
2024-02-01 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2024-02-01 | 150000
FOR STAMP DUTY 125,000/- & REGS.FEES 25,000 PAID FOR SURRENDER OF TENANCY - YAKUB K SAYED ON OUR BEHALF
2024-02-04 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2024-02-04 | 150000
FOR STAMP DUTY 125,000/- & REGS.FEES 25,000 PAID FOR SURRENDER OF TENANCY - MEHBOOB KHAN ON OUR BEHALF
2024-02-07 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY - C308 CENTRIO | 2024-02-07 | 239000
FOR STAMP DUTY 209,000/- & REGS.FEES 30,000 PAID FOR SALE OF AGRREEMENT - MEHBOOB KHAN ON OUR BEHALF -CENTRIO BY MJ SHAH C-308
2024-02-07 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY - C307 CENTRIO | 2024-02-07 | 239000
FOR STAMP DUTY 209,000/- & REGS.FEES 30,000 PAID FOR SALE OF AGRREEMENT - CHAND MEHBOOB KHAN ON OUR BEHALF -CENTRIO BY MJ SHAH C-307
2024-02-23 | Cr | ZP AMIN R RATNANI | Pur - T2 | R/57/23-24 |  | 20000
TOWARDS REGISTRATION OF 4 NOS. SURRENDER OF TENANCY BETWEEN MERAKI HABITATS LLP AND 1) MR. SHAILESH HARI GHADSE, 2) MRS MINALI CHANDDRAKANT PISE, 3) MR DAYAL CHANDRAKANT PISE AND 4) MR ROHTI CHANDRAKANT PISE ALL REGISTERED UNDER KRL5-3680-2024, KRL5-4581-2024, KRL5-4580-2024 AND KRL5-4582-2024
2024-02-23 | Cr | AMIN R RATNANI | Pur - T2 | R/57/23-24 |  | 4100
TOWARDS DOCUMENTS HANDLING CHARGES AS ACTUAL OF REGISTRATION OF 4 NOS. SURRENDER OF TENANCY BETWEEN MERAKI HABITATS LLP AND 1) MR. SHAILESH HARI GHADSE, 2) MRS MINALI CHANDDRAKANT PISE, 3) MR DAYAL CHANDRAKANT PISE AND 4) MR ROHTI CHANDRAKANT PISE ALL REGISTERED UNDER KRL5-3680-2024, KRL5-4581-2024, KRL5-4580-2024 AND KRL5-4582-2024
2024-03-01 | Cr | ZP AMIN R RATNANI | Pur - T2 | R/60/23-24 |  | 10000
TOWARDS REGISTRATION OF 2 NOS. OF AGREEMENT FOR SIDE BETWEEN MERAKI HABITATS LLP AND 1) NEETU SINGH AND 2) MS. RANJEETA SINGH, REGISTERED UNDER KRL5-5295-2024 & KRL5-5300-2024
2024-03-01 | Cr | AMIN R RATNANI | Pur - T2 | R/60/23-24 |  | 6560
TOWARDS DOCUMENTS HANDLING CHARGES AS ACTUAL OF REGISTRATION OF 2 NOS. OF AGREEMENT FOR SALE BETWEEN MERAKI HABITATS LLP AND 1) MS. NEETU SINGH AND 2) MS. RANJEETA SINGH, REGISTERED UNDER KRL5-5295-2024 &KRL5-5300-2024.
3698028

## Approval Cost
Annexure II
Sr. No | Nature of Charges - One Meraki - Wing A & Wing B | Paid Date | Receipt Amount
1 | PAID TO MCGM FOR SCRUTINY FEES 80500 + DEBRIS REMOVAL 20200 + I.O.D. DEPOSIT 10100 + ( BK CHGS1308 ) - One Meraki | 2021-06-21 | 55400
2 | PAID TO MCGM FOR SCRUTINY FEES - RESIDENANCE | 2021-06-29 | 418600
3 | PAID FOR DEMAND NOTE CFO NOC - BLDG - 1 ( 545546 + CHGS 12 ) | 2021-10-11 | 272773
4 | PAID TO MCGM FOR SCRUTINY FEES - SWD | 2021-10-13 | 129500
5 | PAID TO MCGM FOR REVALIDATIONS - SWD | 2021-10-13 | 388400
6 | PAID FOR DEMAND NOTE CFO NOC - BLDG - 1 ( 1004340 + CHGS 12 ) | 2021-11-02 | 502176
7 | PAID FOR MCGM BLDG NO.1 SCRUTINY FEES ( NEW PROPOSALS U/S 337 & 342 ) FEES 13750 + ONLINE CHARGES 163 | 2021-12-08 | 6875
8 | PAID FOR MCGM BLDG NO.1 SCRUTINY FEES FOR TDR & ACCOM RESERVATION UTILISATION FEES 13750 + ONLINE CHARGES 12 | 2021-12-09 | 285503
9 | PAID FOR MCGM BLDG NO.1 SCRUTINY FEES FOR TDR UTILISATION FEES 159800 + ONLINE CHARGES 12 | 2021-12-13 | 79900
10 | Scrutiny Fees (New Proposals U/S 337 & 342 | 2021-12-23 | 2790000
11 | Development Cess 33(7) | 2021-12-23 | 5708100
12 | Premium for Staircase, Lift, Lift Lobby area | 2021-12-23 | 23360125
13 | Premium for .50 % Addition F.S.I | 2021-12-23 | 5437350
14 | Premium for Fungible F.S.I | 2021-12-23 | 32650325
15 | I.O.D Deposit | 2021-12-23 | 142350
16 | Premium for deficiency in Open Space | 2021-12-23 | 3460850
17 | Labour Welfare Cess (ADM -1% ) | 2021-12-23 | 40050
18 | Other deficiency Premium | 2021-12-23 | 201450
19 | 5% Premium for TDR Utilizations | 2021-12-23 | 7675050
20 | Labour Welfare Cess (Tax/Fund - 99% ) | 2021-12-23 | 3960600
21 | Permissible additional 0.50 F.S.I Dharavi redevelopment project (DRP) | 2021-12-23 | 5437350
22 | Premium for paved/ perforated RG | 2021-12-23 | 105200
23 | Premium for conversion of zone from I to R/ C reg 14 B | 2021-12-23 | 10647175
24 | MSRDC share towards Fungible FSI reg 31(3) | 2021-12-23 | 13060125
25 | MSRDC Share towards 0.50 Addi. FSI reg 30 | 2021-12-23 | 5437350
26 | 25% SHARE GOVT 0.50 FSI CHE ES 0840 M W 337 NEW | 2021-12-23 | 5437306.5
27 | 30% SHARE GOVT FUNGIBLE AREA CHE ES 0840 M W 337 NEW | 2021-12-23 | 19590187
28 | MCGM-PROPERTY TAX-MW090744307000- APR/MAR'21 (SABARI GARDENS) | 2021-12-29 | 1970122
29 | 50% SHARE GOVT AS PER REG 14B OF DCPR 2034 FOR I TO R FILE NO CHE ES 0840 M W 337 NEW | 2021-12-30 | 5323587.5
30 | PAID FOR LOC TAX - MCGM | 2022-03-21 | 3950000
| TOTAL - A |  | 158523780
1 | MARKET TDR -MAHAAVIR ASSOCIATES - | 2021-06-07 | 1750000
2 | MARKET TDR -MAHAAVIR ASSOCIATES - | 2021-06-07 | 2800000
3 | MARKET TDR -RELIABLE BUILDERS DEVELOPERS | 2021-11-23 | 16982567.5
4 | MARKET TDR-ENTIRE ESTATES PRIVATE LIMITED | 2021-11-25 | 56550000
| TOTAL - B |  | 78082567.5
| TOTAL - A+B |  | 236606347.5
1 | Balance Cost for Approval |  | 13300000
| TOTAL - A+B+C |  | 249906347.5

## Interest
Sr. No. | Particulars | Amount | Amount in ` Cr. | Amount | Amount in ` Cr. | Balance | Balance in Cr.
| September secured interest |  |  |  |  | 0 | 0
| October |  |  |  |  | 0 | 0
| November |  |  |  |  | 0 | 0
| December |  |  |  |  | 0 | 0
| Jan to March |  |  |  |  | 0 | 0
| April to June |  |  |  |  | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0

## Construction Area of Sale Build
Summary of Cost of Construction
Plinth Area Calculation
Sr. No | Floor Nos. | Total Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | Percentage of work completed | Actual Expenditure till date in `
1 | Excavation |  |  |  | 50738418 | 100% | 50738418
2 | Basement 1 | 1761.59 | 1761.59 | 30000 | 52847700 | 50% | 26423850
3 | Basement 2 | 1761.59 | 1761.59 | 30000 | 52847700 | 50% | 26423850
4 | Basement 3 | 1761.59 | 1761.59 | 30000 | 52847700 | 50% | 26423850
5 | Ground Floor | 1860.68 | 1860.68 | 30000 | 55820400 | 50% | 27910200
6 | 1st Podium Floor | 794.1 | 794.1 | 30000 | 23823000 | 40% | 9529200
7 | 2nd Floor | 496.756 |  | 30000 | 14902680 | 0% | 0
8 | 3rd Floor | 496.756 |  | 30000 | 14902680 | 0% | 0
9 | 4th Floor | 496.756 |  | 30000 | 14902680 | 0% | 0
10 | 5th Floor | 496.756 |  | 30000 | 14902680 | 0% | 0
11 | 6th Floor | 496.756 |  | 30000 | 14902680 | 0% | 0
12 | 7th Floor | 491.46 |  | 30000 | 14743800 | 0% | 0
13 | 8th Floor | 498.306 |  | 30000 | 14949180 | 0% | 0
14 | 9th Floor | 496.756 |  | 30000 | 14902680 | 0% | 0
15 | 10th Floor | 496.756 |  | 30000 | 14902680 | 0% | 0
16 | 11th Floor | 496.756 |  | 30000 | 14902680 | 0% | 0
17 | 12th Floor | 496.756 |  | 30000 | 14902680 | 0% | 0
18 | 13th Floor | 496.756 |  | 30000 | 14902680 | 0% | 0
19 | 14th Floor | 491.45 |  | 30000 | 14743500 | 0% | 0
20 | 15th Floor | 498.306 |  | 30000 | 14949180 | 0% | 0
21 | 16th Floor | 496.756 |  | 30000 | 14902680 | 0% | 0
22 | 17th Floor | 496.756 |  | 30000 | 14902680 | 0% | 0
23 | 18th Floor | 496.756 |  | 30000 | 14902680 | 0% | 0
24 | 19th Floor | 496.756 |  | 30000 | 14902680 | 0% | 0
25 | Terrace | 39.15 |  | 30000 | 1174500 | 0% | 0
Total |  | 16912.806 | 7939.55 |  | 558122598 | 30% | 167449368
|  |  | 0.46944 |  |  |  | 16.7449

## Construction Area (2)
COST OF CONSTRUCTION WING C
Sr. No | Floor Nos. | Built Up Area in Sq. M. | Balcony/FB/ Terrace Area/ Chhajja in Sq. M. | Staircase & Lift Area in Sq. M. | REFUGE AREA in Sq. M. | Stlit Area in Sq. M. | Meter Room/ Electric room / DG Room area in Sq. M. | Lobby Area in Sq. M. | Other Area/ Gents Toilet/Fitness Centre in Sq. M. | Total Area in Sq. M.
1 | Basement 1 | 0 | 0 | 0 | 0 | 1761.59 | 0 | 0 | 0 | 1761.59 | 18961.7548
2 | Basement 2 | 0 | 0 | 0 | 0 | 1761.59 | 0 | 0 | 0 | 1761.59 | 18961.7548
3 | Basement 3 | 0 | 0 | 0 | 0 | 1761.59 | 0 | 0 | 0 | 1761.59 | 18961.7548
4 | Ground Floor | 0 | 0 | 72.4 | 0 | 1717.52 | 70.76 | 0 | 0 | 1860.68 | 20028.3595
5 | 1st Podium Floor | 86.08 | 0 | 72.4 | 0 | 0 | 0 | 0 | 635.62 | 794.1 | 8547.6924
6 | 2nd Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
7 | 3rd Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
8 | 4th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
9 | 5th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
10 | 6th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
11 | 7th Floor | 302.21 | 2.04 | 71.12 | 112.72 | 0 | 0 | 0 | 3.37 | 491.46 | 5290.0754
12 | 8th Floor | 414.92 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 498.306 | 5363.7658
13 | 9th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
14 | 10th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
15 | 11th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
16 | 12th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
17 | 13th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
18 | 14th Floor | 304.13 | 2.04 | 71.12 | 110.79 | 0 | 0 | - | 3.37 | 491.45 | 5289.9678
19 | 15th Floor | 414.92 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 498.306 | 5363.7658
20 | 16th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
21 | 17th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
22 | 18th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
23 | 19th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
24 | Terrace | 0 | 0 | 39.15 | 0 | 0 | 0 | 0 | 0 | 39.15 | 421.4106
| Total | 7309.44 | 200.336 | 1464.11 | 223.51 | 7002.29 | 70.76 | 0 | 642.36 | 16912.806 | 182049.4438
|  | 78678.8122 | [7 empty] | 30000 | 3000
[10 empty] | 507384180 | 546148331
[9 empty] | 10% of Excavation | 50738418 | 54614833
[9 empty] | TOTAL | 558122598 | 600763164