## Final Summary
Project expenses | Estimated Cost as per Cost Vetting | Incurred Cost as per Bill till 31.03.2024 | Incurred Cost as per CA till 31.03.2024 | Incurred Cost as per Bill till 31.12.2023 | Incurred Cost as per CA till 31.12.2023 | Difference between the Bills & CA | Difference between both the Bills | Difference between both CA | Remark
Land Cost | 19.82 | 19.82 | 19.82 | 19.82 | 19.82 | 0 | 0 | 0
Construction Cost of Sale Building | 109.27 | 111.68 | 101.51 | 102.42 | 95.74 | 10.17 | 9.26 | 5.77 | Unpaid bills of 11.34 Cr.
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 24.99 | 23.66 | 23.66 | 23.66 | 23.66 | 0 | 0 | 0
Architect Cost, RCC & other Professional fees | 5.46 | 2.92 | 4.46 | 2.84 | 3.88 | 1.3 | 0.08 | 0.58
On- site expenditure for development / Advance for Project / Administrative Cost / Fixed Assets | 3.28 | 2.84 |  | 1.75 |  |  | 1.09 |  | .
Marketing Expenses | 6.62 | 8.39 | 7.93 | 6.82 | 6.33 | 0.46 | 1.57 | 1.6
Interest Cost | 10.25 | 5.48 | 6.07 | 4.31 | 4.31 | -0.59 | 1.17 | 1.76
Contingency Cost | 5.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost | 185.15 | 174.79 | 163.45 | 161.62 | 153.74 | 11.34 | 13.17 | 9.71
|  | 10.36 | 11.34
Particulars | Revised Estimated Cost (in Cr.) | 31.03.2024 as per Bill Tally (inclusive of GST) | Cost incurred as %age total cost of that Component | Cost incurred as %age of cost incurred as on 31.03.2024
Land Cost | 19.82 | 19.82 | 100% | 10.7%
Construction Cost | 109.27 | 111.68 | 102.2% | 60.32%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 24.99 | 23.66 | 94.68% | 12.78%
Architect Cost, RCC & other Professional fees | 5.46 | 2.92 | 53.48% | 1.577%
On- site expenditure for development / Advance for Project/ Administrative Cost/ Fixed Assets | 3.28 | 2.84 | 86.59% | 1.534%
Marketing Expenses | 6.62 | 8.39 | 126.7% | 4.531%
Interest Cost | 10.25 | 5.48 | 53.46% | 2.96%
Contingency | 5.46 | 0 | 0% | 0%
Total | 185.15 | 174.79 | 94.4% | 94.4%
Pariculars | 31.03.2024 as per Bill Tally (inclusive of GST) | 31.12.2023 as per Bill Tally (inclusive of GST) | Difference b/w bills of 31.03.2024 & 31.12.2023 | Difference of Cost incurred as %age of cost incurred as on 31.03.2024 & 31.12.2023
Land Cost | 19.82 | 19.82 | 0 | 0%
Construction Cost | 111.68 | 102.42 | 9.26 | 5.298%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 23.66 | 23.66 | 0 | 0%
Architect Cost, RCC & other Professional fees | 2.92 | 2.84 | 0.08 | 0.04577%
On- site expenditure for development / Advance for Project/ Administrative Cost/ Fixed Assets | 2.84 | 1.75 | 1.09 | 0.6236%
Marketing Expenses | 8.39 | 6.82 | 1.57 | 0.8982%
Interest Cost | 5.48 | 4.31 | 1.17 | 0.6694%
Contingency | 0 | 0 | 0 | 0%
Total | 174.79 | 161.62 | 13.17 | 7.535%

## Summary Sheet
Sr. No. | Particulars | Incurred Cost in ` till 31.03.2024 | Incurred Cost in ` Cr. Till 31.12.2024 | Incurred Cost in ` till 31.12.2023 | Incurred Cost in ` Cr. Till 31.12.2023 | Balance | Balance in Cr.
1 | Land Cost | 198240326 | 19.82 | 198240326 | 19.82 | 0 | 0
2 | Construction Cost | 1116835031 | 111.68 | 1024211066 | 102.42 | 92623965 | 9.2624
3 | Approval Cost & Stamp Duty | 236606348 | 23.66 | 236606348 | 23.66 | 0 | 0
4 | Professional Cost | 29219120.59 | 2.92 | 28375170.59 | 2.84 | 843950 | 0.084395
5 | Admin Cost | 28439396.15 | 2.84 | 17518332.15 | 1.75 | 10921064 | 1.0921
6 | Marketing Cost | 83927783 | 8.39 | 68213161 | 6.82 | 15714622 | 1.5715
7 | Interest Cost | 54793788 | 5.48 | 43086903 | 4.31 | 11706885 | 1.1707
| Total | 1748061792.74 | 174.79 | 1616251306.74 | 161.62 | 131810486 | 13.181
102500000
47706212
0.08

## Land
S.No | Land Cost: | Amount (in Rs.)
1 | Payment to Land Owners | 437153000
2 | Payment to Tenants | 304088299
741241299
3 | Stamp Duty | 38602044
| Total Land Cost | 779843343
Note: | The Stamp duty at 5% of total cost incurred i.e. 74.12 cr is approx 3.86 crs which has been paid.
S.No | Particulars | Land Cost (in Rs.) | BUA | % of Land Covered
1 | Arena ( Commercial ) | 219607901.4734 | 16122.03 | 28.16%
2 | One Meraki -Wing A & B | 193040325.8621 | 14171.63 | 24.75%
3 | One Meraki -Wing C & D) | 196780681.9875 | 14446.22 | 25.23%
4 | One Meraki -Wing E | 79841530.9745 | 5861.39 | 10.24%
4 | Platina | 90572902.7025 | 6649.21 | 11.61%
|  | 779843343 | 57250.48 | 100%
Additional Stamp Duty Cost inccured for One Meraki -Wing A & B = 52,00,000
So the total land cost = 19,30,40,325/- + 52,00,000/- = Rs. 19,82,00,000/-
| One Meraki | 193040325.8621
| Stamp Duty | 5200000
| Total Land Cost | 198240326

## Approval Cost
Annexure II
Sr. No | Nature of Charges - One Meraki - Wing A & Wing B | Paid Date | Receipt Amount
1 | PAID TO MCGM FOR SCRUTINY FEES 80500 + DEBRIS REMOVAL 20200 + I.O.D. DEPOSIT 10100 + ( BK CHGS1308 ) - One Meraki | 2021-06-21 | 55400
2 | PAID TO MCGM FOR SCRUTINY FEES - RESIDENANCE | 2021-06-29 | 418600
3 | PAID FOR DEMAND NOTE CFO NOC - BLDG - 1 ( 545546 + CHGS 12 ) | 2021-10-11 | 272773
4 | PAID TO MCGM FOR SCRUTINY FEES - SWD | 2021-10-13 | 129500
5 | PAID TO MCGM FOR REVALIDATIONS - SWD | 2021-10-13 | 388400
6 | PAID FOR DEMAND NOTE CFO NOC - BLDG - 1 ( 1004340 + CHGS 12 ) | 2021-11-02 | 502176
7 | PAID FOR MCGM BLDG NO.1 SCRUTINY FEES ( NEW PROPOSALS U/S 337 & 342 ) FEES 13750 + ONLINE CHARGES 163 | 2021-12-08 | 6875
8 | PAID FOR MCGM BLDG NO.1 SCRUTINY FEES FOR TDR & ACCOM RESERVATION UTILISATION FEES 13750 + ONLINE CHARGES 12 | 2021-12-09 | 285503
9 | PAID FOR MCGM BLDG NO.1 SCRUTINY FEES FOR TDR UTILISATION FEES 159800 + ONLINE CHARGES 12 | 2021-12-13 | 79900
10 | Scrutiny Fees (New Proposals U/S 337 & 342 | 2021-12-23 | 2790000
11 | Development Cess 33(7) | 2021-12-23 | 5708100
12 | Premium for Staircase, Lift, Lift Lobby area | 2021-12-23 | 23360125
13 | Premium for .50 % Addition F.S.I | 2021-12-23 | 5437350
14 | Premium for Fungible F.S.I | 2021-12-23 | 32650325
15 | I.O.D Deposit | 2021-12-23 | 142350
16 | Premium for deficiency in Open Space | 2021-12-23 | 3460850
17 | Labour Welfare Cess (ADM -1% ) | 2021-12-23 | 40050
18 | Other deficiency Premium | 2021-12-23 | 201450
19 | 5% Premium for TDR Utilizations | 2021-12-23 | 7675050
20 | Labour Welfare Cess (Tax/Fund - 99% ) | 2021-12-23 | 3960600
21 | Permissible additional 0.50 F.S.I Dharavi redevelopment project (DRP) | 2021-12-23 | 5437350
22 | Premium for paved/ perforated RG | 2021-12-23 | 105200
23 | Premium for conversion of zone from I to R/ C reg 14 B | 2021-12-23 | 10647175
24 | MSRDC share towards Fungible FSI reg 31(3) | 2021-12-23 | 13060125
25 | MSRDC Share towards 0.50 Addi. FSI reg 30 | 2021-12-23 | 5437350
26 | 25% SHARE GOVT 0.50 FSI CHE ES 0840 M W 337 NEW | 2021-12-23 | 5437306.5
27 | 30% SHARE GOVT FUNGIBLE AREA CHE ES 0840 M W 337 NEW | 2021-12-23 | 19590187
28 | MCGM-PROPERTY TAX-MW090744307000- APR/MAR'21 (SABARI GARDENS) | 2021-12-29 | 1970122
29 | 50% SHARE GOVT AS PER REG 14B OF DCPR 2034 FOR I TO R FILE NO CHE ES 0840 M W 337 NEW | 2021-12-30 | 5323587.5
30 | PAID FOR LOC TAX - MCGM | 2022-03-21 | 3950000
| TOTAL - A |  | 158523780
1 | MARKET TDR -MAHAAVIR ASSOCIATES - | 2021-06-07 | 1750000
2 | MARKET TDR -MAHAAVIR ASSOCIATES - | 2021-06-07 | 2800000
3 | MARKET TDR -RELIABLE BUILDERS DEVELOPERS | 2021-11-23 | 16982567.5
4 | MARKET TDR-ENTIRE ESTATES PRIVATE LIMITED | 2021-11-25 | 56550000
| TOTAL - B |  | 78082567.5
| TOTAL - A+B |  | 236606347.5
1 | Balance Cost for Approval |  | 13300000
| TOTAL - A+B+C |  | 249906347.5

## Construction Cost
DIRECT EXP - TOWER - 1
Group Summary
1-Apr-21 to 31-Aug-22
Particulars | Amount
04T1 CONSTRUCTION COST
4T1 ANCHOR WORK & LABOUR CHGS | 1944000
4T1 CEMENT | 57059848
4T1 CEMENT BLOCKS | 15930679
4T1 CHEMICALS MATERIALS | 29207594.73
4T1 ELECTRIC LABOUR | 3317678.66
4T1 ELECTRIC MATERIAL | 25295622
4T1 FABRICATION MATERAILS | 1932590.5
4T1 HARDWARE | 625441.5
4T1 LABOUR CHARGES | 118615707
4T1 PLUMBING MATERIAL | 30639072
4T1 READY MIX | 11880451
4T1 REPAIRS & SERVICES | 418270
4T1 SAND | 27875162
4T1 STEEL | 174235804.14
ATRI BUILDTECH | 26000000
JSW CEMENT LIMITED - PADMAVATI | 652500
S- FORM INDIA PVT LTD | 25223693
S- FORM INDIA PVT LTD | 16815795
S- FORM INDIA PVT LTD | 10633210
HITACHI LIFT INDIA PVT LTD-PO-WORK ORDER | 19456500
JSW CEMENT LIMITED - PADMAVATI | 3485396
ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | 19316348
SHRI GOPESHWAR STEELS | 1939879
SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED | 1578064
Fire Fitting Equipment | 14803884.2
03-AVIGHANNA ENTERPRISES-PO | 280840
03-SHRI GOPESHWAR STEELS-BILL COPY | 2273256
04-KAUSHIK FIRE APPLIANCES SERVICE-PO | 1044895
4T1 CABLES | 6947872.9
4T1 CARPENTER | 2978389.67
4T1 GLASS FIXING MATERIAL WINDOW | 139871347.34
4T1 SAFETY NET EXP | 1319275
4T1 MARBLE | 4966804.45
Unpaid Bills | 95324530
4T1 AIR CONDITIONER | 2633840
4T1 FURNITURE | 839601.61
4T1 GRILL & FABRICATION LABOUR | 664070
4T1 LIFT | 11225513.2
4T1 TILES | 12356900.74
4T1 VENTILATION MATERIAL | 2070500
PO-HOISTEC EQUIPMENTS-PAID ADV ( ALIMEK 1 TON 80M HEIGHT MEN & METERIAL HOIST SALE) | 1062000
PO-QUALDOW LLP-ADVANCE PAID SLIDING WINDOW SUBFRAME MEMBRANE ISO | 58918598.98
PO-TECHNO COMFORT ENGINEERS-INSTALLATION AND WORK FOR VENTILATION FAN | 974680
PO-UHPC INDIA PVT LTD- | 2823300
PO-UNIQUE LOGISTIC SOLUTIONS (I) PVT. LTD-LIFT MATERIALFOR HITACHI ELEVATOR AND ACCESSORIES | 5104489
PO-BHARAT ENGINEERS | 2060368
PO-BRIDGEWAY ELECTRIK SOLUTIONS PVT LTD | 2301458
PO-CANOPUS RETAIL PVT LTD | 1020800
PO-GIGA LINK TECHNOLOGIES INDIA PVT LTD | 350753
PO-K B AJMERA AND CO | 1285189
PO-TEXTURE CONCEPTS PVT LTD | 1834750
PO-THE TATA POWER CO LTD | 1773520
PO-STG HEATING PVT LTD | 416245
PO-ITALIANO STONE AND STEEL | 525000
PO-KAUSHIK FIRE APPLIANCES SERVICE | 3197408
PO-EXCEL INDUSTRIES LIMITED | 523049
PO-CANOPUS RETAIL PVT LTD | 117215
PO-PRATHAM ENVIROTECH SOLUTIONS | 4383000
PO-JYOT ELECTROCNICS | 125500
PO-VIBRANT DOORCRAFT | 2399583
PO-KAJARIA CERAMICS LTD | 363451
PO-KALPAKA POWER CONTROL -DG | 2625500
PO-KAVLE'S PRESSURE CONCRETE PVT LTD | 1205406
PO-PLASMA ENGINEERING COMPANY | 215281
PO-P.O.P ART | 112157
PO-R.K. FACADE PRIVATE LIMITED | 270371
PO-VIBRO INDIA ENTERPRISES | 415142
PO- ENTERPRISE | 3682371
4T1 INTERIOR DESIGNS | 1620000
4T1 GYPSUM WORK | 5315215.75
4T1 PAINTING MATERIAL | 481067.26
4T1 SWIMMING POOL MATERIAL | 2011593.05
4T1 WOOD | 11298482.15
4T1 CLEANING CHARGES | 62410
GST Amount | 72278852.31
Grand Total | 1116835031

## 4T1 ANCHOR WORK & LABOUR CHGS
4T1 ANCHOR WORK & LABOUR CHGS
Ledger Account
1-Jun-22 to 30-Jun-22
Date |  | Vch Type | Vch No. | Debit | Credit
2022-06-20 | ZC TOTAL FOUNDATION(AEUPP8891C) | Pur - T1 | 032/TF/22-23 | 959000
B NO- 032/TF/22-23 - SABARI GARDENS
2022-12-06 | ZC TOTAL FOUNDATION | Pur - T1 | 099/TF/22-23 | 793750
2022-12-06 | ZC TOTAL FOUNDATION | Pur - T1 | 100/TF/22-23 | 191250
1944000

## 4T1 CEMENT
4T1 CEMENT
Ledger Account
1-May-21 to 31-Aug-22
Date |  | Vch Type | Vch No. | Debit | Credit
2021-05-22 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/036 | 104400
B NO 36 - GARDENS
2021-06-01 | ULTRATECH CEMENT LIMITED(AAACL6442L) | Pur - T1 | 8301908686 | 56000
BILL NO - 8301908686 - GARDENS
2021-06-07 | ULTRATECH CEMENT LIMITED(AAACL6442L) | Pur - T1 | 8301911246 | 57000
BILL NO - 8301911246 - GARDENS
2021-06-07 | ULTRATECH CEMENT LIMITED(AAACL6442L) | Pur - T1 | 8301911245 | 57000
BILL NO - 8301911245 - GARDENS
2021-06-15 | ULTRATECH CEMENT LTD -(AAACL6442L-C) | Pur - T1 | 8831302256 | 67478.84
BILL NO - 8831302256 - GARDENS
2021-07-12 | ULTRATECH CEMENT LIMITED(AAACL6442L) | Pur - T1 | 8301918807 | 56000
BILL NO - 8301918807 - GARDENS
2021-07-12 | ULTRATECH CEMENT LIMITED(AAACL6442L) | Pur - T1 | 8301918809 | 56000
BILL NO - 8301918809 - GARDENS
2021-08-19 | ULTRATECH CEMENT LIMITED(AAACL6442L) | Pur - T1 | 8301926632 | 55600
BILL NO - 8301926632 - GARDENS
2021-08-19 | ULTRATECH CEMENT LIMITED(AAACL6442L) | Pur - T1 | 8301926634 | 55600
BILL NO - 8301926634 - GARDENS
2022-03-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301980358 | 61000
B NO 8301980358 - T-1
2022-03-19 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301980696 | 61000
B NO 8301980696
2022-03-19 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301980849 | 152500
B NO 8301980849
2022-03-19 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301980850 | 152500
B NO 8301980850
2022-03-20 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301980991 | 152500
B NO 8301980991
2022-03-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301981211 | 152500
B NO 8301981211
2022-03-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301981217 | 152500
B NO 8301981217
2022-03-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301981289 | 152500
B NO 8301981289
2022-03-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301981365 | 152500
B NO 8301981365
2022-03-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301981369 | 152500
B NO 8301981369
2022-03-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301981399 | 61000
B NO 8301981399
2022-03-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301981400 | 61000
B NO 8301981400
2022-03-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301981401 | 30500
B NO 8301981401
2022-03-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301983526** | 30500
B NO 8301983526
2022-03-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301983499** | 61000
B NO 8301983499
2022-03-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301983501** | 61000
B NO 8301983501
2022-03-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301983503** | 61000
B NO 8301983503
2022-03-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301983527** | 61000
B NO 8301983527
2022-03-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301983528** | 61000
B NO 8301983528
2022-03-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8988153696 | 426085
B NO 8988153696
2022-03-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301983795** | 76250
B NO 8301983795
2022-03-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301983851** | 76250
B NO 8301983851
2022-03-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301983853** | 76250
B NO 8301983853
2022-03-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301983803** | 76250
B NO 8301983803
2022-03-31 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8968267886 | 1278255
B NO 8968267886
2022-04-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301986123 | 61000
B NO 8301986123
2022-04-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301986125 | 61000
B NO 8301986125
2022-04-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301986127 | 61000
B NO 8301986127
2022-04-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301986695 | 122000
B NO 8301986695
2022-04-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301986696 | 122000
B NO 8301986696
2022-04-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301986694 | 30500
B NO 8301986694
2022-04-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301986693 | 30500
BO NO - 8301986693
2022-04-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301991342 | 157500
B NO 8301991342
2022-04-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301991337 | 157500
B NO 8301991337
2022-04-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301991473 | 157500
B NO 8301991473
2022-04-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301991474 | 157500
B NO 8301991474
2022-05-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985571140 | 31500
B NO 8985571140
2022-05-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985571142 | 75600
B NO 8985571142
2022-05-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985571139 | 126000
B NO 8985571139
2022-05-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985571246 | 126000
B NO 8985571246
2022-05-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985571247 | 31500
B NO 8985571247
2022-05-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985571236 | 126000
B NO 8985571236
2022-05-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985571237 | 31500
B NO 8985571237
2022-05-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301993167 | 157500
B NO 8301993167
2022-05-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301993201 | 157500
B NO 8301993201
2022-05-07 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301993336 | 31500
B NO 830199336
2022-05-07 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301993334 | 126000
B NO 8301993334
2022-05-07 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301993432 | 157500
B NO 8301993432
2022-05-07 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301993441 | 94500
B NO 8301993441
2022-05-07 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301993241 | 157500
NO OF PACKAGES OPC 53 BAGS HDPE/ PP PACK
2022-05-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301993554 | 78750
B NO 8301993554
2022-05-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301993555 | 78750
B NO 8301993555
2022-05-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301993571 | 78750
B NO 8301993571
2022-05-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301993573 | 78750
B NO 8301993573
2022-05-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301993583 | 81900
B NO 8301993583
2022-05-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301993592 | 94500
B NO 8301993592
2022-05-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301993593 | 94500
B NO 8301993593
2022-05-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301993597 | 126000
B NO 8301993597
2022-05-11 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301994152 | 63000
NO OF PACKAGES OPC 53 BAGS HDPE/ PP PACK
2022-05-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301997140 | 72600
CASE NO - 35.1.2 NO OF PACKAGES OPC 53 220 BAGS HDPE / PP PACK QTY 11.00 MT
2022-05-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301997128 | 79200
CASE NO - 35.1.2 NO OF PACKAGES OPC 53 240 BAGS HDPE / PP PACK QTY 12.00 MT
2022-05-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301997129 | 79200
CASE NO - 35.1.2 NO OF PACKAGES OPC 53 240 BAGS HDPE / PP PACK QTY 12.00 MT
2022-05-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301997127 | 79200
NO OF PACKAGES OPC 53 BAGS HDPE/ PP PACK
2022-05-27 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301998039 | 33000
NO OF PACKAGES OPC 53 100 BAGS HDPE/ PP PACK 5.000 MT
2022-05-27 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301998042 | 99000
NO OF PACKAGES OPC 53 300 BAGS HDPE / PP PACK 15.000 MT
2022-05-27 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301998041 | 33000
NO OF PACKAGES OPC 53 100 BAGS HDPE/ PP PACK 5.000 MT
2022-05-27 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301998021 | 99000
NO OF PACKAGES OPC 53 300 BAGS HDPE / PP PACK 15.000 MT
2022-05-27 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301998027 | 66000
NO OF PACKAGES OPC 53 BAGS HDPE/ PP PACK
2022-05-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8301998322 | 66000
NO OF PACKAGES OPC 53 200 BAGS HDPE/ PP PACK 10.00 MT
2022-06-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310800457 | 99000
NO OF PACKAGES OPC 53 300 BAGS HDPE / PP PACK 15.000 MT
2022-06-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310800459 | 66000
NO OF PACKAGES OPC 53 200 BAGS HDPE/ PP PACK 10.00 MT
2022-06-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310801255 | 165000
NO OF PACKAGES OPC 53 500 BAGS HDPE / PP PACK 25.000 MT
2022-06-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310801252 | 165000
NO OF PACKAGES OPC 53 500 BAGS HDPE / PP PACK 25.000 MT
2022-06-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310801227 | 99000
NO OF PACKAGES OPC 53 300 BAGS HDPE / PP PACK 15.000 MT
2022-06-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310801226 | 66000
NO OF PACKAGES OPC 53 200 BAGS HDPE/ PP PACK 10.00 MT
2022-06-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310801253 | 165000
NO OF PACKAGES OPC 53 500 BAGS HDPE / PP PACK 25.000 MT
2022-06-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310801657 | 99000
NO OF PACKAGES OPC 53 300 BAGS HDPE / PP PACK 15.000 MT
2022-06-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310801658 | 66000
NO OF PACKAGES OPC 53 200 BAGS HDPE/ PP PACK 10.00 MT
2022-06-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310801679 | 99000
NO OF PACKAGES OPC 53 300 BAGS HDPE / PP PACK 15.000 MT
2022-06-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310801681 | 66000
NO OF PACKAGES OPC 53 200 BAGS HDPE/ PP PACK 10.00 MT
2022-06-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310801696 | 66000
NO OF PACKAGES OPC 53 200 BAGS HDPE/ PP PACK 10.00 MT
2022-06-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310801695 | 99000
NO OF PACKAGES OPC 53 300 BAGS HDPE / PP PACK 15.000 MT
2022-06-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310801848 | 99000
NO OF PACKAGES OPC 53 300 BAGS HDPE / PP PACK 15.000 MT
2022-06-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310801849 | 66000
NO OF PACKAGES OPC 53 200 BAGS HDPE/ PP PACK 10.00 MT
2022-06-10 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985576799 | 165000
NO OF PACKAGES OPC 53 500 BAGS HDPE / PP PACK 25.000 MT
2022-06-11 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 89855776958 | 165000
BILL NO 89855776958
2022-06-11 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985576959 | 165000
BILL NO - 8985576959
2022-06-12 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985577080 | 165000
NO OF PACKAGES OPC 53 500 BAGS HDPE / PP PACK 25.000 MT
2022-06-12 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8302254040 | 165000
BILL NO - 8302254040
2022-06-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8302254166 | 165000
NO OF PACKAGES OPC 53 500 BAGS HDPE / PP PACK 25.000 MT
2022-06-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8302254110 | 165000
NO OF PACKAGES OPC 53 500 BAGS HDPE / PP PACK 25.000 MT
2022-06-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8302254156 | 165000
NO OF PACKAGES OPC 53 500 BAGS HDPE / PP PACK 25.000 MT
2022-06-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985577815 | 165000
BILLNO -8985577815
2022-06-18 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985577988 | 165000
BILLNO - 8985577988
2022-06-19 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310803997 | 99000
BILL NO - 8310803997 -OPC 53 300BAGS, HDPE/PP PACK QTY 15.000
2022-06-19 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310803998 | 66000
BILL NO - 8310803998
2022-06-19 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985578143 | 165000
BILL NO - 8985578143
2022-06-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985578353 | 165000
BILL NO - 8985578353
2022-06-22 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985578451 | 165000
BILL NO -8985578451
2022-06-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985578567 | 165000
BILL NO - 8985578567
2022-06-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985578573 | 165000
BILL NO - 8985578573
2022-06-25 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 83108050186 | 66000
BILL NO -83108050186
2022-06-25 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310805189 | 66000
BILL NO - 8310805189
2022-06-25 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985578815 | 132000
BILL NO 8985578815
2022-06-26 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310805301 | 33000
BILL NO - 8310805301
2022-06-26 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310805302 | 99000
BILL NO - 8310805302
2022-06-26 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985577934 | 165000
BILL NO - 8985577934
2022-06-26 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985578943 | 165000
BILL NO - 8985578943
2022-06-26 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985578987 | 165000
BILL NO - 8985578987
2022-06-26 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985578988 | 165000
BILL NO - 8985578988
2022-06-27 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310805555 | 66000
BILL NO - 831080555
2022-06-27 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985579083 | 165000
BILL NO - 8985579083
2022-06-27 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985579084 | 165000
BILL NO - 8985579084
2022-06-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985579253 | 165000
BILL NO - 8985579253
2022-06-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985579262 | 165000
BILL NO - 8985579262
2022-06-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985579330 | 132000
BILL NO - 8985579330
2022-07-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985579644 | 162500
BILL NO : 8985579644
2022-07-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985579645 | 162500
BILL NO :8985579645
2022-07-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310806504 | 162500
bill no : 8310806504
2022-07-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985580004 | 162500
BILL NO :8985580004
2022-07-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985580014 | 162500
BILL NO : 8985580014
2022-07-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985580114 | 162500
BILL NO : 8985580114
2022-07-11 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310807491 | 97500
BILL NO : 8310807491
2022-07-11 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310807492 | 65000
BILL NO : 8310807492
2022-07-11 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310807493 | 97500
BILL NO :8310807493
2022-07-11 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310807494 | 65000
BILL NO : 8310807494
2022-07-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985580298 | 162500
BILL NO : 8985580298
2022-07-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985580344 | 78000
BILL NO : 8985580344
2022-07-14 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985580358 | 162500
BILL NO : 8985580358
2022-07-14 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985580367 | 84500
BILL NO :8985580367
2022-07-16 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985580466 | 155000
BILL NO : 8985580466
2022-07-16 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985580469 | 155000
BILL NO : 8985580469
2022-07-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985580537 | 155000
BILL NO : 8985580537
2022-07-19 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985580656 | 155000
BILL NO : 8985580656
2022-07-19 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985580755 | 155000
BILL NO : 8985580755
2022-07-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985580881 | 155000
BILL NO : 8985580881
2022-07-22 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985580993 | 155000
BILL NO :8985580993
2022-07-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985581151 | 155000
BILL NO :8985581151
2022-07-25 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985581310 | 155000
BILL NO : 8985581310
2022-07-25 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985581328 | 155000
BILL NO : 8985581328
2022-07-27 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985581594 | 155000
BILL NO : 8985581594
2022-07-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985581754 | 155000
BILL NO : 8985581754
2022-07-30 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985581917 | 155000
BILL NO :8985581917
2022-07-30 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985581946 | 155000
BILL NO : 8985581946
2022-07-31 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985582187 | 152500
AS PER GST DATA
2022-07-31 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985582174 | 152500
AS PER GST DATA
2022-07-31 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985582164 | 152500
AS PER GST DATA
2022-07-31 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985582149 | 152500
AS PER GST DATA
2022-08-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985582311 | 152500
BILL NO 8985582311
2022-08-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985582352 | 152500
BILL NO - 8985582352
2022-08-04 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310811714 | 91500
BILL NO 8310811714
2022-08-04 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310811715 | 61000
BILL NO 8310811715
2022-08-04 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310811716 | 91500
BILL NO 8310811716
2022-08-04 |  |  |  | 61000
BILL NO 8310811717
2022-08-06 |  |  |  | 61000
BILL NO 8310812083
2022-08-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310812080 | 91500
BILL NO 831012080
2022-08-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310812082 | 91500
BILL NO 8310812082
2022-08-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310812081 | 61000
BILL NO 8310812081
2022-08-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985583039 | 147500
BILL NO 8985583039
2022-08-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985583074 | 118000
BILL NO 8985583074
2022-08-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985583090 | 59000
BILL NO 8985583090
2022-08-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985583086 | 29500
BILL NO 8985583086
2022-08-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985583085 | 29500
BILL NO 8985583085
2022-08-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985583079 | 59000
BILL NO 8985583079
2022-08-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985583038 | 147500
BILL NO 8985583038
2022-08-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985583183 | 73750
BILL NO 8985583183
2022-08-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985583196 | 73750
BILL NO 8985583196
2022-08-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985583182 | 73750
BILL NO 8985583182
2022-08-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985583194 | 73750
BILL NO 8985583194
2022-08-12 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985583569 | 73750
BILL NO 8985583569
2022-08-12 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985583571 | 73750
BILL NO 8985583571
2022-08-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985583657 | 73750
BILL NO : 8985583657, AS PER GST DATA
2022-08-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985583662 | 147500
BILL NO :8985583662 AS PER GST DATA
2022-08-18 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985584097 | 147500
BILL NO 8985584097
2022-08-18 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985584098 | 147500
BILL NO- 8985584098
2022-08-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985584457 | 147500
BILL NO 8985584457
2022-08-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985584470 | 73750
BILL NO 8985584470
2022-08-25 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985585048 | 147500
BILL NO :8985585048 AS PER GST DATA
2022-09-01 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985585797 | 147500
2022-09-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985586097 | 147500
2022-09-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985586317 | 147500
2022-09-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985586527 | 147500
2022-09-11 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310818691 | 147500
2022-09-11 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310818690 | 147500
2022-09-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985587047 | 147500
2022-09-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985587040 | 147500
2022-09-14 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985587177 | 73750
2022-09-14 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985587175 | 73750
2022-09-14 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985587181 | 147500
2022-09-15 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985587298 | 147500
2022-09-15 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985587320 | 147500
2022-10-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985590002 | 81250
2022-10-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985590001 | 81250
2022-10-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310823673 | 130000
2022-10-12 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310824278 | 162500
2022-10-12 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985590649 | 162500
2022-10-12 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985590628 | 162500
2022-10-12 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310824286 | 162500
2022-10-12 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985590649 | 162500
2022-10-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985590788 | 162500
2022-10-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985590786 | 162500
2022-10-14 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985590920 | 162500
2022-10-18 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985591322 | 162500
2022-10-18 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985591298 | 162500
2022-10-18 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985591298 | 162500
2022-10-31 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985592985 | 162500
2022-10-31 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985592982 | 162500
2022-10-31 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985592993 | 162500
2022-11-04 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985593563 | 162500
2022-11-04 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985593584 | 162500
2022-11-07 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8908022411 | 78000
2022-11-07 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8908022407 | 78000
2022-11-07 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8908022408 | 78000
2022-11-07 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8908022415 | 78000
2022-11-07 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8908022412 | 78000
2022-11-07 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8908022409 | 78000
2022-11-07 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310829397 | 110500
2022-11-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8908022454 | 78000
2022-11-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8908022455 | 78000
2022-11-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8908022456 | 78000
2022-11-10 | JSW CEMENT LIMITED - PADMAVATI | Pur - T1 | MH2203088345 | 106071.42
2022-11-10 | JSW CEMENT LIMITED - PADMAVATI | Pur - T1 | MH2203088395 | 106071.42
2022-11-14 | JSW CEMENT LIMITED - PADMAVATI | Pur - T1 | MH2203090505 | 106071.42
2022-11-14 | JSW CEMENT LIMITED - PADMAVATI | Pur - T1 | MH2203090442 | 106071.42
2022-11-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310831427 | 162500
2022-11-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985595400 | 162500
2022-11-18 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985595552 | 162500
2022-11-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310832243 | 162500
2022-11-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310832242 | 162500
2022-11-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310832347 | 65000
2022-11-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310832344 | 97500
2022-11-23 | JSW CEMENT LIMITED - PADMAVATI | Pur - T1 | MH2203094884 | 106071.42
2022-11-23 | JSW CEMENT LIMITED - PADMAVATI | Pur - T1 | MH2203094873 | 106071.42
2022-11-27 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310833485 | 130000
2022-11-27 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310833473 | 162500
2022-11-27 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310833421 | 162500
2022-11-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310833608 | 97500
2022-11-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310833534 | 65000
2022-11-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310833533 | 32500
2022-12-03 | JSW CEMENT LIMITED - PADMAVATI | Pur - T1 | MH2203099595 | 106071.42
2022-12-03 | JSW CEMENT LIMITED - PADMAVATI | Pur - T1 | MH2203099593 | 106071.42
2022-12-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985598187 | 165000
2022-12-06 | JSW CEMENT LIMITED - PADMAVATI | Pur - T1 | MH2203100502 | 106071.42
2022-12-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8302262630 | 19800
2022-12-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8302262629 | 19800
2022-12-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8302262628 | 19800
2022-12-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8302262623 | 66000
2022-12-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8302262624 | 66000
2022-12-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8302262633 | 79200
2022-12-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8302262627 | 79200
2022-12-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8302262625 | 79200
2022-12-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8302262632 | 66000
2022-12-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8302262626 | 79200
2022-12-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8302262634 | 66000
2022-12-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8302262631 | 19800
2022-12-07 | JSW CEMENT LIMITED - PADMAVATI | Pur - T1 | MH2203101107 | 106071.42
2022-12-07 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310835500 | 82500
2022-12-07 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310835509 | 82500
2022-12-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310836281 | 82500
2022-12-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310836298 | 82500
2022-12-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310836314 | 66000
2022-12-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310836313 | 99000
2022-12-10 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310836378 | 16500
2022-12-10 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310836342 | 66000
2022-12-10 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310836339 | 66000
2022-12-10 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310836330 | 66000
2022-12-10 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310836329 | 99000
2022-12-12 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310836815 | 16500
2022-12-31 | JSW CEMENT LIMITED - PADMAVATI | Pur - T1 | MH22031112871 | 106071.42
2022-12-31 | JSW CEMENT LIMITED - PADMAVATI | Pur - T1 | MH2203112831 | 106071.42
2023-01-01 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203113485 | 106071.42
2023-01-02 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203113665 | 106071.42
2023-01-02 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203113874 | 106071.42
2023-01-02 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203113853 | 106071.42
2023-01-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985603377 | 165000
2023-01-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985603380 | 165000
2023-01-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985603627 | 165000
2023-01-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985603610 | 165000
2023-01-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985604206 | 165000
2023-01-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985604664 | 165000
2023-01-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985604666 | 165000
2023-01-10 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985604865 | 165000
2023-01-10 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985604855 | 82500
2023-01-10 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985604874 | 165000
2023-01-10 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985604864 | 82500
2023-01-10 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985604867 | 82500
2023-01-10 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985604866 | 165000
2023-01-10 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985604872 | 165000
2023-01-10 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985604878 | 165000
2023-01-11 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985605090 | 82500
2023-01-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985605505 | 165000
2023-01-16 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310844113 | 165000
2023-01-16 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310844112 | 165000
2023-01-16 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985606114 | 165000
2023-01-16 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203121308 | 108571.42
2023-01-16 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203121310 | 108571.42
2023-01-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310844306 | 165000
2023-01-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310844308 | 165000
2023-01-18 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310844477 | 165000
2023-01-18 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310844467 | 165000
2023-01-19 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985606699 | 165000
2023-01-19 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985606700 | 165000
2023-01-19 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203122639 | 108571.42
2023-01-20 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985606918 | 165000
2023-01-20 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203123004 | 108571.42
2023-01-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310845318 | 165000
2023-01-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310845319 | 165000
2023-01-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310845322 | 165000
2023-01-25 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310846217 | 66000
2023-01-25 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310846218 | 66000
2023-01-25 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310846228 | 66000
2023-01-25 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310846253 | 66000
2023-01-25 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310846283 | 66000
2023-01-27 | PADMAVATI MARKETING(ADPPJ4722Q) | Pur - T1 | 8310846721 | 66000
2023-01-27 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310846721 | 66000
2023-01-27 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310846722 | 66000
2023-01-27 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310846723 | 33000
2023-01-27 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310846662 | 33000
2023-01-27 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310846663 | 66000
2023-01-27 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310846664 | 66000
2023-01-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310846991 | 66000
2023-01-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310846981 | 99000
2023-01-30 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203128408 | 108571.42
2023-01-30 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203128423 | 108571.42
2023-01-30 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310847176 | 99000
2023-01-30 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310847198 | 66000
2023-01-31 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310847636 | 66000
2023-01-31 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310847639 | 99000
2023-02-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310848000 | 33000
2023-02-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310847994 | 66000
2023-02-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310847993 | 165000
2023-02-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310847904 | 33000
2023-02-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310847869 | 33000
2023-02-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310847866 | 99000
2023-02-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310847865 | 66000
2023-02-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310847841 | 99000
2023-02-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310847973 | 165000
2023-02-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985609497 | 165000
2023-02-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985609496 | 165000
2023-02-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985609501 | 165000
2023-02-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310848122 | 66000
2023-02-03 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203130347 | 108571.42
2023-02-03 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203130453 | 108571.42
2023-02-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985610169 | 165000
2023-02-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985610171 | 165000
2023-02-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985610172 | 165000
2023-02-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985610174 | 165000
2023-02-07 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203132345 | 108571.42
2023-02-07 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203132377 | 108571.42
2023-02-08 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203132764 | 108571.42
2023-02-08 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203132825 | 108571.42
2023-02-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985610767 | 165000
2023-02-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985610728 | 165000
2023-02-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985610732 | 165000
2023-02-12 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203134831 | 108571.42
2023-02-12 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203134836 | 108571.42
2023-02-14 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985611502 | 165000
2023-02-14 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985611500 | 165000
2023-02-14 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985611501 | 165000
2023-02-15 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985611688 | 165000
2023-02-15 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985611678 | 165000
2023-02-15 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985611679 | 165000
2023-02-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985612049 | 165000
2023-02-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310851556 | 165000
2023-02-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310851557 | 165000
2023-02-17 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203137080 | 108571.42
2023-02-17 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203137106 | 108571.42
2023-02-18 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310851989 | 165000
2023-02-18 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985612276 | 82500
2023-02-18 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310851990 | 33000
2023-02-19 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310852018 | 165000
2023-02-19 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310852021 | 33000
2023-02-19 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985612481 | 66000
2023-02-20 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203138557 | 108571.42
2023-02-20 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203138576 | 108571.42
2023-02-22 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310852953 | 162500
2023-02-22 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310852946 | 162500
2023-02-22 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203139542 | 108571.42
2023-02-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310853242 | 65000
2023-02-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310853250 | 32500
2023-02-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310853249 | 32500
2023-02-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310853213 | 65000
2023-02-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310853211 | 65000
2023-02-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310853244 | 65000
2023-02-25 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310853681 | 65000
2023-02-25 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310853795 | 65000
2023-02-25 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310853796 | 32500
2023-02-25 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310853797 | 65000
2023-02-25 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310853631 | 162500
2023-02-25 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310853629 | 162500
2023-02-28 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | 3068/22-23 | 36750
2023-02-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310854697 | 160000
2023-02-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310854696 | 160000
2023-03-01 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310854954 | 48750
2023-03-01 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310854809 | 64000
2023-03-01 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310854821 | 64000
2023-03-01 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310854870 | 32000
2023-03-01 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310854871 | 32000
2023-03-01 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310854812 | 64000
2023-03-01 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310854819 | 64000
2023-03-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310855174 | 64000
2023-03-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310855084 | 64000
2023-03-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310855086 | 16000
2023-03-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310855177 | 80000
2023-03-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310855188 | 16000
2023-03-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310855004 | 64000
2023-03-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310855034 | 80000
2023-03-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310855006 | 16000
2023-03-02 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310854973 | 80000
2023-03-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310855303 | 80000
2023-03-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310855312 | 16000
2023-03-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310855305 | 64000
2023-03-04 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310855769 | 96000
2023-03-04 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310855770 | 64000
2023-03-05 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310855843 | 64000
2023-03-05 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310855838 | 64000
2023-03-05 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310855846 | 32000
2023-03-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310856393 | 64000
2023-03-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310856877 | 64000
2023-03-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310856881 | 10880
2023-03-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310856882 | 32000
2023-03-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310856879 | 21120
2023-03-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310856777 | 64000
2023-03-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310856785 | 64000
2023-03-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310856767 | 64000
2023-03-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310856782 | 64000
2023-03-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310856799 | 10880
2023-03-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310856801 | 32000
2023-03-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310856797 | 21120
2023-03-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985615642 | 80000
2023-03-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985615640 | 80000
2023-03-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985615639 | 80000
2023-03-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985615648 | 80000
2023-03-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310858710 | 160000
2023-03-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310858707 | 160000
2023-03-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310858830 | 160000
2023-03-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310858708 | 160000
2023-03-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310858713 | 160000
2023-03-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310858711 | 160000
2023-03-20 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310859410 | 64000
2023-03-20 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310859439 | 64000
2023-03-20 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310859440 | 64000
2023-03-20 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310859444 | 32000
2023-03-20 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310859445 | 32000
2023-03-20 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310859413 | 64000
2023-03-20 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310859399 | 160000
2023-03-20 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310859458 | 76800
2023-03-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310860136 | 63000
2023-03-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310860129 | 63000
2023-03-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310860126 | 63000
2023-03-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310860212 | 31500
2023-03-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310860209 | 63000
2023-03-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310860218 | 157500
2023-03-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310860232 | 157500
2023-03-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310860211 | 31500
2023-03-26 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310861033 | 157500
2023-03-26 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310861053 | 157500
2023-03-26 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310861044 | 157500
2023-03-26 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310860929 | 157500
2023-03-26 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310860933 | 157500
2023-03-26 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310860932 | 157500
2023-03-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310861426 | 157500
2023-03-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310861430 | 157500
2023-03-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310861937 | 157500
2023-03-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310861939 | 157500
2023-04-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310863147 | 63000
2023-04-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310863146 | 37800
2023-04-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310863145 | 56700
2023-04-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985620177 | 157500
2023-04-04 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985620401 | 157500
2023-04-04 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985620389 | 78750
2023-04-04 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985620387 | 78750
2023-04-04 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985620391 | 78750
2023-04-04 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985620392 | 78750
2023-04-04 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310863405 | 157500
2023-04-04 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310863393 | 94500
2023-04-04 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310863394 | 157500
2023-04-05 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310863473 | 63000
2023-04-05 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310863439 | 157500
2023-04-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310863695 | 31500
2023-04-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310863729 | 157500
2023-04-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310863707 | 31500
2023-04-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310863731 | 157500
2023-04-07 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310864007 | 31500
2023-04-07 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310864006 | 157500
2023-04-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310864769 | 63000
2023-04-11 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310865292 | 63000
2023-04-11 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310865180 | 94500
2023-04-11 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310865187 | 63000
2023-04-11 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310865179 | 63000
2023-04-11 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310865186 | 94500
2023-04-11 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310865287 | 94500
2023-04-12 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310865561 | 63000
2023-04-12 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310865560 | 94500
2023-04-15 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/0133 | 29400
2023-04-15 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310866369 | 64000
2023-04-15 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310866368 | 96000
2023-04-16 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310866623 | 64000
2023-04-16 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310866499 | 160000
2023-04-16 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310866625 | 64000
2023-04-18 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310867124 | 32000
2023-04-18 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310867105 | 32000
2023-04-18 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310867080 | 160000
2023-04-18 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310867041 | 64000
2023-04-18 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310867050 | 64000
2023-04-19 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310867225 | 160000
2023-04-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985623095 | 80000
2023-04-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985623075 | 80000
2023-04-22 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985623257 | 80000
2023-04-22 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985623250 | 160000
2023-04-22 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8985623265 | 80000
2023-04-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310868199 | 80000
2023-04-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310868134 | 160000
2023-04-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310868118 | 160000
2023-04-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T1 | 8310868169 | 80000
2023-06-01 | K N CONCEPTS(APAPS8825E) | Pur - T1 | 073-23/24 | 79780
2023-06-13 | KRAM INFRA | Pur - T1 | KI/643/23-24 | 152500
2023-10-20 | K N CONCEPTS(APAPS8825E) | Pur - T1 | 216-23/24 | 30749.2
57059847.74

## 4T1 CEMENT BLOCKS
4T1 CEMENT BLOCKS
Ledger Account
1-Jun-21 to 31-Aug-22
Date |  | Vch Type | Vch No. | Debit | Credit
2021-06-18 | MAGICRETE BUILDING SOLUTIONS PVT LTD | Pur - T1 | SI/GJ/22/02316 | 107792.25
BILL NO - SI/GJ/22/02316, SABARI GARDENS SAMPLE FLAT
2021-06-21 | MAGICRETE BUILDING SOLUTIONS PVT LTD | Pur - T1 | SI/GJ/22/02417 | 110856.54
BILL NO - SI/GJ/22/02417, SABARI GARDENS SAMPLE FLAT
2021-08-01 | MAGICRETE BUILDING SOLUTIONS PVT LTD | Pur - T1 | SI/GJ/22/04098 | 43601.69
BILL NO - SI/GJ/22/04098, SABARI GARDENS SAMPLE FLAT
2022-04-06 | SUPERIOR CONCRETE PRODUCTS LLP(ACSFS6816L) | Pur - T1 | SCPL/22-23/005 | 27670
BILL NO - SCPL/22-23/0005
2022-04-19 | SUPERIOR CONCRETE PRODUCTS LLP(ACSFS6816L) | Pur - T1 | SCPL/22-23/0072 | 33400
BILL NO - SCPL/22-23/0072
2022-05-09 | SUPERIOR CONCRETE PRODUCTS LLP(ACSFS6816L) | Pur - T1 | SCPL/22-23/0149 | 22050
BILL NO - SCPL/22-23/0149
2022-06-09 | SUPERIOR CONCRETE PRODUCTS LLP(ACSFS6816L) | Pur - T1 | SCPL/22-23/0278 | 40770
BILL NO - SPCL/22-23/0278, CASE NO 76 URGENT
2022-06-11 | PADMAVATI MARKETING(ADPPJ4722Q) | Pur - T1 | PM/472/22-23 | 68750
CASE NO 9622 - FLY ASHS SUPREME POZZ QTY 25
2022-06-14 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203026916 | 103571.42
CASE NO 8062201 FOR GGBS
2022-06-14 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203026921 | 103571.42
CASE NO 8062201 FOR GGBS
2022-06-25 | SUPERIOR CONCRETE PRODUCTS LLP(ACSFS6816L) | Pur - T1 | SCPL/22-23/0341 | 21750
CASE NO - 89 COVERING FOR BASEMENT 1,2,3& RAJT
2022-06-26 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203031942 | 103571.42
CASE NO 59
2022-06-26 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203031846 | 103571.42
CASE NO 55
2022-06-26 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203031842 | 103571.42
CASE NO 55
2022-06-28 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203032587 | 103571.42
CASE NO 55
2022-06-30 | GODREJ & BOYCE MFG CO LTD(AAACG1395D) | Pur - T1 | 1000NAI20009082 | 32000
B NO 1000NAI20009082 - ONE MERAKI
2022-07-13 | SUPERIOR CONCRETE PRODUCTS LLP(ACSFS6816L) | Pur - T1 | SCPL/22-23/0395 | 10800
CASE NO:96, CONCRETE COVER BLOCK FOR COLUMN COVERING
2022-07-14 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203038132 | 103571.42
AS PER GST DATA
2022-07-15 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH220303842 | 103571.42
AS PER GST DATA
2022-07-16 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203038709 | 103571.42
AS PER GST DATA
2022-07-16 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203038808 | 103571.42
AS PER GST DATA
2022-08-04 | SUPERIOR CONCRETE PRODUCTS LLP(ACSFS6816L) | Pur - T1 | SCPL/22-23/0483 | 36180
CASE NO 79 - COVERS FOR GROUND FLOOR SLAB
2022-08-05 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203046448 | 103571.42
CASE NO 77
2022-08-05 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203046517 | 103571.42
CASE NO 77
2022-08-15 |  |  |  | 103571.42
BILL NO MH2203050165
2022-08-15 |  |  |  | 103571.42
BILL NO MH220305173
2022-08-16 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203050584 | 103571.42
CASE NO 77
2022-09-03 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203057662 | 103571.42
2022-09-19 | SUPERIOR CONCRETE PRODUCTS LLP(ACSFS6816L) | Pur - T1 | SCPL/22-23/0658 | 40830
2022-10-15 | JSW CEMENT LIMITED - PADMAVATI | Pur - T1 | MH2203074045 | 106071.42
2022-10-16 | JSW CEMENT LIMITED - PADMAVATI | Pur - T1 | MH2203074630 | 106071.42
2022-10-19 | JSW CEMENT LIMITED - PADMAVATI | Pur - T1 | MH2203076459 | 106071.42
2022-11-08 | SUPERIOR CONCRETE PRODUCTS LLP | Pur - T1 | SCPL/22-23/0869 | 64900
2022-11-11 | HELLA INFRA MARKET RETAIL PVT LTD | Pur - T1 | MHL/BLC/1122/001 | 130242
2022-11-11 | HELLA INFRA MARKET RETAIL PVT LTD | Pur - T1 | MHL/BLC/1122/002 | 128874.24
2022-12-01 | HELLA INFRA MARKET RETAIL PVT LTD | Pur - T1 | MHL/BLC/1222/002 | 6779.6
2022-12-01 | HELLA INFRA MARKET RETAIL PVT LTD | Pur - T1 | MHL/BLC/1222/001 | 127512
2022-12-10 | HELLA INFRA MARKET RETAIL PVT LTD | Pur - T1 | HIMRPL10956 | 32881.36
2022-12-23 | PADMAVATI MARKETING | Pur - T1 | PM/1185/22-23 | 37076
2023-01-04 | SUPERIOR CONCRETE PRODUCTS LLP(ACSFS6816L) | Pur - T1 | SCPL/22-23/001169 | 55800
2023-01-08 | MAGICRETE BUILDING SOLUTIONS PVT LTD | Pur - T1 | SI/GJ/23/11956 | 176261.32
2023-01-10 | MAGICRETE BUILDING SOLUTIONS PVT LTD | Pur - T1 | SI/GJ/23/12034 | 177503.33
2023-01-21 | SUPERIOR CONCRETE PRODUCTS LLP(ACSFS6816L) | Pur - T1 | SCPL/22-23/01273 | 55800
2023-02-13 | GODREJ & BOYCE MFG CO LTD(AAACG1395D) | Pur - T1 | 1000NAI57001062 | 132300
2023-02-20 | SUPERIOR CONCRETE PRODUCTS LLP(ACSFS6816L) | Pur - T1 | SCPL/22-23/01431 | 55800
2023-02-20 | GODREJ & BOYCE MFG CO LTD(AAACG1395D) | Pur - T1 | 1000NAI33008252 | 14101.6
2023-02-21 | GODREJ & BOYCE MFG CO LTD(AAACG1395D) | Pur - T1 | 1000NAI57001090 | 132300
2023-02-22 | GODREJ & BOYCE MFG CO LTD(AAACG1395D) | Pur - T1 | 1000NAI19012101 | 120330
2023-02-22 | GODREJ & BOYCE MFG CO LTD(AAACG1395D) | Pur - T1 | 1000NAI19012102 | 143640
2023-02-22 | GODREJ & BOYCE MFG CO LTD(AAACG1395D) | Pur - T1 | 1000NAI9012103 | 123962.3
2023-02-25 | GODREJ & BOYCE MFG CO LTD(AAACG1395D) | Pur - T1 | 1000NAI19012158 | 107140.8
2023-02-25 | GODREJ & BOYCE MFG CO LTD(AAACG1395D) | Pur - T1 | 1000NAI19012157 | 165062.1
2023-02-27 | GODREJ & BOYCE MFG CO LTD(AAACG1395D) | Pur - T1 | 1000NAI33008388 | 10576.2
2023-02-27 | GODREJ & BOYCE MFG CO LTD(AAACG1395D) | Pur - T1 | 1000NAI33008386 | 10576.2
2023-02-27 | GODREJ & BOYCE MFG CO LTD(AAACG1395D) | Pur - T1 | 1000NAI33008389 | 10576.2
2023-02-27 | GODREJ & BOYCE MFG CO LTD(AAACG1395D) | Pur - T1 | 1000NAI33008387 | 12338.9
2023-03-01 | SUPERIOR CONCRETE PRODUCTS LLP(ACSFS6816L) | Pur - T1 | SCPL/22-23/01487 | 81530
2023-03-03 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203143923 | 108571.42
2023-03-03 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203143869 | 108571.42
2023-03-05 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203144842 | 108571.42
2023-03-05 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203144799 | 108571.42
2023-03-05 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203144831 | 108571.42
2023-03-05 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203144821 | 108571.42
2023-03-17 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203150071 | 108571.42
2023-03-17 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203151089 | 108571.42
2023-03-18 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203150520 | 108571.42
2023-03-19 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00602223 | 138270
2023-03-19 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203151064 | 108571.42
2023-03-19 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203151089 | 108571.42
2023-03-20 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00642223 | 153648
2023-03-20 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT23652223 | 16102
2023-03-20 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT23662223 | 96610
2023-03-21 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT23722223 | 16102
2023-03-21 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00672223 | 154110
2023-03-21 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00662223 | 164947
2023-03-21 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT23702223 | 96610
2023-03-23 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00702223 | 163944
2023-03-23 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203153006 | 108571.42
2023-03-23 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203153006 | 108571.42
2023-03-23 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203153038 | 108571.42
2023-03-24 | SUPERIOR CONCRETE PRODUCTS LLP(ACSFS6816L) | Pur - T1 | SCPL/22-23/01591 | 105100
2023-03-25 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT24062223 | 105932
2023-03-25 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00712223 | 168300
2023-03-26 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00722223 | 166650
2023-03-27 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203154886 | 108571.42
2023-03-27 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2203154852 | 108571.42
2023-03-27 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT24212223 | 101695
2023-03-27 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00742223 | 174240
2023-03-28 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00762223 | 210131
2023-03-28 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00772223 | 213840
2023-03-28 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00752223 | 168300
2023-04-02 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00022324 | 136620
2023-04-02 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00012324 | 193644
2023-04-03 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00052324 | 194766
2023-04-03 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00042324 | 170676
2023-04-03 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2303000834 | 108571.42
2023-04-04 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2303001215 | 108571.42
2023-04-04 | SRSBM LAB TESTING PVT LTD(ABACS8249K) | Pur - T1 | MRT-17261 | 14000
2023-04-06 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00362324 | 201271
2023-04-06 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00062324 | 194832
2023-04-06 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00072324 | 213365
2023-04-06 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2303002006 | 108571.42
2023-04-07 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT00462324 | 127119
2023-04-07 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2303002328 | 108571.42
2023-04-09 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00102324 | 206712
2023-04-09 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00112324 | 201960
2023-04-11 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2303003986 | 111071.42
2023-04-11 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2303003971 | 111071.42
2023-04-11 | SRSBM LAB TESTING PVT LTD(ABACS8249K) | Pur - T1 | MRT-17522 | 28000
2023-04-11 | SRSBM LAB TESTING PVT LTD(ABACS8249K) | Pur - T1 | MRT-17482/1 | 14000
2023-04-12 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00122324 | 192456
2023-04-13 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00132324 | 188760
2023-04-15 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2303005711 | 111071.42
2023-04-15 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2303005712 | 111071.42
2023-04-15 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2303005723 | 111071.42
2023-04-16 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT01402324 | 127117.76
2023-04-17 | GODREJ & BOYCE MFG CO LTD(AAACG1395D) | Pur - T1 | 1000NAI19012625 | 137220.3
2023-04-18 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00162324 | 202118
2023-04-18 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00152324 | 197472
2023-04-20 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2303007637 | 111071.42
2023-04-20 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2303007615 | 111071.42
2023-04-20 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00172324 | 203702
2023-04-21 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2303007945 | 111071.42
2023-04-21 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2303007933 | 111071.42
2023-04-21 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T1 | MH2303007911 | 111071.42
2023-04-21 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT01812324 | 96610
2023-04-22 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT01862324 | 127117.76
2023-04-25 | RECONS BUILDING PRODUCTS PVT LTD | Pur - T1 | G230278 | 135596.43
2023-06-10 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00412324 | 159588
2023-06-11 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00422324 | 192412
2023-10-04 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT12732324 | 106250
2023-10-10 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Debit Note | RE00102/23 | -106250
2023-10-12 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC04712324 | 118462
2023-10-30 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT14762324 | 127500
2023-10-31 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT14842324 | 32203
2023-10-31 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC05252324 | 127940
2023-11-02 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC05302324 | 122897
2023-11-02 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC05332324 | 122011
2023-11-04 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC05402324 | 146529
2023-11-07 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC05602324 | 14580
2023-11-07 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC05592324 | 134500
2023-11-28 | RECONS BUILDING PRODUCTS PVT LTD | Pur - T1 | G232989 | 66362.5
2023-12-15 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC07282324 | 151924
2023-12-20 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC07462324 | 147550
2023-12-21 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC07522324 | 149810
2024-01-18 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC08482324 | 114635
2024-01-22 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC08572324 | 114295
15930678.96

## 4T1 CHEMICALS MATERIALS
4T1 CHEMICALS MATERIALS
Ledger Account
1-Oct-22 to 31-Dec-22
Date |  | Vch Type | Vch No. | Debit
2022-11-01 | VEDANT MARKETING | Pur - T1 | 1868/22-23 | 18720
2022-11-14 | VEDANT MARKETING | Pur - T1 | 2005/22-23 | 140125
2022-11-14 | VEDANT MARKETING | Pur - T1 | 2006/22-23 | 187200
2022-11-16 | VEDANT MARKETING | Pur - T1 | 2036/22-23 | 7800
2022-12-08 | VEDANT MARKETING | Pur - T1 | 2261/22-23 | 38250
2022-12-10 | VEDANT MARKETING | Pur - T1 | 2291/22-23 | 460350
2023-02-09 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | 2883/22-23 | 144000
2023-02-15 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | 2935/22-23 | 187200
2023-03-06 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | 3138/22-23 | 705600
2023-03-06 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | 3130/22-23 | 43200
2023-03-29 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | 3364/22-23 | 216000
2023-03-31 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | 3393/22-23 | 17820
2023-04-04 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/0030 | 331200
2023-04-07 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/3-24/0059 | 9000
2023-04-19 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/0177 | 70918
2023-04-19 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/0173 | 15300
2023-04-20 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/3-24/0195 | 76500
2023-05-01 | KAVLE'S PRESSURE CONCRETE PVT LTD | Pur - T1 | 3 | 290000
2023-05-30 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/0593 | 18720
2023-06-28 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/0871 | 175500
2023-07-05 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/0931 | 11250
2023-07-12 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/0999 | 5400
2023-07-22 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/1081 | 6021
2023-07-25 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/1114 | 21600
2023-07-25 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/1113 | 8028
2023-07-29 | KAVLE'S PRESSURE CONCRETE PVT LTD | Pur - T1 | 01 | 245000
2023-07-29 | KAVLE'S PRESSURE CONCRETE PVT LTD | Pur - T1 | KPC/MH1/23-24 | 711716.94
2023-07-31 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/1152 | 77149
2023-08-01 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/1174 | 11817
2023-08-18 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/1348 | 1012536
2023-08-20 | KANERIA PLAST PVT LTD | Pur - T1 | KP/4016/23-24 | 154800
2023-08-21 | KANERIA PLAST PVT LTD | Pur - T1 | KP/4029/23-24 | 139500
2023-08-30 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/1487 | 11250
2023-08-31 | KAVLE'S PRESSURE CONCRETE PVT LTD | Pur - T1 | KP/MH-2/23-24 | 745876.6
2023-09-01 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/1515 | 1012536
2023-09-01 | KANERIA PLAST PVT LTD | Pur - T1 | KP/4403/23-24 | 162000
2023-09-03 | KANERIA PLAST PVT LTD | Pur - T1 | KP/4469/23-24 | 162000
2023-09-08 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/1601 | 15750
2023-09-22 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/1721 | 597450
2023-09-25 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/1738, | 23000
2023-09-30 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/1796 | 3640
2023-09-30 | KAVLE'S PRESSURE CONCRETE PVT LTD | Pur - T1 | KPC/MH-3/23-24 | 936798.11
2023-10-05 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/1840 | 602700
2023-10-14 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/1946 | 1595
2023-10-18 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/1970 | 910275
2023-10-26 | KAVLE'S PRESSURE CONCRETE PVT LTD | Pur - T1 | KPC/MKT2/23-24 | 243250
2023-10-26 | KAVLE'S PRESSURE CONCRETE PVT LTD | Pur - T1 | KPC/MH-4/23-24 | 1370013.73
2023-11-01 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/2099 | 144000
2023-11-04 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/2150 | 199900
2023-11-17 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/2246 | 28000
2023-11-25 | KAVLE'S PRESSURE CONCRETE PVT LTD | Pur - T1 | KPC/MH-5/23-24 | 1144465.15
2023-11-25 | KAVLE'S PRESSURE CONCRETE PVT LTD | Pur - T1 | KPC/MKT3/23-24 | 287000
2023-11-29 | KAVLE'S PRESSURE CONCRETE PVT LTD | Pur - T1 | KPC/MHP1/23-24 | 1725675
2023-12-01 | KAVLE'S PRESSURE CONCRETE PVT LTD | Debit Note | T1/KPC/010 | -11486
2023-12-18 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/2567 | 602700
2023-12-23 | KAVLE'S PRESSURE CONCRETE PVT LTD | Pur - T1 | KPC/MH-6/23-24 | 1302592.48
2023-12-23 | KAVLE'S PRESSURE CONCRETE PVT LTD | Pur - T1 | KPC/MKT4/23-24 | 90300
2023-12-23 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/2618 | 3560
2023-12-29 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/2687 | 151200
2024-01-06 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/2756 | 2752
2024-01-11 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/2816 | 29520
2024-01-23 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/2926 | 10500
2024-01-24 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/2952 | 602700
2024-01-25 | KAVLES PRESSURE CONCRETE PVT LTD(AABCK8239K) | Pur - T1 | KPC/MH-7/24-25 | 2431710.06
2024-02-03 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/3049 | 37800
2024-02-03 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/3051 | 3105
2024-02-17 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/3225 | 602700
2024-02-19 | KAVLES PRESSURE CONCRETE PVT LTD(AABCK8239K) | Pur - T1 | KPC/MH-2/24-25 | 1285157.56
2024-02-26 | KAVLES PRESSURE CONCRETE PVT LTD(AABCK8239K) | Pur - T1 | KPC/MH-8/24-25 | 2907432.04
2024-02-29 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/3350 | 5750
2024-03-08 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/3437 | 38160
2024-03-11 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/3469 | 756840
2024-03-12 | KAVLES PRESSURE CONCRETE PVT LTD(AABCK8239K) | Debit Note | T1/JSA/10 | -9400
2024-03-14 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | VM/23-24/3496 | 5400
2024-03-21 | KAVLES PRESSURE CONCRETE PVT LTD(AABCK8239K) | Pur - T1 | KPC/MH-9/24-25 | 1272391.61
2024-03-21 | KAVLES PRESSURE CONCRETE PVT LTD(AABCK8239K) | Pur - T1 | KPC/MH-3/24-25 | 150166.5
2024-03-24 | KAVLES PRESSURE CONCRETE PVT LTD(AABCK8239K) | Pur - T1 | KPC/MH2/24-25 | 211381.62
2024-03-26 | KAVLES PRESSURE CONCRETE PVT LTD(AABCK8239K) | Pur - T1 | KPC/MA1/24-25 | 839266.33
29207594.73

## 4T1 ELECTRIC LABOUR
4T1 ELECTRIC LABOUR
Ledger Account
1-Aug-22 to 31-Aug-22
Date |  | Vch Type | Vch No. | Debit | Credit
2022-08-08 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 131 | 132300
CASE NO 270822.2 - MORE ELECTRICALS( BASEMENT-3 PVC CONDUITING WORK 20% PAYMENT )ONE MERAKI BILL NO - 131
2022-09-14 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 134 | 132300
2022-09-24 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 135 | 128100
2022-10-24 | ZC MORE ELECTRICAL & ENGINEERING WORKS | Pur - T1 | 140 | 40000
2022-11-01 | ZC MORE ELECTRICAL & ENGINEERING WORKS | Pur - T1 | 142 | 132300
2022-11-05 | ZC MORE ELECTRICAL & ENGINEERING WORKS | Pur - T1 | 141 | 132300
2022-11-25 | ZC MORE ELECTRICAL & ENGINEERING WORKS | Pur - T1 | 148 | 68133
2022-11-25 | ZC MORE ELECTRICAL & ENGINEERING WORKS | Pur - T1 | 147 | 66157
2022-12-09 | ZC MORE ELECTRICAL & ENGINEERING WORKS | Pur - T1 | 149 | 128100
2022-12-21 | ZC MORE ELECTRICAL & ENGINEERING WORKS | Pur - T1 | 151 | 68133
2023-11-01 | ZC GOND ENTERPRISE(AMYPG2103J) | Pur - T1 | 94 | 1111543.87
2023-11-07 | ZC GOND ENTERPRISE(AMYPG2103J) | Pur - T1 | 96 | 1183011.79
2024-03-12 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Debit Note | T1/JSA/12 | -4700
3317678.66

## 4T1 ELECTRIC MATERIAL
4T1 ELECTRIC MATERIAL
Ledger Account
1-May-21 to 31-Aug-22
Date |  | Vch Type | Vch No. | Debit | Credit
2021-05-31 | REAL INDUSTRIES(ACGPM3884J) | Pur - T1 | 012 | 68500
FOR GARDENS - FOR DE WATERING PUMP
2021-06-02 | N K TRADING CO(AJEPP2160M) | Pur - T1 | 9097 | 31748
BILL NO - 9097 - SABARI GARDENS
2021-06-07 | REAL INDUSTRIES(ACGPM3884J) | Pur - T1 | 0049 | 37450
FOR GARDENS - FOR DE WATERING PUMP
2021-08-01 | FLOW CHEM PUMPS PVT. LTD | Pur - T1 | 241 | 14100
FOR GARDENS - FOR PVC CABLE
2021-08-05 | REAL INDUSTRIES(ACGPM3884J) | Pur - T1 | 0102 | 8350
FOR GARDENS - FOR DE WATERING PUMP
2021-12-30 | N K TRADING CO(AJEPP2160M) | Pur - T1 | 9538 | 82500
FOR GARDENS - BILL NO 9538
2021-12-30 | N K TRADING CO(AJEPP2160M) | Pur - T1 | 9539 | 8310
FOR GARDENS - BILL NO 9539
2022-04-27 | HILTI (INDIA) PVT LTD.(AAACH3583Q) | Pur - T1 | HI27-3931-2022 | 77715.05
FOR GARDENS - HI27-3931-2022
2022-05-04 | N K TRADING CO(AJEPP2160M) | Pur - T1 | 9872 | 127906.4
FOR GARDENS - BILL NO 9872 , CASE NO - 42
2022-05-16 | N K TRADING CO(AJEPP2160M) | Pur - T1 | 9885 | 1852
FOR GARDENS - BILL NO 9885 , CASE NO -50
2022-05-16 | N K TRADING CO(AJEPP2160M) | Pur - T1 | 9884 | 300753
FOR GARDENS - BILL NO 9884 , CASE NO -50
2022-05-20 | N K TRADING CO(AJEPP2160M) | Pur - T1 | 9892 | 88601.5
CASE NO 52 - PRECISION MKAE PVC 20MM MMS ISI QTY 100NOS
2022-05-24 | N K TRADING CO(AJEPP2160M) | Pur - T1 | 9896 | 53073
CASE NO 56 TOTAL 10 ITEAM COME
2022-06-07 | KIMAYA GLOBAL SOURCING(AACPM1464C) | Pur - T1 | 0208/06/22-23 | 74500
FOR GARDENS - BILL NO 0208/06/22-23 CASE NO72.2 - ELECTRIC MATERIAL
2022-06-07 | N K TRADING CO(AJEPP2160M) | Pur - T1 | 9921 | 24267.6
CASE NO 72 WIRE FOR HALOGENS
2022-06-07 | N K TRADING CO(AJEPP2160M) | Pur - T1 | 9922 | 880.5
SAMPLE FOR JIGER BHAI
2022-06-08 | N K TRADING CO(AJEPP2160M) | Pur - T1 | 9925 | 72500
CASE NO : 72.2, HALOGEN'S FOR SITE, ONE MERAKI
2022-06-13 | MUKESH ELECTRONIC AND HARDWARE STORES(ALVPK4971E) | Pur - T1 | 5942 | 10080
INVOICE NO : 5942, WB 120L - 120 LTR WHEELED GARBAGE BINS
2022-06-15 | N K TRADING CO(AJEPP2160M) | Pur - T1 | 9933 | 57142
CASE NO - 84( ELECTRICAL CONDUICT) MATERIAL FOR SLAB
2022-06-15 |  |  |  | 111080
CASE NO 68 MCB PANEL
2022-06-15 |  |  |  | 1000
CASE NO 68- 16 AMP IP 44 PLUG S.P QTY 8NOS
2022-06-20 | N K TRADING CO(AJEPP2160M) | Pur - T1 | 9949 | 14300
CASE NO 85 - BOOSTER PUMP IN CONCREATE PLANT FOR MARAVLI SITE LABOUR* NEMINATH
2022-07-16 | N K TRADING CO(AJEPP2160M) | Pur - T1 | 10003 | 63355.25
CASE NO 66 & 97
2022-07-22 | N K TRADING CO(AJEPP2160M) | Pur - T1 | 10015 | 127928
CASE NO 99
2022-08-27 | N K TRADING CO(AJEPP2160M) | Pur - T1 | 10101 | 34520
CASE NO 128 ( FOR GROUND SLAB ELECTRICAL MATERAILS )
2022-09-01 | N K TRADING CO(AJEPP2160M) | Pur - T1 | 1017 | 100688
2022-09-03 | N K TRADING CO(AJEPP2160M) | Pur - T1 | 10114 | 106220
2022-10-28 | N K TRADING CO | Pur - T1 | 10222 | 111380
2022-11-08 | N K TRADING CO | Pur - T1 | 10245 | 34400
2022-11-08 | N K TRADING CO | Pur - T1 | 10246 | 2125
2022-11-16 | JAI MAHAKALI ENTERPRISES | Pur - T1 | 3361 | 41784
2022-12-01 | N K TRADING CO | Pur - T1 | 10299 | 2408.75
2022-12-03 | EAGLE SALES CORPORATION | Pur - T1 | 1/12885-22/23 | 13706.97
2022-12-03 | EAGLE SALES CORPORATION | Pur - T1 | 1/12873-22/23 | 47172
2022-12-16 | EAGLE SALES CORPORATION | Pur - T1 | 1/13643-22/23 | 82130.4
2022-12-21 | N K TRADING CO | Pur - T1 | 10343 | 14798
2022-12-24 | EAGLE SALES CORPORATION | Pur - T1 | 2/1970-22/23 | 224519.7
2022-12-26 | N K TRADING CO | Pur - T1 | 10356 | 72360
2022-12-27 | EAGLE SALES CORPORATION | Pur - T1 | 1/14272-22/23 | 14690.2
2022-12-27 | N K TRADING CO | Pur - T1 | 10357 | 1351.5
2022-12-31 | N K TRADING CO | Pur - T1 | 10373 | 5700
2022-12-31 | N K TRADING CO | Pur - T1 | 10372 | 32239
2023-01-07 | EAGLE SALES CORPORATION(AAAFE2557J) | Pur - T1 | 2/2074-22-23 | 60178.97
2023-01-10 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10398 | 644
2023-01-12 | EAGLE SALES CORPORATION(AAAFE2557J) | Pur - T1 | 2/2131-22/23 | 222456.88
2023-01-13 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10408 | 180386
2023-01-14 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10411 | 25575
2023-01-14 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10412 | 6250
2023-01-21 | A.J.INTERNATIONAL | Pur - T1 | 3967 | 108750
2023-02-06 | EAGLE SALES CORPORATION(AAAFE2557J) | Pur - T1 | 1/16746-23/23 | 2895
2023-02-08 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10466 | 14925
2023-02-08 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10469 | 1884
2023-02-10 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10477 | 3250
2023-02-11 | EAGLE SALES CORPORATION(AAAFE2557J) | Pur - T1 | 1/17300/22/23 | 59231.04
2023-02-13 | EAGLE SALES CORPORATION(AAAFE2557J) | Pur - T1 | 2/2446-22/23 | 224446.2
2023-02-22 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10513 | 36885
2023-02-27 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10531 | 6250
2023-03-01 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10534 | 316975
2023-03-16 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10573 | 4940
2023-03-17 | EAGLE SALES CORPORATION(AAAFE2557J) | Pur - T1 | 2/2724-22/23 | 278288.63
2023-03-17 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10578 | 30800
2023-04-07 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10714 | 14250
2023-04-07 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10717 | 18881
2023-04-19 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10747 | 19744.42
2023-04-21 | NEWTECH POWER INDUSTRIES PVT LTD(AAECN5208L) | Pur - T1 | MUM/158/23-24 | 67214.81
2023-05-08 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10785 | 58170
2023-05-08 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10786 | 66340.16
2023-05-08 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10784 | 217896
2023-05-19 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10825 | 9067.6
2023-05-19 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10820 | 43300
2023-05-22 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10832 | 98716.96
2023-05-22 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10834 | 169477.2
2023-05-22 | JAI MAHAKALI ENTERPRISES | Pur - T1 | JME/23-24/739 | 9043
2023-05-23 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10840 | 2950
2023-06-01 | M R ELECTRONICS | Pur - T1 | MRE/23-24/086 | 29200
2023-06-03 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10870 | 20435
2023-06-05 | EAGLE SALES CORPORATION(AAAFE2557J) | Pur - T1 | 1/3594-23/24 | 125056.8
2023-06-07 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10884 | 6575
2023-06-08 | JAI MAHAKALI ENTERPRISES | Pur - T1 | JME/23-24/1025 | 9484.48
2023-06-13 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10899 | 6765
2023-06-13 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10901 | 11229
2023-06-13 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10900 | 58071.8
2023-06-14 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10906 | 41467.7
2023-06-16 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10912 | 343800
2023-06-29 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10943 | 11800
2023-07-07 | JAI MAHAKALI ENTERPRISES | Pur - T1 | JME/23-24/1481 | 33526.64
2023-07-11 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10968 | 55505
2023-07-11 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10966 | 33500
2023-07-11 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10967 | 51256.65
2023-07-18 | EAGLE SALES CORPORATION(AAAFE2557J) | Pur - T1 | 2/794-23/24 | 35441
2023-07-28 | JAI MAHAKALI ENTERPRISES | Pur - T1 | JME/23-24/1858 | 48072.56
2023-08-01 | GLOBOTECH SOLUTIONS(AEDPB2049F) | Pur - T1 | 048/23-24 | 296850
2023-08-08 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11023 | 69390
2023-08-16 | JAI MAHAKALI ENTERPRISES | Pur - T1 | JME/23-24/2204 | 43313.98
2023-08-16 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11054 | 3509.44
2023-08-22 | BHARAT ENGINEERS | Pur - T1 | 1256/23-24 | 30400
2023-08-26 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11084 | 149812
2023-08-28 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11088 | 71074
2023-08-29 | JAI MAHAKALI ENTERPRISES | Pur - T1 | JME/23-24/2445 | 876588.8
2023-09-02 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11101 | 2100
2023-09-08 | BHARAT ENGINEERS | Pur - T1 | 1377/23-24 | 1162932
2023-09-11 | RADVISION ENGINEERING | Pur - T1 | 26 | 201600
2023-09-21 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11168 | 77145
2023-09-25 | JAI MAHAKALI ENTERPRISES | Pur - T1 | JME/23-24/2872 | 274063.36
2023-10-04 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11200 | 4800
2023-10-12 | JAI MAHAKALI ENTERPRISES | Pur - T1 | JME/23-24/3199 | 285067.2
2023-10-16 | JAI MAHAKALI ENTERPRISES | Pur - T1 | JME/23-24/3247 | 494881.8
2023-10-30 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11266 | 4489.6
2023-10-30 | GIGA LINK TECHNOLOGIES INDIA PVT LTD | Pur - T1 | INV/2324/3242 | 297247.5
2023-10-31 | BRIDGEWAY ELECTRIK SOLUTIONS PVT LTD | Pur - T1 | INV/2324/048 | 269500
2023-11-07 | JAI MAHAKALI ENTERPRISES | Pur - T1 | JME/23-24/3642 | 4850
2023-11-09 | BRIDGEWAY ELECTRIK SOLUTIONS PVT LTD | Pur - T1 | TI/23-24/0050 | 1656566
2023-11-17 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11309 | 6080
2023-11-18 | BRIDGEWAY ELECTRIK SOLUTIONS PVT LTD | Pur - T1 | TI/23-24/0054 | 77346
2023-11-21 | R.K. ENGINEERING PVT LTD | Pur - T1 | 12533-24/24 | 299659.65
2023-11-23 | BRIDGEWAY ELECTRIK SOLUTIONS PVT LTD | Pur - T1 | TI/23-24/0055 | 390205
2023-11-23 | R.K. ENGINEERING PVT LTD | Pur - T1 | 12563-23/24 | 853476
2023-11-25 | BRIDGEWAY ELECTRIK SOLUTIONS PVT LTD | Pur - T1 | TI/23-24/0057 | 478222
2023-11-28 | R.K. ENGINEERING PVT LTD | Pur - T1 | 12673-23/24 | 281712
2023-11-28 | R.K. ENGINEERING PVT LTD | Pur - T1 | 12674-23/24 | 50648
2023-11-29 | R.K. ENGINEERING PVT LTD | Pur - T1 | 12678-23/24 | 592
2023-11-29 | BHARAT ENGINEERS | Pur - T1 | 2010/23-24 | 2490300
2023-11-29 | BHARAT ENGINEERS | Pur - T1 | 2011-23-24 | 150000
2023-12-02 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11353 | 14300
2023-12-05 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11370 | 15648
2023-12-12 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11384 | 28170
2023-12-14 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11391 | 34002
2023-12-19 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11402 | 37401
2023-12-19 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11403 | 304756.9
2023-12-19 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11401 | 81093.5
2023-12-20 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11408 | 8245
2023-12-28 | SOLARSQUARE ENERGY PVT LTD | Pur - T1 | SSEPL/23-24/597 | 1778400
2023-12-29 | JAI MAHAKALI ENTERPRISES | Pur - T1 | JME/23-24/4491 | 14753.2
2024-01-06 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11451 | 16070
2024-01-15 | R.K. ENGINEERING PVT LTD | Pur - T1 | 13404-23/24 | 135143.85
2024-01-15 | R.K. ENGINEERING PVT LTD | Pur - T1 | 13405-23/24 | 42132
2024-01-17 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11473 | 9109
2024-01-17 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11469 | 5080
2024-01-19 | PLASMA ENGINEERING COMPANY(AAIFP1669E) | Pur - T1 | 0616 | 472046
2024-01-20 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11481 | 174440
2024-01-27 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11496 | 9774.3
2024-01-27 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11498 | 4551.04
2024-01-28 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 426 | 4220
2024-01-29 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11501 | 6026
2024-01-29 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11500 | 59864.5
2024-01-31 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11507 | 22052.81
2024-02-02 | PLASMA ENGINEERING COMPANY(AAIFP1669E) | Pur - T1 | 2023-24/0638 | 506099
2024-02-02 | TRUEBLUE ELECTRODES(AALFT7091B) | Pur - T1 | 1263 | 157600
2024-02-06 | EAGLE SALES CORPORATION(AAAFE2557J) | Pur - T1 | 1/16879-23/24 | 16737.6
2024-02-06 | GLOBOTECH SOLUTIONS(AEDPB2049F) | Pur - T1 | 0135/23-24 | 66750
2024-02-07 | SOLARSQUARE ENERGY PVT LTD | Pur - T1 | SSEPL/23-24/714 | 444600
2024-02-07 | SOLARSQUARE ENERGY PVT LTD | Pur - T1 | SSEPL/23-24/717 | 444600
2024-02-10 | R.K. ENGINEERING PVT LTD | Pur - T1 | 13804-23/24 | 61280
2024-02-12 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11531 | 500
2024-02-12 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11528 | 7294
2024-02-12 | VIRAJ ENTERPRISES(AAMPK2583J1ZA) | Pur - T1 | VE/23-24/246 | 391350
2024-02-14 | KANERIA PLAST PVT LTD(AAFCK1826N) | Pur - T1 | KP/9852/23-24 | 153900
2024-02-15 | BRIDGEWAY ELECTRIK SOLUTIONS PVT LTD | Pur - T1 | TI/23-24/0092 | 253177
2024-02-15 | R.K. ENGINEERING PVT LTD | Pur - T1 | 13897-23/24 | 6648
2024-02-24 | PLASMA ENGINEERING COMPANY(AAIFP1669E) | Pur - T1 | 2023-24/0699 | 432129
2024-02-29 | R.K. ENGINEERING PVT LTD | Pur - T1 | 14104-23/24 | 2576
2024-03-01 | SOLARSQUARE ENERGY PVT LTD | Pur - T1 | SSEPL/2023-24/511 | 889200
2024-03-01 | BRIDGEWAY ELECTRIK SOLUTIONS PVT LTD | Pur - T1 | TI/23-24/0093 | 221551
2024-03-04 | R.K. ENGINEERING PVT LTD | Pur - T1 | 306P-23/24 | 228718
2024-03-13 | BRIDGEWAY ELECTRIK SOLUTIONS PVT LTD | Pur - T1 | TI/23-24/104 | 64000
2024-03-14 | JAI MAHAKALI ENTERPRISES | Pur - T1 | JME/23-24/5981 | 43582
2024-03-15 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11617 | 34000
2024-03-16 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 11618 | 69550
2024-03-18 | GLOBOTECH SOLUTIONS(AEDPB2049F) | Pur - T1 | 0160/23-24 | 122275
2024-03-19 | R.K. ENGINEERING PVT LTD | Pur - T1 | 14376-23/24 | 228718
2024-03-21 | PRINCE CABLES LLP(ABBFP7158E-P) | Pur - T1 | INV/10802/23-24 | 115752.55
25295621.9

## 4T1 FABRICATION MATERAILS
4T1 FABRICATION MATERAILS
Ledger Account
1-Aug-22 to 31-Aug-22
Date |  | Vch Type | Vch No. | Debit | Credit
2022-08-23 | PARMAR KHIMJI MAVJI & CO(AALPP8208L) | Pur - T1 | PKM/MHLLP/61/2223 | 251750
CASE NO - 20922.2 ( PARMAR KHIMJI MAVJI &CO(GIRDER BEAM PLATE WORK GB7) ONE MERAKI)
2022-11-03 | ZC PARMAR KHIMJI MAVJI & CO | Pur - T1 | 86 | 1297095
2023-03-03 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K7585 | 73558
2023-04-28 | SAGUFA FABRICATION WORK | Pur - T1 | 1 | 45806.5
2023-05-03 | SAGUFA FABRICATION WORK | Pur - T1 | 2 | 21000
2023-07-27 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K11145 | 52905
2024-03-20 | MEGHNA FABRICS | Pur - T1 | 2173/2023-24 | 190476
1932590.5

## 4T1 FIRE FITTING EQUIPMENTS
4T1 FIRE FITTING EQUIPMENTS
Ledger Account
1-Sep-22 to 30-Sep-22
Date |  | Vch Type | Vch No. | Debit
2022-09-23 | HIRAO TRADING CO | Pur - T1 | 0332/22-23 | 3600
2022-11-09 | A.B. AJMERA & CO | Pur - T1 | 58/2022-23 | 52263.22
2022-11-09 | A.B. AJMERA & CO | Pur - T1 | 57/2022-23 | 756229.19
2022-11-15 | A.B. AJMERA & CO | Pur - T1 | 59/2022-23 | 592327.3
2022-11-22 | A.B. AJMERA & CO | Pur - T1 | 63/2022-23 | 120580
2022-11-22 | A.B. AJMERA & CO | Pur - T1 | 65/2022-23 | 11314.55
2022-11-22 | A.B. AJMERA & CO | Pur - T1 | 64/2022-23 | 252680
2022-11-25 | K B AJMERA & COMPANY | Pur - T1 | 2157 | 7200
2022-11-26 | A.B. AJMERA & CO | Pur - T1 | 71/2022-23 | 7550
2022-12-01 | A.B. AJMERA & CO | Pur - T1 | 73/2022-23 | 7200
2022-12-01 | A.B. AJMERA & CO | Pur - T1 | 74/2022-23 | 23500
2022-12-06 | A.B. AJMERA & CO | Pur - T1 | 79/2022-23 | 42625.04
2022-12-06 | A.B. AJMERA & CO | Pur - T1 | 78/22-23 | 102612
2022-12-06 | A.B. AJMERA & CO | Pur - T1 | 77/2022-23 | 194060
2023-01-01 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 82/2022-23 | 5306
2023-01-18 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 97/2022-23 | 864420.96
2023-01-21 | HIRAO TRADING CO | Pur - T1 | 0534/22-23 | 5400
2023-01-23 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 102/2022-23 | 10000
2023-01-23 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 101/2022-23 | 2670
2023-01-23 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 103/2022-23 | 82650
2023-01-25 | ZP LIVE WIRE SERVICES LLP | Pur - T1 | 2022-23/799 | 419262.5
2023-01-25 | ZP LIVE WIRE SERVICES LLP | Pur - T1 | 2022-23/798 | 4115062.5
2023-02-13 | ZP LIVE WIRE SERVICES LLP | Pur - T1 | 2022-23/819 | 580000
2023-02-13 | ZP LIVE WIRE SERVICES LLP | Pur - T1 | 2022-23/818 | 30075
2023-03-18 | HIRAO TRADING CO | Pur - T1 | 0654/22-23 | 55900
2023-03-23 | HIRAO TRADING CO | Pur - T1 | 0667/22-23 | 79735
2023-04-07 | HIRAO TRADING CO | Pur - T1 | 0013/23-24 | 89850
2023-04-10 | HIRAO TRADING CO | Pur - T1 | 0021/23-24 | 24040
2023-04-10 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10721 | 48500
2023-04-11 | H. TAYEBALLY RANGWALA & CO | Pur - T1 | 159 | 15938
2023-04-13 | LIVE WIRE SERVICES LLP(AAIFL6599H) | Pur - T1 | 2023-24/15 | 45000
2023-04-15 | VIRAJ ENTERPRISES(AAMPK2583J1ZA) | Pur - T1 | VE/23-24/14 | 2350
2023-04-21 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 2/2023-24 | 532015.5
2023-04-25 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 203 | 32940
2023-05-08 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 0016/2023-24 | 29160
2023-05-12 | HIRAO TRADING CO | Pur - T1 | 0087/23-24 | 8285
2023-05-23 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 28/2023-24 | 325324.1
2023-05-31 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 36/2023-24 | 10400
2023-05-31 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 35/2023-24 | 19050
2023-05-31 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 37/2023-24 | 15600
2023-05-31 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 34/2023-24 | 360
2023-05-31 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 31/2023-24 | 115696
2023-06-01 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 484 | 43480
2023-06-01 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 486 | 24600
2023-06-01 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 485 | 21360
2023-06-06 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 541 | 89220
2023-06-17 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 46/2023-24 | 847540.92
2023-06-19 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 48/2023-24 | 69942
2023-06-19 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 49/2023-24 | 157208
2023-06-21 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 755 | 2400
2023-07-04 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 56/2023-24 | 98610
2023-07-04 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 57/2023-24 | 64372
2023-07-04 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 55/2023-24 | 334556
2023-07-15 | HIRAO TRADING CO | Pur - T1 | 0207/23-24 | 9275
2023-07-21 | HIRAO TRADING CO | Pur - T1 | 0215/23-24 | 4062
2023-07-26 | H. TAYEBALLY RANGWALA & CO | Pur - T1 | 1935 | 5175
2023-08-03 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 64/2023-24 | 26800
2023-08-03 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1092 | 9150
2023-08-07 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1167 | 43750
2023-08-08 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 65/2023-24 | 28910
2023-08-21 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 69/2023-24 | 17932.8
2023-08-21 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 68/2023-24 | 13192
2023-08-21 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 67/2023-24 | 21009.6
2023-09-16 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1548 | 7200
2023-09-27 | M R ELECTRONICS | Pur - T1 | MRE/23-24/338 | 58400
2023-10-13 | NAVKAR ENTERPRISE | Pur - T1 | 23-24/2436 | 6550
2023-10-14 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 106/2023-24 | 103151.13
2023-10-16 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 108/2023-24 | 25650
2023-10-16 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 111/2023-24 | 1400
2023-10-16 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 107/2023-24 | 21390
2023-10-21 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1887 | 147301.44
2023-10-25 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 112/2023-24 | 132200
2023-10-31 | NAVKAR ENTERPRISE | Pur - T1 | 23-24/2661 | 19898
2023-11-01 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 122/2023-24 | 1152
2023-11-01 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 121/2023-24 | 2850
2023-11-03 | NAVKAR ENTERPRISE | Pur - T1 | 23-24/2705 | 1640
2023-11-09 | NAVKAR ENTERPRISE | Pur - T1 | 23-24/2814 | 2550
2023-11-17 | H. TAYEBALLY RANGWALA & CO | Pur - T1 | 3863 | 5553
2023-11-30 | H. TAYEBALLY RANGWALA & CO | Pur - T1 | 4124 | 3379
2023-11-30 | H. TAYEBALLY RANGWALA & CO | Pur - T1 | 4123 | 4964
2023-12-13 | NEWAGE FIRE PROTECTION INDUSTRIES PVT LTD | Pur - T1 | BM/2324/03218 | 22000
2023-12-29 | H. TAYEBALLY RANGWALA & CO | Pur - T1 | 4640 | 15343
2024-01-18 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 169/2023-24 | 3425
2024-01-18 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 170/2023-24 | 46288.4
2024-01-19 | HIRAO TRADING CO | Pur - T1 | 0559/23-24 | 197890.25
2024-01-19 | HIRAO TRADING CO | Pur - T1 | 0560/23-24 | 16575
2024-01-20 | VIRAJ ENTERPRISES(AAMPK2583J1ZA) | Pur - T1 | VE/23-24/225 | 3950
2024-01-22 | SANTOSH ARTS | Pur - T1 | SA-23-24-669 | 16588.8
2024-01-24 | VIRAJ ENTERPRISES(AAMPK2583J1ZA) | Pur - T1 | VE/23-24/226 | 179700
2024-01-30 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 179/2023-24 | 3072
2024-01-30 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 178/2023-24 | 6300
2024-01-31 | VIRAJ ENTERPRISES(AAMPK2583J1ZA) | Pur - T1 | VE/23-24/229 | 54500
2024-01-31 | HIRAO TRADING CO | Pur - T1 | 0570/23-24 | 10365
2024-02-01 | M R ELECTRONICS | Pur - T1 | MRE/23-24/569 | 87500
2024-02-01 | J K ENTERPRISES | Pur - T1 | 675/2023-24 | 123865
2024-02-01 | VIRAJ ENTERPRISES(AAMPK2583J1ZA) | Pur - T1 | VE/23-24/231 | 419300
2024-02-05 | VIRAJ ENTERPRISES(AAMPK2583J1ZA) | Pur - T1 | VE/23-24/239 | 116150
2024-02-06 | VIRAJ ENTERPRISES(AAMPK2583J1ZA) | Pur - T1 | VE/23-24/241 | 109250
2024-02-06 | MUNSHI FASTENERS(DYPPS0927A) | Pur - T1 | 317 | 325
2024-02-08 | VIRAJ ENTERPRISES(AAMPK2583J1ZA) | Pur - T1 | VE/23-24/242 | 39800
2024-02-09 | VIRAJ ENTERPRISES(AAMPK2583J1ZA) | Pur - T1 | VE/23-24/244 | 215650
2024-02-13 | VIRAJ ENTERPRISES(AAMPK2583J1ZA) | Pur - T1 | VE/23-24/247 | 320000
2024-02-20 | VIRAJ ENTERPRISES(AAMPK2583J1ZA) | Pur - T1 | VE/23-24/254 | 43150
2024-02-20 | VIRAJ ENTERPRISES(AAMPK2583J1ZA) | Debit Note | VE/23-24/CN/01 | -51150
2024-02-21 | ARYAN FIRE SAFETY AND SOLUTIONS | Pur - T1 | 167 | 35117
2024-02-22 | VIRAJ ENTERPRISES(AAMPK2583J1ZA) | Pur - T1 | VE/23-24/256 | 30800
2024-03-01 | HIRAO TRADING CO | Pur - T1 | 0614/23-24 | 8700
2024-03-01 | HIRAO TRADING CO | Pur - T1 | 0615/23-24 | 20273
2024-03-01 | HIRAO TRADING CO | Pur - T1 | 0620/23-24 | 9625
2024-03-01 | HIRAO TRADING CO | Pur - T1 | 0613/23-24 | 86148.5
2024-03-06 | ARYAN FIRE SAFETY AND SOLUTIONS | Pur - T1 | 172 | 66480
2024-03-13 | VIRAJ ENTERPRISES(AAMPK2583J1ZA) | Pur - T1 | VE/23-24/275 | 135000
2024-03-15 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K17009 | 156850
2024-03-16 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K17099 | 38547.5
14803884.2

## 4T1 GST Amount
4T1 GST CREDIT REVERSAL
Ledger Account
1-Apr-21 to 31-Aug-22
Date |  | Vch Type | Vch No. | Debit | Credit
2021-04-30 | 1P T1 CGST INPUT @09.00%(1P MG CGST INPUT @09.00%) | Journal | APR-21 | 27000
INELIGIBLE AGAINST 5%
2021-05-31 | 1P T1 CGST INPUT @09.00%(1P MG CGST INPUT @09.00%) | Journal | MAY-21 | 821400.66
INELIGIBLE AGAINST 5%
2021-06-30 | 1P T1 CGST INPUT @02.50%(1P MG CGST INPUT @02.50%) | Journal | JUN-21 | 630032.94
INELIGIBLE AGAINST 5%
2021-07-31 | 1P T1 CGST INPUT @09.00%(1P MG CGST INPUT @09.00%) | Journal | JUL-21 | 327470.28
INELIGIBLE AGAINST 5%
2021-08-31 |  |  |  | 288531.8
INELIGIBLE AGAINST 5%
2021-09-30 |  |  |  | 62643.74
INELIGIBLE AGAINST 5%
2021-10-31 | 1P T1 CGST INPUT @09.00%(1P MG CGST INPUT @09.00%) | Journal | OCT-21 | 27000
INELIGIBLE AGAINST 5%
2021-11-30 | 1P T1 CGST INPUT @09.00%(1P MG CGST INPUT @09.00%) | Journal | NOV-21 | 180000
INELIGIBLE AGAINST 5%
2021-12-31 | 1P T1 CGST INPUT @06.00%(1P MG CGST INPUT @06.00%) | Journal | DEC-21 | 9900
INELIGIBLE AGAINST 5%
2021-12-31 | 1P T1 CGST INPUT @09.00%(1P MG CGST INPUT @09.00%) | Journal | DEC-21 | 1495.8
INELIGIBLE AGAINST 5%
2021-12-31 | 1P T1 IGST INPUT @18.00%(1P MG IGST INPUT @18.00%) | Journal | DEC-21 | 4899.6
INELIGIBLE AGAINST 5%
2022-01-31 | 1P T1 CGST INPUT @09.00%(1P MG CGST INPUT @09.00%) | Journal | JAN-22 | 113580
INELIGIBLE AGAINST 5%
2022-02-28 | 1P T1 CGST INPUT @09.00%(1P MG CGST INPUT @09.00%) | Journal | FEB-22 | 1782
INELIGIBLE AGAINST 5%
2022-03-31 | 1P T1 CGST INPUT @09.00%(1P MG CGST INPUT @09.00%) | Journal | MAR-22 | 3104119.48
INELIGIBLE AGAINST 5%
2022-04-30 | 1P T1 CGST INPUT @02.50%(1P MG CGST INPUT @02.50%) | Journal | APR-22 | 2888283.38
INELIGIBLE AGAINST 5%
2022-05-31 | 1P T1 CGST INPUT @02.50%(1P MG CGST INPUT @02.50%) | Journal | MAY-22 | 3291464.04
INELIGIBLE AGAINST 5%
2022-06-30 | 1P T1 CGST INPUT @02.50%(1P MG CGST INPUT @02.50%) | Journal | JUN-22 | 3412083.68
INELIGIBLE AGAINST 5%
2022-07-31 | 1P T1 CGST INPUT @02.50%(1P MG CGST INPUT @02.50%) | Journal | JUL-22 | 4178299.9
INELIGIBLE AGAINST 5%
2022-10-31 | 1P T1 CGST INPUT @02.50% | Journal | OCT-22 | 9278426.8
2022-11-30 | 1P T1 CGST INPUT @02.50% | Journal | NOV-22 | 6717548.02
2023-01-31 | 1P T1 CGST INPUT @02.50%(1P MG CGST INPUT @02.50%) | Journal | JAN-23 | 9293779.42
2023-04-30 | 1P T1 CGST INPUT @02.50% | Journal | APR-23 | 7614040.75
2023-07-31 | 1P T1 CGST INPUT @02.50% | Journal | JUL-23 | 2370659.1
2023-08-31 | 1P T1 CGST INPUT @02.50% | Journal | AUG-23 | 3339806.87
2023-10-31 | 1P T1 CGST INPUT @06.00% | Journal | OCT-23 | 3699971.51
2023-11-30 | 1P T1 CGST INPUT @06.00% | Journal | NOV-23 | 10594632.54
72278852.31
`

## 4T1 HARDWARE
4T1 HARDWARE
Ledger Account
1-Mar-22 to 31-Aug-22
Date |  | Vch Type | Vch No. | Debit | Credit
2022-03-31 | MEHTA ENETERPRISES(AABPJ3814A) | Pur - T1 | 619 | 4571
BILL NO - 619 - ONE MERAKI
2022-04-20 | MEHTA ENETERPRISES(AABPJ3814A) | Pur - T1 | 37 | 3290
BILL NO - 37 -PARK
2022-04-26 | MEHTA ENETERPRISES(AABPJ3814A) | Pur - T1 | 45 | 746
BILL NO - 45 -(HARDWARE ITEMS FOR CURING PIPE FITTING FOR MERAKI ONE)
2022-05-13 | MEHTA ENETERPRISES(AABPJ3814A) | Pur - T1 | 84 | 3495
CASE NO- 030622.5 (HARDWARE) BNO 84
2022-05-18 | MEHTA ENETERPRISES(AABPJ3814A) | Pur - T1 | 89 | 2405
CASE NO - 2502522.89 -FOR LABOUR CAMP MERAKI ONE
2022-05-25 | MEHTA ENETERPRISES(AABPJ3814A) | Pur - T1 | 113 | 2431
CASE NO - 030622.02 -FOR LABOUR CAMP MERAKI ONE
2022-05-30 | MEHTA ENETERPRISES(AABPJ3814A) | Pur - T1 | 116 | 1981
BILL NO - 116, ONE MERAKI
2022-06-12 | MEHTA ENETERPRISES(AABPJ3814A) | Pur - T1 | 134 | 4485
CASE NO 250622134 - MEHTA ENTERPRISE( BILL NO:134) ONE MERAKI
2022-06-13 | MEHTA ENETERPRISES(AABPJ3814A) | Pur - T1 | 135 | 3405
CASE NO - 250622135 - MEHTA ENTERPRISES(BILL N0:135) ONE MERAKI
2022-06-18 | MEHTA ENETERPRISES(AABPJ3814A) | Pur - T1 | 145 | 4322
CASE NO 250622145 - MEHTA ENTERPRISE(BILL NO:145) ONE MERAKI
2022-06-19 | MEHTA ENETERPRISES(AABPJ3814A) | Pur - T1 | 147 | 2585
CASE NO - 250622147 - MEHTA ENTERPRISE(BILL NO:147)ONE MERAKI
2022-06-19 | MEHTA ENETERPRISES(AABPJ3814A) | Pur - T1 | 146 | 1070
CASE NO - 250622146 -MEHTA ENTERPRISE(BILL NO:146)ONE MERAKI
2022-06-24 | MEHTA ENETERPRISES(AABPJ3814A) | Pur - T1 | 159 | 860
CASE NO - 300622159 - (CURING LINE WORK
2022-06-24 | MEHTA ENETERPRISES(AABPJ3814A) | Pur - T1 | 158 | 2206
CASE NO -300622158 ( SHILPA TOILET SHIFTING )
2022-06-30 | MEHTA ENETERPRISES(AABPJ3814A) | Pur - T1 | 173 | 559
BILL NO 173 - MEHTA ENTERPRISES(HARDWARE) CURING PIPES REPAIRING FITTINGS SHILPA SIDE
2022-07-05 | MEHTA ENETERPRISES(AABPJ3814A) | Pur - T1 | 181 | 2360
CASE NO - 160722.2 MEHTA ENTERPRISES(HARDWARE ) DANGERTAPE,UPVC PIPE FITTINGS FOR REPAIRING
2022-07-14 |  |  |  | 6258
CASE NO - 160722.3
2022-07-28 |  |  |  | 3845
case no 100822 ( LABOUR TOILET DOOR KADI HINGES,PLUMBING MATERIAL) ONE MERAKI
2022-10-16 | MEHTA ENETERPRISES | Pur - T1 | 336 | 2325
2022-10-28 | MEHTA ENETERPRISES | Pur - T1 | 348 | 1555
2022-11-08 | MUNSHI FASTENERS | Pur - T1 | 313 | 15388
2022-11-18 | MEHTA ENETERPRISES | Pur - T1 | 373 | 1430
2022-12-05 | MEHTA ENETERPRISES | Pur - T1 | 402 | 2704
2022-12-12 | MEHTA ENETERPRISES | Pur - T1 | 411 | 1590
2022-12-25 | MEHTA ENETERPRISES | Pur - T1 | 430 | 3064
2023-01-08 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 456 | 2689
2023-02-17 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 509 | 3426
2023-02-23 | JYOTI HARDWARE STORES(AAAFJ1248F) | Pur - T1 | 3537 | 6200
2023-02-23 | JYOTI HARDWARE STORES(AAAFJ1248F) | Pur - T1 | 3536 | 28040
2023-02-24 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 520 | 2875
2023-05-07 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 58 | 1395
2023-05-13 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 66 | 2015
2023-05-15 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 67 | 925
2023-05-29 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 87 | 1850
2023-05-29 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 88 | 3380
2023-06-13 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 108 | 2950
2023-08-11 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 197 | 1215
2023-08-15 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 205 | 1985
2023-08-19 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 209 | 1777.5
2023-08-23 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 214 | 2555
2023-08-23 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 215 | 4020
2023-09-02 | JYOTI HARDWARE STORES(AAAFJ1248F) | Pur - T1 | 3917 | 42235
2023-09-03 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 225 | 1570
2023-09-03 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 226 | 3786
2023-09-10 | JYOTI HARDWARE STORES(AAAFJ1248F) | Pur - T1 | 3944 | 18000
2023-09-11 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 239 | 2328
2023-09-11 | JYOTI HARDWARE STORES(AAAFJ1248F) | Pur - T1 | 3946 | 77135
2023-09-15 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 247 | 4405
2023-09-23 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 254 | 1465
2023-09-30 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 265 | 1500
2023-10-05 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 271 | 1740
2023-11-02 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 326 | 2363
2023-11-04 | JYOTI HARDWARE STORES(AAAFJ1248F) | Pur - T1 | 4023 | 62880
2023-11-05 | JYOTI HARDWARE STORES(AAAFJ1248F) | Pur - T1 | 4025 | 69130
2023-11-05 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 327 | 5213
2023-11-14 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 335 | 2960
2023-11-18 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T1 | 337 | 2183
2023-11-19 | JYOTI HARDWARE STORES(AAAFJ1248F) | Pur - T1 | 4050 | 13500
2024-01-04 | MEHTA ENTERPRISES | Pur - T1 | 400 | 1930
2024-02-09 | MEHTA ENTERPRISES | Pur - T1 | 442 | 6600
2024-02-09 | JYOTI HARDWARE STORES | Pur - T1 | 4203 | 11050
2024-02-09 | JYOTI HARDWARE STORES | Pur - T1 | 4202 | 13100
2024-02-12 | JYOTI HARDWARE STORES | Pur - T1 | 4207 | 2850
2024-02-17 | JYOTI HARDWARE STORES | Pur - T1 | 4221 | 35980
2024-03-01 | JYOTI HARDWARE STORES | Pur - T1 | 4242 | 19750
2024-03-01 | JYOTI HARDWARE STORES | Pur - T1 | 4241 | 10150
2024-03-15 | MEHTA ENTERPRISES | Pur - T1 | 488 | 3071
2024-03-21 | JYOTI HARDWARE STORES | Pur - T1 | 4293 | 4710
2024-03-21 | JYOTI HARDWARE STORES | Pur - T1 | 4292 | 12300
2024-03-21 | JYOTI HARDWARE STORES | Pur - T1 | 4291 | 5420
2024-03-21 | JYOTI HARDWARE STORES | Pur - T1 | 4289 | 35940
2024-03-30 | MEHTA ENTERPRISES | Pur - T1 | 506 | 3970
625441.5

## 4T1 LABOUR CHARGES
4T1 LABOUR CHARGES
Ledger Account
1-Jul-21 to 31-Aug-22
Date |  | Vch Type | Vch No. | Debit | Credit
2021-07-07 | ZC RAVIPRASAD GANESH ZANTYE - HUF(AAPHR8752M) | Pur - T1 | 02RGZ/21-22 | 622500
BILL NO. 02RGZ/21-22 SABARI GARDENS
2021-07-20 |  |  |  | 390000
BILL NO. 03RGZ/21-22 SABARI GARDENS
2021-09-16 |  |  |  | 348020.8
B NO 05RGZ/21-22 - GARDENS
2022-04-18 | ZC RAVIPRASAD GANESH ZANTYE - HUF(AAPHR8752M) | Pur - T1 | 01RGZ/22-23 | 1747500
BILL NO. 01RGZ/22-23 SABARI GARDENS
2022-10-17 | ZC ATRI BUILDTECH - RESI | Pur - T1 | AB/OM001 | 4000000
2022-11-07 | ZC ATRI BUILDTECH - RESI | Pur - T1 | AB/0M002 | 4000000
2022-11-15 | ZC ATRI BUILDTECH - RESI | Pur - T1 | AB/0M003 | 4500000
2022-11-21 | ZC ATRI BUILDTECH - RESI | Pur - T1 | AB/OM004 | 4000000
2022-11-30 | ZC ATRI BUILDTECH - RESI | Pur - T1 | AB/OM005 | 1500000
2022-12-10 | ZC ATRI BUILDTECH - RESI | Pur - T1 | AB/OM006 | 5000000
2022-12-24 | ZC ATRI BUILDTECH - RESI | Pur - T1 | AB/0M008 | 5000000
2022-12-27 | ZC MORE ELECTRICAL & ENGINEERING WORKS | Pur - T1 | 155 | 68133
2022-12-29 | ZC ATRI BUILDTECH - RESI | Pur - T1 | AB/0M009 | 4325370
2023-01-02 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 157 | 68133
2023-01-11 | ZC ATRI BUILDTECH - RESI(ABUFA5341H-P) | Pur - T1 | AB/OM010 | 4325370
2023-01-18 | ZC ATRI BUILDTECH - RESI(ABUFA5341H-P) | Pur - T1 | AB/OM011 | 2162685
2023-01-23 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 161 | 68133
2023-01-23 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 160 | 68133
2023-01-25 | ZC ATRI BUILDTECH - RESI(ABUFA5341H-P) | Pur - T1 | AB/OM012 | 2162685
2023-01-28 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 162 | 68133
2023-01-28 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 166 | 68133
2023-02-03 | ZC ATRI BUILDTECH - RESI(ABUFA5341H-P) | Pur - T1 | AB/OM013 | 2162685
2023-02-04 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 166 | 68133
2023-02-11 | ZC ATRI BUILDTECH - RESI(ABUFA5341H-P) | Pur - T1 | AB/OM014 | 2162685
2023-02-17 | ZC ATRI BUILDTECH - RESI(ABUFA5341H-P) | Pur - T1 | AB/OM015 | 2162685
2023-02-18 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 171 | 68133
2023-02-18 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 172 | 68133
2023-02-24 | ZC ATRI BUILDTECH - RESI(ABUFA5341H-P) | Pur - T1 | AB/OM016 | 2162685
2023-03-03 | ZC ATRI BUILDTECH - RESI(ABUFA5341H-P) | Pur - T1 | AB/OM017 | 2162685
2023-03-13 | ZC ATRI BUILDTECH - RESI(ABUFA5341H-P) | Pur - T1 | AB/OM018 | 4325370
2023-03-13 | ZC ATRI BUILDTECH - RESI(ABUFA5341H-P) | Pur - T1 | AB/OM019 | 1854160
2023-03-28 | ZC ATRI BUILDTECH - RESI(ABUFA5341H-P) | Pur - T1 | AB/OM020 | 4325370
2023-04-05 | ZC UTRACON STRUCTURAL SYSTEMS PVT LTD - ONE MERAKI(AAACU6685L-M) | Pur - T1 | MH/2324/M012 | 58000
2023-04-06 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 191 | 68133
2023-04-12 | ZC ATRI BUILDTECH - RESI -T1(ABUFA5341H-P) | Pur - T1 | AB/OM021 | 2162685
2023-04-12 | ZC ATRI BUILDTECH - RESI -T1(ABUFA5341H-P) | Pur - T1 | AB/OM022 | 2317700
2023-04-12 | ZC ATRI BUILDTECH - RESI -T1(ABUFA5341H-P) | Pur - T1 | AB/OM023 | 1545635
2023-04-12 | ZC SUNRISE EARTH MOVERS(AAFPC0470K) | Pur - T1 | SEM/23-24/0006 | 7000
2023-04-13 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 192 | 68133
2023-04-17 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 194 | 190773
2023-04-19 | SAITECH INSTRUMENTS PVT LTD | Pur - T1 | 60 | 4000
2023-04-21 | ZC ATRI BUILDTECH - RESI -T1(ABUFA5341H-P) | Pur - T1 | AB/OM024 | 2162685
2023-04-22 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 197 | 68133
2023-05-10 | ZC ATRI BUILDTECH - RESI -T1(ABUFA5341H-P) | Pur - T1 | AB/OM025 | 1854160
2023-05-10 | ZC ATRI BUILDTECH - RESI -T1(ABUFA5341H-P) | Pur - T1 | AB/OM026 | 2473016
2023-05-17 | ZC ATRI BUILDTECH - RESI -T1(ABUFA5341H-P) | Pur - T1 | AB/OM027 | 2162685
2023-05-23 | ZC ATRI BUILDTECH - RESI -T1(ABUFA5341H-P) | Pur - T1 | AB/OM028 | 6845850
2023-05-24 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 201 | 68133
2023-05-24 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 199 | 109013
2023-06-02 | ZC SAJID JAMAL(BNNPJ4700K) | Pur - T1 |  | 116090
2023-06-14 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 202 | 163520
2023-06-27 | ZC ATRI BUILDTECH - RESI -T1(ABUFA5341H-P) | Pur - T1 | AB/OM029 | 1545635
2023-06-27 | ZC ATRI BUILDTECH - RESI -T1(ABUFA5341H-P) | Pur - T1 | AB/OM030 | 2317700
2023-06-27 | ZC ATRI BUILDTECH - RESI -T1(ABUFA5341H-P) | Pur - T1 | AB/OM031 | 8133400
2023-07-01 | ZC SAJID JAMAL(BNNPJ4700K) | Pur - T1 |  | 87425
2023-07-05 | ZC ATRI BUILDTECH - RESI -T1(ABUFA5341H-P) | Pur - T1 | AB/OM032 | 5400000
2023-07-10 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 207 | 217878
2023-07-10 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 206 | 163520
2023-07-10 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 205 | 196650
2023-08-17 | ZC SAJID JAMAL(BNNPJ4700K) | Pur - T1 |  | 58600
2023-09-01 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 217 | 204400
2023-09-03 | ELITE CRETE WESTERN INDIA(AAGFE9079D) | Pur - T1 | ECWI/012/2023-24 | 786165
2023-09-06 | ZC SAJID JAMAL(BNNPJ4700K) | Pur - T1 |  | 76577
2023-09-26 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 225 | 217878
2023-10-05 | ZC SAJID JAMAL(BNNPJ4700K) | Pur - T1 |  | 76950
2023-10-30 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 235 | 42265
2023-11-04 | ZC JSA CONSTRUCTION(BHSPM4751L-P) | Pur - T1 |  | 139575
2023-12-01 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T1 | 237 | 204404
2023-12-01 | ZC ATRI BUILDTECH - RESI -T1(ABUFA5341H-P) | Debit Note | T1/AB/001 | -7600
2023-12-01 | ZC ATRI BUILDTECH - RESI -T1(ABUFA5341H-P) | Debit Note | T1/AB/008 | -287035
2023-12-01 | ZC ATRI BUILDTECH - RESI -T1(ABUFA5341H-P) | Debit Note | T1/AB/009 | -289100
2023-12-01 | ZC ATRI BUILDTECH - RESI -T1(ABUFA5341H-P) | Debit Note | T1/AB/013 | -30630
2023-12-08 | ZC JSA CONSTRUCTION(BHSPM4751L-P) | Pur - T1 | 01 | 159950
2024-01-09 | ZC JSA CONSTRUCTION | Pur - T1 | 01 | 204650
2024-01-13 | ZC MORE ELECTRICAL & ENGINEERING WORKS | Pur - T1 | 246 | 36981
2024-01-22 | ZC SUNRISE EARTH MOVERS | Pur - T1 | SEM/23-24/0089 | 116700
2024-02-01 | ZC SHIVANYA CONSTRUCTION | Pur - T1 | SC/01,23-24 | 981095.1
2024-02-05 | ZC JSA CONSTRUCTION | Pur - T1 |  | 29100
2024-02-05 | ZC JSA CONSTRUCTION | Pur - T1 | 01/24 | 158500
2024-02-05 | ZC GOND ENTERPRISE | Pur - T1 | 104 | 1945132.43
2024-02-07 | ZC GOND ENTERPRISE | Pur - T1 | 105 | 1498324.86
2024-02-19 | ZC SUNRISE EARTH MOVERS | Pur - T1 | SEM/23-24/0094 | 140600
2024-02-26 | ZC MORE ELECTRICAL & ENGINEERING WORKS | Pur - T1 | 250 | 99180
2024-03-01 | ZC SUNRISE EARTH MOVERS | Pur - T1 | SEM/23-24/0100 | 154200
2024-03-01 | ZC SHIVANYA CONSTRUCTION | Pur - T1 | SC/02,23-24 | 787803
2024-03-05 | MAHAVIR SANITATION PVT LTD | Pur - T1 | MSPL2324088 | 525812.13
2024-03-07 | ZC PRATHAM ENVIROTECH SOLUTIONS | Pur - T1 | 84/23-24 | 3800000
2024-03-12 | ZC JSA CONSTRUCTION | Pur - T1 |  | 290225
2024-03-12 | ZC GOND ENTERPRISE | Debit Note | T1/JSA/09 | -18800
2024-03-12 | MAHAVIR SANITATION PVT LTD | Debit Note | T1/JSA/11 | -9400
118615707.32

## 4T1 PLUMBING MATERIAL
4T1 PLUMBING MATERIAL
Ledger Account
1-May-21 to 31-Aug-22
Date |  | Vch Type | Vch No. | Debit | Credit
2021-05-31 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/048 | 46580
B NO 48 - GARDENS
2021-06-09 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/61 | 88180
B NO 61 - GARDENS
2021-07-01 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/54 | 46580
B NO 54 - GARDENS
2021-07-08 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/84 | 14650
B NO 84 - GARDENS
2021-07-23 | HARI OM MARBLE(AAAPC7857R) | Pur - T1 | 740 | 49450
BILL NO -740 - SABARI GARDENS-SAMPLE FLAT
2021-08-02 | SIDDHIVINAYAK ENTERPRISES(EWPS4017K) | Pur - T1 | 2021-22 /SV 4091 | 24153
BILL NO -2021-22 /SV 4091394, SABARI GARDENS
2021-08-09 | ZC STRUCTWEL DESIGNERS & CONSULTANTS PVT. LTD.(AACCS 2638 F) | Pur - T1 | SAN2122-001153 | 4218
B NO SAN2122-001153 - GARDENS
2022-03-23 | CLASSIC CERAMIC PLUS | Pur - T1 | 658/21-22 | 8474.6
BILL NO - 658/21-22 CASE NO 15
2022-03-31 | PIPEWALE.COM(27AACHL1500N1ZD) | Pur - T1 | 565/2021-22' ** | 10950
BILL NO -565/2021-2022 -
2022-04-04 | VEDANT MARKETING(AANFV8458J) | Pur - T1 | 010/22-23 | 108000
BILL NO - 010/22-23 CASE NO - 27.3
2022-04-05 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/08 | 39746
BILL NO TS/08- CASE NO 27
2022-04-05 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/09 | 39746
BILL NO TS/09- CASE NO 27
2022-04-05 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/10 | 39627
BILL NO TS/10 CASE NO 27
2022-04-07 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/13 | 47600
BILL NO TS/13 CASE NO 27
2022-04-12 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/21 | 47600
BILL NO TS/21 CASE NO 27
2022-04-16 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/22 | 47600
BILL NO TS/22 CASE NO 27
2022-04-18 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/23 | 71400
BILL NO TS/23 CASE NO 27
2022-04-20 | VEDANT MARKETING(AANFV8458J) | Pur - T1 | 185/22-23 | 108000
BILL NO -185/22-23 CASE NO - 35.2
2022-04-20 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/25 | 47600
BILL NO TS/25 CASE NO 35
2022-04-21 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/27 | 39746
BILL NO TS/27 CASE NO 35
2022-04-21 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/28 | 39746
BILL NO TS/28 CASE NO 35
2022-04-23 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/31 | 39746
BILL NO TS/31 CASE NO 35
2022-04-23 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/32 | 39746
BILL NO TS/32 CASE NO 35
2022-05-01 | VEDANT MARKETING(AANFV8458J) | Pur - T1 | 001/22-23 | 108000
CASE NO 27.3 - FOSROC CONPLAST SP 430 SRV (250 KG ) QTY 2,500KG
2022-05-04 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/51 | 71400
CASE NO - 35.2 - POZZOCRETE 60 CLASSIFIED COAL FLY ASH 30 KG PER BAG QTY 600 BAG ( ADVANCE PAID )
2022-05-06 | VEDANT MARKETING(AANFV8458J) | Pur - T1 | 339/22-23 | 108000
BILL NO -339/22-23 , CASE NO 35.3
2022-05-07 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/55 | 39746
CASE NO - 35.2 -POZZOCRETE 60 CLASSIFIED COAL FLY ASY 30 KG PER BAG QTY 334 BAGS
2022-05-07 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/56 | 39746
CASE NO - 35.2 -POZZOCRETE 60 CLASSIFIED COAL FLY ASY 30 KG PER BAG QTY 334 BAGS
2022-05-09 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/57 | 47600
CASE NO - 35.2 -POZZOCRETE 60 CLASSIFIED COAL FLY ASY 30 KG PER BAG QTY 400 BAG
2022-05-15 | CLASSIC CERAMIC PLUS | Pur - T1 | 103/22-23 | 19830.56
CASE NO 42 FOR SLAB 3,2 FLOOR - 110MM PIPE 10'S/S TYBE "B" QTY 20 NOS
2022-05-16 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/70 | 71400
CASE NO :36, POZZOCRETE 60 CLASSIFIED COAL FLY ASH
2022-05-19 | VEDANT MARKETING(AANFV8458J) | Pur - T1 | 464/22-23 | 183037.5
CASE NO 35.3 FOSROC CONPLAST SP430 SRV(250KG) ALT QTY 4 DRUM QTY 1000KGS & FOSROC CONPLAST SP 430 SRV (250 KGS )
2022-05-20 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/076 | 8322
CASE NO 55, SAFETY SHOES 9 PAIR AND TRANSPORTATION CHARGES
2022-05-20 | TUSHAR STEEL(AAEPK3479R) | Pur - Park | TS/77 | 47600
CASE NO :36, POZZOCRETE 60 CLASSIFIED COAL FLY ASH
2022-05-20 | TUSHAR STEEL(AAEPK3479R) | Pur - Park | TS/76 | 7722
CASE NO :36, POZZOCRETE 60 CLASSIFIED COAL FLY ASH
2022-05-20 | TUSHAR STEEL(AAEPK3479R) | Pur - Park | TS/76 | 600
CASE NO :36, POZZOCRETE 60 CLASSIFIED COAL FLY ASH
2022-05-21 | TUSHAR STEEL(AAEPK3479R) | Pur - Park | TS/078 | 106800
CASE NO - 54.2, BILL NO - TS/78,PARK
2022-05-24 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/82 | 47600
CASE NO :36, POZZOCRETE 60 CLASSIFIED COAL FLY ASH
2022-05-26 | SAPAN TRADING COMPANY | Pur - T1 | 1174 | 28250
CASE NO - 280522.3 -DEWATERING PUMP REPAIRING 2NOS MERAKI ONE
2022-05-27 | KUBER INFRA SOLUTION(ADKPR6817K) | Pur - T1 | KIS/SL/2022-23/061 | 194000
CASE NO 61 - FOR SLABV STOPPER JOINTS IN BASEMENT 3,2,1 A & B WING -HY-RIB SHEET
2022-05-27 | TUSHAR STEEL(AAEPK3479R) | Pur - Park | TS/86 | 47600
CASE NO :36, POZZOCRETE 60 CLASSIFIED COAL FLY ASH
2022-05-29 | CLASSIC CERAMIC PLUS | Pur - T1 | 133/22-23 | 77313.19
B NO 133 -CASE NO 59,62,64
2022-05-30 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/90 | 71400
CASE NO :36, POZZOCRETE 60 CLASSIFIED COAL FLY ASH
2022-06-01 | S2P SANITATION SERVICES(ACZFS9029G) | Pur - Park | S2P/22-23/05/087 | 46550
FOR TOILET MONTHLY RENT
2022-06-02 | CLASSIC CERAMIC PLUS | Pur - T1 | 143/22-23 | 61702.24
B NO 143 -CASE NO 59,62,64
2022-06-06 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS | 161050
CASE NO 77, DEWATERING HOUSE PIPE WITH ACCESSSORIES
2022-06-10 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/102 | 78290
BILL NO TS/102
2022-06-11 | R.K. DRILLING(ABGPU2524A) | Pur - T1 | 016-2022 | 162018
CASE NO 160622 (REBAR GROUTING OG G+1,CORE CUT FOR WEEP HOLES IN OLD RETAINING WALL,HILTI REBAR GROUTING IN PLUM CONCRETE,BREAKER SUPPLY WITH LABOUR(ONE MERAKI)
2022-06-11 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/104 | 82760
BILL NO TS/104
2022-06-18 | R.K. DRILLING(ABGPU2524A) | Pur - T1 | 022-2022 | 19600
CASE NO -180622.2 ( R.K DRILLING(CLEANING OF CONCRETE PIPELINE (3MTS:6 NOS & 2MTS:1 NOS)ONE MERAKI
2022-06-18 | VEDANT MARKETING(AANFV8458J) | Pur - T1 | 772/22-23 | 42300
CASE NO 54 - BONDING AGENT FOR CONCRET FOR ONE MERAKI
2022-06-18 | CLASSIC CERAMIC PLUS | Pur - T1 | 180/22-23 | 59322.2
CASE NO 81 URGENT WATER TANK FOR CONCRETE PLANT
2022-06-29 | HELLA INFRA MARKET RETAIL PVT LTD | Pur - T1 | KAM/BLC/0622/032 | 123500
BILL KAM/BLC/0622/032
2022-06-29 |  |  |  | 132854.38
BILL KAM/BLC/0622/031
2022-07-01 |  |  |  | 141280.07
CASE NO 56.1- FOR ELECTRICAL FIRE FIGHTING
2022-07-01 | RUBY SALES CORPORATION(AAPPS1713B) | Pur - T1 | UTCL233/22-23 | 6101.7
CASE NO 62 - FOR TIEROD AND TIE PATTI GAP SEALING IN ONE MERAKI
2022-07-01 | S2P SANITATION SERVICES(ACZFS9029G) | Pur - T1 | S2P/22-23/06/076 | 59304
FOR CLEANING & EVACUATION SERVICE FOR INDIAN STYLE PORABLE TOILET PERIOD 01.06.22 TO 30.06.22 QTY 12 & 8 CASE NO 190722.3
2022-07-10 | SAPAN TRADING COMPANY | Pur - T1 | 1348 | 32050
CASE NO -160722.4 - SAPAN TRADING COMPANY( DEWATERING PUMPS REPAIRING 10 HP(3 NOS)+2 STARTERS
2022-07-15 | MOHAMMAD HANIF SYED | Pur - T1 | 100 | 15000
FOR SHUTTERING DESIGN FOR ONE MERAKI GIRDER BEAMS- BILL NO 100
2022-08-01 | S2P SANITATION SERVICES(ACZFS9029G) | Pur - T1 | S2P/22-23/08/024 | 3360
FOR CLEANING AND EXECUTION SERVICES FOR INDIAN STYLE PORTABLE TOILET, PERIOD - 25.07.2022 TO 31.07.2022, QTY 05, CASE NO:210822.2
2022-08-03 | GLOBETREK ENGINEERING CORPORATION | Pur - T1 | GTEC-2022-23-80 | 30400
CASE NO 111 - LAB MATERIAL
2022-08-18 | VEDANT MARKETING(AANFV8458J) | Pur - T1 | 1213/22-23 | 57600
CASE NO 84 FOR CHEMICAL
2022-10-04 | R.K. DRILLING | Pur - T1 | 061-2022 | 47890
2022-10-07 | ZC R K CONSTRUCTIONS | Pur - T1 | 13 | 141176
2022-10-10 | VEDANT MARKETING | Pur - T1 | 1662/22-23 | 210187.5
2022-10-31 | S2P SANITATION SERVICES | Pur - T1 | S2P/22-23/265 | 13650
2022-11-03 | VEDANT MARKETING | Pur - T1 | 1889/22-23 | 9250
2022-11-11 | K B AJMERA & COMPANY | Pur - T1 | 1945 | 70560
2022-12-01 | K B AJMERA & COMPANY | Pur - T1 | 2225 | 12014.4
2022-12-03 | CONCRETE WORKS CONSTRUCTION CHEMICALS PVT LTD | Pur - T1 | CWC/DOM/0392 | 62560
2022-12-06 | K B AJMERA & COMPANY | Pur - T1 | 2238 | 110948
2022-12-15 | UTKRUSHTRA VASTU WAANIJYA | Pur - T1 | FY22-23/UVW/2056 | 14830.5
2022-12-15 | ZC RAJ ENTERPRISES | Pur - T1 | 28/22-23 | 205800
2023-01-17 | R.K. DRILLING(ABGPU2524A) | Pur - T1 | 092-2023 | 73471.2
2023-01-23 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2681 | 12742.8
2023-01-24 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 104/2022-23 | 10255
2023-01-25 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 105/2022-23 | 3190
2023-01-31 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2748 | 3024
2023-02-14 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 113/2022-23 | 700
2023-02-20 | R.K. DRILLING(ABGPU2524A) | Pur - T1 | 099-2022 | 534468
2023-02-20 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T1 | 2990/22-23 | 6750
2023-02-22 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2995 | 10104.64
2023-02-22 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2994 | 1500
2023-02-22 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2993 | 33315
2023-02-23 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2998 | 155160
2023-03-01 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 3009 | 21210
2023-03-04 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10550 | 2520
2023-03-04 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 3037 | 73022.08
2023-03-06 | CANDORR INTERNATIONAL(AGBPM5987B) | Pur - T1 | CI/11017/22-23 | 42249
2023-03-10 | CANDORR INTERNATIONAL(AGBPM5987B) | Pur - T1 | CI/11026/22-23 | 87924
2023-03-16 | N.K.TRADING CO.(AJEPP2160M) | Pur - T1 | 10576 | 1774
2023-03-25 | CANDORR INTERNATIONAL(AGBPM5987B) | Pur - T1 | CI/11072/22-23 | 10911
2023-04-04 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 26 | 53652.5
2023-04-10 | R.K. DRILLING(ABGPU2524A) | Pur - T1 | RK/01 | 235062.4
2023-04-15 | CANDORR INTERNATIONAL(AGBPM5987B) | Pur - T1 | CI/10055/23-24 | 20706
2023-04-15 | CANDORR INTERNATIONAL(AGBPM5987B) | Pur - T1 | CI/10054/23-24 | 7917
2023-04-24 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 179 | 9611.12
2023-04-24 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 183 | 881.28
2023-04-25 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 204 | 1570
2023-04-25 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 200 | 1549.1
2023-04-25 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 201 | 240.75
2023-04-25 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 199 | 22254.45
2023-04-27 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 229 | 36263.6
2023-04-29 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 261 | 35280
2023-05-08 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 0010/2023-24 | 1575
2023-05-08 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 293 | 3934.2
2023-05-08 | VIBRO INDIA ENTERPRISES(AVPPM9470Q) | Pur - T1 | 009 | 383994
2023-05-08 | VIBRO INDIA ENTERPRISES(AVPPM9470Q) | Pur - T1 | 010 | 62200
2023-05-09 | VIBRO INDIA ENTERPRISES(AVPPM9470Q) | Pur - T1 | 011 | 137000
2023-05-10 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 20/2023-24 | 229764.8
2023-05-10 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 21/2023-24 | 56143.4
2023-05-10 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 22/2023-24 | 23777
2023-05-11 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 23/2023-24 | 29263
2023-05-15 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 24/2023-24 | 3600
2023-05-20 | R.K. DRILLING(ABGPU2524A) | Pur - T1 | RK/17 | 222500
2023-05-25 | R.K. DRILLING(ABGPU2524A) | Pur - T1 | RK/20 | 77858
2023-06-14 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 615 | 16920
2023-06-14 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 614 | 1770
2023-06-14 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 608 | 13659.6
2023-06-14 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 612 | 12103.52
2023-06-14 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 613 | 94663.36
2023-06-14 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 610 | 252309.2
2023-06-14 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 611 | 47099.68
2023-06-14 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 609 | 150165.9
2023-06-16 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 673 | 90381.68
2023-06-16 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 676 | 75507.36
2023-06-16 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 674 | 37083.4
2023-06-16 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 675 | 2571
2023-06-17 | KANERIA PLAST PVT LTD | Pur - T1 | KP/2466/23-24 | 5400
2023-06-17 | REAL INDUSTRIES(ACGPM3884J) | Pur - T1 | 0058/23-24 | 38550
2023-06-20 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 50/2023-24 | 27070
2023-07-12 | R.K. DRILLING(ABGPU2524A) | Pur - T1 | RK/51 | 88319
2023-07-12 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 912 | 2750
2023-07-12 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 911 | 41646.1
2023-07-19 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 989 | 1344
2023-07-19 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 988 | 7671.44
2023-07-21 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1012 | 3291.25
2023-07-30 | KANERIA PLAST PVT LTD | Pur - T1 | KP/3386/23-24 | 133200
2023-07-31 | R.K. DRILLING(ABGPU2524A) | Pur - T1 | RK/60 | 140362
2023-08-01 | SHREE SADGURU ENTERPRISES | Pur - T1 | SSE/2424/2023-24 | 8369.4
2023-08-01 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1037 | 10370
2023-08-01 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1036 | 1368000
2023-08-01 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1038 | 4389
2023-08-01 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1039 | 22796
2023-08-03 | PANKAJ TRADING CO(AADPJ0257D) | Pur - T1 | PT0161723-24 | 18900
2023-08-03 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1091 | 34348.96
2023-08-05 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1152 | 11069.7
2023-08-05 | MILESTONE GROUP INTERIOR SOLUTIONS PVT LTD | Pur - T1 | MG/23-24/042 | 1125560
2023-08-07 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1180 | 13688.64
2023-08-07 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1188 | 4332
2023-08-09 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1203 | 4159
2023-08-10 | PANKAJ TRADING CO(AADPJ0257D) | Debit Note | 70 | -4173.06
2023-08-17 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1256 | 14778
2023-08-17 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1257 | 1592.1
2023-08-17 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1258 | 144408.05
2023-08-19 | PANKAJ TRADING CO(AADPJ0257D) | Pur - T1 | PT0182123-24 | 367801.5
2023-08-21 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1280 | 7338.24
2023-08-21 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1269 | 907.6
2023-08-21 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1306 | 23710.08
2023-08-22 | PANKAJ TRADING CO(AADPJ0257D) | Pur - T1 | PT0184023-24 | 306451.6
2023-08-23 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1312 | 57830.25
2023-08-23 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1320 | 2407.5
2023-08-23 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1321 | 40388.2
2023-08-23 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1319 | 20485.8
2023-08-23 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1318 | 2350
2023-08-23 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1315 | 47450
2023-08-23 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1316 | 29803.4
2023-08-25 | B.M.LODHA & COMPANY | Pur - T1 | 54 | 14000
2023-08-27 | KANERIA PLAST PVT LTD | Pur - T1 | KP/4263/23-24 | 157500
2023-08-28 | PANKAJ TRADING CO(AADPJ0257D) | Pur - T1 | PT0184023-24 | 31846.98
2023-08-31 | PANKAJ TRADING CO(AADPJ0257D) | Pur - T1 | PT0202023-24 | 4904.02
2023-08-31 | MM2MM PRODUCTS(AAHHK5126L) | Pur - T1 | MH/23-24/2029 | 175
2023-09-01 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 72/2023-24 | 340
2023-09-02 | MM2MM PRODUCTS(AAHHK5126L) | Pur - T1 | MH/23-24/2059 | 17850
2023-09-02 | MM2MM PRODUCTS(AAHHK5126L) | Pur - T1 | MH/23-24/2053 | 175
2023-09-02 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1428 | 151359.2
2023-09-03 | KANERIA PLAST PVT LTD | Pur - T1 | KP/4446/23-24 | 180000
2023-09-03 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1469 | 639.36
2023-09-05 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 75/2023-24 | 1000
2023-09-06 | KANERIA PLAST PVT LTD | Pur - T1 | KP/4567/23-24 | 180000
2023-09-08 | KANERIA PLAST PVT LTD | Pur - T1 | KP/4643/23-24 | 146100
2023-09-08 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1465 | 191821.9
2023-09-09 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1489 | 4985.5
2023-09-11 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 76/2023-24 | 56422.83
2023-09-13 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 78/2023-24 | 4598
2023-09-13 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 77/2023-24 | 15900
2023-09-15 | PANKAJ TRADING CO(AADPJ0257D) | Pur - T1 | PT0227623-24 | 84159.04
2023-09-16 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1549 | 3721.5
2023-09-18 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1559 | 15784.8
2023-09-18 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1577 | 101.25
2023-09-18 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1576 | 4510.5
2023-09-20 | PANKAJ TRADING CO(AADPJ0257D) | Pur - T1 | PT0231423-24 | 4127.2
2023-09-22 | KANERIA PLAST PVT LTD | Pur - T1 | KP/5047/23-24 | 135000
2023-09-24 | KANERIA PLAST PVT LTD | Pur - T1 | KP/5165/23-24 | 157500
2023-09-25 | R.K. DRILLING(ABGPU2524A) | Pur - T1 | RK/85 | 176126.6
2023-09-26 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 87/2023-24 | 81318
2023-09-27 | MM2MM PRODUCTS(AAHHK5126L) | Pur - T1 | MH/23-24/2421 | 26860
2023-09-27 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 88/2023-24 | 23748
2023-10-16 | MAHAVIR SANITATION PVT LTD | Pur - T1 | MSPL2324050 | 149093.8
2023-10-16 | MAHAVIR SANITATION PVT LTD | Pur - T1 | MSPL2324051 | 32357.35
2023-11-17 | MAHAVIR SANITATION PVT LTD | Pur - T1 | MSPL2324059 | 727989.32
2023-12-01 | MAHAVIR SANITATION PVT LTD | Debit Note | T1/MSPL/012 | -7657
2023-10-02 | KANERIA PLAST PVT LTD | Pur - T1 | KP/5392/23-24 | 157500
2023-10-04 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 89/2023-24 | 9746
2023-10-04 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1667 | 342000
2023-10-04 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1680 | 89712
2023-10-04 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1682 | 1385
2023-10-04 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1681 | 947789.04
2023-10-06 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1766 | 4204.8
2023-10-06 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1765 | 108253.12
2023-10-08 | KANERIA PLAST PVT LTD | Pur - T1 | KP/5610/23-24 | 162000
2023-10-12 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 100/2023-24 | 2875
2023-10-12 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 98/2023-24 | 29230
2023-10-12 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 99/2023-24 | 35135
2023-10-13 | KANERIA PLAST PVT LTD | Pur - T1 | KP/5824/23-24 | 158400
2023-10-13 | KANERIA PLAST PVT LTD | Pur - T1 | KP/5803/23-24 | 157500
2023-10-14 | R.K. DRILLING(ABGPU2524A) | Pur - T1 | RK/93 | 146278.6
2023-10-14 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 104/2023-24 | 431302
2023-10-14 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1813 | 394384.9
2023-10-14 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1815 | 19475
2023-10-14 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1816 | 10974.5
2023-10-16 | MEHTA BROTHERS & CO | Pur - T1 | 231875 | 1246905
2023-10-17 | MEHTA BROTHERS & CO | Pur - T1 | 231883 | 173500
2023-10-17 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1844 | 567206.56
2023-10-17 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1846 | 307750.7
2023-10-17 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1845 | 52809.6
2023-10-17 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1841 | 472.5
2023-10-17 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1840 | 1120922.41
2023-10-17 | GREEN APPLE PRIVATE LIMITED | Pur - T1 | 0582/23-24 | 17033.33
2023-10-18 | KANERIA PLAST PVT LTD | Pur - T1 | KP/6037/23-24 | 133200
2023-10-18 | KANERIA PLAST PVT LTD | Pur - T1 | KP/6010/23-24 | 160200
2023-10-19 | KANERIA PLAST PVT LTD | Pur - T1 | KP/6059/23-24 | 139500
2023-10-20 | KANERIA PLAST PVT LTD | Pur - T1 | KP/6142/23-24 | 121500
2023-10-20 | KANERIA PLAST PVT LTD | Pur - T1 | KP/6135/23-24 | 157500
2023-10-20 | GREEN APPLE PRIVATE LIMITED | Pur - T1 | 0596/23-24 | 1694.5
2023-10-21 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1872 | 5566.05
2023-10-21 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1873 | 43717.8
2023-10-21 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1888 | 11339.52
2023-10-21 | KANERIA PLAST PVT LTD | Pur - T1 | KP/6205/23-24 | 157500
2023-10-25 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 113/2023-24 | 65024
2023-10-25 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1893 | 63460
2023-10-25 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1894 | 51418
2023-10-27 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1934 | 1434
2023-10-27 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1935 | 15973.44
2023-10-28 | NEMIL SOLUTIONS | Pur - T1 | 247-23/24 | 4600.5
2023-10-30 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1968 | 5596.08
2023-10-30 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1963 | 420
2023-10-30 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1972 | 3844.8
2023-10-30 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1971 | 68170.08
2023-10-30 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 1969 | 35709.6
2023-10-31 | KANERIA PLAST PVT LTD | Pur - T1 | KP/6486/23-24 | 159300
2023-11-01 | KANERIA PLAST PVT LTD | Pur - T1 | KP/6534/23-24 | 135000
2023-11-01 | PANKAJ TRADING CO(AADPJ0257D) | Pur - T1 | PT0289523-24 | 35860.35
2023-11-01 | PANKAJ TRADING CO(AADPJ0257D) | Pur - T1 | PT0289623-24 | 4127.19
2023-11-01 | GREEN APPLE PRIVATE LIMITED | Pur - T1 | 0596/23-24 | 1694.5
2023-11-02 | KANERIA PLAST PVT LTD | Pur - T1 | KP/6533/23-24 | 155700
2023-11-03 | R.K. DRILLING(ABGPU2524A) | Pur - T1 | RK/102 | 291463
2023-11-04 | KANERIA PLAST PVT LTD | Pur - T1 | KP/6613/23-24 | 153900
2023-11-08 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2060 | 35790
2023-11-08 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2059 | 27577
2023-11-08 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2061 | 50666.2
2023-11-08 | KANERIA PLAST PVT LTD | Pur - T1 | KP/6765/23-24 | 139500
2023-11-08 | GREEN APPLE PRIVATE LIMITED | Pur - T1 | 0652/23-24 | 2966.08
2023-11-09 | MEHTA BROTHERS & CO | Pur - T1 | 232109 | 54300
2023-11-10 | KANERIA PLAST PVT LTD | Pur - T1 | KP/6808/23-24 | 155700
2023-11-17 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2109 | 12000
2023-11-17 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2108 | 219174.08
2023-11-17 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2107 | 1296
2023-11-17 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2106 | 71547.84
2023-11-19 | KANERIA PLAST PVT LTD | Pur - T1 | KP/7005/23-24 | 162000
2023-11-20 | KANERIA PLAST PVT LTD | Pur - T1 | KP/7023/23-24 | 139500
2023-11-20 | NEMIL SOLUTIONS | Pur - T1 | 281-23/24 | 18500
2023-11-21 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2117 | 6280
2023-11-23 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 130/2023-24 | 31800
2023-11-23 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2174 | 54684
2023-11-23 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 131 | 2304
2023-11-24 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2196 | 6962
2023-11-25 | PANKAJ TRADING CO(AADPJ0257D) | Pur - T1 | PT0313323-24 | 49040.2
2023-11-25 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2220 | 315841.8
2023-11-28 | NEMIL SOLUTIONS | Pur - T1 | 292-23/24 | 2050
2023-11-28 | KANERIA PLAST PVT LTD | Pur - T1 | KP/7250/23-24 | 203500
2023-11-28 | KANERIA PLAST PVT LTD | Pur - T1 | KP/7280/23-24 | 161100
2023-11-28 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2233 | 67069.5
2023-11-28 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2234 | 12217
2023-11-28 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2236 | 108836.92
2023-11-28 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2235 | 14558
2023-11-28 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2248 | 218761.24
2023-11-28 | CANDORR INTERNATIONAL(AGBPM5987B) | Pur - T1 | CI/10702/23-24 | 10400
2023-11-29 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 132/2023-24 | 4612.8
2023-11-29 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2250 | 1375.92
2023-11-29 | CANDORR INTERNATIONAL(AGBPM5987B) | Pur - T1 | CI/10707/23-24 | 8167
2023-11-30 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 141/2023-24 | 20690
2023-11-30 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2294 | 4748.12
2023-11-30 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2295 | 18479.32
2023-12-01 | R.K. DRILLING(ABGPU2524A) | Pur - T1 | RK/115 | 281588
2023-12-01 | MILESTONE GROUP INTERIOR SOLUTIONS PVT LTD | Debit Note | T1/MGISPL/011 | -11486
2023-12-02 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2327 | 208234.38
2023-12-02 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2328 | 17122.56
2023-12-02 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2330 | 2693.3
2023-12-05 | KANERIA PLAST PVT LTD | Pur - T1 | KP/7497/23-24 | 135000
2023-12-06 | CANDORR INTERNATIONAL(AGBPM5987B) | Pur - T1 | CI/10729/23-24 | 2484
2023-12-06 | NEMIL SOLUTIONS | Pur - T1 | 308-23/24 | 1850
2023-12-07 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2366 | 104500
2023-12-07 | KANERIA PLAST PVT LTD | Pur - T1 | KP/7548/23-24 | 157500
2023-12-08 | PANKAJ TRADING CO(AADPJ0257D) | Pur - T1 | PT0332723-24 | 233416
2023-12-09 | KANERIA PLAST PVT LTD | Pur - T1 | KP/7653/23-24 | 180000
2023-12-09 | KANERIA PLAST PVT LTD | Pur - T1 | KP/7647/23-24 | 126000
2023-12-09 | PANKAJ TRADING CO(AADPJ0257D) | Pur - T1 | M11023123558 | 102685.9
2023-12-09 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 145/2023-24 | 6150
2023-12-11 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2416 | 80046.1
2023-12-12 | MEHTA BROTHERS & CO | Pur - T1 | 232509 | 14435
2023-12-12 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2436 | 2607.28
2023-12-13 | KANERIA PLAST PVT LTD | Pur - T1 | KP/7803/23-24 | 157500
2023-12-13 | CANDORR INTERNATIONAL(AGBPM5987B) | Pur - T1 | CI/10753/23-24 | 37072
2023-12-14 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 146/2023-24 | 53054
2023-12-14 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 147/2023-24 | 919529.25
2023-12-15 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2442 | 447705.8
2023-12-15 | KANERIA PLAST PVT LTD | Pur - T1 | KP/7857/23-24 | 135000
2023-12-16 | KANERIA PLAST PVT LTD | Pur - T1 | KP/7943/23-24 | 121500
2023-12-18 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2481 | 4560
2023-12-18 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2483 | 15190.08
2023-12-18 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2494 | 24023.44
2023-12-19 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2512 | 401146.4
2023-12-21 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 154/2023-24 | 18395
2023-12-21 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 155/2023-24 | 1020
2023-12-22 | K B AJMERA AND CO(AAHFK5132C) | Pur - T1 | 2530 | 287784.7
30639072.44

## 4T1 READY MIX
4T1 READY MIX
Ledger Account
1-May-21 to 31-Aug-22
Date |  | Vch Type | Vch No. | Debit | Credit
2021-05-02 | BADGUJAR AND COMPANY(AXBPB2279E) | Pur - T1 | 1000-747 | 250310.79
BILL NO - 1000-747, SABARI GARDENS
2021-05-07 | BADGUJAR AND COMPANY(AXBPB2279E) | Pur - T1 | 1000-756 | 164212.63
BILL NO - 1000-756, SABARI GARDENS
2021-05-26 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0001/21-22 | 1323225
BILL NO - NE/0001/21-22, DT- 26.05.21 , SABARI GARDENS
2021-07-26 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0005/21-22 | 456146.62
BILL NO - NE/0005/21-22, DT- 26.07.21 , SABARI GARDENS
2022-06-02 | BADGUJAR AND COMPANY(AXBPB2279E) | Pur - T1 | 1000/22-23-185 | 155668
BILL NO - 1000/22-23/185
2022-06-02 | BADGUJAR AND COMPANY(AXBPB2279E) | Pur - T1 | 1000/22-23-186 | 47872
BILL NO - 1000/22-23/186
2022-06-09 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0018/22-23 | 386994.29
BILL NO : NE/0018/22-23
2022-06-15 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0019/22-23 | 181620
BILL NO : NE/0019/22-23
2022-06-20 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0022/22-23 | 392496
BILL NO : NE/0022/22-23
2022-07-09 | BADGUJAR AND COMPANY(AXBPB2279E) | Pur - T1 | 1000-22-23-313 | 37874
BILL NO - 1000/22-23/313
2022-07-16 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0029/22-23 | 372540
BILL NO : NE/00029/22-23
2022-07-20 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0030/22-23 | 339378
BILL NO : NE/0030/22-23
2022-07-22 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0031/22-23 | 651921
BILL NO : NE/0031/22-23, CASE NO :102
2022-07-25 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0032/22-23 | 606445
BILL NO : NE/0032/22-23, CASE NO: 104
2022-07-31 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0038/22-23 | 88782
BILL NO : NE/0038/22-23, ONE MERAKI
2022-08-02 | BADGUJAR AND COMPANY(AXBPB2279E) | Pur - T1 | 1000-22-23-384 | 8189
BILL NO - 1000/22-23-384
2022-08-04 | BADGUJAR AND COMPANY(AXBPB2279E) | Pur - T1 | 1000-22-23-392 | 5750
BILL NO - 1000/22-23-392
2022-08-08 | BADGUJAR AND COMPANY(AXBPB2279E) | Pur - T1 | 1000/22-23-404 | 7974.3
BILL NOT REC AS PER GST DATA BOOK BILL
2022-08-17 | BADGUJAR AND COMPANY(AXBPB2279E) | Pur - T1 | 1000-22-23-432 | 7163
BILL NO - 1000/22-23-392
2022-08-23 | BADGUJAR AND COMPANY(AXBPB2279E) | Pur - T1 | 1000/22-23-456 | 6175
BILL NOT REC AS PER GST DATA BOOK BILL
2022-08-25 |  |  |  | 6175
BILL NO - 1000/22-23-467
2022-08-26 |  |  |  | 54159.48
BILL NO - 1000/22-23-472
2022-08-27 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0049/22-23 | 231189
BILL NO : NE/0049/22-23, ONE MERAK (RMC M20:33CUM,M35:12CUM) MERAKI ARENA G+1 ENTRANCE DRIVEWAY SLAB AND 6.00 MTRS ROAD)
2022-08-31 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0053/22-23 | 33870
BILL NO : NE/0058/22-23, ONE MERAKI ( (PUMPING CHARGES FOR RMC ON 24.07.22 47 CUM B2-POUR-3 B WING SLAB)
2022-09-08 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0055/22-23 | 345834.06
2022-09-28 | BADGUJAR AND COMPANY(AXBPB2279E) | Pur - T1 | 1000/22-23/584 | 10585.85
2023-01-11 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0082/22-23 | 60564
2023-01-22 | MAGICRETE BUILDING SOLUTIONS PVT LTD | Pur - T1 | SI/GJ/23/12548 | 115466.1
2023-01-25 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0086/22-23 | 30282
2023-01-31 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0089/22-23 | 95950
2023-01-31 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0091/22-23 | 90846
2023-01-31 | BADGUJAR AND COMPANY(AXBPB2279E) | Pur - T1 | 1000/22-23-913 | 36300
2023-01-31 | BADGUJAR AND COMPANY(AXBPB2279E) | Pur - T1 | 1000/22-23/914 | 363868
2023-03-22 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT23802223 | 105932
2023-03-23 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0101/22-23 | 91464
2023-03-28 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0102/22-23 | 798373.72
2023-03-29 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT24372223 | 101695
2023-04-18 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0004/23-24 | 812853.36
2023-04-22 | BNC EQUIPMENT INDIA PVT.LTD | Pur - T1 | 1000/23-24-54 | 95899.65
2023-04-22 | BNC EQUIPMENT INDIA PVT.LTD | Pur - T1 | 1000/23-24-53 | 57270
2023-04-22 | BNC EQUIPMENT INDIA PVT.LTD | Pur - T1 | 1000/23-24-52 | 70018.77
2023-04-27 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT02272324 | 105932
2023-05-01 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT/02542324 | 105932
2023-05-01 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Debit Note | DN-MHLLP-001-07.04.23 | -25000
2023-05-04 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TC00212324 | 195359.8
2023-05-13 | BNC EQUIPMENT INDIA PVT.LTD | Pur - T1 | 1000/23-24-119 | 11178.6
2023-06-12 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0026/23-24 | 40000
2023-06-17 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0027/23-24 | 38316
2023-06-21 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT05872324 | 127500
2023-06-24 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT06002324 | 127500
2023-07-03 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT06512324 | 127500
2023-07-09 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT06822324 | 106250
2023-07-14 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT07142324 | 106250
2023-07-16 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT07292324 | 127500
2023-07-19 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT07512324 | 127500
2023-07-23 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT07792324 | 127500
2023-08-05 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT08522324 | 106250
2023-08-07 | KANERIA PLAST PVT LTD | Pur - T1 | KP/3603/23-24 | 123750
2023-08-09 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT08802324 | 106250
2023-08-14 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Debit Note | RE00066/23 | -106250
2023-08-25 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - T1 | TT09942324 | 127500
2023-10-04 | PADMAVATI MARKETING(ADPPJ4722Q) | Pur - T1 | PM/450/23-24 | 153000
2023-10-30 | PADMAVATI MARKETING(ADPPJ4722Q) | Pur - T1 | PM/533/23-24 | 129500
2023-11-18 | PADMAVATI MARKETING(ADPPJ4722Q) | Pur - T1 | PM/576/23-24 | 152625
2023-11-18 | PADMAVATI MARKETING(ADPPJ4722Q) | Debit Note | 18 | -129500
2023-11-26 | PADMAVATI MARKETING(ADPPJ4722Q) | Pur - T1 | PM/602/23-24 | 115500
2023-12-17 | PADMAVATI MARKETING(ADPPJ4722Q) | Pur - T1 | PM/716/23-24 | 127875
2024-01-03 | PADMAVATI MARKETING | Pur - T1 | PM/799/23-24 | 125400
2024-01-11 | PADMAVATI MARKETING | Pur - T1 | PM/830/23-24 | 52500
2024-01-21 | PADMAVATI MARKETING | Pur - T1 | PM/849/23-24 | 115500
2024-03-01 | PADMAVATI MARKETING | Pur - T1 | PM/941/23-24 | 132000
11880451.02

## 4T1 REPAIRS & SERVICES
4T1 REPAIRS & SERVICES
Ledger Account
1-Apr-21 to 31-Aug-22
Date |  | Vch Type | Vch No. | Debit | Credit
2021-04-14 | MAURYA ELECTRICAL WORKS | Pur - T1 | 3272 | 16050
2021-05-07 | MAURYA ELECTRICAL WORKS | Pur - T1 | 02 | 14200
2021-05-19 | MAURYA ELECTRICAL WORKS | Pur - T1 | 3297 | 11400
2021-12-13 | MAURYA ELECTRICAL WORKS | Pur - T1 | 3307 | 13800
2022-04-21 | MAURYA ELECTRICAL WORKS | Pur - T1 | 3361 | 1600
2022-08-01 | MAURYA ELECTRICAL WORKS | Pur - T1 | 3367 | 17980
2022-11-04 | MAURYA ELECTRICAL WORKS | Pur - T1 | 3396 | 2850
2022-11-04 | MAURYA ELECTRICAL WORKS | Pur - T1 | 3394 | 27660
2022-11-04 | MAURYA ELECTRICAL WORKS | Pur - T1 | 3393 | 28300
| Repairs & Services |  |  | 53650
2023-03-17 | MAURYA ELECTRICAL WORKS | Pur - T1 | 3445 | 12500
2023-03-17 | MAURYA ELECTRICAL WORKS | Pur - T1 | 3447 | 12500
2023-04-08 | MAURYA ELECTRICAL WORKS | Pur - T1 | 3458 | 17080
2023-08-05 | MAURYA ELECTRICAL WORKS | Pur - T1 | 3484 | 27200
2023-08-12 | MAURYA ELECTRICAL WORKS | Pur - T1 | 3491 | 12500
2023-08-12 | MAURYA ELECTRICAL WORKS | Pur - T1 | 3490 | 16300
2023-08-12 | MAURYA ELECTRICAL WORKS | Pur - T1 | 3492 | 12500
2023-09-04 | MAURYA ELECTRICAL WORKS | Pur - T1 | 3508 | 13800
2023-11-18 | MAURYA ELECTRICAL WORKS | Pur - T1 | 3540 | 7600
2023-10-13 | G.R. ENTERPRISE | Pur - T1 | 159 | 46900
2023-10-13 | G.R. ENTERPRISE | Pur - T1 | 164 | 46900
2024-02-29 | AQUARIUS ENGINEERS PVT LTD | Pur - T1 | 2301S0670 | 5000
418270

## 4T1 SAND
4T1 SAND
Ledger Account
1-Apr-22 to 31-Aug-22
Date |  | Vch Type | Vch No. | Debit | Credit
2022-04-12 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0002/22-23 | 301508.6
BILL NO - NE/0002/21-22, ONE MERAKI
2022-04-18 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0003/22-23 | 871219.94
BILL NO - NE/0003/21-22, ONE MERAKI
2022-04-30 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0004/22-23 | 343833.76
BILL NO - NE/0004/22-23, ONE MERAKI
2022-05-06 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0005/22-23 | 703295.7
BILL NO - NE/0005/22-23, ONE MERAKI
2022-05-12 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0006/22-23 | 724058.28
BILL NO - NE/0006/22-23, ONE MERAKI
2022-05-27 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0007/22-23 | 618128.15
CASE NO 36, BILL NO: NE/0007/22-23, ONE MERAKI
2022-05-31 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0008/22-23 | 675477.65
CASE NO 36, BILL NO: NE/0009/22-23, ONE MERAKI
2022-06-09 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0010/22-23 | 641678.55
BILL NO: NE/0010/22-23, ONE MERAKI
2022-06-09 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0011/22-23 | 366676.8
BILL NO: NE/011/22-23, ONE MERAKI
2022-06-16 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0021/22-23 | 551617.7
BILL NO : NE/0021/22-23
2022-06-20 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0023/22-23 | 953752.68
BILL NO : NE/0023/22-23
2022-06-24 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0024/22-23 | 399961.42
BILL NO : NE/0024/22-23
2022-06-29 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0026/22-23 | 1208798.01
BILL NO : NE/0026/22-23 ( W.SAND:845.56T,M1:101.54T,M2:100.34T,W.SAND:197.73T,W.SAND:71.36T) ONE MERAKI)
2022-06-30 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0027/22-23 | 108211.4
BILL NO : NE/0027/22-23
2022-07-16 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0028/22-23 | 523382
BILL NO: NE/0028/22-23
2022-07-25 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0034/22-23 | 160522.84
BILL NO : NE/0034/22-23
2022-07-29 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0036/22-23 | 565782.47
BILL NO : NE/0036/22-23, ONE MERAKI
2022-08-02 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0039/22-23 | 380127.9
BILL NO : NE/0039/22-23, ONE MERAKI
2022-08-16 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0047/22-23 | 506004.61
BILL NO : NE/0047/22-23, ONE MERAKI
2022-08-16 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0048/22-23 | 465333.33
BILL NO : NE/0048/22-23, ONE MERAKI
2022-09-08 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0054/22-23 | 364693.34
2022-09-08 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0057/22-23 | 623165.52
2022-09-20 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0061/22-23 | 309796.04
2022-10-05 | NEEV ENTERPRISE | Pur - T1 | NE/0064/22-23 | 292661.69
2022-10-21 | NEEV ENTERPRISE | Pur - T1 | NE/0067/22-23 | 71888.38
2022-11-09 | NEEV ENTERPRISE | Pur - T1 | NE/0073/22-23 | 486665.62
2022-11-09 | NEEV ENTERPRISE | Pur - T1 | NE/0072/22-23 | 534606.68
2022-11-21 | NEEV ENTERPRISE | Pur - T1 | NE/0075/22-23 | 472713.02
2022-11-21 | NEEV ENTERPRISE | Pur - T1 | NE/0074/22-23 | 686411.92
2022-11-24 | NEEV ENTERPRISE | Pur - T1 | NE/0076/22-23 | 147187
2022-12-10 | NEEV ENTERPRISE | Pur - T1 | NE/0075/22-23 | 301455.3
2022-12-20 | NEEV ENTERPRISE | Pur - T1 | NE/0076/22-23 | 708956.44
2022-12-27 | NEEV ENTERPRISE | Pur - T1 | NE/0078/22-23 | 240897.35
2022-12-31 | NEEV ENTERPRISE | Pur - T1 | NE/0081/22-23 | 295302.05
2023-01-11 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0083/22-23 | 242844.08
2023-01-13 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0084/22-23 | 474461.88
2023-01-21 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0085/22-23 | 649885.04
2023-01-25 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0088/22-23 | 150017.74
2023-01-31 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0090/22-23 | 852209.06
2023-02-07 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0092/22-23 | 383729.15
2023-02-14 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0093/22-23 | 1147542.62
2023-02-21 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0096/22-23 | 1108349.62
2023-02-28 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0097/22-23 | 633531.1
2023-03-08 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0098/22-23 | 166210.8
2023-03-10 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0099/22-23 | 1140801.44
2023-03-20 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0100/22-23 | 807808.7
2023-03-31 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0105/22-23 | 1411020.83
2023-05-20 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0016/23-24 | 2026778.09
2024-02-29 | NEEV ENTERPRISE | Pur - T1 | NE/0090/23-24 | 74200
27875162.29

## 4T1 STEEL
4T1 STEEL
Ledger Account
1-May-21 to 31-Aug-22
Date |  | Vch Type | Vch No. | Debit | Credit
2021-05-28 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K38053 | 1588500
BILL NO -K38053 - SABARI GARDENS
2021-05-31 | THANE STEELS LIMITED(AABCT1119R) | Pur - T1 | TSL00618/2021-22 | 965442
BILL NO - TSL00618/2021-22
2021-08-02 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K39438 | 335554
BILL NO -K39438 - SABARI GARDENS
2021-12-20 | REAL INDUSTRIES(ACGPM3884J) | Pur - T1 | 0192/21-22 | 27220
BILL NO -0192/21-22 - SABARI GARDENS
2022-03-23 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B2909 | 2310340
BILL NO - B2B2909 - T1
2022-03-25 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B2920 | 2855620
BILL NO - B2B2920 - T1
2022-03-31 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B2991 | 2768920
BILL NO - B2B2991 - T1
2022-03-31 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B2989 | 2791426
BILL NO - B2B2989 - T1
2022-04-01 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K009 | 2125
BILL NO - K009
2022-04-06 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K089 | 296725
BILL NO - K089
2022-04-15 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B130 | 1649095
BILL NO - B2B130- T1
2022-04-15 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B136 | 1649095
BILL NO - B2B136- T1
2022-04-15 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B134 | 1650365
BILL NO - B2B134- T1
2022-04-20 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B187 | 2205064
BILL NO - B2B187- T1
2022-04-20 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B184 | 2670592
BILL NO - B2B184- T1 CASE NO 39
2022-04-27 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | 161 | 1445585
BILL NO -161
2022-05-02 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B304 | 1743718
BILL NO - B2B304
2022-05-04 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B321 | 1804530
BILL NO - B2B321
2022-05-07 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B355 | 1703950
BILL NO - B2B355
2022-05-19 | REAL INDUSTRIES(ACGPM3884J) | Pur - T1 | 0042/22-23 | 363785
SUB DEWATIRNG PUMP QTY 3NOS , STARTER QTY 3NOS , HOSE PIPE QTY 180 MTR , HOSE CLAMP QTY 25NOS , HOSE COPLER QTY 20NOS - CASE NO 29
2022-05-20 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B488 | 600000
CASE NO 51 - M S TMT 721420 QTY 10,000KG ( PAID BILL TO BILL )
2022-05-20 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B487 | 1231956
CASE NO 51 - M S TMT 721420 QTY 17,120 KG & M S TMT 721420 QTY 3,010KG ( PAID BILL TO BILL )
2022-05-20 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B489 | 1825694
CASE NO 51 - M S TMT 721420 QTY 9,890 KG , M S TMT 721420 QTY 19,780 KG ( PAID BILL TO BILL )
2022-05-31 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B58884 | 2246886
CASE NO 66 - M S TMT 721420 QTY 20000 KG , M S TMT 721420 QTY 19,980 KG ( PAID BILL TO BILL )
2022-06-07 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K1463 | 795495
CASE NO 80 - MS BAR
2022-06-18 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K1759 | 1405326
CASE NO 86
2022-06-22 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K1822 | 73850
G.I. WIRE 18G -7217010-KGS QTY 1,000KG
2022-06-28 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K1925 | 2327535
CASE NO - 390 MS BAR TMT HSN KG
2022-07-03 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K2044 | 1928934
BILL NO : K2044
2022-07-05 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B1007 | 567191
CASE NO 63 FOR GRD FLR A WING
2022-07-05 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B1006 | 882543
CASE NO 63 GROUND FLOOR A WING
2022-07-08 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B1046 | 1838275
CASE NO 64 - M S TMT BAR
2022-07-11 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B1064 | 75248
CASE NO 64 - M S WIRES QTY 1,040KG
2022-07-14 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B1109 | 1808064
CASE NO 67
2022-07-22 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B1207 | 1953280
CASE NO 74, M S TMT BAR 72142090
2022-07-22 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | DN/27 | 17440
DEBIT NOTE NO 27, DISCOUNT ALLOWED IGST
2022-07-23 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B1211 | 1414560
CASE NO 74, M S TMT BARS 72142090
2022-07-27 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B1265 | 392500
CASE NO 74.1, M S WIRES 72171020
2022-08-01 |  |  |  | 1752135
CASE NO 105
2022-08-06 |  |  |  | 1767397
CASE NO 105/112
2022-08-13 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B1429 | 2278198
CASE NO 119
2022-08-13 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K2847 | 1872545
CASE NO 119
2022-08-13 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T1 | 42/2022-23 | 14770.05
BILL NOT REC AS PER GST DATA BOOK BILL
2022-08-26 | OM STEEL | Pur - T1 | 1101/22-23 | 886236
CASE NO 85 STEEL TMT BARS FOR B & C WING
2022-08-26 | OM STEEL | Pur - T1 | 1103/22-23 | 1063842
CASE NO 85 STEEL TMT BARS FOR B & C WING
2022-08-27 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K3115 | 1755223
BILL NO K3115
2022-09-01 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K1679 | 1399177
2022-09-07 | OM STEEL | Pur - T1 | 1220/22-23 | 1715112
2022-09-17 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K3543 | 1115347.8
2022-09-17 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K3544 | 1142532.1
2022-09-20 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K3592 | 635438.5
2022-09-20 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K3593 | 629739.5
2022-10-04 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED | Pur - T1 | K3879 | 1692122.5
2022-10-13 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED | Pur - T1 | K4076 | 1639268
2022-10-17 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED | Pur - T1 | K4077 | 39530
2022-10-18 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED | Pur - T1 | K4183 | 1832350
2022-10-28 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED | Pur - T1 | K4431 | 1738852.5
2022-11-01 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED | Pur - T1 | K4539 | 1804986.5
2022-11-06 | SHRI GOPESHWAR STEELS | Pur - T1 | B2B2110 | 1790320
2022-11-07 | THALIA STEELS | Pur - T1 | K215 | 1685990
2022-11-08 | SHRI GOPESHWAR STEELS | Pur - T1 | B2B2128 | 373245
2022-11-11 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED | Pur - T1 | K4763 | 1193448
2022-11-14 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED | Pur - T1 | K4827 | 1166569.1
2022-11-16 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED | Pur - T1 | K4887 | 1236122.3
2022-11-28 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED | Pur - T1 | K5135 | 1745587.5
2022-12-05 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED | Pur - T1 | K5301 | 1186012
2022-12-08 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED | Pur - T1 | K5368 | 1213682
2022-12-09 | SHRI GOPESHWAR STEELS | Pur - T1 | B2B2458 | 1850270
2022-12-15 | SHRI GOPESHWAR STEELS | Pur - T1 | B2B2451 | 1502105
2022-12-22 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED | Pur - T1 | K5716 | 1212575
2022-12-24 | MM METATRADE PRIVATE LIMITED | Pur - T1 | 25/22-23 | 59717.75
2022-12-28 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED | Pur - T1 | K5852 | 1214797
2022-12-29 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED | Pur - T1 | K5888 | 1147146
2023-01-05 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K6042 | 1726570
2023-01-09 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K6119 | 375377.5
2023-01-10 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B2753 | 1792294
2023-01-10 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B2749 | 1752178
2023-01-11 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K6186 | 1234450
2023-01-15 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B2795 | 1980919
2023-01-16 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K6320 | 1234722
2023-01-18 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B2831 | 1590183
2023-01-21 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B2867 | 2432749
2023-01-21 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B2865 | 390200
2023-01-22 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B2869 | 1933180
2023-01-23 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B2871 | 2356412
2023-01-31 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B2973 | 1747390
2023-01-31 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B2974 | 587000
2023-01-31 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B2965 | 1949861
2023-02-04 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3020 | 390942
2023-02-07 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3019 | 100964
2023-02-07 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3018 | 1974416
2023-02-08 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3050 | 2466704
2023-02-11 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3097 | 1269268
2023-02-11 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3098 | 1042220
2023-02-13 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3107 | 1454506
2023-02-13 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3106 | 832832
2023-02-18 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3155 | 1737736
2023-02-20 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3176 | 1505334
2023-02-24 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3206 | 1775818
2023-02-26 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3229 | 1797355
2023-03-02 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3272 | 1789076
2023-03-05 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3304 | 1755894
2023-03-06 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3313 | 2364798
2023-03-08 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K7663 | 355000
2023-03-10 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3355 | 1198920
2023-03-10 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3354 | 727568
2023-03-16 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3422 | 1693038
2023-03-17 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3426 | 197880
2023-03-18 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K7971 | 1478125
2023-03-18 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3438 | 2264925
2023-03-19 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3454 | 1744956
2023-03-19 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3455 | 574425
2023-03-24 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3513 | 1759432
2023-03-24 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3514 | 572125
2023-03-25 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3520 | 2314150
2023-03-27 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3537 | 1183014
2023-03-27 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B3536 | 1109050
2023-04-01 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B4 | 2369520
2023-04-02 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B13 | 2320117
2023-04-04 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B36 | 403214
2023-04-04 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B35 | 1158616
2023-04-04 | SRSBM LAB TESTING PVT LTD(ABACS8249K) | Pur - T1 | MRT-17482 | 15000
2023-04-05 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B51 | 2306997
2023-04-07 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B71 | 2332280
2023-04-11 | SRSBM LAB TESTING PVT LTD(ABACS8249K) | Pur - T1 | MRT-17492 | 3000
2023-04-12 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B117 | 772272
2023-04-12 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B118 | 1134735
2023-04-20 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T1 | B2B214 | 375000
2023-04-26 | MAGICRETE BUILDING SOLUTIONS PVT LTD | Debit Note | CN/ST/24/00430 | -192081.51
2023-05-16 | RUBY STEEL | Pur - T1 | GST-29/23-24 | 116650
2023-06-06 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K10024 | 183510
2023-07-01 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Debit Note | K10518 | -564830
2023-07-01 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K10518 | 564830
2023-07-26 | JATIN STEEL DEPOT | Pur - T1 | 12406 | 329800
2023-09-18 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T1 | K12319 | 161037.5
2024-02-15 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED | Pur - T1 | K16190 | 367363.55
174235804.14

## 4T1 CABLES
4T1 CABLES
Ledger Account
1-Jan-23 to 15-Mar-23
Date |  | Vch Type | Vch No. | Debit
2023-01-23 | PRINCE CABLES(AAIPS4863R) | Pur - T1 | 8083/22-23 | 231904.89
2023-01-27 | PRINCE CABLES(AAIPS4863R) | Pur - T1 | 8225/22-23 | 223437.5
2023-02-16 | PRINCE CABLES(AAIPS4863R) | Pur - T1 | 8936/22-23 | 421867.41
2023-03-06 | HANS WIRES AND CABLES | Pur - T1 | 22-23/1904 | 12696.55
2023-04-04 | HANS WIRES AND CABLES | Pur - T1 | 23-24/20025 | 39037.44
2023-04-05 | HANS WIRES AND CABLES | Pur - T1 | PI/23-24/0002 | 18624
2023-04-22 | PRINCE CABLES(AAIPS4863R) | Pur - T1 | INV/693/23-24 | 3403.76
2023-05-22 | PRINCE CABLES(AAIPS4863R) | Pur - T1 | INV/1471/23-24 | 443584
2023-06-08 | SP ELECTROSOLUTIONS PVT LTD | Pur - T1 | 23-24/02614 | 53532.35
2023-06-08 | HANS WIRES AND CABLES | Pur - T1 | 23-24/0742 | 48056.34
2023-06-09 | HANS WIRES AND CABLES | Pur - T1 | 23-24/0750 | 34794.11
2023-06-09 | SP ELECTROSOLUTIONS PVT LTD | Pur - T1 | 23-24/02685 | 9779.3
2023-07-07 | PRINCE CABLES(ABBFP7158E) | Pur - T1 | INV/2860/23-24 | 221473.3
2023-07-10 | PRINCE CABLES(ABBFP7158E) | Debit Note | 3 | -83241.95
2023-08-11 | PRINCE CABLES(ABBFP7158E) | Pur - T1 | INV/23-24 | 51493.64
2023-08-16 | PRINCE CABLES(ABBFP7158E) | Pur - T1 | INV/23-24 | 151221.59
2023-08-17 | PRINCE CABLES(ABBFP7158E) | Pur - T1 | INV/3997/23-24 | 50590.69
2023-08-17 | PRINCE CABLES(ABBFP7158E) | Pur - T1 | INV/3998/23-24 | 152021.59
2023-09-14 | PRINCE CABLES(ABBFP7158E) | Pur - T1 | INV/4900/23-24 | 3158832.3
2023-09-26 | PRINCE CABLES(ABBFP7158E) | Pur - T1 | INV/5271/23-24 | 242487.5
2023-11-08 | PRINCE CABLES LLP | Pur - T1 | INV/6666/23-24 | 193054.7
2023-11-10 | PRINCE CABLES LLP | Pur - T1 | INV/6734/23-24 | 193054.7
2023-11-25 | PRINCE CABLES LLP | Pur - T1 | INV/7080/23-24 | 219717.74
2024-01-06 | PRINCE CABLES LLP(ABBFP7158E-P) | Pur - T1 | INV/8392/23-24 | 49919.81
2024-01-19 | PRINCE CABLES LLP(ABBFP7158E-P) | Pur - T1 | INV/8819/23-24 | 443599.2
2024-01-24 | PRINCE CABLES LLP(ABBFP7158E-P) | Pur - T1 | INV/8955/23-24 | 362930.44
6947872.9

## 4T1 CARPENTER
4T1 CARPENTER
Ledger Account
1-Jan-23 to 15-Mar-23
Date |  | Vch Type | Vch No. | Debit
2023-01-06 | H. TAYEBALLY RANGWALA & CO | Pur - T1 | 4557 | 8088
2023-05-02 | J K ENTERPRISES | Pur - T1 | 74/2023-24 | 2280
2023-08-22 | ZC DHARMENDRA VISHWAKARMA - T1 | Pur - T1 | 011 | 24200
2023-08-22 | ZC DHARMENDRA VISHWAKARMA - T1 | Pur - T1 | 012 | 15650
2023-08-25 | COLLINS INDIA | Pur - T1 | CSL0720230825 | 8435
2023-08-26 | J K ENTERPRISES | Pur - T1 | 313/2023-24 | 143312.4
2023-09-05 | ZC SANSKRITI INTERIOR(BEAPJ0659F) | Pur - T1 | 011 | 50000
2023-09-14 | J K ENTERPRISES | Pur - T1 | 345/2023-24 | 204958.26
2023-09-28 | J K ENTERPRISES | Pur - T1 | 374/2023-24 | 6900
2023-10-02 | COLLINS INDIA | Pur - T1 | CSL0120231002 | 136
2023-10-04 | J K ENTERPRISES | Pur - T1 | 385/2023-24 | 2360
2023-10-05 | J K ENTERPRISES | Pur - T1 | 387/2023-24 | 132334.54
2023-10-05 | J K ENTERPRISES | Pur - T1 | 388/2023-24 | 151990.53
2023-10-07 | J K ENTERPRISES | Pur - T1 | 394/2023-24 | 138994.84
2023-10-07 | J K ENTERPRISES | Debit Note | CREDIT NOTE 9 | -132334.54
2023-10-16 | J K ENTERPRISES | Pur - T1 | 413/2023-24 | 77497.42
2023-10-19 | J K ENTERPRISES | Pur - T1 | 413/2023-24 | 18415.73
2023-10-20 | J K ENTERPRISES | Pur - T1 | 423/2023-24 | 36997.73
2023-11-03 | ZC SANSKRITI INTERIOR(BEAPJ0659F) | Pur - T1 | 016 | 136000
2023-11-05 | J K ENTERPRISES | Pur - T1 | 471/2023-24 | 55400.02
2023-11-24 | J K ENTERPRISES | Pur - T1 | 497/2023-24 | 189454.08
2023-11-29 | J K ENTERPRISES | Pur - T1 | 512/2023-24 | 44665.24
2023-11-29 | J K ENTERPRISES | Pur - T1 | 513/2023-24 | 4300
2023-12-03 | J K ENTERPRISES | Pur - T1 | 526/2023-24 | 122575
2023-12-03 | JYOTI HARDWARE STORES(AAAFJ1248F) | Pur - T1 | 4077 | 7460
2023-12-03 | JYOTI HARDWARE STORES(AAAFJ1248F) | Pur - T1 | 4080 | 11735
2023-12-06 | J K ENTERPRISES | Pur - T1 | 537/2023-24 | 132732.7
2023-12-07 | J K ENTERPRISES | Pur - T1 | 539/2023-24 | 13700
2023-12-12 | J K ENTERPRISES | Pur - T1 | 550/2023-24 | 15550
2023-12-19 | COLLINS INDIA | Pur - T1 | CSL0520231219 | 536328
2023-12-22 | J K ENTERPRISES | Debit Note | 14 | -58724
2023-12-29 | COLLINS INDIA | Pur - T1 | CSL0520231229 | 649496
2024-01-19 | J K ENTERPRISES | Pur - T1 | 647/2023-24 | 3993.33
2024-01-20 | JYOTI HARDWARE STORES(AAAFJ1248F) | Pur - T1 | 4155 | 1800
2024-01-22 | COLLINS INDIA | Pur - T1 | CSL0120240122 | 36002
2024-02-08 | ZC SANSKRITI INTERIOR(BEAPJ0659F) | Pur - T1 | 036 | 10900
2024-02-14 | J K ENTERPRISES | Pur - T1 | 706/2023-24 | 93961.79
2024-03-12 | ZC TEXTURE CONCEPTS PVT LTD(AAECT8646E) | Debit Note | T1/JSA/15 | -4700
2024-03-18 | J K ENTERPRISES | Pur - T1 | 812/2023-24 | 63857.88
2024-03-22 | J K ENTERPRISES | Pur - T1 | 830/2023-24 | 21686.72
2978389.67

## 4T1 GLASS FIXING MATERIAL WIND
4T1 GLASS FIXING MATERIAL WINDOW
Ledger Account
1-Jan-23 to 15-Mar-23
Date |  | Vch Type | Vch No. | Debit
2023-02-02 | AVIGHANNA ENTERPRISES | Pur - T1 | AVE/INV/271/2022 | 1257000
2023-02-14 | FINETEC GLAZING SYSTEMS LLP | Pur - T1 | 201/22-23 | 191210
2023-02-21 | AVIGHANNA ENTERPRISES | Pur - T1 | AVE/INV/287/2022 | 945000
2023-02-24 | DEEP MILLENNIUM FACADE PRIVATE LIMITED | Pur - T1 | 34/2022-23 | 106469
2023-02-27 | QUALDOW LLP(AAAFQ9648Q) | Pur - T1 | 006/2022-23 | 195737.85
1100000
2023-08-10 | QUALDOW LLP(AAAFQ9648Q) | Pur - T1 | 004/2023-24 | 132264
2023-08-10 | QUALDOW LLP(AAAFQ9648Q) | Pur - T1 | 005/2023-24 | 546750
2023-08-24 | QUALDOW LLP(AAAFQ9648Q) | Pur - T1 | 006/2023-24 | 201330.36
2023-09-29 | QUALDOW LLP(AAAFQ9648Q) | Pur - T1 | 011/2023-24 | 10007780.6
2023-11-01 | QUALDOW LLP(AAAFQ9648Q) | Pur - T1 | 014/2023-24 | 4753272.84
2023-11-22 | QUALDOW LLP(AAAFQ9648Q) | Pur - T1 | 015/2023-24 | 26132202.67
2023-12-15 | QUALDOW LLP(AAAFQ9648Q) | Pur - T1 | 016/2023-24 | 56198285.3
2024-01-01 | QUALDOW LLP - T1(AAAFQ9648Q) | Pur - T1 | 0017/2023-24 | 1657849.12
2024-01-09 | QUALDOW LLP - T1(AAAFQ9648Q) | Pur - T1 | 019/2023-24 | 5619828.53
2024-01-20 | RENOVATION UNITED LLP - T1 | Pur - T1 | 004/2023-24 | 7884618
2024-01-20 | RENOVATION UNITED LLP - T1 | Pur - T1 | 005/2023-24 | 18401995.86
2024-03-01 | GLOBAL BMU - FACADE ACCESS SYSTEM'S | Pur - T1 | GB/23-24/05 | 318750
2024-03-06 | QUALDOW LLP - T1(AAAFQ9648Q) | Pur - T1 | 024/2023-24 | 175000
2024-03-06 | QUALDOW LLP - T1(AAAFQ9648Q) | Pur - T1 | 021/2023-24 | 1404957.13
2024-03-06 | QUALDOW LLP - T1(AAAFQ9648Q) | Pur - T1 | 022/2023-24 | 850368
2024-03-06 | QUALDOW LLP - T1(AAAFQ9648Q) | Pur - T1 | 023/2023-24 | 502574.08
2024-03-12 | QUALDOW LLP - T1(AAAFQ9648Q) | Debit Note | T1/JSA/13 | -15000
2024-03-15 | GLOBAL BMU - FACADE ACCESS SYSTEM'S | Pur - T1 | GB/23-24/13 | 164730
2024-03-30 | GLOBAL BMU - FACADE ACCESS SYSTEM'S | Pur - T1 | GB/23-24/19 | 635800
2024-03-30 | QUALDOW LLP - T1(AAAFQ9648Q) | Pur - T1 | 025/23-24 | 502574
139871347.34

## 4T1 SAFETY NET EXP
4T1 SAFETY NET EXP
Ledger Account
1-Jan-23 to 15-Mar-23
Date |  | Vch Type | Vch No. | Debit
2023-01-12 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/336 | 23675
2023-01-13 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/337 | 89390
2023-01-23 | LOTUS INDIA ENTERPRISES | Pur - T1 | LIE/22-23/377 | 100500
2023-01-28 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/350 | 192020
2023-02-02 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/358 | 23675
2023-02-03 | G.R. ENTERPRISE | Pur - T1 | 115/2022-23 | 4700
2023-02-18 | G.R. ENTERPRISE | Pur - T1 | 123/2022-23 | 40200
2023-03-17 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/396 | 142725
2023-03-18 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/397 | 7880
2023-05-10 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/043 | 34200
2023-06-14 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/068 | 42260
2023-06-15 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/071 | 7900
2023-06-20 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/073 | 72200
2023-08-02 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/104 | 76950
2023-08-09 | G.R. ENTERPRISE | Pur - T1 | 089/2023-24 | 6450
2023-08-12 | G.R. ENTERPRISE | Pur - T1 | 098/2023-24 | 4700
2023-08-24 | G.R. ENTERPRISE | Pur - T1 | 105/2023-24 | 3520
2023-08-24 | G.R. ENTERPRISE | Pur - T1 | 106/2023-24 | 84450
2024-01-03 | TUSHAR STEEL | Pur - T1 | TS/262 | 17400
2024-01-05 | TUSHAR STEEL | Pur - T1 | TS/266 | 222500
2024-02-15 | G.R. ENTERPRISE | Pur - T1 | 298/2023-24 | 6850
2024-02-15 | JAYANTI ENTERPRISE | Pur - T1 | 155 | 48500
2024-02-16 | G.R. ENTERPRISE | Pur - T1 | 301/2023-24 | 50300
2024-03-19 | RIGHT MEDIA | Pur - T1 | RM29-03-24 | 16330
1319275

## 4T1 MARBLE
4T1 MARBLE
Ledger Account
16-Mar-23 to 31-Mar-23
Date |  | Vch Type | Vch No. | Debit
2023-03-25 | CHIMAN GRANITE MARBLE | Pur - T1 | 228 | 330000
2023-04-20 | VAISHNOVI GRANITE AND MARBLE (AIVPB0551A) | Pur - T1 | 6 | 83500
2023-07-11 | GEETA GRANITES & MARBLES(AGLPB1646E) | Pur - T1 | 57 | 45400
2023-08-06 | ITALIANO STONE AND STEEL(AABFI7810H) | Pur - T1 | 3 | 57600
2023-09-12 | MOUNT GRANITE | Pur - T1 | 00270/23-24 | 93285
2023-09-14 | VAISHNOVI GRANITE AND MARBLE (AIVPB0551A) | Pur - T1 | 41 | 53375
2023-09-21 | MOUNT GRANITE | Pur - T1 | 00281/2023-24 | 15070
2023-09-27 | MOUNT GRANITE | Pur - T1 | 00291/2023-24 | 150885.6
2023-09-28 | GEETA GRANITES & MARBLES(AGLPB1646E) | Pur - T1 | 98 | 16740.25
2023-09-30 | GEETA GRANITES & MARBLES(AGLPB1646E) | Pur - T1 | 100 | 92505.5
2023-10-04 | VAISHNOVI GRANITE AND MARBLE (AIVPB0551A) | Pur - T1 | 44 | 565293.75
2023-11-01 | VAISHNOVI GRANITE AND MARBLE (AIVPB0551A) | Pur - T1 | 66 | 99348
2023-11-05 | VAISHNOVI GRANITE AND MARBLE (AIVPB0551A) | Pur - T1 | 71 | 16722.3
2023-11-14 | VAISHNOVI GRANITE AND MARBLE (AIVPB0551A) | Pur - T1 | 75 | 99977.7
2023-11-16 | VAISHNOVI GRANITE AND MARBLE (AIVPB0551A) | Pur - T1 | 77 | 102530.7
2023-11-17 | VAISHNOVI GRANITE AND MARBLE (AIVPB0551A) | Pur - T1 | 79 | 97274.85
2023-11-23 | VAISHNOVI GRANITE AND MARBLE (AIVPB0551A) | Pur - T1 | 84 | 206260.2
2023-11-30 | MOUNT GRANITE | Pur - T1 | 00416/23-24 | 60543.25
2023-12-01 | VAISHNOVI GRANITE AND MARBLE (AIVPB0551A) | Pur - T1 | 89 | 119658
2023-12-11 | VAISHNOVI GRANITE AND MARBLE (AIVPB0551A) | Pur - T1 | 99 | 56388
2023-12-12 | VAISHNOVI GRANITE AND MARBLE (AIVPB0551A) | Pur - T1 | 100 | 112554
2024-01-08 | MOUNT GRANITE | Pur - T1 | 00496/23-24 | 53983.95
2024-01-18 | VAISHNOVI GRANITE AND MARBLE | Pur - T1 | 117 | 19850
2024-02-06 | MOUNT GRANITE | Pur - T1 | 00526/2023-24 | 724416
2024-02-09 | MOUNT GRANITE | Pur - T1 | 00530/2023-24 | 714240
2024-02-14 | MOUNT GRANITE | Pur - T1 | 00541/2023-24 | 45000
2024-02-24 | MOUNT GRANITE | Pur - T1 | 00554/2023-24 | 635236
2024-03-01 | VAISHNOVI GRANITE AND MARBLE | Pur - T1 | 134 | 47507.2
2024-03-09 | VAISHNOVI GRANITE AND MARBLE | Pur - T1 | 140 | 149801.6
2024-03-19 | VAISHNOVI GRANITE AND MARBLE | Pur - T1 | 145 | 101857.6
|  | TOTAL |  | 4966804.45

## 4T1 AIR CONDITIONER
4T1 AIR CONDITIONER
Ledger Account
1-Apr-23 to 30-Jun-23
Date |  | Vch Type | Vch No. | Debit
2023-04-14 | MERCURY AIR CONDITIONERS PVT LTD(AADCM7941E) | Pur - T1 | SAL/23-24/0006 | 362050
2023-05-26 | MERCURY AIR CONDITIONERS PVT LTD(AADCM7941E) | Pur - T1 | SB/23-24/0139 | 20790
2023-08-16 | MERCURY AIR CONDITIONERS PVT LTD(AADCM7941E) | Pur - T1 | PB/23-24/0111 | 118250
2023-08-16 | MERCURY AIR CONDITIONERS PVT LTD(AADCM7941E) | Pur - T1 | PB/23-24/0103 | 33750
2024-03-28 | MERCURY AIR CONDITIONERS PVT LTD(AADCM7941E) | Pur - T1 | SAL/23-24/0307 | 264000
2024-03-28 | MERCURY AIR CONDITIONERS PVT LTD(AADCM7941E) | Pur - T1 | SAL/23-24/0308 | 392000
2024-03-28 | MERCURY AIR CONDITIONERS PVT LTD(AADCM7941E) | Pur - T1 | SAL/23-24/0309 | 205000
2024-03-28 | MERCURY AIR CONDITIONERS PVT LTD(AADCM7941E) | Pur - T1 | SAL/23-24/0310 | 184500
2024-03-28 | MERCURY AIR CONDITIONERS PVT LTD(AADCM7941E) | Pur - T1 | SAL/23-24/0311 | 184500
2024-03-28 | MERCURY AIR CONDITIONERS PVT LTD(AADCM7941E) | Pur - T1 | SAL/23-24/0312 | 228000
2024-03-30 | MERCURY AIR CONDITIONERS PVT LTD(AADCM7941E) | Pur - T1 | SAL/23-24/0317 | 257000
2024-03-30 | MERCURY AIR CONDITIONERS PVT LTD(AADCM7941E) | Pur - T1 | SAL/23-24/0318 | 192000
2024-03-30 | MERCURY AIR CONDITIONERS PVT LTD(AADCM7941E) | Pur - T1 | SAL/23-24/0319 | 192000
2633840

## 4T1 FURNITURE
4T1 FURNITURE & WOOD
Ledger Account
1-Apr-23 to 30-Jun-23
Date |  | Vch Type | Vch No. | Debit
2023-06-23 | SHREE PLUMBING POINT | Pur - T1 | SPP3/23-24/0496 | 1440
2023-06-23 | SWASTIK CERAMICS | Pur - T1 | SS-291 | 7796.61
2023-09-29 | VIBRANT DOORCRAFT | Pur - T1 | VDC-216/23-24 | 105365
2023-09-26 | DONA MODULAR SYSTEMS LLP | Pur - T1 | 515 | 725000
839601.61

## 4T1 GRILL & FABRICATION LABOUR
4T1 GRILL & FABRICATION LABOUR
Ledger Account
1-Apr-23 to 30-Jun-23
Date |  | Vch Type | Vch No. | Debit
2023-06-19 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T1 | 200 | 23000
2023-06-19 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T1 | 199 | 87170
2023-08-11 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T1 | 203 | 137000
2023-08-25 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T1 | 204 | 80500
2023-10-01 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T1 | 213 | 75000
2023-11-01 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T1 | 219 | 96600
2023-11-01 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T1 | 220 | 41000
2024-01-19 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T1 | 228 | 42300
2024-01-19 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T1 | 229 | 19500
2024-01-19 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T1 | 231 | 2000
2024-01-20 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T1 | 236 | 30000
2024-02-12 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T1 | 238 | 30000
664070

## 4T1 LIFT
4T1 LIFT
Ledger Account
1-Apr-23 to 30-Jun-23
Date |  | Vch Type | Vch No. | Debit
2023-06-02 | KAPOOR ELEVATORS(AGVPK1384L) | Pur - T1 | KE/100/2023 | 356350
2023-07-07 | UNIQUE LOGISTIC SOLUTIONS (I) PVT. LTD (AABCU0922D) | Pur - T1 | ULS/IM/2324/125 | 42350
2023-07-07 | UNIQUE LOGISTIC SOLUTIONS (I) PVT. LTD (AABCU0922D) | Pur - T1 | ULS/IM/2324/125A | 5063937
2023-07-13 | HITACHI LIFT INDIA PVT LTD | Pur - T1 | 02 | 2292400
2023-08-01 | KAPOOR ELEVATORS(AGVPK1384L) | Pur - T1 | KE/166/2023 | 42000
2023-09-01 | KAPOOR ELEVATORS(AGVPK1384L) | Pur - T1 | KE/185/2023 | 28000
2023-10-01 | KAPOOR ELEVATORS(AGVPK1384L) | Pur - T1 | KE/226/2023 | 28000
2023-11-01 | KAPOOR ELEVATORS(AGVPK1384L) | Pur - T1 | KE/274/2023 | 28000
2023-11-08 | HITACHI LIFT INDIA PVT LTD | Pur - T1 | PI-01 | 1422000
2023-12-01 | KAPOOR ELEVATORS(AGVPK1384L) | Pur - T1 | KE/303/2023 | 28000
2023-12-02 | ZC BVG INDIA LIMITED(AACCB0943N) | Pur - T1 | OA0322712193 | 65683.02
2023-12-14 | HITACHI LIFT INDIA PVT LTD | Pur - T1 | 04 | 355500
2024-01-01 | KAPOOR ELEVATORS | Pur - T1 | KE/341/2023 | 28000
2024-01-02 | ZC BVG INDIA LIMITED | Pur - T1 | OA0232713873 | 57871.9
2024-01-19 | KAPOOR ELEVATORS | Pur - T1 | KE/378/2023 | 45000
2024-02-02 | ZC BVG INDIA LIMITED | Pur - T1 | OA0232715614 | 49572.33
2024-02-12 | HITACHI LIFT INDIA PVT LTD | Pur - T1 | IN2723240108 | 1088000
2024-03-01 | ZC BVG INDIA LIMITED | Pur - T1 | OA0232717218 | 48717.34
2024-03-13 | HITACHI LIFT INDIA PVT LTD | Pur - T1 | IN2723240125 | 153920
2024-03-21 | ZC BVG INDIA LIMITED | Pur - T1 | OA0232718646 | 2211.61
11225513.2

## 4T1 TILES
4T1 TILES
Ledger Account
1-Apr-23 to 30-Jun-23
Date |  | Vch Type | Vch No. | Debit
2023-04-29 | S RAHEJA CERAMIC(AOQPS0707Q) | Pur - T1 | 035 | 309845
2023-05-31 | S RAHEJA CERAMIC(AOQPS0707Q) | Pur - T1 | 061 | 66340.62
2023-06-01 | HARI OM MARBLE(AAAPC7857R) | Pur - T1 | 23/24-009 | 12740
2023-08-02 | NATIONAL CERAMICS(AFQPP4603M) | Pur - T1 | 2389/23-24 | 192100
2023-08-02 | AARTISTIK | Pur - T1 | 1244/23-24 | 25127.2
2023-08-04 | TELECAST TRANSCONTINENTAL LLP - TILES | Pur - T1 | TTC/67/23-24 | 23026.7
2023-08-09 | S RAHEJA CERAMIC(AOQPS0707Q) | Pur - T1 | 108 | 92417.79
2023-08-17 | KAJARIA CERAMICS LTD(AABCK1613R) | Pur - T1 | 5742314783 | 600823.65
2023-08-24 | KAJARIA CERAMICS LTD(AABCK1613R) | Pur - T1 | 5742315699 | 395164.39
2023-08-24 | KAJARIA CERAMICS LTD(AABCK1613R) | Pur - T1 | 5742315698 | 398710.97
2023-08-25 | NATIONAL CERAMICS(AFQPP4603M) | Pur - T1 | 2792/23-24 | 20900
2023-08-26 | KAJARIA CERAMICS LTD(AABCK1613R) | Pur - T1 | 5742316017 | 395164.39
2023-08-26 | S RAHEJA CERAMIC(AOQPS0707Q) | Pur - T1 | 125 | 680879.97
2023-08-26 | KAJARIA CERAMICS LTD(AABCK1613R) | Pur - T1 | 5742316016 | 398710.97
2023-08-30 | PRISM JOHNSON LIMITED | Pur - T1 | 7462416082 | 413277.17
2023-08-30 | PRISM JOHNSON LIMITED | Pur - T1 | 7462416115 | 413277.17
2023-08-30 | PRISM JOHNSON LIMITED | Pur - T1 | 7462416117 | 453227.15
2023-08-30 | KAJARIA CERAMICS LTD(AABCK1613R) | Pur - T1 | 5742316783 | 398710.97
2023-08-30 | KAJARIA CERAMICS LTD(AABCK1613R) | Pur - T1 | 5742316785 | 395164.39
2023-09-04 | LIDCO BUILDING TECHNOLOGIES LLP | Pur - T1 | 583/23-24 | 9407.7
2023-09-15 | S RAHEJA CERAMIC(AOQPS0707Q) | Pur - T1 | 141 | 189037.87
2023-09-30 | LIDCO BUILDING TECHNOLOGIES LLP | Pur - T1 | LIDCO/662/23-24 | 4151.25
2023-10-07 | TELECAST TRANSCONTINENTAL LLP - TILES | Pur - T1 | TTC/99/23-24 | 351596.09
2023-10-11 | BELLACASA CERAMICA | Pur - T1 | BC/720/2023-24 | 9323.8
2023-10-12 | PRISM JOHNSON LIMITED | Pur - T1 | 7462421669 | 482155.86
2023-10-14 | PRISM JOHNSON LIMITED | Pur - T1 | 7462421867 | 315467.76
2023-10-16 | RAJ ENTERPRISE(27ACNPV0135C1ZP) | Pur - T1 | 23-24/88 | 443856.45
2023-10-16 | PRISM JOHNSON LIMITED | Pur - T1 | 7462422059 | 481329.64
2023-10-17 | NATIONAL CERAMICS(AFQPP4603M) | Pur - T1 | 3779/23-24 | 17100
2023-11-03 | CLASSIC FLOORINGS & INTERIORS PVT LTD | Pur - T1 | SLE-MUM2324-1081 | 12018
2023-11-11 | PRISM JOHNSON LIMITED | Pur - T1 | 7462425418 | 482156.33
2023-11-16 | PRISM JOHNSON LIMITED | Pur - T1 | 7462425530 | 482155.85
2023-11-17 | PRISM JOHNSON LIMITED | Pur - T1 | 7462425618 | 219587.77
2023-11-17 | PRISM JOHNSON LIMITED | Pur - T1 | 7462425619 | 51521.85
2023-11-29 | RELIABLE CERAMICS(AMBPJ9449H) | Pur - T1 | RC/23-24/1799 | 66540.25
2023-12-06 | S RAHEJA CERAMIC(AOQPS0707Q) | Pur - T1 | 239 | 400506.04
2023-12-21 | BLUE FERN INDIA | Pur - T1 | T084/23-24 | 54550
2024-01-01 | BELLACASA CERAMICA | Pur - T1 | BC/1077/2023-24 | 420441.7
2024-01-09 | CANOPUS RETAIL PVT LTD | Pur - T1 | 012502 | 183050.85
2024-01-09 | AARTISTIK | Pur - T1 | 2829/23-24 | 67811.84
2024-01-11 | ITALIANO STONE AND STEEL | Pur - T1 | 036 | 582450
2024-01-15 | AARTISTIK | Debit Note | CN144 | -67811.84
2024-01-22 | TELECAST TRANSCONTINENTAL LLP - TILES | Pur - T1 | TTC/144/23-24 | 36585.25
2024-01-27 | S RAHEJA CERAMIC | Pur - T1 | 308 | 24579.4
2024-01-31 | KANERIA PLAST PVT LTD | Pur - T1 | KP/9363/23-24 | 157500
2024-01-31 | CANOPUS RETAIL PVT LTD | Pur - T1 | CR27/2324/014382 | 183050.85
2024-01-31 | CANOPUS RETAIL PVT LTD | Pur - T1 | CR27/2324/014382 | 183050.85
2024-02-07 | AARTISTIK | Pur - T1 | 3127/23-24 | 50279.6
2024-02-08 | S RAHEJA CERAMIC | Pur - T1 | 320 | 151854.3
2024-02-16 | CANOPUS RETAIL PVT LTD | Pur - T1 | CR27/2324/015780 | 79322.03
2024-02-21 | RAJ ENTERPRISE | Pur - T1 | 23-24/149 | 62470
2024-03-11 | AARTISTIK | Pur - T1 | 3466/23-24 | 19194.9
2024-03-30 | ITALIANO STONE AND STEEL | Pur - T1 | 046 | 465000
12356900.74

## 4T1 INTERIOR DESIGNS
4T1 INTERIOR DESIGNS
1-Jul-23 to 30-Sep-23
Date |  | Vch Type | Vch No. | Debit
2023-08-03 | ZP SUVIDH SHUKLA DESIGN LLP(AESFS4304M) | Pur - T1 | SSA-ONE-MER-001 | 270000
2023-08-03 | ZP SUVIDH SHUKLA DESIGN LLP(AESFS4304M) | Pur - T1 | SSA-ONE-MER-002 | 405000
2024-02-14 | ZP SUVIDH SHUKLA DESIGN LLP | Pur - T1 | SSA-ONE-MER-003 | 945000
1620000

## 4T1 VENTILATION MATERIAL
4T1 VENTILATION MATERIAL
Ledger Account
1-Apr-23 to 30-Jun-23
Date |  | Vch Type | Vch No. | Debit
2023-04-17 | DINESH ELECTRICAL ENGINEERING | Pur - T1 | GST/09 | 660000
2023-04-22 | DINESH ELECTRICAL ENGINEERING | Pur - T1 | GST/11 | 378000
2023-07-29 | TECHNO COMFORT ENGINEERS(AAJFT3284A) | Pur - T1 | 09 | 1032500
2070500

## 4T1 GYPSUM WORK
4T1 GYPSUM WORK
1-Jul-23 to 30-Sep-23
Date |  | Vch Type | Vch No. | Debit
2023-08-14 | SEHBAAZ ENTERPRISES(BQXPB1128A) | Pur - T1 | 52 | 860734.49
2023-09-25 | SEHBAAZ ENTERPRISES(BQXPB1128A) | Pur - T1 | 53 | 557739.26
2023-10-30 | ZC SEHBAAZ ENTERPRISES(BQXPB1128A) | Pur - T1 | RA-3 | 1165796
2023-12-23 | ZC SEHBAAZ ENTERPRISES(BQXPB1128A) | Pur - T1 | 56 | 1250868
2024-03-12 | ZC SEHBAAZ ENTERPRISES(BQXPB1128A) | Pur - T1 | 57 | 1489478
2024-03-12 | ZC SEHBAAZ ENTERPRISES(BQXPB1128A) | Debit Note | T1/JSA/16 | -9400
5315215.75

## 4T1 PAINTING MATERIAL
4T1 PAINTING MATERIAL
Ledger Account
1-Oct-23 to 31-Dec-23
Date |  | Vch Type | Vch No. | Debit
2023-11-01 | ZC SHEETAL ENTERPRISES(CQOPK2575E) | Pur - T1 | SE/2023/0027 | 478117.26
2024-03-12 | ZC TEXTURE CONCEPTS PVT LTD | Debit Note | T1/JSA/14 | -9400
12350
481067.26

## 4T1 SWIMMING POOL MATERIAL
4T1 SWIMMING POOL MATERIAL
Ledger Account
( 04T1 CONSTRUCTION COST )
1-Oct-23 to 31-Dec-23
Date |  | Vch Type | Vch No. | Debit
2023-11-28 | STG HEATING PVT LTD | Pur - T1 | INV/1191/23-24 | 1753732.7
2024-03-21 | STG HEATING PVT LTD | Pur - T1 | INV/1798/23-24 | 257860.35
1753732.7 |  |  |  | 2011593.05

## 4T1 WOOD
4T1 WOOD
Ledger Account
( 04T1 CONSTRUCTION COST )
1-Oct-23 to 31-Dec-23
Date |  | Vch Type | Vch No. | Debit
2023-10-19 | VIBRANT DOORCRAFT | Pur - T1 | VDC-238/23-24 | 14000
2023-12-02 | VIBRANT DOORCRAFT | Pur - T1 | VDC-292/23-24 | 108765
2023-12-22 | VIBRANT DOORCRAFT | Pur - T1 | VDC-315/23-24 | 1486800
2024-01-04 | VIBRANT DOORCRAFT | Pur - T1 | VDC-333/23-24 | 1904400
2024-01-05 | J K ENTERPRISES | Pur - T1 | 614/2023-24 | 15099.48
2024-01-09 | J K ENTERPRISES | Pur - T1 | 622/2023-24 | 78240.74
2024-01-10 | VIBRANT DOORCRAFT | Pur - T1 | VDC-340/23-24 | 2510750
2024-01-11 | VIBRANT DOORCRAFT | Pur - T1 | VDC-341/23-24 | 1200
2024-01-11 | VIBRANT DOORCRAFT | Pur - T1 | VDC-342/23-24 | 21000
2024-01-13 | VIBRANT DOORCRAFT | Pur - T1 | VDC-348/23-24 | 70000
2024-01-17 | VIBRANT DOORCRAFT | Pur - T1 | VDC-357/23-24 | 227320
2024-01-19 | VIBRANT DOORCRAFT | Pur - T1 | VDC-362/23-24 | 1730385
2024-01-19 | VIBRANT DOORCRAFT | Pur - T1 | VDC-363/23-24 | 190440
2024-01-20 | VIBRANT DOORCRAFT | Pur - T1 | VDC-364/23-24 | 1234235
2024-02-22 | J K ENTERPRISES | Pur - T1 | 726/2023-24 | 32764.43
2024-03-05 | VIBRANT DOORCRAFT | Pur - T1 | VDC-419/23-24 | 494720
2024-03-07 | VIBRANT DOORCRAFT | Pur - T1 | VDC-422/23-24 | 808500
2024-03-07 | VIBRANT DOORCRAFT | Pur - T1 | VDC-423/23-24 | 384000
2024-03-12 | VIBRANT DOORCRAFT | Debit Note | T1/JSA/08 | -14137.5
11298482.15

## 4T1 CLEANING CHARGES
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
4T1 CLEANING CHARGES
Ledger Account
( 04T1 CONSTRUCTION COST )
1-Jan-24 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit
2024-01-05 | ZC SEHBAAZ ENTERPRISES(BQXPB1128A) | Journal |  | -4500
2024-01-25 | SHIV ENTERPRISES | Pur - T1 | S0002560/2023-24 | 6335
2024-01-31 | SHIV ENTERPRISES | Pur - T1 | S0002548/2023-24 | 2335
2024-02-02 | ZC GOND ENTERPRISE(AMYPG2103J) | Journal |  | -6955
2024-02-02 | ZC GOND ENTERPRISE(AMYPG2103J) | Journal |  | -18000
2024-02-08 | SHIV ENTERPRISES | Pur - T1 | S0002642/2023-24 | 5235
2024-03-25 | SHIV ENTERPRISES | Pur - T1 | S0003143/23-24 | 77960
TOTAL |  |  |  | 62410

## Unpaid Bills
Sr. No. | Particulars | Materials | Invoice No. | Date | Amount
1 | Atri Group | Excavation | Proforma | 27.09.2022 | 82600000
2 | seven hills | Excavation | Proforma | 16.09.2022 | 12724530
TOTAL |  |  |  |  | 95324530
5000000
90324530

## Professional
Particulars | Amount
04T1 CONSTRUCTION COST
4T1 SOIL TESTING | 230900
Architect & Structural Fees | 8112572
Professional fees | 4100000
Professional fees | 16775648.59
Grand Total | 29219120.59

## Professional Charges
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T1 PROFESSIONAL FEES
Ledger Account
1-Sep-22 to 30-Sep-22
Date |  | Vch Type | Vch No. | Debit
2022-09-01 | ZP JIGER BIPIN MEHTA(AALPM3480F) | Pur - T1 | INV20/AUG/22 | 115000
2022-09-02 | ZP VENTURX PROJECTS SERVICES LLP(AATFV8554H) | Pur - T1 | VPSL/2022-23/97 | 50000
2022-09-08 | ZP SIYA CAPITAL(AETFS8372Q) | Pur - T1 | SC/22-23/01 | 100000
2022-09-12 | ZP JALINDAR ROUNDHAL(BOBPR7751D) | Pur - T1 | P | 18000
2022-09-28 | ZP BUILDCROWN MEP SERVICES CONSULTANT LLP(AAWFB4803C) | Pur - T1 | BMSC/M/006/21-22 | 500000
2022-10-01 | ZP JIGER BIPIN MEHTA | Pur - T1 | INV21/SEP/22 | 115000
2022-10-01 | ZP VENTURX PROJECTS SERVICES LLP | Pur - T1 | VPSL/2022-23/106 | 50000
2022-10-07 | ZC SIDHPURA & ASSOCIATES | Pur - T1 | SA/10/01 | 464880
2022-10-20 | ZP VASTUKALA CONSULTANTS (I) PVT LTD | Pur - T1 | MUM/2223/OCT/129 | 75000
2022-11-01 | ZP JIGER BIPIN MEHTA | Pur - T1 | INV 22/OCT/22 | 115000
2022-11-03 | ZP VENTURX PROJECTS SERVICES LLP | Pur - T1 | VPSL/2022-23/111 | 50000
2022-11-15 | ZC SIDHPURA & ASSOCIATES | Pur - T1 | SA/11/01 | 781200
2022-11-21 | ZP HANSAL PARIKH & ASSOCIATES | Pur - Park | HPA/22-23/0062 | 608683.5
2022-11-28 | ZP ARCHITYPE3D IMAGES | Pur - T1 | AT3DI0024 | 517500
2022-11-29 | ZP V.S. JADON & CO. VALUERS LLP | Pur - T1 | 1737/22-23 | 50000
2022-12-01 | ZP JIGER BIPIN MEHTA | Pur - T1 | INV23/NOV '22 | 115000
2022-12-01 | ZP S R M CONSULTANTS | Pur - T1 | 003 | 475000
2022-12-02 | ZP VENTURX PROJECTS SERVICES LLP | Pur - T1 | VPSL/2022-23/117 | 50000
2022-11-15 | ZP SHANGHVI & ASSOCIATES CONSULTANTS PVT LTD | Pur - T1 | SACPL/261/22-23 | 852590
2022-11-18 | ZP P R CONSULTANTS | Pur - T1 | PRC/2022-23/133 | 582760
2022-12-06 | ZP AMS CONSULTANTS | Pur - T1 | 02/SSD-MTB/22 | 111000
2023-01-05 | ZP P R CONSULTANTS(AAHFP1742P) | Pur - T1 | PRC/2022-23/143 | 388507
2023-03-01 | ZP P R CONSULTANTS(AAHFP1742P) | Pur - T1 | PRC/2022-23/158 | 388507
2023-01-01 | MIRA INFORM PVT LTD | Pur - T1 | 391516 | 2000
2023-01-01 | MIRA INFORM PVT LTD | Pur - T1 | 391185 | 2000
2023-01-02 | ZP JIGER BIPIN MEHTA(AALPM3480F) | Pur - T1 | INV24/DEC/22 | 115000
2023-01-02 | ZP VENTURX PROJECTS SERVICES LLP(AATFV8554H) | Pur - T1 | VPSL/2022-23/125 | 50000
2023-01-09 | ZP ARCHITYPE3D IMAGES(AEFPR6032J) | Pur - T1 | AT3DI 0030 | 345000
2023-01-17 | ZP VASTUKALA CONSULTANTS (I) PVT LTD(AADCV4303R) | Pur - T1 | MUM/2223/JAN/137 | 30000
2023-01-18 | ZP JALINDAR ROUNDHAL(BOBPR7751D) | Pur - T1 | P | 14000
2023-01-21 | LEGAL ENTITY IDENTIFIER INDIA LIMITED | Pur - T1 | IRW/2223/0028509 | 3000
2023-01-31 | MIRA INFORM PVT LTD | Pur - T1 | T0123272O20299 | 24063.89
2023-02-01 | ZP JIGER BIPIN MEHTA(AALPM3480F) | Pur - T1 | INV25/JAN23 | 115000
2023-02-04 | ZP VENTURX PROJECTS SERVICES LLP(AATFV8554H) | Pur - T1 | VPSL/2022-23/132 | 50000
2023-02-14 | A.K. ENTERPRISES(AAOFA6311N) | Pur - T1 | 68/AK/2022-23 | 150000
2023-03-01 | ZP JIGER BIPIN MEHTA(AALPM3480F) | Pur - T1 | INV26/FEBRUARY 23 | 115000
2023-03-03 | ZP VENTURX PROJECTS SERVICES LLP(AATFV8554H) | Pur - T1 | VPSL/2022-23/138 | 130000
2023-03-13 | Shanghvi and Associates Consultants Pvt. Ltd. |  | SACPL/386/22-23 | 1479472.2
2023-03-24 | ZP VASTUKALA CONSULTANTS (I) PVT LTD(AADCV4303R) | Pur - T1 | PG-5971/22-23 | 30000
2023-05-05 | ZP AMS CONSULTANTS(AAIPS6540F) | Pur - T1 | 03/SSD-MTB/23 | 222000
2023-05-11 | ZP P R CONSULTANTS(AAHFP1742P) | Pur - T1 | PRC/2023-24/110 | 777014
2023-04-01 | ZP JIGER BIPIN MEHTA(AALPM3480F) | Pur - T1 | INV27/MARCH23 | 115000
2023-04-01 | ZP JALINDAR ROUNDHAL(BOBPR7751D) | Pur - T1 |  | 25000
2023-04-05 | ZP VENTURX PROJECTS SERVICES LLP(AATFV8554H) | Pur - T1 | VPSL/2023-24/152 | 130000
2023-04-12 | ZP RUSHIRAJ GARJE(ARTPG7698E) | Pur - T1 | RG/156/23-24 | 45000
2023-04-14 | ZP S P ENTERPRISES(ATYPS3028F) | Pur - T1 | 031 | 30000
2023-04-14 | ZP BUILDCROWN MEP SERVICES CONSULTANT LLP(AAWFB4803C) | Pur - T1 | BMSC/M/007/23-24 | 300000
2023-04-22 | ARUN M AGARWAL & ASSOCIATES | Pur - T1 | AMAA/008/2023-24 | 26424
2023-04-22 | ZP KAPURE & KAPURE(AAPFK3547F) | Pur - T1 | KK/2023/24/27 | 10000
2023-04-25 | ZP RUSHIRAJ GARJE(ARTPG7698E) | Pur - T1 | RG/160/23-24 | 35000
2023-05-01 | ZP JIGER BIPIN MEHTA(AALPM3480F) | Pur - T1 | INV28/ARPIL23 | 115000
2023-05-03 | ZP VENTURX PROJECTS SERVICES LLP(AATFV8554H) | Pur - T1 | VPSL/2023-24/155 | 130000
2023-05-11 | MOHAMMAD HANIF SYED | Pur - T1 | 133 | 20000
2023-06-01 | ZP JIGER BIPIN MEHTA(AALPM3480F) | Pur - T1 | INV29/MAY23 | 115000
2023-06-01 | ZP VENTURX PROJECTS SERVICES LLP(AATFV8554H) | Pur - T1 | VPSL/2023-24/158 | 130000
2023-08-24 | ZP AMS CONSULTANTS | Pur - T1 | 04/SSD-MTB/23 | 111000
2023-07-01 | ZP JIGER BIPIN MEHTA | Pur - T1 | INV30/JUNE23 | 115000
2023-07-03 | ZP VENTURX PROJECTS SERVICES LLP | Pur - T1 | VPSL/2023-24/165 | 130000
2023-07-31 | ZP JIGER BIPIN MEHTA | Pur - T1 | INV31/JULY23 | 115000
2023-08-02 | ZP VENTURX PROJECTS SERVICES LLP | Pur - T1 | VPSL/2023-24/180 | 130000
2023-08-07 | ZP P R CONSULTANTS | Pur - T1 | PRC/2023-24/118 | 726794
2023-09-01 | ZP JIGER BIPIN MEHTA | Pur - T1 | INV32/AUG'23 | 115000
2023-09-02 | ZP VENTURX PROJECTS SERVICES LLP | Pur - T1 | VPSL/2023-24/186 | 130000
2023-09-06 | CHOPRA SHAH & ASSOCIATES | Pur - T1 | CSA/ROC2324/0287 | 1300
2023-09-27 | ZP SATISH JAIN CONSULTING ENGINEERS PRIVATE LIMITED | Pur - T1 | SJCEPL/23-24/028 | 275000
2023-10-01 | ZP JIGER BIPIN MEHTA(AALPM3480F) | Pur - T1 | INV33/SEPT 23 | 115000
2023-10-04 | ZP VENTURX PROJECTS SERVICES LLP(AATFV8554H) | Pur - T1 | VPSL/2023-24/200 | 130000
2023-10-12 | ZC KAUSHIK FIRE APPLIANCES SERVICE(AAAPC5880G) | Pur - T1 | KFAS036/OCT | 1429072
2023-11-01 | ZP JIGER BIPIN MEHTA(AALPM3480F) | Pur - T1 | INV34/OCT'23 | 115000
2023-11-02 | ZP VENTURX PROJECTS SERVICES LLP(AATFV8554H) | Pur - T1 | VPSL/2023-24/210 | 130000
2023-11-27 | ZP P R CONSULTANTS(AAHFP1742P) | Pur - T1 | PRC/2023-24/139 | 388507
2023-12-01 | ZP VENTURX PROJECTS SERVICES LLP(AATFV8554H) | Pur - T1 | VPSL/2023-24/226 | 130000
2023-12-01 | ZP JIGER BIPIN MEHTA(AALPM3480F) | Pur - T1 | INV35/NOV23 | 115000
2023-12-20 | ZP MINAKSHI M AGARWAL & ASSOCIATES | Pur - T1 | MMAA/050/2023-24 | 26424
2023-12-27 | ZP RIVASTU CONULTANCY(ALPPA4542F-1) | Pur - T1 | PKN/R-020/2021 | 50000
2024-01-01 | ZP JIGER BIPIN MEHTA | Pur - T1 | INV36/DEC23 | 115000
2024-01-04 | LEGAL ENTITY IDENTIFIER INDIA LIMITED | Pur - T1 | IRW/2324/0026907 | 5850
2024-01-09 | ZP VENTURX PROJECTS SERVICES LLP | Pur - T1 | VPSL/2023-24/237 | 130000
2024-02-01 | ZP JIGER BIPIN MEHTA | Pur - T1 | INV36/JAN24 | 115000
2024-02-02 | ZP VENTURX PROJECTS SERVICES LLP | Pur - T1 | VPSL/2023-24/248 | 130000
2024-02-12 | ZC KAUSHIK FIRE APPLIANCES SERVICE | Pur - T1 | KFAS055/FEB | 70000
2024-02-21 | ZP VASTUKALA CONSULTANTS (I) PVT LTD | Pur - T1 | MUM/2324/FEB/170 | 30000
2024-03-01 | ZP JIGER BIPIN MEHTA | Pur - T1 | INV37/FEB24 | 115000
2024-03-01 | ZP VENTURX PROJECTS SERVICES LLP | Pur - T1 | VPSL/2023-24/258 | 130000
2024-03-01 | CHOPRA SHAH & ASSOCIATES | Pur - T1 | CSA/ROC2324/0756 | 3100
16775648.59

## 4T1 SOIL TESTING
4T1 SOIL TESTING
Ledger Account
1-Feb-22 to 31-Aug-22
Date |  | Vch Type | Vch No. | Debit | Credit
2022-02-12 | ZP SHREE LAB & CONSULTANCY(AKMPC4398P) | Pur - T1 | SLC/INV/462/21-22 | 1200
BILL NO.SLC/INV/462/21-22
2022-02-24 | ZP SHREE LAB & CONSULTANCY(AKMPC4398P) | Pur - T1 | SLC/INV/472/21-22 | 8700
BILL NO.SLC/INV/472/21-22
2022-03-25 | ZP SHREE LAB & CONSULTANCY(AKMPC4398P) | Pur - T1 | SLC/INV/529/21-22 | 22500
BILL NO.SLC/INV/529/21-22
2022-04-01 | ZP URBAN LAB CONSULTANTS(AAEFU8275H) | Pur - T1 | KLR/22/002312 | 12000
BILL NO.KLR/22/002312
2022-04-24 | ZP F M TESTING LAB(AOMPP6000R) | Pur - T1 | 0237 | 48700
BILL NO 0237
2022-05-22 | ZP F M TESTING LAB(AOMPP6000R) | Pur - T1 | 0406 | 9600
CASE NO - 280522.1- FM TESTING LAB(CUBE TEST) MERAKI ONE
2022-06-26 |  |  |  | 7800
CASE NO - 107220795( CUBE TEST REPORTS) ONE MERAKI
2022-07-24 |  |  |  | 5400
CASE NO : 260722.4 (CUBE TEST REPORTS) ONE MERAKI
2022-08-21 | ZP F M TESTING LAB(AOMPP6000R) | Pur - T1 | 1445 | 6000
CASE NO - 10922.1 ( F.M TESTING LAB(ONE MERAKI CUBE TESTING CHARGES)
2022-09-02 | ZP SHREE LAB & CONSULTANCY(AKMPC4398P) | Pur - T1 | SLC/INV/207/2023 | 7700
2022-09-25 | ZP F M TESTING LAB(AOMPP6000R) | Pur - T1 | 1897 | 11000
2022-10-23 | ZP F M TESTING LAB | Pur - T1 | 2109 | 16000
2022-10-23 | ZP F M TESTING LAB | Pur - T1 | 2241 | 5900
2022-11-27 | ZP F M TESTING LAB | Pur - T1 | 2645 | 7500
2022-12-25 | ZP F M TESTING LAB | Pur - T1 | 2959 | 6600
2023-01-22 | ZP F M TESTING LAB(AOMPP6000R) | Pur - T1 | 3321 | 10400
2023-02-22 | ZP F M TESTING LAB(AOMPP6000R) | Pur - T1 | 3805 | 18400
2023-04-24 | ZP F M TESTING LAB(AOMPP6000R) | Pur - T1 | 0060 | 21300
2023-05-02 | ZP SHREE LAB & CONSULTANCY(AKMPC4398P) | Pur - T1 | SLC/INV/64/23-24 | 4200
230900

## Admin
Particulars | Amount
Admin
4T1 MISCL EXPENSES | 7273186
4T1 PRINTING & STATIONERY | 46270
4T1 TREE CUTTING LABOUR FEES | 416000
4T1 WATER CHARGES & Unloading Charges | 6227115.15
SBI General insurance | 2181358
4T1 SECURITY SERVICES | 4173012
Salary | 8122455
Grand Total | 28439396.15
1797209
268400
613400
1547052
4226061
12348516

## 4T1 MISCL EXPENSES
4T1 MISCL EXPENSES
Ledger Account
1-Jun-22 to 30-Jun-22
Date |  | Vch Type | Vch No. | Debit | Credit
2022-06-01 | HEMALI,ADITI & FALGUNI INDUSTRIES(AAAFH2234D) | Pur - T1 | 169 | 17175.12
BILL NO -169 SABARI PARK - ( TARPAULIN PLASTIC TUBING)
2022-06-25 | HEMALI,ADITI & FALGUNI INDUSTRIES(AAAFH2234D) | Pur - T1 | 311 | 20611.2
DIRECT ORDER 311 SABARI PARK - ( TARPAULIN PLASTIC TUBING)
2022-06-28 | BOMBAY SEEDS(AAXFB3023F) | Pur - T1 | MRG647 | 49152.54
AEROSOL CAN
2022-09-07 | DR.VINAY DHAWALE(ABEPD2261M) | Pur - T1 | 817 | 6000
2022-10-12 | DR.VINAY DHAWALE | Pur - T1 | 862 | 9000
2022-10-18 | TUSHAR STEEL | Pur - T1 | TS/243 | 26234
2022-11-14 | MD ALIFSANI RAZA | Pur - T1 | 021 | 7300
2022-11-14 | DR.VINAY DHAWALE | Pur - T1 | 893 | 9000
2022-12-08 | DR.VINAY DHAWALE | Pur - T1 | 911 | 9000
2023-01-04 | DR.VINAY DHAWALE(ABEPD2261M) | Pur - T1 | 942 | 9000
2023-01-09 | TUSHAR STEEL(AAEPK3479R) | Pur - T1 | TS/333 | 147500
2023-02-04 | AZMI PATHOLOGY LABORATORY | Pur - T1 |  | 4980
2023-02-06 | DR.VINAY DHAWALE(ABEPD2261M) | Pur - T1 | 961 | 9000
2023-03-20 | MD ALIFSANI RAZA(DHYPR0692P) | Pur - Park | 29 | 56100
2023-04-04 | DR.VINAY DHAWALE(ABEPD2261M) | Pur - T1 | 726 | 9000
2023-04-28 | ASHUTOSH RUBBER PVT LTD | Pur - T1 | U1/2/0054/23-24 | 3500
2023-05-05 | DR.VINAY DHAWALE(ABEPD2261M) | Pur - T1 | 753 | 9000
2023-05-08 | PRAMOD A CHIMANE | Pur - T1 |  | 3600
2023-05-10 | HEMALI,ADITI & FALGUNI INDUSTRIES(AAAFH2234D) | Pur - T1 | 65/23-24 | 26429.41
2023-05-12 | HEMALI,ADITI & FALGUNI INDUSTRIES(AAAFH2234D) | Pur - T1 | 66/23-24 | 29001
2023-05-15 | GLOBETREK ENGINEERING CORPORATION | Pur - T1 | GTEC-2023-24-30 | 20900
2023-06-01 | ACE ENGINEERS & CONSULTANTS(AIMPG0681R) | Pur - T1 | AEC/DL/23-24/51 | 196000
2023-06-09 | DR.VINAY DHAWALE(ABEPD2261M) | Pur - T1 | 798 | 9000
2023-07-12 | ZC ACE ENGINEERS & CONSULTANTS(AIMPG0681R) | Pur - T1 | AEC/DL/23-24/98 | 130060
2023-07-17 | DR.VINAY DHAWALE(ABEPD2261M) | Pur - T1 | 624 | 9000
2023-08-10 | ZC ACE ENGINEERS & CONSULTANTS(AIMPG0681R) | Pur - T1 | AEC/DL/23-24/119 | 168000
2023-08-10 | ZC ACE ENGINEERS & CONSULTANTS(AIMPG0681R) | Pur - T1 | AEC/DL/23-24/120 | 14000
2023-08-16 | DR.VINAY DHAWALE(ABEPD2261M) | Pur - T1 | 671 | 9000
2023-08-22 | GLOBETREK ENGINEERING CORPORATION | Pur - T1 | GTEC-2023-24-118 | 35000
2023-08-22 | SONALI ENTERPRISES | Pur - T1 | 215-23/24 | 20440
2023-09-04 | ZC ACE ENGINEERS & CONSULTANTS(AIMPG0681R) | Pur - T1 | AEC/DL/23-24/135 | 168000
2023-09-06 | ZC ACE ENGINEERS & CONSULTANTS(AIMPG0681R) | Pur - T1 | AEC/DL/23-24/150 | 22000
2023-09-11 | DR.VINAY DHAWALE(ABEPD2261M) | Pur - T1 | 007 | 9000
2023-09-25 | 2Z STATE BANK OF INDIA - 2756-ESCROW ACCOUNT ONE MERAKI WING A & WING B -30%(41125812756) | Payment | CMS | 84450
2023-09-30 | BAHRI AUTO SERVICE | Pur - T1 | 187 | 94220
2023-10-01 | Opening Balance
2023-10-01 | SAMRUDDHI ENGINEERS | Pur - T1 | SE/23-24/873 | 1500
2023-10-04 | ZC ACE ENGINEERS & CONSULTANTS(AIMPG0681R) | Pur - T1 | AEC/DL/23-24/169 | 89600
2023-10-10 | SAMRUDDHI ENGINEERS | Pur - T1 | SE/23-24/1205 | 1500
2023-10-11 | SAMRUDDHI ENGINEERS | Pur - T1 | SE/23-24/1216 | 1500
2023-10-11 | DR.VINAY DHAWALE(ABEPD2261M) | Pur - T1 | 042 | 9000
2023-10-21 | SONALI ENTERPRISES | Pur - T1 | 319-23/24 | 290160
2023-11-02 | ZC ACE ENGINEERS & CONSULTANTS(AIMPG0681R) | Pur - T1 | AEC/DL/23-24/205 | 453404
2023-11-03 | SAMRUDDHI ENGINEERS | Pur - T1 | SE/23-24/1359 | 1500
2023-11-11 | DR.VINAY DHAWALE(ABEPD2261M) | Pur - T1 | 081 | 9000
2023-11-24 | SAMRUDDHI ENGINEERS | Pur - T1 | SE/23-24/1460 | 1500
2023-11-30 | BAHRI AUTO SERVICE | Pur - T1 | 715 | 188440
2023-12-01 | ZC ATRI BUILDTECH - RESI -T1(ABUFA5341H-P) | Debit Note | T1/AEC/014 | -66080
2023-12-01 | ZC ATRI BUILDTECH - RESI -T1(ABUFA5341H-P) | Debit Note | T1/AEC/015 | -16520
2023-12-02 | ZC ACE ENGINEERS & CONSULTANTS(AIMPG0681R) | Pur - T1 | AEC/DL/23-24/213 | 557048
2023-12-07 | DR.VINAY DHAWALE(ABEPD2261M) | Pur - T1 | 113 | 9000
2023-12-15 | SAMRUDDHI ENGINEERS | Pur - T1 | SE/23-24/1559 | 3000
2023-12-15 | SAMRUDDHI ENGINEERS | Pur - T1 | SE/23-24/1559 | 3000
2023-12-15 | SAMRUDDHI ENGINEERS | Pur - T1 | SE/23-24/1558 | 3000
2023-12-16 | SAMRUDDHI ENGINEERS | Pur - T1 | SE/23-24/1570 | 1500
2023-12-18 | SAMRUDDHI ENGINEERS | Pur - T1 | SE/23-24/1585 | 1500
2023-12-22 | SAMRUDDHI ENGINEERS | Pur - T1 | SE/23-24/1625 | 1500
2023-12-22 | SAMRUDDHI ENGINEERS | Pur - T1 | SE/23-24/1626 | 1500
2023-12-25 | SAMRUDDHI ENGINEERS | Pur - T1 | SE/23-24/1647 | 1500
2024-01-03 | HEMALI,ADITI & FALGUNI INDUSTRIES | Pur - T1 | 630/23-24 | 6544.56
2024-01-03 | ZC ACE ENGINEERS & CONSULTANTS | Pur - T1 | AEC/DL/23-24/245 | 560000
2024-01-03 | ZC ATRI BUILDTECH - RESI -T1 | Debit Note | T1/AEC/016 | -148680
2024-01-04 | DR.VINAY DHAWALE | Pur - T1 | 138 | 9000
2024-01-10 | MD ALIFSANI RAZA | Pur - T1 | 035 | 16000
2024-01-20 | SAMRUDDHI ENGINEERS | Pur - T1 | SE/23-24/1788 | 4500
2024-01-29 | ZC GOND ENTERPRISE | Debit Note | T1/JSA/01 | -22500
2024-01-29 | KAVLES PRESSURE CONCRETE PVT LTD | Debit Note | T1/JSA/02 | -4500
2024-01-29 | ZC ATRI BUILDTECH - RESI -T1 | Debit Note | T1/JSA/03 | -6750
2024-01-29 | QUALDOW LLP - T1 | Debit Note | T1/JSA/04 | -2250
2024-01-29 | MAHAVIR SANITATION PVT LTD | Debit Note | T1/JSA/05 | -4500
2024-01-29 | ZC MORE ELECTRICAL & ENGINEERING WORKS | Debit Note | T1/JSA/06 | -2250
2024-01-29 | ZC SEHBAAZ ENTERPRISES | Debit Note | T1/JSA/07 | -2250
2024-02-01 | ZC ACE ENGINEERS & CONSULTANTS | Pur - T1 | AEC/DL/23-24/272 | 560000
2024-02-01 | SAMRUDDHI ENGINEERS | Pur - T1 | SE/23-24/1855 | 4500
2024-02-05 | BLUE FERN INDIA | Pur - T1 | T107/23-24 | 4000
2024-02-05 | BAHRI AUTO SERVICE | Pur - T1 | 901 | 94220
2024-02-06 | PARVIOM TECHNOLOGIES PVT LTD | Pur - T1 | PTI202324-27836 | 4200
2024-02-07 | MAHAVIR PLASTICS | Pur - T1 | 5355 | 3200
2024-02-08 | SAMRUDDHI ENGINEERS | Pur - T1 | SE/23-24/1910 | 1500
2024-02-14 | MAHAVIR PLASTICS | Pur - T1 | 5363 | 10300
2024-02-20 | DR.VINAY DHAWALE | Pur - T1 | 216 | 9000
2024-02-20 | SAMRUDDHI ENGINEERS | Pur - T1 | SE/23-24/1976 | 3000
2024-02-27 | MAHAVIR PLASTICS | Pur - T1 | 5383 | 15600
2024-02-29 | ZC RAMESH CRANE SERVICE | Pur - T1 | 852 | 73400
2024-03-01 | ZC ACE ENGINEERS & CONSULTANTS | Pur - T1 | AEC/DL/23-24/301 | 560000
2024-03-07 | DR.VINAY DHAWALE | Pur - T1 | 231 | 9000
2024-03-09 | SAMRUDDHI ENGINEERS | Pur - T1 | SE/23-24/2122 | 3000
2024-03-10 | ZC VAISHNAVI GAS | Pur - T1 | VG/MUM22-23-25 | 2361504
2024-03-11 | MAHAVIR PLASTICS | Pur - T1 | 5400 | 14650
2024-03-11 | SAMRUDDHI ENGINEERS | Pur - T1 | SE/23-24/2141 | 1500
2024-03-22 | SAMRUDDHI ENGINEERS | Pur - T1 | SE/23-24/2211 | 3000
2024-03-22 | 2Z ICICI BANK - 0689 - MERAKI ARENA(777705190689) | Payment | CMS | 8798
2024-03-29 | 2Z STATE BANK OF INDIA - 2756-ESCROW ACCOUNT ONE MERAKI WING A & WING B -30%(41125812756) | Payment | CMS | 127541
2024-03-29 | 2Z STATE BANK OF INDIA - 2756-ESCROW ACCOUNT ONE MERAKI WING A & WING B -30%(41125812756) | Payment | CMS | 2203
7273185.83

## 4T1 PRINTING & STATIONERY
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T1 PRINTING & STATIONERY
Ledger Account
1-Apr-21 to 31-Aug-22
Date |  | Vch Type | Vch No. | Debit | Credit
2021-10-20 | AMIN R RATNANI | Pur - T1 | R/34/21-22 - DEBIT NOTE | 24440
FOR SALE AGREEMENT OF GARDEN FLAT NO - B-0403/0404/0503/0504/0603/0604 - SINGIT
2022-03-31 | 22 WORK IN PROGRESS - TOWER - 1 | Journal
2022-09-10 | ZP AMIN R RATNANI(ADZPR2048F) | Pur - T1 | R/22/22-23 | 18500
2022-11-01 | AMIN R RATNANI | Pur - T1 | R/29/22-23 | 3330
46270

## 4T1 TREE CUTTING LABOUR FEES
4T1 TREE CUTTING LABOUR FEES
Ledger Account
1-Apr-22 to 31-Aug-22
Date | Particulars |  | Vch Type | Vch No. | Bank Date | Debit | Credit
2022-04-17 | To | ZC VINOD GELYE(AQEPG8039P) | Pur - T1 | P |  | 147000
B NO TREE CUTTING
2022-06-08 | To | ZC VINOD GELYE(AQEPG8039P) | Pur - T1 | P |  | 269000
TREE TRABSPLANT & CUT BILL
416000
| By | Closing Balance |  |  |  | 416000
416000 | [5 empty] | 416000

## 4T1 INSURANCE
4T1 INSURANCE
Ledger Account
1-Sep-22 to 30-Sep-22
Date |  | Vch Type | Vch No. | Debit
2022-09-27 | SBI GENERAL INSURANCE CO LTD | Pur - T1 | 80412370 | 781358
| SBI GENERAL INSURANCE CO LTD |  |  | 600000
2024-03-31 | SBI GENERAL INSURANCE CO LTD | Pur - T1 | 105185220 | 800000
2181358

## 4T1 WATER CHARGES Transport U
4T1 WATER CHARGES
Ledger Account
1-Jul-22 to 31-Aug-22
Date |  | Vch Type | Vch No. | Debit | Credit
2022-07-04 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T1 | 918 | 45600
2022-07-04 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T1 | 917 | 73950
2022-11-15 | ZC DINESH MORE | Pur - T1 | 05 | 216936
2022-11-15 | ZC DINESH MORE | Pur - T1 | 05/A | 145660
2022-11-15 | ZC DINESH MORE | Pur - T1 | 07 | 222343
2022-11-15 | ZC DINESH MORE | Pur - T1 | 08 | 87168
2022-11-15 | ZC DINESH MORE | Pur - T1 | 09 | 94640
2022-10-04 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T1 | 973 | 55200
2022-10-04 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T1 | 972 | 25500
2022-11-02 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T1 | 999 | 25500
2022-12-08 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T1 | 1048 | 55200
2023-01-25 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T1 | NE/0087/22-23 | 32960
2023-01-04 | ZC DINESH MORE(APWPM8856R) | Pur - T1 | 10 | 251608.5
2023-02-06 | ZC DINESH MORE(APWPM8856R) | Pur - T1 | 11 | 261553.5
2023-01-01 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T1 | 1077 | 21600
2023-01-01 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T1 | 1060 | 37400
2023-02-03 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T1 | 1121 | 34000
2023-02-03 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T1 | 1122 | 74400
2023-03-17 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T1 | 1145 | 36000
2023-05-02 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T1 | 1284 | 47600
2023-05-02 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T1 | 1282 | 57600
2023-04-14 | ZC DINESH MORE(APWPM8856R) | Pur - T1 | 13 | 481075
2023-08-02 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T1 | 1394 | 86700
2023-09-04 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T1 | 1461 | 59150
2023-07-28 | ZC DINESH MORE(APWPM8856R) | Pur - T1 | 15 | 171868.4
2023-08-24 | ZC DINESH MORE(APWPM8856R) | Pur - T1 | 16 | 83269
2023-08-24 | ZC DINESH MORE(APWPM8856R) | Pur - T1 | 12 | 201725
2023-07-04 | ZC PATHAK TRANSPORT(AIEPP5002B) | Pur - T1 | 01 | 182400
2023-07-04 | QADRI ENTERPRISES | Pur - T1 | 066 | 58000
2023-07-05 | DARSHAN ROADLINES PVT LTD | Pur - T1 | GTA-246/23-24 | 102300
2023-08-03 | ZC PATHAK TRANSPORT(AIEPP5002B) | Pur - T1 | 02 | 52800
2023-09-05 | ZC PATHAK TRANSPORT(AIEPP5002B) | Pur - T1 | 03 | 105600
2023-10-03 | ZC PATHAK TRANSPORT(AIEPP5002B) | Pur - T1 | 04 | 57600
2023-11-06 | ZC PATHAK TRANSPORT(AIEPP5002B) | Pur - T1 | 05 | 129200
2023-12-01 | ZC PATHAK TRANSPORT(AIEPP5002B) | Pur - T1 | 06 | 81600
2023-10-28 | ZC DAIVIK ENTERPRISES | Pur - T1 | 01 | 450060
2023-11-23 | ZC DAIVIK ENTERPRISES | Pur - T1 | 02 | 120929.25
2023-12-05 | ZC DAIVIK ENTERPRISES | Pur - T1 | 03 | 288282.5
2024-03-04 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T1 | 1602 | 58000
2024-03-04 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T1 | 1603 | 129500
2024-03-08 | SAMYAK FACILITIES | Pur - T1 | 03 | 16000
2024-01-07 | ZC DAIVIK ENTERPRISES | Pur - T1 | 04 | 274086
2024-02-27 | ZC DAIVIK ENTERPRISES | Pur - T1 | 05 | 267205
2024-03-11 | ZC DAIVIK ENTERPRISES | Pur - T1 | 06 | 166546
2024-01-01 | ZC PATHAK TRANSPORT | Pur - T1 | 07 | 187200
2024-02-05 | ZC PATHAK TRANSPORT | Pur - T1 | 08 | 158400
2024-03-06 | ZC PATHAK TRANSPORT | Pur - T1 | 09 | 355200
6227115.15

## 4T1 SECURITY SERVICES
4T1 SECURITY SERVICES
Ledger Account
1-Jan-23 to 15-Mar-23
Date |  | Vch Type | Vch No. | Debit
2023-01-31 | ZC PREMIER SECURITY SERVICES INDIA(BULPS4306R-PP) | Pur - T1 | PSS-175/2023 | 333087
2023-02-28 | ZC PREMIER SECURITY SERVICES INDIA(BULPS4306R-PP) | Pur - T1 | PSS-194/2023 | 336700
2023-03-31 | ZC PREMIER SECURITY SERVICES INDIA(BULPS4306R-PP) | Pur - T1 | PSS-213/2023 | 355600
2023-04-30 | ZC PREMIER SECURITY SERVICES INDIA(BULPS4306R-PP) | Pur - T1 | PSS-009/2023 | 343000
2023-05-31 | ZC PREMIER SECURITY SERVICES INDIA(BULPS4306R-PP) | Pur - T1 | PSS-029/2023 | 343000
2023-07-31 | ZC PREMIER SECURITY SERVICES INDIA - RCM | Pur - T1 | PSS-073/2023 | 306239
2023-08-31 | ZC PREMIER SECURITY SERVICES INDIA - RCM | Pur - T1 | PSS-098/2023 | 318800
2023-09-30 | ZC PREMIER SECURITY SERVICES INDIA - RCM | Pur - T1 | PSS-121/2023 | 305078
2023-10-31 | ZC PREMIER SECURITY SERVICES INDIA - RCM | Pur - T1 | PSS-141/2023 | 306700
2023-11-30 | ZC PREMIER SECURITY SERVICES INDIA - RCM | Pur - T1 | PSS-165/2023 | 306700
2024-01-31 | ZC PREMIER SECURITY SERVICES INDIA - RCM | Pur - T1 | PSS-208/2023-24 | 306177
2024-02-29 | ZC PREMIER SECURITY SERVICES INDIA - RCM | Pur - T1 | PSS-237/23-24 | 306700
2024-03-31 | ZC PREMIER SECURITY SERVICES INDIA - RCM | Pur - T1 | PSS-260/23-24 | 305231
4173012

## Salary
SALARY -OCT-DEC-23
49 SALARY - BASIC | 2536460
49 SALARY - HRA | 1057344
49 SALARY - OTHER | 49824
49 SALARY - BONUS | 1090728
49 SALARY - OVERTIME | 73761
Salary - Basic | 3314338
8122455

## 4T1 ADVERTISEMENT
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T1 ADVERTISEMENT
Ledger Account
1-Apr-01 to 15-Mar-23
Date |  | Vch Type | Vch No. | Debit
2022-06-29 | SATISH PANDEY | Pur - T1 | 12688 | 12000
2022-09-01 | RUTAKSHI TECHNOLOGIES PVT LTD(ABGFS9495N) | Pur - T1 | RU984202209 | 11160
2022-09-13 | RUTAKSHI TECHNOLOGIES PVT LTD(ABGFS9495N) | Pur - T1 | RU984202209A | 11284
2022-11-04 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2223004881 | 25400
2022-11-17 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2223005167 | 800
2022-11-22 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2223005264 | 10400
2022-12-01 | ZP BRIGHT BRAIN MARKETING TECHNOLOGIES LLP(AAQFB0591D) | Pur - T1 | 5860 | 162500
2022-12-09 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2223005706 | 350
2022-12-15 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2223005819 | 500
2022-12-22 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2223005967 | 500
2022-12-26 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2223005999 | 1000
2022-12-31 | ZP BRIGHT BRAIN MARKETING TECHNOLOGIES LLP(AAQFB0591D) | Pur - T1 | 5908 | 162500
2023-01-06 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2223006315 | 10400
2023-01-19 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2223006559 | 1000
2023-01-19 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2223006560 | 2000
2023-01-23 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2223006646 | 10400
2023-01-24 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2223006667 | 2000
2023-02-02 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2223006839 | 2000
2023-02-10 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2223007157 | 2000
2023-02-11 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2223007111 | 1166.2
2023-02-20 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2223007241 | 11800
2023-02-25 | CHAMPION PRINTS | Pur - T1 | S0000307 | 3600
2023-02-27 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2223007343 | 2000
2023-03-01 | CHAMPION PRINTS | Pur - T1 | S0000311 | 9000
2023-03-03 | CHAMPION PRINTS | Pur - T1 | S0000314 | 17000
2023-03-16 | ZC MASH AUDIO VISUALS PVT. LTD. | Pur - T1 | 128541 | 64000
2023-03-17 | ZC JEET PUBLICITY | Pur - T1 | 34440 | 6786.19
2023-03-29 | CHAMPION PRINTS | Pur - T1 | S0000345 | 9000
2023-04-04 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2324000086 | 11800
2023-04-04 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2324000088 | 5000
2023-04-11 | CHAMPION PRINTS | Pur - T1 | S0000011 | 10800
2023-04-12 | ZC JEET PUBLICITY | Pur - T1 | JP-48-23-24 | 93308
2023-05-16 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2324000849 | 11800
2023-05-17 | CHAMPION PRINTS | Pur - T1 | S0000037 | 1800
2023-05-04 | ZB PANKAJ S DEMBLA | Pur - T1 | 004 | 760200
2023-05-09 | 2Z PUNJAB NATIONAL BANK - 0077002102302129(0077002102302129) | Payment | SD+REG -T1-B-303 | 1338000
2023-05-09 | 2Z PUNJAB NATIONAL BANK - 0077002102302129(0077002102302129) | Payment | SD+REG -T1-B-402 | 1980000
2023-05-11 | AMIN R RATNANI | Pur - T1 | R/02/23-24 | 8680
2023-05-11 | ZP AMIN R RATNANI(ADZPR2048F) | Pur - T1 | R/03/23-24 | 15000
2023-05-18 | ZP AMIN R RATNANI(ADZPR2048F) | Pur - T1 | R/05/23-24 | 5000
2023-05-18 | AMIN R RATNANI | Pur - T1 | R/05/23-24 | 3200
2023-06-06 | 2Z STATE BANK OF INDIA - 2756-ESCROW ACCOUNT ONE MERAKI WING A & WING B -30%(41125812756) | Payment | SD+REG -T1-A-1101 | 2659000
33074780
2023-08-23 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2324002796 | 11800
2023-08-03 | ZB PANKAJ S DEMBLA | Pur - T1 | 014 | 473040
2023-07-05 | ZS AKSHAY NITIN PATANI | Journal | SD+REG -T1-B-1302 | 2807500
2023-07-05 | ZS AKSHAY NITIN PATANI | Journal | SD+REG -T1-B-1303 | 1696000
2023-07-05 | ZS AKSHAY NITIN PATANI | Journal | SD+REG -T1-B-1102 | 600
2023-07-05 | ZP AMIN R RATNANI | Pur - T1 | R/13/23-24 | 11000
2023-07-05 | ZP AMIN R RATNANI | Pur - T1 | R/14/23-24 | 20000
2023-07-05 | AMIN R RATNANI | Pur - T1 | R/14/23-24 | 14680
2023-08-04 | ZS AKSHAY NITIN PATANI | Journal | SD+REG -T1-A-1904 | 1079000
2023-08-08 | AMIN R RATNANI | Pur - T1 | R/17/23-24 | 3200
2023-08-08 | ZP AMIN R RATNANI | Pur - T1 | R/17/23-24 | 5000
2023-08-11 | ZP AMIN R RATNANI | Pur - T1 | R/20/23-24 | 9000
2023-08-11 | ZP AMIN R RATNANI | Pur - T1 | R/19/23-24 | 10000
2023-08-11 | AMIN R RATNANI | Pur - T1 | R/19/23-24 | 1040
2023-08-25 | ZS VISHAL MAHADU TAPAL | Journal | SD+REG -T1-B-1501 | 2101512
2023-08-25 | ZS VISHAL MAHADU TAPAL | Journal | SD+REG -T1-B-1502 | 2101512
2023-08-29 | ZP AMIN R RATNANI | Pur - T1 | R/25/23-24 | 10000
2023-08-29 | AMIN R RATNANI | Pur - T1 | R/25/23-24 | 6640
2023-09-07 | ZS VISHAL MAHADU TAPAL | Journal | SD+REG -T1-B-1802 | 2172012
2023-09-07 | ZS VISHAL MAHADU TAPAL | Journal | SD+REG -T1-B-1803 | 1410012
2023-09-12 | ZS VISHAL MAHADU TAPAL | Journal | SD+REG -T1-B-1801 | 2740012
2023-09-12 | AMIN R RATNANI | Pur - T1 | R/29/23-24 | 6800
2023-09-12 | ZP AMIN R RATNANI | Pur - T1 | R/29/23-24 | 10000
2023-09-15 | AMIN R RATNANI | Pur - T1 | R/30/23-24 | 3280
2023-09-15 | ZP AMIN R RATNANI | Pur - T1 | R/30/23-24 | 5000
2023-10-31 | ZC REALATEE VENTURES LLP(27AAVFR7098A1ZM) | Pur - T1 | Mum2210/RV/23-24 | 50000
2023-11-08 | ZC MILLENNIUM ADVERTISING AGENCY(ACDPT1520F) | Pur - T1 | 2023-24/MAA/36 | 493450
2023-11-18 | ZC LOCON SOLUTIONS PRIVATE LIMITED(AACCL2441D) | Pur - T1 | 27600-L-MH-2324 | 985000
2023-11-23 | ZC MAGICBRICKS REALTY SERVICES LIMITED(AAICM8228P) | Pur - T1 |  | 812999.99
2023-11-24 | ZC 99ACRES.COM - INFO EDGE INDIA LTD(AAACI1838D) | Pur - T1 | NN09I1124/005246 | 800000.12
2023-12-12 | CODE SEPTEM TECHNOLOGIES LLP | Pur - T1 | VM2024298 | 5000
2023-12-13 | CODE SEPTEM TECHNOLOGIES LLP | Pur - T1 | VM2024300 | 35000
2023-12-15 | OPTION PRINT | Pur - T1 | OP/817/23-24 | 12900
2023-12-18 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2324004881 | 141600
2023-12-18 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2324004880 | 20000
2023-10-04 | ZP AMIN R RATNANI(ADZPR2048F) | Pur - T1 | R/32/23-24 | 5000
2023-10-04 | AMIN R RATNANI | Pur - T1 | R/32/23-24 | 2000
2023-10-17 | ZS VISHAL MAHADU TAPAL(AFSPT5522M) | Journal | SD+REG -T1-A-1103 | 720012
2023-11-20 | ZS VISHAL MAHADU TAPAL(AFSPT5522M) | Journal | SD+REG -T1-A-1303 | 687512
2023-11-24 | ZS VISHAL MAHADU TAPAL(AFSPT5522M) | Journal | SD+REG -T1-A-1903 | 720012
2023-11-28 | ZS VISHAL MAHADU TAPAL(AFSPT5522M) | Journal | SD+REG -T1-B-1002 | 2762000
2023-12-01 | ZP AMIN R RATNANI(ADZPR2048F) | Pur - T1 | R/42/23-24 | 15000
2023-12-01 | AMIN R RATNANI | Pur - T1 | R/42/23-24 | 9840
2023-12-08 | 2Z PUNJAB NATIONAL BANK - 0077002102302129(0077002102302129) | Payment | SD+REG -T1-B-1102 | 2688000
2023-12-11 | AMIN R RATNANI | Pur - T1 | R/43/23-24 | 3280
2023-12-11 | ZP AMIN R RATNANI(ADZPR2048F) | Pur - T1 | R/43/23-24 | 5000
2024-01-01 | FUN BLASTERS | Pur - T1 | 01 | 15400
2024-01-22 | JIO HAPTIK TECHNOLOGIES LTD | Pur - T1 | INV-077757 | 3499
2024-01-22 | JIO HAPTIK TECHNOLOGIES LTD | Pur - T1 | INV-077950 | 4000
2024-01-29 | ZC BRIGHT OUTDOOR MEDIA LTD | Pur - T1 | BRIGHT/0124/141 | 412200
2024-01-31 | GOOGLE INDIA PVT LTD | Pur - T1 | 4906831361 | 331739.27
2024-02-01 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2324005584 | 29736
2024-02-01 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2324005608 | 5000
2024-02-19 | MDS DIGITAL MEDIA PVT LTD | Pur - T1 | MDS/61/23-24 | 21750
2024-02-19 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 |  | 4400
2024-02-20 | JIO HAPTIK TECHNOLOGIES LTD | Pur - T1 | INV-087522 | 33599
2024-02-20 | JIO HAPTIK TECHNOLOGIES LTD | Debit Note | CN-5523 | -225.75
2024-02-22 | CODE SEPTEM TECHNOLOGIES LLP | Pur - T1 | VM2024385 | 120000
2024-02-26 | ZC 99ACRES.COM - INFO EDGE INDIA LTD | Pur - T1 | NN09I0224/007884 | 400000
2024-02-29 | GOOGLE INDIA PVT LTD | Pur - T1 | 4928901256 | 110209.37
2024-03-01 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | 32402760727240301 | 39362.4
2024-03-06 | ZP INFO EDGE (INDIA) LIMITED | Pur - T1 | NN09I0324/001203 | 70000
2024-03-07 | ZC JEET PUBLICITY | Pur - T1 | JP-1497-23-24 | 133980
2024-03-08 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | 5605406721240308 | 5000
2024-03-11 | MDS DIGITAL MEDIA PVT LTD | Pur - T1 | MDS/3/23-24 | 24000
2024-03-14 | ZC REALATEE VENTURES LLP | Pur - T1 | Mum3951/RV/23-24 | 375000
2024-03-20 | CODE SEPTEM TECHNOLOGIES LLP | Pur - T1 | VM2024422 | 141000
2024-03-22 | JUST DIAL LIMITED | Pur - T1 | MH0324SN00474493 | 25000
2024-03-27 | ZC K2V2 TECHNOLOGIES PRIVATE LIMITED | Pur - T1 | K2324006617 | 4000
2024-03-31 | GOOGLE INDIA PVT LTD | Pur - T1 | 4949031831 | 28933.55
2024-02-03 | ZP AMIN R RATNANI | Pur - T1 | R/46/23-24 | 5000
2024-02-03 | AMIN R RATNANI | Pur - T1 | R/46/23-24 | 2200
2024-02-03 | AMIN R RATNANI | Pur - T1 | R/47/23-24 | 1080
2024-02-03 | ZP AMIN R RATNANI | Pur - T1 | R/47/23-24 | 5000
2024-02-03 | AMIN R RATNANI | Pur - T1 | R/48/23-24 | 1000
2024-02-05 | ZP AMIN R RATNANI | Pur - T1 | R/48/23-24 | 5000
2024-02-05 | ZP AMIN R RATNANI | Pur - T1 | R/49/23-24 | 40000
2024-02-05 | AMIN R RATNANI | Pur - T1 | R/49/23-24 | 9120
2024-02-12 | ZP AMIN R RATNANI | Pur - T1 | R/50/23-24 | 35000
2024-02-12 | ZP AMIN R RATNANI | Pur - T1 | R/51/23-24 | 5500
2024-02-12 | ZP AMIN R RATNANI | Pur - T1 | R/52/23-24 | 10000
2024-02-12 | AMIN R RATNANI | Pur - T1 | R/52/23-24 | 2400
2024-02-27 | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | SD+REG -T1-B-1602 | 1980500
2024-02-27 | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | SD+REG -T1-B-1603 | 1260500
2024-03-06 | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | SD+REG -T1-A-804 | 668000
2024-03-14 | ZP AMIN R RATNANI | Pur - T1 | R/61/23-24 | 5000
2024-03-14 | AMIN R RATNANI | Pur - T1 | R/61/23-24 | 3240
2024-03-27 | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | SD+REG -T1-A-1803 | 666000
2024-03-28 | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | SD+REG -T1-B-0401 | 2040000
2024-03-29 | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | SD+REG -T1-A-1703 | 720000
2024-03-29 | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | SD+REG -T1-B-0501 | 1479000
2024-03-29 | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | SD+REG -T1-B-0502 | 1479000
2024-03-31 | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | SD+REG -T1-B-1601 | 1806000
2024-03-31 | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | SD+REG -T1-B-1604 | 1148500
83927783.34

## Interest
|  | 102500000 |  |  |  |  | 47706212
Sr. No. | Particulars | Amount | Amount in ` Cr. | Amount | Amount in ` Cr. | Balance | Balance in Cr.
| September | 754630 | 0.075463 | 754630 | 0.075463 | 0 | 0
| October | 957837 | 0.095784 | 957837 | 0.095784 | 0
| November | 1232872 | 0.12329 | 1232872 | 0.12329 | 0
| December | 1651387 | 0.16514 | 1651387 | 0.16514 | 0
| January | 1854073 | 0.18541 | 1854073 | 0.18541 | 0
| February | 1806968 | 0.1807 | 1806968 | 0.1807 | 0
| March | 2431623 | 0.24316 | 2431623 | 0.24316 | 0
| April | 2808552 | 0.28086 | 2808552 | 0.28086 | 0
| May | 3041628 | 0.30416 | 3041628 | 0.30416 | 0
| June | 3342778 | 0.33428 | 3342778 | 0.33428 | 0
| July | 3719313 | 0.37193 | 3719313 | 0.37193
| August | 3798677 | 0.37987 | 3798677 | 0.37987
| September | 3682129 | 0.36821 | 3682129 | 0.36821
| October | 3948860 | 0.39489 | 3682129 | 0.36821
| November | 3913772 | 0.39138 | 3682129 | 0.36821
| December | 4141804 | 0.41418 | 3682129 | 0.36821
| January | 4060892 | 0.40609
| February | 3688049 | 0.3688
| March | 3957944 | 0.39579
|  | 54793788 | 5.4794 | 42128854 | 4.2129 | 0 | 0
| 102500000 | 47706212
43231
694857
16542
957837
1232872
1651387
1854073
1806968
2431623
10689390

## Construction Area of Sale Build
Summary of Cost of Construction
Plinth Area Calculation
Sr. No | Floor Nos. | Total Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | Percentage of work completed | Actual Expenditure till date in `
1 | Excavation |  |  |  | 99338862 | 100% | 95324530 | 100
2 | Basement 1 | 3392.65 | 3392.65 | 30000 | 101779500 | 90% | 91601550 | 50
3 | Basement 2 | 3392.65 | 3392.65 | 30000 | 101779500 | 90% | 91601550 | 50
4 | Basement 3 | 3392.65 | 3392.65 | 30000 | 101779500 | 90% | 91601550 | 50
5 | Ground Floor | 3986.06 | 3986.06 | 30000 | 119581800 | 90% | 107623620 | 50
6 | 1st Podium Floor | 1459.03 | 1459.03 | 30000 | 43770900 | 90% | 39393810 | 50
7 | 2nd Floor | 973.052 | 973.052 | 30000 | 29191560 | 90% | 26272404 | 100%
8 | 3rd Floor | 968.432 | 968.432 | 30000 | 29052960 | 90% | 26147664
9 | 4th Floor | 968.432 | 968.432 | 30000 | 29052960 | 90% | 26147664
10 | 5th Floor | 968.432 | 968.432 | 30000 | 29052960 | 90% | 26147664
11 | 6th Floor | 968.432 | 968.432 | 30000 | 29052960 | 90% | 26147664
12 | 7th Floor | 952.946 | 952.946 | 30000 | 28588380 | 90% | 25729542
13 | 8th Floor | 971.532 | 971.532 | 30000 | 29145960 | 90% | 26231364
14 | 9th Floor | 968.432 | 968.432 | 30000 | 29052960 | 90% | 26147664
15 | 10th Floor | 968.432 | 968.432 | 30000 | 29052960 | 90% | 26147664
16 | 11th Floor | 968.432 | 968.432 | 30000 | 29052960 | 90% | 26147664
17 | 12th Floor | 968.432 | 968.432 | 30000 | 29052960 | 90% | 26147664
18 | 13th Floor | 968.432 | 968.432 | 30000 | 29052960 | 90% | 26147664
19 | 14th Floor | 952.936 | 952.936 | 30000 | 28588080 | 90% | 25729272
20 | 15th Floor | 971.532 | 971.532 | 30000 | 29145960 | 90% | 26231364
21 | 16th Floor | 968.432 | 968.432 | 30000 | 29052960 | 90% | 26147664
22 | 17th Floor | 968.432 | 968.432 | 30000 | 29052960 | 90% | 26147664
23 | 18th Floor | 968.432 | 968.432 | 30000 | 29052960 | 90% | 26147664
24 | 19th Floor | 968.432 | 968.432 | 30000 | 29052960 | 90% | 26147664
25 | Terrace | 78.3 | 78.3 | 30000 | 2349000 | 90% | 2114100
Total |  | 33112.954 | 33112.954 |  | 1092727482 | 90.54% | 989374288
|  | 33112.95 | 32550.44 |  | 1092727482 | 74.16% | 810353095
|  | 0.004 | 562.514 | 0 | 0 | 16.38% | 179021193

## Construction Area
COST OF CONSTRUCTION WING A
Sr. No | Floor Nos. | Built Up Area in Sq. M. | Balcony/FB/ Terrace Area/ Chhajja in Sq. M. | Staircase & Lift Area in Sq. M. | Refuge Area in Sq. M. | Stlit Area in Sq. M. | Meter Room/ Electric room / DG Room area in Sq. M. | Lobby Area in Sq. M. | Other Area/ Gents Toilet/Fitness Centre in Sq. M. | Total Area in Sq. M. | Rate per Sq. M. | Full Value after completion | Percentage of work completed | Actual Expenditure till date in `
1 | Deep Excavation & Piling Working | [10 empty] | 48600444 | 100% | 48600444
2 | Basement 1 | 0 | 0 | 0 | 0 | 1631.06 | 0 | 0 | 0 | 1631.06 | 30000 | 48931800 | 66% | 32294988 | 1631.06
3 | Basement 2 | 0 | 0 | 0 | 0 | 1631.06 | 0 | 0 | 0 | 1631.06 | 30000 | 48931800 | 66% | 32294988 | 1631.06
4 | Basement 3 | 0 | 0 | 0 | 0 | 1631.06 | 0 | 0 | 0 | 1631.06 | 30000 | 48931800 | 66% | 32294988 | 1631.06
5 | Ground Floor | 0 | 0 | 71.61 | 0 | 2002.99 | 50.78 |  | 0 | 2125.38 | 30000 | 63761400 | 50% | 31880700 | 2125.38
6 | 1st Podium Floor | 75.4 | 0 | 71.61 | 0 | 0 | 0 | 0 | 517.92 | 664.93 | 30000 | 19947900 | 55% | 10971345 | 664.93
7 | 2nd Floor | 386.32 | 4.086 | 71.12 | 0 | 0 | 0 | 14.77 | 0 | 476.296 | 30000 | 14288880 | 70% | 10002216 | 238.148
8 | 3rd Floor | 381.7 | 4.086 | 71.12 | 0 | 0 | 0 | 14.77 | 0 | 471.676 | 30000 | 14150280 | 70% | 9905196
9 | 4th Floor | 381.7 | 4.086 | 71.12 | 0 | 0 | 0 | 14.77 | 0 | 471.676 | 30000 | 14150280 | 70% | 9905196
10 | 5th Floor | 381.7 | 4.086 | 71.12 | 0 | 0 | 0 | 14.77 | 0 | 471.676 | 30000 | 14150280 | 70% | 9905196
11 | 6th Floor | 381.7 | 4.086 | 71.12 | 0 | 0 | 0 | 14.77 | 0 | 471.676 | 30000 | 14150280 | 70% | 9905196
12 | 7th Floor | 270.64 | 4.086 | 71.12 | 112.62 | 0 | 0 | 0 | 3.02 | 461.486 | 30000 | 13844580 | 70% | 9691206
13 | 8th Floor | 383.25 | 4.086 | 71.12 | 0 | 0 | 0 | 14.77 | 0 | 473.226 | 30000 | 14196780 | 70% | 9937746
14 | 9th Floor | 381.7 | 4.086 | 71.12 | 0 | 0 | 0 | 14.77 | 0 | 471.676 | 30000 | 14150280 | 70% | 9905196
15 | 10th Floor | 381.7 | 4.086 | 71.12 | 0 | 0 | 0 | 14.77 | 0 | 471.676 | 30000 | 14150280 | 63% | 8914676.4
16 | 11th Floor | 381.7 | 4.086 | 71.12 | 0 | 0 | 0 | 14.77 | 0 | 471.676 | 30000 | 14150280 | 60% | 8490168
17 | 12th Floor | 381.7 | 4.086 | 71.12 | 0 | 0 | 0 | 14.77 | 0 | 471.676 | 30000 | 14150280 | 60% | 8490168
18 | 13th Floor | 381.7 | 4.086 | 71.12 | 0 | 0 | 0 | 14.77 | 0 | 471.676 | 30000 | 14150280 | 60% | 8490168
19 | 14th Floor | 297.94 | 4.086 | 71.12 | 85.32 | 0 | 0 | - | 3.02 | 461.486 | 30000 | 13844580 | 60% | 8306748
20 | 15th Floor | 383.25 | 4.086 | 71.12 | 0 | 0 | 0 | 14.77 | 0 | 473.226 | 30000 | 14196780 | 60% | 8518068
21 | 16th Floor | 381.7 | 4.086 | 71.12 | 0 | 0 | 0 | 14.77 | 0 | 471.676 | 30000 | 14150280 | 60% | 8490168
22 | 17th Floor | 381.7 | 4.086 | 71.12 | 0 | 0 | 0 | 14.77 | 0 | 471.676 | 30000 | 14150280 | 60% | 8490168
23 | 18th Floor | 381.7 | 4.086 | 71.12 | 0 | 0 | 0 | 14.77 | 0 | 471.676 | 30000 | 14150280 | 50% | 7075140
24 | 19th Floor | 381.7 | 4.086 | 71.12 | 0 | 0 | 0 | 14.77 | 0 | 471.676 | 30000 | 14150280 | 40% | 5660112
25 | Terrace | 0 | 0 | 39.15 | 0 | 0 | 0 | 0 | 0 | 39.15 | 30000 | 1174500 | 0% | 0
| Total | 6758.9 | 73.548 | 1462.53 | 197.94 | 6896.17 | 50.78 | 236.32 | 523.96 | 16200.148 |  | 534604884 | 65.17% | 348420185.4
706538455.2
COST OF CONSTRUCTION WING B
Sr. No | Floor Nos. | Built Up Area in Sq. M. | Balcony/FB/ Terrace Area/ Chhajja in Sq. M. | Staircase & Lift Area in Sq. M. | REFUGE AREA in Sq. M. | Stlit Area in Sq. M. | Meter Room/ Electric room / DG Room area in Sq. M. | Lobby Area in Sq. M. | Other Area/ Gents Toilet/Fitness Centre in Sq. M. | Total Area in Sq. M. | Rate per Sq. M. | Full Value after completion | Percentage of work completed | Actual Expenditure till date in `
1 | Deep Excavation & Piling Working | [10 empty] | 50738418 | 100% | 50738418
2 | Basement 1 | 0 | 0 | 0 | 0 | 1761.59 | 0 | 0 | 0 | 1761.59 | 30000 | 52847700 | 66% | 34879482 | 1761.59
3 | Basement 2 | 0 | 0 | 0 | 0 | 1761.59 | 0 | 0 | 0 | 1761.59 | 30000 | 52847700 | 66% | 34879482 | 1761.59
4 | Basement 3 | 0 | 0 | 0 | 0 | 1761.59 | 0 | 0 | 0 | 1761.59 | 30000 | 52847700 | 66% | 34879482 | 1761.59
5 | Ground Floor | 0 | 0 | 72.4 | 0 | 1717.52 | 70.76 | 0 | 0 | 1860.68 | 30000 | 55820400 | 50% | 27910200 | 1860.68
6 | 1st Podium Floor | 86.08 | 0 | 72.4 | 0 | 0 | 0 | 0 | 635.62 | 794.1 | 30000 | 23823000 | 55% | 13102650 | 794.1
7 | 2nd Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 30000 | 14902680 | 72% | 10729929.6
8 | 3rd Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 30000 | 14902680 | 72% | 10729929.6
9 | 4th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 30000 | 14902680 | 72% | 10729929.6
10 | 5th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 30000 | 14902680 | 72% | 10729929.6
11 | 6th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 30000 | 14902680 | 72% | 10729929.6
12 | 7th Floor | 302.21 | 2.04 | 71.12 | 112.72 | 0 | 0 | 0 | 3.37 | 491.46 | 30000 | 14743800 | 67% | 9878346
13 | 8th Floor | 414.92 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 498.306 | 30000 | 14949180 | 67% | 10015950.6
14 | 9th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 30000 | 14902680 | 67% | 9984795.6
15 | 10th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 30000 | 14902680 | 67% | 9984795.6
16 | 11th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 30000 | 14902680 | 55% | 8196474
17 | 12th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 30000 | 14902680 | 55% | 8196474
18 | 13th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 30000 | 14902680 | 55% | 8196474
19 | 14th Floor | 304.13 | 2.04 | 71.12 | 110.79 | 0 | 0 | - | 3.37 | 491.45 | 30000 | 14743500 | 55% | 8108925
20 | 15th Floor | 414.92 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 498.306 | 30000 | 14949180 | 55% | 8222049
21 | 16th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 30000 | 14902680 | 50% | 7451340
22 | 17th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 30000 | 14902680 | 50% | 7451340
23 | 18th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 30000 | 14902680 | 40% | 5961072
24 | 19th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 30000 | 14902680 | 40% | 5961072
25 | Terrace | 0 | 0 | 39.15 | 0 | 0 | 0 | 0 | 0 | 39.15 | 30000 | 1174500 | 40% | 469800
| Total | 7309.44 | 200.336 | 1464.11 | 223.51 | 7002.29 | 70.76 | 0 | 642.36 | 16912.806 |  | 558122598 | 64.16% | 358118269.8
129.3%
64.67%