8th LENDER’S INDEPENDENT ENGINEER REPORT



**Details of the property under consideration:**

**Name of Project: Ambarish CHSL**

**"Ambarish CHSL", Proposed Redevelopment of Existing Building No. 113, along with**

**Plot No. 98 (R – 3) bearing on C. T. S. No. 12 (pt), S. No. 229 & 267, MHADA Colony, Nehru Nagar, Village – Kurla III, Kurla (East), Mumbai – 400 024, State - Maharashtra, Country – India**

**Latitude Longitude: 19°03'34.7"N 72°52'55.5"E**

Intended User:

State Bank of India

SME Chembur Branch

Unit No. 11, Building No. 11, Ground Floor, Corporate Park, Sion Trombay Road,

Chembur, Mumbai, Pin Code – 400 071, State - Maharashtra, Country – India

Vastu/SBI/Mumbai/05/2024/7358/2305268

02/01-16-PY

Date: - 17.05.2024

EIGHTTH LENDER’S INDEPENDENT ENGINEER REPORT

**To,**

**State Bank of India**

SME Chembur Branch

Unit No. 11, Building No. 11,

Ground Floor, Corporate Park,

Sion Trombay Road, Chembur,

Mumbai, Pin Code – 400 071,

State - Maharashtra, Country – India

**Subject**: Construction of Residential Building "Ambarish CHSL", Proposed Redevelopment of Existing Building No. 113, along with Plot No. 98 (R – 3) bearing on C. T. S. No. 12 (pt), S. No. 229 & 267, MHADA Colony, Nehru Nagar, Village – Kurla III, Kurla (East), Mumbai – 400 024, State - Maharashtra, Country – India.

**Ref:** You’re Request for Lender’s Independent Engineer Report of under Construction Building.

**Dear Sir,**

**The Construction work as per approved plan was in progress during the site visit on 08th April 2024. Total expenditure occurred as on 31/03/2024 on this project by M/s. Peerless Constructions Pvt. Ltd. is ` 53.47 Cr. & as per CA Certificate actual total expenditure occurred as on 31/03/2024 is ` 53.16 Cr. Hence, release of Balance Amount as requested by M/s. Peerless Constructions Pvt. Ltd. is hereby recommended.**

**DECLARATION**

1. The information furnished in the report is based on our 8th site visit Dated 08.04.2024 & Document Provided by Client.
2. Vastukala 7th LIE Report of the project dated 02.03.2024.
3. I have no direct and indirect interest in the property examined for report.
4. I have not been found guilty of misconduct in my professional capacity.

**Manoj B. Chalikwar**

Registered Valuer

Chartered Engineer (India)

Reg. No. IBBI/RV/07/2018/10366

Encl.: LIE report

# Purpose & Methodology

• State Bank of India Banks and financial institutions require monitoring & an independent review of the progress of the sanctioned projects

**VCIPL** undertakes such study to independently review the progress of the project and put forward a comprehensive analysis

# Advantages:

* Assurance on present practices
* Identification of risk
* Analyzing the performance of third parties
* Recommendations

# The Methodology



**EIGHTTH LENDER’S INDEPENDENT ENGINEER REPORT**

**OF**

**"Ambarish CHSL"**

**"Ambarish CHSL", Proposed Redevelopment of Existing Building No. 113, along with Plot No. 98 (R – 3) bearing on C. T. S. No. 12 (pt), S. No. 229 & 267, MHADA Colony, Nehru Nagar, Village – Kurla III,**

**Kurla (East), Mumbai – 400 024, State - Maharashtra, Country – India.**

**Latitude Longitude: 19°03'34.7"N 72°52'55.5"E**

**NAME OF DEVELOPER: M/s. Peerless Constructions Pvt. Ltd.**

|  |
| --- |
| Pursuant to instructions from State of India, SME Chembur Branch, Chembur we have duly visited, inspected, surveyed & assessed the above said property on **08th April 2024** to determine the fair & reasonable market value of the said property/project as on Quarter ending **31st March 2024** for LIE purpose.  **1. Location Details:**  Proposed Redevelopment of Existing Building No. 113, along with Plot No. 98 (R – 3) bearing on C. T. S. No. 12 (pt), S. No. 229 & 267, MHADA Colony, Nehru Nagar, Village – Kurla III, Kurla (East), Mumbai – 400 024. It is about 800 M. walking distance from Kurla Railway station. Surface transport to the property is by buses, Auto, taxis & private vehicles. The property is in developed locality. All the amenities like shops, banks, hotels, markets, schools, hospitals, etc. are all available in the nearby locality. The locality is higher middle class & developed. |

**2. Developer Details:**

|  |  |
| --- | --- |
| **Name of builder** | **M/s. Peerless Constructions Pvt. Ltd.** |
| **Project Rera Registration Number** | **P51800027680** |
| **Registered office address** | Office No. 2, Akshat, Ram Mandir, Babhai, Borivali (West), Mumbai – 400 091, State - Maharashtra, Country – India |
| **Contact details** | **Contact Person:**  Mr. Satyakishore Singh Rathore (Company Represntative)  Mobile No. 9867827090  Mrs. Mona Mehta  Mobile No. 9820950066 |
| **E – mail ID and website** |  |

**3. Boundaries of the Property:**

|  |  |
| --- | --- |
| **Direction** | **Particulars** |
| **On or towards North** | Internal Road |
| **On or towards South** | Nalla |
| **On or towards East** | Nehru Nagar Police Station Road |
| **On or towards West** | Building No. 112 |

# Introduction

**As per Information on site M/s. Peerless Constructions Pvt. Ltd.** has acquired land by Supplementary Development Agreement Date 19.06.2017 admeasuring **area is 1,345.66 Sq. M.** bearing **Existing Building No. 113, along with Plot No. 98 (R – 3) bearing on C. T. S. No. 12 (pt), S. No. 229 & 267, MHADA Colony, Nehru Nagar, Village – Kurla III, Kurla (East), Mumbai – 400 024**. For the Proposed Residential Building.

# Area Statement:

# Land:

|  |  |  |
| --- | --- | --- |
| **Date** | **Particular** | **Area in Sq. M.** |
| 19.06.2017 | C. T. S. No. 12 (pt), S. No. 229 & 267 | 744.41 |
| Plot No. 98 (R – 3) bearing on C. T. S. No. 12 (pt), S. No. 229 & 267 | 601.25 |
| **TOTAL LAND AREA IN Sq. M.** | | **1,345.66** |

1. Copy of Lease Deed dated on 26.07.1989 b/w Maharashtra Housing and Area Development Authority (MHADA) (Lessor) and Ambarish CHSL (Lessee).
2. Copy of Development Agreement dated 26.05.2016 b/w M/s. Ambarish CHSL (The Owners / Society) And M/s. Peerless Construction Pvt. Ltd (The Developer).
3. Copy of Supplemental Development Agreement dated on 19.06.2017 b/w M/s. Ambarish CHSL (The Owners / Society) And M/s. Peerless Construction Pvt. Ltd (The Developer).
4. Copy of Power of Attorney dated on 26.05.2016 b/w M/s. Ambarish CHSL (The Owners / Society) And M/s. Peerless Construction Pvt. Ltd (The Developer).

# Building Area As per Approved Plan:

| A | Area Statement | SQ. M. |
| --- | --- | --- |
| 1a | Plot Area as Per Demarcation 27.07.2017 | 1,345.66 |
| 1b | Plot Area as Per MHADA N.O.C 18.07.2017 | 1,345.66 |
| 1c | Plot Area as Per L.S/ Architect Certificate | 1,345.66 |
| 1d | Plot Area as Per Layout (733.70+617.28) | 1,350.98 |
| 1 | Least Plot Area Consider | 1,345.66 |
| 2 | Deduction For |  |
| a | Road- Set Back Area |  |
| b | Reservation of any |  |
| c | Proposed Road |  |
| d | % Amenity Space As per D.C.P.R.56/57(sub plot) |  |
|  | Total (a + b + c + d) |  |
| 3 | Balance Area Plot (1-2) | 1,345.66 |
| 4 | Deductible Recreational Ground 15% | NIL |
| 5 | Net Plot Area | 1,345.66 |
| 6 | Addition For Floor Space Index |  |
|  | 2(a) 100% (Set-Back Area) | NIL |
|  | 2(a) 100% (D.P. Road) |
| 7 | Total Area (5+8) | 1,345.66 |
| 8 | Floor Space Index Permissible | 3.00 |
| 9 | Permissible Built-up Area | 4,036.98 |
| 10 | Add. Area Allotted by MHADA Under No | 1,252.40 |
| 11 | Total Permissible Built – Up Area | 5289.38 |
| 12 | Existing Floor Area | NIL |
| 13 | Proposed Built up Area | 5282.50 |
| 14 | Purely Residential Built-up Area | 5282.50 |
| 15 | Remaining Non-Residential Built-up Area | NIL |
| 16 | Total Built up Area Prop (12+13) | 5282.50 |
| 17 | F.S.I Consumed | 3.93 |
| B | Details of FSI Availed as per DCR35(4) | |
| 1 | Fungible BUA Component Proposed Vide 35(4) For Purely |  |
|  | Residential = OR, (16AX0.35) (4036.56X35%) | 1,848.88 |
| 2 | Fungible BUA Component Proposed DCR 35(4) For Non | NIL |
|  | Residential = OR, (16AX0.20) |
| 3 | Total Fungible BUA Vide DCR 35(4) = 1B + 2B | 1848.88 |
| 4 | Total Gross Built up Area Proposed (17+3B) | 7131.38 |
| C | Tenant Statement | |
| 1 | Proposed Area (Item A,12 above) | 7131.38 |
| 2 | Less Deduction of Non-Res, Area | NIL |
| 3 | Area of Tenements | 7131.38 |
| 4 | Tenements Permissible | 321.00 |
| 5 | Tenements Existing | 20.00 |
| 6 | Tenements Proposed | 94.00 Nos. |
| 7 | Total Tenements | 114.00 Nos. |
| D | Parking Statement | |
| 1 | Parking Required by Regulations |  |
|  | Car | 48.00 Nos |
|  | Scooter Motor cycle |  |
|  | Out (Visitors) | 1.00 Nos |
| 2 | Covered Garages Permissible | NIL |
| 3 | Covered Garages Permissible | NIL |
| 4 | Total parking Required | 48.00 |
| 5 | Total parking Provided | 50.00 |
| E | Loading & Unloading Statement |  |
| 1 | Loading & Unloading Provided | N. A |
| 2 | Total Loading & Unloading Provided | N. A |

# List of Approvals:

1. Copy of Approved Plans No. MHADA – 22/026 dated 08.01.2020 issued by Maharashtra Housing & Area Development Authority (MHADA).

Approval Upto: Ground Floor + 15 Upper Floors for built up area 5,449.36 Sq. M.

1. Copy of Revised Approved Plans No. MHADA – 22/026/2022 dated 04.05.2022 issued by Maharashtra Housing & Area Development Authority (MHADA).

Approval Upto: Ground Floor + 15 Upper Floors for built up area 7,131.38 Sq. M.

1. Copy of 1st Commencement Certificate No. EE/BP/Cell/GM/MHADA-22/026/2018 dated 15.06.2018 issued by Maharashtra Housing & Area Development Authority (MHADA).

(This CC is endorsed for the work upto Plinth Level)

1. Copy of 2nd Commencement Certificate No. EE/BP/Cell/GM/MHADA-22/026/2018 dated 30.11.2018 issued by Maharashtra Housing & Area Development Authority (MHADA).

(This CC is endorsed for the work upto Plinth Level)

1. Copy of 3rd Commencement Certificate No. EE/BP/Cell/GM/MHADA-22/026/2021 dated 22.01.2021 issued by Maharashtra Housing & Area Development Authority (MHADA).

(This CC is endorsed for the work upto Ground + 13th Upper Floors)

1. Copy of 4th Commencement Certificate No. EE/BP/Cell/GM/MHADA-22/026/2022 dated 08.04.2022 issued by Maharashtra Housing & Area Development Authority (MHADA).

(This CC is endorsed for the work upto Ground + 15th Upper Floors)

1. Copy of 5th Commencement Certificate No. MH/EE/BP/GM/MHADA-22/0026/2022/FCC/1/Amend dated 09.06.2022 issued by Maharashtra Housing & Area Development Authority (MHADA).

(This CC is endorsed for the work upto Ground + 15th Upper Floors for flat no. 1,2,3,6,7 & 8 and Ground + 15th Upper Floors for flat no. 4 & 5)

# LEVEL OF COMPLETION:

# Rehab cum Sales Building

| Sr. No. | Floor No. | Construction Area in Sq. M. | Completed Area Sq. M. | Work Completion as on 7th LIE report dated 02.03.2024 | Work Completion as on 08.04.2024 |
| --- | --- | --- | --- | --- | --- |
| 1 | Ground | 611.99 | 611.99 | Slab work is completed, Under ground water tank, Septic tank, Fire fighting tank work is in progress | Slab work, block work, plaster work, lift work, firefighting work is completed, Under ground water tank, Septic tank work is completed, Fire fighting tank work & compound wall work is in progress |
| 2 | 1st | 611.99 | 611.99 | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works are completed. Windows & Doors are installed. Electrical & plumbing installation work is don. Final santiary & electrical fitting work is pending & final finsihing is pending | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works, painting work are completed. Windows & Doors are installed. Electrical & plumbing installation work is done. Final santiary & electrical fitting work is pending & final finsihing is pending |
| 3 | 2nd | 611.99 | 611.99 | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works are completed. Windows & Doors are installed. Electrical & plumbing installation work is don. Final santiary & electrical fitting work is pending & final finsihing is pending | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works, painting work are completed. Windows & Doors are installed. Electrical & plumbing installation work is done. Final santiary & electrical fitting work is pending & final finsihing is pending |
| 4 | 3rd | 615.39 | 615.39 | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works are completed. Windows & Doors are installed. Electrical & plumbing installation work is don. Final santiary & electrical fitting work is pending & final finsihing is pending | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works, painting work are completed. Windows & Doors are installed. Electrical & plumbing installation work is done. Final santiary & electrical fitting work is pending & final finsihing is pending |
| 5 | 4th | 615.39 | 615.39 | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works are completed. Windows & Doors are installed. Electrical & plumbing installation work is don. Final santiary & electrical fitting work is pending & final finsihing is pending | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works, painting work are completed. Windows & Doors are installed. Electrical & plumbing installation work is done. Final santiary & electrical fitting work is pending & final finsihing is pending |
| 6 | 5th | 618.91 | 618.91 | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works are completed. Windows & Doors are installed. Electrical & plumbing installation work is don. Final santiary & electrical fitting work is pending & final finsihing is pending | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works, painting work are completed. Windows & Doors are installed. Electrical & plumbing installation work is done. Final santiary & electrical fitting work is pending & final finsihing is pending |
| 7 | 6th | 618.91 | 618.91 | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works are completed. Windows & Doors are installed. Electrical & plumbing installation work is don. Final santiary & electrical fitting work is pending & final finsihing is pending | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works, painting work are completed. Windows & Doors are installed. Electrical & plumbing installation work is done. Final santiary & electrical fitting work is pending & final finsihing is pending |
| 8 | 7th | 618.91 | 618.91 | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works are completed. Windows & Doors are installed. Electrical & plumbing installation work is don. Final santiary & electrical fitting work is pending & final finsihing is pending | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works, painting work are completed. Windows & Doors are installed. Electrical & plumbing installation work is done. Final santiary & electrical fitting work is pending & final finsihing is pending |
| 9 | 8th | 621.74 | 621.74 | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works are completed. Windows & Doors are installed. Electrical & plumbing installation work is don. Final santiary & electrical fitting work is pending & final finsihing is pending | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works, painting work are completed. Windows & Doors are installed. Electrical & plumbing installation work is done. Final santiary & electrical fitting work is pending & final finsihing is pending |
| 10 | 9th | 620.81 | 620.81 | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works are completed. Windows & Doors are installed. Electrical & plumbing installation work is don. Final santiary & electrical fitting work is pending & final finsihing is pending | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works, painting work are completed. Windows & Doors are installed. Electrical & plumbing installation work is done. Final santiary & electrical fitting work is pending & final finsihing is pending |
| 11 | 10th | 634.58 | 634.58 | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works are completed. Windows & Doors are installed. Electrical & plumbing installation work is don. Final santiary & electrical fitting work is pending & final finsihing is pending | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works, painting work are completed. Windows & Doors are installed. Electrical & plumbing installation work is done. Final santiary & electrical fitting work is pending & final finsihing is pending |
| 12 | 11th | 634.62 | 634.62 | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works are completed. Windows & Doors are installed. Electrical & plumbing installation work is don. Final santiary & electrical fitting work is pending & final finsihing is pending | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works, painting work are completed. Windows & Doors are installed. Electrical & plumbing installation work is done. Final santiary & electrical fitting work is pending & final finsihing is pending |
| 13 | 12th | 620.46 | 620.46 | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works are completed. Windows & Doors are installed. Electrical & plumbing installation work is don. Final santiary & electrical fitting work is pending & final finsihing is pending | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works, painting work are completed. Windows & Doors are installed. Electrical & plumbing installation work is done. Final santiary & electrical fitting work is pending & final finsihing is pending |
| 14 | 13th | 620.46 | 620.46 | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works are completed. Windows & Doors are installed. Electrical & plumbing installation work is don. Final santiary & electrical fitting work is pending & final finsihing is pending | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works, painting work are completed. Windows & Doors are installed. Electrical & plumbing installation work is done. Final santiary & electrical fitting work is pending & final finsihing is pending |
| 15 | 14th | 620.46 | 620.46 | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works are completed. Windows & Doors are installed. Electrical & plumbing installation work is don. Final santiary & electrical fitting work is pending & final finsihing is pending | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works, painting work are completed. Windows & Doors are installed. Electrical & plumbing installation work is done. Final santiary & electrical fitting work is pending & final finsihing is pending |
| 16 | 15th | 508.90 | 508.90 | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works are completed. Windows & Doors are installed. Electrical & plumbing installation work is don. Final santiary & electrical fitting work is pending & final finsihing is pending | Slab work, Blockwork, Plasterworks, Gypsum, Door frame, window frame, Kitchen paltform, Flooring, Dazoing, waterproofing, fire fighting and lift works, painting work are completed. Windows & Doors are installed. Electrical & plumbing installation work is done. Final santiary & electrical fitting work is pending & final finsihing is pending |
| 17 | Terrace | 132.41 | 132.41 | Slab work, Blockwork, Parapett wall, OHT works are completed, LMR room, Painting and Waterproofing are completed. Firefighting, water tank & lift final checking is in progress. | Slab work, Blockwork, Parapett wall, OHT works are completed, LMR room, Painting and Waterproofing are completed. Firefighting, water tank & lift final checking is completed. |
| Total | | 9,937.92 | 9,937.92 |  |  |

# Details of the Project as Financed By SBI:

# Project Cost: (as per C.A. Certificate)

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Particulars** | **Estimated Cost (in Cr.)** | **Incurred Cost**  **(In Cr.) till 31.03.2024 by**  **M/s. Ishwarlal & Co.** | **Incurred Cost**  **(In Cr.) till 31.12.2023 by**  **M/s. Ishwarlal & Co.** | **Net** |
| Land Cost & Stamp Duty | 0.77 | 3.24 | 3.24 | - |
| Rent Cost & Corpus Fund & Shifting Charges | 6.56 | 4.08 | 3.87 | 0.21 |
| Construction Cost | 25.84 | 27.60 | 26.11 | 1.49 |
| Approval Cost Of Fungible Cost & Development cess premium | 7.92 | 9.81 | 9.76 | 0.05 |
| Architect Cost, RCC & other Professional fees | 1.03 | 1.05 | 0.97 | 0.08 |
| Admin Cost | 0.78 | 1.79 | 1.77 | 0.02 |
| Marketing Cost | 1.24 | 2.53 | 2.53 | - |
| Interest Cost | 2.57 | 3.06 | 2.65 | 0.41 |
| **Total** | **46.71** | **53.16** | **50.90** | **2.26** |

* **The Builder has incurred about 4.08 Cr. as Rent Cost, 27.60 Cr. as construction cost, 9.81 Cr. for Approval cost, 1.05 Cr. for professional charges, 1.79 Cr. for admin cost & 3.06 Cr. for interest cost till 31.03.2024 as per C.A. certificate issued by M/s. Ishwarlal & Co.**

# Project Cost: (as per Bills):

|  |  |  |  |
| --- | --- | --- | --- |
| **Particulars** | **Incurred Cost (in Cr.)** | | **Net** |
| **31.03.2024 as per Bill (Inclusive GST)** | **31.12.2023 as per Bill (Inclusive GST)** |
| Land Cost & Stamp Duty | 1.31 | 1.31 | - |
| Rent Cost & Corpus Fund & Shifting Charges | 5.71 | 5.64 | 0.07 |
| Construction Cost | 27.65 | 25.67 | 1.97 |
| Approval Cost Of Fungible Cost & Development cess premium | 10.32 | 10.29 | 0.03 |
| Architect Cost, RCC & other Professional fees | 1.50 | 1.38 | 0.11 |
| Admin Cost | 1.37 | 1.31 | 0.07 |
| Marketing Cost | 2.53 | 2.53 | - |
| Interest Cost | 3.07 | 2.66 | 0.41 |
| **Total** | **53.47** | **50.80** | **2.67** |

# Land Cost:

|  |  |  |  |
| --- | --- | --- | --- |
| Sr. No. | Date | Description | Incurred Cost in ` |
| 1 | 26.05.2016 | Stamp Duty | 38,64,350.00 |
| 2 | Reg. Fees | 30,000.00 |
| 3 | 1,440.00 |
| 4 | 100.00 |
| 5 | 19.06.2017 | Stamp Duty | 37,72,350.00 |
| 6 | Reg. Fees | 30,000.00 |
| 7 | 1,960.00 |
| 8 | 100.00 |
| 9 | 07.03.2018 to 30.03.2022 | Stamp Duty Reg. Fees of Tenants Flat | 54,18,650.00 |
| Total | | | 77,00,300.00 |

*As per Developer Agreement, Supplementary Developer Agreement & Register Agreement for Tenants.*

*There is no cost incurred for land cost in this quarter.*

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Summary of Bills** | | | | | | |
| **Sr. No.** | **Particulars** | **Amount in `**  **(Till 31.03.2024)** | **Amount in `**  **(In Cr.)** | **Amount in `**  **(Till 31.12.2023)** | **Amount in `**  **(In Cr.)** | **Net in Cr.** |
| **1** | Construction Cost | 27,64,57,356.00 | 27.64 | 25,67,18,229.00 | 25.67 | 1.97 |
| **2** | Rent Cost & Corpus Fund & Shifting Charges | 5,71,05,000.00 | 5.71 | 5,64,05,000.00 | 5.64 | 0.07 |
| **2** | Premium Cost / FSI/ GOM Charges/ fees/ security Deposits | 10,32,30,444.00 | 10.32 | 10,28,92,906.00 | 10.29 | 0.03 |
| **3** | Professional Cost | 1,49,66,812.00 | 1.50 | 1,38,44,195.00 | 1.38 | 0.11 |
| **4** | Administrative Cost | 1,37,26,447.00 | 1.37 | 1,30,71,935.00 | 1.31 | 0.07 |
| **5** | Marketing Cost | 2,53,42,500.00 | 2.53 | 2,53,42,500.00 | 2.53 | - |
| **TOTAL** | | **49,08,28,559.00** | **49.08** | **45,03,91,970.00** | **45.04** | **2.26** |

Note: Bills were provided by the client up to 31.03.2024

# Interest Cost:

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Sr. No** | **Particulars** | **Estimate Amount in `** | **Incurred Amount in ` till 31.12.2023** | **Incurred Amount in ` till 31.12.2023** | **Balance Amount in `** |
| **1** | Interest Cost | 2,57,00,000.00 | 3,07,21,671.00 | 2,66,06,792.00 | -50,21,671.00 |
| **TOTAL** | | **2,57,00,000.00** | **3,07,21,671.00** | **2,66,06,792.00** | **-50,21,671.00** |

Interest Cost is based on discussion with the client.

# Cost of Construction as on 08th April 2024:

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Plinth Area Calculation | | | | | | | |
| Sr. | **Floor No.** | **Construction Area in Sq. M.** | **Completed area in Sq. M.** | **Rate per Sq. M.** | **Full Value after completion** | **Percentage of work completed** | **Actual Expenditure till date in `** |
| 1 | Ground | 611.99 | 611.99 | 26,000.00 | 1,59,11,740.00 | 80% | 1,27,29,392.00 |
| 2 | 1st | 611.99 | 611.99 | 26,000.00 | 1,59,11,740.00 | 95% | 1,51,16,153.00 |
| 3 | 2nd | 611.99 | 611.99 | 26,000.00 | 1,59,11,740.00 | 95% | 1,51,16,153.00 |
| 4 | 3rd | 615.39 | 615.39 | 26,000.00 | 1,60,00,140.00 | 95% | 1,52,00,133.00 |
| 5 | 4th | 615.39 | 615.39 | 26,000.00 | 1,60,00,140.00 | 95% | 1,52,00,133.00 |
| 6 | 5th | 618.91 | 618.91 | 26,000.00 | 1,60,91,660.00 | 95% | 1,52,87,077.00 |
| 7 | 6th | 618.91 | 618.91 | 26,000.00 | 1,60,91,660.00 | 95% | 1,52,87,077.00 |
| 8 | 7th | 618.91 | 618.91 | 26,000.00 | 1,60,91,660.00 | 95% | 1,52,87,077.00 |
| 9 | 8th | 621.74 | 621.74 | 26,000.00 | 1,61,65,240.00 | 95% | 1,53,56,978.00 |
| 10 | 9th | 620.81 | 620.81 | 26,000.00 | 1,61,41,060.00 | 95% | 1,53,34,007.00 |
| 11 | 10th | 634.58 | 634.58 | 26,000.00 | 1,64,99,080.00 | 95% | 1,56,74,126.00 |
| 12 | 11th | 634.62 | 634.62 | 26,000.00 | 1,65,00,120.00 | 95% | 1,56,75,114.00 |
| 13 | 12th | 620.46 | 620.46 | 26,000.00 | 1,61,31,960.00 | 95% | 1,53,25,362.00 |
| 14 | 13th | 620.46 | 620.46 | 26,000.00 | 1,61,31,960.00 | 95% | 1,53,25,362.00 |
| 15 | 14th | 620.46 | 620.46 | 26,000.00 | 1,61,31,960.00 | 95% | 1,53,25,362.00 |
| 16 | 15th | 508.90 | 508.90 | 26,000.00 | 1,32,31,400.00 | 95% | 1,25,69,830.00 |
| 17 | Terrace | 132.41 | 132.41 | 26,000.00 | 34,42,660.00 | 95% | 32,70,527.00 |
|  | Total | 9,937.92 | 9,937.92 |  | 25,83,85,920.00 | 94% | 24,30,79,863.00 |

##### Note: Details of work completed is as per site visit dated 08.04.2024 but report is prepared for 31st March quarter 2024.

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Particulars** | **Estimated Cost**  **(In Cr.)** | **Incurred Cost (in Cr.)** | | | **Net** |
| **As per CA till 31.03.2024** | **As per Bills upto 31.03.2024** | **As Bills upto 31.12.2023** |
| Land Cost & Stamp Duty | 0.77 | 3.24 | 1.31 | 1.31 | - |
| Rent Cost & Corpus Fund & Shifting Charges | 6.56 | 4.08 | 5.71 | 5.64 | 0.07 |
| Construction Cost | 25.84 | 27.60 | 27.65 | 25.67 | 1.97 |
| Approval Cost Of Fungible Cost & Development cess premium | 7.92 | 9.81 | 10.32 | 10.29 | 0.03 |
| Architect Cost, RCC & other Professional fees | 1.03 | 1.05 | 1.50 | 1.38 | 0.11 |
| Admin Cost | 0.78 | 1.79 | 1.37 | 1.31 | 0.07 |
| Marketing Cost | 1.24 | 2.53 | 2.53 | 2.53 | - |
| Interest Cost | 2.57 | 3.06 | 3.07 | 2.66 | 0.41 |
| **Total** | **46.71** | **53.16** | **53.47** | **50.80** | **2.67** |

Note:

As per site inspection, 94% of total work is completed, which amounts to ` 24.31 Cr. However, as per data provided by client, they have incurred the cost of ` 27.65 Cr. till 31.03.2024 which consits of advances to vendors and cost incurred for on site matertial.

# Comparison of Cost incurred on dated 31.03.2024 & 31.12.2023

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Particulars | 31.03.2024 as per Bill | 31.12.2023 as per Bill | Net | % of net amount |
| Land Cost & Stamp Duty | 1.31 | 1.31 | - | 0.00% |
| Rent Cost & Corpus Fund & Shifting Charges | 5.71 | 5.64 | 0.07 | 0.13% |
| Construction Cost | 27.65 | 25.67 | 1.97 | 3.68% |
| Approval Cost Of Fungible Cost & Development cess premium | 10.32 | 10.29 | 0.03 | 0.06% |
| Architect Cost, RCC & other Professional fees | 1.50 | 1.38 | 0.11 | 0.21% |
| Admin Cost | 1.37 | 1.31 | 0.07 | 0.13% |
| Marketing Cost | 2.53 | 2.53 | - | 0.00% |
| Interest Cost | 3.07 | 2.66 | 0.41 | 0.77% |
| Total | **53.47** | **50.80** | **2.67** | **4.98%** |

# % of Fund Utilised till 31st March 2024

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Particulars | Estimated Project Cost  (in Cr.) | Incurred cost as on 31.03.2024 | % of Incurred Cost | % of Estimated Project Cost |
| Land Cost & Stamp Duty | 0.77 | 1.31 | 170.38% | 2.81% |
| Rent Cost & Corpus Fund & Shifting Charges | 6.56 | 5.71 | 87.05% | 12.23% |
| Construction Cost | 25.84 | 27.65 | 106.99% | 59.19% |
| Approval Cost Of Fungible Cost & Development cess premium | 7.92 | 10.32 | 130.34% | 22.10% |
| Architect Cost, RCC & other Professional fees | 1.03 | 1.50 | 145.31% | 3.20% |
| Admin Cost | 0.78 | 1.37 | 175.98% | 2.94% |
| Marketing Cost | 1.24 | 2.53 | 204.38% | 5.43% |
| Interest Cost | 2.57 | 3.07 | 119.54% | 6.58% |
| Total | **46.71** | **53.47** | **114.47%** | **114.47%** |

Based on above Calculation it is found that total Project cost incurred till 31.03.2024 is 114.47% of the Total Project Cost. Project cost is over running by 14.47% and in amount 6.76 Cr.

# Means of Finance:

|  |  |  |
| --- | --- | --- |
| **Sr. No.** | **Particulars** | **Exp. Cumulative (Cr.)** |
|  | Equity share capital / Quassi Loan from Promoter including unsecured loan | 15.97 |
|  | Sales (Advance from customer) | 27.33 |
|  | Bank Laon Amount | 9.86 |
|  | **Total** | **53.16** |

The Details of the Means of Finance are provided by Client as on 31.03.2024.

# Mandatory Arrangements:

|  |  |  |
| --- | --- | --- |
| **Sr. No.** | **Particulars** | **Status** |
|  | Rainwater Harvesting | To be executed after RCC Structure |
|  | Firefighting System | To be executed after RCC Structure |
|  | Solid Waste Management | To be executed after RCC Structure |

# Quality of Construction:

|  |  |  |
| --- | --- | --- |
| **Sr. No.** | **Particulars** | **Status** |
|  | Soundness of Structures | Executing as per approved Structural Design |
|  | Look of Structures | Good |
|  | Quality of Material Used | Good |
|  | Safety Measures for Construction/labour | Taken Care by Contractor |

# Schedule V/s. Actual Progress:

| Activity | Date of Implementation | Date of Completion | Status |
| --- | --- | --- | --- |
| Land |  |  | Completed |
| Development of Land |  |  | Completed |
| Foundation Work |  |  | Completed |
| Ground Floor Slab |  | Slab work is completed |
| 1st Floor Slab |  | Slab work is completed |
| 2nd Floor Slab |  | Slab work is completed |
| 3rd Floor Slab |  |  | Slab work is completed |
| 4th Floor Slab |  | Slab work is completed |
| 5th Floor Slab |  | Slab work is completed |
| 6th Floor Slab |  | Slab work is completed |
| 7th Floor Slab |  |  | Slab work is completed |
| 8th Floor Slab |  | Slab work is completed |
| 9th Floor Slab |  | Slab work is completed |
| 10th Floor Slab |  | Slab work is completed |
| 11th Floor Slab |  | Slab work is completed |
| 12th Floor Slab |  |  | Slab work is completed |
| 13th Floor Slab |  | Slab work is completed |
| 14th Floor Slab |  | Slab work is completed |
| 15th Floor Slab |  | Slab work is completed |
| Block work /Internal Plaster work |  |  | Work is completed |
| Terrace Parapet wall / Overhead water tank / Lift Machine room / compound wall / External Plaster work |  |  | Work is completed |
| Electric Work |  |  | Work is in progress |
| Water Proofing |  |  | Work is completed |
| Plumbing Work |  |  | Work is completed |
| Tiling / Marble Flooring |  |  | Work is completed |
| Door Frames |  |  | Work is completed |
| Window Installation |  | Work is completed |
| Staircase Flooring |  |  | Work is in progress |
| Staircase Railing |  | Work is in progress |
| Refuge Area Flooring |  | Work is in progress |
| Internal Painting |  | Work is completed |
| External Painting |  | Work is in progress |
| Lift Work |  | Lift are installed |
| Fire Fighting Installation |  | Work is completed |
| Stack Parking |  | Work is in progress |
| CP Fitting & Sanitary Work |  | Work is in progress |
| Final Finishing & Fitting |  | Work is in progress |

Work schedule is not provided by the client.

# Action initiated to complete the project in time:

**For Sales Building:** Building work is completed, sanitary fitting & final finishing work is in progress

**The developers have Major work on themselves only hence (all Manpower (Labour Contractor) and material resources) shall be enhanced by the Developer to meet the TimeLine. Detail periodically progress report needs to be checked for timely completion of project.**

**Multiple activists to be done for achieving the timely progress & detail periodically bar chart is to be submitted for the further next quarter.**

# Comments related to cost overrun if any:

The cost of Rehab cum Sales Building is ` 53.47 Cr. Land Cost, Construction cost, Approval cost, Professional charges, Admin cost, Marketing cost & Interest cost are over running, take justification from client. Project cost is over running by 14.47% and in amount ` 6.76 Cr.

# Balance investment required for completion of project:

We opinion that project cost is over run by **` 6.76 Cr.** Will required more amount to complete the Project.

# Mandatory Approval Status:

| **Sr. No.** | **Particulars** | **Name of Department** | **Status** | **Order Details** |
| --- | --- | --- | --- | --- |
| **1A** | IOD of Building | Maharashtra Housing & Area Development Authority (MHADA). | Obtained and available at site | MHADA – 22/026 dated 08.01.2020. **Approval Upto**: Ground Floor + 15 Upper Floors for built up area 5,449.36 Sq. M. |
| **1B** | Revised Approved Plan | Maharashtra Housing & Area Development Authority (MHADA). | Obtained and available at site | MHADA – 22/026/2022 dated 04.05.2022 Approval Upto: Ground Floor + 15 Upper Floors for built up area 7,131.38 Sq. M. |
| **2A** | First C.C. | Maharashtra Housing & Area Development Authority (MHADA). | Obtained and available at site | EE/BP/Cell/GM/MHADA-22/026/2018 dated 15.06.2018. This CC is endorsed for the work upto Plinth Level |
| **2B** | Second C.C. | Maharashtra Housing & Area Development Authority (MHADA). | Obtained and available at site | EE/BP/Cell/GM/MHADA-22/026/2018 dated 30.11.2018. This CC is endorsed for the work upto Plinth Level |
| **2C** | Third C.C. | Maharashtra Housing & Area Development Authority (MHADA). | Obtained and available at site | EE/BP/Cell/GM/MHADA-22/026/2021 dated 22.01.2021. This CC is endorsed for the work upto Ground + 13th Upper Floors |
| **2D** | Fourth C.C. | Maharashtra Housing & Area Development Authority (MHADA). | Obtained and available at site | EE/BP/Cell/GM/MHADA-22/026/2022 dated 08.04.2022. This CC is endorsed for the work upto Ground + 15th Upper Floors |
| **2E** | Fifth C.C. | Maharashtra Housing & Area Development Authority (MHADA). | Obtained and available at site | MH/EE/BP/GM/MHADA-22/0026/2022/FCC/1/Amend dated 09.06.2022). This CC is endorsed for the work upto Ground + 15th Upper Floors for flat no. 1,2,3,6,7 & 8 and Ground + 15th Upper Floors for flat no. 4 & 5 |
| **3B** | Occupancy | Maharashtra Housing & Area Development Authority (MHADA). | Pending (Project is not completed) |  |

# Status Insurance Coverage:

Information not provided

# Assumptions & Remarks:

* The adequacy of Engineering / Structural design is beyond the scope of our assignment.
* Estimated project completion dated 30/06/2025 for Rehab cum Sales Building, respectively. The cost is certified based on the assumptions that the project will be completed within period. Few assumptions were made regarding inflation & cost rise etc. during construction period.

**Manoj B. Chalikwar**

Registered Valuer

Chartered Engineer (India)

Reg. No. IBBI/RV/07/2018/10366

**About the Project:**

|  |  |  |
| --- | --- | --- |
| **1. Introduction** | |  |
| a) | Project Name  (With Address & Phone Nos.) | **"Ambarish CHSL",** Proposed Redevelopment of Existing Building No. 113, along with Plot No. 98 (R – 3) bearing on C. T. S. No. 12 (pt), S. No. 229 & 267, MHADA Colony, Nehru Nagar, Village – Kurla III, Kurla (East), Mumbai – 400 024, State - Maharashtra, Country – India  Contact Person:  Mr. Satyakishore Singh Rathore (Company Represntative)  Mobile No. 9867827090  Mrs. Mona Mehta  Mobile No. 9820950066 |
| b) | Purpose of Valuation | As per request from State Bank of India, SME Chembur Branch to assess fair market value of the Project for LIE purpose. |
| c) | Date of Inspection of Property | 08.04.2024 |
| d) | Date of LIE Report | 17.05.2024 |
| e) | Name of the Developer of Property  (in case of developer built properties) | M/s. Peerless Constructions Pvt. Ltd.  Office No. 2, Akshat, Ram Mandir, Babhai, Borivali (West), Mumbai – 400 091, State - Maharashtra, Country – India |
| **2. Physical Characteristics of the Property** | | |
| a) | Location of the Property | **"Ambarish CHSL",** Proposed Redevelopment of Existing Building No. 113, along with Plot No. 98 (R – 3) bearing on C. T. S. No. 12 (pt), S. No. 229 & 267, MHADA Colony, Nehru Nagar, Village – Kurla III, Kurla (East), Mumbai – 400 024, State - Maharashtra, Country – India |
| Brief description of the property |  |
|  | **TYPE OF THE BUILDING**   1. **Rehab cum Sales Building**  |  |  | | --- | --- | | No. of Floors | Ground Floor + 1st to 15th Residential Floor | | Building type | Residential Rehab cum Sale building |   Rehab cum Sales Building work is given on contract based for RCC contract. Developer has grant to the contractor do the work of construction and completion includes Concrete work, Reinforcement work, Masonry, Internal Plaster, External Plaster and other miscellaneous work such as repairing, joints b/w concrete and masonry surface, etc. Bill must be paid on measurement of construction area inclusive of Steel & Cement Material.  Lift & lift installation contract is not finalized till now.  Firefighting work contract is not finalized.  **PROPOSED DATE OF COMPLETION & FUTURE LIFE:**  Expected completion date as per RERA is 30th June 2025 | |
|  | Nearby landmark | Near MHADA Colony, Nehru Nagar |
| Postal Address of the Property | **"Ambarish CHSL",** Proposed Redevelopment of Existing Building No. 113, along with Plot No. 98 (R – 3) bearing on C. T. S. No. 12 (pt), S. No. 229 & 267, MHADA Colony, Nehru Nagar, Village – Kurla III, Kurla (East), Mumbai – 400 024, State - Maharashtra, Country – India. |
|  | Area of the plot/land  (Supported by a plan) | Plot Area: 1,345.66 Sq. M. |
| Type of Land: Solid, Rocky, Marsh land, reclaimed land, Water-logged, Land locked. | Solid land |
|  | Independent access/approach to the property etc. | Yes |
| Google Map Location of the Property with a neighborhood layout map | Provided |
|  | Details of roads abutting the property | 18.00 Mt. wide Road |
| Description of adjoining property | Located in Higher Middle-class locality |
| Plot No. Survey No. | Plot No. 98 (R – 3) bearing on C. T. S. No. 12 (pt), S. No. 229 & 267 |
| Ward/Village/Taluka | Village – Kurla III, Taluka – Kurla |
| Sub-Registry/Block | Kurla – 1 |
| District | District – Mumbai Suburban |
| b) | **Boundaries of the Plot** |  |
|  | |  |  |  |  | | --- | --- | --- | --- | |  | **As per Agreement** | **As per RERA Certificate** | **Actual** | | **North** | 12. Mtr. wide Road | 12 Mtr wide road | Internal Road | | **South** | Existing Nalla | Nalla | Nalla | | **East** | Building No. 114 & 15.50 Mtr. wide Road | 15 Mtr wide road | Nehru Nagar Police Station Road | | **West** | Building No. 112 | Open | Building No. 112 | | |

| **4. Document Details and Legal Aspects of Property:** | |
| --- | --- |
| a) | Ownership Documents (**Building Permission, Commencement Certificate & Status of Plan)** |
|  | Sale Deed, Gift Deed, Lease Deed |
| 1. Copy of Development Agreement dated 26.05.2016 b/w M/s. Ambarish CHSL (The Owners / Society) And M/s. Peerless Construction Pvt. Ltd (The Developer) |
| 1. Copy of Supplemental Development Agreement dated on 19.06.2017 b/w M/s. Ambarish CHSL (The Owners / Society) And M/s. Peerless Construction Pvt. Ltd (The Developer) |
| 1. Copy of Lease Deed dated on 26.07.1989 b/w Maharashtra Housing and Area Development Authority (MHADA)(Lessor) and Ambarish CHSL (Lessee) |
| 1. Copy of Power of Attorney dated on 26.05.2016 b/w M/s. Ambarish CHSL (The Owners / Society) And M/s. Peerless Construction Pvt. Ltd (The Developer) |
| 1. Copy of General Power of Attorney dated on 19.06.2017 |
| 1. Copy of MHADA Offer Letter No. CO/MB/REE/NOC/F-505/361/2017 dated on 20.03.2017 issued by Maharashtra Housing and Development Authority |
| 1. Copy of 1st Commencement Certificate No. EE/BP/Cell/GM/MHADA-22/026/2018 dated 15.06.2018 issued by Maharashtra Housing & Area Development Authority (MHADA).   (This CC is endorsed for the work upto Plinth Level) |
| 1. Copy of 2nd Commencement Certificate No. EE/BP/Cell/GM/MHADA-22/026/2018 dated 30.11.2018 issued by Maharashtra Housing & Area Development Authority (MHADA).   (This CC is endorsed for the work upto Plinth Level) |
| 1. Copy of Approved Plans No. MHADA – 22/026 dated 08.01.2020 issued by Maharashtra Housing & Area Development Authority   Approval Upto: Ground Floor + 15 Upper Floors for built up area 5,449.36 Sq. M. |
| 1. Copy of Concessions Drawing issued by M/s. S. B. Associates   Approval Upto: Ground Floor + 15 Upper Floors for built up area 7,133.19 Sq. M. |
| 1. Copy of RERA Form 3 issued by M/s. Ishwarlal & Company. |
| 1. Copy of CA Certificate dated 30.11.2021 issued by M/s. Ishwarlal & Company. |
| 1. Copy of RERA Certificate No. P51800027680 dated 08.09.2021 issued by Maharashtra Real Estate Regulatory Authority. |
| 1. Copy of Architect Certificate dated 16.12.2021 issued by M/s. S.B Associates. |
| 1. Copy of 3rd Commencement Certificate No. EE/BP/Cell/GM/MHADA-22/026/2021 dated 22.01.2021 issued by Maharashtra Housing & Area Development Authority (MHADA).   (This CC is endorsed for the work upto Ground + 13th Upper Floors) |
| 1. Copy of 4th Commencement Certificate No. EE/BP/Cell/GM/MHADA-22/026/2022 dated 08.04.2022 issued by Maharashtra Housing & Area Development Authority (MHADA).   (This CC is endorsed for the work upto Ground + 15th Upper Floors) |
| 1. Copy of Engineer Certificate dated 28.01.2022 issued by Mr. Sandeep S. Samel. |
| 1. Copy of CA Certificate dated 30.04.2022 issued by M/s. Ishwarlal & Company. |
| 1. Copy of Bill till 31.03.2022 |
| 1. Copy of CA Certificate dated 03.11.2022 issued by M/s. Ishwarlal & Company |
| 1. Copy of Bills from 01.04.2022 to 30.09.2022 |
| 1. Copy of Revised Approved Plans No. MHADA – 22/026/2022 dated 04.05.2022 issued by Maharashtra Housing & Area Development Authority (MHADA).   Approval Upto: Ground Floor + 15 Upper Floors for built up area 7,131.38 Sq. M. |
| 1. Copy of 5th Commencement Certificate No. MH/EE/BP/GM/MHADA-22/0026/2022/FCC/1/Amend dated 09.06.2022 issued by Maharashtra Housing & Area Development Authority (MHADA).   (This CC is endorsed for the work upto Ground + 15th Upper Floors for flat no. 1,2,3,6,7 & 8 and Ground + 15th Upper Floors for flat no. 4 & 5) |
| 1. Copy of CA Certificate dated 14.01.2023 issued by M/s. Ishwarlal & Company |
| 1. Copy of Bills from 01.10.2022 to 31.12.2022 |
| 1. Copy of CA Certificate dated 19.06.2023 issued by M/s. Ishwarlal & Company |
| 1. Copy of Bills from 01.01.2023 to 31.03.2023 |
| 1. Copy of CA Certificate dated 19.06.2023 issued by M/s. Ishwarlal & Company |
| 1. Copy of Bills from 01.04.2023 to 30.06.2023 |
| 1. Copy of CA Certificate dated 12.10.2023 issued by M/s. Ishwarlal & Company |
| 1. Copy of Bills from 01.07.2023 to 30.09.2023 |
|  | 1. Copy of CA Certificate dated 24.02.2024 issued by M/s. Ishwarlal & Company |
| 1. Copy of Bills from 01.10.2023 to 31.12.2023 |

|  |  |
| --- | --- |
| b) | **Documents verified for present LIE report** |
|  | 1. Copy of CA Certificate incurred till dated 31.03.2024 issued by M/s. Ishwarlal & Company |
| 1. Copy of Bills from 01.01.2024 to 31.03.2024 |
|  | 1. Copy of Architect Certificate dated 12.03.2024 issued by M/s. SB Associates. |

**Actual Site Photographs as on 08.04.2024**



**Actual Site Photographs as on 08.04.2024**





**Actual Site Photographs as on 08.04.2024**



**Actual Site Photographs as on 08.04.2024**



**Actual Site Photographs as on 08.04.2024**




**Actual Site Photographs as on 08.04.2024**






**Route Map of the property**


**Site u/r**





## Latitude Longitude: 19°03'34.7"N 72°52'55.5"E

Note: The Blue line shows the route to site from nearest railway station (Kurla – 800 M.)

**CA Certificate Cost Incurred Till 31.03.2024**