## Final Summary
Project expenses | Estimated Cost | Incurred Cost as per Bill till 31.03.2024 | Incurred Cost as per Bill till 31.12.2023 | Incurred Cost as per CA till 31.03.2024 | Incurred Cost as per CA till 31.12.2023 | Difference between both Bills | Difference between both CA | Difference between Bills & CA | Remark
Land Cost & Stamp Duty | 0.77 | 1.3119 | 1.3119 | 3.24 | 3.24 | 0 | 0 | -1.9281
Rent Cost & Corpus Fund & Shifting Charges | 6.56 | 5.7105 | 5.6405 | 4.08 | 3.87 | 0.07 | 0.21 | 1.6305
Construction Cost | 25.84 | 27.6457 | 25.6718 | 27.6 | 26.11 | 1.9739 | 1.49 | 0.045736
Approval Cost Of Fungible Cost & Development cess premium | 7.92 | 10.323 | 10.2893 | 9.81 | 9.76 | 0.033754 | 0.05 | 0.51304
Architect Cost, RCC & other Professional fees | 1.03 | 1.4967 | 1.3844 | 1.05 | 0.97 | 0.11226 | 0.08 | 0.44668
Admin Cost | 0.78 | 1.3726 | 1.3072 | 1.79 | 1.77 | 0.065451 | 0.02 | -0.41736
Marketing Cost | 1.24 | 2.5343 | 2.5343 | 2.53 | 2.53 | 0 | 0 | 0.00425
Interest Cost | 2.57 | 3.0722 | 2.6607 | 3.06 | 2.65 | 0.41149 | 0.41 | 0.012167
Total Cost | 46.71 | 53.4669 | 50.8001 | 53.16 | 50.9 | 2.6669 | 2.26 | 0.30692
|  | -6.7569 | -6.7569
Particulars | Revised Estimated Cost (in Cr.) | 31.03.2024 as per Bill Tally (inclusive of GST) | Cost incurred as %age total cost of that Component | Cost incurred as %age of cost incurred as on 31.03.2024
Land Cost & Stamp Duty | 0.77 | 1.3119 | 170.4% | 2.809%
Rent Cost & Corpus Fund & Shifting Charges | 6.56 | 5.7105 | 87.05% | 12.23%
Construction Cost | 25.84 | 27.6457 | 107% | 59.19%
Approval Cost Of Fungible Cost & Development cess premium | 7.92 | 10.323 | 130.3% | 22.1%
Architect Cost, RCC & other Professional fees | 1.03 | 1.4967 | 145.3% | 3.204%
Admin Cost | 0.78 | 1.3726 | 176% | 2.939%
Marketing Cost | 1.24 | 2.5343 | 204.4% | 5.425%
Interest Cost | 2.57 | 3.0722 | 119.5% | 6.577%
Total Cost | 46.71 | 53.4669 | 114.5% | 114.5%
Pariculars | 31.03.2024 as per Bill Tally (inclusive of GST) | 31.12.2023 as per Bill Tally (inclusive of GST) | Difference b/w bills of 31.03.2024 & 31.12.2023 | Difference of Cost incurred as %age of cost incurred as on 31.03.2024 & 31.12.2023
Land Cost & Stamp Duty | 1.3119 | 1.3119 | 0 | 0%
Rent Cost & Corpus Fund & Shifting Charges | 5.7105 | 5.6405 | 0.07 | 0.1309%
Construction Cost | 27.6457 | 25.6718 | 1.97 | 3.685%
Approval Cost Of Fungible Cost & Development cess premium | 10.323 | 10.2893 | 0.03 | 0.05611%
Architect Cost, RCC & other Professional fees | 1.4967 | 1.3844 | 0.11 | 0.2057%
Admin Cost | 1.3726 | 1.3072 | 0.07 | 0.1309%
Marketing Cost | 2.5343 | 2.5343 | 0 | 0%
Interest Cost | 3.0722 | 2.6607 | 0.41 | 0.7668%
Total Cost | 53.4669 | 50.8001 | 2.66 | 4.975%

## Summary Sheet
Sr. No. | Particulars | Incurred Cost in ` till 31.03.2024 | Incurred Cost in ` Cr. Till 31.03.2024 | Incurred Cost in ` till 31.12.2023 | Incurred Cost in ` Cr. Till 31.12.2023 | Net in Cr.
1 | Land Cost | 13118950 | 1.3119 | 13118950 | 1.3119 | 0
2 | Rent | 57105000 | 5.7105 | 56405000 | 5.6405 | 0.07
3 | Construction Cost | 276457356 | 27.6457 | 256718229 | 25.6718 | 1.9739
4 | Approval Cost | 103230444 | 10.323 | 102892906 | 10.2893 | 0.033754
5 | Professional Cost | 14966812 | 1.4967 | 13844195 | 1.3844 | 0.11226
6 | Admin Cost | 13726447 | 1.3726 | 13071935 | 1.3072 | 0.065451
7 | Marketing Cost | 25342500 | 2.5343 | 25342500 | 2.5343 | 0
8 | Interest Cost | 30721671 | 3.0722 | 26606792 | 2.6607 | 0.41149
| Total | 534669180 | 53.4669 | 508000507 | 50.8001 | 2.6669
|  | 25700000 |  | 14700000
|  | -5021671 |  | -16021671
4114879

## Land & Approval Cost
Land Cost Description |  |  |  |  | Approval Cost
Sr. No. | Date | Description | Total Cost | Incurred Cost | Date |  | Vch Type | Vch No. | Debit
1 | 26.05.2016 | Stamp Duty | 3864350 | 3864350 | 2021-12-18 | IDBI Rera A/c Ambrish | Payment | 457 | 122058
2 |  | Reg. Fees | 30000 | 30000 |  | issued cheque 796309 to Account Officer Mhada on a/c payment lease Rent Ambarish Soc
3 |  |  | 1440 | 1440 | 2021-12-18 | IDBI Rera A/c Ambrish | Payment | 458 | 122316
4 |  |  | 100 | 100 |  | issued cheque 796310 for Payment to Account Officer Mhada Mumbai Board on a/c lease Rent
| 2017 | Stamp Duty | 3772350 | 3772350 | 2021-12-28 | IDBI Rera A/c Ambrish | Payment | 472 | 19796
|  | Reg. Fees | 30000 | 30000 |  | paid by cheque 796315 on a/c Rent instalment
|  |  | 1960 | 1960 | 2021-12-28 | IDBI Rera A/c Ambrish | Payment | 473 | 75050
|  |  | 100 | 100 |  | being amt paid 796318 on a/c Rent charges Kurla
Total |  |  | 7700300 | 7700300 | 2022-01-17 | IDBI Rera A/c Ambrish | Payment | 510 | 351810
| 2018-03-07 | IDBI Bank |  | 243700 |  | being amt issued by cheque 806482 on a/c pest control payment
|  | issued cheque 094268 & 094271 to S.G.Bokil on a/c Registration Flat |  |  | 2022-01-18 | IDBI Rera A/c Ambrish | Payment | 514 | 47600
| 2018-03-07 | IDBI Bank |  | 169200 |  | paid by cheque 806483 on a/c Water Charges paid
|  | paid by cheque 094270 to Sudha Chaubey on a/c Registration of Flat |  |  | 2022-01-29 | IDBI Rera A/c Ambrish | Payment | 540 | 2181306
| 2018-03-07 | IDBI Bank |  | 243700 |  | being amt paid by cheque 806486 on a/cMhada Charges
|  | issued cheque 094272 & 094277 to Vinod kamat |  |  | 2022-01-29 | IDBI Rera A/c Ambrish | Payment | 541 | 4275093
| 2018-03-07 | IDBI Bank |  | 169200 |  | being amt paid by cheque 806487 on a/c MCGM Charges
|  | paid by cheque 094275 to Dinesh Pandya |  |  | 2022-01-29 | IDBI Rera A/c Ambrish | Payment | 542 | 1583321
| 2018-03-07 | IDBI Bank |  | 161500 |  | being amt issued for MCGM charges
|  | paid by cheque 094276 to Prakashrao on a/c Registration |  |  | 2022-01-31 | IDBI Rera A/c Ambrish | Payment | 548 | 11657200
| 2018-03-09 | IDBI Bank |  | 247600 |  | being amt paid by RTGS for Mhada charges
|  | issued cheque 094278 & 094279 on a/c payment Maya Bhatia |  |  | 2022-02-08 | State Bank of India(A/c 40740926519) CC A/c | Payment | 574 | 1462136
| 2018-03-09 | IDBI Bank |  | 243700 |  | paid by cheque No 890826 on a/c property Tax for Ambarish upto March-21
|  | issued cheque 094280 & 094281 for Radhakrishan bh |  |  | 2022-03-04 | State Bank of India(A/c 40740926519) CC A/c | Payment | 713 | 1035485
| 2018-03-09 | IDBI Bank |  | 202500 |  | being amt online transfer Development charges
|  | issued cheque 094282 to Avinash Fulari |  |  | 2022-03-12 | State Bank of India(A/c 40740926519) CC A/c | Payment | 734 | 1462136
| 2018-03-09 | IDBI Bank |  | 209500 |  | being amt paid by cheque 890841 to MCGM On a/c property Tax 31.3.22
|  | paid by cheque 094283 to Prabha Patil |  |  | 2022-03-22 | State Bank of India(A/c 40740926519) CC A/c | Payment | 745 | 496328
| 2018-03-09 | IDBI Bank |  | 169200 |  | being amt issued by cheque 890839 for payorder for lease ent 1.10.21 to 31.3.22
|  | paid by cheque 094285 to Ranbir Thakur |  |  | 2022-03-25 | State Bank of India(A/c 40740926519) CC A/c | Payment | 751 | 59500
| 2018-03-12 | IDBI Bank |  | 209500 |  | being amt paid by cheque 890845 on water charges
|  | paid by cheque 094284 Sunil Gaokar |  |  | 2017-02-25 | HDFC Bank Ambrish | Payment | 151 | 1078371
| 2018-03-12 | IDBI Bank |  | 251700 |  | Ch. No. :issued cheque 00004 to Cheif account Officer on a/c Payment of Mahada
|  | paid by cheque 094286 & 094287 to Baidanath Ghara |  |  | 2017-03-29 | HDFC Bank Ambrish | Payment | 164 | 1658965
| 2018-03-12 | IDBI Bank |  | 243700 |  | Ch. No. :issued cheque 00005 to Cheif Account Office on a/c Payment for B.P. Charges
|  | issued cheque 094288 & 094289 to Purnima Yadav |  |  | 2017-04-04 | HDFC Bank Ambrish | Payment | 3 | 19520
| 2018-03-12 | IDBI Bank |  | 243700 |  | Ch. No. :issued cheque 00007 on a/c payment of MCGM Charges
|  | issued cheque 094290 & 094291 to Manohar Parab |  |  | 2017-04-06 | HDFC Bank Ambrish | Payment | 4 | 12361.72
| 2018-03-27 | IDBI Bank |  | 200000 |  | Ch. No. :issued cheque 00008 on a/c MCGM Charges
|  | paid by cheque 094292 on a/c SD+ Registration Mukesh Bharukha |  |  | 2017-04-06 | HDFC Bank Ambrish | Payment | 5 | 12361.72
| 2018-03-27 | IDBI Bank |  | 209500 |  | Ch. No. :being chrages paid by chyeque 00009
|  | paid by cheque 094293 Nikhil |  |  | 2017-05-04 | HDFC Bank Ambrish | Payment | 21 | 39080
| 2018-03-27 | IDBI Bank |  | 209500 |  | Ch. No. :paid by cheque 00011 on a/c MCGM
|  | paid by chqeue 094294 to Vishwanathan Shatri |  |  | 2017-06-23 | Cash in Hand | Payment | 46 | 6750
| 2018-03-27 | IDBI Bank |  | 209500 |  | paid in cash for search Report
|  | paid by cheque 094295 to Savion Dalima |  |  | 2017-07-05 | HDFC Bank Ambrish | Payment | 56 | 6239841
| 2018-03-27 | IDBI Bank |  | 128500 |  | Ch. No. :issued cheque 00018, 000015 & 000017 on a/c Various Exp of Ambrish Project
|  | PAID BY CHEQUE 094296 cHANDUR'S FLAT |  |  | 2017-11-29 | HDFC Bank Ambrish | Payment | 101 | 404200
| 2018-03-27 | IDBI Bank |  | 326000 |  | issued cheque 000022 to Payorder CFO Payment
|  | paid by cheque 094297 to Chandure |  |  | 2017-12-01 | HDFC Bank Ambrish | Payment | 104 | 10680
| 2018-03-27 | IDBI Bank |  | 301000 |  | paid by cheque 00023 for Scutiny fees paid
|  | paid by chque 094298 on a/c Digmaber Naik Flat |  |  | 2018-01-09 | IDBI Bank | Payment | 124 | 33500
| 2018-03-27 | IDBI Bank |  | 91250 |  | being amt paid by cheque ,262,263 & 264 for S.D & Registration
|  | paid by cheque 094299 on a/c Digmber Naik |  |  | 2018-02-03 | HDFC Bank Ambrish | Payment | 137 | 646400
| 2022-03-30 | Stamp Duty Charges |  | 367500 |  | paid by Cheque 00024,25,26,27,28 &29 on a/c Various Charges
|  | Amount paid for Flat no 1403 |  |  | 2018-03-07 | HDFC Bank Ambrish | Payment | 158 | 920
| 2022-03-30 | Stamp Duty Charges |  | 367500 |  | issued cheque 000035 on a/c MCGM Charges
|  | Amount paid for Flat no 1402 |  |  | 2018-03-27 | HDFC Bank Ambrish | Payment | 185 | 49200
TOTAL STAMP DUTY PAID AGAINST FLAT |  |  |  | 5418650 |  | issued cheque 00040 on a/c various Exp ambrish
[5 empty] | 2018-05-03 | HDFC Bank Ambrish | Payment | 40 | 3100
Total Land Cost |  |  |  | 13118950 |  | paid by cheque 000047 on a/c MCGM Charges
[5 empty] | 2018-05-03 | HDFC Bank Ambrish | Payment | 41 | 7810
paid by cheque 000048
[5 empty] | 2018-06-26 | HDFC Bank Ambrish | Payment | 91 | 65900
paid by cheque 000279 in the name of brihanmumbai mahanagarpalika
[5 empty] | 2018-07-02 | HDFC Bank Ambrish | Payment | 106 | 44410
issued cheque 199194 on a/c MCGM Charges
[5 empty] | 2018-08-04 | HDFC Bank Ambrish | Payment | 156 | 1237755
issued cheque payorder 000114 for Asstt Account Officer
[5 empty] | 2018-10-20 | HDFC Bank Ambrish | Payment | 351 | 147200
paid by cheque 000177 Payorder Renewal
[5 empty] | 2018-10-20 | HDFC Bank Ambrish | Payment | 352 | 13794
paid by cgheque 000178 HDFC Property Tax 1,4,18 to 31.3.19
[5 empty] | 2018-10-25 | HDFC Bank Ambrish | Payment | 357 | 82000
issued cheque 000182 & 183 on a/c Renewal on Tree Plantation
[5 empty] | 2018-12-27 | HDFC Bank Ambrish | Payment | 476 | 50000
issued cheque 000257 on a/c payment Drinking Water Connection
[5 empty] | 2019-01-16 | HDFC Bank Ambrish | Payment | 504 | 50000
issued cheque payorder 000266 For DeeWatering permission
[5 empty] | 2019-02-05 | HDFC Bank Ambrish | Payment | 557 | 72520
paid by cheque 000257 0n a/c litigation charges
[5 empty] | 2019-02-05 | HDFC Bank LTD | Payment | 558 | 460685.8
being amt transfer
[5 empty] | 2019-03-16 | HDFC Bank Ambrish | Payment | 665 | 1510002
issued cheque000291 on Vaerios Mhada Charges
[5 empty] | 2019-07-26 | HDFC Bank Ambrish | Payment | 245 | 3300
being amt paid by cheque 000415 on a/c revalidation C.C.Charges
[5 empty] | 2019-11-07 | HDFC Bank Ambrish | Payment | 455 | 95200
paid by cheque 000469 on a/c water charges
[5 empty] | 2020-01-03 | HDFC Bank Ambrish | Payment | 577 | 135500
issued cheque 000503 for Scrutiny fees
[5 empty] | 2020-01-03 | HDFC Bank Ambrish | Payment | 578 | 58700
paid by cheque 000504 I>O>A Dep[osit
[5 empty] | 2020-01-03 | HDFC Bank Ambrish | Payment | 579 | 45000
paid by cheque 000505 debris Deposit
[5 empty] | 2020-01-03 | HDFC Bank Ambrish | Payment | 580 | 552410
paid by cheque 000506 on a/c 10% funjible 50% Premium MCGM Share
[5 empty] | 2020-01-03 | HDFC Bank Ambrish | Payment | 581 | 3314500
paid by cheque 000507 on a/c 30% Premium Govt Share
[5 empty] | 2020-01-03 | HDFC Bank Ambrish | Payment | 582 | 2209700
paid by cheque 000509 on a/c 20% Prem MSRDC Share
[5 empty] | 2020-01-03 | HDFC Bank Ambrish | Payment | 583 | 216190
paid by cheque 000510 on a/c 10% Staircase premium
[5 empty] | 2020-01-03 | HDFC Bank Ambrish | Payment | 584 | 43500
paid by cheque 000511 on a/c Deficiency in Chowk payment
[5 empty] | 2020-01-10 | HDFC Bank Ambrish | Payment | 600 | 3410
issued cheque 000525 on a/c Renewal of HE Noc
[5 empty] | 2020-01-18 | HDFC Bank Ambrish | Payment | 612 | 273630
paid by cheque 000527 on a/c Pest Control Charges
[5 empty] | 2020-01-20 | HDFC Bank Ambrish | Payment | 615 | 1854974
paid by cheque 000258 on a/c Extra Swerage charges paid
[5 empty] | 2020-01-20 | HDFC Bank Ambrish | Payment | 616 | 11900
paid by cheque 000529 on a/c water charges paid
[5 empty] | 2020-02-07 | HDFC Bank Ambrish | Payment | 652 | 10115200
issued cheque 000536 on a/c Development charges
[5 empty] | 2020-02-07 | HDFC Bank Ambrish | Payment | 653 | 1498800
issued cheque 000357 on a/c Labour cess Payment
[5 empty] | 2020-02-07 | HDFC Bank Ambrish | Payment | 654 | 583730
paid by cheque 000538 on a/c 10% Open space deficiency premium
[5 empty] | 2020-02-18 | HDFC Bank Ambrish | Payment | 697 | 11900
paid by cheque 000542 MCGM on a/c payment water bills
[5 empty] | 2020-02-27 | HDFC Bank Ambrish | Payment | 707 | 2000000
paid by cheque n000545 on a/c Property Tax paid
[5 empty] | 2020-03-31 | HDFC Bank Ambrish | Receipt | 143
being amt cheque issued in Feb-20 is cancelled
[5 empty] | 2020-12-29 | HDFC Bank Ambrish | Payment | 262 | 651814
paid by cheque 000715 to a/c mahada charges
[5 empty] | 2020-12-29 | HDFC Bank Ambrish | Payment | 263 | 1759947
[6 empty] | paid by cheque 000716 on a/c Mhada charges |  |  |  | 11900
[5 empty] | 2020-12-29 | HDFC Bank Ambrish | Payment | 264 | 1665502
paid by cheque 000717
[5 empty] | 2020-12-29 | HDFC Bank Ambrish | Payment | 265 | 3300
being amt paid for revalidation fees
[5 empty] | 2021-01-01 | HDFC Bank Ambrish | Receipt | 41
being amt payordrr cancelled
[5 empty] | 2021-01-05 | Cash in Hand | Payment | 277 | 3300
being revalidation fees paid
[5 empty] | 2021-02-11 | HDFC Bank Ambrish | Payment | 331 | 130900
[6 empty] | paid by cheque 000731 on a/c water charges paid |  |  |  | 3300
[5 empty] | 2021-07-31 | IDBI Rera A/c Ambrish | Payment | 217 | 59500
paid by cheque 787059 on a/c water bills paid
[5 empty] | 2021-08-13 | IDBI Rera A/c Ambrish | Payment | 250 | 3899067
being amt paid to cheif account officer/MB being payment Mhada charges
[5 empty] | 2021-09-06 | Cash in Hand | Payment | 285 | 9420
being amt paid for renewal of C.C of Kurla project
[5 empty] | 2021-09-28 | IDBI Rera A/c Ambrish | Payment | 308 | 515965
issued cheque 790742 to Att Account Office on a/c 1st Instalment lease Rent for Ambarish
[5 empty] | 2021-10-01 | IDBI Rera A/c Ambrish | Payment | 312 | 23800
paid by cheque 790752 on a/c water charges
[5 empty] | 2021-11-15 | IDBI Rera A/c Ambrish | Payment | 412 | 787241
paid by cheque 798292 on a/c property Tax
[5 empty] | 2022-04-05 | MCGM |  |  | 118900
[5 empty] | 2022-04-26 | MCGM |  |  | 7207850
[5 empty] | 2022-05-12 | MCGM |  |  | 512145
[5 empty] | 2022-05-19 | MCGM |  |  | 23800
[5 empty] | 2022-05-21 | MCGM |  |  | 140386
[5 empty] | 2022-05-30 | MCGM |  |  | 4785800
[5 empty] | 2022-07-29 | Revalidation Charges |  |  | 10340
[5 empty] | 2022-07-29 | MCGM Charges |  |  | 27500
[5 empty] | 2022-09-01 | MCGM Charges |  |  | 63080
[5 empty] | 2022-11-25 | MCGM Expenses |  |  | 10497627
[5 empty] | 2022-12-07 | MCGM Expenses |  |  | 2588711
[5 empty] | 2022-12-29 | MCGM Expenses |  |  | 2508288
[5 empty] | 2023-01-04 | MCGM Expenses |  |  | 566100.57
[5 empty] | 2023-01-04 | MCGM Expenses |  |  | 44252.59
[5 empty] | 2023-01-12 | MCGM Expenses |  |  | 134111.8
[5 empty] | 2023-01-25 | MCGM Expenses |  |  | 279050
[5 empty] | 2023-03-10 | MCGM Ambrish - IOD Premium |  |  | 1006100
[5 empty] | 2023-03-12 | MCGM Ambrish - CC |  |  | 599300
[5 empty] | 24.04.2023 | MCGM Charges |  |  | 182882
[5 empty] | 7.8.23 | ECS CHARGES |  |  | 31920
[5 empty] | 14.8.23 | WATER CHARGES |  |  | 59500
[5 empty] | 25.07.2023 | CC |  |  | 59500
[5 empty] | 25.03.2024 | MCGM Exp |  |  | 194738
[5 empty] | 25.03.2024 | MCGM Exp |  |  | 142800
[6 empty] | TOTAL |  |  | 103230444

## Rent
Date | Particulars | Amount
2018-05-14 | HDFC Bank Ambrish | 64000
paid by cheque 00078 to Sudha Chaubey on a/c Rent May & june-18
2018-05-14 | HDFC Bank Ambrish | 64000
issued cheque 00079 to Bimladevi Thakur on a/c Rent May & Junae-18
2018-05-14 | HDFC Bank Ambrish | 64000
paid by cheque 00080 to Prakash Venkantrao on a/c Rent May & june-18
2018-05-14 | HDFC Bank Ambrish | 64000
paid by cheque 00082 to Baidyanath Ghara on a/c Rent April-May-18
2018-05-14 | HDFC Bank Ambrish | 64000
paid by cheque 00083 to Sumitra Kamat Rent May & june-18
2018-05-14 | HDFC Bank Ambrish | 64000
paid by cheque 00084 to Vishwanath Shatri on a/c Rent May & june-18
2018-05-14 | HDFC Bank Ambrish | 64000
paid by cheque 00085 to Radhakishan Bhelare May & june-18
2018-05-14 | HDFC Bank Ambrish | 64000
paid by cheque 00086 to S.G. Bokil Rent May & June-18
2018-05-14 | HDFC Bank Ambrish | 64000
paid by cheque 00087 Purnima Yadav Rent May & June-18
2018-05-14 | HDFC Bank Ambrish | 64000
paid by cheque 00088 to Sunila Gaokar on a/c Rent for May & june-18
2018-05-14 | HDFC Bank Ambrish | 64000
paid by cheque 00089 to Prabha Patil Rent May & june-18
2018-05-14 | HDFC Bank Ambrish | 64000
paid by cheque 00090 Nikhil Mayekar Rent May & june-18
2018-05-14 | HDFC Bank Ambrish | 64000
paid by cheque 00091 to Mukesh Bhakuka Rent May-18 to June-18
2018-05-14 | HDFC Bank Ambrish | 64000
paid by cheque 00092 to Avinash Fulari on a/ Rent May & june-18
2018-05-14 | HDFC Bank Ambrish | 64000
paid by cheque 00093 to Vijay Chandure on a/c May & june-18
2018-05-14 | HDFC Bank Ambrish | 64000
paid by cheque 00094 to Dinesh Pandya Rent May-June-18
2018-05-14 | HDFC Bank Ambrish | 64000
paid by cheque 000095 to Manohar Parab Rent May-June-18
2018-05-14 | HDFC Bank Ambrish | 64000
paid by cheque 00096 to Digambar Naik May & une-18
2018-05-14 | HDFC Bank Ambrish | 64000
paid by cheque 00081 to Maya Bhatia Rent May & june-18
2018-05-16 | HDFC Bank Ambrish | 64000
paid to Savio Rent May & june-18 by cHEQUE 000097
2018-08-14 | HDFC Bank Ambrish | 96000
paid by cheque 00015 Sudha Chaubey July to Sept-18
2018-08-14 | HDFC Bank Ambrish | 96000
paid by cheque 00016 to Dinesh Pandya
2018-08-14 | HDFC Bank Ambrish | 96000
paid by cheque 00017 Bimladevi Thakur
2018-08-14 | HDFC Bank Ambrish | 96000
paid by cheque 000118 to Prakash Venkatrao
2018-08-14 | HDFC Bank Ambrish | 96000
paid by cheque 000119 Maya Bhatia
2018-08-14 | HDFC Bank Ambrish | 96000
paid by cheque 000120 Manohar Parab
2018-08-14 | HDFC Bank Ambrish | 96000
paid by cheque 000121 to Baidyanath Gahara
2018-08-14 | HDFC Bank Ambrish | 96000
Paid by cheque 000122 Sumitra Kamat
2018-08-14 | HDFC Bank Ambrish | 96000
paid by cheque 000123 Radhakrishan Belhalani
2018-08-14 | HDFC Bank Ambrish | 96000
paid by cheque S.G.Bokil
2018-08-14 | HDFC Bank Ambrish | 96000
paid by cheque 000125 Purnima Yadav
2018-08-14 | HDFC Bank Ambrish | 96000
Paid by cheque 000126 Sunila Gaokar
2018-08-14 | HDFC Bank Ambrish | 96000
paid by cheque 000127 to Prabha Patil
2018-08-14 | HDFC Bank Ambrish | 96000
paid by cheque 000128 Nikhil Maykekar
2018-08-14 | HDFC Bank Ambrish | 96000
paid by cheque 000129 Avinash Fulari
2018-08-14 | HDFC Bank Ambrish | 96000
[aid by cheque 000130 Vijay Chandure
2018-08-14 | HDFC Bank Ambrish | 96000
paid by cheque 000131 Digamber Naik
2018-08-14 | HDFC Bank Ambrish | 96000
paid by cheque 000132 Mukesh Bharuka
2018-08-14 | HDFC Bank Ambrish | 96000
paid by cheque 000133 Vishwanath Shatri
2018-08-14 | HDFC Bank Ambrish | 96000
paid by cheque 000135 Fatima Dlima
2018-11-15 | HDFC Bank Ambrish | 96000
issued cheque 000199 &00029 on a/c Rent Oct to Dec-18 paid Sudha Chaubey
2018-11-15 | HDFC Bank Ambrish | 96000
paid by cheque 000200 & 000238 to D.B.Panmdya Oct-to Dec-18
2018-11-15 | HDFC Bank Ambrish | 96000
paid by cheque 000201 & 000237 Bimladevi Thakur Oct to Dec-18
2018-11-15 | HDFC Bank Ambrish | 96000
paid by cheque 000202 & 000236 Praksh Venkatrao Rent Oct to Dec-18
2018-11-15 | HDFC Bank Ambrish | 96000
paid by cheque 000203 & 000235 Maya Bhatia on a/c Rent Oct to Dec-18
2018-11-15 | HDFC Bank Ambrish | 96000
paid by cheque 000204 & 000234 Manohar Parab on a/c Rent Oct to Dec-18
2018-11-15 | HDFC Bank Ambrish | 96000
paid by cheque 000205 & 000233 to Baidyanath Ghara Rent Oct to Dec-18
2018-11-15 | HDFC Bank Ambrish | 96000
paid by cheque 000207 & 000231 to Radhakishan Bhalani Rent Oct to Dec-18
2018-11-15 | HDFC Bank Ambrish | 96000
paid by cheque 000208 & 200230 Shashikala Bokil on a/c Rent Oct-to Dec-18
2018-11-15 | HDFC Bank Ambrish | 96000
paid by cheque 000216 & 000221 to Mukesh Bhakura Oct to Dec-18
2018-11-15 | HDFC Bank Ambrish | 96000
paid by cheque 000217 & 000219 on a/c Rent Oct to Dec-18 to Vishwanath Shatri
2018-11-15 | HDFC Bank Ambrish | 96000
paid by cheque 000218 to Fatima Dlima & 000220 Rent Oct to Dec-18
2018-11-15 | HDFC Bank Ambrish | 96000
paid by cheque 00209 & 000228 Purnima Yadav Oct to Dec-18
2018-11-15 | HDFC Bank Ambrish | 96000
paid by cheque 000210 & 000227 to Sunila Gaokar Rent Oct to Dec-18
2018-11-15 | HDFC Bank Ambrish | 96000
paid by cheque 000211 & 00000026 Prabha Patil Oct to Dec-18
2018-11-15 | HDFC Bank Ambrish | 96000
Paid by cheque 000212 & 000225 Nikhil Mayekar Oct to Dec-18
2018-11-15 | HDFC Bank Ambrish | 96000
paid by cheque 000213 & 000224 Avinash Fulari Oct to Dec-18
2018-11-15 | HDFC Bank Ambrish | 96000
paid by cheque 000214 &000223 to Vijay Chandure Oct to Dec-18
2018-11-15 | HDFC Bank Ambrish | 96000
paid by cheque 000215 & 000222 to Digamber Naik on a/c Oct-Dec-18
2018-11-15 | HDFC Bank Ambrish | 96000
paid by cheque 000206 & 000232 to Sumitra D.Kamat Oct to Dec-18
2019-02-15 | HDFC Bank Ambrish | 96000
paid by cheque 000290 Fatima Dalima Rent Jan to March-19
2019-02-15 | HDFC Bank Ambrish | 96000
paid by cheque 000293 to Vishwanath Shatri Rent Jan to March-19
2019-02-15 | HDFC Bank Ambrish | 96000
paid by cheque 000294 to Mukesh Bharuka
2019-02-15 | HDFC Bank Ambrish | 96000
paid by cheque 000295 to Digamber Naik on a/c Rent for Jan to March-19
2019-02-15 | HDFC Bank Ambrish | 96000
paid by cheque 000296 to Vijay Chandure
2019-02-15 | HDFC Bank Ambrish | 96000
paid by cheque 000297 Avinash Fulari
2019-02-15 | HDFC Bank Ambrish | 96000
paid by cheque 000298 Prabha Patil
2019-02-15 | HDFC Bank Ambrish | 96000
paid by cheque 000299 Sunila Gaokar on a/c Rent Jan to March 19
2019-02-15 | HDFC Bank Ambrish | 96000
paid by cheque 000300 Purnima A. Yadav Rent Jan to March 19
2019-02-15 | HDFC Bank Ambrish | 96000
paid by cheque 000301 To Radhakishan Bhalani
2019-02-15 | HDFC Bank Ambrish | 96000
paid by cheque 000302 Sumitra Kamat
2019-02-15 | HDFC Bank Ambrish | 96000
paid by cheque 000303 Baidyanath Ghara
2019-02-15 | HDFC Bank Ambrish | 96000
paid by cheque 000304 Manohar Parab
2019-02-15 | HDFC Bank Ambrish | 96000
paid by cheque 000305 Maya Bhatia
2019-02-15 | HDFC Bank Ambrish | 96000
paid by cheque 000306 Prakash Venkatrao
2019-02-15 | HDFC Bank Ambrish | 96000
paid by cheque 000307 Bimaladevi Thakur
2019-02-15 | HDFC Bank Ambrish | 96000
paid by cheque 000308 Sudha Chaubey
2019-02-15 | HDFC Bank Ambrish | 96000
paid by cheque 000309 to Dinesh Pandya
2019-02-15 | HDFC Bank Ambrish | 96000
paid by cheque 000310 Nikhil Mayekar
2019-02-15 | HDFC Bank Ambrish | 96000
paid by cheque 000311 to Shashikala Bokil
2019-05-14 | HDFC Bank Ambrish | 99000
paid by cheque 000364 Sudha Chaubey on a/c payment of Rent Aprilto june-19
2019-05-14 | HDFC Bank Ambrish | 99000
paid by cheque 000365 Dinesh Pandya on a/c payment of Rent April-June-19
2019-05-14 | HDFC Bank Ambrish | 99000
paid by cheque 000366 Bimladevi Jain Rent April-june-19
2019-05-14 | HDFC Bank Ambrish | 99000
paid by cheque 000367 to Prakesh Venkatrao April-june-19
2019-05-14 | HDFC Bank Ambrish | 99000
paid by cheque 000368 Maya Bhatia Rent April-june-19
2019-05-14 | HDFC Bank Ambrish | 99000
paid by cheque 000370 Baidyanath Gahra Rent for April to June-19
2019-05-14 | HDFC Bank Ambrish | 99000
paid by cheque 000371 Sumitra Kamat Rent April-june-19
2019-05-14 | HDFC Bank Ambrish | 99000
paid by cheque 000372 Radhakishan Bahalani Rent April-june-19
2019-05-14 | HDFC Bank Ambrish | 99000
paid by cheque 000373 Sashikala Bokil Rent April-june-19
2019-05-14 | HDFC Bank Ambrish | 99000
paid by cheque 000374 Purnima Yadav on a/c Rent April-june-19
2019-05-14 | HDFC Bank Ambrish | 99000
paid by cheque 000375 Sunila Gaokar Rent April-june-19
2019-05-14 | HDFC Bank Ambrish | 99000
paid by cheque 000376 Rent April-june-19
2019-05-14 | HDFC Bank Ambrish | 99000
paid by cheque 000377 Nikhil Mayekar on a/c April-june-19
2019-05-14 | HDFC Bank Ambrish | 99000
paid by cheque 000378 to Avinash Fulari Rent April-june-19
2019-05-14 | HDFC Bank Ambrish | 99000
paid by cheque 000379 Vijay Chandure Rent April-june-19
2019-05-14 | HDFC Bank Ambrish | 99000
paid by cheque 000380 Digamber Naik on a/c Rent Apriljune-19
2019-05-14 | HDFC Bank Ambrish | 99000
paid by cheque 000381 to Mukesh Bharuka Rent Aprilto june-19
2019-05-14 | HDFC Bank Ambrish | 99000
paid by cheque 000382 to Vishwanath Shatri Rent April-june-19
2019-05-14 | HDFC Bank Ambrish | 99000
paid by cheque 000383 To Fatima Dalima Rent Aprilto june-19
2019-05-14 | HDFC Bank Ambrish | 99000
paid by cheque 000384 to Manohar parab Rent April to june-19
2019-08-10 | HDFC Bank Ambrish | 105000
paid by cheque 000425 to Sudha Chaubey on a/c Rent for July-sspt-19
2019-08-10 | HDFC Bank Ambrish | 105000
paid by cheque 000426 to Dinesh Pandya On a/c Rent for July-Sept-19
2019-08-10 | HDFC Bank Ambrish | 105000
paid by cheque 000427 to Bimladevi Thakur Rent July-Sept-19
2019-08-10 | HDFC Bank Ambrish | 105000
paid by Cheque 000428 to Prakash VentkatRao on a/c Rent July-Sept-19
2019-08-10 | HDFC Bank Ambrish | 105000
Paid by cheque 000429 to Maya Bhatia On a/c Rent July-Sept-19
2019-08-10 | HDFC Bank Ambrish | 105000
Paid by cheque 000430 to Baidyanath Ghara on a/c Rent July to Sept-19
2019-08-10 | HDFC Bank Ambrish | 105000
Paid by cheque 000431 to Sumitra Kamat On a/c Rent July to Sept-19
2019-08-10 | HDFC Bank Ambrish | 105000
Paid by cheque 000432 Radhakishan Bhalani on a/c Rent July to Sept-19
2019-08-10 | HDFC Bank Ambrish | 105000
paid by cheque 000443 to Shashikala Bokil on a/c Rent July-Sept-19
2019-08-10 | HDFC Bank Ambrish | 105000
paid by cheque 000434 to Purnima Yadav on a/c Rent for July-Sept-19
2019-08-10 | HDFC Bank Ambrish | 105000
paid by cheque 000435 to Sunila Gaokar on a/c Rent Julyto Sept-19
2019-08-10 | HDFC Bank Ambrish | 105000
paid by cheque 000436 to Prabha Patil on a/c Rent July to Sept-19
2019-08-10 | HDFC Bank Ambrish | 105000
paid by cheque 000437 to Nikhil Mayekar on a/c Rent July to Sept-19
2019-08-10 | HDFC Bank Ambrish | 105000
paid by cheque 000438 to Avinash Fulari on a/c Rent July to Sept-19
2019-08-10 | HDFC Bank Ambrish | 105000
paid by cheque 000439 to Rent Vijay Chandure July to Sept-19
2019-08-10 | HDFC Bank Ambrish | 105000
paid by cheque000440 to Digamber Naik on a/c Rent July to Sept-19
2019-08-10 | HDFC Bank Ambrish | 105000
paid by cheque 000441 to Mukesh Bharuka Rent July to Sept-19
2019-08-10 | HDFC Bank Ambrish | 105000
paid by cheque 000442 to Vishwanath Shatri on a/c Rent July to Sept-19
2019-08-10 | HDFC Bank Ambrish | 105000
paid by cheque 000443 to Fatima Dalima On a/c Rent July to Sept-19
2019-08-10 | HDFC Bank Ambrish | 105000
paid by cheque 000444 to Manohar Parab on a/c Rent July to Sept-19
2019-11-20 | HDFC Bank Ambrish | 102000
paid by cheque 000472 Digamber Nail on a/c Rent Oct-19 to Dec-19
2019-11-20 | HDFC Bank Ambrish | 102000
paid by cheque 000473 to Sudha Chaubey on a/c Rent Oct to Dec-19
2019-11-20 | HDFC Bank Ambrish | 102000
paid by cheque 000474 to Dinesh Pandya on a/c Rent Oct to Dec-19
2019-11-20 | HDFC Bank Ambrish | 102000
paid by cheque 000475 to Bimladevi Thakur rent oct-19 to Dec-19
2019-11-20 | HDFC Bank Ambrish | 102000
paid by cheque 000476 to Prakash Venkatraoon a/c Rent Oct to Dec-19
2019-11-20 | HDFC Bank Ambrish | 102000
paid by cheque 000477 to Maya bhatia on a/c Rent Oct to Dec-19
2019-11-20 | HDFC Bank Ambrish | 102000
paid by cheque 000478 to Manohar Parab on a/c Rent oct-Dec-19
2019-11-20 | HDFC Bank Ambrish | 102000
paid by cheque 000479 to Baidyanath Ghara on a/c Rent oct-Dec-19
2019-11-20 | HDFC Bank Ambrish | 102000
paid by cheque 000480 Sumitra Kamat on a/c rent Oct to Dec-19
2019-11-20 | HDFC Bank Ambrish | 102000
paid by cheque 000481 to Radhakishan Behalani on a/c rent oct-Dec-19
2019-11-20 | HDFC Bank Ambrish | 102000
paid by cheque 000482 to shashikala Bokil on a/c Rent Oct-Dec-19
2019-11-20 | HDFC Bank Ambrish | 102000
paid by cheque 000483 to purnima A.Yadav Rent OPct to Dec-19
2019-11-20 | HDFC Bank Ambrish | 102000
paid by cheque 000484 to sunila Gaokar on a/c rent OCt-Dec-19
2019-11-20 | HDFC Bank Ambrish | 102000
paid by cheque 000485 toprabha Patil on a/c Rent Oct-Dec-19
2019-11-20 | HDFC Bank Ambrish | 102000
paid by cheque 000486 to Nikhil Mayekar on a/c Rent Oct-19 to Dec-19
2019-11-20 | HDFC Bank Ambrish | 102000
paid by cheque 000487 to, Avinash Fulari ct-19 to Dec-19
2019-11-20 | HDFC Bank Ambrish | 102000
paid by cheque 000489 to Vijay Chandure Oct-Dec-19
2019-11-20 | HDFC Bank Ambrish | 102000
paid by cheque 000491 to Mukesh Bharuka on a/c Rent Oct-Dec-19
2019-11-20 | HDFC Bank Ambrish | 102000
paid by cheque 000492 to Vishwanath Shatri on a/c Rent Oct-Dec-19
2019-11-20 | HDFC Bank Ambrish | 102000
paid by cheque 000493 to Fatima Dalima on a/c Rent Oct-Dec-19
2020-02-15 | HDFC Bank Ambrish | 102000
paid by cheque 000651 Sudha Chaubey on a/c Rent for Jan to March-20
2020-02-15 | HDFC Bank Ambrish | 102000
paid by cheque 000653 to Dinesh Pandya Jan to March-20
2020-02-15 | HDFC Bank Ambrish | 102000
paid by cheque 000654 to Bimladevi Thakur Rent Jan to March-20
2020-02-15 | HDFC Bank Ambrish | 102000
paid by cheque 000655 to Prakash Venkatrao Jan to March-20
2020-02-15 | HDFC Bank Ambrish | 102000
paid by cheque 000656 to Maya bhatia on a/c ent Jan to March-20
2020-02-15 | HDFC Bank Ambrish | 102000
paid by cheque 000657 to Manohar Parab on a/c rent Jan to March-20
2020-02-15 | HDFC Bank Ambrish | 102000
paid by cheque 000658 to Baidnath Ghara Rent Jan to March-20
2020-02-15 | HDFC Bank Ambrish | 102000
paid by cheque 000659 to sumitra D. Kamat Rent Jan to March-20
2020-02-15 | HDFC Bank Ambrish | 102000
paid by cheque 000660 to Radhakishan Bahalani Rent Jan to March-20
2020-02-15 | HDFC Bank Ambrish | 102000
paid by cheque 000661 to Shashikala Bokil Rent Jan to March-20
2020-02-15 | HDFC Bank Ambrish | 102000
paid by cheque 000662 to Purnima Yadav Rent fior Jan to March -20
2020-02-15 | HDFC Bank Ambrish | 102000
paid by cheque 000663 to Sunila Gaokar Rent Jan to March-20
2020-02-15 | HDFC Bank Ambrish | 102000
Paid by cheque 000664 to Prabha Patil Rent Jan to March-20
2020-02-15 | HDFC Bank Ambrish | 102000
paid by cheque 000665 to Nikhil Mayekar Rent Jan to March-20
2020-02-15 | HDFC Bank Ambrish | 102000
paid by cheque 000666 to Avinash Fulari Rent Jan to March-20
2020-02-15 | HDFC Bank Ambrish | 102000
paid by cheque 000667 to Vijay Chandure Rent Jan to March-20
2020-02-15 | HDFC Bank Ambrish | 102000
paid by cheque 000668 to Digamber Naik Rent Jan to March-20
2020-02-15 | HDFC Bank Ambrish | 102000
paid by cheque 000669 to Mukesh Bharuka Rent Jan to March-20
2020-02-15 | HDFC Bank Ambrish | 102000
paid by cheque 000670 Vishwanath Shatri Jan to March-20
2020-02-15 | HDFC Bank Ambrish | 102000
paid by cheque 000671 to Fatima Dalima Rent Jan to March-20
2020-11-17 | HDFC Bank Ambrish | 105000
paid by cheque 000694 o to Purnima Yadav on a/c Rent for Oct to Dec-20
2020-11-17 | HDFC Bank Ambrish | 105000
paid by cheque 000695 to Praksh Venkatrao on a/c Rent for Oct to Dec-20
2020-11-17 | HDFC Bank Ambrish | 105000
paid by cheque 000696 to Bainath Ghara Rent for Oct to Dec-20
2020-11-23 | HDFC Bank Ambrish | 105000
paid by cheque 000697 to Sudha Chaubey on a/c Rent Oct to Dec-20
2020-11-23 | HDFC Bank Ambrish | 105000
paid by cheque 000698 to Maya Bhatia on a/c Rent Oct to Dec-20
2020-11-23 | HDFC Bank Ambrish | 105000
paid by cheque 000699 to sumitra D.Kamat Oct to Dec-20
2020-12-07 | HDFC Bank Ambrish | 105000
paid by cheque 00070 to Vishwanath Shatri on a/c rent Oct to Dec-20
2020-12-07 | HDFC Bank Ambrish | 105000
paid in by cheque 000701 to Radhakishan behlani on a/c Oct to Dec-20 rent
2020-12-07 | HDFC Bank Ambrish | 105000
paid by cheque 000702 to Vijay S.Chandure on a/c rent Oct toi Dec-20
2020-12-07 | HDFC Bank Ambrish | 105000
paid by cheque 000703 to Bimaladevi Thakur Rent Oct to Dec-20
2020-12-15 | HDFC Bank Ambrish | 105000
paid by cheque 00710 to fatima Dalima on a/c rent Oct to Dec-20
2020-12-15 | HDFC Bank Ambrish | 105000
paid by cheque 000707 to shashikala Bokil on a/c rent Oct to Dec-20
2020-12-19 | HDFC Bank Ambrish | 105000
paid by cheque 000708 to Prabha Rao on a/c rent oct to Dec-20
2020-12-19 | HDFC Bank Ambrish | 105000
paid by cheque 000711 Avinash Fulari Rent for oct to Dec-20
2020-12-19 | HDFC Bank Ambrish | 105000
paid by cheque 000712 sunila goankar rent Oct to Dec-20
2020-12-30 | HDFC Bank Ambrish | 105000
paid by cheque 000719 to Mukesh Bharuka on a/c rent for Oct to Dec-20
2020-12-30 | HDFC Bank Ambrish | 105000
paid by cheque 000720 to Digambe000720 to Nikhi aaaaaa Mayekar
2020-12-30 | HDFC Bank Ambrish | 105000
paid by cheque 000721 toDiagmber naik Rent Oct to Dec-20
2020-12-30 | HDFC Bank Ambrish | 105000
paid by cheque 000722 to Manohar Parab on a/c rent oct to dec-20
2020-12-30 | HDFC Bank Ambrish | 105000
paid by cheque 000723 to Dinesh Pandya on a/c Rent Oct to Dec-20
2020-12-31 | HDFC Bank Ambrish
being amt RTGS return
2021-01-07 | HDFC Bank Ambrish | 105000
paid by cheque00725 HDFC BankDinesh Pandya
2021-03-01 | HDFC Bank Ambrish | 105000
paid by cheque 000741 to Radhakishan Bhalani
2021-03-01 | HDFC Bank Ambrish | 105000
paid by cheque 000740 to Baidyanath Ghara on a/c payment renet Jan to March-21
2021-03-01 | HDFC Bank Ambrish | 105000
paid by cheque 000742 Maya bhatia Jan to March-21
2021-03-01 | HDFC Bank Ambrish | 105000
paid by cheque 000743 to Prakash Venkat Rao on a/c Rent for Jan to March-21
2021-03-01 | HDFC Bank Ambrish | 105000
paid by cheque 000744 to Purnima Yadav on a/c Rent Jan to March-21
2021-04-09 | IDBI Rera A/c Ambrish | 105000
paid by cheque 631485 to Sudha Chubey Rent Jan to March-21
2021-04-09 | IDBI Rera A/c Ambrish | 105000
paid by cheque 631488 to Dinesh Pandya on a/c Rent Jan to March-21
2021-04-09 | IDBI Rera A/c Ambrish | 105000
paid by cheque 631489 to Shashikala Bokil on a/c Rent Jan to March-21
2021-04-09 | IDBI Rera A/c Ambrish | 105000
paid by cheque 631490 prabha Patil rent Jan to March-21
2021-04-09 | IDBI Rera A/c Ambrish | 105000
paid by cheque 000491 to sunila Gaonkar Rent Jan to March-21
2021-04-09 | IDBI Rera A/c Ambrish | 105000
paid by cheque 000492 to Nikhil Mayker on a/c Rent Jan to March-21
2021-04-09 | HDFC Bank Ambrish | 105000
paid by cheque 000747 to Fatima Dalima on a/c Rent Jan to March-21
2021-04-09 | HDFC Bank Ambrish | 105000
paid by cheque 000746 to Vishwanath Sharti Rent Jan to March-21
2021-04-09 | HDFC Bank Ambrish | 105000
paid by cheque 000750 Vijay Chandure on a/c Rent Jan to March-21
2021-04-09 | HDFC Bank Ambrish | 105000
Paid by cheque 000749 Bimaldevi Thakur Rent Jan to March-21
2021-04-09 | HDFC Bank Ambrish | 105000
paid by cheque 000748 Sumitra Kamat on a/c Rent Jan to March-21
2021-04-21 | IDBI Rera A/c Ambrish | 105000
paid by chequr 631494 Manohar Parab Rent Jan to mRach-21
2021-04-21 | IDBI Rera A/c Ambrish | 105000
paid by cheque 631495 on a/c rent Avinash Fulary Rent Jan to March-21
2021-04-21 | IDBI Rera A/c Ambrish | 105000
paid by cheque 631497 Mukesh Bharuka rent Jan to March-21
2021-04-21 | IDBI Rera A/c Ambrish | 105000
paid by chequr 631496 to Digmbar Naik on a/c payment Rent Jan to March 21
2021-05-17 | IDBI Rera A/c Ambrish | 105000
paid by cheque 631505 to Baidyanath Ghara Rent Aprl to June-21
2021-06-11 | IDBI Rera A/c Ambrish | 105000
paid by cheque 631518 Bimladev Thakur Rent April-June-21
2021-06-11 | IDBI Rera A/c Ambrish | 105000
paid by cheque 631519 Praksh Venkatrao Rent April-June-21
2021-06-11 | IDBI Rera A/c Ambrish | 105000
paid by cheque 631520 Maya Bhatia Rent April-June-21
2021-06-11 | IDBI Rera A/c Ambrish | 105000
paid by cheque 631521 Sumita Kamat Rent April-Jan-21
2021-06-11 | IDBI Rera A/c Ambrish | 105000
paid by cheque 631522 Radhakishan Bhalani Rent April to June-21
2021-06-14 | IDBI Rera A/c Ambrish | 105000
paid by cheque 613523 to Vishwanath Shatri on a/c Rent April to June-21
2021-06-14 | IDBI Rera A/c Ambrish | 105000
paid by cheque 613524 to Purnima Yadav on a/c Rent for April to june-21
2021-06-14 | IDBI Rera A/c Ambrish | 105000
paid by cheque 613526 Sudha Chaubey on a/c Rent April to june-21
2021-06-14 | IDBI Rera A/c Ambrish | 105000
paid by cheque 613525 Vijay Chandure on a/c Rent April to June-21
2021-07-26 | IDBI Rera A/c Ambrish | 105000
paid by cheque 787051 to shashikala Bokil Rent April to june-21
2021-07-26 | IDBI Rera A/c Ambrish | 105000
paid by cheque 787052 Nikhil Mayekar Rent April to june-21
2021-07-26 | IDBI Rera A/c Ambrish | 105000
paid by cheque 787054 Ftima Dalima Rent April to june-21
2021-07-29 | IDBI Rera A/c Ambrish | 105000
paid by cheque 787055 Prabha patil on a/c rent April to june-21
2021-07-29 | IDBI Rera A/c Ambrish | 105000
paid by cheque 787056 Avinash fulari on a/c rent for April to june-21
2021-07-29 | IDBI Rera A/c Ambrish | 105000
paid by cheque 787057 Dinesh pandya on a/c rent april to june-21
2021-07-29 | IDBI Rera A/c Ambrish | 105000
paid by cheque 00058 Manohar parab on a/c rent april to june-21
2021-07-31 | IDBI Rera A/c Ambrish | 105000
paid by cheque 787060 sunila Goankar on a/c Rent April to june-21
2021-07-31 | IDBI Rera A/c Ambrish | 105000
issured cheque 787061 Digambar naik on a/c Rent April to june-21
2021-07-31 | IDBI Rera A/c Ambrish | 105000
paid by cheque 787066 Mukesh Bharuka on a/c rent April to june-21
2021-10-11 | IDBI Rera A/c Ambrish | 105000
paid by cheque 790753 to Sumitra D. Kamat on a/c rent for July to Sept-21
2021-10-14 | IDBI Rera A/c Ambrish | 105000
paid by cheque000757 Vishwanath Shatri on a/c Rent July to sept 21
2021-10-14 | IDBI Rera A/c Ambrish | 105000
paid by cheque 000758 to Radhakishan Bhalani Rent July to Sept-21
2021-10-14 | IDBI Rera A/c Ambrish | 105000
paid by cheque 790759 Purnima Yadav on a/c Rent July to sept 21
2021-10-14 | IDBI Rera A/c Ambrish | 105000
paid by cheque 790760 Prakash Venkatrao on a/c Rent July to Sept-21
2021-10-14 | IDBI Rera A/c Ambrish | 105000
paod by cheque 790761 to Baidyanath Ghara on a/c Rent july to sept-21
2021-10-14 | IDBI Rera A/c Ambrish | 105000
paid by cheque 790762 to Sudha Chaubey on a/c Rent July to sept-21
2021-10-14 | IDBI Rera A/c Ambrish | 105000
paid by cheque 790763 Fatima Dalima on a/c Rent July to sept-21
2021-10-14 | IDBI Rera A/c Ambrish | 105000
paid by cheque 790764 prabha Patil on a/c Rent july to sept-21
2021-10-14 | IDBI Rera A/c Ambrish | 105000
paid by cheque 790765 Digamber Naik on a/c Rent july to sept-21
2021-10-14 | IDBI Rera A/c Ambrish | 105000
paid by cheque 790766 to Avinash Fulari on a/c Rent july to sept-21
2021-10-14 | IDBI Rera A/c Ambrish | 105000
paid by chequ 790767 Maukesh Bharuka July to Sept-21
2021-10-14 | IDBI Rera A/c Ambrish | 105000
paid by cheque 790768 Nikhil Mayekar Rent july to sept-21
2021-10-14 | IDBI Rera A/c Ambrish | 105000
paid by cheque 790769 to Sanjay Parab on a/c Rent july to sept-21
2021-10-14 | IDBI Rera A/c Ambrish | 105000
paid by cheque 790770 to Shashikala Bokil Rent july to sept-21 Medha Ajitkumar/Bokil Rajeev
2021-10-14 | IDBI Rera A/c Ambrish | 105000
paid by cheque 790771 to Ranbir Thakur Rent july to sept-21
2021-10-14 | IDBI Rera A/c Ambrish | 105000
paid by cheque 790772 to Vivek Chandure Rent july to sept-21
2021-10-14 | IDBI Rera A/c Ambrish | 105000
paid by cheque 790773 to Dinesh Pandya Rent July to sept-21
2021-10-16 | IDBI Rera A/c Ambrish | 105000
paid by cheque 790776 To Sameer Gonkar On a/c Rent July to sept-21
2021-10-28 | IDBI Rera A/c Ambrish | 105000
PAID BY CHEQUE 796281 TO vIVEK cHANDURE ON A/C rENT jULY TO SEPT-21
2018-03-28 | Maya Arjan Bhatia | 900000
being amt Courpus adjusted on split of Flat
2018-03-28 | Vijay Gulabrao Chandure | 900000
being amount Corpus adjsted
2018-03-28 | Sunila Mohan Gaokar | 900000
being amt Corpus adjusted in Flat
2018-03-28 | Vishwanath Shatri | 450000
being 50% corpus adjusted
2018-03-28 | Manohar Parab | 900000
being amount Courpus adjusted in Flat
2018-03-28 | Digambar Naik | 900000
being amt of Corpus adjusted in flat
2018-03-28 | Baidayanath S.Ghara | 900000
being amt of Corpus adjusted in Flat
2018-03-28 | Prabha Bajirao Patil | 900000
being amt Corpus adjusted in flat
2018-03-28 | Sumitra D.Kamat & Vinod D.Kamat | 900000
being amt Corpus adjusted in Flat
2018-03-28 | Radhakishan S.Bahlani | 900000
being amt Corpus fund adjusted & transfer
2018-03-28 | Shasikala G.Bokil | 900000
being amt Corpus fund adjusted in Split flat
2018-03-28 | Nikhil S. Mayekar | 900000
being amt Corpus adjusted in Flat
2018-03-28 | Purnima Amos Yadav | 900000
being amt corpus adjusted in flat
2018-03-28 | Avinash Fulari | 900000
being amt Corpus fund adjusted in flat
2018-03-28 | Savio Ivan D'lima | 450000
being amt corpus fund 50% adjusted
2018-05-01 | HDFC Bank Ambrish | 450000
paid by cheque 000051 Mukesh Bharuka on a/c 50% Corpus paid
2018-05-01 | HDFC Bank Ambrish | 450000
paid by cheque 000052 to Sudha Chaubey on a/c 50% corpus paid
2018-05-01 | HDFC Bank Ambrish | 450000
paid by cheque 00054 to Bimladevi Thakkar on a/c corpus paid 50%
2018-05-01 | HDFC Bank Ambrish | 450000
paid by xcheque 00057 to Dinesh Pandya
2018-05-01 | HDFC Bank Ambrish | 450000
paid by cheque 00055 Praksh Venkatrao 50%
2019-08-08 | HDFC Bank Ambrish | 450000
paid by cheque 000424 on a/c 50% Courps Paid to Mukesh Bharuka
2022-02-21 | IDBI Rera A/c Ambrish | 105000
paid by cheque 806515 Avinash Fulari Rent Oct to Dec-21
2022-02-21 | IDBI Rera A/c Ambrish | 105000
paid by cheque 806518 to Ranbir Thakur on a/c Rent Oct-Dec-21
2022-02-21 | IDBI Rera A/c Ambrish | 105000
paid by cheque 806516 on a/c Rent Oct Dec-21
2022-02-21 | IDBI Rera A/c Ambrish | 105000
paid by cheque 806514 to Fatima Dlima on a/c Rent Oct to Dec-21
2022-02-21 | IDBI Rera A/c Ambrish | 105000
p[aid by cheque 806511 to Mukesh Bharuka on a/c Rent Oct to Dec-21
2022-02-21 | IDBI Rera A/c Ambrish | 105000
rent paid by cheque 806517 to Nikhil Mayekar on a/c Rent Oct to Dec-21
2022-02-21 | IDBI Rera A/c Ambrish | 105000
paid by cheque 806512 to Vishwanath Shatri Rent for Oct to Dec-21
2022-02-21 | IDBI Rera A/c Ambrish | 105000
paid by cheque 806520 to Sudha Chaubey Rent for Oct to Dec-21
2022-02-21 | IDBI Rera A/c Ambrish | 105000
renet for cheque 806519 Vinod Kamat on a/c Rent for Oct to Dec-21
2022-02-21 | IDBI Rera A/c Ambrish | 105000
paid by cheque 806521 Prabha Patil Rent Oct to Dec-21
2022-02-21 | IDBI Rera A/c Ambrish | 105000
paid by cheque 806525 to Baidyanath Ghara on a/c Rent Oct to Dec-21
2022-02-21 | IDBI Rera A/c Ambrish | 105000
paid by cheque 806524 to Prakash Venkatrao on a/c Rent Oct to Dec-21
2022-02-22 | IDBI Rera A/c Ambrish | 105000
paid by cheque 806527 to Rajashree Bokil on a/c Rent Oct to Dec-21
2022-02-22 | IDBI Rera A/c Ambrish | 105000
paiby cheque 806523 to Radhakishan Bahalani on a/c Rent Oct to Dec-21
2022-02-22 | IDBI Rera A/c Ambrish | 105000
paid by cheque 806522 to Purnima Yadav on a/c Rent Oct to Dec-21
2022-02-22 | IDBI Rera A/c Ambrish | 105000
paid by cheque 806528 Vivek Chandure on a/c Rent Oct to Dec-21
2022-02-22 | IDBI Rera A/c Ambrish | 105000
paid by cheque 814682 to Dinesh Pandya on a/c Rent for Oct to Dec-21
2022-02-22 | IDBI Rera A/c Ambrish | 105000
paid by cheque 806526 to Santosh Rent Oct to Dec-21
2022-02-22 | IDBI Rera A/c Ambrish | 105000
paid by cheque 814681 to Sameer Goankar on a/c Rent for Oct to Dec-21
2022-02-23 | IDBI Rera A/c Ambrish | 105000
paid by cheque 814687 to Sunil Bhatia on a/c Rent Oct to Dec-21
2022-06-06 | Rent A/c(Ambrish Project) | 105000
2022-06-06 | Rent A/c(Ambrish Project) | 105000
2022-06-06 | Rent A/c(Ambrish Project) | 105000
2022-06-06 | Rent A/c(Ambrish Project) | 105000
2022-06-06 | Rent A/c(Ambrish Project) | 105000
2022-06-06 | Rent A/c(Ambrish Project) | 105000
2022-06-06 | Rent A/c(Ambrish Project) | 105000
2022-06-06 | Rent A/c(Ambrish Project) | 105000
2022-06-06 | Rent A/c(Ambrish Project) | 105000
2022-06-06 | Rent A/c(Ambrish Project) | 105000
2022-06-06 | Rent A/c(Ambrish Project) | 105000
2022-06-06 | Rent A/c(Ambrish Project) | 105000
2022-06-06 | Rent A/c(Ambrish Project) | 105000
2022-06-06 | Rent A/c(Ambrish Project) | 105000
2022-06-06 | Rent A/c(Ambrish Project) | 105000
2022-06-06 | Rent A/c(Ambrish Project) | 105000
2022-06-06 | Rent A/c(Ambrish Project) | 105000
2022-06-06 | Rent A/c(Ambrish Project) | 105000
2022-06-06 | Rent A/c(Ambrish Project) | 105000
2022-06-07 | Rent A/c(Ambrish Project) | 105000
2022-08-18 | Rent A/c(Ambrish Project) | 1995000
2022-11-29 | Rent Cost - State Bank of India CC A/c | 105000
2022-11-29 | Rent Cost - State Bank of India CC A/c | 105000
2022-11-29 | Rent Cost - State Bank of India CC A/c | 105000
2022-11-29 | Rent Cost - State Bank of India CC A/c | 105000
2022-11-29 | Rent Cost - State Bank of India CC A/c | 105000
2022-11-29 | Rent Cost - State Bank of India CC A/c | 105000
2022-11-29 | Rent Cost - State Bank of India CC A/c | 105000
2022-11-29 | Rent Cost - State Bank of India CC A/c | 105000
2022-11-29 | Rent Cost - State Bank of India CC A/c | 105000
2022-11-29 | Rent Cost - State Bank of India CC A/c | 105000
2022-11-29 | Rent Cost - State Bank of India CC A/c | 105000
2022-11-29 | Rent Cost - State Bank of India CC A/c | 105000
2022-11-29 | Rent Cost - State Bank of India CC A/c | 105000
2022-11-30 | Rent Cost - State Bank of India CC A/c | 105000
2022-11-30 | Rent Cost - State Bank of India CC A/c | 105000
2022-11-30 | Rent Cost - State Bank of India CC A/c | 105000
2022-11-30 | Rent Cost - State Bank of India CC A/c | 105000
2022-11-30 | Rent Cost - State Bank of India CC A/c | 105000
2022-11-30 | Rent Cost - State Bank of India CC A/c | 105000
2022-11-30 | Rent Cost - State Bank of India CC A/c | 105000
2022-11-30 | Rent Cost - State Bank of India CC A/c | 105000
2023-02-16 | Rent | 2100000
2023-05-16 | Rent | 2100000
2023-11-16 | Rent | 2100000
| Corpus & Stamp Duty | 2700000
| Rent | 700000
57105000

## Construction Cost
Date |  | Vch Type | Vch No. | Amount
2018-08-20 | (as per details) | Purchase | 1 | 16500
Power Post(Ambrish)
| CGST 9% Purchase |  |  | 1485
| SGST 9% Purchase |  |  | 1485
received bills
2018-09-01 | (as per details) | Purchase | 2 | 88694
Relcon Infraprojects Ltd(Ambrish)
| CGST 9% Purchase |  |  | 7982.5
| SGST 9% Purchase |  |  | 7982.5
received bills
2018-09-01 | (as per details) | Purchase | 3 | 26877
Relcon Infraprojects Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2419
| CGST 9% Purchase |  |  | 2419
received bills
2018-09-01 | (as per details) | Purchase | 4 | 80631
Relcon Infraprojects Ltd(Ambrish)
| CGST 9% Purchase |  |  | 7257
| SGST 9% Purchase |  |  | 7257
received bills
2018-09-04 | (as per details) | Purchase | 5 | 7904
Mateshvari Electric & Hardwear Stores(A)
| CGST 9% Purchase |  |  | 711
| SGST 9% Purchase |  |  | 711
received bills
2018-09-04 | (as per details) | Purchase | 6 | 18106
Superior Concrete Products LLP(A)
| SGST 9% Purchase |  |  | 1629
| CGST 9% Purchase |  |  | 1629
2018-09-05 | (as per details) | Purchase | 7 | 219404
Masina Ispat Private Limited(A)
| CGST 9% Purchase |  |  | 19746.5
| SGST 9% Purchase |  |  | 19746.5
received bills
2018-09-05 | (as per details) | Purchase | 8 | 218652
Masina Ispat Private Limited(A)
| SGST 9% Purchase |  |  | 19678.5
| CGST 9% Purchase |  |  | 19678.5
received bills
2018-09-06 | Maharashtra Vikas Tranport & General Kamgar Sanghat | Purchase | 9 | 2500
received bills
2018-09-12 | Aqsa Enterprises | Purchase | 10 | 27623
rECEIVED BILLS
2018-09-15 | (as per details) | Purchase | 11 | 26822
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2414
| SGST 9% Purchase |  |  | 2414
received bills
2018-09-15 | (as per details) | Purchase | 12 | 26822
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2414
| CGST 9% Purchase |  |  | 2414
received bills
2018-09-17 | (as per details) | Purchase | 13 | 26822
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2414
| SGST 9% Purchase |  |  | 2414
received bills
2018-09-17 | (as per details) | Purchase | 14 | 18775
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 1690
| CGST 9% Purchase |  |  | 1690
received bills
2018-09-18 | (as per details) | Purchase | 15 | 26822
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2414
| SGST 9% Purchase |  |  | 2414
received bills
2018-09-18 | (as per details) | Purchase | 16 | 26822
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2414
| CGST 9% Purchase |  |  | 2414
received bills
2018-09-18 | (as per details) | Purchase | 17 | 26822
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2414
| SGST 9% Purchase |  |  | 2414
received bills
2018-09-19 | (as per details) | Purchase | 18 | 26822
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2414
| CGST 9% Purchase |  |  | 2414
received bills
2018-09-19 | (as per details) | Purchase | 19 | 18775
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 1690
| SGST 9% Purchase |  |  | 1690
received bills
2018-09-20 | (as per details) | Purchase | 20 | 26822
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2414
| CGST 9% Purchase |  |  | 2414
receuved bills
2018-09-20 | (as per details) | Purchase | 21 | 26822
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2414
| SGST 9% Purchase |  |  | 2414
received bills
2018-09-20 | (as per details) | Purchase | 22 | 26822
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2414
| CGST 9% Purchase |  |  | 2414
received bills
2018-09-20 | (as per details) | Purchase | 23 | 940454
Mody Associates Co.(Ambrish)
| CGST 9% Purchase |  |  | 84641
| SGST 9% Purchase |  |  | 84641
received bills
2018-09-21 | (as per details) | Purchase | 24 | 53754
Relcon Infraprojects Ltd(Ambrish)
| CGST 9% Purchase |  |  | 4838
| SGST 9% Purchase |  |  | 4838
received bills
2018-09-22 | (as per details) | Purchase | 25 | 24189
Relcon Infraprojects Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2177
| CGST 9% Purchase |  |  | 2177
received bills
2018-09-22 | (as per details) | Purchase | 26 | 32253
Relcon Infraprojects Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2902.5
| CGST 9% Purchase |  |  | 2902.5
receibed bills
2018-09-24 | (as per details) | Purchase | 27 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 1448
| SGST 9% Purchase |  |  | 1448
received bills
2018-09-24 | (as per details) | Purchase | 28 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 1448
| CGST 9% Purchase |  |  | 1448
received bills
2018-09-24 | (as per details) | Purchase | 29 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2173
| SGST 9% Purchase |  |  | 2173
received bills
2018-09-24 | (as per details) | Purchase | 30 | 7670
Mateshvari Electric & Hardwear Stores(A)
| SGST 9% Purchase |  |  | 690
| CGST 9% Purchase |  |  | 690
received bills
2018-09-25 | (as per details) | Purchase | 31 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 1448
| CGST 9% Purchase |  |  | 1448
rececived bills
2018-09-25 | (as per details) | Purchase | 32 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2173
| SGST 9% Purchase |  |  | 2173
received bills
2018-09-25 | (as per details) | Purchase | 33 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2173
| CGST 9% Purchase |  |  | 2173
received bills
2018-09-25 | (as per details) | Purchase | 34 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 1448
| SGST 9% Purchase |  |  | 1448
received bills
2018-09-26 | (as per details) | Purchase | 35 | 16126
Relcon Infraprojects Ltd(Ambrish)
| CGST 9% Purchase |  |  | 1451.5
| SGST 9% Purchase |  |  | 1451.5
received bills
2018-09-27 | (as per details) | Purchase | 36 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 1448
| CGST 9% Purchase |  |  | 1448
received bills
2018-09-27 | (as per details) | Purchase | 37 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 1448
| SGST 9% Purchase |  |  | 1448
received bills
2018-09-27 | (as per details) | Purchase | 38 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2173
| CGST 9% Purchase |  |  | 2173
received bills
2018-09-27 | (as per details) | Purchase | 39 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 1448
| SGST 9% Purchase |  |  | 1448
received bills
2018-09-27 | (as per details) | Purchase | 40 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 1448
| CGST 9% Purchase |  |  | 1448
received bills
2018-09-27 | (as per details) | Purchase | 41 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 1448
| SGST 9% Purchase |  |  | 1448
received bills
2018-09-28 | (as per details) | Purchase | 42 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 1448
| CGST 9% Purchase |  |  | 1448
received bills
2018-09-28 | (as per details) | Purchase | 43 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2173
| SGST 9% Purchase |  |  | 2173
received bills
2018-09-28 | (as per details) | Purchase | 44 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 1448
| CGST 9% Purchase |  |  | 1448
received bills
2018-09-28 | (as per details) | Purchase | 45 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2173
| SGST 9% Purchase |  |  | 2173
received bills
2018-09-29 | (as per details) | Purchase | 46 | 32253
Relcon Infraprojects Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2902.5
| CGST 9% Purchase |  |  | 2902.5
received bills
2018-10-01 | (as per details) | Purchase | 47 | 40316
Relcon Infraprojects Ltd(Ambrish)
| CGST 9% Purchase |  |  | 3628
| SGST 9% Purchase |  |  | 3628
received bills
2018-10-01 | (as per details) | Purchase | 48 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 1448
| CGST 9% Purchase |  |  | 1448
received bills
2018-10-01 | (as per details) | Purchase | 49 | 59040
Bhairav Tarpaulins(Ambrish)
| CGST 9% Purchase |  |  | 5313.5
| SGST 9% Purchase |  |  | 5313.5
received bills
2018-10-01 | Almighty Enterprises | Purchase | 50 | 2400
received bills
2018-10-03 | (as per details) | Purchase | 51 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 1448
| SGST 9% Purchase |  |  | 1448
received bills
2018-10-03 | (as per details) | Purchase | 52 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 1448
| CGST 9% Purchase |  |  | 1448
received bills
2018-10-03 | (as per details) | Purchase | 53 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 1448
| SGST 9% Purchase |  |  | 1448
received bills
2018-10-03 | (as per details) | Purchase | 54 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2173
| CGST 9% Purchase |  |  | 2173
received bills
2018-10-04 | (as per details) | Purchase | 55 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 1448
| SGST 9% Purchase |  |  | 1448
received bills
2018-10-04 | (as per details) | Purchase | 56 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 1448
| CGST 9% Purchase |  |  | 1448
received bills
2018-10-04 | (as per details) | Purchase | 57 | 29504
ACC Limited(Ambrish)
| SGST 9% Purchase |  |  | 2655
| CGST 9% Purchase |  |  | 2656
received bills
2018-10-04 | (as per details) | Purchase | 58 | 21458
ACC Limited(Ambrish)
| CGST 9% Purchase |  |  | 1931
| SGST 9% Purchase |  |  | 1931
received bills
2018-10-05 | (as per details) | Purchase | 59 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 1448
| SGST 9% Purchase |  |  | 1448
received bills
2018-10-05 | (as per details) | Purchase | 60 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 1448
| CGST 9% Purchase |  |  | 1448
received bills
2018-10-10 | Rajput Electricals | Purchase | 61 | 43300
received bills
2018-10-11 | (as per details) | Purchase | 62 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2173
| SGST 9% Purchase |  |  | 2173
received bills
2018-10-11 | (as per details) | Purchase | 63 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 1448
| CGST 9% Purchase |  |  | 1448
received bills
2018-10-11 | (as per details) | Purchase | 64 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 1448
| SGST 9% Purchase |  |  | 1448
received bills
2018-10-11 | (as per details) | Purchase | 65 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2173
| CGST 9% Purchase |  |  | 2173
received bills
2018-10-11 | (as per details) | Purchase | 66 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2173
| SGST 9% Purchase |  |  | 2173
received bills
2018-10-11 | (as per details) | Purchase | 67 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 1448
| CGST 9% Purchase |  |  | 1448
received bills
2018-10-12 | (as per details) | Purchase | 68 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2173
| SGST 9% Purchase |  |  | 2173
received bills
2018-10-12 | (as per details) | Purchase | 69 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 1448
| CGST 9% Purchase |  |  | 1448
received bills
2018-10-12 | (as per details) | Purchase | 70 | 16126
Relcon Infraprojects Ltd(Ambrish)
| SGST 9% Purchase |  |  | 1451.5
| CGST 9% Purchase |  |  | 1451.5
received bills
2018-10-13 | (as per details) | Purchase | 71 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2173
| SGST 9% Purchase |  |  | 2173
received bills
2018-10-13 | (as per details) | Purchase | 72 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 1448
| SGST 9% Purchase |  |  | 1448
received bills
2018-10-13 | (as per details) | Purchase | 73 | 40316
Relcon Infraprojects Ltd(Ambrish)
| CGST 9% Purchase |  |  | 3628
| SGST 9% Purchase |  |  | 3628
received bills
2018-10-15 | (as per details) | Purchase | 74 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2173
| CGST 9% Purchase |  |  | 2173
received bills
2018-10-15 | (as per details) | Purchase | 75 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2173
| CGST 9% Purchase |  |  | 2173
received bills
2018-10-15 | (as per details) | Purchase | 76 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 1448
| SGST 9% Purchase |  |  | 1448
received bills
2018-10-16 | (as per details) | Purchase | 77 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2173
| CGST 9% Purchase |  |  | 2173
received bills
2018-10-16 | (as per details) | Purchase | 78 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2173
| SGST 9% Purchase |  |  | 2173
received bills
2018-10-16 | (as per details) | Purchase | 79 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 1448
| CGST 9% Purchase |  |  | 1448
received bills
2018-10-16 | (as per details) | Purchase | 80 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 1448
| SGST 9% Purchase |  |  | 1448
received bills
2018-10-16 | (as per details) | Purchase | 81 | 2500
SKG Project & Engg Pvt.Ltd.
| SGST 9% Purchase |  |  | 225
| CGST 9% Purchase |  |  | 225
received bills
2018-10-17 | (as per details) | Purchase | 82 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2173
| CGST 9% Purchase |  |  | 2173
received bills
2018-10-17 | (as per details) | Purchase | 83 | 16093
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 1448
| SGST 9% Purchase |  |  | 1448
received bills
2018-10-17 | (as per details) | Purchase | 84 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2173
| CGST 9% Purchase |  |  | 2173
received bills
2018-10-19 | (as per details) | Purchase | 85 | 21458
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 1931
| SGST 9% Purchase |  |  | 1931
reveived bills
2018-10-19 | (as per details) | Purchase | 86 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2173
| CGST 9% Purchase |  |  | 2173
reved bills
2018-10-19 | (as per details) | Purchase | 87 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2173
| SGST 9% Purchase |  |  | 2173
received bills
2018-10-20 | (as per details) | Purchase | 88 | 21458
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 1931
| CGST 9% Purchase |  |  | 1931
RECEIVED BILLS
2018-10-20 | (as per details) | Purchase | 89 | 26822
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2414
| SGST 9% Purchase |  |  | 2414
RECEIVED BILLS
2018-10-21 | (as per details) | Purchase | 90 | 16093
ACC Limited(Ambrish)
| SGST 9% Purchase |  |  | 1448.5
| CGST 9% Purchase |  |  | 1448.5
RECEIVED BILLS
2018-10-21 | (as per details) | Purchase | 91 | 21458
ACC Limited(Ambrish)
| CGST 9% Purchase |  |  | 1931
| SGST 9% Purchase |  |  | 1931
RECEIVED BILLS
2018-10-21 | (as per details) | Purchase | 92 | 29504
ACC Limited(Ambrish)
| SGST 9% Purchase |  |  | 2655
| CGST 9% Purchase |  |  | 2656
RECEIVED BILLS
2018-10-22 | (as per details) | Purchase | 93 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2173
| CGST 9% Purchase |  |  | 2173
RECEIVED BILLS
2018-10-22 | (as per details) | Purchase | 94 | 26822
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2414
| SGST 9% Purchase |  |  | 2414
RECEIVED BILLSD
2018-10-23 | (as per details) | Purchase | 95 | 21458
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 1931
| CGST 9% Purchase |  |  | 1931
RECEIVED BILLS
2018-10-23 | (as per details) | Purchase | 96 | 18775
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 1690
| SGST 9% Purchase |  |  | 1690
RECEIVED BILLS
2018-10-23 | (as per details) | Purchase | 97 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2173
| CGST 9% Purchase |  |  | 2173
RECEIVED BILLS
2018-10-24 | (as per details) | Purchase | 98 | 29504
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2655
| SGST 9% Purchase |  |  | 2655
RECEIVED BILLS
2018-10-24 | (as per details) | Purchase | 99 | 18775
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 1690
| CGST 9% Purchase |  |  | 1690
RECEUVED BILLS
2018-10-24 | (as per details) | Purchase | 100 | 21458
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 1931
| SGST 9% Purchase |  |  | 1931
RECEIVED BILLS
2018-10-24 | (as per details) | Purchase | 101 | 4030
Mateshvari Electric & Hardwear Stores(A)
| SGST 9% Purchase |  |  | 363
| CGST 9% Purchase |  |  | 363
received bills
2018-10-25 | (as per details) | Purchase | 102 | 29504
ACC Limited(Ambrish)
| CGST 9% Purchase |  |  | 2655
| SGST 9% Purchase |  |  | 2656
received bills
2018-10-25 | (as per details) | Purchase | 103 | 21458
ACC Limited(Ambrish)
| SGST 9% Purchase |  |  | 1931
| CGST 9% Purchase |  |  | 1931
received bills
2018-10-25 | (as per details) | Purchase | 104 | 26822
ACC Limited(Ambrish)
| CGST 9% Purchase |  |  | 2414
| SGST 9% Purchase |  |  | 2414
received bills
2018-10-26 | (as per details) | Purchase | 105 | 18775
ACC Limited(Ambrish)
| CGST 9% Purchase |  |  | 1690
| SGST 9% Purchase |  |  | 1690
received bills
2018-10-26 | (as per details) | Purchase | 106 | 18775
ACC Limited(Ambrish)
| SGST 9% Purchase |  |  | 1690
| CGST 9% Purchase |  |  | 1690
received bills
2018-10-26 | (as per details) | Purchase | 107 | 29504
ACC Limited(Ambrish)
| CGST 9% Purchase |  |  | 2655
| SGST 9% Purchase |  |  | 2656
received bills
2018-10-27 | (as per details) | Purchase | 108 | 18775
ACC Limited(Ambrish)
| SGST 9% Purchase |  |  | 1690
| CGST 9% Purchase |  |  | 1690
received bills
2018-10-27 | (as per details) | Purchase | 109 | 18775
ACC Limited(Ambrish)
| SGST 9% Purchase |  |  | 1690
| CGST 9% Purchase |  |  | 1690
received bills
2018-10-27 | (as per details) | Purchase | 110 | 24140
ACC Limited(Ambrish)
| CGST 9% Purchase |  |  | 2173
| SGST 9% Purchase |  |  | 2172
received bills
2018-10-27 | (as per details) | Purchase | 111 | 24140
ACC Limited(Ambrish)
| SGST 9% Purchase |  |  | 2173
| CGST 9% Purchase |  |  | 2172
received bills
2018-10-29 | (as per details) | Purchase | 112 | 21458
ACC Limited(Ambrish)
| CGST 9% Purchase |  |  | 1931
| SGST 9% Purchase |  |  | 1931
received bills
2018-10-29 | (as per details) | Purchase | 113 | 24140
ACC Limited(Ambrish)
| SGST 9% Purchase |  |  | 2173
| CGST 9% Purchase |  |  | 2172
received bills
2018-10-30 | (as per details) | Purchase | 114 | 21458
ACC Limited(Ambrish)
| SGST 9% Purchase |  |  | 1931
| CGST 9% Purchase |  |  | 1931
received bills
2018-10-30 | (as per details) | Purchase | 115 | 24140
ACC Limited(Ambrish)
| CGST 9% Purchase |  |  | 2173
| SGST 9% Purchase |  |  | 2172
received bills
2018-12-05 | Bharuka Cement Suppliers | Purchase | 116 | 3970
received bills
2018-12-21 | (as per details) | Purchase | 117 | 285000
K.N.Enterprise
| CGST 9% Purchase |  |  | 25650
| SGST 9% Purchase |  |  | 25650
received bills
2018-12-23 | Bharuka Cement Suppliers | Purchase | 118 | 2260
received bills
2018-12-27 | YNational Enterprise | Purchase | 119 | 7830
received bills
2019-01-06 | Maharashtra Vikas Tranport & General Kamgar Sanghat | Purchase | 121 | 11500
received bills
2019-01-09 | (as per details) | Purchase | 122 | 856540
K.C.Ferro
| CGST 9% Purchase |  |  | 77089
| SGST 9% Purchase |  |  | 77088
received bills
2019-01-16 | (as per details) | Purchase | 123 | 872909
K.N.Enterprise
| SGST 9% Purchase |  |  | 59122
| CGST 9% Purchase |  |  | 59122
received bills
2019-01-17 | (as per details) | Purchase | 124 | 13898
Sukun Agencies
| CGST 9% Purchase |  |  | 1251
| SGST 9% Purchase |  |  | 1251
received bills
2019-01-21 | (as per details) | Purchase | 126 | 21400
Deepam Infotech(Kurla)
| CGST 9% Purchase |  |  | 2116
| SGST 9% Purchase |  |  | 2116
received bills
2019-01-23 | (as per details) | Purchase | 128 | 835488
K.C.Ferro
| SGST 9% Purchase |  |  | 75194
| CGST 9% Purchase |  |  | 75193
received bills
2019-01-23 | Maharashtra Vikas Tranport & General Kamgar Sanghat | Purchase | 129 | 11752
recived billws
2019-02-04 | (as per details) | Purchase | 132 | 18220
Techmaxx
| CGST 9% Purchase |  |  | 1640
| SGST 9% Purchase |  |  | 1640
received bills
2019-02-15 | (as per details) | Purchase | 133 | 492779
K.C.Ferro
| CGST 9% Purchase |  |  | 44350
| SGST 9% Purchase |  |  | 44350
received bills
2019-02-16 | Maharashtra Vikas Tranport & General Kamgar Sanghat | Purchase | 134 | 3100
received bills
2019-02-16 | Bharuka Cement Suppliers | Purchase | 135 | 11450
received bills
2019-02-16 | (as per details) | Purchase | 136 | 8774
New Super Hiring Hiring
| CGST 9% Purchase |  |  | 790
| SGST 9% Purchase |  |  | 790
received bills
2019-02-19 | Maharashtra Vikas Tranport & General Kamgar Sanghat | Purchase | 137 | 11440
received bills
2019-02-19 | (as per details) | Purchase | 138 | 6000
Power Post(Ambrish)
| CGST 9% Purchase |  |  | 540
| SGST 9% Purchase |  |  | 540
RECEIVED BILLS
2019-02-20 | Aqsa Enterprises | Purchase | 139 | 35800
received bills
2019-03-15 | (as per details) | Purchase | 143 | 5000
Power Post(Ambrish)
| SGST 9% Purchase |  |  | 450
| CGST 9% Purchase |  |  | 450
received bills
2019-04-10 | (as per details) | Purchase | 1 | 41900
Deepam Infotech(Kurla)
| CGST 9% Purchase |  |  | 3841
| SGST 9% Purchase |  |  | 3841
received bills
2019-04-19 | (as per details) | Purchase | 2 | 412751
K.C.Ferro
| SGST 9% Purchase |  |  | 37147.5
| CGST 9% Purchase |  |  | 37147.5
received bills
2019-04-19 | (as per details) | Purchase | 3 | 11291
Mody Associates Co.(Ambrish)
| SGST 9% Purchase |  |  | 1016
| CGST 9% Purchase |  |  | 1016
received bills
2019-04-26 | (as per details) | Purchase | 4 | 24979
Prism Johnson Limited(Kurla)
| CGST 9% Purchase |  |  | 2248
| SGST 9% Purchase |  |  | 2248
received bills
2019-04-26 | (as per details) | Purchase | 5 | 24979
Prism Johnson Limited(Kurla)
| SGST 9% Purchase |  |  | 2248
| CGST 9% Purchase |  |  | 2248
received bills
2019-04-26 | (as per details) | Purchase | 6 | 27754
Prism Johnson Limited(Kurla)
| CGST 9% Purchase |  |  | 2498
| SGST 9% Purchase |  |  | 2498
receivedbills
2019-04-26 | (as per details) | Purchase | 7 | 25481
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2293
| CGST 9% Purchase |  |  | 2293
received bills
2019-04-26 | (as per details) | Purchase | 8 | 24979
Prism Johnson Limited(Kurla)
| SGST 9% Purchase |  |  | 2248
| CGST 9% Purchase |  |  | 2248
received bills
2019-04-26 | (as per details) | Purchase | 9 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2172.5
| SGST 9% Purchase |  |  | 2172.5
received bills
2019-04-26 | (as per details) | Purchase | 10 | 24979
Prism Johnson Limited(Kurla)
| CGST 9% Purchase |  |  | 2248
| SGST 9% Purchase |  |  | 2248
received bills
2019-04-27 | (as per details) | Purchase | 11 | 24979
Prism Johnson Limited(Kurla)
| CGST 9% Purchase |  |  | 2248
| SGST 9% Purchase |  |  | 2248
received bills
2019-04-27 | (as per details) | Purchase | 12 | 33305
Prism Johnson Limited(Kurla)
| SGST 9% Purchase |  |  | 2997.5
| CGST 9% Purchase |  |  | 2997.5
received bills
2019-04-27 | (as per details) | Purchase | 13 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2172.5
| CGST 9% Purchase |  |  | 2172.5
received bills
2019-04-28 | (as per details) | Purchase | 14 | 33305
Prism Johnson Limited(Kurla)
| CGST 9% Purchase |  |  | 2997.5
| SGST 9% Purchase |  |  | 2997.5
received bills
2019-04-28 | (as per details) | Purchase | 15 | 33305
Prism Johnson Limited(Kurla)
| SGST 9% Purchase |  |  | 2997.5
| CGST 9% Purchase |  |  | 2997.5
received bills
2019-04-28 | (as per details) | Purchase | 16 | 24979
Prism Johnson Limited(Kurla)
| CGST 9% Purchase |  |  | 2248
| SGST 9% Purchase |  |  | 2248
received bills
2019-04-28 | (as per details) | Purchase | 17 | 24979
Prism Johnson Limited(Kurla)
| SGST 9% Purchase |  |  | 2248
| CGST 9% Purchase |  |  | 2248
received bills
2019-04-30 | (as per details) | Purchase | 18 | 33305
Prism Johnson Limited(Kurla)
| CGST 9% Purchase |  |  | 2997.5
| SGST 9% Purchase |  |  | 2997.5
received bills
2019-04-30 | (as per details) | Purchase | 19 | 24979
Prism Johnson Limited(Kurla)
| SGST 9% Purchase |  |  | 2248
| CGST 9% Purchase |  |  | 2248
received bills
2019-04-30 | (as per details) | Purchase | 20 | 33305
Prism Johnson Limited(Kurla)
| SGST 9% Purchase |  |  | 2997.5
| CGST 9% Purchase |  |  | 2997.5
received bills
2019-05-02 | (as per details) | Purchase | 23 | 32186
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2897
| SGST 9% Purchase |  |  | 2897
received bills
2019-05-02 | (as per details) | Purchase | 24 | 32186
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2897
| CGST 9% Purchase |  |  | 2897
received bills
2019-05-02 | (as per details) | Purchase | 25 | 24979
Prism Johnson Limited(Kurla)
| SGST 9% Purchase |  |  | 2248
| CGST 9% Purchase |  |  | 2248
received bills
2019-05-03 | (as per details) | Purchase | 26 | 33305
Prism Johnson Limited(Kurla)
| SGST 9% Purchase |  |  | 2997.5
| CGST 9% Purchase |  |  | 2997.5
received bills
2019-05-03 | (as per details) | Purchase | 27 | 33305
Prism Johnson Limited(Kurla)
| CGST 9% Purchase |  |  | 2997.5
| SGST 9% Purchase |  |  | 2997.5
received bills
2019-05-03 | (as per details) | Purchase | 28 | 33305
Prism Johnson Limited(Kurla)
| CGST 9% Purchase |  |  | 2997
| SGST 9% Purchase |  |  | 2998
received bills
2019-05-04 | (as per details) | Purchase | 29 | 24979
Prism Johnson Limited(Kurla)
| CGST 9% Purchase |  |  | 2248
| SGST 9% Purchase |  |  | 2248
received bills
2019-05-04 | (as per details) | Purchase | 30 | 33305
Prism Johnson Limited(Kurla)
| SGST 9% Purchase |  |  | 2997.5
| CGST 9% Purchase |  |  | 2997.5
received bills
2019-05-04 | (as per details) | Purchase | 31 | 33305
Prism Johnson Limited(Kurla)
| CGST 9% Purchase |  |  | 2997.5
| SGST 9% Purchase |  |  | 2997.5
received bills
2019-05-06 | (as per details) | Purchase | 32 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2173
| SGST 9% Purchase |  |  | 2172
received bills
2019-05-06 | (as per details) | Purchase | 33 | 33305
Prism Johnson Limited(Kurla)
| SGST 9% Purchase |  |  | 2997.5
| CGST 9% Purchase |  |  | 2997.5
received bills
2019-05-06 | (as per details) | Purchase | 34 | 24978
Prism Johnson Limited(Kurla)
| CGST 9% Purchase |  |  | 2248.5
| SGST 9% Purchase |  |  | 2248.5
received bills
2019-05-06 | (as per details) | Purchase | 35 | 24979
Prism Johnson Limited(Kurla)
| CGST 9% Purchase |  |  | 2248
| SGST 9% Purchase |  |  | 2248
received bills
2019-05-07 | (as per details) | Purchase | 36 | 24979
Prism Johnson Limited(Kurla)
| SGST 9% Purchase |  |  | 2248
| CGST 9% Purchase |  |  | 2248
received bills
2019-05-07 | (as per details) | Purchase | 37 | 24979
Prism Johnson Limited(Kurla)
| CGST 9% Purchase |  |  | 2248
| SGST 9% Purchase |  |  | 2248
received bills
2019-05-07 | (as per details) | Purchase | 38 | 24979
Prism Johnson Limited(Kurla)
| SGST 9% Purchase |  |  | 2248
| CGST 9% Purchase |  |  | 2248
received bills
2019-05-07 | (as per details) | Purchase | 39 | 32186
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2897
| CGST 9% Purchase |  |  | 2897
received bills
2019-05-08 | (as per details) | Purchase | 40 | 24979
Prism Johnson Limited(Kurla)
| SGST 9% Purchase |  |  | 2248
| CGST 9% Purchase |  |  | 2248
received bills
2019-05-08 | (as per details) | Purchase | 41 | 33305
Prism Johnson Limited(Kurla)
| CGST 9% Purchase |  |  | 2997.5
| SGST 9% Purchase |  |  | 2997.5
received bills
2019-05-08 | (as per details) | Purchase | 42 | 24979
Prism Johnson Limited(Kurla)
| SGST 9% Purchase |  |  | 2248
| CGST 9% Purchase |  |  | 2248
received bills
2019-05-08 | (as per details) | Purchase | 43 | 24979
Prism Johnson Limited(Kurla)
| CGST 9% Purchase |  |  | 2248
| SGST 9% Purchase |  |  | 2248
received bills
2019-05-09 | (as per details) | Purchase | 44 | 24979
Prism Johnson Limited(Kurla)
| CGST 9% Purchase |  |  | 2248
| SGST 9% Purchase |  |  | 2248
received bills
2019-05-09 | (as per details) | Purchase | 45 | 33305
Prism Johnson Limited(Kurla)
| SGST 9% Purchase |  |  | 2997.5
| CGST 9% Purchase |  |  | 2997.5
received bills
2019-05-09 | (as per details) | Purchase | 46 | 33305
Prism Johnson Limited(Kurla)
| CGST 9% Purchase |  |  | 2997.5
| SGST 9% Purchase |  |  | 2997.5
received bills
2019-05-10 | (as per details) | Purchase | 47 | 24979
Prism Johnson Limited(Kurla)
| CGST 9% Purchase |  |  | 2248
| SGST 9% Purchase |  |  | 2248
received bills
2019-05-10 | (as per details) | Purchase | 48 | 33305
Prism Johnson Limited(Kurla)
| SGST 9% Purchase |  |  | 2997.5
| CGST 9% Purchase |  |  | 2997.5
received bills
2019-05-10 | (as per details) | Purchase | 49 | 32186
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2897
| SGST 9% Purchase |  |  | 2897
received bills
2019-05-11 | (as per details) | Purchase | 51 | 24979
Prism Johnson Limited(Kurla)
| SGST 9% Purchase |  |  | 2248
| CGST 9% Purchase |  |  | 2248
received bills
2019-05-11 | (as per details) | Purchase | 52 | 24979
Prism Johnson Limited(Kurla)
| CGST 9% Purchase |  |  | 2248
| SGST 9% Purchase |  |  | 2248
received bills
2019-05-11 | (as per details) | Purchase | 53 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2173
| CGST 9% Purchase |  |  | 2172
received bills
2019-05-11 | (as per details) | Purchase | 54 | 32186
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2897
| SGST 9% Purchase |  |  | 2897
received bills
2019-05-13 | (as per details) | Purchase | 55 | 24979
Prism Johnson Limited(Kurla)
| CGST 9% Purchase |  |  | 2248
| SGST 9% Purchase |  |  | 2248
received bills
2019-05-13 | (as per details) | Purchase | 56 | 24979
Prism Johnson Limited(Kurla)
| SGST 9% Purchase |  |  | 2248
| CGST 9% Purchase |  |  | 2248
received bills
2019-05-13 | (as per details) | Purchase | 57 | 24979
Prism Johnson Limited(Kurla)
| CGST 9% Purchase |  |  | 2248
| SGST 9% Purchase |  |  | 2248
received bills
2019-05-13 | (as per details) | Purchase | 58 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| SGST 9% Purchase |  |  | 2173
| CGST 9% Purchase |  |  | 2172
received bills
2019-05-13 | (as per details) | Purchase | 59 | 24140
Godrej & Boyce Mfg Co.Ltd(Ambrish)
| CGST 9% Purchase |  |  | 2173
| SGST 9% Purchase |  |  | 2172
received bills
2019-05-14 | (as per details) | Purchase | 60 | 33305
Prism Johnson Limited(Kurla)
| SGST 9% Purchase |  |  | 2997.5
| CGST 9% Purchase |  |  | 2997.5
received bills
2019-05-14 | (as per details) | Purchase | 61 | 24979
Prism Johnson Limited(Kurla)
| CGST 9% Purchase |  |  | 2248
| SGST 9% Purchase |  |  | 2248
received biills
2019-05-14 | (as per details) | Purchase | 62 | 24979
Prism Johnson Limited(Kurla)
| SGST 9% Purchase |  |  | 2248
| CGST 9% Purchase |  |  | 2248
received bills
2019-05-14 | (as per details) | Purchase | 63 | 24979
Prism Johnson Limited(Kurla)
| SGST 9% Purchase |  |  | 2248
| CGST 9% Purchase |  |  | 2248
received bills
2019-05-22 | (as per details) | Purchase | 65 | 1950
Deepam Infotech(Kurla)
| CGST 9% Purchase |  |  | 175.5
| SGST 9% Purchase |  |  | 175.5
received bills
2019-06-13 | (as per details) | Purchase | 66 | 1780
Sukun Agencies
| SGST 9% Purchase |  |  | 160
| CGST 9% Purchase |  |  | 160
received bills
2019-06-25 | (as per details) | Purchase | 69 | 4100
Techmaxx
| SGST 9% Purchase |  |  | 369
| CGST 9% Purchase |  |  | 369
received bills
2019-07-27 | (as per details) | Purchase | 70 | 25847.5
Surya Enterprises
| CGST 9% Purchase |  |  | 2326.25
| SGST 9% Purchase |  |  | 2326.25
received bills
2019-09-06 | (as per details) | Purchase | 81 | 23700
Minit Tube
| CGST 9% Purchase |  |  | 2133
| SGST 9% Purchase |  |  | 2133
received bills
2019-10-15 | (as per details) | Purchase | 89 | 996
Variety Plywood
| CGST 9% Purchase |  |  | 89.5
| SGST 9% Purchase |  |  | 89.5
received bills
2019-10-24 | (as per details) | Purchase | 92 | 224.5
Variety Plywood
| CGST 9% Purchase |  |  | 20.25
| SGST 9% Purchase |  |  | 20.25
received bills
2020-09-30 | (as per details) | Purchase | 8 | 7300
M/s. Vaman Pacific Technology
| CGST 9% Purchase |  |  | 657
| SGST 9% Purchase |  |  | 657
received bills & transfer
2020-11-20 | (as per details) | Purchase | 16 | 38135.59
Maxell
| CGST 9% Purchase |  |  | 3432.2
| SGST 9% Purchase |  |  | 3432.21
being bills received for purchase of Mobile
2020-11-20 | (as per details) | Purchase | 17 | 38135.59
Maxell
| SGST 9% Purchase |  |  | 3432.21
| CGST 9% Purchase |  |  | 3432.2
received bills for purchase of Mobile
2020-12-01 | (as per details) | Purchase | 21 | 2403.14
Jai Vijayalaxmi Stationery & Xerox
| CGST 9% Purchase |  |  | 147.93
| SGST 9% Purchase |  |  | 147.93
2021-01-02 | (as per details) | Purchase | 31 | 1534
Jai Vijayalaxmi Stationery & Xerox
| CGST 9% Purchase |  |  | 112.14
| SGST 9% Purchase |  |  | 112.14
Round of
received on 2/10/20 but entry is made on 2.1.21
2021-01-02 | (as per details) | Purchase | 32 | 6497
Jai Vijayalaxmi Stationery & Xerox
| SGST 9% Purchase |  |  | 457.47
| CGST 9% Purchase |  |  | 457.47
| Round of |  |  | 0.06
being amt bills received dated 1.11.20 but entru made 2.1.21
2021-01-10 | (as per details) | Purchase | 34 | 1677
Jai Vijayalaxmi Stationery & Xerox
| SGST 9% Purchase |  |  | 111.57
| CGST 9% Purchase |  |  | 111.57
Round of
received bills
2021-01-10 | (as per details) | Purchase | 35 | 8500
M/s. Vaman Pacific Technology
| SGST 9% Purchase |  |  | 765
| CGST 9% Purchase |  |  | 765
received bills dated 18.11.20
2021-01-31 | (as per details) | Purchase | 37 | 4245
Jai Vijayalaxmi Stationery & Xerox
| CGST 9% Purchase |  |  | 278.25
| SGST 9% Purchase |  |  | 278.25
| Round of |  |  | 0.5
received bills & transfer
2021-02-01 | (as per details) | Purchase | 38 | 10800
Software at Work (India) Pvt Ltd
| CGST 9% Purchase |  |  | 972
| SGST 9% Purchase |  |  | 972
being amt bills received for tally renewal
2021-02-13 | (as per details) | Purchase | 45 | 3650
M/s. Vaman Pacific Technology
| CGST 9% Purchase |  |  | 328.5
| SGST 9% Purchase |  |  | 328.5
received bill dated 30.1.21 received on 13.2.21
2021-02-22 | (as per details) | Purchase | 47 | 7300
M/s. Vaman Pacific Technology
| SGST 9% Purchase |  |  | 657
| CGST 9% Purchase |  |  | 657
received bills
2021-03-02 | (as per details) | Purchase | 55 | 5480
Jai Vijayalaxmi Stationery & Xerox
| CGST 9% Purchase |  |  | 198.9
| SGST 9% Purchase |  |  | 198.9
| CGST @ 6% |  |  | 196.2
| SGST @ 6% on Purchases |  |  | 196.2
Round of
bills received
2021-03-31 | (as per details) | Purchase | 64 | 6924
Jai Vijayalaxmi Stationery & Xerox
| SGST @ 6% on Purchases |  |  | 351.24
| CGST @ 6% |  |  | 351.24
| SGST 9% Purchase |  |  | 96.3
| CGST 9% Purchase |  |  | 96.3
Round of
being bills received
2021-06-04 | (as per details) | Purchase | 19 | 10000
Software at Work (India) Pvt Ltd
| SGST 9% Purchase |  |  | 900
| CGST 9% Purchase |  |  | 900
bills received
2021-07-05 | Pooja Telecom | Purchase | 26 | 8110
received bills
2021-07-05 | Pooja Telecom | Purchase | 27 | 5585
received bills
2021-07-31 | (as per details) | Purchase | 32 | 1073
Jai Vijayalaxmi Stationery & Xerox
| SGST @ 6% on Purchases |  |  | 73.68
| CGST @ 6% on Purchases |  |  | 73.68
Round of
received bills
2021-07-31 | (as per details) | Purchase | 33 | 4536
Jai Vijayalaxmi Stationery & Xerox
| CGST 9% Purchase |  |  | 289.65
| SGST 9% Purchase |  |  | 289.35
received bills
2021-07-31 | (as per details) | Purchase | 34 | 4745
Jai Vijayalaxmi Stationery & Xerox
| SGST 9% Purchase |  |  | 318.15
| CGST 9% Purchase |  |  | 318.15
Round of
received bills
2021-07-31 | (as per details) | Purchase | 35 | 1402
Jai Vijayalaxmi Stationery & Xerox
| CGST 9% Purchase |  |  | 86.37
| SGST 9% Purchase |  |  | 86.37
| Round of |  |  | 0.26
received bills
2021-08-12 | (as per details) | Purchase | 36 | 42402
Shree Laxmi Saw Mills Kurla
| CGST 9% Purchase |  |  | 3816.18
| SGST 9% Purchase |  |  | 3816.18
Round of
received bills
2021-08-26 | (as per details) | Purchase | 41 | 3000
Power Post(Ambrish)
| CGST 9% Purchase |  |  | 270
| SGST 9% Purchase |  |  | 270
received bills 1.9.21
2021-09-02 | (as per details) | Purchase | 42 | 2551
Jai Vijayalaxmi Stationery & Xerox
| CGST 9% Purchase |  |  | 190.86
| SGST 9% Purchase |  |  | 190.86
| Round of |  |  | 0.28
received bills
2021-09-17 | (as per details) | Purchase | 48 | 42402
Shree Laxmi Saw Mills Kurla
| SGST 9% Purchase |  |  | 3816.18
| CGST 9% Purchase |  |  | 3816.18
Round of
received bills dated 10.9/.21
2021-10-07 | (as per details) | Purchase | 49 | 84804
Shree Laxmi Saw Mills Kurla
| CGST 9% Purchase |  |  | 7632.36
| SGST 9% Purchase |  |  | 7632.64
received bills
2021-11-01 | (as per details) | Purchase | 54 | 6386
Jai Vijayalaxmi Stationery & Xerox
| CGST 9% Purchase |  |  | 502.79
| SGST 9% Purchase |  |  | 502.79
| Round of |  |  | 0.42
Received bills
2021-11-01 | (as per details) | Purchase | 55 | 4414
Jai Vijayalaxmi Stationery & Xerox
| CGST 9% Purchase |  |  | 453.26
| SGST 9% Purchase |  |  | 453.26
| Round of |  |  | 0.48
received bills
2021-11-17 | (as per details) | Purchase | 56 | 84804
Shree Laxmi Saw Mills Kurla
| SGST 9% Purchase |  |  | 7632.36
| CGST 9% Purchase |  |  | 7632.36
| Round of |  |  | 0.28
received bills 1939/21-22
2021-12-11 | (as per details) | Purchase | 57 | 1440.67
Sukun Agencies
| CGST 9% Purchase |  |  | 129.66
| SGST 9% Purchase |  |  | 129.67
2021-12-13 | (as per details) | Purchase | 58 | 174906
Madhav Marble & Genite(Kurla)
| CGST 9% Purchase |  |  | 15742
| SGST 9% Purchase |  |  | 15742
2021-12-13 | (as per details) | Purchase | 59 | 2201
Shree Laxmi Saw Mills Kurla
| CGST 9% Purchase |  |  | 198.09
| SGST 9% Purchase |  |  | 198.09
Round of
2022-01-01 | (as per details) | Purchase | 60 | 2490
Shree Mahavir Ceramics (Ambarish
| CGST 9% Purchase |  |  | 224.1
| SGST 9% Purchase |  |  | 224.1
Round of
2022-01-06 | (as per details) | Purchase | 62 | 635881.36
Mody Associates Co.(Ambrish)
| CGST 9% Purchase |  |  | 57229.32
| SGST 9% Purchase |  |  | 57229.32
| TCS 1% |  |  | 750.34
Round of
2022-01-06 | (as per details) | Purchase | 63 | 16628.75
Mody Associates Co.(Ambrish)
| CGST 9% Purchase |  |  | 1496.59
| Output SGST |  |  | 1496.59
| TCS 1% |  |  | 19.62
| Round of |  |  | 0.45
2022-01-07 | (as per details) | Purchase | 64 | 266163
Madhav Marble & Genite(Kurla)
| SGST 9% Purchase |  |  | 23955
| CGST 9% Purchase |  |  | 23955
2022-01-07 | (as per details) | Purchase | 65 | 3986
Jai Vijayalaxmi Stationery & Xerox
| GST 12% |  |  | 190.32
| GST 18% |  |  | 427.5
| GST 28% |  |  | 7.18
2022-01-07 | (as per details) | Purchase | 66 | 12806
Jai Vijayalaxmi Stationery & Xerox
| GST 12% |  |  | 842.16
| GST 18% |  |  | 1041.84
2022-01-10 | (as per details) | Purchase | 67 | 46610.18
Schindalr India Pvt Ltd Ambarish
| CGST 9% Purchase |  |  | 4195
| SGST 9% Purchase |  |  | 4195
2022-01-10 | (as per details) | Purchase | 68 | 41313.55
Schindalr India Pvt Ltd Ambarish
| SGST 9% Purchase |  |  | 3718
| CGST 9% Purchase |  |  | 3718
2022-01-10 | (as per details) | Purchase | 69 | 41313.55
Schindalr India Pvt Ltd Ambarish
| CGST 9% Purchase |  |  | 3718
| SGST 9% Purchase |  |  | 3718
2022-01-10 | (as per details) | Purchase | 70 | 42372.88
Schindalr India Pvt Ltd Ambarish
| SGST 9% Purchase |  |  | 3814
| CGST 9% Purchase |  |  | 3814
2022-01-16 | (as per details) | Purchase | 71 | 594309.31
Mody Associates Co.(Ambrish)
| CGST 9% Purchase |  |  | 53487.84
| SGST 9% Purchase |  |  | 53487.84
| TCS 1% |  |  | 701.29
Round of
2022-01-16 | (as per details) | Purchase | 72 | 19102.5
Mody Associates Co.(Ambrish)
| CGST 9% Purchase |  |  | 1719.22
| SGST 9% Purchase |  |  | 1719.22
| TCS 1% |  |  | 22.54
Round of
2022-01-28 | (as per details) | Purchase | 73 | 1125738
Mody Associates Co.(Ambrish)
| CGST 9% Purchase |  |  | 101316.51
| SGST 9% Purchase |  |  | 101316.51
| TCS 1% |  |  | 1328.37
| Round of |  |  | 0.61
2022-02-02 | (as per details) | Purchase | 74 | 4140
Shree Mahavir Ceramics (Ambarish
| SGST 9% Purchase |  |  | 372.6
| CGST 9% Purchase |  |  | 372.6
Round of
2022-02-04 | (as per details) | Purchase | 75 | 1223461.92
Mody Associates Co.(Ambrish)
| CGST 9% Purchase |  |  | 110111.57
| SGST 9% Purchase |  |  | 110111.57
| TCS 1% |  |  | 1443.69
| Round of |  |  | 0.25
2022-02-04 | (as per details) | Purchase | 76 | 28200
Mody Associates Co.(Ambrish)
| CGST 9% Purchase |  |  | 2538
| SGST 9% Purchase |  |  | 2538
| TCS 1% |  |  | 33.28
Round of
2022-02-17 | (as per details) | Purchase | 77 | 19450.13
Shree Mahavir Ceramics (Ambarish
| CGST 9% Purchase |  |  | 1750.51
| SGST 9% Purchase |  |  | 1750.51
Round of
2022-02-18 | (as per details) | Purchase | 78 | 65710
Madhav Marble & Genite(Kurla)
| CGST 9% Purchase |  |  | 5914
| SGST 9% Purchase |  |  | 5914
2022-02-18 | (as per details) | Purchase | 79 | 71704
Shree Laxmi Saw Mills Kurla
| CGST 9% Purchase |  |  | 6453.36
| SGST 9% Purchase |  |  | 6453.36
| Round of |  |  | 0.28
2022-02-19 | (as per details) | Purchase | 80 | 142500
Suntex Corporation
| CGST 9% Purchase |  |  | 19950
| SGST 9% Purchase |  |  | 19950
2022-02-20 | (as per details) | Purchase | 81 | 5835.04
Shree Mahavir Ceramics (Ambarish
| SGST 9% Purchase |  |  | 525.15
| CGST 9% Purchase |  |  | 525.15
Round of
2022-02-20 | (as per details) | Purchase | 82 | 19689.12
Shree Mahavir Ceramics (Ambarish
| CGST 9% Purchase |  |  | 1772.02
| SGST 9% Purchase |  |  | 1772.02
Round of
2022-02-21 | (as per details) | Purchase | 83 | 106384
Shree Laxmi Saw Mills Kurla
| SGST 9% Purchase |  |  | 3358.36
| CGST 9% Purchase |  |  | 3358.36
| Round of |  |  | 0.28
2022-02-25 | (as per details) | Purchase | 84 | 54073
Doorset Industries Pvt.Ltd(Kurla)
| IGST |  |  | 9733.14
Round of
2022-02-28 | (as per details) | Purchase | 85 | 92305
Madhav Marble & Genite(Kurla)
| SGST 9% Purchase |  |  | 8307.5
| CGST 9% Purchase |  |  | 8307.5
2022-02-28 | (as per details) | Purchase | 86 | 23409
Mody Associates Co.(Ambrish)
| CGST 9% Purchase |  |  | 2106.81
| SGST 9% Purchase |  |  | 2106.81
| TCS 1% |  |  | 27.62
Round of
2022-02-28 | (as per details) | Purchase | 87 | 1370474.67
Mody Associates Co.(Ambrish)
| CGST 9% Purchase |  |  | 123342.72
| SGST 9% Purchase |  |  | 123342.72
| TCS 1% |  |  | 1617.16
Round of
2022-02-28 | (as per details) | Purchase | 88 | 14400
Doorset Industries Pvt.Ltd(Kurla)
| IGST |  |  | 2592
2022-03-02 | (as per details) | Purchase | 89 | 11670
Shree Mahavir Ceramics (Ambarish
| SGST 9% Purchase |  |  | 1050.31
| CGST 9% Purchase |  |  | 1050.31
| Round of |  |  | 0.38
2022-03-03 | (as per details) | Purchase | 90 | 83103
Shree Laxmi Saw Mills Kurla
| CGST 9% Purchase |  |  | 7479.27
| SGST 9% Purchase |  |  | 7479.27
| Round of |  |  | 0.46
2022-03-17 | (as per details) | Purchase | 91 | 166849.85
JKCera International(Ambarish)
| IGST |  |  | 30032.97
| Round of |  |  | 0.18
2022-03-17 | (as per details) | Purchase | 92 | 30000
Tatkalorry Private Limited
| CGST 2.5% |  |  | 750
| SGST 2.5% |  |  | 750
2022-03-18 | (as per details) | Purchase | 93 | 198280
Madhav Marble & Genite(Kurla)
| CGST 9% Purchase |  |  | 17845.5
| SGST 9% Purchase |  |  | 17845.5
2022-03-31 | (as per details) | Purchase | 94 | 83572
Shree Mahavir Ceramics (Ambarish
| CGST 9% Purchase |  |  | 7521.48
| SGST 9% Purchase |  |  | 7521.48
| Round of |  |  | 0.04
2022-03-31 | (as per details) | Purchase | 95 | 63290
Shree Mahavir Ceramics (Ambarish
| CGST 9% Purchase |  |  | 5696.1
| SGST 9% Purchase |  |  | 5696.1
Round of
2022-03-31 | (as per details) | Purchase | 96 | 60375
Shree Mahavir Ceramics (Ambarish
| SGST 9% Purchase |  |  | 5433.75
| CGST 9% Purchase |  |  | 5433.75
| Round of |  |  | 0.5
2022-03-31 | (as per details) | Purchase | 97 | 62049.5
Shree Mahavir Ceramics (Ambarish
| CGST 9% Purchase |  |  | 5584.46
| SGST 9% Purchase |  |  | 5584.46
Round of
2022-03-31 | (as per details) | Purchase | 98 | 49222.8
Shree Mahavir Ceramics (Ambarish
| SGST 9% Purchase |  |  | 4430.05
| CGST 9% Purchase |  |  | 4430.05
| Round of |  |  | 0.1
2022-03-31 | (as per details) | Purchase | 99 | 49222.8
Shree Mahavir Ceramics (Ambarish
| CGST 9% Purchase |  |  | 4430.05
| SGST 9% Purchase |  |  | 4430.05
| Round of |  |  | 0.1
2022-03-31 | (as per details) | Purchase | 100 | 164076
Shree Mahavir Ceramics (Ambarish
| CGST 9% Purchase |  |  | 14766.84
| SGST 9% Purchase |  |  | 14766.84
| Round of |  |  | 0.32
2022-03-31 | (as per details) | Purchase | 101 | 165
Shree Mahavir Ceramics (Ambarish
| CGST 9% Purchase |  |  | 16.6
| SGST 9% Purchase |  |  | 16.6
Round of
2022-03-31 | (as per details) | Purchase | 102 | 6527.6
Shree Mahavir Ceramics (Ambarish
| SGST 9% Purchase |  |  | 589.26
| CGST 9% Purchase |  |  | 589.26
Round of
2022-03-31 | (as per details) | Purchase | 103 | 25200
Vaishnavi Traders(Kurla)
| CGST 2.5% |  |  | 630
| SGST 2.5% |  |  | 630
2018-10-02 | (as per details) | Journal | 30 | 1195829
| CGST 9% Labour |  |  | 107625
| SGST 9% Labour |  |  | 107625
Foundation Engineering(Ambrish)
TDS Contractor - 94C
received bills Foundation Enginnring
2018-10-12 | (as per details) | Journal | 33 | 404549
| CGST 9% Labour |  |  | 36409
| SGST 9% Labour |  |  | 36409
Foundation Engineering(Ambrish)
TDS Contractor - 94C
RECEIVED BILLS
2018-10-16 | (as per details) | Journal | 34 | 322951
| CGST 9% Labour |  |  | 29066
| SGST 9% Labour |  |  | 29066
Foundation Engineering(Ambrish)
TDS Contractor - 94C
RECEIVED BILLS
2018-11-13 | (as per details) | Journal | 47 | 1109165
| CGST 9% Labour |  |  | 99825
| SGST 9% Labour |  |  | 99825
Foundation Engineering(Ambrish)
TDS Contractor - 94C
received bills & transfer
2018-12-11 | Rishi Constructions | Journal | 54 | 50505
2019-02-15 | (as per details) | Journal | 72 | 147575
| CGST 9% Labour |  |  | 13282
| SGST 9% Labour |  |  | 13282
Foundation Engineering(Ambrish)
TDS Contractor - 94C
received bills
2019-02-15 | (as per details) | Journal | 73 | 9450
| CGST 9% Labour |  |  | 851
| SGST 9% Labour |  |  | 851
Foundation Engineering(Ambrish)
TDS Contractor - 94C
2019-02-27 | (as per details) | Debit Note | 1
| Foundation Engineering(Ambrish) |  |  | 17145
CGST 9% Labour
SGST 9% Labour
Round of
2019-03-25 | (as per details) | Journal | 120 | 2959011
| CGST 9% Labour |  |  | 266311
| SGST 9% Labour |  |  | 266311
Mantra Turnkey Projects LLP (Kurla)
TDS Contractor - 94C
Retention Money @ 5% (Mantra LLP)
being amt bills received ant transfer (Balance TDS already deducted on advance payment)
2019-05-02 | (as per details) | Journal | 47 | 3945348
| CGST 9% Labour |  |  | 355081
| SGST 9% Labour |  |  | 355081
Mantra Turnkey Projects LLP (Kurla)
TDS Contractor - 94C
Retention Money @ 5% (Mantra LLP)
received invoice 103 dt 2.5.19
2019-05-13 | (as per details) | Journal | 64 | 1100000
| CGST 9% Labour |  |  | 99000
| SGST 9% Labour |  |  | 99000
FEC India
received bills No 1
2019-06-17 | (as per details) | Journal | 94 | 2959011
| CGST 9% Labour |  |  | 266311
| SGST 9% Labour |  |  | 266311
Mantra Turnkey Projects LLP (Kurla)
TDS Contractor - 94C
Retention Money @ 5% (Mantra LLP)
received bills No 106/19-20
2019-07-15 | (as per details) | Journal | 104 | 3945348
| CGST 9% Labour |  |  | 355081
| SGST 9% Labour |  |  | 355081
Mantra Turnkey Projects LLP (Kurla)
Retention Money @ 5% (Mantra LLP)
TDS Contractor - 94C
received bills No 107/19-20
2019-09-03 | (as per details) | Journal | 123 | 3945348
| CGST 9% Labour |  |  | 355081
| SGST 9% Labour |  |  | 355081
Mantra Turnkey Projects LLP (Kurla)
TDS Contractor - 94C
Retention Money @ 5% (Mantra LLP)
received bill No 112
2019-10-26 | Initial Pest Control | Purchase | 93 | 17850
Pre construction termiseal service - Termite Service
2021-06-21 | (as per details) | Journal | 13 | 4931685
| CGST 9% Labour |  |  | 443852
| SGST 9% Labour |  |  | 443852
Mantra Turnkey Projects LLP (Kurla)
Retention Money @ 5% (Mantra LLP)
received bills no M/02/2021-22
2021-08-12 | (as per details) | Journal | 28 | 4438516
| CGST 9% Labour |  |  | 399466
| SGST 9% Labour |  |  | 399466
Mantra Turnkey Projects LLP (Kurla)
Retention Money @ 5% (Mantra LLP)
received bills from Mantra Turnkey project bill No M/03/21-22
2021-10-04 | (as per details) | Journal | 40 | 5424853
| CGST 9% Labour |  |  | 488237
| SGST 9% Labour |  |  | 488237
Mantra Turnkey Projects LLP (Kurla)
Retention Money @ 5% (Mantra LLP)
Retention Money @ 5% (Mantra LLP)
received bill no M/05/21-22 dated 4.10.21
2021-11-15 | (as per details) | Journal | 50 | 4931684
| CGST 9% Labour |  |  | 443852
| SGST 9% Labour |  |  | 443852
Mantra Turnkey Projects LLP (Kurla)
Retention Money @ 5% (Mantra LLP)
being amt bills received & transfer
2022-01-03 | (as per details) | Journal | 67 | 6663254
| CGST 9% Labour |  |  | 599693
| SGST 9% Labour |  |  | 599693
Mantra Turnkey Projects LLP (Kurla)
Retention Money @ 5% (Mantra LLP)
TDS Contractor - 94C
received bills M/09/21-22
2022-01-21 | (as per details) | Journal | 74 | 1047200
| CGST 9% Labour |  |  | 94248
| SGST 9% Labour |  |  | 94248
Prerana Electricals Works(Ambarish)
TDS Contractor - 94C
Retention Monney(Prerana)
received bills dated 21.1.2022
2022-01-27 | (as per details) | Journal | 75 | 10455172
| CGST 9% Labour |  |  | 940965
| SGST 9% Labour |  |  | 940965
Mantra Turnkey Projects LLP (Kurla)
Retention Money @ 5% (Mantra LLP)
TDS Contractor - 94C
received bills
2022-02-01 | (as per details) | Journal | 77 | 300785
| CGST 9% Labour |  |  | 27070.5
| SGST 9% Purchase |  |  | 27070.5
Raj Interior(Ambarish)
TDS Contractor - 94C
Retention Monney(Prerana)
2022-03-14 | (as per details) | Journal | 88 | 7550957
| CGST 9% Labour |  |  | 679586
| SGST 9% Labour |  |  | 679586
Mantra Turnkey Projects LLP (Kurla)
Retention Money @ 5% (Mantra LLP)
TDS Contractor - 94C
received bills
2022-01-29 | Evershine Arts |  |  | 5124504
2022-02-18 | Evershine Arts |  |  | 781704
2022-01-29 | Sunrise Arts |  |  | 4469462
2022-02-18 | Sunrise Arts |  |  | 681782
2022-03-31 | Mantra Turnkey Projects LLP (Kurla) |  |  | 8910130
2022-03-20 | Evershine Arts |  |  | 2041200
2022-03-16 | Wet Guard Enterprises |  |  | 867076
2022-03-25 | Raj Interior(Ambarish) |  |  | 571290
2022-03-18 | Shrishti Sanitation |  |  | 475540
2022-03-31 | Prerana Electricals Works(Ambarish) |  |  | 1204000
Proforma Invoice
2021-04-07 | Sunrise Arts(Ambarish) | Payment | 12 | 1000000
being amt paid by cheque 000699 on a/c advance payment
2021-08-02 | Sunrise Arts(Ambarish) | Payment | 230 | 500000
paid by cheque 000780 on a/c
2022-04-03 | Pupular Copy Centre |  |  | 2063
2022-04-03 | Popular Copy Centre |  |  | 17315
2022-04-04 | Popular Copy Centre |  |  | 3491
2022-04-06 | Pooja Telecom |  |  | 47188
2022-04-07 | Protect Engineers |  |  | 21122
2022-04-02 | Madhav Marble & Gre |  |  | 79482.63
2022-04-09 | Tarkalorry Pvt.Ltd |  |  | 25000
2022-04-09 | JK Cera International |  |  | 97002
2022-04-09 | Shree Mahavir ceramics |  |  | 1510.4
2022-04-05 | Shree Mahavir ceramics |  |  | 35459
2022-04-30 | Sneh Enterprise |  |  | 42499.84
2022-04-26 | Shree Mahavir cera |  |  | 76295.78
2022-04-25 | Shree Mahavir cera |  |  | 96395
2022-05-03 | Madhav Marble & Granite |  |  | 217578
2022-05-06 | Shree Laxmi Saw mills |  |  | 102849
2022-05-21 | Shree Mahavir Ceramics |  |  | 362
2022-05-19 | Shree Mahavir Ceramics |  |  | 16393.82
2022-05-20 | Shree Mahavir Ceramics |  |  | 56994
2022-05-19 | Tatkalorry Pvt.Ltd |  |  | 4500
2022-05-31 | Shree Mhavir Ceramics |  |  | 928.58
2022-06-01 | Shree Mahavir ceramics(Ambarish) |  |  | 4007
2022-06-01 | Shree Mahavir ceramics(Ambarish) |  |  | 56994
2022-06-03 | Popular Copy Centre (Ambarish) |  |  | 15461
2022-06-03 | Popular Copy Centre (Ambarish) |  |  | 4108.9
2022-06-03 | Shree Mahavir ceramics(Ambarish) |  |  | 12601
2022-06-08 | Shree Laxmi Saw mills Kurla |  |  | 123522
2022-06-10 | Shree Mahavir ceramics(Ambarish) |  |  | 514
2022-06-14 | Madhav Marble & Granite Kurla |  |  | 241918
2022-06-15 | Shree Mahavir ceramics(Ambarish) |  |  | -3039.74
2022-06-25 | Shree Laxmi Saw mills Kurla |  |  | 171599
2022-06-27 | Shree Mahavir ceramics(Ambarish) |  |  | 2882.4
2022-06-27 | Shree Mahavir ceramics(Ambarish) |  |  | 13085.6
2022-06-28 | Schindalr India Pvt Ltd Ambarish |  |  | 1021250
2022-06-28 | Schindalr India Pvt Ltd Ambarish |  |  | 926249
2022-06-01 | Evershine Arts (Ambarish) |  |  | 1041200 | 1085913 | Total bill amount and paid amt in cash
2022-06-01 | Shrishti Sanitation Kurla |  |  | 475540 | 520253
2022-06-05 | Mantra Turnkey Projects LLP (Kurla) |  |  | 3000000 | 3044717
2022-06-07 | Prerana Electricals Works(Ambarish) |  |  | 348480 | 393199
2022-06-09 | Wet Guard Enterprises |  |  | 867076
2022-08-02 | Mantraa Turnkey Projects LLP |  |  | 6853947
2022-08-07 | Wet Guard |  |  | 855618
2022-08-29 | Mantraa Turnkey Projects LLP-Advance |  |  | 5146667
2022-07-01 | Shree Mahavir Ceramics |  |  | 35342
2022-07-07 | Popular Copy Centre |  |  | 4468
2022-07-21 | Madhav Marble & Granite |  |  | 274609
2022-07-31 | Vaishnavi Tarders |  |  | 30441
2022-08-06 | Popular Copy Centre |  |  | 4118.16
2022-08-06 | Shree Mahavir Ceramics |  |  | 711
2022-08-16 | JK Cera International |  |  | 734789.14
2022-08-16 | New Sanjari Roadway |  |  | 102116
2022-08-20 | Shree Laxmi Saw Mills |  |  | 120997
2022-08-24 | Shree Laxmi Saw Mills |  |  | 12823
2022-08-25 | Suntex Corporation |  |  | 89856
2022-08-30 | Madhav Marble & Granite |  |  | 389542
2022-09-01 | Vaishnavi Tarders |  |  | 7140
2022-09-14 | Popular Copy Centre |  |  | 9091.96
2022-09-15 | Madhav Marble & Granite |  |  | 235169
2022-09-24 | Sakshi Corportaion |  |  | 39040
2022-09-24 | Sakshi Corportaion |  |  | 36480
2022-10-02 | Shree Mahavir Ceramics (Ambarish |  |  | 235512
2022-10-07 | Popular Copy Centre(Ambarish) |  |  | 1439.1
2022-10-10 | Shree Laxmi Saw Mills Kurla |  |  | 98276.3
2022-10-11 | Sneh Enterprises(Ambarish) |  |  | 75520
2022-10-20 | Shree Mahavir Ceramics (Ambarish |  |  | 1251
2022-11-01 | Trust Document Systems |  |  | 40000
2022-11-02 | Shree Mahavir Ceramics (Ambarish |  |  | 34220
2022-11-03 | Popular Copy Centre(Ambarish) |  |  | 2811.8
2022-11-13 | Madhav Marble & Genite(Kurla) |  |  | 209141
2022-11-15 | Schindalr India Pvt Ltd Ambarish |  |  | 780001
2022-11-15 | Schindalr India Pvt Ltd Ambarish |  |  | 860000
2022-11-22 | Shree Laxmi Saw Mills Kurla |  |  | 100459
2022-11-29 | Kailash Decor |  |  | 26870
2022-11-30 | Gayatri Ceramics(Ambarish) |  |  | 78942
2022-12-01 | Shree Mahavir Ceramics (Ambarish |  |  | 69266
2022-12-01 | Vaishnavi Traders(Kurla) |  |  | 62976
2022-12-01 | Popular Copy Centre(Ambarish) |  |  | 4390
2022-12-06 | Gayatri Ceramics(Ambarish) |  |  | 51684
2022-12-12 | Suntex Corporation |  |  | 37760
2022-12-12 | Shree Mahavir Ceramics (Ambarish |  |  | 34751
2022-12-16 | Mody Aoociates Company(Ambarish) |  |  | 270094.91
2022-12-20 | Shree Mahavir Ceramics (Ambarish |  |  | 5287
2022-12-21 | Exxaro Tiles(Ambarish) |  |  | 523197.44
2022-12-21 | Madhav Marble & Genite(Kurla) |  |  | 651284
2022-12-22 | Shree Mahavir Ceramics (Ambarish |  |  | 18027
2022-12-22 | Shree Mahavir Ceramics (Ambarish |  |  | 166657.8
2022-12-23 | Shree Mahavir Ceramics (Ambarish |  |  | 58083
2022-12-24 | Shree Mahavir Ceramics (Ambarish |  |  | 77444
2022-12-29 | Suntex Corporation |  |  | 37760
2022-12-31 | Vaishnavi Traders(Kurla) |  |  | 149808
2022-12-24 | Vallabh Aluminium |  |  | 950000
2022-10-06 | Mantra Turnkey Projects LLP(Kurla) |  |  | 8224736
2022-11-01 | Shrishti Sanitation Retention Kurla |  |  | 545042
2022-11-01 | Bullet Security Service(Kurla) |  |  | 45000
2022-12-01 | Wet Gaurad Reterntion Kurla |  |  | 650535
2022-12-02 | Mantra Turnkey Projects LLP(Kurla) |  |  | 6853948
2022-12-31 | Prerna Electricals Works (Ambarish) |  |  | 495003
2022-11-30 | Lift License Expenses- HDFC bank |  |  | 10223.6
2022-11-30 | Lift License Expenses- HDFC bank |  |  | 10223.6
2022-12-28 | Advance invoice of Mantra Turnkey Projects LLP |  |  | 17820260
2023-01-10 | Schindalr India Pvt Ltd Ambarish |  |  | 194000
2023-01-10 | Schindalr India Pvt Ltd Ambarish |  |  | 213750
2023-01-24 | Suntex Corporation |  |  | 72960
2023-01-31 | Vaishnavi Traders(Kurla) |  |  | 90165.6
2023-01-07 | Shrishti Sanitation |  |  | 695020
2023-01-14 | Raj Interior(Ambarish) |  |  | 521518.7
2023-01-14 | Raj Interior(Ambarish) |  |  | 842857.48
2023-01-19 | Saamit Transport |  |  | 63313
2023-02-04 | Madhav Marble & Genite(Kurla) |  |  | 449001
2023-02-06 | Shree Laxmi Saw Mills Kurla |  |  | 63596.1
2023-02-09 | New Sanjari Roadway |  |  | 72775
2023-02-09 | JK Cera International |  |  | 756630.75
2023-02-11 | Suntex Corporation |  |  | 72960
2023-02-28 | Saamit Transport |  |  | 63325
2023-02-05 | Prerna Electricals Works (Ambarish) |  |  | 822426
2023-03-01 | Suntex Corporation |  |  | 72960
2023-03-01 | Vaishnavi Traders(Kurla) |  |  | 114156
2023-03-07 | Gayatri Ceramics(Ambarish) |  |  | 4529.86
2023-03-07 | Gayatri Ceramics(Ambarish) |  |  | 51920
2023-03-14 | Suntex Corporation |  |  | 72960
2023-03-21 | Gayatri Ceramics(Ambarish) |  |  | 10030
2023-03-23 | Schindalr India Pvt Ltd Ambarish |  |  | 997500.87
2023-03-23 | Schindalr India Pvt Ltd Ambarish |  |  | 950000.63
2023-03-23 | Schindalr India Pvt Ltd Ambarish |  |  | 45926
2023-03-29 | Shree Mahavir Ceramics |  |  | 57526
2023-03-31 | Kiran maurrya |  |  | 8000
2023-03-31 | Vaishnavi Traders(Kurla) |  |  | 64398
2023-03-01 | Shrishti Santation Retention |  |  | 658440
2023-03-01 | Wet Guard Retention |  |  | 1226512.06
1.4.23 | Suntrex Corp |  |  | 70400
1.4.23 | Jalaram Eng work |  |  | 1180000
9.4.23 | Suntrx Corp |  |  | 107250
11.4.23 | Shree Mahavir |  |  | 13004
11.4.23 | Shree Mahavir |  |  | 57289
12.4.23 | Exxro Tiles |  |  | 617373
12.4.23 | Saamit Transport |  |  | 63325
15.4.23 | Gayatri Ceramics |  |  | 92370
17.4.23 | Gayatri Ceramics |  |  | 72629
22.4.23 | Madhav Marble |  |  | 390861
25.4.23 | Suntrex Corp |  |  | 72960
4.5.23 | Suntrex Corporation |  |  | 107520
4.5.23 | Shree Maha Cera |  |  | 80240
5.5.23 | Shree Maha Cera |  |  | 20060
5.5.23 | Shree Maha Cera |  |  | 49560
7.5.23 | New Sanjari |  |  | 53000
7.5.23 | JK Ceramics |  |  | 629118
8.5.23 | Mody Associates |  |  | 389946
9.5.23 | Mody Associates |  |  | 197426
10.5.23 | Shree Maha Cera |  |  | 2580
14.5.23 | Shree Maha Cera |  |  | 20341
16.5.23 | Suntrex Corporation |  |  | 120740
21.5.23 | Suntrex Corporation |  |  | 107250
22.5.23 | Shree Maha Cera |  |  | 31396
24.5.23 | Shree Maha Cera |  |  | 3816
27.5.23 | Suntrex Corporation |  |  | 70400
30.5.23 | Mody Associates |  |  | 212750
31.5.23 | Vaishanavi Traders |  |  | 256111
5.6.23 | Shree Mahavir Cea |  |  | 20060
6.6.23 | Suntrex Corp |  |  | 71680
7.6.23 | JK Ceramics |  |  | 76770
7.6.23 | New Sanjari |  |  | 7632
7.6.23 | Shree Mahavir Cea |  |  | 66847
8.6.23 | Saamit Transport |  |  | 49195
8.6.23 | Exxaro Tiles |  |  | 479698
8.6.23 | Schindlar Lift |  |  | 840000
14.6.23 | Doorset |  |  | 462632
14.6.23 | Schindlar Lift |  |  | 840000
19.6.23 | Doorset |  |  | 498510
20.6.23 | Gayatri Ceramics |  |  | 846200
21.6.23 | Gayatri Ceramics |  |  | 202888
27.6.23 | Gayatri Ceramics |  |  | 38515
2.4.23 | Shrishiti Sanitation |  |  | 4650
5.4.23 | Raj Interior |  |  | 521519
1.5.23 | Shristi Sanitation |  |  | 623844
4.5.23 | Wet Guard |  |  | 1190236
4.5.23 | Mantra Turnkey |  |  | 5483156
3.6.23 | Raj Interior |  |  | 521519
7.6.23 | Shriti sanitation |  |  | 548700
15.6.23 | Mantra Turnkey |  |  | 4112368
28.06.2023 | Mantra Turnkey |  |  | 3426973 | PG Invoive
1.8.23 | Madhav Marble |  |  | 28910
3.8.23 | Shree Laxmi Saw Mills |  |  | 750955
5.8.23 | Shree Mahavir Ceramics |  |  | 1921
7.8.23 | Doorset Industries |  |  | 56444
12.8.23 | Doorset Industries |  |  | 336300
14.8.23 | Gayatri Cderamics |  |  | 80900
14.8.23 | Gayatri Ceramics |  |  | 82010
16.8.23 | Gayatri Ceramics |  |  | 68735
16.8.23 | Gayatri Ceramics |  |  | 2832
17.8.23 | Schindlar Lift |  |  | 22126
17.8.23 | Schindlar Lift |  |  | 22126
24.8.23 | Suntrex Corporation |  |  | 70400
25.8.23 | Shree Laxmi Saw mills |  |  | 45897
28.8.23 | Shree Mahavir Ceramics |  |  | 55826
29.8.23 | Schindlar Lift |  |  | 261250
29.8.23 | Schindlar Lift |  |  | 212500
30.8.23 | Gayatri Ceramics |  |  | 3705
10.8.23 | Prerara Electric |  |  | 214760
9.8.23 | Raj Interior |  |  | 521517
10.8.23 | Prerara Electric |  |  | 275884
14.9.23 | Mody Associates |  |  | 103578
16.9.23 | Gayatri Ceramics |  |  | 52121
18.9.23 | Madhav Marble |  |  | 6240
12.9.23 | Shree Mahavir Cer |  |  | 1251
1.9.23 | Evershine Arts |  |  | 1008547
1.9.23 | Evershine Arts |  |  | 1487607
11.9.23 | Beenee Fire |  |  | 457028
15.9.23 | Sunrise Arts |  |  | 1003000
15.9.23 | Sunrise Arts |  |  | 1194160
17.08.2023 | Wet Gauarad Retention |  |  | 1460911
31.08.2023 | Shrishti Sanitation |  |  | 731600
01.07.2023 | Jay Jalaram Engineering |  |  | 1059829
01.07.2023 | Shrishti Sanitation |  |  | 823050
06.07.2023 | Raj Interior |  |  | 521519
15.07.2023 | Prerana Electricals Works(Ambarish) |  |  | 1643102
2023-07-07 | Vallabh Alluminium(Kurla) |  |  | 15000
2023-07-08 | Shree Laxmi Saw Mills Kurla |  |  | 877876
2023-07-09 | Popular Copy Centre(Ambarish) |  |  | 15767.4
2023-07-10 | Beenee Fire Fiting LLP |  |  | 355543.88
2023-07-11 | Mody Aoociates Company(Ambarish) |  |  | 909340.06
2023-07-11 | Shree Mahavir Ceramics (Ambarish |  |  | 17452.3
2023-07-12 | Suntex Corporation |  |  | 69120
2023-07-16 | Gayatri Ceramics(Ambarish) |  |  | 53100
2023-07-21 | Shree Laxmi Saw Mills Kurla |  |  | 1561591.09
2023-07-22 | Gayatri Ceramics(Ambarish) |  |  | 34975.2
2023-07-31 | Shree Mahavir Ceramics (Ambarish |  |  | 14750
2023-07-31 | Shree Mahavir Ceramics (Ambarish |  |  | 20020.34
2023-07-31 | Vaishnavi Traders(Kurla) |  |  | 12600
2023-08-18 | Shree Mahavir Ceramics (Ambarish |  |  | 4298
2023-09-12 | Shree Mahavir Ceramics (Ambarish |  |  | 1251
2023-09-28 | Shree Mahavir Ceramics (Ambarish |  |  | 20676
2023-09-28 | Shree Mahavir Ceramics (Ambarish |  |  | 5015
2023-10-01 | Shree Mahavir Ceramics (Ambarish |  |  | 8110.14
2023-10-04 | Shree Mahavir Ceramics (Ambarish |  |  | 45194
2023-10-05 | Shree Mahavir Ceramics (Ambarish |  |  | 2138.8
2023-10-05 | Popular Copy Centre(Ambarish) |  |  | 12867.14
2023-10-07 | Shree Mahavir Ceramics (Ambarish |  |  | 735
2023-10-10 | Mody Aoociates Company(Ambarish) |  |  | 104522.04
2023-10-12 | Shree Mahavir Ceramics (Ambarish |  |  | 14233.26
2023-10-15 | Shree Mahavir Ceramics (Ambarish |  |  | 63106.4
2023-10-21 | Shree Mahavir Ceramics (Ambarish |  |  | 5203.8
2023-10-25 | Sneh Enterprises(Ambarish) |  |  | 38540
2023-10-30 | Shree Laxmi Saw Mills Kurla |  |  | 6224.5
2023-10-31 | Vallabh Alluminium(Kurla) |  |  | 3000001
2023-10-31 | Mody Aoociates Company(Ambarish) |  |  | 455685.32
2023-10-31 | Vaishnavi Traders(Kurla) |  |  | 81452.7
2023-11-01 | Popular Copy Centre(Ambarish) |  |  | 7200.3
2023-11-07 | Shree Mahavir Ceramics (Ambarish |  |  | 87615
2023-11-07 | Shree Mahavir Ceramics (Ambarish |  |  | 1840.8
2023-11-09 | Shree Mahavir Ceramics (Ambarish |  |  | 69974
2023-11-27 | Shree Mahavir Ceramics (Ambarish |  |  | 41300
2023-11-30 | Vaishnavi Traders(Kurla) |  |  | 10210
2023-12-01 | Shree Mahavir Ceramics (Ambarish |  |  | 45897.28
2023-12-02 | Shree Mahavir Ceramics (Ambarish |  |  | 61301
2023-12-02 | Shree Mahavir Ceramics (Ambarish |  |  | 1298
2023-12-03 | Shree Mahavir Ceramics (Ambarish |  |  | 68794
2023-12-13 | Popular Copy Centre(Ambarish) |  |  | 10483.48
2023-12-13 | Shree Mahavir Ceramics (Ambarish |  |  | 25075
2023-12-18 | Shree Mahavir Ceramics (Ambarish |  |  | 25665
2023-12-24 | Shree Mahavir Ceramics (Ambarish |  |  | 3162.4
2023-12-27 | Shree Mahavir Ceramics (Ambarish |  |  | 9735
2023-12-31 | Vaishnavi Traders(Kurla) |  |  | 22575
2023-10-01 | Labour Charges (Ambrish) |  |  | 52500
2023-10-15 | Labour Charges (Ambrish) |  |  | 239375
2023-11-01 | Labour Charges (Ambrish) |  |  | 744000
2023-11-01 | Labour Charges (Ambrish) |  |  | 60000
2023-11-03 | Labour Charges (Ambrish) |  |  | 1012000
2023-11-16 | Labour Charges (Ambrish) |  |  | 2323372
2023-12-01 | Labour Charges (Ambrish) |  |  | 60000
2023-12-07 | Labour Charges (Ambrish) |  |  | 1043032
2023-12-15 | Labour Charges (Ambrish) |  |  | 500000
2023-12-15 | Labour Charges (Ambrish) |  |  | 500000
| Ambuj Kumar Pandey |  |  | 116000
02.01.2024 | Shree Mahavir Ceramics |  |  | 14632
04.01.2024 | Shree Mahavir Ceramics |  |  | 2351
11.01.2024 | Beenee Fire Protection |  |  | 622141
11.01.2024 | Protect Engineering |  |  | 226523
11.01.2024 | Perfect Enginnerng |  |  | 226523
17.01.2024 | Mody Associates |  |  | 662235
19.01.2024 | Shree Mahavir Ceramics |  |  | 4474
21.01.2024 | Shree Laxmi Saw Mills |  |  | 51825
31.01.2024 | Vbishanavi Traders |  |  | 42524
01.01.2024 | Prerana Electric |  |  | 578200
2024-02-01 | Shrishti Sanitation Cr. (Ambarish) |  |  | 907184
2024-02-03 | Shree Laxmi Saw Mills Kurla |  |  | 42952
2024-02-04 | Shree Mahavir Ceramics (Ambarish |  |  | 61572
2024-02-05 | Shree Mahavir Ceramics (Ambarish |  |  | 61572
2024-02-08 | JK Lakshmi Cement Ltd (New Abhiram) |  |  | 182400
2024-02-08 | JK Lakshmi Cement Ltd (New Abhiram) |  |  | 145920
2024-02-09 | Shree Laxmi Saw Mills Kurla |  |  | 45312
2024-02-10 | Wet Guard Enterprises Cr. (Ambarish) |  |  | 477030.34
2024-02-10 | Shree Laxmi Saw Mills Kurla |  |  | 9062
2024-02-12 | I Stron Corporation Pvt.Ltd (Kurla) |  |  | 4587840
2024-02-13 | Shree Laxmi Saw Mills Kurla |  |  | 33984
2024-02-19 | Shree Mahavir Ceramics (Ambarish |  |  | 4475
2024-02-26 | Neeraj Steel Sales (New Abhiram) |  |  | 1101159
2024-02-29 | Prerana Electricals Works(Ambarish) |  |  | 1610700
2024-02-29 | Suntex Corporation ( New Abhiram) |  |  | 111360
2024-02-29 | Suntex Corporation ( New Abhiram) |  |  | 74240
2024-02-29 | Bhakti Steel LLP(New Abhiram |  |  | 1543031
2024-02-29 | RDC Concrete (India) Pvt. Ltd (New Abhiram) |  |  | 42480
2024-02-29 | RDC Concrete (India) Pvt. Ltd (New Abhiram) |  |  | 42480
2024-02-29 | RDC Concrete (India) Pvt. Ltd (New Abhiram) |  |  | 42480
2024-02-29 | RDC Concrete (India) Pvt. Ltd (New Abhiram) |  |  | 42480
2024-02-29 | RDC Concrete (India) Pvt. Ltd (New Abhiram) |  |  | 42480
2024-02-29 | RDC Concrete (India) Pvt. Ltd (New Abhiram) |  |  | 42480
2024-02-29 | RDC Concrete (India) Pvt. Ltd (New Abhiram) |  |  | 42480
2024-02-29 | RDC Concrete (India) Pvt. Ltd (New Abhiram) |  |  | 42480
2024-02-29 | RDC Concrete (India) Pvt. Ltd (New Abhiram) |  |  | 42480
2024-02-29 | RDC Concrete (India) Pvt. Ltd (New Abhiram) |  |  | 42480
2024-02-29 | RDC Concrete (India) Pvt. Ltd (New Abhiram) |  |  | 42480
2024-02-29 | RDC Concrete (India) Pvt. Ltd (New Abhiram) |  |  | 42480
2024-02-29 | RDC Concrete (India) Pvt. Ltd (New Abhiram) |  |  | 42480
2024-02-29 | RDC Concrete (India) Pvt. Ltd (New Abhiram) |  |  | 42480
2024-02-29 | Shree Mahavir Ceramics (Ambarish |  |  | 7788
2024-02-29 | Vaishnavi Traders(Kurla) |  |  | 31626
11.03.2024 | Gayatri Ceramics |  |  | 214347
11.03.2024 | Gayatri Ceramics |  |  | 33656
21.03.2024 | Gayatri Ceramics |  |  | 52274
28.03.2024 | Shree Mahavir Ceramics |  |  | 81682
28.03.2024 | Shree Mahavir Ceramics |  |  | 478293
31.03.2024 | shree Laxmi Saw mills |  |  | 26196
31.03.2024 | Vaisha Traders |  |  | 48825
04.03.2024 | Mantra |  |  | 2741579
05.03.2024 | Prerana Electric |  |  | 998460
05.03.2024 | Prerana Electric |  |  | 998460
| TOTAL |  |  | 276457356

## Admin Cost
2018-05-24 | HDFC Bank Ambrish | Payment | 67 | 5673.75
paid by cheque 000098 on a/c Electricity bills paid
2018-09-27 | HDFC Bank Ambrish | Payment | 305 | 5079
paid by cheque 000150 on a/c Electricity bills paid
2018-10-16 | HDFC Bank Ambrish | Payment | 347 | 4840
paid by cheque 000175 HDFC Bank
2018-11-27 | HDFC Bank Ambrish | Payment | 426 | 4080
paid by cheque 000239 on a/c payment of electric bills kurla
2019-01-21 | HDFC Bank Ambrish | Payment | 519 | 11910
paid by cheque 000265 on a/c Electricity bills paid
2019-02-15 | HDFC Bank Ambrish | Payment | 586 | 11974
paid by cheque 000292 Electricity bills paid
2019-02-16 | HDFC Bank Ambrish | Payment | 606 | 11150
paid by cheque 000315 on a/c Electric bills paid
2019-02-23 | HDFC Bank Ambrish | Payment | 618 | 18380
paid by cheque 000327 on a/c Electric bills paid
2019-04-01 | HDFC Bank Ambrish | Payment | 6 | 21140
paid by cheque 000338 on a/c payment of electric bills
2019-05-08 | HDFC Bank Ambrish | Payment | 76 | 20860
paid by cheque 000360 on a/c payment of electric bills
2019-06-07 | HDFC Bank Ambrish | Payment | 159 | 24090
paid by cheque 000398 on a/c payment of bills
2019-07-08 | HDFC Bank Ambrish | Payment | 219 | 28090
paid by cheque 000407 on a/c payment bills
2019-08-06 | HDFC Bank Ambrish | Payment | 267 | 25700
paid by cheque 000422 on a/c elctric bills
2019-09-25 | HDFC Bank Ambrish | Payment | 371 | 12360
paid by cheque 000459 on a/c Payment for Electric bills
2019-10-15 | HDFC Bank Ambrish | Payment | 417 | 16460
paid by cheque 000464 towards electric bills paid
2019-11-16 | HDFC Bank Ambrish | Payment | 466 | 11110
paid by cheque 000470 on a/c light bills paid
2019-12-13 | HDFC Bank Ambrish | Payment | 540 | 11230
paid by cheque 000501 on a/c pyment of Electricity bills
2020-01-22 | HDFC Bank Ambrish | Payment | 620 | 9880
apid by cheque 000531 on a/c payment of bills
2020-02-14 | HDFC Bank Ambrish | Payment | 668 | 7030
paid by cheque 000540 on a/c light bills paid
2020-04-01 | HDFC Bank LTD | Payment | 1 | 12230
being amt paid by Bank on a/c electricity bills
2020-04-17 | HDFC Bank LTD | Payment | 4 | 7320
being amt electricity bills paid
2020-05-11 | HDFC Bank LTD | Payment | 14 | 12690
being amt Electricity bills paid
2020-07-06 | HDFC Bank LTD | Payment | 48 | 6070
being amt debited by Bank for electric bills
2020-09-28 | HDFC Bank Ambrish | Payment | 133 | 3430
paid by cheque 000687 on a/c electric bills paid kurla site
2020-11-24 | (as per details) | Payment | 205 | 1220
| Electricity Charges(Jayakunj) |  |  | 16080
HDFC Bank LTD
paid by cheque 000636 on a/c electricity bills paid
2020-12-16 | HDFC Bank Ambrish | Payment | 241 | 5430
paid by cheque 000713 on a/c electricity bills paid
2021-01-28 | (as per details) | Payment | 310
| Electricity Charges(Sumasam) |  |  | 5630
| Electricity Charges(Jayakunj) |  |  | 9290
HDFC Bank LTD
paid by cjheque 000661 On a/c electric bills paid
2021-01-28 | HDFC Bank Ambrish | Payment | 311 | 3280
paid by cheque 000728 on a/c payment electricity bills
2021-02-24 | HDFC Bank Ambrish | Payment | 347 | 4170
paid by cheque 000735 HDFC Bank
2021-03-31 | HDFC Bank Ambrish | Payment | 401 | 10830
being amt paid by cheqoe 000739 electric bills paid
2021-04-28 | IDBI Rera A/c Ambrish | Payment | 60 | 11370
being amt paid by cheque 631498
2021-06-15 | IDBI Rera A/c Ambrish | Payment | 138 | 9820
being amt paid by cheque 613528 on a/c Electricity bills paid
2021-07-21 | IDBI Rera A/c Ambrish | Payment | 201 | 13690
paid by cheque 787050 on a/c electric bills paid
2021-08-13 | IDBI Rera A/c Ambrish | Payment | 251 | 15090
being amt paid by cheque 787072 on a/c electric bills paid
2021-09-17 | IDBI Rera A/c Ambrish | Payment | 296 | 33080
paid by cheque 787079 on a/c payment of elcrtic bills
2021-10-13 | IDBI Rera A/c Ambrish | Payment | 340 | 32820
paid by cheque 790954 on a/c electricity bills paid
2021-11-29 | IDBI Rera A/c Ambrish | Payment | 427 | 35750
PAID BY CHEQUE 796297 ON NA/C eLECTRICITY BILLS PAID
2021-12-21 | IDBI Rera A/c Ambrish | Payment | 465 | 32070
being amt paid for electricity bills 796312 on a/c electricity bills paid
2022-01-18 | IDBI Rera A/c Ambrish | Payment | 515 | 30920
paid by cheque 806484 on a/c elctric bills paid
2022-02-24 | IDBI Rera A/c Ambrish | Payment | 697 | 32210
paid by cheque 814683 to Adnani Electricity bills paid
2022-03-12 | State Bank of India(A/c 40740926519) CC A/c | Payment | 733 | 34380
paid by cheque 890838 on a/c electric bills paid
2018-05-20 | (as per details) | Journal | 12 | 6717
| CGST 9% Labour |  |  | 605
| SGST 9% Labour |  |  | 605
Steadfast Security (Solution)
received bills
2018-06-06 | (as per details) | Journal | 13 | 31000
| CGST 9% Labour |  |  | 2790
| SGST 9% Labour |  |  | 2790
Steadfast Security (Solution)
received bills
2018-07-05 | (as per details) | Journal | 14 | 31000
| CGST 9% Labour |  |  | 2790
| SGST 9% Labour |  |  | 2790
Steadfast Security (Solution)
received bills
2018-07-31 | (as per details) | Journal | 15 | 31000
| CGST 9% Labour |  |  | 2790
| SGST 9% Labour |  |  | 2790
Steadfast Security (Solution)
yeceived bills
2018-08-31 | (as per details) | Journal | 21 | 31000
| CGST 9% Labour |  |  | 2790
| SGST 9% Labour |  |  | 2790
Steadfast Security (Solution)
received bills
2018-10-01 | (as per details) | Journal | 27 | 32550
| CGST 9% Labour |  |  | 2930
| SGST 9% Labour |  |  | 2930
Steadfast Security (Solution)
received bills
2018-10-01 | (as per details) | Journal | 28 | 6536
| CGST 9% Labour |  |  | 588
| SGST 9% Labour |  |  | 588
Steadfast Security (Solution)
received bills
2018-11-02 | (as per details) | Journal | 43 | 32550
| CGST 9% Labour |  |  | 2930
| SGST 9% Labour |  |  | 2930
Steadfast Security (Solution)
received bills
2019-01-01 | (as per details) | Journal | 58 | 32550
| CGST 9% Labour |  |  | 2930
| SGST 9% Labour |  |  | 2930
Steadfast Security (Solution)
2019-01-09 | (as per details) | Journal | 59 | 32550
| CGST 9% Labour |  |  | 2930
| SGST 9% Labour |  |  | 2930
Steadfast Security (Solution)
received bills o for 31.12.18
2019-02-16 | (as per details) | Journal | 76 | 10161
| CGST 9% Labour |  |  | 914
| SGST 9% Labour |  |  | 914
Bullet Security Service(Kurla)
being amt bills received & transfer
2019-02-16 | (as per details) | Journal | 77 | 45000
| CGST 9% Labour |  |  | 4050
| SGST 9% Labour |  |  | 4050
Bullet Security Service(Kurla)
being amt bills received & Transfer
2019-03-01 | (as per details) | Journal | 91 | 25200
| CGST 9% Labour |  |  | 2268
| SGST 9% Labour |  |  | 2268
Steadfast Security (Solution)
received bills
2019-04-01 | (as per details) | Journal | 5 | 45000
| CGST 9% Labour |  |  | 4050
| SGST 9% Labour |  |  | 4050
Bullet Security Service(Kurla)
TDS Contractor - 94C
received bills
2019-05-01 | (as per details) | Journal | 45 | 55000
Bullet Security Service(Kurla)
TDS Contractor - 94C
received bills
2019-06-01 | Bullet Security Service(Kurla) | Journal | 83 | 60000
being amt bill received
2019-07-01 | Bullet Security Service(Kurla) | Journal | 99 | 58000
being Bill No 6 Recewived & transfer
2019-08-01 | Bullet Security Service(Kurla) | Journal | 107 | 60000
being amt bill received
2019-09-01 | Bullet Security Service(Kurla) | Journal | 121 | 60000
being amt bill received
2019-10-01 | Bullet Security Service(Kurla) | Journal | 135 | 60000
being amt bill received
2019-11-01 | Bullet Security Service(Kurla) | Journal | 143 | 60000
being amt bill received
2019-12-01 | Bullet Security Service(Kurla) | Journal | 157 | 60000
being amt bill received
2020-01-01 | Bullet Security Service(Kurla) | Journal | 169 | 60000
being amt bill received
2020-02-01 | Bullet Security Service(Kurla) | Journal | 184 | 60000
being amt bill received
2020-03-31 | Bullet Security Service(Kurla) | Journal | 200 | 120000
being amt transfer
2020-04-30 | Bullet Security Service(Kurla) | Journal | 2 | 60000
being amt bills received & transfer
2020-06-01 | Bullet Security Service(Kurla) | Journal | 3 | 60000
being amt bills received & transfer
2020-07-01 | Bullet Security Service(Kurla) | Journal | 4 | 30000
being amt bills received & transfer
2020-08-01 | Bullet Security Service(Kurla) | Journal | 5 | 15000
being amt bills receied & transfer
2020-09-01 | Bullet Security Service(Kurla) | Journal | 6 | 15000
being amt bills received & transfer
2020-10-01 | Bullet Security Service(Kurla) | Journal | 12 | 15000
received bills & transfer
2020-11-01 | Bullet Security Service(Kurla) | Journal | 13 | 15000
being amt bills received & Transfer
2020-12-01 | Bullet Security Service(Kurla) | Journal | 14 | 15000
being amt bills received & transfer
2021-01-01 | Bullet Security Service(Kurla) | Journal | 17 | 15000
being amt bills received & transfer
2021-02-01 | Bullet Security Service(Kurla) | Journal | 19 | 15000
being amt bills received & transfere
2021-03-01 | Bullet Security Service(Kurla) | Journal | 34 | 15000
being amt bills received & traansfer
2021-04-01 | Bullet Security Service(Kurla) | Journal | 1 | 15000
being amt bills received March-21
2021-05-01 | Bullet Security Service(Kurla) | Journal | 9 | 15000
being amt bills received April-21
2021-06-01 | Bullet Security Service(Kurla) | Journal | 12 | 15000
being amt bills received june-21
2021-07-01 | Bullet Security Service(Kurla) | Journal | 17 | 15000
being amt bills received & transfer
2021-08-01 | Bullet Security Service(Kurla) | Journal | 25 | 15000
being amt bills july received & transfer
2021-09-01 | Bullet Security Service(Kurla) | Journal | 32 | 15000
received bills
2021-10-01 | Bullet Security Service(Kurla) | Journal | 39 | 15000
received bills dated 1.10.21
2021-11-01 | Bullet Security Service(Kurla) | Journal | 46 | 15000
being amt bills received & transfer
2021-12-07 | Bullet Security Service(Kurla) | Journal | 59 | 45000
received bills dated 1.12.21
2022-01-01 | Bullet Security Service(Kurla) | Journal | 66 | 45000
being bills received & transfer
2022-02-01 | Bullet Security Service(Kurla) | Journal | 78 | 45000
being amt bills received & transfer
2022-03-31 | Bullet Security Service(Kurla) | Journal | 96 | 45000
being amt bills received & transfer
2022-01-28 | State Bank of India(30%) A/c 40695382068 | Payment | 529 | 1947000
being online payment commission on loan processing
2022-01-28 | State Bank of India(30%) A/c 40695382068 | Payment | 530 | 11800
being online amt paid ors mis
2022-02-22 | State Bank of India(30%) A/c 40695382068 | Payment | 690 | 501500
being online payment for Insurance
2021-12-30 | HDFC Bank LTD | Payment | 475 | 6750
being online amt paid
2022-01-24 | HDFC Bank LTD | Payment | 520 | 465011.8
being amt paid for stampduty for loan from SBI
2022-01-27 | HDFC Bank LTD | Payment | 523 | 1925000
being paid online for loan processing fees
2022-01-27 | HDFC Bank LTD | Payment | 524 | 25960
being amt charges pid for documentaion charges
2022-01-28 | State Bank of India(30%) A/c 40695382068 | Payment | 527 | 472
being amt online transfer for Recoveries for cersai charges
2022-01-28 | State Bank of India(30%) A/c 40695382068 | Payment | 528 | 25960
being onlie payment for mis charges
2021-04-03 | Petty Cash | Payment | 4 | 100
2021-04-05 | Petty Cash | Payment | 5 | 300
2021-04-07 | HDFC Bank LTD | Payment | 15 | 64613
2021-04-30 | Petty Cash | Payment | 63 | 300
2021-05-07 | Petty Cash | Payment | 76 | 2700
2021-05-08 | Petty Cash | Payment | 77 | 5010
2021-05-14 | Petty Cash | Payment | 82 | 400
2021-05-16 | Petty Cash | Payment | 83 | 2170
2021-05-16 | Petty Cash | Payment | 84 | 2399
2021-05-22 | Petty Cash | Payment | 88 | 2500
2021-05-27 | Petty Cash | Payment | 94 | 2599
2021-05-28 | Petty Cash | Payment | 95 | 400
2021-05-29 | Petty Cash | Payment | 96 | 3400
2021-06-06 | Petty Cash | Payment | 110 | 3819
2021-06-07 | Petty Cash | Payment | 115 | 3300
2021-06-10 | Petty Cash | Payment | 123 | 300
2021-06-17 | Petty Cash | Payment | 140 | 3000
2021-06-22 | Petty Cash | Payment | 146 | 3659
2021-06-24 | HDFC Bank LTD | Payment | 149 | 400
2021-06-24 | HDFC Bank LTD | Payment | 150 | 1600
2021-06-24 | Petty Cash | Payment | 152 | 300
2021-07-01 | Petty Cash | Payment | 161 | 4000
2021-07-01 | Petty Cash | Payment | 162 | 300
2021-07-03 | Cash in Hand | Payment | 165 | 29861
2021-07-05 | Petty Cash | Payment | 167 | 3000
2021-07-07 | HDFC Bank LTD | Payment | 181 | 21258.88
2021-07-09 | Petty Cash | Payment | 185 | 4000
2021-07-09 | Petty Cash | Payment | 186 | 300
2021-07-09 | Petty Cash | Payment | 187 | 210
2021-07-13 | Petty Cash | Payment | 189 | 4500
2021-07-13 | Petty Cash | Payment | 191 | 1300
2021-07-13 | Petty Cash | Payment | 192 | 2300
2021-07-14 | Petty Cash | Payment | 194 | 3250
2021-07-14 | Petty Cash | Payment | 195 | 400
2021-07-21 | Petty Cash | Payment | 202 | 2500
2021-07-21 | Petty Cash | Payment | 203 | 400
2021-07-26 | Petty Cash | Payment | 208 | 4560
2021-07-28 | Petty Cash | Payment | 209 | 503
2021-07-28 | Petty Cash | Payment | 210 | 400
2021-07-30 | Petty Cash | Payment | 216 | 3299
2021-08-02 | Petty Cash | Payment | 236 | 1995
2021-08-04 | Petty Cash | Payment | 238 | 400
2021-08-05 | Petty Cash | Payment | 240 | 3300
2021-08-05 | Petty Cash | Payment | 241 | 1500
2021-08-07 | Petty Cash | Payment | 246 | 3700
2021-08-11 | Petty Cash | Payment | 248 | 400
2021-08-12 | Petty Cash | Payment | 249 | 4600
2021-08-14 | HDFC Bank LTD | Payment | 253 | 44055.5
2021-08-17 | Petty Cash | Payment | 259 | 3000
2021-08-19 | Petty Cash | Payment | 260 | 3400
2021-08-20 | Petty Cash | Payment | 262 | 3300
2021-08-23 | Petty Cash | Payment | 263 | 4340
2021-08-26 | Petty Cash | Payment | 266 | 3000
2021-08-30 | Petty Cash | Payment | 268 | 2800
2021-08-31 | Petty Cash | Payment | 269 | 3000
2021-09-02 | Petty Cash | Payment | 271 | 400
2021-09-05 | Petty Cash | Payment | 283 | 1500
2021-09-10 | Petty Cash | Payment | 291 | 400
2021-09-16 | Petty Cash | Payment | 294 | 400
2021-09-17 | HDFC Bank LTD | Payment | 298 | 107450
2021-09-20 | Petty Cash | Payment | 301 | 400
2021-09-21 | Petty Cash | Payment | 302 | 4400
2021-09-22 | Petty Cash | Payment | 304 | 5500
2021-09-24 | Petty Cash | Payment | 305 | 3500
2021-09-28 | Petty Cash | Payment | 307 | 300
2021-09-29 | Petty Cash | Payment | 309 | 3999
2021-10-02 | Petty Cash | Payment | 313 | 2400
2021-10-04 | Petty Cash | Payment | 314 | 220
2021-10-05 | Petty Cash | Payment | 323 | 300
2021-10-05 | Petty Cash | Payment | 327 | 1000
2021-10-06 | Petty Cash | Payment | 328 | 3400
2021-10-07 | Petty Cash | Payment | 329 | 3860
2021-10-10 | Petty Cash | Payment | 338 | 300
2021-10-13 | Petty Cash | Payment | 344 | 300
2021-10-16 | Petty Cash | Payment | 365 | 3500
2021-10-16 | Petty Cash | Payment | 366 | 1505
2021-10-18 | Petty Cash | Payment | 369 | 5700
2021-10-19 | Petty Cash | Payment | 372 | 400
2021-10-22 | Petty Cash | Payment | 375 | 3000
2021-10-23 | Petty Cash | Payment | 378 | 400
2021-10-26 | Petty Cash | Payment | 379 | 4500
2021-10-27 | Petty Cash | Payment | 380 | 3799
2021-10-27 | Petty Cash | Payment | 381 | 400
2021-11-01 | Petty Cash | Payment | 383 | 400
2021-11-02 | Petty Cash | Payment | 387 | 2699
2021-11-02 | Petty Cash | Payment | 388 | 4800
2021-11-05 | Petty Cash | Payment | 397 | 1500
2021-11-08 | Petty Cash | Payment | 399 | 400
2021-11-09 | Petty Cash | Payment | 402 | 3230
2021-11-13 | Petty Cash | Payment | 410 | 400
2021-11-15 | Petty Cash | Payment | 413 | 3300
2021-11-17 | Petty Cash | Payment | 414 | 4500
2021-11-18 | Petty Cash | Payment | 416 | 400
2021-11-20 | Petty Cash | Payment | 419 | 2600
2021-11-22 | Petty Cash | Payment | 420 | 3600
2021-11-26 | Petty Cash | Payment | 423 | 400
2021-11-27 | Petty Cash | Payment | 424 | 2500
2021-11-27 | Petty Cash | Payment | 425 | 3399
2021-12-06 | Petty Cash | Payment | 446 | 3000
2021-12-06 | Petty Cash | Payment | 447 | 2000
2021-12-07 | Petty Cash | Payment | 448 | 400
2021-12-11 | Petty Cash | Payment | 451 | 400
2021-12-16 | Petty Cash | Payment | 456 | 4000
2021-12-21 | Petty Cash | Payment | 466 | 3200
2021-12-21 | Petty Cash | Payment | 467 | 3000
2021-12-21 | Petty Cash | Payment | 468 | 400
2021-12-27 | Petty Cash | Payment | 471 | 400
2021-12-30 | Petty Cash | Payment | 476 | 3349
2021-12-30 | Petty Cash | Payment | 477 | 400
2021-12-31 | Petty Cash | Payment | 478 | 3759
2022-01-04 | Petty Cash | Payment | 483 | 400
2022-01-04 | Petty Cash | Payment | 484 | 2359
2022-01-04 | Petty Cash | Payment | 485 | 3001
2022-01-07 | HDFC Bank LTD | Payment | 489 | 6347
2022-01-07 | Petty Cash | Payment | 491 | 2899
2022-01-15 | Petty Cash | Payment | 505 | 400
2022-01-15 | Petty Cash | Payment | 506 | 2650
2022-01-15 | Petty Cash | Payment | 507 | 2899
2022-01-20 | Petty Cash | Payment | 517 | 400
2022-01-21 | Petty Cash | Payment | 518 | 3001
2022-01-25 | Petty Cash | Payment | 522 | 400
2022-01-27 | HDFC Bank LTD | Payment | 525 | 5014.16
2022-01-29 | Petty Cash | Payment | 544 | 400
2022-02-17 | HDFC Bank LTD | Payment | 661 | 40000
2022-02-19 | HDFC Bank LTD | Payment | 665 | 2200
2021-05-05 | IDBI Rera A/c Ambrish | Payment | 68 | 15000
2021-05-06 | HDFC Bank LTD | Payment | 70 | 13750
2021-06-01 | HDFC Bank LTD | Payment | 102 | 13750
2021-06-05 | IDBI Rera A/c Ambrish | Payment | 107 | 15000
2021-06-05 | IDBI Rera A/c Ambrish | Payment | 108 | 9000
2021-06-05 | IDBI Rera A/c Ambrish | Payment | 109 | 8250
2021-07-05 | HDFC Bank LTD | Payment | 168 | 13750
2021-07-05 | IDBI Rera A/c Ambrish | Payment | 174 | 9000
2021-07-05 | IDBI Rera A/c Ambrish | Payment | 175 | 15000
2021-07-05 | IDBI Rera A/c Ambrish | Payment | 176 | 8250
2021-08-01 | HDFC Bank LTD | Payment | 225 | 13750
2021-08-02 | IDBI Rera A/c Ambrish | Payment | 231 | 15000
2021-08-02 | IDBI Rera A/c Ambrish | Payment | 232 | 9000
2021-08-02 | IDBI Rera A/c Ambrish | Payment | 233 | 8250
2021-09-04 | IDBI Rera A/c Ambrish | Payment | 275 | 8250
2021-09-04 | IDBI Rera A/c Ambrish | Payment | 276 | 9000
2021-09-04 | IDBI Rera A/c Ambrish | Payment | 277 | 15000
2021-09-05 | HDFC Bank LTD | Payment | 281 | 13750
2021-10-05 | IDBI Rera A/c Ambrish | Payment | 317 | 15000
2021-10-05 | IDBI Rera A/c Ambrish | Payment | 318 | 8250
2021-10-05 | IDBI Rera A/c Ambrish | Payment | 319 | 9000
2021-10-05 | HDFC Bank LTD | Payment | 321 | 13750
2021-11-03 | HDFC Bank LTD | Payment | 390 | 13750
2021-11-03 | IDBI Rera A/c Ambrish | Payment | 391 | 15000
2021-11-03 | IDBI Rera A/c Ambrish | Payment | 392 | 9000
2021-11-03 | IDBI Rera A/c Ambrish | Payment | 393 | 8250
2021-12-01 | IDBI Rera A/c Ambrish | Payment | 430 | 15000
2021-12-01 | IDBI Rera A/c Ambrish | Payment | 431 | 18000
2021-12-01 | IDBI Rera A/c Ambrish | Payment | 432 | 16500
2021-12-01 | IDBI Rera A/c Ambrish | Payment | 434 | 27500
2021-12-01 | IDBI Rera A/c Ambrish | Payment | 436 | 35999
2022-01-10 | IDBI Rera A/c Ambrish | Payment | 492 | 40000
2022-01-10 | IDBI Rera A/c Ambrish | Payment | 493 | 15000
2022-01-11 | IDBI Rera A/c Ambrish | Payment | 495 | 18000
2022-01-11 | IDBI Rera A/c Ambrish | Payment | 496 | 16500
2022-01-11 | IDBI Rera A/c Ambrish | Payment | 497 | 27500
2022-02-04 | IDBI Rera A/c Ambrish | Payment | 565 | 15000
2022-02-04 | IDBI Rera A/c Ambrish | Payment | 566 | 27500
2022-02-05 | IDBI Rera A/c Ambrish | Payment | 567 | 40000
2022-02-05 | IDBI Rera A/c Ambrish | Payment | 570 | 16500
2022-02-22 | IDBI Rera A/c Ambrish | Payment | 687 | 18000
2022-03-05 | State Bank of India(A/c 40740926519) CC A/c | Payment | 715 | 20000
2022-03-05 | State Bank of India(A/c 40740926519) CC A/c | Payment | 716 | 27500
2022-03-05 | State Bank of India(A/c 40740926519) CC A/c | Payment | 717 | 18000
2022-03-05 | State Bank of India(A/c 40740926519) CC A/c | Payment | 718 | 16500
2022-03-07 | State Bank of India(A/c 40740926519) CC A/c | Payment | 727 | 40000
2022-03-31 | Professional Tax | Journal | 92 | 18000
2022-03-31 | Salary Payable A/c | Journal | 93 | 20000
2022-03-31 | Professional Tax | Journal | 94 | 27500
2022-03-31 | Salary Payable A/c | Journal | 95 | 16500
2022-04-26 | Insurance Premium-SBI |  |  | 1972
2022-04-26 | Insurance Premium-SBI |  |  | 3204
2022-05-25 | Electricity-Expenses |  |  | 73540
2022-04-01 | Bullet Securities |  |  | 45000
2022-05-01 | Bullet Securities |  |  | 45000
2022-04-08 | State bank of India CC A/c |  |  | 35400
2022-04-08 | State bank of India CC A/c |  |  | 5900
2022-06-29 | Electricity-Expenses (Ambarish) |  |  | 31850
2022-06-01 | Bullet Security Service (Kurla) |  |  | 45000
2022-06-07 | Salary |  |  | 20000
2022-06-07 | Salary |  |  | 27500
2022-06-27 | Salary |  |  | 16500
2022-07-08 | Salary |  |  | 27500
2022-07-08 | Salary |  |  | 16500
2022-07-08 | Salary |  |  | 20000
2022-08-04 | Salary |  |  | 16500
2022-08-04 | Salary |  |  | 27500
2022-08-05 | Salary |  |  | 18000
2022-08-05 | Salary |  |  | 20000
2022-09-05 | Salary |  |  | 16500
2022-09-05 | Salary |  |  | 20000
2022-09-05 | Salary |  |  | 18000
2022-09-05 | Salary |  |  | 27500
2022-07-08 | Bullet Security |  |  | 45000
2022-08-08 | Bullet Security |  |  | 45000
2022-09-05 | Bullet Security |  |  | 45000
2022-06-29 | Electricity-Expenses (Ambarish) |  |  | 62870
2022-09-20 | Electricity-Expenses (Ambarish) |  |  | 40960
2022-11-11 | State Bank of India CC A/c |  |  | 96580
2022-12-19 | State Bank of India CC A/c |  |  | 60010
2022-10-13 | Office Expenses- HDFC Bank |  |  | 4425
2022-12-19 | Office Expenses- HDFC Bank |  |  | 5133
2022-10-06 | State Bank of India - Salary Expenses |  |  | 20000
2022-10-06 | State Bank of India - Salary Expenses |  |  | 16500
2022-10-06 | State Bank of India - Salary Expenses |  |  | 18000
2022-10-07 | State Bank of India - Salary Expenses |  |  | 27500
2022-10-20 | State Bank of India - Salary Expenses |  |  | 16500
2022-10-20 | State Bank of India - Salary Expenses |  |  | 27500
2022-10-20 | State Bank of India - Salary Expenses |  |  | 20000
2022-11-01 | State Bank of India - Salary Expenses |  |  | 18000
2022-11-04 | State Bank of India - Salary Expenses |  |  | 20000
2022-11-04 | State Bank of India - Salary Expenses |  |  | 16500
2022-11-04 | State Bank of India - Salary Expenses |  |  | 27500
2022-12-03 | State Bank of India - Salary Expenses |  |  | 20000
2022-12-03 | State Bank of India - Salary Expenses |  |  | 27500
2022-12-03 | State Bank of India - Salary Expenses |  |  | 16500
2023-01-05 | Popular Copy Centre |  |  | 4295
2023-01-10 | Stationary Expenses |  |  | 8850
2022-12-19 | Electricity |  |  | 64480
2023-01-01 | Bullet Security Services |  |  | 45000
2023-01-04 | State Bank of India - Salary Expenses |  |  | 20000
2023-01-04 | State Bank of India - Salary Expenses |  |  | 27500
2023-01-04 | State Bank of India - Salary Expenses |  |  | 16500
2023-01-05 | State Bank of India - Salary Expenses |  |  | 18000
2023-01-23 | State Bank of India - Salary Expenses |  |  | 42000
2023-02-04 | State Bank of India - Salary Expenses |  |  | 18500
2023-02-04 | State Bank of India - Salary Expenses |  |  | 27500
2023-02-09 | State Bank of India - Salary Expenses |  |  | 18000
2023-02-02 | Water Charges |  |  | 11900
2023-02-01 | Bullet Security Services |  |  | 45000
2023-02-18 | Electricity |  |  | 53880
2023-02-07 | Popular Copy Centre |  |  | 1934.72
2023-03-01 | Popular Copy Centre |  |  | 4529.86
2023-03-31 | Insurance Premium-SBI |  |  | 150450
2023-03-24 | Electricity |  |  | 49410
2023-03-01 | Bullet Security Services |  |  | 45000
2023-03-06 | State Bank of India - Salary Expenses |  |  | 18500
2023-03-06 | State Bank of India - Salary Expenses |  |  | 27500
2023-03-06 | State Bank of India - Salary Expenses |  |  | 18000
17.4.23 | Electricity Charges |  |  | 51190
26.5.23 | Electricity Charges |  |  | 49880
14.6.23 | Electricity Charges |  |  | 48270
1.5.23 | Bullet security |  |  | 45000
2022-10-01 | Bullet Security Service(Kurla) |  |  | 45000
2.4.23 | Bullet security |  |  | 45000
4.6.23 | Popular Copy |  |  | 4618
5.5.23 | Popular Copy |  |  | 2862
5.5.23 | Popular Copy |  |  | 8481
1.6.23 | Bullet Security |  |  | 45000
2023-08-01 | Popular copy Centre |  |  | 8438
2023-08-01 | Bullet Secuirty |  |  | 45000
2023-08-19 | Electricity Charges |  |  | 44430
2023-08-07 | Salary |  |  | 82000
2023-09-01 | Popular Copy Centrea |  |  | 3407
2023-09-01 | Bullet Security |  |  | 45000
2023-09-14 | Electricty |  |  | 48450
2023-07-01 | Bullet Security |  |  | 45000
2023-07-09 | Electricity Charges |  |  | 644864
2023-07-18 | Electricity Charges |  |  | 36790
2023-07-01 | Salary |  |  | 111000
2023-07-09 | Popular Copy Centre |  |  | 15767
| Bank Charges |  |  | 124284.2
| Pranay Nagar CHSL |  |  | 10096
| ROC |  |  | 3717
| Salary |  |  | 274500
2023-10-06 | Salary |  |  | 18500
2023-10-06 | Salary |  |  | 30000
2023-10-07 | Salary |  |  | 15000
2023-10-10 | Salary |  |  | 18000
2023-11-04 | Salary |  |  | 30000
2023-11-04 | Salary |  |  | 18300
2023-11-06 | Salary |  |  | 18000
2023-11-06 | Salary |  |  | 15000
2023-12-05 | Salary |  |  | 15000
2023-12-05 | Salary |  |  | 20000
2023-12-05 | Salary |  |  | 30000
| Bank Charges |  |  | 50
| General Exp |  |  | 5957.82
| Pranay Nagar Co-Op Hsg.Soc.Ltd |  |  | 6773
2023-10-13 | Electricity Bill |  |  | 44260
2023-11-24 | Electricity Bill |  |  | 43070
2023-12-02 | Electricity Bill |  |  | 92652
2023-12-26 | Electricity Bill |  |  | 32680
29.01.2024 | Popular Copy Centre |  |  | 6314
01.01.2024 | Bullet Security Service |  |  | 68708
30.01.2024 | Electicity Charges |  |  | 30690
2024-02-01 | Bullet Security Service(Kurla) |  |  | 75000
2024-02-29 | Popular Copy Centre(Ambarish) |  |  | 6314
04.03.2024 | Popular Copy Centre |  |  | 6314
04.03.2024 | Popular Copy Centre |  |  | 9031
01.03.2024 | Bullet Security |  |  | 75000
04.03.2024 | Electicity Charges |  |  | 29130
25.03.2024 | Electicity Charges |  |  | 31220
05.03.2024 | Suzan Sport Club |  |  | 196179
05.03.2024 | Suzan Sport Club |  |  | 53210
05.03.2024 | Suzan Sport Club |  |  | 67402
13726447

## Marketing Cost
2022-03-07 | (as per details) | Payment | 726 | 800000
State Bank of India(A/c 40740926519) CC A/c
TDS on Commission
being online amt paid to Vijaysingh Mahajan on a/c Brokarage
2022-03-08 | (as per details) | Payment | 730 | 400000
State Bank of India(A/c 40740926519) CC A/c
TDS on Commission
being amt paid by online on a/c commision on sale of flat at Ambarish
2022-07-18 | Stamp Duty Charges Paid |  |  | 432000
2022-07-19 | Stamp Duty Charges Paid |  |  | 30000
2022-08-25 | Stamp Duty Charges Paid |  |  | 648000
2022-07-01 | Pooja Telecom |  |  | 8500
2022-09-21 | Stamp Duty Charges Paid |  |  | 384000
2022-09-28 | Stamp Duty Charges Paid |  |  | 468000
2022-10-13 | Stamp Duty - State Bank of India CC A/c |  |  | 372000
2022-11-29 | Stamp Duty - State Bank of India CC A/c |  |  | 540000
2022-12-05 | Stamp Duty - State Bank of India CC A/c |  |  | 504000
2022-12-13 | Stamp Duty - State Bank of India CC A/c |  |  | 390000
2023-01-06 | Stamp Duty - State Bank of India CC A/c |  |  | 350000
2023-01-06 | Stamp Duty - State Bank of India CC A/c |  |  | 390000
2023-01-06 | Stamp Duty - State Bank of India CC A/c |  |  | 528000
2023-01-25 | Stamp Duty - State Bank of India CC A/c |  |  | 450000
2023-01-29 | Stamp Duty - State Bank of India CC A/c |  |  | 540000
2023-02-09 | Stamp Duty - State Bank of India CC A/c |  |  | 540000
2023-02-09 | Stamp Duty - State Bank of India CC A/c |  |  | 552000
2023-02-17 | Stamp Duty - State Bank of India CC A/c |  |  | 504000
2023-02-22 | Stamp Duty - State Bank of India CC A/c |  |  | 455000
2023-02-22 | Stamp Duty - State Bank of India CC A/c |  |  | 528000
2023-03-01 | Stamp Duty - State Bank of India CC A/c |  |  | 540000
2023-03-01 | Stamp Duty - State Bank of India CC A/c |  |  | 450000
2023-03-03 | Stamp Duty - State Bank of India CC A/c |  |  | 528000
2023-03-06 | Stamp Duty - State Bank of India CC A/c |  |  | 528000
2023-03-06 | Stamp Duty - State Bank of India CC A/c |  |  | 438000
2023-03-08 | Stamp Duty - State Bank of India CC A/c |  |  | 492000
2023-03-14 | Stamp Duty - State Bank of India CC A/c |  |  | 540000
2023-03-14 | Stamp Duty - State Bank of India CC A/c |  |  | 540000
2023-03-14 | Stamp Duty - State Bank of India CC A/c |  |  | 468000
2023-03-17 | Stamp Duty - State Bank of India CC A/c |  |  | 516000
2023-03-21 | Stamp Duty - State Bank of India CC A/c |  |  | 540000
2023-03-21 | Stamp Duty - State Bank of India CC A/c |  |  | 528000
2023-03-25 | Stamp Duty - State Bank of India CC A/c |  |  | 504000
2023-03-28 | Stamp Duty - State Bank of India CC A/c |  |  | 528000
2023-03-28 | Stamp Duty - State Bank of India CC A/c |  |  | 540000
2023-03-30 | Stamp Duty - State Bank of India CC A/c |  |  | 534000
1/4 to 30/6 | Stamp Duty |  |  | 4765000
2023-08-12 | Stamp Duty |  |  | 456000
2023-08-12 | Stamp Duty |  |  | 450000
2023-11-03 | Stamp Duty |  |  | 540000
2023-11-08 | Stamp Duty |  |  | 564000
2023-11-21 | Stamp Duty |  |  | 540000
| TOTAL |  |  | 25342500

## Professional Cost
Date | Particulars | Vch Type | Vch No. | Amount
2016-10-03 | Associated Architect |  |  | 115000
Ch. No. :paid by cheque 0000087 on a/c appointment for Architect for Ambrish Kurla
2018-05-02 | (as per details) | Payment | 39 | 35000
HDFC Bank LTD
TDS on Professional Fees
paid by cheque 000262 on a/c transfer - Ajit Upadhaya
2018-06-01 | (as per details) | Payment | 74 | 35000
HDFC Bank LTD
TDS on Professional Fees
paid by cheque 000272 on a/c fees paid
2018-07-02 | (as per details) | Payment | 105 | 35000
HDFC Bank LTD
TDS on Professional Fees
paid by cheque 000287 on a/c fees paid - Ajit Upadhaya
2018-08-01 | (as per details) | Payment | 144 | 35000
HDFC Bank LTD
TDS on Professional Fees
paid by cheque000294 to Ajit Upadyay
2018-09-05 | (as per details) | Payment | 240 | 35000
HDFC Bank LTD
TDS on Professional Fees
paid by 000305 on a/c Professional - Ajit Upadhyay
2018-10-01 | (as per details) | Payment | 324 | 35000
HDFC Bank LTD
TDS on Professional Fees
paid by cheque 000313 on a/c professional fees paid - Ajit Upadhaya
2018-11-01 | (as per details) | Payment | 377 | 35000
HDFC Bank LTD
TDS on Professional Fees
paid by cheque 000326 On a/c Professional fees - Ajit Upadhyay
2019-04-01 | (as per details) | Journal | 1 | 750
| CGST 9% on Professional Fees |  |  | 67.5
| SGST 9% on Professional Fees |  |  | 67.5
Global Lab(Kurla)
received bills No 13243
2019-04-01 | (as per details) | Journal | 2 | 375
| CGST 9% on Professional Fees |  |  | 34
| SGST 9% on Professional Fees |  |  | 34
Global Lab(Kurla)
received bills 13244
2019-04-01 | (as per details) | Journal | 3 | 375
| SGST 9% on Professional Fees |  |  | 34
| CGST 9% on Professional Fees |  |  | 34
Global Lab(Kurla)
received bills 13245
2019-04-02 | (as per details) | Journal | 10 | 1125
| SGST 9% on Professional Fees |  |  | 101.5
| CGST 9% on Professional Fees |  |  | 101.5
Global Lab(Kurla)
received bills 13560
2019-04-02 | (as per details) | Journal | 11 | 750
| SGST 9% on Professional Fees |  |  | 67.5
| CGST 9% on Professional Fees |  |  | 67.5
Global Lab(Kurla)
received bills 13316
2019-04-02 | (as per details) | Journal | 12 | 375
| CGST 9% on Professional Fees |  |  | 34
| SGST 9% on Professional Fees |  |  | 34
Global Lab(Kurla)
received bills 13317
2019-04-02 | (as per details) | Journal | 13 | 375
| SGST 9% on Professional Fees |  |  | 34
| CGST 9% on Professional Fees |  |  | 34
Global Lab(Kurla)
received bills 13410
2019-04-25 | (as per details) | Journal | 28 | 750
| CGST 9% on Professional Fees |  |  | 67.5
| SGST 9% on Professional Fees |  |  | 67.5
Global Lab(Kurla)
received bills 107356
2019-04-25 | (as per details) | Journal | 29 | 750
| CGST 9% on Professional Fees |  |  | 67.5
| SGST 9% on Professional Fees |  |  | 67.5
Global Lab(Kurla)
received bills 107354
2019-04-25 | (as per details) | Journal | 30 | 1125
| CGST 9% on Professional Fees |  |  | 101.5
| SGST 9% on Professional Fees |  |  | 101.5
Global Lab(Kurla)
received bills 107348
2019-04-25 | (as per details) | Journal | 31 | 1000
| CGST 9% on Professional Fees |  |  | 90
| SGST 9% on Professional Fees |  |  | 90
Global Lab(Kurla)
received bills 107346
2019-04-25 | (as per details) | Journal | 32 | 375
| CGST 9% on Professional Fees |  |  | 34
| SGST 9% on Professional Fees |  |  | 34
Global Lab(Kurla)
received bills 107352
2019-05-04 | (as per details) | Journal | 51 | 375
| CGST 9% on Professional Fees |  |  | 34
| SGST 9% on Professional Fees |  |  | 34
Global Lab(Kurla)
received bills 108230
2019-05-04 | (as per details) | Journal | 52 | 1125
| CGST 9% on Professional Fees |  |  | 101.5
| SGST 9% on Professional Fees |  |  | 101.5
Global Lab(Kurla)
received bills 108229
2019-05-08 | (as per details) | Journal | 55 | 1125
| CGST 9% on Professional Fees |  |  | 101.5
| SGST 9% on Professional Fees |  |  | 101.5
Global Lab(Kurla)
received bills 108439
2019-05-14 | (as per details) | Journal | 67 | 1125
| CGST 9% on Professional Fees |  |  | 101.5
| SGST 9% on Professional Fees |  |  | 101.5
Global Lab(Kurla)
received bills 108936
2019-05-14 | (as per details) | Journal | 68 | 375
| CGST 9% on Professional Fees |  |  | 34
| SGST 9% on Professional Fees |  |  | 34
Global Lab(Kurla)
bill No 108938
2019-05-14 | (as per details) | Journal | 69 | 750
| CGST 9% on Professional Fees |  |  | 67.5
| SGST 9% on Professional Fees |  |  | 67.5
Global Lab(Kurla)
received bills 108942
2019-05-15 | (as per details) | Journal | 74 | 750
| CGST 9% on Professional Fees |  |  | 67.5
| SGST 9% on Professional Fees |  |  | 67.5
Global Lab(Kurla)
received bills 109066
2019-05-23 | (as per details) | Journal | 81 | 2250
| CGST 9% on Professional Fees |  |  | 202.5
| SGST 9% on Professional Fees |  |  | 202.5
Global Lab(Kurla)
received bills 109679
2019-06-01 | (as per details) | Journal | 84 | 1125
| SGST 9% on Professional Fees |  |  | 101.5
| CGST 9% on Professional Fees |  |  | 101.5
Global Lab(Kurla)
received bill No 110309
2019-06-04 | (as per details) | Journal | 87 | 375
| CGST 9% on Professional Fees |  |  | 34
| SGST 9% on Professional Fees |  |  | 34
Global Lab(Kurla)
received bills No 110631
2019-06-04 | (as per details) | Journal | 88 | 1500
| CGST 9% on Professional Fees |  |  | 135
| SGST 9% on Professional Fees |  |  | 135
Global Lab(Kurla)
received bills 110632
2019-06-11 | (as per details) | Journal | 90 | 2125
| CGST 9% on Professional Fees |  |  | 191.5
| SGST 9% on Professional Fees |  |  | 191.5
Global Lab(Kurla)
received bills No 111214
2019-06-11 | (as per details) | Journal | 91 | 375
| SGST 9% on Professional Fees |  |  | 34
| CGST 9% on Professional Fees |  |  | 34
Global Lab(Kurla)
received bills 111223
2019-06-13 | (as per details) | Journal | 92 | 375
| CGST 9% on Professional Fees |  |  | 34
| SGST 9% on Professional Fees |  |  | 34
Global Lab(Kurla)
received bills 111451
2019-06-13 | (as per details) | Journal | 93 | 5500
| CGST 9% on Professional Fees |  |  | 495
| SGST 9% on Professional Fees |  |  | 495
Global Lab(Kurla)
received bills 111450
2019-06-19 | (as per details) | Journal | 95 | 375
| CGST 9% on Professional Fees |  |  | 34
| SGST 9% on Professional Fees |  |  | 34
Global Lab(Kurla)
received bills 110630
2019-06-19 | (as per details) | Journal | 96 | 1125
| CGST 9% on Professional Fees |  |  | 101.5
| SGST 9% on Professional Fees |  |  | 101.5
Global Lab(Kurla)
received bills 111936
2019-06-19 | (as per details) | Journal | 97 | 750
| SGST 9% on Professional Fees |  |  | 67
| CGST 9% on Professional Fees |  |  | 68
Global Lab(Kurla)
received bills 111935
2019-07-08 | (as per details) | Journal | 102 | 500
| CGST 9% on Professional Fees |  |  | 45
| SGST 9% on Professional Fees |  |  | 45
Global Lab(Kurla)
received bill no 1448-113299
2019-07-08 | (as per details) | Journal | 103 | 375
| CGST 9% on Professional Fees |  |  | 34
| SGST 9% on Professional Fees |  |  | 34
Global Lab(Kurla)
received bills 113298
2019-07-16 | (as per details) | Journal | 105 | 375
| CGST 9% on Professional Fees |  |  | 34
| SGST 9% on Professional Fees |  |  | 34
Global Lab(Kurla)
received bill No 114078
2019-07-16 | (as per details) | Journal | 106 | 375
| CGST 9% on Professional Fees |  |  | 34
| SGST 9% on Professional Fees |  |  | 34
Global Lab(Kurla)
received bills No 114080
2019-08-03 | (as per details) | Journal | 109 | 375
| CGST 9% on Professional Fees |  |  | 34
| SGST 9% on Professional Fees |  |  | 34
Global Lab(Kurla)
received bills 14752
2019-08-03 | (as per details) | Journal | 110 | 375
| CGST 9% on Professional Fees |  |  | 34
| SGST 9% on Professional Fees |  |  | 34
Global Lab(Kurla)
received bills No 14852
2019-08-05 | (as per details) | Journal | 111 | 115000
| CGST 9% on Professional Fees |  |  | 10350
| SGST 9% on Professional Fees |  |  | 10350
ECO MEP Consultant
being amt professional fees (Proforma invoice) received
2019-08-28 | (as per details) | Journal | 118 | 750
| CGST 9% on Professional Fees |  |  | 67.5
| SGST 9% on Professional Fees |  |  | 67.5
Global Lab(Kurla)
received bills 15162
2019-09-13 | (as per details) | Journal | 125 | 375
| CGST 9% on Professional Fees |  |  | 34
| SGST 9% on Professional Fees |  |  | 34
Global Lab(Kurla)
received bills 15452 dt.13.9
2019-09-28 | (as per details) | Journal | 132 | 375
| CGST 9% on Professional Fees |  |  | 34
| SGST 9% on Professional Fees |  |  | 34
Global Lab(Kurla)
received bills 119419
2020-01-20 | (as per details) | Journal | 177 | 1000000
| CGST 9% on Professional Fees |  |  | 90000
| SGST 9% on Professional Fees |  |  | 90000
S.B.Associates(Ambrish Exp)
TDS on Professional Fees
being amt bill received Bill No 082
2021-01-07 | (as per details) | Journal | 18 | 2500
| CGST 9% on Professional Fees |  |  | 225
| SGST 9% on Professional Fees |  |  | 225
Global Lab(Kurla)
TDS on Professional Fees
received bills
2021-02-24 | (as per details) | Journal | 32 | 750
| CGST 9% on Professional Fees |  |  | 67.5
| SGST 9% on Professional Fees |  |  | 67.5
Global Lab(Kurla)
TDS on Professional Fees
received bills dated 24.4.21
2021-02-24 | (as per details) | Journal | 33 | 375
| CGST 9% on Professional Fees |  |  | 33.75
| SGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
TDS on Professional Fees
received bills kurla site
2021-04-16 | (as per details) | Journal | 3 | 750
| CGST 9% on Professional Fees |  |  | 67.5
| SGST 9% Purchase |  |  | 67.5
Global Lab(Kurla)
TDS on Professional Fees
received bills on 11.6.21
2021-04-16 | (as per details) | Journal | 4 | 750
| CGST 9% on Professional Fees |  |  | 67.5
| SGST 9% on Professional Fees |  |  | 67.5
Global Lab(Kurla)
TDS on Professional Fees
being Bill no 20315-154315 received on aa.6.21
2021-04-16 | (as per details) | Journal | 5 | 375.5
| CGST 9% on Professional Fees |  |  | 33.75
| SGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
TDS on Professional Fees
being amt bills received 19693-154316 on 11.6.21
2021-04-16 | (as per details) | Journal | 6 | 750
| SGST 9% on Professional Fees |  |  | 67.5
| CGST 9% on Professional Fees |  |  | 67.5
Global Lab(Kurla)
TDS on Professional Fees
being amt bill dated 8.3.21 No 19537-150927 on 11.6.21
2021-07-01 | (as per details) | Journal | 16 | 150000
| CGST 9% on Professional Fees |  |  | 13500
| SGST 9% on Professional Fees |  |  | 13500
Ubaid Pettiwala(Ambrish)
being amt bills received & transfer
2021-07-05 | (as per details) | Journal | 18 | 119426
| CGST 9% on Professional Fees |  |  | 10748.34
| SGST 9% on Professional Fees |  |  | 10748.34
ECO MEP Consultant
TDS on Professional Fees
TDS on Professional Fees
being amt bills received
2021-07-13 | (as per details) | Journal | 20 | 375
| CGST 9% on Professional Fees |  |  | 33.75
| SGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills 38152-159096
2021-07-13 | (as per details) | Journal | 21 | 750
| CGST 9% on Professional Fees |  |  | 67.5
| SGST 9% on Professional Fees |  |  | 67.5
Global Lab(Kurla)
received bills 38152-158630
2021-07-22 | (as per details) | Journal | 23 | 750
| CGST 9% on Professional Fees |  |  | 67.5
| SGST 9% on Professional Fees |  |  | 67.5
Global Lab(Kurla)
received bills no 38152/22.7.21
2021-07-29 | (as per details) | Journal | 24 | 375
| CGST 9% on Professional Fees |  |  | 33.75
| SGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bill no 38566-160413 dated 29.7.21
2021-08-04 | (as per details) | Journal | 26 | 375
| CGST 9% on Professional Fees |  |  | 33.75
| SGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills 38152 -160794
2021-08-04 | (as per details) | Journal | 27 | 375
| CGST 9% on Professional Fees |  |  | 33.75
| SGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills no 38152/160861
2021-08-18 | (as per details) | Journal | 29 | 375
| SGST 9% on Professional Fees |  |  | 33.75
| CGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills 38566-162081
2021-08-24 | (as per details) | Journal | 30 | 375
| CGST 9% on Professional Fees |  |  | 33.75
| SGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
receiced bills 39016-162490
2021-08-24 | (as per details) | Journal | 31 | 375
| SGST 9% on Professional Fees |  |  | 33.75
| CGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills 38566-162491
2021-09-02 | (as per details) | Journal | 33 | 375
| CGST 9% on Professional Fees |  |  | 33.75
| SGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills No 39016-162804 dated 27.8.21
2021-09-11 | (as per details) | Journal | 36 | 375
| CGST 9% on Professional Fees |  |  | 33.75
| SGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills164018
2021-09-15 | (as per details) | Journal | 37 | 375
| SGST 9% on Professional Fees |  |  | 33.75
| CGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills 39458-164373
2021-09-15 | (as per details) | Journal | 38 | 375
| SGST 9% on Professional Fees |  |  | 33.75
| CGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills 39016-164508
2021-10-08 | (as per details) | Journal | 41 | 375
| CGST 9% on Professional Fees |  |  | 33.75
| SGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills 39458-166452
2021-10-09 | (as per details) | Journal | 42 | 375
| CGST 9% on Professional Fees |  |  | 33.75
| SGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills 39864-166628
2021-10-09 | (as per details) | Journal | 43 | 375
| SGST 9% on Professional Fees |  |  | 33.75
| CGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills 39864-166687
2021-10-09 | (as per details) | Journal | 44 | 375
| CGST 9% on Professional Fees |  |  | 33.75
| SGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bill 39864-166688
2021-10-13 | (as per details) | Journal | 45 | 375
| CGST 9% on Professional Fees |  |  | 33.75
| SGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills
2021-11-02 | (as per details) | Journal | 47 | 375
| CGST 9% on Professional Fees |  |  | 33.75
| SGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills 39864-166688
2021-11-02 | (as per details) | Journal | 48 | 375
| CGST 9% on Professional Fees |  |  | 33.75
| SGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills 40261-168236
2021-11-02 | (as per details) | Journal | 49 | 375
| SGST 9% on Professional Fees |  |  | 33.75
| CGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills 39864-168544
2021-11-20 | (as per details) | Journal | 53 | 375
| SGST 9% on Professional Fees |  |  | 33.75
| CGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills 40261-170110
2021-11-24 | (as per details) | Journal | 54 | 375
| CGST 9% on Professional Fees |  |  | 33.75
| SGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills 40261-170423
2021-11-25 | IDBI Rera A/c Ambrish | Payment | 422 | 10000
PAID BY CHEQUE 796295 tO nIKHIN dHING
2021-12-01 | (as per details) | Journal | 57 | 375
| CGST 9% on Professional Fees |  |  | 33.75
| SGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills 170627 dated 26.11.21
2021-12-11 | (as per details) | Journal | 61 | 375
| CGST 9% on Professional Fees |  |  | 33.75
| SGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills KRL-40723-172109
2021-12-15 | (as per details) | Journal | 62 | 375
| CGST 9% on Professional Fees |  |  | 33.75
| SGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
rexceived bills 40723-172570
2021-12-20 | (as per details) | Journal | 63 | 375
| CGST 9% on Professional Fees |  |  | 33.75
| SGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills KRL-41237-172843
2021-12-20 | (as per details) | Journal | 64 | 95000
| CGST 9% on Professional Fees |  |  | 8550
| SGST 9% on Professional Fees |  |  | 8550
Loan Processing Charges
TDS on Professional Fees
being amt bills received
2021-12-23 | (as per details) | Journal | 65 | 375
| CGST 9% on Professional Fees |  |  | 33.75
| SGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills41237-173215
2022-01-07 | (as per details) | Journal | 68 | 75000
| CGST 9% on Professional Fees |  |  | 6750
| SGST 9% on Professional Fees |  |  | 6750
ARA Designes(Kurla)
TDS on Professional Fees
being bills received & transfer
2022-01-07 | (as per details) | Journal | 69 | 375
| SGST 9% on Professional Fees |  |  | 33.75
| CGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills 41237-174792
2022-01-12 | (as per details) | Journal | 70 | 375
| SGST 9% on Professional Fees |  |  | 33.75
| CGST 9% on Professional Fees |  |  | 33.75
Global Lab(Kurla)
| Round of |  |  | 0.5
received bills 41237-175336
2022-01-17 | (as per details) | Journal | 71 | 450
| CGST 9% on Professional Fees |  |  | 40.5
| SGST 9% on Professional Fees |  |  | 40.5
Global Lab(Kurla)
received bills 41866-175765
2022-01-18 | (as per details) | Journal | 72 | 450
| CGST 9% on Professional Fees |  |  | 40.5
| SGST 9% on Professional Fees |  |  | 40.5
Global Lab(Kurla)
received bills KRL-41866-175871
2022-01-29 | (as per details) | Journal | 76 | 1125000
| CGST 9% on Professional Fees |  |  | 101250
| SGST 9% on Professional Fees |  |  | 101250
Mona Mehta(Ambarish)
TDS on Professional Fees
received bills
2022-02-01 | (as per details) | Journal | 79 | 110574
| CGST 9% on Professional Fees |  |  | 9951.66
| SGST 9% on Professional Fees |  |  | 9951.66
ECO MEP Consultant
Round of
Received bills & transfer
2022-02-09 | (as per details) | Journal | 84 | 25000
| CGST 9% on Professional Fees |  |  | 2250
| SGST 9% on Professional Fees |  |  | 2250
Shree Constructions(Ambarish)
TDS on Professional Fees
received bills
2022-02-19 | (as per details) | Payment | 666 | 60000
IDBI Rera A/c Ambrish
TDS on Professional Fees
beinf amt paid by cheque 806509 to Nikhil Dhing
2022-02-26 | (as per details) | Journal | 86 | 1500000
| CGST 9% on Professional Fees |  |  | 135000
| SGST 9% on Professional Fees |  |  | 135000
S.B.Associates(Ambrish Exp)
TDS on Professional Fees
received bills & transfer
2022-03-25 | (as per details) | Journal | 90 | 7500
| CGST 9% on Professional Fees |  |  | 675
| SGST 9% on Professional Fees |  |  | 675
Varma & Associates(Kurla)
being amt bills received & transfer
2021-12-14 | HDFC Bank LTD | Payment | 452 | 5900
being online payment for Cubictree Technology solutions pvt Ltd
2021-12-16 | HDFC Bank LTD | Payment | 454 | 20000
being online payment the legalist for fees
2021-12-16 | HDFC Bank LTD | Payment | 455 | 37500
being advance amt paid to Vastukala Consultant I pvt Lid on a/c advance payment
2021-12-24 | HDFC Bank LTD | Payment | 470 | 58350
paid by cheque 000827 to Vastukal Conslutancy
2022-02-02 | Mona Mehta(Ambarish) | Journal | 83 | 461768
being amt of stampduty for SBI loan paid & transfer Hypothication charges & Registration
2022-02-25 | IDBI Rera A/c Ambrish | Payment | 699 | 113000
being amt paid by cheque by RTGS
2022-02-28 | IDBI Rera A/c Ambrish | Payment | 704 | 5900
being amt paid by RTGS
2022-03-27 | S B Associates |  |  | 4012000
2015-08-03 | Union Bank of India Factory Lane | Payment | 36 | 85500
Ch. No. :paid by cheque 060226 on a/c Professiona fees paid
2017-08-09 | S.B.Associates(Ambrish Exp) | Payment |  | 767000
pqaid by cheque 000202 on a/c FArchitect fees paid
2018-02-16 | S.B.Associates(Ambrish Exp) | Payment |  | 236000
paid by cheque 00030 on a/c Architect fees paid
2018-08-14 | S.B.Associates(Ambrish Exp) | Payment |  | 200000
Bills Received
2018-12-05 | S.B.Associates(Ambrish Exp) | Payment |  | 200000
Bills Received
2017-01-24 | Associated Architect | Payment |  | 425500
Ch. No. :issued cheque 000001 towards Architect fees paid
2022-04-26 | Global Lab Materislas Test P L |  |  | 531
2022-04-26 | Global Lab Materislas Test P L |  |  | 531
2022-04-26 | Global Lab Materislas Test P L |  |  | 531
2022-04-26 | Global Lab Materislas Test P L |  |  | 531
2022-04-26 | Global Lab Materislas Test P L |  |  | 531
2022-04-26 | Global Lab Materislas Test P L |  |  | 531
2022-04-26 | Global Lab Materislas Test P L |  |  | 531
2022-04-26 | Global Lab Materislas Test P L |  |  | 531
2022-04-26 | Global Lab Materislas Test P L |  |  | 531
2022-04-26 | Global Lab Materislas Test P L |  |  | 531
2022-04-26 | Global Lab Materislas Test P L |  |  | 531
2022-04-26 | Global Lab Materislas Test P L |  |  | 531
2022-04-26 | Global Lab Materislas Test P L |  |  | 531
2022-06-07 | Professional Fees (Ambarish) |  |  | 10500
2022-06-24 | Global Lab Materislas Test P L |  |  | 531
2022-06-24 | Global Lab Materislas Test P L |  |  | 531
2022-06-24 | Global Lab Materislas Test P L |  |  | 531
2022-06-24 | Global Lab Materislas Test P L |  |  | 531
2022-06-24 | Global Lab Materislas Test P L |  |  | 531
2022-06-24 | Global Lab Materislas Test P L |  |  | 531
2022-06-24 | Global Lab Materislas Test P L |  |  | 531
2022-06-27 | Verma & Associates(Kurla) |  |  | 23600
2022-07-02 | Vastukala |  |  | 41300
2022-07-02 | Nikhil Dhing |  |  | 60000
2022-08-06 | Global Lab Materislas Test P L |  |  | 2124
2022-11-09 | Global Lab Materials test P L |  |  | 4779
2022-11-09 | Global Lab Materials test P L |  |  | 4779
2022-12-02 | Global Lab Materials test P L |  |  | 3186
2022-12-29 | Global Lab Materials test P L |  |  | 4779
2022-11-14 | R D Magdum |  |  | 250000
2023-01-01 | The Design Studio |  |  | 495600
2023-01-27 | Vastukala |  |  | 41300
2023-01-27 | Varma & Associates(Kurla) |  |  | 23600
2023-01-27 | Varma & Associates(Kurla) |  |  | 35400
2023-02-06 | Global Lab Materials test P L |  |  | 4248
2023-02-15 | S.B.Associates(Ambrish Exp) |  |  | 590000
2023-02-15 | Legal Expenses |  |  | 10000
2023-03-03 | Global Lab Materials test P L |  |  | 2124
2023-10-18 | Global Lab Materials Test Pvt.Ltd |  |  | 531
2023-10-19 | Global Lab Materials Test Pvt.Ltd |  |  | 1947
2023-10-19 | Global Lab Materials Test Pvt.Ltd |  |  | 2655
01.03.2024 | Design Studito |  |  | 330400
01.03.2024 | Arun M.Agarwal |  |  | 30385
13.03.2024 | S.B Associates |  |  | 590000
25.03.2024 | Eco MEP |  |  | 47200
31.03.2024 | Vastukala |  |  | 88500
31.03.2024 | Global Lab |  |  | 1062
2024-02-29 | Arun M Agarwal & Associate |  |  | 30350
2024-02-07 | Kheprri Consultancy Pvt. Ltd (Abhiram) |  |  | 4720
| TOTAL |  |  | 14966812

## Interest Cost
Date | Particulars | Vch Type | Vch No. | Amount
2022-01-31 | State Bank of India(A/c 40740926519) CC A/c | Payment | 553 | 53498
being online amt int paid
2022-02-28 | State Bank of India(A/c 40740926519) CC A/c | Payment | 702 | 521723
being amt interest debited by bank
2022-03-31 | State Bank of India(A/c 40740926519) CC A/c | Payment | 760 | 655906
being amt debited for int on loan
2022-04-30 | Interest on SBI CC A/c |  |  | 611715
2022-05-31 | Interest on SBI CC A/c |  |  | 712122
2022-06-30 | Interest on SBI CC A/c |  |  | 893040
2022-07-31 | Interest on SBI CC A/c |  |  | 973742
2022-08-31 | Interest on SBI CC A/c |  |  | 943802
2022-09-30 | Interest on SBI CC A/c |  |  | 971829
2022-10-31 | State Bank Of India CC A/c - Interest |  |  | 1052929
2022-11-30 | State Bank Of India CC A/c - Interest |  |  | 1010022
2022-12-31 | State Bank Of India CC A/c - Interest |  |  | 1117196
2023-01-31 | State Bank Of India CC A/c - Interest |  |  | 1143059
2023-02-28 | State Bank Of India CC A/c - Interest |  |  | 1140941
2023-03-31 | State Bank Of India CC A/c - Interest |  |  | 1279434
Till June | State Bank Of India CC A/c - Interest |  |  | 4316365
Till July |  |  |  | 1510314
Till August |  |  |  | 1599013
Till Sept | State Bank Of India CC A/c - Interest |  |  | 1534124
Till Oct |  |  |  | 1581522
Till Nov |  |  |  | 1471296
Till Dec |  |  |  | 1513200
31.01.2024 |  |  |  | 1553219
29.02.2024 |  |  |  | 1406039
31.03.2024 |  |  |  | 1155621
30721671

## Work Details
Sr. No. | Floor No. | Construction Area in Sq. M. | Completed area (Sq. M.) | Rate per Sq. M. | Full Value after completion | Percentage of work completed | Actual Expenditure till date in ` | Sr. No. | Floor No. | Construction Area in Sq. M. | Completed area (Sq. M.) | Work Completion as on 14.10.2022 | RCC Footing/Foundation | 5 | 5 | 5 | 5
1 | Ground | 611.99 | 611.99 | 26000 | 15911740 | 80% | 12729392 | 1 | Ground | 611.99 | 611.99 | Slab work is completed | RCC Plinth | 5 | 5 | 5 | 5
2 | 1st | 611.99 | 611.99 | 26000 | 15911740 | 95% | 15116153 | 2 | 1st | 611.99 | 611.99 | Slab work, Blockwork, Plasterwork, Flooring, Dadoing, Gypsum work, Door & Windows Frames and Kitchen Platform are completed | Full Building RCC | 40 | 40 | 5 | 40
3 | 2nd | 611.99 | 611.99 | 26000 | 15911740 | 95% | 15116153 | 3 | 2nd | 611.99 | 611.99 | Slab work, Blockwork, Plasterwork, Gypsum work, Door & Windows Frames and Kitchen Platform are completed | Internal Blockwork | 7 | 7 | 0.875 | 7
4 | 3rd | 615.39 | 615.39 | 26000 | 16000140 | 95% | 15200133 | 4 | 3rd | 615.39 | 615.39 | Slab work, Blockwork, Plasterwork, Gypsum work, Door & Windows Frames and Kitchen Platform are completed | External Blockwork | 7 | 0.4375 | 0.875 | 7
5 | 4th | 615.39 | 615.39 | 26000 | 16000140 | 95% | 15200133 | 5 | 4th | 615.39 | 615.39 | Slab work, Blockwork, Plasterwork, Gypsum work, Door & Windows Frames and Kitchen Platform are completed | Internal plastering | 3.5 | 3.5 | 0.4375 | 3.5
6 | 5th | 618.91 | 618.91 | 26000 | 16091660 | 95% | 15287077 | 6 | 5th | 618.91 | 618.91 | Slab work, Blockwork, Plasterwork, Door & Windows Frames and gypsum work are completed | External plastering | 3.5 | 3.5 | 0.4375 | 3.5
7 | 6th | 618.91 | 618.91 | 26000 | 16091660 | 95% | 15287077 | 7 | 6th | 618.91 | 618.91 | Slab work, 50% Blockwork, Door & Windows Frames are completed, | Doors & Windows | 5 | 5 | 0.625 | 5
8 | 7th | 618.91 | 618.91 | 26000 | 16091660 | 95% | 15287077 | 8 | 7th | 618.91 | 618.91 | Slab work, Blockwork, Plasterwork, Door & Windows Frames and gypsum work are completed | Flooring, Tiling, Kitchen Platform | 10 | 8 | 1.25
9 | 8th | 621.74 | 621.74 | 26000 | 16165240 | 95% | 15356978 | 9 | 8th | 621.74 | 621.74 | Slab work, Blockwork, Plasterwork, Door & Windows Frames are completed, | Internal painting | 1.5 | 0 | 0.1875
10 | 9th | 620.81 | 620.81 | 26000 | 16141060 | 95% | 15334007 | 10 | 9th | 620.81 | 620.81 | Slab work, is completed, | External painting | 1.5 | 0 | 0.1875
11 | 10th | 634.58 | 634.58 | 26000 | 16499080 | 95% | 15674126 | 11 | 10th | 634.58 | 514.58 | Slab work, Blockwork, Door & Windows Frames are completed, | Electrification, plumbing & Sanitary installation | 5 | 2 | 0.625
12 | 11th | 634.62 | 634.62 | 26000 | 16500120 | 95% | 15675114 | 12 | 11th | 634.62 | 514.62 | Slab work is completed, | Lift Installation | 2 | 2 | 0.25
13 | 12th | 620.46 | 620.46 | 26000 | 16131960 | 95% | 15325362 | 13 | 12th | 620.46 | 500.46 | Slab work is completed | Passage, Staircase & Lobby development | 2 | 0 | 0.25
14 | 13th | 620.46 | 620.46 | 26000 | 16131960 | 95% | 15325362 | 14 | 13th | 620.46 | 500.46 | Slab work is completed, | External developments / Final finishing work | 2 | 0 | 0.25
15 | 14th | 620.46 | 620.46 | 26000 | 16131960 | 95% | 15325362 | 15 | 14th | 620.46 | 500.46 | Slab work is completed |  | 100 | 81.4375
16 | 15th | 508.9 | 508.9 | 26000 | 13231400 | 95% | 12569830 | 16 | 15th | 508.9 | 388.9 | Shuttering work is in progress
17 | Terrace | 132.41 | 132.41 | 26000 | 3442660 | 95% | 3270527 | 17 | Terrace | 132.41 | 82.41
| Total | 9937.92 | 9937.92 |  | 258385920 | 94.08% | 243079863 |  | Total | 9937.92 | 9167.92