## Final Summary
Project expenses | Estimated Cost as per Cost Vetting | Incurred Cost as per Bill till 31.03.2024 | Incurred Cost as per CA till 31.03.2024 | Incurred Cost as per Bill till 31.12.2023 | Incurred Cost as per CA till 31.12.2023 | Difference between the Bills & CA | Difference between both the Bills | Difference between both CA | Remark
Land Cost | 3.08 | 3.0809 | 3.08 | 3.0809 | 3.07 | 0.000898 | 0 | 0.01
Rent Cost | 0.27 | 0.39823 | 0.4 | 0.37062 | 0.37 | -0.0017724 | 0.02761 | 0.03
Construction Cost of Sale Building | 34.85 | 18.0784 | 19.23 | 16.1517 | 17.06 | -1.1516 | 1.9267 | 2.17
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty & TDR Cost | 14.94 | 8.3392 | 8.25 | 8.2623 | 8.18 | 0.089178 | 0.07689 | 0.07
Architect Cost, RCC & other Professional fees | 1.74 | 0.55519 | 0.64 | 0.45368 | 0.54 | -0.08481 | 0.10151 | 0.1
Administrative Expenses | 1.39 | 3.1825 | 4.95 | 2.8731 | 4.23 | 0.76817 | 0.30935 | 0.72
Marketing Expences | 3.16 | 2.5357 |  | 2.0275 |  |  | 0.50824
Interest Cost (Bank Loan) | 3.7 | 2.3167 | 2.32 | 1.8456 | 1.85 | -0.0032777 | 0.47116 | 0.47
Contingency Cost | 1.05 | 0 | 0.89 | 0 | 0 | -0.89 | 0 | 0.89 | DSRA amount is not considered in the lie
Total Cost | 64.18 | 38.4868 | 39.76 | 35.0653 | 35.3 | -1.2732 | 3.4214 | 4.46
|  | 25.6932 | -1.2732
Particulars | Revised Estimated Cost (in Cr.) | 31.03.2024 as per Bill Tally (inclusive of GST) | Cost incurred as %age total cost of that Component | Cost incurred as %age of cost incurred as on 31.03.2024
Land Cost | 3.08 | 3.0809 | 100% | 4.8%
Rent Cost | 0.27 | 0.39823 | 147.5% | 0.6205%
Construction Cost of Sale Building | 34.85 | 18.0784 | 51.87% | 28.17%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 14.94 | 8.3392 | 55.82% | 12.99%
Architect Cost, RCC & other Professional fees | 1.74 | 0.55519 | 31.91% | 0.8651%
Administrative Expenses | 1.39 | 3.1825 | 229% | 4.959%
Marketing Expences | 3.16 | 2.5357 | 80.24% | 3.951%
Interest Cost | 3.7 | 2.3167 | 62.61% | 3.61%
Contingency Cost | 1.05 | 0 | 0% | 0%
Total | 64.18 | 38.4868 | 59.97% | 59.97%
Pariculars | 31.03.2024 as per Bill Tally (inclusive of GST) | 31.12.2023 as per Bill Tally (inclusive of GST) | Difference b/w bills of 31.03.2024 & 31.12.2023 | Difference of Cost incurred as %age of cost incurred as on 31.03.2024 & 31.12.2023
Land Cost | 3.0809 | 3.0809 | 0 | 0%
Rent Cost | 0.39823 | 0.37062 | 0.03 | 0.07795%
Construction Cost of Sale Building | 18.0784 | 16.1517 | 1.93 | 5.015%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 8.3392 | 8.2623 | 0.08 | 0.2079%
Architect Cost, RCC & other Professional fees | 0.55519 | 0.45368 | 0.1 | 0.2598%
Administrative Expenses | 3.1825 | 2.8731 | 0.31 | 0.8055%
Marketing Expences | 2.5357 | 2.0275 | 0.51 | 1.325%
Interest Cost | 2.3167 | 1.8456 | 0.47 | 1.221%
Contingency Cost | 0 | 0 | 0 | 0%
Total | 38.4868 | 35.0653 | 3.42 | 8.886%

## Summary Sheet
Sr. No. | Particulars | Incurred Cost in ` till 31.03.2024 | Incurred Cost in ` Cr. Till 31.03.2024 | Incurred Cost in ` till 31.12.2023 | Incurred Cost in ` Cr. Till 31.12.2023 | Balance | Balance in Cr.
1 | Land Cost | 30808980 | 3.0809 | 30808980 | 3.0809 | 0 | 0
2 | Rent Cost | 3982276 | 0.39823 | 3706172 | 0.37062 | 276104 | 0.02761
3 | Construction Cost | 180783888.26 | 18.0784 | 161517161.31 | 16.1517 | 19266726.95 | 1.9267 | 127278700 | 15.1374
4 | Approval Cost & Stamp Duty | 83391779.56 | 8.3392 | 82622879.56 | 8.2623 | 768900 | 0.07689
5 | Professional Cost | 5551895 | 0.55519 | 4536795 | 0.45368 | 1015100 | 0.10151
6 | Admin Cost | 31824677.62 | 3.1825 | 28731210.95 | 2.8731 | 3093466.67 | 0.30935
7 | Marketing Cost | 25356973.52 | 2.5357 | 20274593.52 | 2.0275 | 5082380 | 0.50824
8 | Interest Cost | 23167223 | 2.3167 | 18455635 | 1.8456 | 4711588 | 0.47116
| Total | 384867692.96 | 38.4868 | 350653427.34 | 35.0653 | 34214265.62 | 3.4214
37000000
13832777

## Construction Area
Wing B Maternity Hospital | [13 empty] | Wing A Residential Building
Sr. No. | Floor | Built Up Area in Sq. M. | Staircase & Lobby Area in Sq. M. | Lift & Lobby Area in Sq. M. | Refuge Area in Sq. M. | Stlit Area in Sq. M. | Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | Percentage of work completed | Actual Expenditure till date in ` |  | Sr. No. | Floor | Built Up Area in Sq. M. | Staircase & Lobby Area in Sq. M. | Lift & Lobby Area in Sq. M. | Refuge Area in Sq. M. | Stlit Area in Sq. M. | Duct Area in Sq. M. | Society / Fitness Area in Sq. M. | Total Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | Percentage of work completed | Actual Expenditure till date in `
1 | Ground | 39.99 | 34.96 | 26.35 | 0 | 49.98 | 151.28 | 151.28 | 30000 | 4538400 | 100% | 4538400 |  | 1 | Ground | 94.56 | 19.85 | 26.09 | 0 | 163.18 | 0 | 16.54 | 320.22 | 320.22 | 30000 | 9606600 | 70% | 6724620
2 | 1st | 119.35 | 46.75 | 12.28 | 0 | 0 | 178.38 | 178.38 | 30000 | 5351400 | 100% | 5351400 |  | 2 | 1st | 219.11 | 19.81 | 27.55 | 0 | 25.2 | 5.29 | 100.25 | 397.21 | 397.21 | 30000 | 11916300 | 90% | 10724670
3 | 2nd | 119.35 | 46.75 | 12.28 | 0 | 0 | 178.38 | 178.38 | 30000 | 5351400 | 100% | 5351400 |  | 3 | 2nd | 333.49 | 19.81 | 27.55 | 0 | 25.2 | 5.29 | 0 | 411.34 | 411.34 | 30000 | 12340200 | 85% | 10489170
4 | 3rd | 119.35 | 46.75 | 12.28 | 0 | 0 | 178.38 | 178.38 | 30000 | 5351400 | 100% | 5351400 |  | 4 | 3rd | 333.49 | 19.81 | 27.55 | 0 | 25.2 | 5.29 | 0 | 411.34 | 411.34 | 30000 | 12340200 | 85% | 10489170
5 | 4th | 119.35 | 46.75 | 12.28 | 0 | 0 | 178.38 | 178.38 | 30000 | 5351400 | 100% | 5351400 |  | 5 | 4th | 333.49 | 19.81 | 27.55 | 0 | 25.2 | 5.29 | 0 | 411.34 | 411.34 | 30000 | 12340200 | 85% | 10489170
6 | 5th | 119.35 | 46.75 | 12.28 | 0 | 0 | 178.38 | 178.38 | 30000 | 5351400 | 100% | 5351400 |  | 6 | 5th | 333.49 | 19.81 | 27.55 | 0 | 25.2 | 5.29 | 0 | 411.34 | 411.34 | 30000 | 12340200 | 85% | 10489170
7 | 6th | 119.35 | 46.75 | 12.28 | 0 | 0 | 178.38 | 178.38 | 30000 | 5351400 | 100% | 5351400 |  | 7 | 6th | 333.49 | 19.81 | 27.55 | 0 | 25.2 | 5.29 | 0 | 411.34 | 411.34 | 30000 | 12340200 | 73% | 9008346
8 | 7th | 103.75 | 47.76 | 13.14 | 13.73 | 0 | 178.38 | 178.38 | 30000 | 5351400 | 100% | 5351400 |  | 8 | 7th | 333.49 | 19.81 | 27.55 | 0 | 25.2 | 5.29 | 0 | 411.34 | 411.34 | 30000 | 12340200 | 70% | 8638140
9 | 8th | 119.35 | 46.75 | 12.28 | 0 | 0 | 178.38 | 178.38 | 30000 | 5351400 | 100% | 5351400 |  | 9 | 8th | 233.24 | 19.81 | 27.55 | 105.89 | 25.2 | 5.29 | 0 | 416.98 | 416.98 | 30000 | 12509400 | 70% | 8756580
10 | 9th | 119.35 | 46.75 | 12.28 | 0 | 0 | 178.38 | 178.38 | 30000 | 5351400 | 100% | 5351400 |  | 10 | 9th | 333.49 | 19.81 | 27.55 | 0 | 25.2 | 5.29 | 0 | 411.34 | 411.34 | 30000 | 12340200 | 70% | 8638140
11 | Terrace | 0 | 46.75 | 12.28 | 0 | 0 | 59.03 | 59.03 | 30000 | 1770900 | 100% | 1770900 |  | 11 | 10th | 333.49 | 19.81 | 27.55 | 0 | 25.2 | 5.29 | 0 | 411.34 | 411.34 | 30000 | 12340200 | 70% | 8638140
TOTAL |  | 1098.54 | 503.47 | 150.01 | 13.73 | 49.98 | 1815.73 | 1815.73 |  | 54471900 | 100% | 54471900 | 19544.5177 | 12 | 11th | 333.49 | 19.81 | 27.55 | 0 | 25.2 | 5.29 | 0 | 411.34 | 411.34 | 30000 | 12340200 | 70% | 8638140
[7 empty] | 30000 | [6 empty] | 13 | 12th | 333.49 | 19.81 | 27.55 | 0 | 25.2 | 5.29 | 0 | 411.34 | 411.34 | 30000 | 12340200 | 50% | 6170100
[7 empty] | 54471900 | [6 empty] | 14 | 13th | 333.49 | 19.81 | 27.55 | 0 | 25.2 | 5.29 | 0 | 411.34 |  | 30000 | 12340200 |  | 0
[6 empty] | Excavation | [7 empty] | 15 | 14th | 333.49 | 19.81 | 27.55 | 0 | 25.2 | 5.29 | 0 | 411.34 |  | 30000 | 12340200 |  | 0
[7 empty] | 54471900 | [6 empty] | 16 | 15th | 250.67 | 19.81 | 27.55 | 70.5 | 25.2 | 5.29 | 13.92 | 412.94 |  | 30000 | 12388200 |  | 0
[14 empty] | 17 | 16th | 333.49 | 19.81 | 27.55 | 0 | 25.2 | 5.29 | 0 | 411.34 |  | 30000 | 12340200 |  | 0
[14 empty] | 18 | 17th | 333.49 | 19.81 | 27.55 | 0 | 25.2 | 5.29 | 0 | 411.34 |  | 30000 | 12340200 |  | 0
[14 empty] | 19 | 18th | 333.49 | 19.81 | 27.55 | 0 | 25.2 | 5.29 | 0 | 411.34 |  | 30000 | 12340200 |  | 0
[14 empty] | 20 | 19th | 333.49 | 19.81 | 27.55 | 0 | 25.2 | 5.29 | 0 | 411.34 |  | 30000 | 12340200 |  | 0
[14 empty] | 21 | Terrace | 0 | 19.81 | 27.55 | 0 | 25.2 | 0 | 0 | 72.56 |  | 30000 | 2176800 |  | 0
[14 empty] | TOTAL |  | 6133.42 | 416.05 | 577.09 | 176.39 | 667.18 | 100.51 | 130.71 | 8201.35 | 5247.81 |  | 246040500 | 47.92% | 117893556
[14 empty] | 22 | No. of Parking | [7 empty] | 96 |  | 500000 | 48000000 |  | 0
[14 empty] | TOTAL | [11 empty] | 294040500 | 40.09% | 117893556
[22 empty] | Excavation |  |  |  | 348512400 | 49.46% | 172365456
96

## Land
Land Cost Description
Sr. No. | Date | Description | Total Cost | Incurred Cost | Seller Name | Purchaser Name | Sr. No. | Tenant Name | Month | Amount
1 | 28.06.2013 | Deed of Surrender | 3000000 | 3000000 | Mrs. Asha Ramesh Tiwari + 2 Others | M/s. Amey Construction | 1 | Bhupendra Trivedi | April | 40000
2 | 28.06.2013 | Declaration Cum Indemnity | 200 | 200 | Mrs. Asha Ramesh Tiwari + 2 Others |  |  |  | May | 40000
3 | 28.06.2013 | Power of Attorney | 100 | 100 | Mrs. Asha Ramesh Tiwari + 2 Others |  |  |  | June | 40000
4 | 06.02.2014 | Deed of Surrender | 5000000 | 5000000 | Bheem Kamlashankar Tiwari |  |  |  | July | 40000
5 | 06.02.2014 | Power of Attorney | 1420 | 1420 | Bheem Kamlashankar Tiwari |  |  |  | August | 40000
6 | 06.02.2014 | Declaration Cum Indemnity | 100 | 100 | Bheem Kamlashankar Tiwari |  |  |  | September | 40000
7 | 17.01.2014 | Deed of Surrender | 7000000 | 7000000 | Lalji Chandrabali Tiwari and 1 other |  |  |  | October | 40000
8 | 17.01.2014 | Power of Attorney | 1020 | 1020 | Lalji Chandrabali Tiwari and 1 other |  |  |  | November | 40000
9 | 17.01.2014 | Declaration Cum Indemnity | 110 | 110 | Lalji Chandrabali Tiwari and 1 other |  |  |  | December | 40000
10 | 17.01.2014 | Deed of Surrender | 2500000 | 2500000 | Ashokkumar Mahabali Tiwari |  |  |  | January | 44000
11 | 17.01.2014 | Declaration Cum Indemnity | 720 | 720 | Ashokkumar Mahabali Tiwari |  |  |  | February | 44000
12 | 17.01.2014 | Power of Attorney | 510 | 510 | Ashokkumar Mahabali Tiwari |  |  |  | March | 44000
13 | 13.02.2006 | Deed of Surrender | 500000 | 500000 | M/s. Bagwe Housing Pvt.Ltd | Raamdular pandey |  |  | April | 44000
14 | 21.12.2006 | Conveyance Deed | 7200000 | 7200000 | Paamdular Pandey | M/s. Amey Construction | 2 | Vinod Shantilal Trivedi | April | 25000
15 |  | Stamp Duty | 462500 | 462500 |  |  |  |  | May | 25000
16 |  | Penalty Fees | 37000 | 37000 |  |  |  |  | June | 25000
17 |  | Reg. Fees | 31040 | 31040 |  |  |  |  | July | 25000
18 |  |  | 100 | 100 |  |  |  |  | August | 25000
19 | 15.01.2007 | Power of Attorney | 110 | 110 | Smt. Pushpavati Pandey |  |  |  | September | 25000
20 | 15.01.2007 | Power of Attorney | 110 | 110 | Shri Vijaykumar Pandey |  |  |  | October | 25000
21 | 15.01.2007 | Power of Attorney | 110 | 110 | Smt. Rajdulari Pandey |  |  |  | November | 25000
22 | 15.01.2007 | Power of Attorney | 110 | 110 | Shri Santoshkumar Pandey |  |  |  | December | 25000
23 | 15.01.2007 | Power of Attorney | 110 | 110 | Shri Laxminarayan Pandey |  |  |  | January | 27500
24 | 10.01.2007 | Reg. Fees | 310 | 310 |  |  |  |  | February | 27500
25 | 12.04.2019 | Alternate Accommodation Agreement | 800 | 800 | Vinod Trivedi |  |  |  | March | 27500
26 |  | Reg. Fees | 100 | 100 |  |  |  |  | April | 27500
27 |  | Stamp Duty | 500 | 500 |  |  | 3 | Deepchand Chandel | April | 16940
28 | 13.03.2018 | Alternate Accommodation Agreement | 0 | 0 | Deepchand Chandel |  |  |  | May | 16940
29 |  | Stamp Duty | 43000 | 43000 |  |  |  |  | June | 16940
30 |  | Reg. Fees | 8600 | 8600 |  |  |  |  | July | 16940
31 | 08.04.2019 | Alternate Accommodation Agreement | 800 | 800 | Bhupendra Trivedi |  |  |  | August | 16940
32 |  | Stamp Duty | 14000 | 14000 |  |  |  |  | September | 16940
33 |  | Reg. Fees | 2500 | 2500 |  |  |  |  | October | 16940
34 | 02.01.2021 | Deed of Surrender | 4500000 | 4500000 | Pankaj Pandey + 1 |  |  |  | November | 16940
35 | 14.02.2022 | Supplementary Agreement | 150000 | 150000 |  |  |  |  | December | 16940
36 |  | Stamp Duty | 32300 | 32300 |  |  |  |  | January | 16940
37 |  | Reg. Fees | 6500 | 6500 |  |  |  |  | February | 16940
38 |  |  | 1300 | 1300 |  |  |  |  | March | 16940
39 | 10.02.2022 | Supplementary Agreement | 250000 | 250000 |  |  |  |  | April | 18634
40 |  | Stamp Duty | 51300 | 51300 |  |  | 4 | Nirmala Chandel | April | 16940
41 |  | Reg. Fees | 10300 | 10300 |  |  |  |  | May | 16940
42 |  |  | 1300 | 1300 |  |  |  |  | June | 16940
Total |  |  | 30808980 | 30808980 |  |  |  |  | July | 16940
[9 empty] | August | 16940
[9 empty] | September | 16940
[9 empty] | October | 16940
[9 empty] | November | 16940
[9 empty] | December | 16940
[9 empty] | January | 16940
[9 empty] | February | 16940
[9 empty] | March | 16940
[9 empty] | April | 18634
[8 empty] | Rent |  | 1521200
[8 empty] | BHUPENDRA SHANTILAL TRIVEDI |  | 88000
[8 empty] | DEEP CHAND CHANDEL |  | 37268
[8 empty] | NIRMALA DIPCHAND CHANDEL |  | 37268
[8 empty] | VINOD SHANTILAL TRIVEDI |  | 55000
[8 empty] | BHUPENDRA SHANTILAL TRIVEDI |  | 132000
[8 empty] | DEEP CHAND CHANDEL |  | 55902
[8 empty] | NIRMALA DIPCHAND CHANDEL |  | 55902
[8 empty] | VINOD SHANTILAL TRIVEDI |  | 82500
[8 empty] | BHUPENDRA SHANTILAL TRIVEDI |  | 132000
[8 empty] | DEEP CHAND CHANDEL |  | 55902
[8 empty] | NIRMALA DIPCHAND CHANDEL |  | 55902
[8 empty] | VINOD SHANTILAL TRIVEDI |  | 82500
[8 empty] | BHUPENA SHANTILAL TRIVEDI |  | 101200
[8 empty] | DEEP CHAND CHANDEL |  | 55902
[8 empty] | NIRMALA DIPCHAND CHANDEL |  | 55902
[8 empty] | VINOD SHANTILAL TRIVEDI |  | 63100
[7 empty] | TOTAL |  |  | 3982276

## Purchase Register
AMEY REALTY & CONSTRUCTION LLP
G - B, SHIV CHHAYA CHS LTD.,
SIR.M.V.ROAD,
ANDHERI (EAST), MUMBAI
Purchase Register
1-Apr-19 to 31-Jan-23
Date | Particulars | Voucher Type | Voucher No. | Supplier Invoice No. | Supplier Invoice Date | Gross Total
2022-01-20 | DARSHAN ELECTRICAL INDUSTRIES | Purchase | 4 | DEI/21-22/607 | 2022-01-20 | 41048
2022-01-28 | MEHTA PLYWOOD | Purchase | 5 | 661-21-22 | 2022-01-28 | 4683
2022-01-31 | S H ENTERPRISES | Purchase | 6 | 169 | 2022-01-31 | 23776
2022-02-16 | ANUPAM ELECTRICALS | Purchase | 8 | GST/21-22/630 | 2022-02-16 | 5899
2022-03-06 | MEHTA PLYWOOD | Purchase | 10 | 776-21-22 | 2022-03-06 | 5729
2022-03-08 | SUNTREK CORPORATION | Purchase | 11 | SCMAR/2122/16 | 2022-03-08 | 43651
2022-03-10 | OM SWASTIK ENTERPRISES | Purchase | 13 | 164 | 2022-03-10 | 128625
2022-03-12 | KRISHNA TRADING CORPORATION | Purchase | 14 | 5815 | 2022-03-12 | 28839
2022-03-15 | ANUPAM ELECTRICALS | Purchase | 16 | GST/21-22/654 | 2022-03-15 | 754
2022-03-15 | ANUPAM ELECTRICALS | Purchase | 17 | GST/21-22/664 | 2022-03-15 | 21504
2022-03-15 | ANUPAM ELECTRICALS | Purchase | 18 | GST/21-22/693 | 2022-03-15 | 51336
2022-03-15 | SHARADA ENTERPRISES | Purchase | 15 | 182 | 2022-02-28 | 61320
2022-03-15 | SHARADA ENTERPRISES | Purchase | 19 | 190 | 2022-03-15 | 61320
2022-03-16 | PATEL BOREWELLS | Purchase | 20 | 083/21-22 | 2022-03-16 | 95037
2022-03-18 | SWASTIK SANITARY STORES | Purchase | 21 | 616/21-22 | 2022-03-18 | 6488
2022-03-21 | KRISHNA CERAMICS | Purchase | 23 | 627 | 2022-03-21 | 37500
2022-03-22 | PATEL BOREWELLS | Purchase | 24 | 087/21-22 | 2022-03-22 | 112395
2022-03-22 | SKY TELECOM | Purchase | 25 | ST/2021-22/478 | 2022-03-22 | 57466
2022-03-25 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 26 | SCSS/2720/21-22 | 2022-03-25 | 2705233
2022-03-26 | SUNTREK CORPORATION | Purchase | 27 | SC/MAR/2122/40 | 2022-03-26 | 36352
2022-03-27 | KRISHNA TRADING CORPORATION | Purchase | 28 | 5876 | 2022-03-27 | 20668
2022-03-28 | R.K.TRADING CO. | Purchase | 29 | 688 | 2022-03-28 | 13806
2022-03-29 | ANUPAM ELECTRICALS | Purchase | 30 | GST/21-22/717 | 2022-03-29 | 31841
2022-03-31 | ABHISHEK KISAN SHINDE | Purchase | 32 | 1819 | 2022-03-31 | 16800
2022-03-31 | OM SWASTIK ENTERPRISES | Purchase | 31 | 175 | 2022-03-31 | 61600
2022-03-31 | SHARADA ENTERPRISES | Purchase | 33 | 203 | 2022-03-31 | 78122
2022-04-01 | KRISHNA TRADING CORPORATION | Purchase | 35 | 5898 | 2022-04-01 | 16852
2022-04-05 | A TO Z MACHINERY | Purchase | 36 | 3553 | 2022-04-05 | 10920
2022-04-08 | OM SWASTIK ENTERPRISES | Purchase | 37 | 005 | 2022-04-08 | 629562
2022-04-11 | SWASTIK SANITARY STORES | Purchase | 38 | 033/22-23 | 2022-04-11 | 1009
2022-04-12 | KIRIT TRADING COMPANY | Purchase | 40 | 85-KTC/22-22 | 2022-04-12 | 88781
2022-04-15 | ABHISHEK KISAN SHINDE | Purchase | 42 | 1824 | 2022-04-15 | 16275
2022-04-15 | S H ENTERPRISES | Purchase | 43 | 6 | 2022-04-15 | 74551
2022-04-15 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 41 | SCSS/0128/21-22 | 2022-04-15 | 1501251
2022-04-16 | ABHISHEK KISAN SHINDE | Purchase | 44 | 1826 | 2022-04-16 | 21525
2022-04-18 | AMIN WATERPROFING COMPANY | Purchase | 47 | 2 | 2022-04-18 | 100000
2022-04-18 | GAURI TRANSPORT | Purchase | 45 | 37 | 2022-04-18 | 27671
2022-04-18 | OM SWASTIK ENTERPRISES | Purchase | 46 | 012 | 2022-04-18 | 417000
2022-04-20 | ASHISH INFRATECH SYSTEMS | Purchase | 48 | AIS/042/22-23 | 2022-04-20 | 7552
2022-04-25 | GOPI TRANSPORT | Purchase | 50 | 199 | 2022-04-25 | 300000
2022-04-25 | R.K.TRADING CO. | Purchase | 49 | RK/59 | 2022-04-25 | 10841
2022-04-30 | ANUPAM ELECTRICALS | Purchase | 54 | GST/22-23/85 | 2022-04-30 | 8974
2022-04-30 | OM SWASTIK ENTERPRISES | Purchase | 55 | 027 | 2022-04-30 | 29600
2022-05-01 | ABHISHEK KISAN SHINDE | Purchase | 58 | 1827 | 2022-05-01 | 15750
2022-05-01 | GAURI TRANSPORT | Purchase | 57 | 72 | 2022-05-01 | 19796
2022-05-07 | ABHISHEK KISAN SHINDE | Purchase | 59 | 1830 | 2022-05-07 | 17850
2022-05-11 | ABHISHEK KISAN SHINDE | Purchase | 60 | 1832 | 2022-05-11 | 10500
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 61 | 1000NAI12044203 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 62 | 1000NAI12044204 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 63 | 1000NAI12044205 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 64 | 1000NAI12044206 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 65 | 1000NAI12044207 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 66 | 1000NAI12044208 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 67 | 1000NAI12044209 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 68 | 1000NAI12044211 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 69 | 1000NAI12044212 | 2022-05-12 | 53917.49
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 70 | 1000NAI12044213 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 71 | 1000NAI12044214 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 72 | 1000NAI12044215 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 73 | 1000NAI12044216 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 74 | 1000NAI12044217 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 75 | 1000NAI12044218 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 76 | 1000NAI12044219 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 77 | 1000NAI12044220 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 78 | 1000NAI12044221 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 79 | 1000NAI12044222 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 80 | 1000NAI12044223 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 81 | 1000NAI12044224 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 82 | 1000NAI12044225 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 83 | 1000NAI12044226 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 84 | 1000NAI12044227 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 85 | 1000NAI12044228 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 86 | 1000NAI12044229 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 87 | 1000NAI12044230 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 88 | 1000NAI12044231 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 89 | 1000NAI12044232 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 90 | 1000NAI12044233 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 91 | 1000NAI12044234 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 92 | 1000NAI12044235 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 93 | 1000NAI12044236 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 94 | 1000NAI12044237 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 95 | 1000NAI12044238 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 96 | 1000NAI12044241 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 97 | 1000NAI12044247 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 98 | 1000NAI11050909 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 99 | 1000NAI11050910 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 100 | 1000NAI11050911 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 101 | 1000NAI11050912 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 102 | 1000NAI11050913 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 103 | 1000NAI11050914 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 104 | 1000NAI11050915 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 105 | 1000NAI11050916 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 106 | 1000NAI11050917 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 107 | 1000NAI11050918 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 108 | 1000NAI11050919 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 109 | 1000NAI11050920 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 110 | 1000NAI11050921 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 111 | 1000NAI11050922 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 112 | 1000NAI11050923 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 113 | 1000NAI11050924 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 114 | 1000NAI11050925 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 115 | 1000NAI11050926 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 116 | 1000NAI11050927 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 117 | 1000NAI11050928 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 118 | 1000NAI11050929 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 119 | 1000NAI11050930 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 120 | 1000NAI11050931 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 121 | 1000NAI11050932 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 122 | 1000NAI11050933 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 123 | 1000NAI11050934 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 124 | 1000NAI11050935 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 125 | 1000NAI11050936 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 126 | 1000NAI11050937 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 127 | 1000NAI11050938 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 128 | 1000NAI11050939 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 129 | 1000NAI11050940 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 130 | 1000NAI11050941 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 131 | 1000NAI11050942 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 132 | 1000NAI11050943 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 133 | 1000NAI11050944 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 134 | 1000NAI11050945 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 135 | 1000NAI11050946 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 136 | 1000NAI11050947 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 137 | 1000NAI11050948 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 138 | 1000NAI11050949 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 139 | 1000NAI11050950 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 140 | 1000NAI11050951 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 141 | 1000NAI11050952 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 142 | 1000NAI11050953 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 143 | 1000NAI11050954 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 144 | 1000NAI11050955 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 145 | 1000NAI11050956 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 146 | 1000NAI11050957 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 147 | 1000NAI11050958 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 148 | 1000NAI11050959 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 149 | 1000NAI11050960 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 150 | 1000NAI11050961 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 151 | 1000NAI11050962 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 152 | 1000NAI11050963 | 2022-05-12 | 49770
2022-05-12 | GODREJ & BOYCE MFC CO.LTD | Purchase | 153 | 1000NAI11050964 | 2022-05-12 | 49770
2022-05-14 | GAURI TRANSPORT | Purchase | 155 | 90 | 2022-05-14 | 13400
2022-05-14 | VEDANT MARKETING | Purchase | 154 | 419/22-23 | 2022-05-14 | 5664
2022-05-17 | GOPI TRANSPORT | Purchase | 156 | 329 | 2022-05-17 | 250000
2022-05-26 | MAHIMA ENTERPRISES | Purchase | 158 | 013 | 2022-05-26 | 271575
2022-05-31 | MAHIMA ENTERPRISES | Purchase | 161 | 014 | 2022-05-31 | 59000
2022-05-31 | S H ENTERPRISES | Purchase | 160 | 36 | 2022-05-31 | 23209
2022-05-31 | SWASTIK SANITARY STORES | Purchase | 159 | 199/22-23 | 2022-05-31 | 385
2022-06-01 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 163 | SCSS/0108/22-23 | 2022-06-01 | 2246399
2022-06-01 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 164 | SCSS/0135/22-23 | 2022-06-01 | 1575161
2022-06-01 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 165 | SCSS/027/22-23 | 2022-06-01 | 2227077
2022-06-01 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 166 | SCSS/0333/22-23 | 2022-06-01 | 2592248
2022-06-01 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 167 | SCSS/0374/22-23 | 2022-06-01 | 1482022
2022-06-06 | GKP CONTRUCTION & INFRASTRUCTURES | Purchase | 170 |  |  | 2950000
2022-06-08 | SKYWAY RMC PLANTS PVT LTD | Purchase | 171 | 20/22-23/06/0040 | 2022-06-08 | 322223
2022-06-17 | YM LANDMARK PVT LTD | Purchase | 175 | JW/22-23/000320 | 2022-06-17 | 48650
2022-07-21 | BUCON READY MIX LLP | Purchase | 181 | BRL/0277/22-23 | 2022-07-21 | 837166
2022-07-21 | BUCON READY MIX LLP | Purchase | 182 | BRL/0276/22-23 | 2022-07-21 | 135710
2022-07-21 | MAHIMA ENTERPRISES | Purchase | 183 | 034 | 2022-07-21 | 191750
2022-07-21 | MAHIMA ENTERPRISES | Purchase | 184 | 037 | 2022-07-21 | 130050
2022-07-21 | MAHIMA ENTERPRISES | Purchase | 185 | 038 | 2022-07-21 | 582725
2022-07-29 | ANUPAM ELECTRICALS | Purchase | 186 | GST/22-23/289 | 2022-07-29 | 739
2022-07-30 | JK LAKSHMI CEMENT LTD | Purchase | 187 | 7360073311 | 2022-07-30 | 34560
2022-07-31 | S H ENTERPRISES | Purchase | 188 | 85 | 2022-07-31 | 8467
2022-08-01 | RAMASHREY PRAJAPATI | Purchase | 189 | 489 | 2022-08-01 | 4386
2022-08-01 | RAMASHREY PRAJAPATI | Purchase | 190 | 010 | 2022-08-01 | 12718
2022-08-01 | RAMASHREY PRAJAPATI | Purchase | 191 | 011 | 2022-08-01 | 6494
2022-08-09 | BUCON READY MIX LLP | Purchase | 193 | BRL-0420/22-23 | 2022-08-09 | 68250
2022-08-10 | MAHIMA ENTERPRISES | Purchase | 194 | 83 | 2022-08-10 | 87000
2022-08-15 | SHARADA ENTERPRISES | Purchase | 195 | 112 | 2022-08-15 | 17105
2022-08-21 | BUCON READY MIX LLP | Purchase | 196 | BRL/0444/22-23 | 2022-08-21 | 176500
2022-08-22 | MAHIMA ENTERPRISES | Purchase | 197 | 70 | 2022-08-22 | 90400
2022-08-22 | MAHIMA ENTERPRISES | Purchase | 198 | 71 | 2022-08-22 | 447900
2022-08-31 | SHARADA ENTERPRISES | Purchase | 200 | 113 | 2022-08-31 | 33623
2022-09-01 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 202 | SCSS/1521/22-23 | 2022-09-01 | 787882
2022-09-02 | ABHISHEK KISAN SHINDE | Purchase | 204 | 1850 | 2022-09-02 | 6300
2022-09-02 | GAURAV K PAUL | Purchase | 203 | 001 | 2022-09-02 | 1000000
2022-09-16 | PATEL BOREWELLS | Purchase | 207 | 038/22-23 | 2022-09-16 | 17700
2022-09-26 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 208 | SCSS/1770/22-23 | 2022-09-26 | 1907086
2022-09-27 | ABHISHEK KISAN SHINDE | Purchase | 210 | 1856 | 2022-09-27 | 15750
2022-09-27 | ANUPAM ELECTRICALS | Purchase | 209 | GST/22-23/453 | 2022-09-27 | 561
2022-10-01 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 212 | SCSS/1827/22-23 | 2022-10-01 | 1269390
2022-10-02 | ABHISHEK KISAN SHINDE | Purchase | 213 | 1858 | 2022-10-02 | 11025
2022-10-03 | DINESH S.MISHRA HUF | Purchase | 214 | 216 | 2022-09-30 | 12718
2022-10-03 | PUJARI TRANSPORT | Purchase | 215 | 357 | 2022-09-27 | 18334
2022-10-10 | MAHIMA ENTERPRISES | Purchase | 216 | 92 | 2022-10-10 | 61050
2022-10-12 | AMIN WATERPROFING COMPANY | Purchase | 217 | 2 | 2022-10-12 | 50000
2022-10-15 | SHARADA ENTERPRISES | Purchase | 218 | 172 | 2022-10-15 | 23877
2022-10-16 | SNEH ENTERPRISE | Purchase | 219 | G/30/22-23 | 2022-10-16 | 37760
2022-10-17 | S.S.ENTERPRISES | Purchase | 220 | 147/22-23 | 2022-10-17 | 11025
2022-10-18 | MAHIMA ENTERPRISES | Purchase | 221 | 097 | 2022-10-18 | 138000
2022-11-05 | BUCON READY MIX LLP | Purchase | 226 | BRL/0580/22-23 | 2022-11-05 | 297660
2022-11-08 | ASHISH INFRATECH SYSTEMS | Purchase | 227 | AIS/529/22-23 | 2022-11-08 | 29087
2022-11-09 | RAJLAXMI CORPORATION | Purchase | 229 | 118 | 2022-11-09 | 85631
2022-11-09 | THE INDIA CEMENTS LIMITED | Purchase | 228 | 198/200662 | 2022-11-09 | 78080
2022-11-11 | R.K.TRADING CO. | Purchase | 232 | RK/626 | 2022-11-11 | 7245
2022-11-11 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 230 | SCSS2202/22-23 | 2022-11-11 | 77103
2022-11-11 | THE INDIA CEMENTS LIMITED | Purchase | 231 | 198/200759 | 2022-11-11 | 78080
2022-11-13 | RAJLAXMI CORPORATION | Purchase | 233 | 119 | 2022-11-13 | 78067
2022-11-14 | DINESH S.MISHRA HUF | Purchase | 234 | 274 | 2022-11-14 | 900
2022-11-15 | HARIOM CARRIERS | Purchase | 237 | 423/2022-23 | 2022-11-15 | 24556
2022-11-15 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 235 | SCSS/2241/22-23 | 2022-11-15 | 1801367
2022-11-16 | ABHISHEK KISAN SHINDE | Purchase | 238 | 1876 | 2022-11-16 | 15750
2022-11-19 | R.K.TRADING CO. | Purchase | 239 | RK/648 | 2022-11-19 | 4425
2022-11-30 | SHARADA ENTERPRISES | Purchase | 240 | 217 | 2022-11-30 | 21373
2022-12-01 | SANGAM ENTERPRISES | Purchase | 1 |  | 2022-12-01 | 183012
2022-12-01 | THE INDIA CEMENTS LIMITED | Purchase | 3 | 814/200350 | 2022-12-01 | 238080
2022-12-01 | VELAVA TRANSPORT | Purchase | 4 | 057 | 2022-12-01 | 9000
2022-12-03 | GAURAV K PAUL | Purchase | 5 | 002 | 2022-12-03 | 1078409
2022-12-04 | AMIT CORPORATION | Purchase | 7 | ACO/22-23/144 | 2022-12-04 | 96875
2022-12-04 | AMIT CORPORATION | Purchase | 8 | ACO/22-23/145 | 2022-12-04 | 91550
2022-12-04 | AMIT CORPORATION | Purchase | 9 | ACO/22-23 | 2022-12-04 | 73293
2022-12-05 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 10 | SCSS/2476/22-23 | 2022-12-05 | 1905652
2022-12-05 | THE INDIA CEMENTS LIMITED | Purchase | 11 | 814/200365 | 2022-12-05 | 268800
2022-12-06 | ABHISHEK KISAN SHINDE | Purchase | 13 | 1882 | 2022-12-06 | 16275
2022-12-06 | ASHISH INFRATECH SYSTEMS | Purchase | 12 | AIS/602/22-23 | 2022-12-06 | 25311
2022-12-08 | R.K.TRADING CO. | Purchase | 14 | RK/684 | 2022-12-08 | 3374
2022-12-09 | THE INDIA CEMENTS LIMITED | Purchase | 15 | 198/202300 | 2022-12-09 | 115200
2022-12-12 | AMIT CORPORATION | Purchase | 16 | ACO/22-23/158 | 2022-12-12 | 40513
2022-12-13 | ABHISHEK KISAN SHINDE | Purchase | 17 | 1887 | 2022-12-13 | 16275
2022-12-13 | ABHISHEK KISAN SHINDE | Purchase | 18 | 1888 | 2022-12-13 | 5400
2022-12-14 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 19 | SCSS/2598/22-23 | 2022-12-14 | 1849288
2022-12-14 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 20 | SCSS/2599/22-23 | 2022-12-14 | 74091
2022-12-16 | PUJARI TRANSPORT | Purchase | 21 | 546 | 2022-12-16 | 18920
2022-12-17 | KIRIT TRADING COMPANY | Purchase | 22 | 1545-KTC/22-23 | 2022-12-17 | 157344
2022-12-17 | KIRIT TRADING COMPANY | Purchase | 23 | 1546-KTC/22-23 | 2022-12-17 | 157344
2022-12-17 | KIRIT TRADING COMPANY | Purchase | 24 | 1547-KTC/22-23 | 2022-12-17 | 157344
2022-12-21 | RAMASHREY PRAJAPATI | Purchase | 25 | 185 | 2022-12-21 | 9792
2022-12-24 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 26 | SCSS/2717/22-23 | 2022-12-24 | 923539
2022-12-24 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 27 | SCSS/2718/22-23 | 2022-12-24 | 946481
2022-12-25 | AMIT CORPORATION | Purchase | 28 | ACO/22-23/174 | 2022-12-25 | 91423
2022-12-27 | ANUPAM ELECTRICALS | Purchase | 29 | GST/22-23/677 | 2022-12-27 | 18432
2022-12-28 | AMIT CORPORATION | Purchase | 32 | ACO/22-23/179 | 2022-12-28 | 93980
2022-12-29 | AMIT CORPORATION | Purchase | 33 | ACO22-23/181 | 2022-12-29 | 80976
2022-12-31 | JK LAKSHMI CEMENT LTD | Purchase | 34 | 7360085143 | 2022-12-31 | 156160
2022-12-31 | MAHIMA ENTERPRISES | Purchase | 35 | 109 | 2022-12-31 | 312120
2023-01-01 | ABHISHEK KISAN SHINDE | Purchase | 37 | 1893 | 2023-01-01 | 15750
2023-01-01 | GAURI TRANSPORT | Purchase | 38 | 542 | 2022-12-24 | 19878
2023-01-02 | GAURAV K PAUL | Purchase | 40 | 003 | 2023-01-02 | 1660049
2023-01-05 | RAMASHREY PRAJAPATI | Purchase | 41 | 190 | 2023-01-05 | 9792
2023-01-08 | ABHISHEK KISAN SHINDE | Purchase | 44 | 003 | 2023-01-08 | 7968
2023-01-08 | WALJI PUNJA & CO. | Purchase | 43 | 650 | 2023-01-08 | 166700
2023-01-12 | JK LAKSHMI CEMENT LTD | Purchase | 45 | 7360086280 | 2023-01-12 | 197120
2023-01-13 | JK LAKSHMI CEMENT LTD | Purchase | 46 | 7360086365 | 2023-01-13 | 197120
2023-01-14 | AMIT CORPORATION | Purchase | 47 | ACO/22-23/200 | 2023-01-14 | 88069
2023-01-14 | AMIT CORPORATION | Purchase | 48 | ACO/22-23/201 | 2023-01-14 | 62603
2023-01-15 | RAJLAXMI CORPORATION | Purchase | 49 | 198 | 2023-01-15 | 37333
2023-01-16 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 50 | SCSS/2990 | 2023-01-16 | 1366587
2023-01-17 | GAURI TRANSPORT | Purchase | 52 | 589 | 2023-01-17 | 12554
2023-01-17 | GAUTAM K PAUL | Purchase | 51 | 1 | 2023-01-17 | 1359265
2023-01-17 | THE INDIA CEMENTS LIMITED | Purchase | 53 | 198/204888 | 2023-01-17 | 96000
2023-01-18 | THE INDIA CEMENTS LIMITED | Purchase | 54 | 198/204889 | 2023-01-18 | 19200
2023-01-18 | THE INDIA CEMENTS LIMITED | Purchase | 55 | 198/204890 | 2023-01-18 | 69120
2023-01-21 | D.R LINKS | Purchase | 56 | 583/22-23 | 2023-01-21 | 8938
2023-01-22 | RAJLAXMI CORPORATION | Purchase | 57 | 202 | 2023-01-22 | 72182
2023-01-25 | ASHISH INFRATECH SYSTEMS | Purchase | 59 | AIS/782/22-23 | 2023-01-25 | 25311
2023-01-25 | JK LAKSHMI CEMENT LTD | Purchase | 58 | 7360087660 | 2023-01-25 | 81920
2023-01-25 | RAJLAXMI CORPORATION | Purchase | 60 | 203 | 2023-01-25 | 68770
2023-01-27 | ANUPAM ELECTRICALS | Purchase | 63 | GST/22-23/725 | 2023-01-27 | 4973
2023-01-27 | GLOBAL GYPSUM PVT LTD | Purchase | 62 | 595 | 2023-01-27 | 157080
2023-01-27 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 61 | SCSS/3113/22-23 | 2023-01-27 | 2104468
2023-01-28 | JSW CEMENT LIMITED | Purchase | 64 | MH2203127316 | 2023-01-28 | 116625
2023-01-28 | KIRIT TRADING COMPANY | Purchase | 65 | 1834-KTC/22-23 | 2023-01-28 | 117120
2023-01-30 | AMIT CORPORATION | Purchase | 66 | ACO/22-23/217 | 2023-01-30 | 79324
2023-01-31 | KARAN ENTERPRISES | Purchase | 67 | 715-KE/22-23 | 2023-01-31 | 195200
2023-02-01 | AMIN WATERPROFING COMPANY | Purchase | 68 | 3 | 2023-02-01 | 51000
2023-02-01 | RAMASHREY PRAJAPATI | Purchase | 72 | 245 | 2023-02-01 | 13100
2023-02-01 | RAMASHREY PRAJAPATI | Purchase | 73 | 030 | 2023-02-01 | 5052
2023-02-01 | SHREEJI WATER PUMPS & BOREWELL | Purchase | 70 | 140/2022-23 | 2023-02-01 | 20933
2023-02-02 | KARAN ENTERPRISES | Purchase | 74 | 726-KE/22-23 | 2023-02-02 | 195200
2023-02-03 | ABHISHEK KISAN SHINDE | Purchase | 75 | 007 | 2023-02-03 | 10500
2023-02-06 | ABHISHEK KISAN SHINDE | Purchase | 76 | 015 | 2023-02-06 | 16275
2023-02-06 | ABHISHEK KISAN SHINDE | Purchase | 77 | 019 | 2023-02-06 | 8540
2023-02-06 | AMIT CORPORATION | Purchase | 78 | ACO/22-23/226 | 2023-02-06 | 91325
2023-02-06 | AMIT CORPORATION | Purchase | 79 | ACO/22-23/227 | 2023-02-06 | 93380
2023-02-07 | R.K.TRADING CO. | Purchase | 81 | RK/872 | 2023-02-07 | 1416
2023-02-07 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 80 | SCSS/3275/22-23 | 2023-02-07 | 2032863
2023-02-08 | ABHISHEK KISAN SHINDE | Purchase | 84 | 026 | 2023-02-08 | 15750
2023-02-08 | KIRIT TRADING COMPANY | Purchase | 83 | 1927-KTC/22-23 | 2023-02-08 | 117120
2023-02-10 | ABHISHEK KISAN SHINDE | Purchase | 85 | 029 | 2023-02-10 | 10200
2023-02-10 | AMIT CORPORATION | Purchase | 86 | ACO/22-23/235 | 2023-02-10 | 96116
2023-02-12 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 87 | SCSS/3342/22-23 | 2023-02-12 | 1934000
2023-02-13 | ABHISHEK KISAN SHINDE | Purchase | 89 | 014 | 2023-02-13 | 5100
2023-02-13 | ABHISHEK KISAN SHINDE | Purchase | 90 | 034 | 2023-02-13 | 15225
2023-02-13 | WE ARE ONE ENTERPRISES PVT LTD | Purchase | 88 | E/1266/22-23 | 2023-02-13 | 167457
2023-02-14 | JK LAKSHMI CEMENT LTD | Purchase | 91 | 7360089689 | 2023-02-14 | 157696
2023-02-14 | JK LAKSHMI CEMENT LTD | Purchase | 92 | 7360089690 | 2023-02-14 | 157696
2023-02-14 | JK LAKSHMI CEMENT LTD | Purchase | 93 | 7360089722 | 2023-02-14 | 78848
2023-02-16 | MAHIMA ENTERPRISES | Purchase | 94 | 121 | 2023-02-16 | 289240
2023-02-18 | AMIT CORPORATION | Purchase | 98 | ACO/22-23/245 | 2023-02-18 | 96377
2023-02-18 | MAHIMA ENTERPRISES | Purchase | 97 | 122 | 2023-02-18 | 338350
2023-02-18 | R.K.TRADING CO. | Purchase | 96 | RK/902 | 2023-02-18 | 14514
2023-02-20 | AMIT CORPORATION | Purchase | 100 | ACO/22-23/246 | 2023-02-20 | 96063
2023-02-20 | KIRIT TRADING COMPANY | Purchase | 99 | 1991-KTC/22-23 | 2023-02-20 | 195200
2023-02-24 | AMIT CORPORATION | Purchase | 101 | ACO/22-23/252 | 2023-02-24 | 64254
2023-02-25 | ASHISH INFRATECH SYSTEMS | Purchase | 102 | AIS/905/22-23 | 2023-02-25 | 55460
2023-02-25 | WE ARE ONE ENTERPRISES PVT LTD | Purchase | 103 | E/1655/22-23 | 2023-02-25 | 158407
2023-02-27 | GAUTAM K PAUL | Purchase | 104 | 001 | 2023-02-27 | 2499025
2023-02-27 | KHETHAVATH PADMA | Purchase | 105 | 001 | 2023-02-27 | 1011200
2023-02-28 | KIRIT TRADING COMPANY | Purchase | 106 | 2055-KTC/22-23 | 2023-02-28 | 195200
2023-02-28 | OM SWASTIK ENTERPRISES | Purchase | 107 | 164 | 2023-02-28 | 45900
2023-03-01 | ABHISHEK KISAN SHINDE | Purchase | 112 | 049 | 2023-03-01 | 7940
2023-03-01 | CHAMUNDA ENTERPRISE | Purchase | 121 | 281 | 2023-03-01 | 53808
2023-03-01 | HIRAL SHROFF | Purchase | 120 |  |  | 75000
2023-03-01 | KIRIT TRADING COMPANY | Purchase | 113 | 2073-KTC/22-23 | 2023-03-01 | 120960
2023-03-01 | R.K.TRADING CO. | Purchase | 115 | RK/943 | 2023-03-01 | 60457
2023-03-01 | RAMASHREY PRAJAPATI | Purchase | 116 | 105 | 2023-03-01 | 14028
2023-03-01 | SHREE KRISHNA TRANSPORT | Purchase | 110 | 187 | 2023-03-01 | 592212
2023-03-01 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 111 | SCSS/3571/22-23 | 2023-03-01 | 2081720
2023-03-02 | ABHISHEK KISAN SHINDE | Purchase | 122 | 054 | 2023-03-02 | 16275
2023-03-02 | PATEL BOREWELLS | Purchase | 123 | 087/22-23 | 2023-03-02 | 10030
2023-03-04 | THAKKAR ELECTRICAL WORKS | Purchase | 124 | 85 | 2023-03-04 | 10000
2023-03-05 | RAJLAXMI CORPORATION | Purchase | 125 | 238 | 2023-03-05 | 65298
2023-03-06 | ANUPAM ELECTRICALS | Purchase | 128 | GST/22-23/836 | 2023-03-06 | 5469
2023-03-06 | D.R LINKS | Purchase | 130 | 733/22-23 | 2023-03-06 | 6393
2023-03-06 | KARAN ENTERPRISES | Purchase | 126 | 843-KE/22-23 | 2023-03-06 | 97600
2023-03-06 | KARAN ENTERPRISES | Purchase | 127 | 844-KE/22-23 | 2023-03-06 | 97600
2023-03-06 | SKY TELECOM | Purchase | 129 | ST/2022-23/414 | 2023-03-06 | 29205
2023-03-07 | KARAN ENTERPRISES | Purchase | 131 | 845-KE/22-23 | 2023-03-07 | 78080
2023-03-07 | KARAN ENTERPRISES | Purchase | 132 | 846-KE/22-23 | 2023-03-07 | 78080
2023-03-07 | KARAN ENTERPRISES | Purchase | 133 | 850-KE/22-23 | 2023-03-07 | 39040
2023-03-09 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 134 | SCSS/3653/22-23 | 2023-03-09 | 1726039
2023-03-10 | ABHISHEK KISAN SHINDE | Purchase | 135 | 059 | 2023-03-10 | 13650
2023-03-11 | AMIT CORPORATION | Purchase | 136 | ACO/22-23/265 | 2023-03-11 | 85842
2023-03-11 | RAJLAXMI CORPORATION | Purchase | 137 | 239 | 2023-03-11 | 87093
2023-03-12 | RAJLAXMI CORPORATION | Purchase | 138 | 240 | 2023-03-12 | 73975
2023-03-13 | PUJARI TRANSPORT | Purchase | 140 | 708 | 2023-03-13 | 17224
2023-03-13 | RAJLAXMI CORPORATION | Purchase | 139 | 229 | 2023-03-13 | 60310
2023-03-14 | R.K.TRADERS | Purchase | 141 | RKT/660/22-23 | 2023-03-14 | 10030
2023-03-15 | MEHTA PLYWOOD | Purchase | 142 | 9200/22-23 | 2023-03-15 | 24923
2023-03-16 | R.R.ENTERPRISES | Purchase | 143 | 22 | 2023-03-16 | 9322
2023-03-17 | ABHISHEK KISAN SHINDE | Purchase | 144 | 065 | 2023-03-17 | 6984
2023-03-18 | JK LAKSHMI CEMENT LTD | Purchase | 145 | 7360093134 | 2023-03-18 | 67840
2023-03-19 | JK LAKSHMI CEMENT LTD | Purchase | 146 | 7360093233 | 2023-03-19 | 77312
2023-03-19 | JK LAKSHMI CEMENT LTD | Purchase | 147 | 7360093240 | 2023-03-19 | 77312
2023-03-19 | JK LAKSHMI CEMENT LTD | Purchase | 148 | 7360093241 | 2023-03-19 | 38656
2023-03-19 | THE INDIA CEMENTS LIMITED | Purchase | 149 | 198/209346 | 2023-03-19 | 75520
2023-03-21 | ANUPAM ELECTRICALS | Purchase | 151 | GST/22-23/865 | 2023-03-21 | 1770
2023-03-21 | KRISHNA TRADING CORPORATION | Purchase | 150 | 7208 | 2023-03-21 | 26810
2023-03-23 | AMIT CORPORATION | Purchase | 153 | ACO/22-23/271 | 2023-03-23 | 80649
2023-03-23 | JSW CEMENT LIMITED | Purchase | 152 | MH2203152588 | 2023-03-22 | 58313
2023-03-25 | ABHISHEK KISAN SHINDE | Purchase | 154 | 074 | 2023-03-25 | 9600
2023-03-26 | ABHISHEK KISAN SHINDE | Purchase | 155 | 077 | 2023-03-26 | 11624
2023-03-27 | R.K.TRADING CO. | Purchase | 157 | RK/1011 | 2023-03-27 | 2832
2023-03-27 | S.S.ENTERPRISES | Purchase | 158 | 527/22-23 | 2023-03-27 | 74567
2023-03-27 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 156 | SCSS/3903/22-23 | 2023-03-27 | 2062308
2023-03-28 | ABHISHEK KISAN SHINDE | Purchase | 159 | 08 | 2023-03-28 | 16275
2023-03-29 | SUNTREK CORPORATION | Purchase | 160 | SC/MAR/2223/64 | 2023-03-29 | 37760
2023-03-31 | ABHISHEK KISAN SHINDE | Purchase | 161 | 088 | 2023-03-31 | 6696
2023-03-31 | GODREJ & BOYCE MFC CO.LTD | Purchase | 165 | 1000NAI57001370 | 2023-03-31 | 115739.36
2023-03-31 | GODREJ & BOYCE MFC CO.LTD | Purchase | 166 | 1000NAI33008791 | 2023-03-31 | 12599.92
2023-03-31 | RISHABH ENTERPRISE | Purchase | 163 | 729 | 2023-03-31 | 44770
2023-03-31 | RISHABH ENTERPRISE | Purchase | 164 | 727 | 2023-03-31 | 852424
2023-04-01 | K.R. ENTERPRISES | Purchase | 167 | 564 | 2023-04-01 | 21500
2023-04-03 | JK LAKSHMI CEMENT LTD | Purchase | 168 | 7360095007 | 2023-04-03 | 188800
2023-04-04 | D.R LINKS | Purchase | 169 | 0023/23-24 | 2023-04-04 | 7476
2023-04-05 | GAURAV K PAUL | Purchase | 170 | 002 | 2022-12-03 | 1925225
2023-04-05 | GAUTAM K PAUL | Purchase | 171 |  | 2023-02-27 | 1975265
2023-04-05 | R C ENGINEERING WORKS | Purchase | 172 | 200 | 2023-04-05 | 32496
2023-04-09 | ABHISHEK KISAN SHINDE | Purchase | 175 | 099 | 2023-04-09 | 6344
2023-04-09 | JK LAKSHMI CEMENT LTD | Purchase | 173 | 7360095789 | 2023-04-09 | 190080
2023-04-09 | JK LAKSHMI CEMENT LTD | Purchase | 174 | 7360095803 | 2023-04-09 | 76032
2023-04-11 | GKP CONTRUCTION & INFRASTRUCTURES | Purchase | 176 | GKPCIN002 | 2023-04-11 | 3212319
2023-04-11 | KRISHNA TRADING CORPORATION | Purchase | 177 | 7290 | 2023-04-11 | 11474
2023-04-12 | KRISHNA CERAMICS | Purchase | 178 | 752 | 2023-04-12 | 36108
2023-04-14 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 179 | SCSS/0203/23-24 | 2023-04-14 | 2014239
2023-04-17 | WEATHER COOL SERVICE | Purchase | 180 | 73 | 2023-04-17 | 10578.7
2023-04-19 | ABHISHEK KISAN SHINDE | Purchase | 182 | 105/106/107 | 2023-04-19 | 38382
2023-04-19 | RAMASHREY PRAJAPATI | Purchase | 183 | 171 | 2023-04-19 | 12606
2023-04-19 | RAMASHREY PRAJAPATI | Purchase | 184 | 172 | 2023-04-19 | 10488
2023-04-19 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 181 | SCSS/0257/23-24 | 2023-04-19 | 2022819
2023-04-20 | S.S.ENTERPRISES | Purchase | 185 | 39/23-24 | 2023-04-20 | 33075
2023-04-24 | ANUPAM ELECTRICALS | Purchase | 188 | GST/23-24/58 | 2023-04-24 | 6278
2023-04-24 | GKP CONTRUCTION & INFRASTRUCTURES | Purchase | 186 | GKPCIN003 | 2023-04-24 | 1879391
2023-04-24 | JANATA SAND SUPPLYING CO. | Purchase | 187 | 0954 | 2023-04-24 | 1181
2023-04-26 | MAHIMA ENTERPRISES | Purchase | 190 | 00001 | 2023-04-26 | 1270999
2023-04-26 | OM SWASTIK ENTERPRISES | Purchase | 189 | 00001 | 2023-04-26 | 93725
2023-02-27 | GAUTAM K PAUL | Journal | 61 |  |  | 24990
2023-05-02 | SHREEJI WOODCRAFT PVT.LTD. | Purchase | 207 | 26AALCS3011M1Z9 |  | 69478
2023-05-02 | SHREEJI WOODCRAFT PVT.LTD. | Purchase | 208 | 26AALCS3011M1Z9 |  | 139464
2023-05-03 | OTIS ELEVATOR COMPANY (I) LTD | Purchase | 209 | 27AAACO0481E1ZR |  | 171100
2023-05-03 | OTIS ELEVATOR COMPANY (I) LTD | Purchase | 210 | 27AAACO0481E1ZR |  | 153400
2023-05-03 | JK LAKSHMI CEMENT LTD | Purchase | 211 | 27AAACJ6715G1ZN |  | 190080
2023-05-05 | S.S.ENTERPRISES | Purchase | 212 | 27ADXFS3023P1Z9 |  | 33075
2023-05-06 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 213 | 27ADBFS3046G1Z7 |  | 1826062
2023-05-08 | S.S.ENTERPRISES | Purchase | 218 | 27ADXFS3023P1Z9 |  | 11918
2023-05-08 | GODREJ & BOYCE MFC CO.LTD | Purchase | 219 | 27AAACG1395D1ZU |  | 121830.9
2023-05-09 | OTIS ELEVATOR COMPANY (I) LTD | Purchase | 220 | 27AAACO0481E1ZR |  | 684400
2023-05-09 | OTIS ELEVATOR COMPANY (I) LTD | Purchase | 221 | 27AAACO0481E1ZR |  | 613600
2023-05-10 | JK LAKSHMI CEMENT LTD | Purchase | 222 | 27AAACJ6715G1ZN |  | 81408
2023-05-11 | GLOBAL GYPSUM PVT LTD | Purchase | 223 | 27AAGCG9765K1ZV |  | 92400
2023-05-12 | JK LAKSHMI CEMENT LTD | Purchase | 224 | 27AAACJ6715G1ZN |  | 94400
2023-05-12 | D.R LINKS | Purchase | 226 | 27AVQPS7709F1ZY |  | 6331
2023-05-12 | D.R LINKS | Purchase | 227 | 27AVQPS7709F1ZY |  | 2336
2023-05-13 | JANATA SAND SUPPLYING CO. | Purchase | 228 | 27AAAFJ4746Q1ZT |  | 1181
2023-05-13 | JK LAKSHMI CEMENT LTD | Purchase | 229 | 27AAACJ6715G1ZN |  | 94400
2023-05-15 | MEHTA PLYWOOD | Purchase | 232 | 27ABZPJ2820R1ZS |  | 3540
2023-05-15 | SHARADA ENTERPRISES | Purchase | 234 | 27AIEPD3168L1Z5 |  | 96873
2023-05-15 | SHARADA ENTERPRISES | Purchase | 235 | 27AIEPD3168L1Z5 |  | 100813
2023-05-16 | CHETAN ELECTRICALS & HARDWARE | Purchase | 237 | 27ABYPM9092M1ZE |  | 54166
2023-05-16 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 238 | 27ADBFS3046G1Z7 |  | 1840763
2023-05-18 | GODREJ & BOYCE MFC CO.LTD | Purchase | 241 | 27AAACG1395D1ZU |  | 12599.92
2023-05-19 | CHETAN ELECTRICALS & HARDWARE | Purchase | 242 | 27ABYPM9092M1ZE |  | 1416
2023-05-19 | ANUPAM ELECTRICALS | Purchase | 243 | 27ADUPG3954C1ZE |  | 2168
2023-05-20 | ASHISH INFRATECH SYSTEMS | Purchase | 244 | 27AEBPT7394B1ZA |  | 55460
2023-05-21 | JK LAKSHMI CEMENT LTD | Purchase | 245 | 27AAACJ6715G1ZN |  | 148480
2023-05-21 | JK LAKSHMI CEMENT LTD | Purchase | 246 | 27AAACJ6715G1ZN |  | 185600
2023-05-22 | JK LAKSHMI CEMENT LTD | Purchase | 248 | 27AAACJ6715G1ZN |  | 67840
2023-05-22 | JK LAKSHMI CEMENT LTD | Purchase | 249 | 27AAACJ6715G1ZN |  | 148480
2023-05-22 | D.R LINKS | Purchase | 250 | 27AVQPS7709F1ZY |  | 3764
2023-05-22 | ANUPAM ELECTRICALS | Purchase | 251 | 27ADUPG3954C1ZE |  | 9228
2023-05-25 | KIAAN ENTERPRISE | Purchase | 252 | 27AOLPB6420N1ZR |  | 157977
2023-05-27 | D.R LINKS | Purchase | 253 | 27AVQPS7709F1ZY |  | 36817
2023-05-27 | SUPREME GYPSUM PVT LTD | Purchase | 254 | 27AAACA4000D1ZK |  | 38350
2023-05-28 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 255 | 27ADBFS3046G1Z7 |  | 688524
2023-05-28 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 256 | 27ADBFS3046G1Z7 |  | 1098270
2023-05-28 | RAJLAXMI CORPORATION | Purchase | 257 | 27AGMPK6447P1ZJ |  | 111735
2023-05-29 | S.S.ENTERPRISES | Purchase | 259 | 27ADXFS3023P1Z9 |  | 33075
2023-05-31 | JK LAKSHMI CEMENT LTD | Purchase | 260 | 27AAACJ6715G1ZN |  | 92800
2023-05-31 | JK LAKSHMI CEMENT LTD | Purchase | 261 | 27AAACJ6715G1ZN |  | 92800
2023-05-31 | RAJLAXMI CORPORATION | Purchase | 262 | 27AGMPK6447P1ZJ |  | 121356
2023-05-31 | SHARADA ENTERPRISES | Purchase | 263 | 27AIEPD3168L1Z5 |  | 92103
2023-05-31 | SHARADA ENTERPRISES | Purchase | 264 | 27AIEPD3168L1Z5 |  | 59733
2023-06-01 | D.R LINKS | Purchase | 266 | 27AVQPS7709F1ZY |  | 8707
2023-06-01 | SHARADA ENTERPRISES | Purchase | 269 | 27AIEPD3168L1Z5 |  | 96873
2023-06-02 | KARAN ENTERPRISES | Purchase | 270 | 27AAJFK0527B1ZR |  | 33920
2023-06-02 | KIAAN ENTERPRISE | Purchase | 272 | 27AOLPB6420N1ZR |  | 70013
2023-06-03 | S.S.ENTERPRISES | Purchase | 273 | 27ADXFS3023P1Z9 |  | 33075
2023-06-05 | PADMAVATI DECOR | Purchase | 277 | 27AFSPK8649C1ZY |  | 5198
2023-06-07 | KIAAN ENTERPRISE | Purchase | 282 | 27AOLPB6420N1ZR |  | 80078
2023-06-08 | KARAN ENTERPRISES | Purchase | 284 | 27AAJFK0527B1ZR |  | 155161.6
2023-06-10 | PADMAVATI DECOR | Purchase | 288 | 27AFSPK8649C1ZY |  | 97750
2023-06-10 | R.K.TRADING CO. | Purchase | 295 | 27AGAPG1412C1ZB |  | 35265
2023-06-12 | VEDANT MARKETING | Purchase | 301 | 27AANFV8458J1Z9 |  | 4798
2023-06-13 | JANATA SAND SUPPLYING CO. | Purchase | 308 | 27AAAFJ4746Q1ZT |  | 1418
2023-06-13 | KIAAN ENTERPRISE | Purchase | 309 | 27AOLPB6420N1ZR |  | 10475
2023-06-13 | S.S.ENTERPRISES | Purchase | 310 | 27ADXFS3023P1Z9 |  | 33075
2023-06-14 | KIAAN ENTERPRISE | Purchase | 311 | 27AOLPB6420N1ZR |  | 142179
2023-06-14 | SUSHMA CONSTRUCTION STEEL LLP | Purchase | 313 | 27ADBFS3046G1Z7 |  | 1697427
2023-06-14 | KRISHNA TRADING CORPORATION | Purchase | 314 | 27AFRPB4005J1ZJ |  | 18113
2023-06-16 | ANUPAM ELECTRICALS | Purchase | 321 | 27ADUPG3954C1ZE |  | 27848
2023-06-16 | JK LAKSHMI CEMENT LTD | Purchase | 322 | 27AAACJ6715G1ZN |  | 186880
2023-06-19 | D.R LINKS | Purchase | 325 | 27AVQPS7709F1ZY |  | 12463
2023-06-19 | JANATA SAND SUPPLYING CO. | Purchase | 326 | 27AAAFJ4746Q1ZT |  | 2363
2023-06-20 | GLOBAL GYPSUM PVT LTD | Purchase | 327 | 27AAGCG9765K1ZV |  | 231000
2023-06-20 | JK LAKSHMI CEMENT LTD | Purchase | 328 | 27AAACJ6715G1ZN |  | 74752
2023-05-08 | SUSHMA ENTERPRISES | LABOUR CHARGES | 214 |  |  | 198004
2023-05-13 | RAMASHREY PRAJAPATI | LABOUR CHARGES | 230 |  |  | 6450
2023-05-15 | THAKKAR ELECTRICAL WORKS | LABOUR CHARGES | 231 |  |  | 5000
2023-05-15 | SHREEJI WATER PUMPS & BOREWELL | LABOUR CHARGES | 233 |  |  | 49560
2023-05-17 | BHIMRAI NARSAPPA POOJARY | LABOUR CHARGES | 239 |  |  | 50220
2023-05-22 | GKP CONTRUCTION & INFRASTRUCTURES | LABOUR CHARGES | 247 |  |  | 1528223
2023-05-31 | R.R.ENTERPRISES | LABOUR CHARGES | 265 |  |  | 18681
2023-06-01 | MUSTAK ALAM | LABOUR CHARGES | 267 |  |  | 307500
2023-06-02 | MOHAMMAD JAVEED | LABOUR CHARGES | 271 |  |  | 307000
03-Jun-23 | SUDIP BISWAS | LABOUR CHARGES | 274 |  |  | 351300
05-Jun-23 | GKP CONTRUCTION & INFRASTRUCTURES | LABOUR CHARGES | 275 |  |  | 3459382
05-Jun-23 | UNITED ONE CONSTRUCTION | LABOUR CHARGES | 276 |  |  | 2549219
05-Jun-23 | INDUDEVI RAMAVATAR PRASAD | LABOUR CHARGES | 278 |  |  | 503000
05-Jun-23 | ANAND DEVENDRA TIWARI | LABOUR CHARGES | 279 |  |  | 314600
07-Jun-23 | BHIMJI DEVJI PATEL HUF | LABOUR CHARGES | 283 |  |  | 350400
08-Jun-23 | DAYALAL K PATEL HUF | LABOUR CHARGES | 285 |  |  | 260000
08-Jun-23 | NUREJA KHATUN NAYYAR ALAM | LABOUR CHARGES | 286 |  |  | 203200
08-Jun-23 | KANTABEN DAYALAL PATEL | LABOUR CHARGES | 287 |  |  | 310500
10-Jun-23 | DIPEN P RAMJIYANI | LABOUR CHARGES | 289 |  |  | 825000
10-Jun-23 | TARULATA BHARAT PATEL | LABOUR CHARGES | 290 |  |  | 1175000
10-Jun-23 | SUSHIL VINOD VELANI HUF | LABOUR CHARGES | 291 |  |  | 305000
10-Jun-23 | RAKESH BHIMJI CHAUHAN HUF | LABOUR CHARGES | 292 |  |  | 300000
10-Jun-23 | DEV JAYESH CHAUHAN | LABOUR CHARGES | 293 |  |  | 320000
10-Jun-23 | MOHAN SUDHIR YADAV | LABOUR CHARGES | 294 |  |  | 303100
10-Jun-23 | SUSHIL V VELANI | LABOUR CHARGES | 296 |  |  | 310500
10-Jun-23 | KABITA HALDER | LABOUR CHARGES | 297 |  |  | 351500
11-Jun-23 | SHAMIM KHALIL ALAM | LABOUR CHARGES | 298 |  |  | 312800
11-Jun-23 | ROHIT P RAMJIYANI | LABOUR CHARGES | 299 |  |  | 1050000
11-Jun-23 | MOHD SHAKIL ABDUL MATIN | LABOUR CHARGES | 300 |  |  | 302900
12-Jun-23 | VINOD D VELANI HUF | LABOUR CHARGES | 302 |  |  | 307000
12-Jun-23 | VINOD DHANJI VELANI | LABOUR CHARGES | 303 |  |  | 305000
13-Jun-23 | SNEHAL ANAND TIWARI | LABOUR CHARGES | 305 |  |  | 310000
13-Jun-23 | PRAVIN DAYALAL PATEL HUF | LABOUR CHARGES | 306 |  |  | 312000
14-Jun-23 | DEEPTI JAYESH CHAUHAN | LABOUR CHARGES | 312 |  |  | 310000
14-Jun-23 | RAJUKUMAR SUKHDEV DAS | LABOUR CHARGES | 315 |  |  | 311000
15-Jun-23 | JAYESH BHIMJI PATEL HUF | LABOUR CHARGES | 316 |  |  | 340700
15-Jun-23 | SATENDER KUMAR B SINGH HUF | LABOUR CHARGES | 317 |  |  | 436500
16-Jun-23 | ANJAMMA BHIMREDDY PUJARI | LABOUR CHARGES | 320 |  |  | 200000
17-Jun-23 | R.R.ENTERPRISES | LABOUR CHARGES | 323 |  |  | 2237.28
19-Jun-23 | SHAH INTERIOR | LABOUR CHARGES | 324 |  |  | 200000
20-Jun-23 | SUMIT VINOD VELANI | LABOUR CHARGES | 333 |  |  | 315000
20-Jun-23 | HARENDRA PRASAD KOYARI | LABOUR CHARGES | 334 |  |  | 505000
21-Jun-23 | SADAF HUSSAIN AZIZ MULLA | LABOUR CHARGES | 336 |  |  | 215000
23-Jun-23 | SHUBHAM YADAV | LABOUR CHARGES | 337 |  |  | 35000
2023-07-06 | REHAN ENTERPRISES | LABOUR CHARGES |  |  |  | 132000
2023-07-06 | RAMASHREY PRAJAPATI | LABOUR CHARGES |  |  |  | 11640
2023-07-18 | MANGESH AMGOTHU | LABOUR CHARGES |  |  |  | 500600
2023-07-18 | GKP CONTRUCTION & INFRASTRUCTURES | LABOUR CHARGES |  |  |  | 1873088
2023-08-01 | GKP CONTRUCTION & INFRASTRUCTURES | LABOUR CHARGES | GKPCN007 |  |  | 3365934
2023-08-17 | SHUBHAM YADAV | LABOUR CHARGES |  |  |  | 50000
2023-09-08 | WATER PUMP HIRE SERVICE | LABOUR CHARGES | 611 |  |  | 8000
2023-06-16 | GODREJ & BOYCE MFC CO.LTD | 108777.6 | 6526.66 | 6526.66 |  | 121830.92
2023-06-16 | GODREJ & BOYCE MFC CO.LTD | 21755.52 | 1305.33 | 1305.33 |  | 24366.18
2023-06-26 | GODREJ & BOYCE MFC CO.LTD | 119655.36 | 7179.32 | 7179.32 |  | 134014
2023-06-29 | GODREJ & BOYCE MFC CO.LTD | 130533.12 | 7831.99 | 7831.99 |  | 146197.1
2023-06-15 | SHARADA ENTERPRISES | 86072 | 2151.8 | 2151.8 |  | 90375.6
2023-06-15 | SHARADA ENTERPRISES | 75273 | 1881.83 | 1881.83 |  | 79036.66
2023-06-23 | S.S.ENTERPRISES | 73656 | 1841.4 | 1841.4 |  | 77338.8
2023-06-26 | S.S.ENTERPRISES | 31500 | 787.5 | 787.5 |  | 33075
2023-06-27 | RAJLAXMI CORPORATION | 93632 | 2340.8 | 2340.8 |  | 98313.6
2023-06-28 | RAJLAXMI CORPORATION | 118569.5 | 2964.24 | 2964.24 |  | 124497.98
2023-06-30 | SHARADA ENTERPRISES | 87958.5 | 2198.96 | 2198.96 |  | 92356.42
2023-06-30 | SHARADA ENTERPRISES | 89806.5 | 2245.16 | 2245.16 |  | 94296.82
2023-06-23 | JK LAKSHMI CEMENT LTD | 147500 | 20650 | 20650 |  | 188800
2023-06-23 | JK LAKSHMI CEMENT LTD | 147500 | 20650 | 20650 |  | 188800
2023-06-23 | JK LAKSHMI CEMENT LTD | 59000 | 8260 | 8260 |  | 75520
2023-06-03 | R.K.TRADERS | 2600 | 234 | 234 |  | 3068
2023-06-07 | MEHTA PLYWOOD | 1680 | 151.2 | 151.2 |  | 1982.4
2023-06-09 | KRISHNA TRADING CORPORATION | 14297.49 | 1286.77 | 1286.77 |  | 16871.03
2023-06-14 | KRISHNA TRADING CORPORATION | 26982 | 2428.38 | 2428.38 |  | 31838.76
2023-06-14 | R.K.TRADERS | 8613 | 775.17 | 775.17 |  | 10163.34
2023-06-23 | KIAAN ENTERPRISE | 13836.34 | 1245.27 | 1245.27 |  | 16326.88
2023-06-24 | KIAAN ENTERPRISE | 59333.31 | 5340 | 5340 |  | 70013.31
2023-06-26 | SUSHMA CONSTRUCTION STEEL LLP | 1513390 | 136205.1 | 136205.1 |  | 1787586
2023-06-26 | SUSHMA CONSTRUCTION STEEL LLP | 60728 | 5465.52 | 5465.52 |  | 71731
2023-06-26 | GODREJ & BOYCE MFC CO.LTD | 10677.9 | 961.01 | 961.01 |  | 12599.92
2023-06-26 | GODREJ & BOYCE MFC CO.LTD | 10677.9 | 961.01 | 961.01 |  | 12599.92
2023-06-28 | D.R LINKS | 1650 | 148.5 | 148.5 |  | 1947
2023-06-30 | GODREJ & BOYCE MFC CO.LTD | 17796.5 | 1601.69 | 1601.69 |  | 20999.88
2023-07-11 | GODREJ & BOYCE MFC CO.LTD | 119655.36 | 7179.32 | 7179.32 |  | 134014
2023-07-11 | GODREJ & BOYCE MFC CO.LTD | 135972 | 8158.32 | 8158.32 |  | 152288.64
2023-07-22 | GODREJ & BOYCE MFC CO.LTD | 108777.6 | 6526.66 | 6526.66 |  | 121830.92
2023-08-08 | GODREJ & BOYCE MFC CO.LTD | 122428.08 | 7345.68 | 7345.68 |  | 137119.44
2023-08-15 | SHARADA ENTERPRISES | 56000 | 3360 | 3360 |  | 62720
2023-08-31 | SHARADA ENTERPRISES | 53732 | 3223.92 | 3223.92 |  | 60179.84
2023-07-04 | S.S.ENTERPRISES | 5600 | 504 | 504 |  | 6608
2023-07-05 | D.R LINKS | 2392 | 215.28 | 215.28 |  | 2822.56
2023-07-11 | R.K.TRADERS | 2240 | 201.6 | 201.6 |  | 2643.2
2023-07-12 | H P CORPORATION | 126750 | 11407.5 | 11407.5 |  | 149565
2023-07-12 | KRISHNA TRADING CORPORATION | 5155.95 | 464.04 | 464.04 |  | 6084.03
2023-07-13 | ANUPAM ELECTRICALS | 1475 | 132.75 | 132.75 |  | 1740.5
2023-07-13 | GODREJ & BOYCE MFC CO.LTD | 10677.9 | 961.01 | 961.01 |  | 12599.92
2023-07-18 | VEDANT MARKETING | 7455 | 670.95 | 670.95 |  | 8796.9
2023-07-20 | KRISHNA CERAMICS | 30600 | 2754 | 2754 |  | 36108
2023-07-22 | R.K.TRADING CO. | 2400 | 216 | 216 |  | 2832
2023-07-24 | S.S.ENTERPRISES | 10100 | 909 | 909 |  | 11918
2023-07-25 | KRISHNA TRADING CORPORATION | 2840.68 | 255.66 | 255.66 |  | 3352
2023-07-26 | R.K.TRADERS | 3087 | 277.83 | 277.83 |  | 3642.66
2023-07-27 | KRISHNA TRADING CORPORATION | 1281.36 | 115.32 | 115.32 |  | 1512
2023-07-29 | SUSHMA CONSTRUCTION STEEL LLP | 1550764 | 139568.76 | 139568.76 |  | 1831731.52
2023-07-29 | SUSHMA CONSTRUCTION STEEL LLP | 1550764 | 139568.76 | 139568.76 |  | 1831731.52
2023-08-05 | SUSHMA CONSTRUCTION STEEL LLP | 59100 | 5319 | 5319 |  | 69808
2023-08-05 | KIAAN ENTERPRISE | 195580.17 | 17602.22 | 17602.22 |  | 230784.61
2023-08-06 | SUSHMA CONSTRUCTION STEEL LLP | 1288225 | 115940.25 | 115940.25 |  | 1521625.5
2023-08-06 | SUSHMA CONSTRUCTION STEEL LLP | 300705 | 27063.45 | 27063.45 |  | 355186.9
2023-08-09 | R.K.TRADERS | 3340 | 300.6 | 300.6 |  | 3941.2
2023-08-09 | S.S.ENTERPRISES | 12350 | 1111.5 | 1111.5 |  | 14573
2023-08-11 | PADMAVATI DECOR | 397197.21 | 35747.75 | 35747.75 |  | 468692.71
2023-08-19 | CHAMUNDA ENTERPRISE | 22200 | 1998 | 1998 |  | 26196
2023-08-26 | R.K.TRADING CO. | 1300 | 117 | 117 |  | 1534
2023-09-01 | SHREE GANESHA TRADING | 200000 | 18000 | 18000 |  | 236000
2023-09-07 | JYOTI KITCHEN INDUSTRIES PVT.LTD. | 33037.29 | 2973.36 | 2973.36 |  | 38984.01
2023-09-07 | JYOTI KITCHEN INDUSTRIES PVT.LTD. | 27444.08 | 2469.97 | 2469.97 |  | 32384.02
2023-09-08 | S.S.ENTERPRISES | 12350 | 1111.5 | 1111.5 |  | 14573
2023-09-15 | D.R LINKS | 12415 | 1117.35 | 1117.35 |  | 14649.7
2023-07-01 | JANATA SAND SUPPLYING CO. | 683.5 | 95.75 | 95.75 |  | 875
2023-07-05 | JK LAKSHMI CEMENT LTD | 66250 | 9275 | 9275 |  | 84800
2023-07-11 | JK LAKSHMI CEMENT LTD | 72500 | 10150 | 10150 |  | 92800
2023-07-11 | JK LAKSHMI CEMENT LTD | 72500 | 10150 | 10150 |  | 92800
2023-07-17 | JK LAKSHMI CEMENT LTD | 143500 | 20090 | 20090 |  | 183680
2023-07-31 | JANATA SAND SUPPLYING CO. | 781.2 | 109.4 | 109.4 |  | 1000
2023-08-04 | JK LAKSHMI CEMENT LTD | 65750 | 9205 | 9205 |  | 84160
2023-08-05 | JK LAKSHMI CEMENT LTD | 143500 | 20090 | 20090 |  | 183680
2023-08-05 | JK LAKSHMI CEMENT LTD | 143500 | 20090 | 20090 |  | 183680
2023-08-07 | SNEH ENTERPRISE | 61000 | 8540 | 8540 |  | 78080
2023-08-09 | KARAN ENTERPRISES | 146000 | 20440 | 20440 |  | 186880
2023-08-19 | KARAN ENTERPRISES | 58400 | 8176 | 8176 |  | 74752
2023-08-19 | KARAN ENTERPRISES | 87600 | 12264 | 12264 |  | 112128
2023-08-24 | KARAN ENTERPRISES | 175200 | 24528 | 24528 |  | 224256
2023-09-12 | JK LAKSHMI CEMENT LTD | 145000 | 20300 | 20300 |  | 185600
2023-09-12 | JK LAKSHMI CEMENT LTD | 66250 | 9275 | 9275 |  | 84800
2023-07-01 | JANATA SAND SUPPLYING CO. | 2250 | 56.5 | 56.5 |  | 2363
2023-07-08 | S.S.ENTERPRISES | 31500 | 787.5 | 787.5 |  | 33075
2023-07-11 | S.S.ENTERPRISES | 72123 | 1803.08 | 1803.08 |  | 75729.16
2023-07-11 | R.K.TRADERS | 3900 | 97.5 | 97.5 |  | 4095
2023-07-13 | AMIT CORPORATION | 75979 | 1899.48 | 1899.48 |  | 79777.96
2023-07-19 | AMIT CORPORATION | 81160.5 | 2029.01 | 2029.01 |  | 85218.52
2023-07-21 | AMIT CORPORATION | 90652.5 | 2266.31 | 2266.31 |  | 95185.12
2023-07-22 | RAJLAXMI CORPORATION | 79909 | 1997.73 | 1997.73 |  | 83904.46
2023-07-26 | R.K.TRADERS | 2600 | 65 | 65 |  | 2730
2023-07-28 | AMIT CORPORATION | 85228.5 | 2130.71 | 2130.71 |  | 89489.92
2023-07-31 | JANATA SAND SUPPLYING CO. | 1125 | 28 | 28 |  | 1181
2023-07-31 | OM ENTERPRISES | 25740 | 643.5 | 643.5 |  | 27027
2023-08-08 | S.S.ENTERPRISES | 65286 | 1632.15 | 1632.15 |  | 68550.3
2023-08-08 | AMIT CORPORATION | 84336 | 2108.4 | 2108.4 |  | 88552.8
2023-08-09 | JANATA SAND SUPPLYING CO. | 1350 | 33.75 | 33.75 |  | 1417.5
2023-08-09 | AMIT CORPORATION | 79650.5 | 1991.26 | 1991.26 |  | 83633.02
2023-08-10 | AMIT CORPORATION | 72572.5 | 1814.31 | 1814.31 |  | 76201.12
2023-08-10 | AMIT CORPORATION | 92427 | 2310.68 | 2310.68 |  | 97048.36
2023-08-19 | AMIT CORPORATION | 90863.5 | 2271.59 | 2271.59 |  | 95406.68
2023-08-21 | AMIT CORPORATION | 93851 | 2346.28 | 2346.28 |  | 98543.56
2023-08-29 | AMIT CORPORATION | 64699 | 1617.48 | 1617.48 |  | 67933.96
2023-08-30 | AMIT CORPORATION | 42955 | 1073.88 | 1073.88 |  | 45102.76
2023-08-30 | AMIT CORPORATION | 62110 | 1552.75 | 1552.75 |  | 65215.5
2023-08-31 | RAJLAXMI CORPORATION | 43218 | 1080.45 | 1080.45 |  | 45378.9
2023-08-31 | S.S.ENTERPRISES | 32100 | 802.5 | 802.5 |  | 33705
2023-09-08 | S.S.ENTERPRISES | 32100 | 802.5 | 802.5 |  | 33705
2023-09-09 | GLOBAL GYPSUM PVT LTD | 220000 | 5500 | 5500 |  | 231000
2023-09-09 | S.S.ENTERPRISES | 84909 | 2122.73 | 2122.73 |  | 89154.46
2023-09-10 | JANATA SAND SUPPLYING CO. | 2250 | 56.25 | 56.25 |  | 2362.5
2023-09-07 | SHREEJI WOODCRAFT PVT.LTD. | 3740 |  |  | 673.2 | 4413.2
2023-08-05 | MAHAVIR MINERALS | 110000 |  |  | 5500 | 115500
2023-07-20 | R.R.ENTERPRISES | Purchase | 41 | 27ABEFR4889H1ZM | 22302 | 22302
2023-08-02 | OTIS ELEVATOR COMPANY (I) LTD | Purchase | MH/NE/23002793 | 27AAACO0481E1ZR | 684400 | 684400
2023-08-26 | OTIS ELEVATOR COMPANY (I) LTD | Purchase | MH/NE/23002622 | 27AAACO0481E1ZR | 613600 | 613600
2023-09-13 | R.R.ENTERPRISES | Purchase | 61 | 27ABEFR4889H1ZM | 22302 | 22302
2023-10-14 | SULEKHABIBI BISWAS |  |  |  |  | 13328
2023-10-26 | RAJENDRA K.CHAVDA |  |  |  |  | 450000
2023-10-26 | JAYESH MAHESH BHAI PARMAR |  |  |  |  | 250000
2023-11-20 | MANGESH AMGOTHU |  |  |  |  | 504200
2023-12-05 | AKSHAY RAJENDRA POL |  |  |  |  | 500000
2023-12-12 | DEVENDRA YADAV |  |  |  |  | 200000
2023-12-19 | KRISHNA R.CHAVDA |  |  |  |  | 300000
2023-10-06 | R.R.ENTERPRISES |  |  |  |  | 7080
2023-10-06 | R.R.ENTERPRISES |  |  |  |  | 12744
2023-10-13 | R.R.ENTERPRISES |  |  |  |  | 5630.96
2023-10-21 | R.R.ENTERPRISES |  |  |  |  | 4063.92
2023-10-26 | GKP CONTRUCTION & INFRASTRUCTURES |  |  |  |  | 945171
2023-11-20 | GKP CONTRUCTION & INFRASTRUCTURES |  |  |  |  | 1629863
2023-10-06 | R.K.TRADING CO. |  |  |  |  | 3683.68
2023-10-15 | SHARADA ENTERPRISES |  |  |  |  | 62720
2023-10-23 | GODREJ & BOYCE MFC CO.LTD |  |  |  |  | 125196.02
2023-10-23 | GODREJ & BOYCE MFC CO.LTD |  |  |  |  | 143083.58
2023-10-23 | GODREJ & BOYCE MFC CO.LTD |  |  |  |  | 119234.3
2023-11-08 | GODREJ & BOYCE MFC CO.LTD |  |  |  |  | 143083.58
2023-11-09 | GODREJ & BOYCE MFC CO.LTD |  |  |  |  | 143083.58
2023-11-09 | GODREJ & BOYCE MFC CO.LTD |  |  |  |  | 143083.58
2023-10-06 | R.K.TRADERS |  |  |  |  | 6088.8
2023-10-06 | KRISHNA TRADING CORPORATION |  |  |  |  | 1552
2023-10-17 | PADMAVATI DECOR |  |  |  |  | 66779.98
2023-10-17 | PADMAVATI DECOR |  |  |  |  | 85249.39
2023-10-23 | GODREJ & BOYCE MFC CO.LTD |  |  |  |  | 12599.92
2023-10-23 | GODREJ & BOYCE MFC CO.LTD |  |  |  |  | 12599.92
2023-10-25 | MEHTA PLYWOOD |  |  |  |  | 4130
2023-10-26 | R.K.TRADERS |  |  |  |  | 13797.74
2023-11-07 | VEDANT MARKETING |  |  |  |  | 3168.3
2023-11-08 | GODREJ & BOYCE MFC CO.LTD |  |  |  |  | 12599.92
2023-11-08 | GODREJ & BOYCE MFC CO.LTD |  |  |  |  | 12599.92
2023-11-08 | GODREJ & BOYCE MFC CO.LTD |  |  |  |  | 12599.92
2023-11-08 | GODREJ & BOYCE MFC CO.LTD |  |  |  |  | 12599.92
2023-11-14 | KRISHNA TRADING CORPORATION |  |  |  |  | 13893.08
2023-11-21 | KRISHNA TRADING CORPORATION |  |  |  |  | 1062
2023-12-02 | S.S.ENTERPRISES |  |  |  |  | 14573
2023-12-02 | MEHTA PLYWOOD |  |  |  |  | 4908.8
2023-12-02 | PADMAVATI DECOR |  |  |  |  | 23913.18
2023-12-07 | SUSHMA CONSTRUCTION STEEL LLP |  |  |  |  | 1498619.82
2023-12-13 | SAPNA CERAMICS |  |  |  |  | 97740.58
2023-12-18 | KIAAN ENTERPRISE |  |  |  |  | 2562.71
2023-12-18 | R.K.TRADERS |  |  |  |  | 4413.2
2023-12-18 | TEJAS CERAMICS |  |  |  |  | 53999.92
2023-12-19 | ASHA METAL AND HARDWARE |  |  |  |  | 586381.88
2023-10-02 | KIRIT TRADING COMPANY |  |  |  |  | 218880
2023-10-14 | KIRIT TRADING COMPANY |  |  |  |  | 74240
2023-10-20 | JK LAKSHMI CEMENT LTD |  |  |  |  | 84800
2023-10-20 | KIRIT TRADING COMPANY |  |  |  |  | 100800
2023-10-27 | KIRIT TRADING COMPANY |  |  |  |  | 74240
2023-11-02 | KIRIT TRADING COMPANY |  |  |  |  | 80640
2023-11-08 | KIRIT TRADING COMPANY |  |  |  |  | 201600
2023-11-08 | KIRIT TRADING COMPANY |  |  |  |  | 120960
2023-11-17 | JK LAKSHMI CEMENT LTD |  |  |  |  | 89600
2023-12-03 | JANATA SAND SUPPLYING CO. |  |  |  |  | 12000
2023-12-04 | JK LAKSHMI CEMENT LTD |  |  |  |  | 94400
2023-12-07 | KIRIT TRADING COMPANY |  |  |  |  | 106368
2023-12-07 | KIRIT TRADING COMPANY |  |  |  |  | 90624
2023-12-11 | KARAN ENTERPRISES |  |  |  |  | 75520
2023-12-12 | KIRIT TRADING COMPANY |  |  |  |  | 70912
2023-10-04 | AMIT CORPORATION |  |  |  |  | 95422.96
2023-10-04 | AMIT CORPORATION |  |  |  |  | 99555.22
2023-10-04 | AMIT CORPORATION |  |  |  |  | 84620.56
2023-10-04 | AMIT CORPORATION |  |  |  |  | 96464.02
2023-10-04 | AMIT CORPORATION |  |  |  |  | 36506.4
2023-10-06 | S.S.ENTERPRISES |  |  |  |  | 84076.66
2023-10-06 | S.S.ENTERPRISES |  |  |  |  | 33705
2023-10-06 | R.K.TRADING CO. |  |  |  |  | 5460
2023-10-06 | R.K.TRADING CO. |  |  |  |  | 25725
2023-10-09 | S.S.ENTERPRISES |  |  |  |  | 33705
2023-10-16 | S.S.ENTERPRISES |  |  |  |  | 33705
2023-10-16 | GLOBAL GYPSUM PVT LTD |  |  |  |  | 249480
2023-10-28 | S.S.ENTERPRISES |  |  |  |  | 33705
2023-10-30 | S.S.ENTERPRISES |  |  |  |  | 33705
2023-11-03 | R.K.TRADING CO. |  |  |  |  | 20475
2023-11-04 | S.S.ENTERPRISES |  |  |  |  | 33705
2023-11-05 | S.S.ENTERPRISES |  |  |  |  | 33705
2023-11-10 | S.S.ENTERPRISES |  |  |  |  | 33705
2023-11-10 | S.S.ENTERPRISES |  |  |  |  | 33705
2023-11-21 | GLOBAL GYPSUM PVT LTD |  |  |  |  | 166320
2023-11-22 | S.S.ENTERPRISES |  |  |  |  | 33705
2023-12-02 | SHIV ENTERPRISES |  |  |  |  | 69902.7
2023-12-02 | SHIV ENTERPRISES |  |  |  |  | 71060.86
2023-12-02 | SHIV ENTERPRISES |  |  |  |  | 63727.66
2023-12-02 | S.S.ENTERPRISES |  |  |  |  | 33705
2023-12-02 | S.S.ENTERPRISES |  |  |  |  | 33705
2023-12-02 | S.S.ENTERPRISES |  |  |  |  | 33705
2023-12-03 | JANATA SAND SUPPLYING CO. |  |  |  |  | 4725
2023-12-03 | R.K.TRADING CO. |  |  |  |  | 9450
2023-12-04 | JANATA SAND SUPPLYING CO. |  |  |  |  | 1181.26
2023-12-07 | S.S.ENTERPRISES |  |  |  |  | 33705
2023-12-13 | S.S.ENTERPRISES |  |  |  |  | 33705
2023-12-18 | SHIV ENTERPRISES |  |  |  |  | 75776.4
2023-12-18 | SHIV ENTERPRISES |  |  |  |  | 59060.92
2023-12-18 | SHIV ENTERPRISES |  |  |  |  | 75225.16
2023-12-18 | SHIV ENTERPRISES |  |  |  |  | 95963.18
2023-12-18 | SHIV ENTERPRISES |  |  |  |  | 91187.78
2023-12-19 | S.S.ENTERPRISES |  |  |  |  | 33705
2023-12-22 | S.S.ENTERPRISES |  |  |  |  | 33075
2023-09-18 | VISHWANATH G. MENON (HUF) |  |  |  |  | 200000
2023-09-21 | GKP CONTRUCTION & INFRASTRUCTURES |  |  |  |  | 3121509
2023-09-21 | DEVENDRA YADAV |  |  |  |  | 50000
2023-09-18 | R.R ENTERPRISES |  |  |  |  | 15840
2023-09-30 | GODREJ & BOYCE MFC CO.LTD | 108777.6 | 6526.65 | 6526.65 |  | 121830.9
2023-09-01 | ASHA ENTERPRISE | 83606.25 | 7524.56 | 7524.56 |  | 98655.37
2023-09-06 | ASHA ENTERPRISE | 82350 | 7411.5 | 7411.5 |  | 97173
2023-09-11 | ASHA ENTERPRISE | 84019.97 | 7561.8 | 7561.8 |  | 99143.57
2023-09-15 | KRISHNA TRADING CORPORATION | 5152.56 | 463.73 | 463.73 |  | 6080.02
2023-09-30 | AXLER WOODWORKS LLP | 611277 | 55014.93 | 55014.93 |  | 721306.86
2023-09-13 | KARAN ENTERPRISES | 179800 | 25172 | 25172 |  | 230144
2023-09-17 | KARAN ENTERPRISES | 69600 | 9744 | 9744 |  | 89088
2023-09-27 | KARAN ENTERPRISES | 66250 | 9275 | 9275 |  | 84800
2023-09-18 | S.S.ENTERPRISES | 32100 | 802.5 | 802.5 |  | 33705
| MENON SANITATION |  |  |  |  | 350000
| ALFISHAN BAIG |  |  |  |  | 183680
| CHANDRA PRAKASH YADAV |  |  |  |  | 601000
| MOTIRAM S. DUKARE |  |  |  |  | 46550
| JAYESH MAHESH BHAI PARMAR |  |  |  |  | 200000
| MOTIRAM S. DUKARE |  |  |  |  | 82923
| HANSA R CHAVDA |  |  |  |  | 100000
| RAMASHREY PRAJAPATI |  |  |  |  | 1836
| CHAMAN PARWEEN |  |  |  |  | 100000
| MOTIRAM S. DUKARE |  |  |  |  | 109539.5
| MOHAMMED SADDAM SHAIKH |  |  |  |  | 333752
| ANISH FIRDOS MAKNOJIA |  |  |  |  | 119753
| R.R.ENTERPRISES |  |  |  |  | 3240
| GKP CONTRUCTION & INFRASTRUCTURES |  |  |  |  | 1354988
| R.R.ENTERPRISES |  |  |  |  | 1000
| GKP CONTRUCTION & INFRASTRUCTURES |  |  |  |  | 848000
| GKP CONTRUCTION & INFRASTRUCTURES |  |  |  |  | 3190400
| OTIS ELEVATOR COMPANY (I) LTD |  |  |  |  | 145000
| OTIS ELEVATOR COMPANY (I) LTD |  |  |  |  | 130000
2024-01-12 | GODREJ & BOYCE MFC CO.LTD |  |  |  |  | 143083.58
2024-02-07 | GODREJ & BOYCE MFC CO.LTD |  |  |  |  | 112576.36
2024-02-07 | GODREJ & BOYCE MFC CO.LTD |  |  |  |  | 137642.8
2024-02-16 | GODREJ & BOYCE MFC CO.LTD |  |  |  |  | 143375.5
2024-03-31 | SHIV ENTERPRISES |  |  |  |  | 62720
2024-01-01 | AVINASH ENTERPRISE |  |  |  |  | 413000
2024-01-02 | KRISHNA CERAMICS |  |  |  |  | 3941.2
2024-01-05 | S.S.ENTERPRISES |  |  |  |  | 14573
2024-01-05 | ASHISH INFRATECH SYSTEMS |  |  |  |  | 55460
2024-01-06 | TEJAS CERAMICS |  |  |  |  | 53999.99
2024-01-12 | D.R LINKS |  |  |  |  | 8531.4
2024-01-15 | SUSHMA CONSTRUCTION STEEL LLP |  |  |  |  | 556094.48
2024-01-15 | SUSHMA CONSTRUCTION STEEL LLP |  |  |  |  | 21071.26
2024-01-24 | GODREJ & BOYCE MFC CO.LTD |  |  |  |  | 8399.94
2024-02-04 | PADMAVATI DECOR |  |  |  |  | 69228.67
2024-02-05 | VEDANT MARKETING |  |  |  |  | 5982.6
2024-02-06 | DILIP PAINT & HARDWARE STORES |  |  |  |  | 12188.22
2024-02-06 | MEHTA PLYWOOD |  |  |  |  | 43346.12
2024-02-07 | PADMAVATI DECOR |  |  |  |  | 522273.34
2024-02-07 | TEJAS CERAMICS |  |  |  |  | 53999.52
2024-02-07 | GODREJ & BOYCE MFC CO.LTD |  |  |  |  | 8399.94
2024-02-07 | GODREJ & BOYCE MFC CO.LTD |  |  |  |  | 12599.92
2024-02-07 | R.K.TRADERS |  |  |  |  | 9056.5
2024-02-07 | JYOTI KITCHEN INDUSTRIES PVT.LTD. |  |  |  |  | 38984
2024-02-09 | ASHISH INFRATECH SYSTEMS |  |  |  |  | 55460
2024-02-10 | D.R LINKS |  |  |  |  | 8206.9
2024-02-12 | MEHTA PLYWOOD |  |  |  |  | 31860
2024-02-14 | MAHIMA ENTERPRISES |  |  |  |  | -1225.05
2024-02-14 | KRISHNA TRADING CORPORATION |  |  |  |  | 32096
2024-02-14 | KRISHNA TRADING CORPORATION |  |  |  |  | 21240
2024-02-16 | OM SWASTIK ENTERPRISES |  |  |  |  | 76299.94
2024-02-16 | OM SWASTIK ENTERPRISES |  |  |  |  | 68999.98
2024-02-16 | S.S.ENTERPRISES |  |  |  |  | 14573
2024-02-16 | MEHTA PLYWOOD |  |  |  |  | 2454.4
2024-02-16 | AXLER WOODWORKS LLP |  |  |  |  | 80712
2024-02-16 | GODREJ & BOYCE MFC CO.LTD |  |  |  |  | 8399.94
2024-02-17 | MAHIMA ENTERPRISES |  |  |  |  | 236849.9
2024-02-17 | MAHIMA ENTERPRISES |  |  |  |  | 812175.27
2024-02-17 | KRISHNA TRADING CORPORATION |  |  |  |  | 47386.44
2024-02-20 | SAPNA CERAMICS |  |  |  |  | 58797.04
2024-02-22 | S.S.ENTERPRISES |  |  |  |  | 14573
2024-02-26 | ANUPAM ELECTRICALS |  |  |  |  | 1752.3
2024-02-26 | OM SWASTIK ENTERPRISES |  |  |  |  | 172499.48
2024-02-26 | OM SWASTIK ENTERPRISES |  |  |  |  | 101039.86
2024-03-04 | MEHTA PLYWOOD |  |  |  |  | 37804.61
2024-03-07 | H.V. ENTERPRISE |  |  |  |  | 117290.53
2024-03-19 | KRISHNA TRADING CORPORATION |  |  |  |  | 101019.8
2024-03-19 | KRISHNA TRADING CORPORATION |  |  |  |  | 1888
2024-03-19 | KIAAN ENTERPRISE |  |  |  |  | 77792.56
2024-03-19 | MEHTA PLYWOOD |  |  |  |  | 1101.83
2024-03-19 | KRISHNA CERAMICS |  |  |  |  | 89739
2024-03-19 | R.K.TRADERS |  |  |  |  | 1800.68
2024-03-28 | OM SWASTIK ENTERPRISES |  |  |  |  | 26599.98
2024-03-28 | ROYAL ACCOLADE |  |  |  |  | 1500000.53
2024-03-30 | SKY TELECOM |  |  |  |  | 21181
2024-03-30 | MEHTA PLYWOOD |  |  |  |  | 3780.46
2024-03-30 | R.K.TRADERS |  |  |  |  | 5274.6
2024-03-30 | DILIP PAINT & HARDWARE STORES |  |  |  |  | 63494.62
2024-03-30 | S.S.ENTERPRISES |  |  |  |  | 14573
2024-03-30 | DILIP PAINT & HARDWARE STORES |  |  |  |  | 13427.22
2024-03-30 | SIGNARCH |  |  |  |  | 739802.07
2024-03-31 | UNIQUE POINT |  |  |  |  | 903795.74
2024-03-31 | AXLER WOODWORKS LLP |  |  |  |  | 60234.28
2024-01-04 | KIRIT TRADING COMPANY |  |  |  |  | 86400
2024-01-19 | JK LAKSHMI CEMENT LTD |  |  |  |  | 84800
2024-02-09 | JK LAKSHMI CEMENT LTD |  |  |  |  | 84800
2024-02-17 | JK LAKSHMI CEMENT LTD |  |  |  |  | 84800
2024-03-01 | KIRIT TRADING COMPANY |  |  |  |  | 50880
2024-03-06 | KIRIT TRADING COMPANY |  |  |  |  | 67840
2024-03-18 | JANATA SAND SUPPLYING CO. |  |  |  |  | 1800
2024-03-19 | KIRIT TRADING COMPANY |  |  |  |  | 101760
2024-03-30 | KIRIT TRADING COMPANY |  |  |  |  | 84800
2024-03-30 | KIRIT TRADING COMPANY |  |  |  |  | 67840
2024-03-30 | KIRIT TRADING COMPANY |  |  |  |  | 101760
2024-03-30 | KIRIT TRADING COMPANY |  |  |  |  | 84800
2024-03-31 | KIRIT TRADING COMPANY |  |  |  |  | 84160
2024-01-05 | S.S.ENTERPRISES |  |  |  |  | 33075
2024-01-09 | S.S.ENTERPRISES |  |  |  |  | 33075
2024-01-12 | SHIV ENTERPRISES |  |  |  |  | 65655.98
2024-01-12 | SHIV ENTERPRISES |  |  |  |  | 48519.46
2024-01-12 | SHIV ENTERPRISES |  |  |  |  | 18345.6
2024-02-03 | S.S.ENTERPRISES |  |  |  |  | 85995
2024-02-13 | S.S.ENTERPRISES |  |  |  |  | 61152
2024-02-14 | S.S.ENTERPRISES |  |  |  |  | 83032.96
2024-02-16 | S.S.ENTERPRISES |  |  |  |  | 33075
2024-02-16 | S.S.ENTERPRISES |  |  |  |  | 33075
2024-02-16 | S.S.ENTERPRISES |  |  |  |  | 33075
2024-02-16 | S.S.ENTERPRISES |  |  |  |  | 33075
2024-02-16 | S.S.ENTERPRISES |  |  |  |  | 69999.3
2024-02-16 | S.S.ENTERPRISES |  |  |  |  | 33075
2024-02-16 | SHIV ENTERPRISES |  |  |  |  | 57653.4
2024-02-16 | SHIV ENTERPRISES |  |  |  |  | 58800
2024-02-16 | SHIV ENTERPRISES |  |  |  |  | 58461.9
2024-02-16 | SHIV ENTERPRISES |  |  |  |  | 58800
2024-02-16 | SHIV ENTERPRISES |  |  |  |  | 26852.7
2024-02-26 | GLOBAL GYPSUM PVT LTD |  |  |  |  | 249480
2024-03-18 | JANATA SAND SUPPLYING CO. |  |  |  |  | 2100
2024-03-19 | S.S.ENTERPRISES |  |  |  |  | 82364.1
2024-03-19 | SHIV ENTERPRISES |  |  |  |  | 35764
2024-03-19 | SHIV ENTERPRISES |  |  |  |  | 53286.46
2024-03-19 | SHIV ENTERPRISES |  |  |  |  | 44707.96
2024-03-19 | SHIV ENTERPRISES |  |  |  |  | 62086.5
2024-03-19 | S H ENTERPRISES |  |  |  |  | 30712.5
2024-03-30 | GLOBAL GYPSUM PVT LTD |  |  |  |  | 249480
2024-03-30 | S.S.ENTERPRISES |  |  |  |  | 83032.96
2024-03-30 | SHARADA ENTERPRISES |  |  |  |  | 31563
2024-03-30 | S.S.ENTERPRISES |  |  |  |  | 83988.46
2024-03-31 | S.S.ENTERPRISES |  |  |  |  | 83128.5
2024-03-31 | RAJLAXMI CORPORATION |  |  |  |  | 79490.26
2024-03-31 | RAJLAXMI CORPORATION |  |  |  |  | 91035
2024-03-31 | RAJLAXMI CORPORATION |  |  |  |  | 26653.2
2024-03-19 | S H ENTERPRISES |  |  |  |  | 29680
| Grand Total |  |  |  |  | 180783888.26
Formulas:
Supplier Invoice Date = [Date]

## TDR & Approval
2022-12-03 | STAMP DUTY & REGISTRATION TDR | Journal | 2 | 258480 | 2021-08-18 | MUNICIPAL TAX & OTHER CHARGES | Journal | 74 | 239900
2022-12-03 | STAMP DUTY & REGISTRATION TDR | Journal | 3 | 100 | 2021-08-18 | MUNICIPAL TAX & OTHER CHARGES | Journal | 75 | 491700
2022-12-03 | STAMP DUTY & REGISTRATION TDR | Journal | 4 | 100 | 2021-08-18 | MUNICIPAL TAX & OTHER CHARGES | Journal | 76 | 2569100
2022-12-03 | STAMP DUTY & REGISTRATION TDR | Journal | 5 | 100 | 2021-10-11 | MUNICIPAL TAX & OTHER CHARGES | Journal | 84 | 13280
2022-12-03 | STAMP DUTY & REGISTRATION TDR | Journal | 6 | 100 | 2021-10-11 | MUNICIPAL TAX & OTHER CHARGES | Journal | 85 | 51273
2022-12-03 | STAMP DUTY & REGISTRATION TDR | Journal | 7 | 300 | 2021-10-11 | MUNICIPAL TAX & OTHER CHARGES | Journal | 86 | 174488
2022-12-03 | STAMP DUTY & REGISTRATION TDR | Journal | 8 | 221130 | 2021-11-03 | MUNICIPAL TAX & OTHER CHARGES | Journal | 87 | 373256
2022-12-03 | STAMP DUTY & REGISTRATION TDR | Journal | 9 | 100 | 2021-11-03 | MUNICIPAL TAX & OTHER CHARGES | Journal | 88 | 46524.16
2022-12-03 | STAMP DUTY & REGISTRATION TDR | Journal | 10 | 100 | 2021-11-17 | MUNICIPAL TAX & OTHER CHARGES | Journal | 90 | 2208900
2022-12-03 | STAMP DUTY & REGISTRATION TDR | Journal | 11 | 100 | 2021-11-17 | MUNICIPAL TAX & OTHER CHARGES | Journal | 91 | 4526600
2022-12-03 | STAMP DUTY & REGISTRATION TDR | Journal | 12 | 300 | 2021-11-17 | MUNICIPAL TAX & OTHER CHARGES | Journal | 92 | 17766400
2022-12-06 | TDR - AMEY APARTMENTS | Journal | 14 | 7371000 | 2021-12-20 | MUNICIPAL TAX & OTHER CHARGES | Journal | 1 | 9464000
2022-12-09 | TDR - AMEY APARTMENTS | Journal | 21 | 8616000 | 2023-02-10 | MUNICIPAL TAX & OTHER CHARGES | Journal | 57 | 331900
2022-12-12 | TDR - AMEY APARTMENTS | Journal | 24 | 480910 | 2023-03-14 | MUNICIPAL TAX & OTHER CHARGES | Journal | 88 | 10370
|  |  |  | 16948820 | 2020-02-29 | SHRI.MINESH NIRANJAN SHAH | Journal | 12 | 26711.8
[5 empty] | 2020-02-29 | SHRI.MINESH NIRANJAN SHAH | Journal | 13 | 18811.8
[5 empty] | 2020-03-19 | ANDHRA BANK A/C NO. 002811100006481 | Payment | 49 | 50000
[5 empty] | 2021-09-28 | UNION BANK OF INDIA A/C NO. 002811100006481 | Payment | 256 | 1334100
[5 empty] | 2021-11-03 | TRIUMPH BUILDERS LLP | Journal | 87 | 373256
[5 empty] | 2022-01-19 | AXIS BANK - A/C. NO. 921020032222546 | Payment | 50 | 14806500
[5 empty] | 2022-01-31 | AXIS BANK - A/C. NO. 921020032222546 | Payment | 54 | 705200
[5 empty] | 2022-01-31 | AXIS BANK - A/C. NO. 921020032222546 | Payment | 56 | 2378070
[5 empty] | 2022-02-15 | AXIS BANK - A/C. NO. 921020032222546 | Payment | 84 | 11456
[5 empty] | 2022-02-15 | AXIS BANK - A/C. NO. 921020032222546 | Payment | 85 | 190141
[5 empty] | 2022-02-16 | AXIS BANK - A/C. NO. 921020032222546 | Payment | 86 | 72910
[5 empty] | 2022-06-03 | AXIS BANK - A/C. NO. 921020032222546 | Payment | 250 | 30000
[5 empty] | 2022-06-24 | AXIS BANK - A/C. NO. 921020032222546 | Payment | 276 | 29757.8
[5 empty] | 2022-08-20 | MINESH SHAH (CREDITOR) | Journal | 105 | 30000
[5 empty] | 2022-08-26 | MINESH SHAH (CREDITOR) | Journal | 106 | 134000
[5 empty] | 2022-09-30 | MINESH SHAH (CREDITOR) | Journal | 115 | 273400
[5 empty] | 2022-11-07 | TRIUMPH BUILDERS LLP | Journal | 137 | 1585380
[5 empty] | 2022-12-12 | MINESH SHAH (CREDITOR) | Journal | 24 | 33080
[5 empty] | 2023-02-16 | STATE BANK OF INDIA - A/C NO.- 41156455207 | Payment | 165 | 72499
[5 empty] | 2023-02-16 | STATE BANK OF INDIA - A/C NO.- 41156455207 | Payment | 166 | 1079450
[5 empty] | 2023-02-27 | STATE BANK OF INDIA - A/C NO.- 41156455207 | Payment | 177 | 142800
[5 empty] | 2020-03-31 | MINESH SHAH (CREDITOR) | Journal | 61 | 14725
2794471
[6 empty] | MUNICIPAL TAX & OTHER CHARGES PAID TO MUMBAI INTERNATIONAL AIRPOT |  |  | 35400
[5 empty] | 2023-07-06 | MUNICIPAL TAX & OTHER CHARGES |  |  | 235685
[5 empty] | 2023-07-31 | MUNICIPAL TAX & OTHER CHARGES |  |  | 44522
[5 empty] | 2023-11-03 | STATE BANK OF INDIA - A/C NO.- 41156455207 |  |  | 66706
[5 empty] | 2023-11-22 | MINESH SHAH (CREDITOR) |  |  | 357520
[5 empty] | 2023-12-09 | STATE BANK OF INDIA - A/C NO.- 41156455207 |  |  | 19400
[5 empty] | 2023-12-09 | STATE BANK OF INDIA - A/C NO.- 41156455207 |  |  | 159670
[5 empty] | 2023-12-14 | MINESH SHAH (CREDITOR) |  |  | 50466
[5 empty] | 2023-12-15 | STATE BANK OF INDIA - A/C NO.- 41156455207 |  |  | 250280
[5 empty] | 2024-03-20 | MUNICIPAL TAX & OTHER CHARGES |  |  | 768900
66442959.56

## Professional
Date | Particulars | Voucher Type | Voucher No. | Supplier Invoice No. | Supplier Invoice Date | Gross Total
2020-01-03 | J.J. SANGANEE & CO. | Purchase | 1 | CO/01-20/02 | 2020-01-03 | 35400
2020-02-01 | J.J. SANGANEE & CO. | Purchase | 2 | ST/02-20/12 | 2020-02-01 | 2655
2020-02-03 | J.J. SANGANEE & CO. | Purchase | 3 | DT/01-20/08 | 2020-02-03 | 53100
2020-03-02 | J.J. SANGANEE & CO. | Purchase | 4 | ST/03-20/02 | 2020-03-02 | 5900
2020-07-01 | J.J. SANGANEE & CO. | Purchase | 5 | ST/06-20/02 | 2020-07-01 | 1770
2020-07-07 | J.J. SANGANEE & CO. | Purchase | 6 | ST/07-20/09 | 2020-07-07 | 2655
2020-11-01 | J.J. SANGANEE & CO. | Purchase | 7 | ST/11-20/10 | 2020-11-01 | 5310
2021-02-01 | J.J. SANGANEE & CO. | Purchase | 1 | ST/02-21/07 | 2021-02-01 | 2655
2021-03-02 | J.J. SANGANEE & CO. | Purchase | 2 | DT/03-21/16 | 2021-03-02 | 59000
2021-05-05 | J.J. SANGANEE & CO. | Purchase | 3 | ST/05-21/14 | 2021-05-05 | 1770
2021-12-10 | J.J. SANGANEE & CO. | Purchase | 1 | 01/12-21 | 2021-12-10 | 200
2021-12-10 | J.J. SANGANEE & CO. | Purchase | 2 | CO/12-21/01 | 2021-12-10 | 7080
2022-01-03 | J.J. SANGANEE & CO. | Purchase | 3 | CO/01/22/02 | 2022-01-03 | 7080
2022-02-11 | TARANATH SHETTY & ASSOCIATES | Purchase | 7 | 0010/2022 | 2022-02-11 | 1180000
2022-03-01 | J.J. SANGANEE & CO. | Purchase | 9 | DT/03-22/18 | 2022-03-01 | 59000
2022-03-08 | AJIT SURVEYORS | Purchase | 12 | AS/S/61/21-22 | 2022-03-08 | 20500
2022-03-21 | J.J. SANGANEE & CO. | Purchase | 22 | ST/02/22/10 | 2022-03-21 | 5310
2022-03-31 | Y.R.GOSWAMI & CO. | Purchase | 34 | 04/RERA | 2022-03-31 | 5000
2022-04-11 | AJIT SURVEYORS | Purchase | 39 | AS/S/01/22-23 | 2022-04-11 | 8500
2022-04-25 | AQUA LAB BUILDING MATERIAL TESTING PVT LTD | Purchase | 51 | ALPL/22-23/PI-433 | 2022-04-25 | 413
2022-04-29 | TARANATH SHETTY & ASSOCIATES | Purchase | 52 | TSA/002/22-23 | 2022-04-29 | 354000
2022-05-01 | J.J. SANGANEE & CO. | Purchase | 56 | CO/04-22/04 | 2022-05-01 | 23600
2022-06-01 | Global Lab Material Testing Pvt Ltd | Purchase | 162 | KRL-44885-190474 | 2022-06-01 | 531
2022-06-01 | Global Lab Material Testing Pvt Ltd | Purchase | 168 | KRL-44885-190298 | 2022-06-01 | 1062
2022-06-02 | Global Lab Material Testing Pvt Ltd | Purchase | 169 | KRL-44996-190592 | 2022-06-02 | 531
2022-06-09 | VASTUKALA CONSULTANT (I) PVT LTD | Purchase | 172 | PG-807/22-23 | 2022-06-09 | 82600
2022-06-16 | Global Lab Material Testing Pvt Ltd | Purchase | 173 | KRL-45287-192240 | 2022-06-16 | 531
2022-06-16 | Global Lab Material Testing Pvt Ltd | Purchase | 174 | KRL-44885-192239 | 2022-06-16 | 531
2022-06-18 | Global Lab Material Testing Pvt Ltd | Purchase | 176 | KRL-44885-192410 | 2022-06-18 | 531
2022-06-20 | Global Lab Material Testing Pvt Ltd | Purchase | 177 | KRL-45418-192544 | 2022-06-20 | 531
2022-06-25 | J.J. SANGANEE & CO. | Purchase | 178 | CO/06-22/02 | 2022-06-25 | 17700
2022-06-25 | YOGESH R. GOSWAMI | Purchase | 179 | 02/RERA | 2022-06-25 | 4000
2022-08-22 | Global Lab Material Testing Pvt Ltd | Purchase | 199 | KRL-44885-193940 | 2022-08-22 | 5841
2022-09-16 | Global Lab Material Testing Pvt Ltd | Purchase | 206 | KRL-46585-198686 | 2022-09-16 | 7434
2022-11-01 | J.J. SANGANEE & CO. | Purchase | 223 | CO/10-22/18 | 2022-11-01 | 17700
2022-11-01 | J.J. SANGANEE & CO. | Purchase | 224 | ST/09-22/05 | 2022-10-01 | 3540
2022-11-02 | J.J. SANGANEE & CO. | Purchase | 225 | 04/11-22 | 2022-11-02 | 300
2022-11-15 | J.J. SANGANEE & CO. | Purchase | 236 | CO/11-22/04 | 2022-11-15 | 5900
2022-12-03 | J.J. SANGANEE & CO. | Purchase | 6 | CO/12-22/05 | 2022-12-03 | 5900
2022-12-28 | TARANATH SHETTY & ASSOCIATES | Purchase | 30 | TSA/011/22-23 | 2022-12-28 | 509760
2022-12-28 | TARANATH SHETTY & ASSOCIATES | Purchase | 31 | TSA/011/22-23 | 2022-12-28 | 472000
2023-01-01 | Global Lab Material Testing Pvt Ltd | Purchase | 39 | KRL-48671-211610 | 2023-01-01 | 1062
2023-01-05 | Global Lab Material Testing Pvt Ltd | Purchase | 42 | KRL-48994-215567 | 2023-01-05 | 3717
2023-03-01 | J.J. SANGANEE & CO. | Purchase | 118 | DT/03-23/01 | 2023-03-01 | 59000
2023-03-01 | J.J. SANGANEE & CO. | Purchase | 119 | ST/03-23/07 | 2023-03-01 | 3540
2023-02-07 | TARANATH SHETTY & ASSOCIATES | Purchase | 82 |  | 2023-02-07 | 472000
| RERA Registration Charges |  |  |  |  | 17815
| PROFESSIONAL FEES (S & A) |  |  |  |  | 529000
| PROFESSIONALFEES -GST |  |  |  |  | 186000
2023-02-18 | Global Lab Material Testing Pvt Ltd | Purchase | 95 | KRL-49294-222070 | 2023-02-18 | 4248
| VASTUKALA CONSULTANT (I) PVT LTD | PROFESSIONALFEES -GST |  | MUM/2324/MAY/141 | 2023-05-12 | 47200
| TARANATH SHETTY & ASSOCIATES | ARCHITECT FEES |  |  | 2023-07-17 | 155760
| Global Lab Material Testing Pvt Ltd | TESTING CHARGES |  |  |  | 4500
| Global Lab Material Testing Pvt Ltd | TESTING CHARGES |  |  |  | 9000
| Global Lab Material Testing Pvt Ltd | TESTING CHARGES |  |  |  | 10200
| J.J. SANGANEE & CO. | PROFESSIONALFEES -GST |  |  | 2023-09-04 | 10620
2023-12-01 | J.J. SANGANEE & CO. | PROFESSIONALFEES -GST |  | CO/12-23/05 |  | 5900
2023-12-19 | VASTUKALA CONSULTANT (I) PVT LTD | PROFESSIONALFEES -GST |  | MUM/2324/DEC/156 |  | 29500
| UNIVERSAL TESTING LAB | TESTING CHARGES WITH GST | 2944/2023-24 |  | 2023-10-06 | 7080
| UNIVERSAL TESTING LAB | TESTING CHARGES WITH GST | 2943/2023-24 |  | 2023-10-06 | 1416
| UNIVERSAL TESTING LAB | TESTING CHARGES WITH GST | 3184/2023-24 |  | 2023-10-20 | 708
| UNIVERSAL TESTING LAB | TESTING CHARGES WITH GST | 3342/2023-24 |  | 2023-11-03 | 708
| PROFESSIONALFEES -GST |  |  |  |  | 112500
| PROFESSIONAL FEES (S & A) |  |  |  |  | 902000
| Testing Charges |  |  |  |  | 300
| Testing Charges |  |  |  |  | 300
5551895

## MArketing
Date | Particulars | Voucher Type | Voucher No. | Gross Total
2022-05-24 | MAGICBRICKS REALTY SERVICES LIMITED | Purchase | 157 | 506000
2023-03-02 | SWANAND M.PRABHUTENDOLKAR-701 AMEY APRT | Journal | 70 | 90533
2023-03-02 | MAHENDRAKUMAR CHANDRABHUSHAN RAI A/802 AMEY APART | Journal | 72 | 1459
2023-03-02 | MAHENDRAKUMAR CHANDRABHUSHAN RAI A/802 AMEY APART | Journal | 74 | 1459
2023-03-04 | RANJINI PRABHTENDOLKAR-702-A AMEY APART | Journal | 76 | 90533
2023-03-04 | HIREN DINESHCHANDRA KAPADIA 704 AMEY APARTMENT | Journal | 78 | 88627
2023-03-04 | ADHESHKUMAR SHYAMNARAYAN MISHRA 804 AMEY APT | Journal | 80 | 99098
2023-03-04 | SHYAMNARAYAN N. PANDEY-1101-AMEY APT. | Journal | 82 | 5344
2023-03-31 | STAMP DUTY & REGISTRATION-EXP | Journal | 155 | 765000
2023-03-31 | ADVERTISE MENT | Journal | 159 | 77186.52
2022-10-03 | Stamp duty for 1101 |  |  | 831600
| 802 |  |  | 1030800
| 704 |  |  | 1115300
| 804 |  |  | 1243500
| 702 |  |  | 1138600
| 701 |  |  | 1138600
| 1604 |  |  | 1280100
2023-06-13 | STAMP DUTY AND REGISTRATION FEES | PAID TO FLAT NO 1201 | 440 | 843000
2023-07-26 | PROPTIGER MARKETING SERVICES PVT LTD |  |  | 390954
2023-07-04 | STAMP DUTY & REGISTRATION | CH.NO 898109 FOR FALT NO.1703 AMEY APARTMENT |  | 1172500
2023-07-17 | STAMP DUTY & REGISTRATION | CH.NO 983400 AG FLAT NO. 904 AMEY APARTMENT |  | 1280300
2023-08-29 | STAMP DUTY & REGISTRATION | CH.NO 165594 STAMP DUTY PAID FLAT NO 1203 AMEY APT KINJAL VIPUL SHAH ( SD 1206360 + REG 30000) |  | 1236400
2023-08-29 | STAMP DUTY & REGISTRATION | CH.NO 898131 AG STAMP DUTY PAID FOR 902 AMEY APARTMENT |  | 946100
2023-10-04 | BONANZA ESTATE AGENCY | BROKARAGE & COMMISSION |  | 130000
2023-10-10 | STAMP DUTY & REGISTRATION |  |  | 1594600
2023-11-06 | STAMP DUTY & REGISTRATION |  |  | 1653200
2023-12-20 | STAMP DUTY & REGISTRATION |  |  | 1263800
2023-09-26 | Harsha Reality Real Estate |  |  | 260000
2024-01-12 | SUSAN AROZA |  |  | 507780
2024-01-10 | STAMP DUTY & REGISTRATION |  |  | 968300
2024-01-15 | STAMP DUTY & REGISTRATION |  |  | 1100300
2024-02-20 | STAMP DUTY & REGISTRATION |  |  | 1322800
2024-03-27 | STAMP DUTY & REGISTRATION |  |  | 1183200
25356973.52

## Admin
Date | Particulars | Voucher Type | Voucher No. | Supplier Invoice No. | Supplier Invoice Date | Gross Total
2022-04-29 | RAJGURU ENTERPRISES | Purchase | 53 | R-0005 | 2022-04-29 | 4278
2022-07-01 | Escorts Protection Detection & Security Services | Purchase | 180 | EPS/JUNE/22/0080 | 2022-07-01 | 17000
2022-08-04 | Escorts Protection Detection & Security Services | Purchase | 192 | EPS/JULY/22/0494 | 2022-08-04 | 17000
2022-09-01 | Escorts Protection Detection & Security Services | Purchase | 201 | EPS/AUG/22/0061 | 2022-09-01 | 17000
2022-10-01 | Escorts Protection Detection & Security Services | Purchase | 211 | EPS/SEPT/22/0103 | 2022-10-01 | 17000
2022-11-01 | Escorts Protection Detection & Security Services | Purchase | 222 | EPS/OCT/22/0079 | 2022-11-01 | 17000
2022-12-01 | Escorts Protection Detection & Security Services | Purchase | 2 | EPS/NOV/22/0118 | 2022-12-01 | 17000
2023-01-01 | Escorts Protection Detection & Security Services | Purchase | 36 | EPS/DEC/22/0140 | 2023-01-01 | 17000
2022-09-16 | SHEETAL PEST CONTROL | Purchase | 205 | SPC-062 | 2022-08-31 | 15675
2021-03-31 | PRINTING & STATIONERY | Journal | 14 |  |  | 1080.2
2021-04-03 | LATE FILLING FEES | Journal | 61 |  |  | 200
2021-05-25 | SUNDRY BALANCE WRITTEN OFF | Journal | 62 |  |  | 30
2021-08-11 | STAMP DUTY & REGISTRATION | Journal | 73 |  |  | 6250
2021-11-04 | PRINTING & STATIONERY | Journal | 89 |  |  | 215
2021-11-24 | PRINTING & STATIONERY | Journal | 93 |  |  | 6756
2022-03-31 | LABOUR CHARGES | Journal | 12 |  |  | 26516.7
2022-03-31 | MATERIAL PURCHASED | Journal | 14 |  |  | 3156869.5
2022-03-31 | MATERIAL PURCHASED | Journal | 37 |  |  | 224538.3
2022-03-31 | LABOUR CHARGES | Journal | 73 |  |  | 3600
2022-03-31 | ELECTRICITY CHARGES | Journal | 78 |  |  | 9600
2022-03-31 | FIXED DEPOSIT | Journal | 79 |  |  | 39091
2022-03-31 | INTEREST ON FIXED DEPOSIT | Journal | 80 |  |  | 43435
2022-04-16 | RERA REGISTRATION FEES | Journal | 87 |  |  | 17815
2022-07-30 | LOAN PROCESSING CHARGES | Journal | 101 |  |  | 3318278
2022-07-30 | LOAN PROCESSING CHARGES | Journal | 102 |  |  | 751500
2023-02-01 | SAI FACILITY | Purchase | 69 |  | 2023-02-01 | 38322
2023-02-01 | Escorts Protection Detection & Security Services | Purchase | 71 | EPS/JAN/23/0362 | 2023-02-01 | 8226
2023-02-01 | SUNDRY BALANCE WRITTEN OFF | Journal | 50 |  |  | 200
2023-02-05 | STAFF INCOME TAX | Journal | 51 |  |  | 8670
2023-02-15 | ABHISHEK KISAN SHINDE | Journal | 58 |  |  | 819
2023-02-27 | KHETHAVATH PADMA | Journal | 60 |  |  | 10112
2023-03-01 | SAI FACILITY | Purchase | 114 |  | 2023-03-01 | 54000
2023-03-31 | SAI FACILITY | Purchase | 162 | MARCH2023 | 2023-03-31 | 54000
2023-03-21 | CGST ON REVERSE | Journal | 89 |  |  | 4189
2023-03-31 | ELECTRICITY CHARGES | Journal | 145 |  |  | 46690
2023-03-31 | TRANSPORTATION CHARGES | Journal | 160 |  |  | 16384
2023-03-31 | TRANSPORTATION CHARGES | Journal | 161 |  |  | 14160
2023-03-31 | Security Guards Charges | Journal | 162 |  |  | 3060
2023-03-31 | Security Guards Charges | Journal | 163 |  |  | 3060
2023-03-31 | TRANSPORTATION CHARGES | Journal | 164 |  |  | 4612
2023-03-31 | Security Guards Charges | Journal | 165 |  |  | 3060
2023-03-31 | Security Guards Charges | Journal | 166 |  |  | 3060
2023-03-31 | Security Guards Charges | Journal | 167 |  |  | 8378
2023-04-01 | Cooli & Cartage Expenses |  |  |  |  | 44726
2023-04-01 | ELECTRICITY CHARGES |  |  |  |  | 3690
2023-04-01 | STAMP DUTY & REGISTRATION |  |  |  |  | 6250
2023-03-01 | RAJGURU ENTERPRISES | Purchase | 117 | R-0033 | 2023-03-01 | 944
| Salary |  |  |  |  | 7700000
| Salary |  |  |  |  | 5285755
| Insurance Charges |  |  |  |  | 358744
| SUNDRY BALANCE WRITTEN OFF |  |  |  |  | 6994.86
| SGST INTEREST |  |  |  |  | 45
| SGST FEES |  |  |  |  | 550
| REPAIR AND MANTENACE CHARGES |  |  |  |  | 13284
| PRINTING & STATIONERY |  |  |  |  | 4425
| LATE FILLING FEES |  |  |  |  | 300
| CGST INTEREST |  |  |  |  | 45
| CGST FEES |  |  |  |  | 550
| BANK CHARGES |  |  |  |  | 6985.47
| AMIT PATIL | SALARY PAID | 337 |  | 2023-05-02 | 35000
| UMESWH GANESH THAKUR | SALARY PAID | 345 |  | 2023-05-08 | 41450
| MOOL CHAND KEWALA SHANKAR YADAV | SALARY PAID | 346 |  | 2023-05-08 | 31400
| SHASHIKANT PATEL | SALARY PAID | 347 |  | 2023-05-08 | 32450
| RAMESHWAR S HOGADE | SALARY PAID | 348 |  | 2023-05-08 | 29000
| AMIT SHOK PATIL | SALARY PAID | 349 |  | 2023-05-08 | 7750
| MADHUKAR RATHOD | SALARY PAID | 350 |  | 2023-05-08 | 32800
| PRATHAMESH LAD | SALARY PAID | 351 |  | 2023-05-08 | 56100
| TEJAS RAJENDRA POKHARKAR | SALARY PAID | 352 |  | 2023-05-08 | 31700
| KALU BHIKARI SINGH | SALARY PAID | 353 |  | 2023-05-08 | 23000
| FAISAL ABDUL MASJID | SALARY PAID | 354 |  | 2023-05-08 | 10000
| MAYUR BHOSALE | SALARY PAID | 355 |  | 2023-05-08 | 27450
| DHAWAL SHAH | SALARY PAID | 356 |  | 2023-05-08 | 46100
| RAMESH V. SINGH | SALARY PAID | 357 |  | 2023-05-08 | 48300
| SUNIL MULAY | SALARY PAID | 358 |  | 2023-05-08 | 47250
| DHANRAJ V HATKAR | SALARY PAID | 359 |  | 2023-05-08 | 26100
| MADHUKAR RATHOD | SALARY PAID | 362 |  | 2023-05-08 | 30000
| MR SANDEEP TAPARIA | SALARY PAID | 363 |  | 2023-05-10 | 48000
| BRIJESH GANDHI | SALARY PAID | 365 |  | 2023-05-11 | 19150
| MAYUR BHOSALE | SALARY PAID | 408 |  | 2023-06-01 | 27450
| DHAWAL SHAH | SALARY PAID | 409 |  | 2023-06-01 | 46100
| RAMESH V. SINGH | SALARY PAID | 410 |  | 2023-06-01 | 48300
| BRIJESH GANDHI | SALARY PAID | 411 |  | 2023-06-01 | 19150
| SUNIL MULAY | SALARY PAID | 412 |  | 2023-06-01 | 47250
| DHANRAJ V HATKAR | SALARY PAID | 413 |  | 2023-06-01 | 26100
| UMESH GANESH THAKUR | SALARY PAID | 414 |  | 2023-06-01 | 41450
| MOOL CHAND KEWALA SHANKAR YADAV | SALARY PAID | 415 |  | 2023-06-01 | 31400
| SHASHIKANT PATEL | SALARY PAID | 416 |  | 2023-06-01 | 32450
| RAMESHWAR S HOGADE | SALARY PAID | 417 |  | 2023-06-01 | 29000
| AMIT ASHOK PATEL | SALARY PAID | 418 |  | 2023-06-01 | 42750
| MADHUKAR RATHOD | SALARY PAID | 419 |  | 2023-06-01 | 32800
| PRATHAMESH LAD | SALARY PAID | 420 |  | 2023-06-01 | 56100
| TEJAS RAJENDRA POKHARKAR | SALARY PAID | 421 |  | 2023-06-01 | 31700
| KALU BHIKARI SINGH | SALARY PAID | 423 |  | 2023-06-01 | 23000
| FAISAL ABDUL MASJID | SALARY PAID | 424 |  | 2023-06-01 | 10000
| NAFISA HOZEFA UJJAINWALA SALARY | SALARY PAID | 439 |  | 2023-06-07 | 80000
| ADANI ELECTRICITY | ELECTRICITY CHARGES | 395 |  | 2023-05-30 | 3200
| K.R. ENTERPRISES | TRANSPORTATION CHARGES | 206 |  | 2023-05-01 | 17200
| A1 STAR TRANSPORT | TRANSPORTATION CHARGES | 215 |  | 2023-05-08 | 5000
| A1 STAR TRANSPORT | TRANSPORTATION CHARGES | 216 |  | 2023-05-08 | 3900
| K.R. ENTERPRISES | TRANSPORTATION CHARGES | 268 |  | 2023-06-01 | 12900
| A1 STAR TRANSPORT | TRANSPORTATION CHARGES | 280 |  | 2023-06-06 | 14000
| VISION TRANSPORT | TRANSPORTATION CHARGES | 329 |  | 2023-06-20 | 2400
| VISION TRANSPORT | TRANSPORTATION CHARGES | 330 |  | 2023-06-20 | 1500
| VISION TRANSPORT | TRANSPORTATION CHARGES | 331 |  | 2023-06-20 | 27600
| VISION TRANSPORT | TRANSPORTATION CHARGES | 332 |  | 2023-06-20 | 8400
| VISION TRANSPORT | TRANSPORTATION CHARGES | 335 |  | 2023-06-20 | 10000
| ABHISHEK KISAN SHINDE | Cooli & Cartage Expenses | 217 |  | 2023-05-08 | 22696
| ABHISHEK KISAN SHINDE | Cooli & Cartage Expenses | 240 |  | 2023-05-17 | 26200
| ABHISHEK KISAN SHINDE | Cooli & Cartage Expenses | 258 |  | 2023-05-29 | 16146
| ABHISHEK KISAN SHINDE | Cooli & Cartage Expenses | 281 |  | 2023-06-07 | 6696
| SAI FACILITY | SECURITY GUARDS CHARGES | 236 |  | 2023-05-16 | 51000
| PRINTING & STATIONERY |  |  |  | 2023-06-16 | 2300
| SANTOSH ELECTRICALS | REPAIR AND MANTENACE CHARGES |  |  | 2023-06-10 | 5150
| SANTOSH ELECTRICALS | REPAIR AND MANTENACE CHARGES |  |  | 2023-06-11 | 2250
| SHEETAL PEST CONTROL | REPAIR AND MANTENACE CHARGES |  |  | 2023-06-16 | 6075
| M.P.WATER SUPPLIER | WELFARE AT SITE | 049 |  | 2023-08-01 | 2260
| M.P.WATER SUPPLIER | WELFARE AT SITE | 155 |  | 2023-09-01 | 3640
| ADANI ELECTRICITY | ELECTRICITY CHARGES | 498 |  | 2023-07-01 | 3220
| ADANI ELECTRICITY | ELECTRICITY CHARGES | 545 |  | 2023-07-26 | 2360
| ADANI ELECTRICITY | ELECTRICITY CHARGES | 606 |  | 2023-08-17 | 222090
| PUJARI TRANSPORT | TRANSPORTATION CHARGES |  |  | 2023-07-01 | 33932
| K.R. ENTERPRISES | TRANSPORTATION CHARGES |  |  | 2023-07-01 | 21500
| A1 STAR TRANSPORT | TRANSPORTATION CHARGES |  |  | 2023-07-10 | 12000
| GAURI TRANSPORT | TRANSPORTATION CHARGES |  |  | 2023-07-31 | 20558
| K.R. ENTERPRISES | TRANSPORTATION CHARGES |  |  | 2023-08-01 | 55900
| GAURI TRANSPORT | TRANSPORTATION CHARGES |  |  | 2023-08-07 | 20930
| VISION TRANSPORT | TRANSPORTATION CHARGES |  |  | 2023-08-08 | 7200
| VISION TRANSPORT | TRANSPORTATION CHARGES |  |  | 2023-08-08 | 15000
| VISION TRANSPORT | TRANSPORTATION CHARGES |  |  | 2023-08-08 | 1200
| VISION TRANSPORT | TRANSPORTATION CHARGES |  |  | 2023-08-08 | 7500
| A1 STAR TRANSPORT | TRANSPORTATION CHARGES |  |  | 2023-08-08 | 7000
| K.R. ENTERPRISES | TRANSPORTATION CHARGES |  |  | 2023-09-01 | 25800
| A1 STAR TRANSPORT | TRANSPORTATION CHARGES |  |  | 2023-09-07 | 10000
| ABHISHEK KISAN SHINDE | Cooli & Cartage Expenses |  |  | 2023-07-06 | 30336
| ABHISHEK KISAN SHINDE | Cooli & Cartage Expenses |  |  | 2023-07-10 | 23475
| ABHISHEK KISAN SHINDE | Cooli & Cartage Expenses |  |  | 2023-07-13 | 26292
| ABHISHEK KISAN SHINDE | Cooli & Cartage Expenses | 190/193/197/198 |  | 2023-08-02 | 38371
| ABHISHEK KISAN SHINDE | Cooli & Cartage Expenses | 202/203/207/210/216/219 |  | 2023-08-25 | 48745
| ABHISHEK KISAN SHINDE | Cooli & Cartage Expenses | 224 |  | 2023-08-30 | 6850
| GOOD LUCK FACILITY | Security Guards Charges |  |  | 2023-07-10 | 54000
| GOOD LUCK FACILITY | Security Guards Charges |  |  | 2023-08-08 | 54000
| GOOD LUCK FACILITY | Security Guards Charges |  |  | 2023-09-07 | 54000
| SALARY | CH.NO 165475 BEING AMOUNT PAID MAYUR BHOSALE FOR SALARY MONTH OF JUNE-2023 |  |  | 2023-07-01 | 27450
| SALARY | CH.NO 165476 BEING AMOUNT PAID DHAWAL SHAH FOR SALARY MONTH OF JUNE-2023 |  |  | 2023-07-01 | 46100
| SALARY | CH.NO 165477 BEING AMOUNT PAID RAMESH V.SINGH FOR SALARY MONTH OF JUNE-2023 |  |  | 2023-07-01 | 48300
| SALARY | CH.NO 165478 BEING AMOUNT PAID BRIJESH GANDHI FOR SALARY MONTH OF JUNE-2023 |  |  | 2023-07-01 | 19150
| SALARY | CH.NO 165479 BEING AMOUNT PAID SUNIL MULAY FOR SALARY MONTH OF JUNE-2023 |  |  | 2023-07-01 | 47250
| SALARY | CH.NO 165480 BEING AMOUNT PAID DHANRAJ VHATKAR- FOR SALARY MONTH OF JUNE-2023 |  |  | 2023-07-01 | 26100
| SALARY | CH.NO 165481 BEING AMOUNT PAID UMESH GANESH THAKUR- FOR SALARY MONTH OF JUNE-2023 |  |  | 2023-07-01 | 41450
| SALARY | CH.NO 165482 BEING AMOUNT PAID MOOLCHAND KEWALASHANKAR YADAV- FOR SALARY MONTH OF JUNE-2023 |  |  | 2023-07-01 | 31400
| SALARY | CH.NO 165483 BEING AMOUNT PAID SHASHIKANT PATEL- FOR SALARY MONTH OF JUNE-2023 |  |  | 2023-07-01 | 32450
| SALARY | CH.NO 165484 BEING AMOUNT PAID RAMESHWAR S HOGADE- FOR SALARY MONTH OF JUNE-2023 |  |  | 2023-07-01 | 29000
| SALARY | CH.NO 165485 BEING AMOUNT PAID AMIT ASHOK PATIL- FOR SALARY MONTH OF JUNE-2023 |  |  | 2023-07-01 | 42750
| SALARY | CH.NO 165486 BEING AMOUNT PAID MADHUKAR RATHOD- FOR SALARY MONTH OF JUNE-2023 |  |  | 2023-07-01 | 32800
| SALARY | CH.NO 165487 BEING AMOUNT PAID PRATHAMESH LAD- FOR SALARY MONTH OF JUNE-2023 |  |  | 2023-07-01 | 56100
| SALARY | CH.NO 165488 BEING AMOUNT PAID TEJAS RAJENDRA POKHARKAR- FOR SALARY MONTH OF JUNE-2023 |  |  | 2023-07-01 | 31700
| SALARY | CH.NO 165490 BEING AMOUNT PAID YOUR SELF A/C RTGS NAFISA HOZEFA UJJAINWALA- FOR SALARY MONTH OF JUNE-2023 |  |  | 2023-07-01 | 80000
| SALARY | CH.NO 165491 BEING AMOUNT PAID KALU BHIKARI SINGH- FOR SALARY MONTH OF JUNE-2023 |  |  | 2023-07-01 | 23000
| SALARY | CH.NO 165492 BEING AMOUNT PAID FAISAL ABDUL MASJID LOHARI- FOR SALARY MONTH OF JUNE-2023 |  |  | 2023-07-01 | 10000
| SALARY | Cheque No 165531 BEING AMOUNT PAID FOR MAYUR BHOSALE FOR SALARY MONTH OF JULY 2023 |  |  | 2023-08-01 | 27450
| SALARY | Cheque No 165549 BEING AMOUNT PAID FOR DHAWAL SHAH- FOR SALARY MONTH OF JULY 2023 |  |  | 2023-08-01 | 46100
| SALARY | Cheque No 165533 BEING AMOUNT PAID FOR RAMESH V SINGH- FOR SALARY MONTH OF JULY 2023 |  |  | 2023-08-01 | 48300
| SALARY | Cheque No 165534 BEING AMOUNT PAID FOR BRIJESH GANDHI- FOR SALARY MONTH OF JULY 2023 |  |  | 2023-08-01 | 19150
| SALARY | Cheque No 165535 BEING AMOUNT PAID FOR SUNIL MULAY- FOR SALARY MONTH OF JULY 2023 |  |  | 2023-08-01 | 47250
| SALARY | Cheque No 165536 BEING AMOUNT PAID FOR DHANRAJ VHATKAR- FOR SALARY MONTH OF JULY 2023 |  |  | 2023-08-01 | 26100
| SALARY | Cheque No 165537 BEING AMOUNT PAID FOR UMESH GANESH THAKUR- FOR SALARY MONTH OF JULY 2023 |  |  | 2023-08-01 | 41450
| SALARY | Cheque No 165538 BEING AMOUNT PAID FOR MOOLCHAND KEWALASHANKAR YADAV- FOR SALARY MONTH OF JULY 2023 |  |  | 2023-08-01 | 31400
| SALARY | Cheque No 165539 BEING AMOUNT PAID FOR SHASHIKANT PATEL- FOR SALARY MONTH OF JULY 2023 |  |  | 2023-08-01 | 32450
| SALARY | Cheque No 165540 BEING AMOUNT PAID FOR RAMESHWAR S HOGADE- FOR SALARY MONTH OF JULY 2023 |  |  | 2023-08-01 | 29000
| SALARY | Cheque No 165541 BEING AMOUNT PAID FOR MADHUKAR RATHOD- FOR SALARY MONTH OF JULY 2023 |  |  | 2023-08-01 | 32800
| SALARY | Cheque No 165542 BEING AMOUNT PAID FOR PRATHAMESH LAD - FOR SALARY MONTH OF JULY 2023 |  |  | 2023-08-01 | 56100
| SALARY | Cheque No 165543 BEING AMOUNT PAID FOR TEJAS RAJENDRA POKHARKAR - FOR SALARY MONTH OF JULY 2023 |  |  | 2023-08-01 | 31700
| SALARY | Cheque No 165545 BEING AMOUNT PAID FOR YOUR SELF A/C RTGS NAFISA HOZEFA UJJAINWALA - FOR SALARY MONTH OF JULY 2023 |  |  | 2023-08-01 | 80000
| SALARY | Cheque No 165546 BEING AMOUNT PAID FOR KALU BHIKARI SINGH - FOR SALARY MONTH OF JULY 2023 |  |  | 2023-08-01 | 23000
| SALARY | Cheque No 165547 BEING AMOUNT PAID FOR FAISAL ABDUL MASJID LAHORI - FOR SALARY MONTH OF JULY 2023 |  |  | 2023-08-01 | 10000
| SALARY | Cheque No 165613 BEING AMOUNT PAID FOR KALU BHIKARI SINGH - FOR SALARY MONTH OF AUGUST 2023 |  |  | 2023-08-02 | 23000
| SALARY | CH.NO 898127 SALARY FOR JULY PAID TO AMIT ASHOK PATIL |  |  | 2023-08-04 | 42750
| SALARY | Cheque No 165597 BEING AMOUNT PAID FOR MAYUR BHOSALE FOR SALARY MONTH OF AUGUST 2023 |  |  | 2023-09-01 | 27450
| SALARY | Cheque No 165598 BEING AMOUNT PAID FOR DHAWAL SHAH- FOR SALARY MONTH OF AUGUST 2023 |  |  | 2023-09-01 | 46100
| SALARY | Cheque No 165599 BEING AMOUNT PAID FOR RAMESH V SINGH- FOR SALARY MONTH OF AUGUST 2023 |  |  | 2023-09-01 | 48300
| SALARY | Cheque No 165600 BEING AMOUNT PAID FOR BRIJESH GANDHI- FOR SALARY MONTH OF AUGUST 2023 |  |  | 2023-09-01 | 19150
| SALARY | Cheque No 165601 BEING AMOUNT PAID FOR SUNIL MULAY- FOR SALARY MONTH OF AUGUST 2023 |  |  | 2023-09-01 | 47250
| SALARY | Cheque No 165602 BEING AMOUNT PAID FOR DHANRAJ VHATKAR- FOR SALARY MONTH OF AUGUST 2023 |  |  | 2023-09-01 | 26100
| SALARY | Cheque No 165603 BEING AMOUNT PAID FOR UMESH GANESH THAKUR- FOR SALARY MONTH OF AUGUST 2023 |  |  | 2023-09-01 | 41450
| SALARY | Cheque No 165604 BEING AMOUNT PAID FOR MOOLCHAND KEWALASHANKAR YADAV- FOR SALARY MONTH OF AUGUST 2023 |  |  | 2023-09-01 | 31400
| SALARY | Cheque No 165605 BEING AMOUNT PAID FOR SHASHIKANT PATEL- FOR SALARY MONTH OF AUGUST 2023 |  |  | 2023-09-01 | 32450
| SALARY | Cheque No 165606 BEING AMOUNT PAID FOR RAMESHWAR S HOGADE- FOR SALARY MONTH OF AUGUST 2023 |  |  | 2023-09-01 | 29000
| SALARY | CH.NO 165607 SALARY FOR AUGUST 2023 PAID TO AMIT ASHOK PATIL |  |  | 2023-09-01 | 42750
| SALARY | Cheque No 165608 BEING AMOUNT PAID FOR MADHUKAR RATHOD- FOR SALARY MONTH OF AUGUST 2023 |  |  | 2023-09-01 | 32800
| SALARY | Cheque No 165609 BEING AMOUNT PAID FOR PRATHAMESH LAD - FOR SALARY MONTH OF AUGUST 2023 |  |  | 2023-09-01 | 56100
| SALARY | Cheque No 165610 BEING AMOUNT PAID FOR TEJAS RAJENDRA POKHARKAR - FOR SALARY MONTH OF AUGUST 2023 |  |  | 2023-09-01 | 31700
| SALARY | Cheque No 165612 BEING AMOUNT PAID FOR YOUR SELF A/C RTGS NAFISA HOZEFA UJJAINWALA - FOR SALARY MONTH OF AUGUST 2023 |  |  | 2023-09-01 | 80000
| SALARY | Cheque No 165613 BEING AMOUNT PAID FOR KALU BHIKARI SINGH - FOR SALARY MONTH OF AUGUST 2023 |  |  | 2023-09-01 | 23000
| SALARY | Cheque No 165614 BEING AMOUNT PAID FOR FAISAL ABDUL MASJID LAHORI - FOR SALARY MONTH OF AUGUST 2023 |  |  | 2023-09-01 | 10000
| AUDIT FEES | SALES & ADMINISTRATIVE EXPENSE |  |  |  | 15000
| BANK CHARGES | SALES & ADMINISTRATIVE EXPENSE |  |  |  | 85830.68
| GENERAL EXPENSESS | SALES & ADMINISTRATIVE EXPENSE |  |  |  | 28640
| INTEREST ON GOVERNMENT DUE | SALES & ADMINISTRATIVE EXPENSE |  |  |  | 568
| LATE FILLING FEES | SALES & ADMINISTRATIVE EXPENSE |  |  |  | 200
| REPAIR AND MANTENACE CHARGES | SALES & ADMINISTRATIVE EXPENSE |  |  |  | 5500
| SUNDRY BALANCE WRITTEN OFF | SALES & ADMINISTRATIVE EXPENSE |  |  |  | 7.4
| BANK CHARGES | SALES & ADMINISTRATIVE EXPENSE |  |  |  | 6555.92
| INTEREST ON GOVERNMENT DUE | SALES & ADMINISTRATIVE EXPENSE |  |  |  | 1568
| LATE FILLING FEES | SALES & ADMINISTRATIVE EXPENSE |  |  |  | 900
| REPAIR AND MAINTENACE CHARGES GST | SALES & ADMINISTRATIVE EXPENSE |  |  |  | 1400
| SUNDRY BALANCE WRITTEN OFF | SALES & ADMINISTRATIVE EXPENSE |  |  |  | 0.52
| M.P.WATER SUPPLIER | WELFARE AT SITE | 2020 |  | 2023-10-01 | 5090
| M.P.WATER SUPPLIER | WELFARE AT SITE | 2525 |  | 2023-11-01 | 6650
| ADANI ELECTRICITY | ELECTRICITY CHARGES | 769 |  | 2023-10-18 | 22870
| ADANI ELECTRICITY | ELECTRICITY CHARGES | 770 |  | 2023-10-18 | 130445
| ADANI ELECTRICITY | ELECTRICITY CHARGES | 831 |  | 2023-11-16 | 323690
| ADANI ELECTRICITY | ELECTRICITY CHARGES | 847 |  | 2023-11-28 | 1170
| K.R. ENTERPRISES | TRANSPORTATION CHARGES | 636 |  | 2023-10-01 | 51600
| A1 STAR TRANSPORT | TRANSPORTATION CHARGES | 566 |  | 2023-10-06 | 17000
| K.R. ENTERPRISES | TRANSPORTATION CHARGES | 645 |  | 2023-11-01 | 120400
| PUJARI TRANSPORT | TRANSPORTATION CHARGES | 335 |  | 2023-11-06 | 10000
| A1 STAR TRANSPORT | TRANSPORTATION CHARGES | 583 |  | 2023-11-16 | 30400
| K.R. ENTERPRISES | TRANSPORTATION CHARGES | 655 |  | 2023-12-01 | 8600
| AIWALE ENTERPRISES | TRANSPORTATION CHARGES | 126 |  | 2023-12-01 | 13500
| AIWALE ENTERPRISES | TRANSPORTATION CHARGES | 141 |  | 2023-12-02 | 40500
| VISION TRANSPORT | TRANSPORTATION CHARGES | 268 |  | 2023-12-15 | 27500
| VISION TRANSPORT | TRANSPORTATION CHARGES | 269 |  | 2023-12-15 | 15000
| VISION TRANSPORT | TRANSPORTATION CHARGES | 270 |  | 2023-12-15 | 7500
| VISION TRANSPORT | TRANSPORTATION CHARGES | 276 |  | 2023-12-15 | 22500
| VISION TRANSPORT | TRANSPORTATION CHARGES | 276 |  | 2023-12-15 | 16800
| VISION TRANSPORT | TRANSPORTATION CHARGES | 285 |  | 2023-12-15 | 2400
| VISION TRANSPORT | TRANSPORTATION CHARGES | 286 |  | 2023-12-15 | 1200
| VISION TRANSPORT | TRANSPORTATION CHARGES | 287 |  | 2023-12-15 | 6000
| ABHISHEK KISAN SHINDE | Cooli & Cartage Expenses |  |  | 2023-10-18 | 41802
| ABHISHEK KISAN SHINDE | Cooli & Cartage Expenses |  |  | 2023-11-06 | 31326
| ABHISHEK KISAN SHINDE | Cooli & Cartage Expenses |  |  | 2023-12-01 | 16212
| ABHISHEK KISAN SHINDE | Cooli & Cartage Expenses |  |  | 2023-12-09 | 22435
| SAI SERVICE FACILITY | Security Guards Charges |  |  | 2023-10-06 | 54000
| SAI SERVICE FACILITY | Security Guards Charges |  |  | 2023-11-01 | 54000
| INSURANCE CHARGES |  |  |  | 2023-10-09 | 19116
| SALARY | Cheque No 164777 BEING AMOUNT PAID FOR MAYUR BHOSALE FOR SALARY MONTH OF SEPTEMBER 2023 | 715 |  | 2023-10-03 | 27450
| SALARY | Cheque No 164778 BEING AMOUNT PAID FOR DHAWAL SHAH- FOR SALARY MONTH OF SEPTEMBER 2023 | 716 |  | 2023-10-03 | 46100
| SALARY | Cheque No.164779 BEING AMOUNT PAID FOR RAMESH V SINGH- FOR SALARY MONTH OF SEPTEMBER 23 | 717 |  | 2023-10-03 | 48300
| SALARY | Cheque No 164780 BEING AMOUNT PAID FOR BRIJESH GANDHI- FOR SALARY MONTH OF SEPTEMBER 2023 | 718 |  | 2023-10-03 | 19150
| SALARY | Cheque No 164781 BEING AMOUNT PAID FOR SUNIL MULAY- FOR SALARY MONTH OF SEPTEMBER 2023 | 719 |  | 2023-10-03 | 47250
| SALARY | Cheque No 164782 BEING AMOUNT PAID FOR DHANRAJ VHATKAR- FOR SALARY MONTH OF SEPTEMBER 2023 | 720 |  | 2023-10-03 | 26100
| SALARY | Cheque No 164783 BEING AMOUNT PAID FOR UMESH GANESH THAKUR- FOR SALARY MONTH OF SEPTEMBER 2023 | 721 |  | 2023-10-03 | 41450
| SALARY | Cheque No 164784 BEING AMOUNT PAID FOR MOOLCHAND KEWALASHANKAR YADAV- FOR SALARY MONTH OF SEPTEMBER 2023 | 722 |  | 2023-10-03 | 31400
| SALARY | Cheque No 164795 BEING AMOUNT PAID FOR SHASHIKANT PATEL- FOR SALARY MONTH OF SEPTEMBER 2023 | 723 |  | 2023-10-03 | 32450
| SALARY | Cheque No 164786 BEING AMOUNT PAID FOR RAMESHWAR S HOGADE- FOR SALARY MONTH OF SEPTEMBER 2023 | 724 |  | 2023-10-03 | 29000
| SALARY | CH.NO 164796 SALARY FOR SEPTEMBER 2023 PAID TO AMIT ASHOK PATIL | 725 |  | 2023-10-03 | 42750
| SALARY | Cheque No 164788 BEING AMOUNT PAID FOR MADHUKAR RATHOD- FOR SALARY MONTH OF SEPTEMBER 2023 | 726 |  | 2023-10-03 | 32800
| SALARY | Cheque No 164789 BEING AMOUNT PAID FOR PRATHAMESH LAD - FOR SALARY MONTH OF SEPTEMBER 2023 | 727 |  | 2023-10-03 | 56100
| SALARY | Cheque No 164790 BEING AMOUNT PAID FOR TEJAS RAJENDRA POKHARKAR - FOR SALARY MONTH OF SEPTEMBER 2023 | 728 |  | 2023-10-03 | 31700
| SALARY | Cheque No 164792 BEING AMOUNT PAID FOR YOUR SELF A/C RTGS NAFISA HOZEFA UJJAINWALA - FOR SALARY MONTH OF SEPTEMBER 2023 | 730 |  | 2023-10-03 | 80000
| SALARY | Cheque No 164793 BEING AMOUNT PAID FOR KALU BHIKARI SINGH - FOR SALARY MONTH OF SEPTEMBER 2023 | 731 |  | 2023-10-03 | 23000
| SALARY | Cheque No 164794 BEING AMOUNT PAID FOR FAISAL ABDUL MASJID LAHORI - FOR SALARY MONTH OF SEPTEMBER 2023 | 732 |  | 2023-10-03 | 10000
| SALARY | Cheque No 164814 BEING AMOUNT PAID FOR MAYUR BHOSALE- FOR SALARY MONTH OF OCT- 2023 | 789 |  | 2023-11-01 | 27450
| SALARY | Cheque No 164815 BEING AMOUNT PAID FOR DHAWAL SHAH- FOR SALARY MONTH OF OCT- 2023 | 790 |  | 2023-11-01 | 46100
| SALARY | Cheque No 164816 BEING AMOUNT PAID FOR RAMESH V.SINGH- FOR SALARY MONTH OF OCT- 2023 | 791 |  | 2023-11-01 | 48300
| SALARY | Cheque No 164817 BEING AMOUNT PAID FOR BRIJESH GANDHI- FOR SALARY MONTH OF OCT- 2023 | 792 |  | 2023-11-01 | 19150
| SALARY | Cheque No 164818 BEING AMOUNT PAID FOR SUNIL MULAY- FOR SALARY MONTH OF OCT- 2023 | 793 |  | 2023-11-01 | 47250
| SALARY | Cheque No 164819 BEING AMOUNT PAID FOR DHANRAJ VHATKAR- FOR SALARY MONTH OF OCT- 2023 | 794 |  | 2023-11-01 | 26100
| SALARY | Cheque No 164820 BEING AMOUNT PAID FOR UMESH GANESH THAKUR FOR SALARY MONTH OF OCT- 2023 | 795 |  | 2023-11-01 | 41450
| SALARY | Cheque No 164821 BEING AMOUNT PAID FOR MOOLCHAND KEWALASHANKAR YADAV FOR SALARY MONTH OF OCT- 2023 | 796 |  | 2023-11-01 | 31400
| SALARY | Cheque No 164822 BEING AMOUNT PAID FOR SHASHIKANT PATEL- FOR SALARY MONTH OF OCT- 2023 | 797 |  | 2023-11-01 | 32450
| SALARY | Cheque No 164823 BEING AMOUNT PAID FOR RAMESHWAR S HOGADE- FOR SALARY MONTH OF OCT- 2023 | 798 |  | 2023-11-01 | 29000
| SALARY | Cheque No 164824 BEING AMOUNT PAID FOR MADHUKAR RATHOD- FOR SALARY MONTH OF OCT- 2023 | 799 |  | 2023-11-01 | 32800
| SALARY | Cheque No 164825 BEING AMOUNT PAID FOR PRATHAMESH LAD- FOR SALARY MONTH OF OCT- 2023 | 800 |  | 2023-11-01 | 56100
| SALARY | Cheque No 164827 BEING AMOUNT PAID FOR YOUR SELF A/C RTGS NAFISA HOZEFA UJJAINWALA - FOR MONTH OF OCT- 202 | 801 |  | 2023-11-01 | 80000
| SALARY | Cheque No 164828 BEING AMOUNT PAID FOR KALU BHIKARI SINGH - FOR MONTH OF OCT- 202 | 802 |  | 2023-11-01 | 23000
| SALARY | CH.NO 164875 AMOUNT PAID SHASHI KANT PATEL FOR SALARY MONTH OF NOV 2023 | 3 |  | 2023-12-01 | 32450
| SALARY | CH.NO 164874 AMOUNT PAID MAYUR BHOSALE FOR SALARY MONTH OF NOV 2023 | 4 |  | 2023-12-01 | 27450
| SALARY | CH.NO 164874 AMOUNT PAID DHAWAL SHAH- FOR SALARY MONTH OF NOV 2023 | 5 |  | 2023-12-01 | 46100
| SALARY | CH.NO 164874 AMOUNT PAID RAMESH V SINGH- FOR SALARY MONTH OF NOV 2023 | 6 |  | 2023-12-01 | 48300
| SALARY | CH.NO 164874 AMOUNT PAID BRIJESH GANDHI- FOR SALARY MONTH OF NOV 2023 | 7 |  | 2023-12-01 | 19150
| SALARY | CH.NO 164874 AMOUNT PAID SUNIL MULAY- FOR SALARY MONTH OF NOV 2023 | 8 |  | 2023-12-01 | 47250
| SALARY | CH.NO 164874 AMOUNT PAID DHANRAJ VHATKAR- FOR SALARY MONTH OF NOV 2023 | 9 |  | 2023-12-01 | 26100
| SALARY | CH.NO 164874 AMOUNT PAID MOOL CHAND KEWALASHANKAR YADAV- FOR SALARY MONTH OF NOV 2023 | 11 |  | 2023-12-01 | 31400
| SALARY | CH.NO 164874 AMOUNT PAID RAMESHWAR S HOGADE- FOR SALARY MONTH OF NOV 2023 | 12 |  | 2023-12-01 | 29000
| SALARY | CH.NO 164874 AMOUNT PAID MADHUKAR RATHOD- FOR SALARY MONTH OF NOV 2023 | 13 |  | 2023-12-01 | 32800
| SALARY | CH.NO 164874 AMOUNT PAID PRATHAMESH LAD- FOR SALARY MONTH OF NOV 2023 | 14 |  | 2023-12-01 | 56100
| SALARY | CH.NO 164874 AMOUNT PAID NAFISA HONEFA UJJANWALA FOR SALARY MONTH OF NOV 2023 | 16 |  | 2023-12-01 | 80000
| SALARY | CH.NO 164874 AMOUNT PAID KALU BHIKARI SINGH FOR SALARY MONTH OF NOV 2023 | 17 |  | 2023-12-01 | 23000
| SALARY | CH.NO 164874 AMOUNT PAID UMESH GANESH THAKUR- FOR SALARY MONTH OF NOV 2023 | 146 |  | 2023-12-01 | 41450
| SALARY | CH.NO 164874 AMOUNT PAID UMESH GANESH THAKUR- FOR SALARY MONTH OF NOV 2023 (TRF NEFT FAIL DT 011223 INVALID) | 33 |  | 2023-12-02 | 41450
| SALARY | CH.NO 164879 AMOUNT PAID UMESH GANESH THAKUR- FOR SALARY MONTH OF NOV 2023 | 10 |  | 2023-12-05 | 41450
| BANK CHARGES |  |  |  |  | 94.4
| Coolie and Cartage |  |  |  | 2023-09-30 | 18450
| M.P.WATER SUPPLIER |  |  |  | 31.03.2024 | 5000
| ELECTRICITY CHARGES |  |  |  |  | 77270
| ELECTRICITY CHARGES |  |  |  |  | 910
| ELECTRICITY CHARGES |  |  |  |  | 156207.86
| ELECTRICITY CHARGES |  |  |  |  | 6160
| ELECTRICITY CHARGES |  |  |  |  | 6160
| ELECTRICITY CHARGES |  |  |  |  | 2010
| ELECTRICITY CHARGES |  |  |  |  | 8380
| ELECTRICITY CHARGES |  |  |  |  | 2810
| ABHISHEK KISAN SHINDE | Cooli & Cartage Expenses |  |  |  | 23120
| ABHISHEK KISAN SHINDE | Cooli & Cartage Expenses |  |  |  | 69119
| INSURANCE CHARGES |  |  |  |  | 203777
| SAI SERVICE FACILITY | Security Guards Charges |  |  |  | 54000
| SAI SERVICE FACILITY | Security Guards Charges |  |  |  | 54000
| SAI SERVICE FACILITY | Security Guards Charges |  |  |  | 54000
| SAI SERVICE FACILITY | Security Guards Charges |  |  |  | 54000
| SAI SERVICE FACILITY | Security Guards Charges |  |  |  | 54000
| BANK CHARGES |  |  |  |  | 3850.24
| CGST FEES |  |  |  |  | 425
| INTEREST ON GOVERNMENT DUE |  |  |  |  | 7992
| SGST FEES |  |  |  |  | 425
| SUNDRY BALANCE WRITTEN OFF |  |  |  |  | 20800.57
| SALARY |  |  |  | 2024-01-01 | 32450
| SALARY |  |  |  | 2024-01-01 | 27450
| SALARY |  |  |  | 2024-01-01 | 46100
| SALARY |  |  |  | 2024-01-01 | 48300
| SALARY |  |  |  | 2024-01-01 | 19150
| SALARY |  |  |  | 2024-01-01 | 47250
| SALARY |  |  |  | 2024-01-01 | 26100
| SALARY |  |  |  | 2024-01-01 | 41450
| SALARY |  |  |  | 2024-01-01 | 31400
| SALARY |  |  |  | 2024-01-01 | 29000
| SALARY |  |  |  | 2024-01-01 | 32800
| SALARY |  |  |  | 2024-01-01 | 56100
| SALARY |  |  |  | 2024-01-01 | 80000
| SALARY |  |  |  | 2024-01-01 | 23000
| SALARY |  |  |  | 2024-01-31 | 42750
| SALARY |  |  |  | 2024-02-01 | 32450
| SALARY |  |  |  | 2024-02-01 | 27450
| SALARY |  |  |  | 2024-02-01 | 46100
| SALARY |  |  |  | 2024-02-01 | 48300
| SALARY |  |  |  | 2024-02-01 | 19150
| SALARY |  |  |  | 2024-02-01 | 47250
| SALARY |  |  |  | 2024-02-01 | 26100
| SALARY |  |  |  | 2024-02-01 | 41450
| SALARY |  |  |  | 2024-02-01 | 31400
| SALARY |  |  |  | 2024-02-01 | 29000
| SALARY |  |  |  | 2024-02-01 | 43000
| SALARY |  |  |  | 2024-02-01 | 56100
| SALARY |  |  |  | 2024-02-01 | 80000
| SALARY |  |  |  | 2024-02-01 | 23000
| SALARY |  |  |  | 2024-03-01 | 27450
| SALARY |  |  |  | 2024-03-01 | 46100
| SALARY |  |  |  | 2024-03-01 | 48300
| SALARY |  |  |  | 2024-03-01 | 19150
| SALARY |  |  |  | 2024-03-01 | 47250
| SALARY |  |  |  | 2024-03-01 | 26100
| SALARY |  |  |  | 2024-03-01 | 43000
| SALARY |  |  |  | 2024-03-01 | 56100
| SALARY |  |  |  | 2024-03-01 | 80000
| SALARY |  |  |  | 2024-03-01 | 23000
| SALARY |  |  |  | 2024-03-30 | 27450
| SALARY |  |  |  | 2024-03-30 | 46100
| SALARY |  |  |  | 2024-03-30 | 48300
| SALARY |  |  |  | 2024-03-30 | 19150
| SALARY |  |  |  | 2024-03-30 | 47250
| SALARY |  |  |  | 2024-03-30 | 26100
| SALARY |  |  |  | 2024-03-30 | 43000
| SALARY |  |  |  | 2024-03-30 | 56100
| SALARY |  |  |  | 2024-03-30 | 23000
| A1 STAR TRANSPORT | TRANSPORTATION CHARGES |  |  |  | 20400
| K.R. ENTERPRISES | TRANSPORTATION CHARGES |  |  |  | 17200
| AIWALE ENTERPRISES | TRANSPORTATION CHARGES |  |  |  | 63000
| A1 STAR TRANSPORT | TRANSPORTATION CHARGES |  |  |  | 4400
| K.R. ENTERPRISES | TRANSPORTATION CHARGES |  |  |  | 98900
| AIWALE ENTERPRISES | TRANSPORTATION CHARGES |  |  |  | 22500
| VISION TRANSPORT | TRANSPORTATION CHARGES |  |  |  | 15000
| VISION TRANSPORT | TRANSPORTATION CHARGES |  |  |  | 7200
| VISION TRANSPORT | TRANSPORTATION CHARGES |  |  |  | 40000
| A1 STAR TRANSPORT | TRANSPORTATION CHARGES |  |  |  | 4800
| VISION TRANSPORT | TRANSPORTATION CHARGES |  |  |  | 17500
| A1 STAR TRANSPORT | TRANSPORTATION CHARGES |  |  |  | 8400
| A1 STAR TRANSPORT | TRANSPORTATION CHARGES |  |  |  | 22800
31824677.62

## Interest
Month | Gross Total
2022-07-01 | 37973
2022-08-01 | 591658
2022-09-01 | 544052
2022-10-01 | 582008
2022-11-01 | 524503
2022-12-01 | 549574
2023-01-01 | 574970
2023-02-01 | 826953
2023-03-01 | 1074714
2023-04-01 | 1277271
2023-05-01 | 1060276
2023-06-01 | 1348854
2023-07-31 | 1578723
2023-08-31 | 1606480
2023-09-30 | 1563924
2023-10-31 | 1591724
2023-11-30 | 1530200
2023-12-31 | 1591778
2024-01-31 | 1612451
2024-02-29 | 1507483
2024-03-31 | 1591654
23167223