WORK PROGRESS REPORT

Details of the property under consideration:

Name of Project: “Sheetal Ekta”

"Sheetal Ekta", Proposed Redevelopment of existing building No. 18 – A & B, known as

Dindoshi Ekta CHSL on Plot bearing S. No. 31 & 39, CTS. No. 110(pt.) & 146 (pt.),

Shivdham Complex, Gen. A. K. Vaidya Marg, Village – Dindoshi, Malad (East),

Mumbai – 400 097, State – Maharashtra, Country – India

Latitude Longitude: 19°10'32.1"N 72°51'40.3"E

Intended User:

State Bank of India

SME Chembur Branch

Unit No. 11, Building No. 11, Ground Floor, Corporate Park, Sion Trombay Road,

Chembur, Mumbai, Pin Code – 400 071, State - Maharashtra, Country – India

Vastu/SBI/Mumbai/06/2024/9380/2305872

02/10-11-PY

Date: - 19.06.2024

WORK PROGRESS REPORT

To,

State Bank of India

SME Chembur Branch

Unit No. 11, Building No. 11,

Ground Floor, Corporate Park,

Sion Trombay Road, Chembur,

Mumbai, Pin Code – 400 071,

State - Maharashtra, Country – India

Subject: Construction of Proposed Redevelopment of existing building No. 18 – A & B, known as Dindoshi Ekta CHSL on Plot bearing S. No. 31 & 39, CTS. No. 110(pt.) & 146 (pt.), Shivdham Complex, Gen. A. K. Vaidya Marg, Village – Dindoshi, Malad (East), Mumbai – 400 097, State – Maharashtra, Country – India.

Ref: You’re Request for Work Progress Report of under Construction Building.

Dear Sir,

- As per your instruction, we have inspected the under-construction Rehab and Sale Building project situated on plot bearing C S. No. 31 & 39, CTS. No. 110(pt.) & 146 (pt.), Shivdham Complex, Gen. A. K. Vaidya Marg, Village – Dindoshi, Malad (East), Mumbai – 400 097, State – Maharashtra, Country – India which is being developed by M/s. DGS Township Pvt. Ltd. in order to give the physical progress at site.

- The Construction work as per approved plan was in progress during the site visit on 17th June 2024.

- Status of work:

- For Sales Building (Wing A & B): 12th floor slab work is completed, Ground to 3rd Floor, Blockwork, plaster work, tiling, flooring, door and windows, electrical work, plumbing work, painting, firefighting, lift work are completed (Applied for OC). 4th to 6th floor block work is completed. 13h floor slab work is in progress.

- Overall Physical progress of the sale building construction as on 17/06/2024 is 30.23% as per physical site inspection.

- Overall Physical progress of the sale building construction including Mivan Material & Other Material on Site as on 17/06/2024 is 32.15%.

Manoj B. Chalikwar

Registered Valuer

Chartered Engineer (India)

Reg. No. IBBI/RV/07/2018/10366

Encl.: Report

WORK PROGRESS REPORT

OF

"SHEETAL EKTA"

"Sheetal Ekta", Proposed Redevelopment of existing building No. 18 – A & B, known as Dindoshi Ekta CHSL on Plot bearing S. No. 31 & 39, CTS. No. 110(pt.) & 146 (pt.), Shivdham Complex, Gen. A. K. Vaidya Marg, Village – Dindoshi, Malad (East), Mumbai – 400 097, State – Maharashtra, Country – India

Latitude Longitude: 19°10'32.1"N 72°51'40.3"E

NAME OF DEVELOPER: M/s. DGS Township Pvt. Ltd.

Pursuant to instructions from State of India, SME Chembur Branch, Chembur we have duly visited, inspected, surveyed & assessed the above said property on 17th June 2024 to determine the work progress of the said property/project. 1. Location Details: Proposed Redevelopment of existing building No. 18 – A & B, known as Dindoshi Ekta CHSL on Plot bearing S. No. 31 & 39, CTS. No. 110(pt.) & 146 (pt.), Shivdham Complex, Gen. A. K. Vaidya Marg, Village – Dindoshi, Malad (East), Mumbai – 400 097. It is about 2.60 Km. travelling distance from Malad (East) Railway station. Surface transport to the property is by buses, taxis & private vehicles. The property is in developed locality. All the amenities like shops, banks, hotels, markets, schools, hospitals, etc. are all available in the surrounding locality. The area is higher middle class & developed.

2. Developer Details:

| Name of builder | M/s. DGS Township Pvt. Ltd. |
| --- | --- |
| Project Rera Registration Number | P51800051884 |
| Registered office address | DGS house, 1st floor, Sheetal Krupa, Aarey Road, Walawalkar Street, Goregaon (E), Mumbai – 400 063, State - Maharashtra, Country – India |
| Contact details | Contact Person: Mr. Prabudh Khandelwal (Consultants) Mobile No. 7738001775 Mr. Deep Shah (Consultants) Mobile No. 7977861026 |
| E – mail ID and website |  |

3. 	Boundaries of the Property:

| Direction | Particulars |
| --- | --- |
| On or towards North | Aster Tower |
| On or towards South | Road & Omkar CHSL |
| On or towards East | Sagar Society |
| On or towards West | Khatu Shyam Mandir Road |

# Level of Construction

For Rehab cum Sales Building (Wing A & B): 12th floor slab work is completed, Ground to 3rd Floor, Blockwork, plaster work, tiling, flooring, door and windows, electrical work, plumbing work, painting, firefighting, lift work are completed (Applied for OC). 4th to 6th floor block work is completed. 13h floor slab work is in progress.

# Sales Building (Wing A & B)

| Sr. | Floor No. | Construction Area in Sq. M. | Completed Area in Sq. M. | Work Completion as on 17.06.2024 |
| --- | --- | --- | --- | --- |
| 1 | Excavation & Shore Piling |  |  | Work is completed |
| 2 | Basement Floor | 438.74 | 438.74 | Slab work is completed |
| 3 | Ground Floor | 486.07 | 486.07 | Slab work, block work, plaster work, flooring, tiling work, electrical & plumbing, door & windows, painting, firefighting & lift work are completed (Applied for OC) |
| 4 | 1st Floor | 514.07 | 514.07 |  |
| 5 | 2nd Floor | 514.07 | 514.07 |  |
| 6 | 3rd Floor | 514.07 | 514.07 |  |
| 7 | 4th Floor | 459.08 | 459.08 | Slab work & Block work are completed |
| 8 | 5th Floor | 459.08 | 459.08 |  |
| 9 | 6th Floor | 465.64 | 465.64 |  |
| 10 | 7th Floor | 459.08 | 459.08 | Slab work is completed |
| 11 | 8th Floor | 459.08 | 459.08 |  |
| 12 | 9th Floor | 459.08 | 459.08 |  |
| 13 | 10th Floor | 459.08 | 459.08 |  |
| 14 | 11th Floor | 459.08 | 459.08 |  |
| 15 | 12th Floor | 459.08 | 459.08 |  |
| 16 | 13th Floor | 465.64 |  |  |
| 17 | 14th Floor | 459.08 |  |  |
| 18 | 15th Floor | 459.08 |  |  |
| 19 | 16th Floor | 459.08 |  |  |
| 20 | 17th Floor | 459.08 |  |  |
| 21 | 18th Floor | 459.08 |  |  |
| 22 | 19th Floor | 459.08 |  |  |
| 23 | 20th Floor | 468.19 |  |  |
| 24 | 21st Floor | 459.08 |  |  |
| 25 | 22nd Floor | 459.08 |  |  |
| 26 | 23rd Floor | 459.08 |  |  |
| 27 | 24th Floor | 460.45 |  |  |
| 28 | 25th Floor | 460.45 |  |  |
| 29 | 26th Floor | 460.45 |  |  |
| 30 | 27th Floor | 467.98 |  |  |
| 31 | 28th Floor | 462.33 |  |  |
| 32 | 29th Floor | 462.33 |  |  |
| 33 | 30th Floor | 462.33 |  |  |
| 34 | 31st Floor | 462.33 |  |  |
| 35 | 32nd Floor | 462.33 |  |  |
| 36 | 33rd Floor | 459.65 |  |  |
| 37 | Terrace Floor / OHT / LMR | 114.39 |  |  |
| Total |  | 16,405.79 | 6,605.25 |  |

# Cost of Construction as on 17th June 2024

# Rehab cum Sales Building (Wing A & B)

| Sr. | Floor | Total Construction Area in Sq. M. | Completed Area in Sq. Ft. | Rate per Sq. Ft. | Full Value after completion | % of work completed | Actual Expenditure till date in ` |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Excavation Cost |  |  |  | 24,608,686.00 | 100% | 24,608,686.00 |
| 2 | Basement Floor | 438.74 | 438.74 | 30,000.00 | 13,162,092.00 | 98% | 1,28,98,850.16 |
| 3 | Ground Floor | 486.07 | 486.07 | 30,000.00 | 14,581,992.00 | 98% | 1,42,90,352.16 |
| 4 | 1st Floor | 514.07 | 514.07 | 30,000.00 | 15,421,992.00 | 98% | 1,51,13,552.16 |
| 5 | 2nd Floor | 514.07 | 514.07 | 30,000.00 | 15,421,992.00 | 98% | 1,51,13,552.16 |
| 6 | 3rd Floor | 514.07 | 514.07 | 30,000.00 | 15,421,992.00 | 98% | 1,51,13,552.16 |
| 7 | 4th Floor | 459.08 | 459.08 | 30,000.00 | 13,772,292.00 | 65% | 89,51,989.80 |
| 8 | 5th Floor | 459.08 | 459.08 | 30,000.00 | 13,772,292.00 | 65% | 89,51,989.80 |
| 9 | 6th Floor | 465.64 | 465.64 | 30,000.00 | 13,969,200.00 | 65% | 90,79,980.00 |
| 10 | 7th Floor | 459.08 | 459.08 | 30,000.00 | 13,772,292.00 | 60% | 82,63,375.20 |
| 11 | 8th Floor | 459.08 | 459.08 | 30,000.00 | 13,772,292.00 | 60% | 82,63,375.20 |
| 12 | 9th Floor | 459.08 | 459.08 | 30,000.00 | 13,772,292.00 | 60% | 82,63,375.20 |
| 13 | 10th Floor | 459.08 | 459.08 | 30,000.00 | 13,772,292.00 | 60% | 82,63,375.20 |
| 14 | 11th Floor | 459.08 | 459.08 | 30,000.00 | 13,772,292.00 | 60% | 82,63,375.20 |
| 15 | 12th Floor | 459.08 | 459.08 | 30,000.00 | 13,772,292.00 | 55% | 75,74,760.60 |
| 16 | 13th Floor | 465.64 |  | 30,000.00 | 13,969,200.00 |  |  |
| 17 | 14th Floor | 459.08 |  | 30,000.00 | 13,772,292.00 |  |  |
| 18 | 15th Floor | 459.08 |  | 30,000.00 | 13,772,292.00 |  |  |
| 19 | 16th Floor | 459.08 |  | 30,000.00 | 13,772,292.00 |  |  |
| 20 | 17th Floor | 459.08 |  | 30,000.00 | 13,772,292.00 |  |  |
| 21 | 18th Floor | 459.08 |  | 30,000.00 | 13,772,292.00 |  |  |
| 22 | 19th Floor | 459.08 |  | 30,000.00 | 13,772,292.00 |  |  |
| 23 | 20th Floor | 468.19 |  | 30,000.00 | 14,045,700.00 |  |  |
| 24 | 21st Floor | 459.08 |  | 30,000.00 | 13,772,292.00 |  |  |
| 25 | 22nd Floor | 459.08 |  | 30,000.00 | 13,772,292.00 |  |  |
| 26 | 23rd Floor | 459.08 |  | 30,000.00 | 13,772,292.00 |  |  |
| 27 | 24th Floor | 460.45 |  | 30,000.00 | 13,813,500.00 |  |  |
| 28 | 25th Floor | 460.45 |  | 30,000.00 | 13,813,500.00 |  |  |
| 29 | 26th Floor | 460.45 |  | 30,000.00 | 13,813,500.00 |  |  |
| 30 | 27th Floor | 467.98 |  | 30,000.00 | 14,039,400.00 |  |  |
| 31 | 28th Floor | 462.33 |  | 30,000.00 | 13,869,900.00 |  |  |
| 32 | 29th Floor | 462.33 |  | 30,000.00 | 13,869,900.00 |  |  |
| 33 | 30th Floor | 462.33 |  | 30,000.00 | 13,869,900.00 |  |  |
| 34 | 31st Floor | 462.33 |  | 30,000.00 | 13,869,900.00 |  |  |
| 35 | 32nd Floor | 462.33 |  | 30,000.00 | 13,869,900.00 |  |  |
| 36 | 33rd Floor | 459.65 |  | 30,000.00 | 13,789,500.00 |  |  |
| 37 | Terrace / OHT | 114.39 |  | 30,000.00 | 3,431,700.00 |  |  |
| 38 | Sub Total | 16,405.79 | 4,309.87 |  | 516,782,410.00 | 33.48% | 17,30,14,141.00 |
| 39 | Parking | 111.00 |  | 500,000.00 | 55,500,000.00 |  |  |
| TOTAL |  | 16,405.79 | 4,309.87 |  | 572,282,410.00 | 30.23% | 17,30,14,141.00 |
| Mavin & Other Material on Site |  |  |  |  |  |  | 1,10,00,000.00 |

##### Note: Details of work completed is as per site visit dated 17.06.2024

Actual Site Photographs As on 17.06.2024

Actual Site Photographs As on 17.06.2024

Actual Site Photographs As on 17.06.2024

Actual Site Photographs As on 17.06.2024

Actual Site Photographs As on 17.06.2024

Route Map of the property

Site u/r

## Latitude Longitude: 19°10'32.1"N 72°51'40.3"E

Note: The Blue line shows the route to site from nearest railway station (Malad– 2.60 Km.)