## Final Summary
Project expenses | Estimated Cost as per Cost Vetting | Incurred Cost as per CA for wing A & B till 30.06.2024 | Incurred Cost as per CA for wing C till 30.06.2024 | TOTAL Incurred Cost as per CA till 30.06.2024 | Incurred Cost as per CA till 31.07.2023 | Difference between both CA | Remark
Land Cost | 0 | 0 | 0 | 0
Rent Cost | 8.29 | 4.3261 | 0.8334 | 5.1595
Construction Cost of Rehab Building | 26.24 | 7.5547 | 3.7774 | 11.3321
Construction Cost of Sale Building | 51.54 | 11.4024 | 1.2864 | 12.6888
Approval Cost | 33.93 | 8.8689 | 3.1624 | 12.0313
Professional Charges | 3.89 | 3.9868 | 1.7999 | 5.7867
Admin Cost | 3.11
Marketing Cost | 7.3
Interest Cost | 10.01 | 0.057497 | 0.0092964 | 0.066794
Contingency Cost | 2.33 | 0 | 0 | 0
Total Cost | 146.64 | 36.1964 | 10.8688 | 47.0652 | 0 | 0
99.5748
Particulars | Estimated Cost (in Cr.) | TOTAL Incurred Cost as per CA till 30.06.2024 | Cost incurred as %age total cost of that Component | Cost incurred as %age of cost incurred as CA Certificate
Land Cost | 0 | 0 | #DIV/0! | 0%
Rent Cost | 8.29 | 5.1595 | 62.24% | 3.518%
Construction Cost of Rehab Building | 26.24 | 11.3321 | 43.19% | 7.728%
Construction Cost of Sale Building | 51.54 | 12.6888 | 24.62% | 8.653%
Approval Cost | 33.93 | 12.0313 | 35.46% | 8.205%
Professional Charges | 3.89 | 5.7867 | 40.47% | 3.946%
Admin Cost | 3.11
Marketing Cost | 7.3
Interest Cost | 10.01 | 0.066794 | 0.6673% | 0.04555%
Contingency Cost | 2.33 | 0 | 0% | 0%
Total | 146.64 | 47.0652 | 32.1% | 32.1%

## Plinth Area Calculation
REHAB BUILDING
Sr. | Floor | Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | % of work completed | Actual Expenditure till date in `
1 | Excavation Cost |  |  |  | 23856093 | 100% | 23856093
2 | Ground Floor | 421.88 | 421.88 | 27000 | 11390760 | 50% | 5695380
3 | 1st Floor | 421.87 | 421.87 | 27000 | 11390490 | 75% | 8542867.5
4 | 2nd Floor | 421.87 | 421.87 | 27000 | 11390490 | 75% | 8542867.5
5 | 3rd Floor | 421.88 | 421.88 | 27000 | 11390760 | 75% | 8543070
6 | 4th Floor | 421.88 | 421.88 | 27000 | 11390760 | 75% | 8543070
7 | 5th Floor | 421.88 | 421.88 | 27000 | 11390760 | 75% | 8543070
8 | 6th Floor | 421.88 | 421.88 | 27000 | 11390760 | 75% | 8543070
9 | 7th Floor | 421.88 | 421.88 | 27000 | 11390760 | 75% | 8543070
10 | 8th Floor | 421.88 | 421.88 | 27000 | 11390760 | 75% | 8543070
11 | 9th Floor | 421.88 | 421.88 | 27000 | 11390760 | 75% | 8543070
12 | 10th Floor | 421.88 | 421.88 | 27000 | 11390760 | 65% | 7403994
13 | 11th Floor | 421.88 | 421.88 | 27000 | 11390760 | 65% | 7403994
14 | 12th Floor | 421.88 | 421.88 | 27000 | 11390760 | 65% | 7403994
15 | 13th Floor | 421.88 | 421.88 | 27000 | 11390760 | 65% | 7403994
16 | 14th Floor | 485.61 | 485.61 | 27000 | 13111470 | 65% | 8522455.5
17 | 15th Floor | 358.15 | 358.15 | 27000 | 9670050 | 65% | 6285532.5
18 | 16th Floor | 421.88 | 421.88 | 27000 | 11390760 | 65% | 7403994
19 | 17th Floor | 421.88 | 421.88 | 27000 | 11390760 | 65% | 7403994
20 | 18th Floor | 421.88 | 421.88 | 27000 | 11390760 | 50% | 5695380
21 | 19th Floor | 421.88 | 421.88 | 27000 | 11390760 | 50% | 5695380
22 | 20th Floor | 358.15 | 358.15 | 27000 | 9670050 | 50% | 4835025
23 | OHT / LMR | 39.86 |  | 27000 | 1076220 |  | 0
TOTAL |  | 8835.59 | 8795.73 |  | 262417023 | 69.32% | 181896435
SALE BUILDING (WING A & B)
Sr. | Floor | Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | % of work completed | Actual Expenditure till date in `
1 | Excavation Cost |  |  |  | 27753180 | 100% | 27753180
2 | Ground Floor | 437.59 | 437.59 | 30000 | 13127700 | 50% | 6563850 | 218.8
3 | 1st Floor | 437.59 | 437.59 | 30000 | 13127700 | 68% | 8926836 | 218.7967
4 | 2nd Floor | 437.59 | 437.59 | 30000 | 13127700 | 68% | 8926836
5 | 3rd Floor | 437.59 | 437.59 | 30000 | 13127700 | 68% | 8926836
6 | 4th Floor | 437.59 | 437.59 | 30000 | 13127700 | 68% | 8926836
7 | 5th Floor | 437.59 | 437.59 | 30000 | 13127700 | 68% | 8926836
8 | 6th Floor | 437.59 | 437.59 | 30000 | 13127700 | 68% | 8926836
9 | 7th Floor | 437.59 | 437.59 | 30000 | 13127700 | 68% | 8926836
10 | 8th Floor | 437.59 | 437.59 | 30000 | 13127700 | 68% | 8926836
11 | 9th Floor | 437.59 | 437.59 | 30000 | 13127700 | 68% | 8926836
12 | 10th Floor | 437.59 | 437.59 | 30000 | 13127700 | 68% | 8926836
13 | 11th Floor | 437.59 | 437.59 | 30000 | 13127700 | 68% | 8926836
14 | 12th Floor | 437.59 | 437.59 | 30000 | 13127700 | 68% | 8926836
15 | 13th Floor | 437.59 | 437.59 | 30000 | 13127700 | 68% | 8926836
16 | 14th Floor | 437.59 | 437.59 | 30000 | 13127700 | 68% | 8926836
17 | 15th Floor | 437.59 | 437.59 | 30000 | 13127700 | 68% | 8926836
18 | 16th Floor | 437.59 | 437.59 | 30000 | 13127700 | 68% | 8926836
19 | 17th Floor | 437.59 | 437.59 | 30000 | 13127700 | 68% | 8926836
20 | 18th Floor | 437.59 | 437.59 | 30000 | 13127700 | 68% | 8926836
21 | 19th Floor | 437.59 | 437.59 | 30000 | 13127700 | 68% | 8926836
22 | 20th Floor | 437.59 | 437.59 | 30000 | 13127700 | 68% | 8926836 |  | 30.8367
23 | OHT / LMR | 61.67 |  | 30000 | 1850100 |  | 0 |  | 61.6733
SUB - TOTAL |  | 9251.06 | 9189.39 |  | 305284980 | 69.72% | 212853750
24 | Stack Parking | 77 |  | 500000 | 38500000 |  | 0 |  | 38.3333
TOTAL |  |  |  |  | 343784980 | 61.91% | 212853750 |  | 76.6667
115
SALE BUILDING (WING C)
Sr. | Floor | Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | % of work completed | Actual Expenditure till date in `
1 | Excavation Cost |  |  |  | 13876920 | 100% | 13876920
2 | Ground Floor | 218.8 | 218.8 | 30000 | 6564000 | 50% | 3282000
3 | 1st Floor | 218.8 | 218.8 | 30000 | 6564000 | 50% | 3282000
4 | 2nd Floor | 218.8 | 218.8 | 30000 | 6564000 | 50% | 3282000
5 | 3rd Floor | 218.8 | 218.8 | 30000 | 6564000 | 50% | 3282000
6 | 4th Floor | 218.8 | 218.8 | 30000 | 6564000 | 50% | 3282000
7 | 5th Floor | 218.8 |  | 30000 | 6564000 |  | 0
8 | 6th Floor | 218.8 |  | 30000 | 6564000 |  | 0
9 | 7th Floor | 218.8 |  | 30000 | 6564000 |  | 0
10 | 8th Floor | 218.8 |  | 30000 | 6564000 |  | 0
11 | 9th Floor | 218.8 |  | 30000 | 6564000 |  | 0
12 | 10th Floor | 218.8 |  | 30000 | 6564000 |  | 0
13 | 11th Floor | 218.8 |  | 30000 | 6564000 |  | 0
14 | 12th Floor | 218.8 |  | 30000 | 6564000 |  | 0
15 | 13th Floor | 218.8 |  | 30000 | 6564000 |  | 0
16 | 14th Floor | 218.8 |  | 30000 | 6564000 |  | 0
17 | 15th Floor | 218.8 |  | 30000 | 6564000 |  | 0
18 | 16th Floor | 218.8 |  | 30000 | 6564000 |  | 0
19 | 17th Floor | 218.8 |  | 30000 | 6564000 |  | 0
20 | 18th Floor | 218.8 |  | 30000 | 6564000 |  | 0
21 | 19th Floor | 218.8 |  | 30000 | 6564000 |  | 0
22 | 20th Floor | 218.8 |  | 30000 | 6564000 |  | 0
23 | OHT / LMR | 30.84 |  | 30000 | 925200 |  | 0
SUB - TOTAL |  | 4625.64 | 1094 |  | 152646120 | 19.84% | 30286920
24 | Stack Parking | 38 |  | 500000 | 19000000 |  | 0
TOTAL |  |  |  |  | 171646120 | 17.64% | 30286920

## Sheet2
Stagewise pecentage of work completion
Sr. | Particulars | Percentage
| Extra 10% for Excavation & Piling Work | 10 | 9.091%
1 | RCC Footing/Foundation | 5 | 4.545% | 1.6667 | 3.3333
2 | RCC Plinth | 5 | 4.545% | 1.6667 | 3.3333
3 | Full Building RCC | 40 | 36.36% | 13.3333 | 26.6667
4 | Internal Brick work | 7 | 6.364% | 2.3333 | 4.6667
5 | External Brickwork | 7 | 6.364% | 2.3333 | 4.6667
6 | Internal plastering | 3.5 | 3.182% | 1.1667 | 2.3333
7 | External plastering | 3.5 | 3.182% | 1.1667 | 2.3333
8 | Doors & Windows | 5 | 4.545% | 1.6667 | 3.3333
9 | Flooring, Tiling, Kitchen Platform | 10 | 9.091% | 3.3333 | 6.6667
10 | Internal painting | 1.5 | 1.364% | 0.5 | 1
11 | External painting | 1.5 | 1.364% | 0.5 | 1
12 | Electrification, plumbing & Sanitary installation | 5 | 4.545% | 1.6667 | 3.3333
13 | Lift Installation | 2 | 1.818% | 0.66667 | 1.3333
14 | Passage, Staircase & Lobby development | 2 | 1.818% | 0.66667 | 1.3333
15 | External developments / Final finishing work | 2 | 1.818% | 0.66667 | 1.3333
|  | 110 | 100%