## Final Summary
Project expenses | Estimated Cost as per Cost Vetting | Incurred Cost as per Bill till 30.06.2024 | Incurred Cost as per CA till 30.06.2024 | Incurred Cost as per Bill till 31.03.2024 | Incurred Cost as per CA till 31.03.2024 | Difference between the Bills & CA | Difference between both the Bills | Difference between both CA | Remark
Land Cost | 0.38 | 0.38139 | 0.44 | 0.38139 | 0.44 | -0.05861 | 0 | 0
Rent Cost | 11.26 | 10.5682 | 10.58 | 10.5682 | 10.58 | -0.01184 | 0 | 0
Construction Cost of Rehab & Amenity Building | 30.97 | 57.6196 | 58.4 | 52.9171 | 53.76 | -0.78036 | 4.7025 | 4.64
Construction Cost of Sale Building | 85.33
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 13 | 15.5243 | 14.82 | 13.1872 | 12.23 | 0.70426 | 2.3371 | 2.59
Architect Cost, RCC & other Professional fees | 2.33 | 1.1474 | 1.16 | 1.1013 | 1.12 | -0.01262 | 0.04609 | 0.04
Administrative Expenses | 1.16 | 3.7861 | 3.42 | 3.3181 | 3.26 | 0.75988 | 0.46806 | 0.16
Marketing Expences | 5.07 | 0.39374 |  | 0.39374 |  |  | 0
Interest Cost | 4 | 1.5866 | 1.59 | 0.97718 | 0.98 | -0.0034135 | 0.60941 | 0.61
Contingency Cost | 1.74 | 0 | 1.37 | 0 | 1.37 | -1.37 | 0 | 0
Total Cost | 155.24 | 91.0073 | 91.78 | 82.8441 | 83.74 | -0.77271 | 8.1632 | 8.04
|  | 64.2327 | -0.77271
Particulars | Revised Estimated Cost (in Cr.) | 30.06.2024 as per Bill Tally (inclusive of GST) | Cost incurred as %age total cost of that Component | Cost incurred as %age of cost incurred as on 30.06.2024
Land Cost | 0.38 | 0.38139 | 100.4% | 0.2457%
Rent Cost | 11.26 | 10.5682 | 93.86% | 6.808%
Construction Cost of Rehab & Amenity Building | 30.97 | 57.6196 | 49.54% | 37.12%
Construction Cost of Sale Building | 85.33
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 13 | 15.5243 | 119.4% | 10%
Architect Cost, RCC & other Professional fees | 2.33 | 1.1474 | 49.24% | 0.7391%
Administrative Expenses | 1.16 | 3.7861 | 326.4% | 2.439%
Marketing Expences | 5.07 | 0.39374 | 7.766% | 0.2536%
Interest Cost | 4 | 1.5866 | 39.66% | 1.022%
Contingency Cost | 1.74 | 0 | 0% | 0%
Total | 155.24 | 91.0073 | 58.62% | 58.62%
Pariculars | 30.06.2024 as per Bill Tally (inclusive of GST) | 31.03.2024 as per Bill Tally (inclusive of GST) | Difference b/w bills of 31.03.2024 & 30.06.2024 | Difference of Cost incurred as %age of cost incurred as on 31.03.2024 & 30.06.2024
Land Cost | 0.38139 | 0.38139 | 0 | 0%
Rent Cost | 10.5682 | 10.5682 | 0 | 0%
Construction Cost of Rehab & Amenity Building | 57.6196 | 52.9171 | 4.7 | 5.164%
Construction Cost of Sale Building
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 15.5243 | 13.1872 | 2.34 | 2.571%
Architect Cost, RCC & other Professional fees | 1.1474 | 1.1013 | 0.05 | 0.05494%
Administrative Expenses | 3.7861 | 3.3181 | 0.47 | 0.5164%
Marketing Expences | 0.39374 | 0.39374 | 0 | 0%
Interest Cost | 1.5866 | 0.97718 | 0.61 | 0.6703%
Contingency Cost | 0 | 0 | 0 | 0%
Total | 91.0073 | 82.8441 | 8.16 | 8.966%

## Summary Sheet
Sr. No. | Particulars | Incurred Cost in ` till 30.06.2024 | Incurred Cost in ` Cr. Till 30.06.2024 | Incurred Cost in ` till 31.03.2024 | Incurred Cost in ` Cr. Till 31.03.2024 | Balance | Balance in Cr.
1 | Land Cost | 3813900 | 0.38139 | 3813900 | 0.38139 | 0 | 0
2 | Rent Cost | 105681600 | 10.5682 | 105681600 | 10.5682 | 0 | 0
3 | Construction Cost of Rehab & Amenity Building | 576196382 | 57.6196 | 529171155 | 52.9171 | 47025227 | 4.7025
4 | Construction Cost of Sale Building | [6 empty] | 127278700 | 36.9467
5 | Approval Cost & Stamp Duty | 155242571 | 15.5243 | 131871784 | 13.1872 | 23370787 | 2.3371
6 | Professional Cost | 11473801 | 1.1474 | 11012901 | 1.1013 | 460900 | 0.04609
7 | Admin Cost | 37861391.85 | 3.7861 | 33180742.03 | 3.3181 | 4680649.82 | 0.46806
8 | Marketing Cost | 3937434 | 0.39374 | 3937434 | 0.39374 | 0 | 0
9 | Interest Cost | 15865865 | 1.5866 | 9771780 | 0.97718 | 6094085 | 0.60941
| Total | 910072944.85 | 91.0073 | 828441296.03 | 82.8441 | 81631648.82 | 8.1632
40000000
24134135

## Land, Stamp Duty and rent cost
Stamp Duty & Registration Fees
[6 empty] | 12 | Rent per Year (Jan to Jun 24) | #REF! | Rupees
Sr. No. | Agreement Name | Date | Particulars | Total Cost in ` | Incurred Cost in ` | 13 | Rent for Full Loft per Tenant | 60000 | Rupees
1 | Agreement for Sale | 24.12.2020 | Stamp Duty | 3106500 | 3106500 | 14 | Rent for Full Loft | #REF! | Rupees
2 |  |  | Reg. Fees | 30000 | 30000 | 15 | Rent for Half Loft per tenant | 15000 | Rupees
3 |  |  |  | 7700 | 7700 | 16 | Rent for Half Loft | #REF! | Rupees
4 | Rectification Deed | 05.07.2021 | Stamp Duty | 40000 | 40000 | 17 | Shifting Cost per Tenant | 20000 | Rupees
5 |  |  | Reg. Fees | 30000 | 30000 | 18 | Shifting Cost | #REF! | Rupees
6 |  |  |  | 9800 | 9800 | 19 | Brokerage Cost | #REF! | Rupees
7 | Power of Attorney | 22.01.2021 | Stamp Duty | 500 | 500 | 20 | Ownership Cost | 1250000 | Rupees
8 |  |  | Reg. Fees | 100 | 100 |  | TOTAL RENT COST | #REF! | Rupees
9 |  |  |  | 800 | 800
10 | Surrender Deed | 02.01.2023 | Purchase Cost | 550000 | 550000
11 |  |  | Stamp Duty | 38500 | 38500
| TOTAL |  |  | 3813900 | 3813900

## Rent Cost
|  |  | Till August 2023 |  | 2023-09-01 | Oct - Dec 2023 | Jan - March 24
1 | Abhay Y. Ayre | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
2 | Ajay Pandurang Sawant | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
3 | Ajit Keshav Naik | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
4 | Ajit L. Rathod | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
5 | Amruta Ashok Bhagat | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
6 | Amruta Ashok Bobhate | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
7 | Anil Babu Nikam | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
8 | Anil Madhukar Sawant | COMPENSATION | 17000 | 85000 | 17000 | 51000 | 162000 | 332000
9 | Anita Prakash Bhangle | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
10 | Aparna Anil Sawant | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
11 | Aruna Namdev Malap | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
12 | Asaram R.Yadav | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
13 | Asha Vishwanath Parkar | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
14 | ASHOK ANANT SAWANT | COMPENSATION | 34000 | 0 | 0 | 0 | 162000 | 196000
15 | Ashok R Narkar | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
16 | Bapu B. Shelte | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
17 | Benny Thomas | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
18 | Bhakti Chittaranjan Shetye | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
19 | Bhikaji yashwant keluskar | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
20 | Bhujang Vaiju Patil | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
21 | Chandrakant Deu Dhumak | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
22 | Chandrakant P. Dalvi | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
23 | Chandrakant R. Agre | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
24 | Dashrath G. More | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
25 | Datta Damodar Sawant | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
26 | Datta Laxman Sardesai Pednekar | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
27 | Deepak S. Alave | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 192600 | 684600
28 | Dilip Motiram Kokate | COMPENSATION | 418400 | 102000 | 20400 | 61200 | 162000 | 764000
29 | Dinesh Yashwant Patil | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
30 | Dipa Deepak Sawant | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
31 | Dipesh B. Joshi | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
32 | Ganesh Jagannath Parab | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
33 | Ganesh Manohar Sawant | COMPENSATION | 339000 | 102000 | 17000 | 51000 | 162000 | 671000
34 | Geeta N.Patil | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
35 | Geeta S. Tawde | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
36 | Gowda Lata Kempa | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
37 | Jayshree Madhukar Sawant | COMPENSATION | 322000 | 0 | 0 | 0 | 162000 | 484000
38 | Jyoti Janardhan Deshprabhu | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
39 | Kamal Shashikant Khadtare | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
40 | Kamraj Ramchandra Belure | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
41 | Kanchan Mahadev Kanade | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
42 | Keshav Budhaji Kanade | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
43 | Kiran Kashinath Thoravade | COMPENSATION | 319000 | 85000 | 17000 | 51000 | 162000 | 634000
44 | Kiran Ravindranath Chavan | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
45 | Kishor Gopichand Chavan | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
46 | Kishor Vishnu Bane | COMPENSATION | 364000 | 85000 | 17000 | 34000 | 162000 | 662000
47 | Kunal Ravindranath Chavan | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
48 | Kusum Dattaram Bhingarde | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
49 | Laxman N.Salunkhe | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
50 | Laxmi B. Dalvi | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
51 | Laxmi Vishwas Matkar | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
52 | Madhuri Subhash Salshingekar | COMPENSATION | 279000 | 85000 | 17000 | 51000 | 162000 | 594000
53 | Mahendra Eknath Sawant | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
54 | Mahesh Parshuram Dhumak | COMPENSATION | 364000 | 85000 | 17000 | 68000 | 162000 | 696000
55 | Malati Madhukar Vanzare | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
56 | Mangesh Babu Naik | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
57 | Mangesh Mohan Girkar | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
58 | Mangesh Shankar Pimpalkar | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
59 | Manjiri Mangesh Anjarlekar | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
60 | Manoj Shivaji Dalvi | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
61 | Manoj Tatyarao Mahamunakar | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
62 | Manorama Anant Sawant | COMPENSATION | 294000 | 68000 | 17000 | 51000 | 162000 | 592000
63 | Milind Raghunath Patole | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
64 | Mohan Shantaram Surve | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 324000 | 816000
65 | Munindar Lalamani Bind | COMPENSATION | 319000 | 88400 | 17000 | 51000 | 162000 | 637400
66 | Muralidevi S. Gupta - 165 | COMPENSATION | 339000 | 153000 | 17000 | 34000 | 162000 | 705000
67 | Muralidevi S. Gupta - 166 | COMPENSATION | 279000 | 17000 | 17000 | 0 | 162000 | 475000
68 | Namdev Dagadu Bhusare Patil | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
69 | Nandkishor A Shirke | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
70 | Narayan Shankar Bandekar | COMPENSATION | 304000 | 85000 | 17000 | 51000 | 162000 | 619000
71 | Narayan Vijay Kudalkar | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
72 | Naresh Namdeo Parab | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
73 | Narhari Ranganath Madkaikar | COMPENSATION | 319000 | 85000 | 17000 | 51000 | 162000 | 634000
74 | NILAM DHYANESHWAR SAWANT | COMPENSATION | 398000 | 85000 | 17000 | 51000 | 162000 | 713000
75 | Niranjan Bhalchandra Kadam | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
76 | Nitin S. Galave | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 182700 | 674700
77 | Omkar Shankar zagade | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
78 | Pandharinath Bhikaji Bane | COMPENSATION | 339000 | 68000 | 19300 | 51000 | 162000 | 639300
79 | Pandurang Narayan Karpe | COMPENSATION | 317900 | 113500 | 17000 | 57900 | 162000 | 668300
80 | Parshuram Sitaram Chavan | COMPENSATION | 279000 | 85000 | 17000 | 51000 | 162000 | 594000
81 | Parvati D. Waikar | COMPENSATION | 339000 | 85000 | 0 | 0 | 162000 | 586000
82 | Poonam Kishor warekar | COMPENSATION | 319000 | 85000 | 17000 | 51000 | 162000 | 634000
83 | Prabhakar D. Joshi | COMPENSATION | 339000 | 34000 | 0 | 0 | 162000 | 535000
84 | Pradip Shivaram Kadam | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
85 | Prakash Balkrishna Chavan | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
86 | Prakash Janardan Sawant | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
87 | Pramila D. Dalvi | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 324000 | 771000
88 | PRAMILA PRABHAKAR JOSHI | COMPENSATION | 0 | 51000 | 17000 | 51000 | 162000 | 281000
89 | Pramila Shrikant Mahajan | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
90 | Pramod Sitaram Mhapsekar | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
91 | Pravin Shankhar Tanawade | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
92 | Prema Ganesh Dhond | COMPENSATION | 617000 | 119000 | 17000 | 85000 | 162000 | 1000000
93 | Prema Ganesh Dhond-134 | COMPENSATION | 51000 | 51000 | 17000 | 17000 | 162000 | 298000
94 | Priti Pramod Bhagat | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
95 | Priyanka M. Brown | COMPENSATION | 319000 | 85000 | 17000 | 51000 | 162000 | 634000
96 | Radhaballabh C. Kejriwal | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
97 | Raghunath Shridhar Desai | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
98 | Rajendra Vasant Parab | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
99 | Rajesh Bhavani Narvekar | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
100 | Ramakant Parashuram Apate | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
101 | Ramchandra Gana Bhagat | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
102 | Ramchandra H. Narkar | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
103 | Ranjana Ramakant Naik | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
104 | Ravindra Dasharath Batwalkar | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
105 | Ravindra S Chavan | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
106 | Ravindra Shridhar Desai | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
107 | Rohini Ramesh Patil | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
108 | Rukmini Dinkar Kokate | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
109 | Rupali Rajan Shinde | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
110 | Rupesh Ravindra desai | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
111 | Sachidanand Ramakant Karekar | COMPENSATION | 304000 | 85000 | 17000 | 51000 | 162000 | 619000
112 | Sadhana S. Kanade | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 220500 | 737500
113 | Sandip Shantaram Sawant | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
114 | Sanket P. Misal | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
115 | Santosh Sadashiv Raorane | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 177300 | 669300
116 | Santosh V. Salunke | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
117 | Sarvajanik Shri Ganeshothav Mandal Shamnagar | COMPENSATION | 263000 | 85000 | 17000 | 51000 | 162000 | 578000
118 | Satish S. Amin | COMPENSATION | 417500 | 117500 | 23500 | 70500 | 162000 | 791000
119 | Savita Madhukar Dhuri | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
120 | Savita Shantaram Kadam | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 123500 | 640500
121 | Seema Govind Dhuri | COMPENSATION | 380200 | 90100 | 18700 | 56100 | 162000 | 707100
122 | Shankar Mahadev Pimpalkar | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 38500 | 555500
123 | Shankar Sahadev Gavas | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
124 | Shankar Vaiju Patil | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
125 | Sharad Laxman Kadge | COMPENSATION | 319000 | 85000 | 17000 | 51000 | 162000 | 634000
126 | Sharda Dasharath Kshirsagar | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
127 | Shashikant Sahadev Chavan | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
128 | Sheela Shekhar Naik | COMPENSATION | 34000 | 85000 | 17000 | 51000 | 162000 | 349000
129 | Shekhar Rajaram Naik | COMPENSATION | 339000 | 0 | 0 |  | 162000 | 501000
130 | Shevanti Shivaram Shinde | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
131 | Shilpa N. Dandekar | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
132 | Shilpa Vilas Sawant | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
133 | Shrikrishna J Pednekar | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
134 | Shrutika Suhas Salvi | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
135 | Snehal Ganeshraj Nadar | COMPENSATION | 319000 | 85000 | 17000 | 51000 | 162000 | 634000
136 | Suhasini K. Wadekar | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
137 | Sulabha Sadanand Patade | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 329400 | 846400
138 | Sumati Madhukar Parab | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
139 | Sumitra Vithal Ghawali | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
140 | Sunanda Shankar Ghare | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
141 | Sunanda T. Tulaskar | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
142 | Sunil B. Sawant | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
143 | SUNIL PANDURANG SURVE | COMPENSATION | 135000 | 120802 | 34600 | 103800 | 162000 | 556202
144 | Sunil Pandurang Surve (S) | COMPENSATION | 348600 | 52198 | 0 | 0 | 162000 | 562798
145 | Sushant Sudhakar Dhamapurkar | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
146 | Sushila Ramchandra Panchal | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
147 | Sushilkumar Dattaram Patole | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
148 | Suvarna Suresh Nar | COMPENSATION | 294000 | 85000 | 17000 | 51000 | 162000 | 609000
149 | Suvidha Shantaram Dhawade | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
150 | Swati Satyavan Ghone | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
151 | TULASABAI JANU ILAGE | COMPENSATION | 279000 | 85000 | 17000 | 51000 | 162000 | 594000
152 | Umesh Mahadev Kadam | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
153 | Umesh Shridhar Shirke | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
154 | Vaishali D. Pednekar | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
155 | Vaishali Vinayak Bhingarde | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
156 | Vanita Govind Kadam | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
157 | Vasudev Laxman Dalvi | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
158 | Vasudev Shridhar Jikamde | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
159 | Vijaya Shrirang Pawar | COMPENSATION | 339000 | 85000 | 17000 | 51000 | 162000 | 654000
160 | Vijay Babaji Vanjare | COMPENSATION | 364000 | 85000 | 17000 | 51000 | 162000 | 679000
161 | Vijay Ghansham Naik | COMPENSATION | 364000 | 85000 | 17000 | 51000 |  | 517000
162 | Vijay Narayan Raorane | COMPENSATION | 356000 | 85000 | 17000 | 51000 |  | 509000
163 | Vilas Shridhar Sawant | COMPENSATION | 339000 | 85000 | 17000 | 51000 |  | 492000
164 | Vishwanath S Brid | COMPENSATION | 339000 | 85000 | 17000 | 51000 |  | 492000
165 | Vishwanath Vishnu Rane | COMPENSATION | 339000 | 85000 | 17000 | 51000 |  | 492000
166 | Yatin D. Sawant | COMPENSATION | 294000 | 85000 | 17000 | 51000 |  | 447000
167 | Yogesh Raghunath Majagaonkar | COMPENSATION | 339000 | 85000 | 17000 | 51000 |  | 492000
0
0
|  |  | 54373600 | 13927500 | 2768500 | 8237500 | 26374500 | 105681600
[5 empty] | 2768500 | 8237500
[5 empty] | 0 | 0

## TDR & Approval
SR.NO | PARTICULARS | DATE | TOTAL AMOUNT
| MRTP DEVELOPMENT CHARGES | 2023-06-03 | 644125
| MRTP DEVELOPMENT CHARGES | 2023-06-03 | 115943
| MUNICIPAL TAX & FEES | 2021-03-09 | 16801
| MUNICIPAL TAX & FEES | 2021-03-09 | 116484
| MUNICIPAL TAX & FEES | 2021-03-15 | 500
| MUNICIPAL TAX & FEES | 2021-09-23 | 492600
| MUNICIPAL TAX & FEES | 2021-09-23 | 2134600
| MUNICIPAL TAX & FEES | 2021-12-21 | 4882000
| MUNICIPAL TAX & FEES | 2021-12-22 | 2500
| MUNICIPAL TAX & FEES | 2021-12-22 | 5000
| MUNICIPAL TAX & FEES | 2021-12-29 | 2400
| MUNICIPAL TAX & FEES | 2021-12-29 | 1600
| MUNICIPAL TAX & FEES | 2021-12-29 | 500000
| MUNICIPAL TAX & FEES | 2021-12-29 | 5500
| MUNICIPAL TAX & FEES | 2021-12-29 | 6000
| MUNICIPAL TAX & FEES | 2022-01-10 | 4140
| MUNICIPAL TAX & FEES | 2022-01-10 | 4140
| MUNICIPAL TAX & FEES | 2022-01-25 | 29000
| MUNICIPAL TAX & FEES | 2022-01-27 | 50000
| MUNICIPAL TAX & FEES | 2022-01-31 | 15120
| MUNICIPAL TAX & FEES | 2022-02-09 | 57320
| MUNICIPAL TAX & FEES | 2022-02-09 | 786900
| MUNICIPAL TAX & FEES | 2022-02-10 | 480000
| MUNICIPAL TAX & FEES | 2022-02-15 | 200
| MUNICIPAL TAX & FEES | 2022-02-23 | 969809
| MUNICIPAL TAX & FEES | 2022-02-23 | 121820
| MUNICIPAL TAX & FEES | 2022-02-28 | 276400
| MUNICIPAL TAX & FEES | 2022-02-28 | 428100
| MUNICIPAL TAX & FEES | 2022-03-04 | 33603
| MUNICIPAL TAX & FEES | 2022-03-04 | 26887
| MUNICIPAL TAX & FEES | 2022-03-07 | 3148500
| MUNICIPAL TAX & FEES | 2022-03-10 | 159000
| MUNICIPAL TAX & FEES | 2022-03-10 | 198500
| MUNICIPAL TAX & FEES | 2022-03-10 | 5000
| MUNICIPAL TAX & FEES | 2022-03-19 | 28600
| MUNICIPAL TAX & FEES | 2022-03-25 | 62287
| MUNICIPAL TAX & FEES | 2022-03-25 | 496845
| MUNICIPAL TAX & FEES | 2022-03-28 | 247000
| MUNICIPAL TAX & FEES | 2022-03-28 | 57000
| MUNICIPAL TAX & FEES | 2022-03-31 | 2500
| MUNICIPAL TAX & FEES | 2022-04-19 | 31500
| MUNICIPAL TAX & FEES | 2022-04-19 | 66500
| MUNICIPAL TAX & FEES | 2022-04-21 | 119000
| MUNICIPAL TAX & FEES | 2022-04-21 | 129500
| MUNICIPAL TAX & FEES | 2022-06-17 | 700000
| MUNICIPAL TAX & FEES | 2022-09-01 | 3704000
| MUNICIPAL TAX & FEES | 2022-11-09 | 1362500
| MUNICIPAL TAX & FEES | 2022-11-09 | 626875
| MUNICIPAL TAX & FEES | 2022-11-09 | 741000
| MUNICIPAL TAX & FEES | 2022-11-09 | 138750
| MUNICIPAL TAX & FEES | 2022-11-09 | 328750
| MUNICIPAL TAX & FEES | 2022-11-09 | 91000
| MUNICIPAL TAX & FEES | 2022-11-11 | 488229
| MUNICIPAL TAX & FEES | 2022-11-11 | 61216
| MUNICIPAL TAX & FEES | 2022-11-16 | 17250
1 | MUNICIPAL TAX & FEES | 2022-11-18 | 500
2 | MUNICIPAL TAX & FEES | 2022-12-15 | 5799
3 | MUNICIPAL TAX & FEES | 2022-12-15 | 4020
4 | MUNICIPAL TAX & FEES | 2022-12-15 | 2683
5 | MUNICIPAL TAX & FEES | 2022-12-15 | 8757
6 | MUNICIPAL TAX & FEES | 2022-12-15 | 999
7 | MUNICIPAL TAX & FEES | 2022-12-15 | 5833
8 | MUNICIPAL TAX & FEES | 2022-12-15 | 12345
9 | MUNICIPAL TAX & FEES | 2022-12-15 | 10095
10 | MUNICIPAL TAX & FEES | 2022-12-15 | 6408
11 | MUNICIPAL TAX & FEES | 2022-12-15 | 6579
12 | MUNICIPAL TAX & FEES | 2022-12-15 | 15992
13 | MUNICIPAL TAX & FEES | 2022-12-15 | 9456
14 | MUNICIPAL TAX & FEES | 2022-12-15 | 6473
15 | MUNICIPAL TAX & FEES | 2022-12-15 | 10447
16 | MUNICIPAL TAX & FEES | 2022-12-16 | 83730
17 | MUNICIPAL TAX & FEES | 2023-02-10 | 2129375
18 | MUNICIPAL TAX & FEES | 2023-02-10 | 3948125
19 | MUNICIPAL TAX & FEES | 2023-02-10 | 673750
20 | MUNICIPAL TAX & FEES | 2023-02-10 | 1369875
21 | MUNICIPAL TAX & FEES | 2023-04-20 | 2360000
22 | MUNICIPAL TAX & FEES | 2023-05-10 | 2000
23 | MUNICIPAL TAX & FEES | 2023-05-10 | 4000
24 | MUNICIPAL TAX & FEES | 2023-05-12 | 29800
25 | MUNICIPAL TAX & FEES | 2023-08-25 | 1281832
26 | OPEN SPACE DEFICIENCY | 2023-06-03 | 328750
27 | OPEN SPACE DEFICIENCY | 2023-06-03 | 59175
30 | STAIRCASE PREMIUM | 2023-06-03 | 138750
31 | STAIRCASE PREMIUM | 2023-06-03 | 24975
32 | INFRASTRUCTURE CHARGES | 2023-06-03 | 1362500
33 | INFRASTRUCTURE CHARGES | 2023-06-03 | 245250
34 | MRTP DEVELOPMENT CHARGES | 2023-09-14 | 121275
35 | MRTP DEVELOPMENT CHARGES | 2023-09-14 | 1369875
36 | MRTP DEVELOPMENT CHARGES | 2023-09-14 | 246578
37 | MRTP DEVELOPMENT CHARGES | 2023-09-14 | 2129375
38 | MRTP DEVELOPMENT CHARGES | 2023-09-14 | 673750
39 | MRTP DEVELOPMENT CHARGES | 2023-09-14 | 710663
40 | MRTP DEVELOPMENT CHARGES | 2023-09-14 | 3948125
41 | MRTP DEVELOPMENT CHARGES | 2023-09-14 | 383288
42 | INFRASTRUCTURE CHARGES | 2023-12-03 | 1362500
43 | INFRASTRUCTURE CHARGES | 2023-12-03 | 163500
44 | MRTP DEVELOPMENT CHARGES | 2023-12-03 | 644125
45 | MRTP DEVELOPMENT CHARGES | 2023-12-03 | 77295
46 | MUNICIPAL TAX & FEES | 2023-11-01 | 44891
47 | MUNICIPAL TAX & FEES | 2023-11-03 | 33300
48 | OPEN SPACE DEFICIENCY | 2023-12-03 | 328750
49 | OPEN SPACE DEFICIENCY | 2023-12-03 | 39450
50 | STAIRCASE PREMIUM | 2023-12-03 | 138750
51 | STAIRCASE PREMIUM | 2023-12-03 | 16650
52 | MRTP DEVELOPMENT CHARGES |  | 2129375
53 | MRTP DEVELOPMENT CHARGES |  | 255525
54 | MRTP DEVELOPMENT CHARGES |  | 673750
55 | MRTP DEVELOPMENT CHARGES |  | 80850
56 | MRTP DEVELOPMENT CHARGES |  | 1369875
57 | MRTP DEVELOPMENT CHARGES |  | 164385
58 | MRTP DEVELOPMENT CHARGES |  | 3948125
59 | MRTP DEVELOPMENT CHARGES |  | 473775
60 | MRTP DEVELOPMENT CHARGES |  | 473775
61 | MUNICIPAL TAX & FEES-KONSHILA | 2024-02-07 | 3570
62 | MUNICIPAL TAX & FEES-KONSHILA | 2024-02-27 | 2000
63 | MUNICIPAL TAX & FEES-KONSHILA | 2024-02-27 | 4000
64 | MUNICIPAL TAX & FEES-KONSHILA | 2024-02-29 | 1220000
65 | MUNICIPAL TAX & FEES-KONSHILA | 2024-02-29 | 2500
66 | MUNICIPAL TAX & FEES-KONSHILA | 2024-03-15 | 8972
67 | MUNICIPAL TAX & FEES-KONSHILA | 2024-03-22 | 9600
68 | MUNICIPAL TAX & FEES-KONSHILA | 2024-03-27 | 57500
69 | MUNICIPAL TAX & FEES-KONSHILA | 2024-03-27 | 69110500
70 | MUNICIPAL TAX & FEES-KONSHILA | 2024-03-27 | 47000
71 | MUNICIPAL TAX & FEES-KONSHILA | 2024-03-28 | 35500
72 | STAIRCASE PREMIUM | 2024-06-03 | 138750
73 | STAIRCASE PREMIUM | 2024-06-03 | 8325
74 | STAIRCASE PREMIUM | 2024-06-12 | 8325
75 | STAIRCASE PREMIUM | 2024-06-12 | 138750
76 | OPEN SPACE DEFICIENCY | 2024-06-03 | 328750
77 | OPEN SPACE DEFICIENCY | 2024-06-03 | 19725
78 | OPEN SPACE DEFICIENCY | 2024-06-12 | 328750
79 | OPEN SPACE DEFICIENCY | 2024-06-12 | 19725
80 | MUNICIPAL TAX & FEES-KONSHILA |  | 4238500
81 | MUNICIPAL TAX & FEES-KONSHILA |  | 3505000
82 | MUNICIPAL TAX & FEES-KONSHILA |  | 1030000
83 | MUNICIPAL TAX & FEES-KONSHILA |  | 1980500
84 | MUNICIPAL TAX & FEES-KONSHILA |  | 7360000
85 | MRTP DEVELOPMENT CHARGES | 2024-06-03 | 38648
86 | MRTP DEVELOPMENT CHARGES | 2024-06-03 | 644125
87 | MRTP DEVELOPMENT CHARGES | 2024-06-12 | 38648
88 | MRTP DEVELOPMENT CHARGES | 2024-06-12 | 644125
89 | MRTP DEVELOPMENT CHARGES | 2024-06-19 | 11641
90 | INFRASTRUCTURE CHARGES | 2024-06-03 | 81750
91 | INFRASTRUCTURE CHARGES | 2024-06-03 | 1362500
92 | INFRASTRUCTURE CHARGES | 2024-06-12 | 81750
93 | INFRASTRUCTURE CHARGES | 2024-06-12 | 1362500
94
95
96
155242571

## Construction Cost
Date | Particular |  | Total Amount
2022-03-19 | A TO Z MACHINERY |  | 4144
2022-03-29 | ANUPAM ELECTRICALS |  | 448
2022-04-15 | S.H.ENTERPRISES |  | 65408
2022-04-19 | ANUPAM ELECTRICALS |  | 2800
2022-04-30 | S.H.ENTERPRISES |  | 65408
2022-04-30 | S.H.ENTERPRISES |  | 65408
2022-05-11 | R.K.TRADING CO. |  | 952
2022-05-14 | A TO Z MACHINERY |  | 5544
2022-06-04 | ANUPAM ELECTRICALS |  | 76608
2022-12-06 | GODREJ & BOYCE MFG CO.LTD |  | 135795.74
2022-12-29 | GODREJ & BOYCE MFG CO.LTD |  | 134552.61
2022-12-29 | GODREJ & BOYCE MFG CO.LTD |  | 135794.86
2023-01-10 | GODREJ & BOYCE MFG CO.LTD |  | 103781
2023-01-10 | GODREJ & BOYCE MFG CO.LTD |  | 121415.06
2023-01-13 | GODREJ & BOYCE MFG CO.LTD |  | 135135.16
2023-01-13 | GODREJ & BOYCE MFG CO.LTD |  | 69558.04
2023-01-31 | GODREJ & BOYCE MFG CO.LTD |  | 71068.04
2023-02-10 | GODREJ & BOYCE MFG CO.LTD |  | 84604.8
2023-02-10 | GODREJ & BOYCE MFG CO.LTD |  | 71068.04
2023-02-11 | GODREJ & BOYCE MFG CO.LTD |  | 97462.3
2023-02-22 | GODREJ & BOYCE MFG CO.LTD |  | 126879
2023-02-25 | WE ARE ONE ENTERPRISES PVT LTD |  | 145507.33
2023-02-25 | GODREJ & BOYCE MFG CO.LTD |  | 73098.54
2023-02-27 | GODREJ & BOYCE MFG CO.LTD |  | 60631.2
2023-02-27 | GODREJ & BOYCE MFG CO.LTD |  | 109647.82
2023-03-01 | PROFESSIONAL BUILDING CONTRACTOR |  | 12320
2023-03-02 | PROFESSIONAL BUILDING CONTRACTOR |  | 26880
2023-03-31 | GODREJ & BOYCE MFG CO.LTD |  | 117570.24
2023-03-31 | GODREJ & BOYCE MFG CO.LTD |  | 109647.82
2023-03-31 | GODREJ & BOYCE MFG CO.LTD |  | 59223.36
2023-03-31 | GODREJ & BOYCE MFG CO.LTD |  | 65427.72
2023-03-31 | GODREJ & BOYCE MFG CO.LTD |  | 63453.6
2023-04-19 | GODREJ & BOYCE MFG CO.LTD |  | 67004.58
2023-04-19 | GODREJ & BOYCE MFG CO.LTD |  | 60915.46
2023-04-20 | GODREJ & BOYCE MFG CO.LTD |  | 75298.28
2023-04-20 | GODREJ & BOYCE MFG CO.LTD |  | 69375.94
2023-04-20 | GODREJ & BOYCE MFG CO.LTD |  | 73606.18
2023-04-29 | GODREJ & BOYCE MFG CO.LTD |  | 85279.22
2023-04-29 | GODREJ & BOYCE MFG CO.LTD |  | 103556.28
2023-04-30 | SHARADA ENTERPRISES |  | 66552.64
2023-05-11 | PROFESSIONAL BUILDING CONTRACTOR |  | 14560
2023-05-15 | RECONS BUILDING PRODUCTS PVT.LTD |  | 68322
2023-05-17 | RECONS BUILDING PRODUCTS PVT.LTD |  | 66495
2023-05-17 | GODREJ & BOYCE MFG CO.LTD |  | 71068.04
2023-05-18 | GODREJ & BOYCE MFG CO.LTD |  | 103556.28
2023-05-18 | GODREJ & BOYCE MFG CO.LTD |  | 56403.2
2023-05-20 | GODREJ & BOYCE MFG CO.LTD |  | 52454.98
2023-05-26 | RECONS BUILDING PRODUCTS PVT.LTD |  | 53103
2023-05-26 | GODREJ & BOYCE MFG CO.LTD |  | 121828.5
2023-05-26 | GODREJ & BOYCE MFG CO.LTD |  | 121828.5
2023-05-26 | GODREJ & BOYCE MFG CO.LTD |  | 67007
2023-05-31 | RECONS BUILDING PRODUCTS PVT.LTD |  | 62085
2023-05-31 | RECONS BUILDING PRODUCTS PVT.LTD |  | 61839
2023-06-06 | RECONS BUILDING PRODUCTS PVT.LTD |  | 59334.99
2023-06-08 | RECONS BUILDING PRODUCTS PVT.LTD |  | 61541
2023-06-08 | RECONS BUILDING PRODUCTS PVT.LTD |  | 50221
2023-06-12 | RECONS BUILDING PRODUCTS PVT.LTD |  | 52693
2023-06-13 | RECONS BUILDING PRODUCTS PVT.LTD |  | 57290
2023-06-16 | GODREJ & BOYCE MFG CO.LTD |  | 102202.6
2023-06-19 | RECONS BUILDING PRODUCTS PVT.LTD |  | 64638
2023-06-19 | RECONS BUILDING PRODUCTS PVT.LTD |  | 60833
2023-06-26 | RECONS BUILDING PRODUCTS PVT.LTD |  | 60020.01
2023-06-28 | RECONS BUILDING PRODUCTS PVT.LTD |  | 68473.01
2023-06-29 | GODREJ & BOYCE MFG CO.LTD |  | 97464.72
2023-06-29 | GODREJ & BOYCE MFG CO.LTD |  | 85281.64
2023-06-30 | RECONS BUILDING PRODUCTS PVT.LTD |  | 64227
2023-07-03 | RECONS BUILDING PRODUCTS PVT.LTD |  | 50215
2023-07-03 | RECONS BUILDING PRODUCTS PVT.LTD |  | 61516.99
2023-07-10 | RECONS BUILDING PRODUCTS PVT.LTD |  | 51446.01
2023-07-11 | RECONS BUILDING PRODUCTS PVT.LTD |  | 59873
2023-07-15 | RECONS BUILDING PRODUCTS PVT.LTD |  | 51981.01
2023-07-17 | RECONS BUILDING PRODUCTS PVT.LTD |  | 52671
2023-07-18 | GODREJ & BOYCE MFG CO.LTD |  | 58377.32
2023-07-18 | GODREJ & BOYCE MFG CO.LTD |  | 54823.92
2023-07-23 | GODREJ & BOYCE MFG CO.LTD |  | 60915.46
2023-07-25 | RECONS BUILDING PRODUCTS PVT.LTD |  | 50221
2023-07-25 | RECONS BUILDING PRODUCTS PVT.LTD |  | 54876.01
2023-07-29 | GODREJ & BOYCE MFG CO.LTD |  | 51608.92
2023-07-31 | RECONS BUILDING PRODUCTS PVT.LTD |  | 48334
2023-08-03 | RECONS BUILDING PRODUCTS PVT.LTD |  | 61245
2023-08-03 | RECONS BUILDING PRODUCTS PVT.LTD |  | 56280.99
2023-08-05 | PROFESSIONAL BUILDING CONTRACTOR |  | 14336
2023-08-07 | RECONS BUILDING PRODUCTS PVT.LTD |  | 67370.01
2023-08-07 | RECONS BUILDING PRODUCTS PVT.LTD |  | 48986.99
2023-08-10 | GODREJ & BOYCE MFG CO.LTD |  | 51608.92
2023-08-10 | GODREJ & BOYCE MFG CO.LTD |  | 63453.6
2023-08-11 | RECONS BUILDING PRODUCTS PVT.LTD |  | 60972
2023-08-14 | RECONS BUILDING PRODUCTS PVT.LTD |  | 64920.01
2023-08-14 | RECONS BUILDING PRODUCTS PVT.LTD |  | 52262
2023-08-15 | S.H.ENTERPRISES |  | 66640
2023-08-18 | RECONS BUILDING PRODUCTS PVT.LTD |  | 50293
2023-08-21 | RECONS BUILDING PRODUCTS PVT.LTD |  | 47771.01
2023-08-22 | RECONS BUILDING PRODUCTS PVT.LTD |  | 44096.01
2023-08-25 | RECONS BUILDING PRODUCTS PVT.LTD |  | 58795
2023-08-28 | RECONS BUILDING PRODUCTS PVT.LTD |  | 45321
2023-08-29 | RECONS BUILDING PRODUCTS PVT.LTD |  | 46700
2023-08-29 | RECONS BUILDING PRODUCTS PVT.LTD |  | 58387.01
2023-08-31 | RECONS BUILDING PRODUCTS PVT.LTD |  | 68594
2022-01-21 | DISHA TRADE LINK |  | 63404.94
2022-01-23 | DISHA TRADE LINK |  | 146258.06
2022-02-15 | SKY TELECOM |  | 58115
2022-03-01 | SAHARSH ENTERPRISES |  | 295354
2022-03-04 | ANUPAM ELECTRICALS |  | 1321.6
2022-03-12 | ANUPAM ELECTRICALS |  | 16537.7
2022-03-13 | ANUPAM ELECTRICALS |  | 60375.88
2022-03-14 | KRISHNA TRADING CORPORATION |  | 7043.42
2022-03-14 | BHARAT ELECTRICALS |  | 77290
2022-03-17 | MEHTA PLYWOOD |  | 18904.93
2022-03-22 | SKY TELECOM |  | 13983
2022-03-23 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2784870.8
2022-03-23 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2734945
2022-03-29 | ANUPAM ELECTRICALS |  | 18181.44
2022-03-31 | OM SWASTIK ENTRRPTISES |  | 637174.99
2022-03-31 | SKY TELECOM |  | 12649.6
2022-04-05 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2691993
2022-04-09 | KRISHNA TRADING CORPORATION |  | 14786.46
2022-04-11 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2272453.44
2022-04-12 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2610971.84
2022-04-12 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2593910.22
2022-04-16 | KRISHNA TRADING CORPORATION |  | 13994.27
2022-04-18 | OM SWASTIK ENTRRPTISES |  | 910349.99
2022-04-19 | ANUPAM ELECTRICALS |  | 4513.5
2022-04-22 | ANUPAM ELECTRICALS |  | 2348.2
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-04-26 | GODREJ & BOYCE MFG CO.LTD |  | 49169.96
2022-05-01 | OM SWASTIK ENTRRPTISES |  | 40700.01
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 20160
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-10 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | R.K.TRADING CO. |  | 14514
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 54599.96
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-11 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-12 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-05-14 | ANUPAM ELECTRICALS |  | 2095.68
2022-05-22 | BHARAT ELECTRICALS |  | 43833.46
2022-05-25 | NUVOCO VISTAS CORP LTD |  | 24987.1
2022-05-25 | NUVOCO VISTAS CORP LTD |  | 24986.74
2022-05-26 | OM SWASTIK ENTRRPTISES |  | 6199200
2022-05-26 | MAHIMA ENTERPRISES |  | 183600
2022-05-26 | MAHIMA ENTERPRISES |  | 195749.99
2022-05-30 | BUCON READYMIX LLP |  | 394160.12
2022-05-31 | MAHIMA ENTERPRISES |  | 229500.01
2022-05-31 | BUCON READYMIX LLP |  | 235600.08
2022-05-31 | MAHIMA ENTERPRISES |  | 150150
2022-05-31 | MAHIMA ENTERPRISES |  | 154700
2022-06-03 | ANUPAM ELECTRICALS |  | 43306
2022-06-04 | ANUPAM ELECTRICALS |  | 7298.3
2022-06-04 | GODREJ & BOYCE MFG CO.LTD |  | 47040.02
2022-06-04 | GODREJ & BOYCE MFG CO.LTD |  | 47040.02
2022-06-04 | GODREJ & BOYCE MFG CO.LTD |  | 47040.02
2022-06-04 | GODREJ & BOYCE MFG CO.LTD |  | 47040.02
2022-06-04 | GODREJ & BOYCE MFG CO.LTD |  | 47040.02
2022-06-06 | BUCON READYMIX LLP |  | 348040.1
2022-06-07 | GODREJ & BOYCE MFG CO.LTD |  | 47040.02
2022-06-07 | GODREJ & BOYCE MFG CO.LTD |  | 47040.02
2022-06-07 | GODREJ & BOYCE MFG CO.LTD |  | 47040.02
2022-06-07 | GODREJ & BOYCE MFG CO.LTD |  | 39200.01
2022-06-07 | SKY TELECOM |  | 35872
2022-06-09 | SKY TELECOM |  | 4838
2022-06-10 | A TO Z MACHINERY |  | 134520
2022-06-12 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1987575.48
2022-06-18 | ANUPAM ELECTRICALS |  | 13953.5
2022-06-18 | Hella Infra Market Pvt Ltd |  | 34200.02
2022-06-18 | Hella Infra Market Pvt Ltd |  | 34200.02
2022-06-18 | Hella Infra Market Pvt Ltd |  | 34200.02
2022-06-18 | Hella Infra Market Pvt Ltd |  | 34200.02
2022-06-23 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1872858.24
2022-06-24 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2080533.52
2022-06-26 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1896425.2
2022-06-30 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2511073.04
2022-06-30 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2551125.78
2022-06-30 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2416846.5
2022-06-30 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2651653.52
2022-06-30 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2289388.8
2022-06-30 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2250271.8
2022-06-30 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2277423.6
2022-06-30 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2248112.4
2022-06-30 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2183631.3
2022-06-30 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2034627.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 46199.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-08 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-09 | GODREJ & BOYCE MFG CO.LTD |  | 50399.98
2022-07-12 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1990806.32
2022-07-20 | ANUPAM ELECTRICALS |  | 2737.6
2022-07-22 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1886467.18
2022-07-25 | MAHIMA ENTERPRISES |  | 191249.99
2022-07-25 | MAHIMA ENTERPRISES |  | 222299.99
2022-07-25 | MAHIMA ENTERPRISES |  | 570000.01
2022-07-25 | MAHIMA ENTERPRISES |  | 131099.99
2022-07-28 | SKY TELECOM |  | 17759
2022-08-09 | BUCON READYMIX LLP |  | 409360.12
2022-08-10 | MAHIMA ENTERPRISES |  | 91799.99
2022-08-11 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2193268.36
2022-08-11 | SKY TELECOM |  | 1711
2022-08-14 | BUCON READYMIX LLP |  | 753600.08
2022-08-17 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2095626.9
2022-08-18 | Hella Infra Market Pvt Ltd |  | 34200.02
2022-08-18 | Hella Infra Market Pvt Ltd |  | 46800
2022-08-20 | Hella Infra Market Pvt Ltd |  | 46800
2022-08-20 | Hella Infra Market Pvt Ltd |  | 46800
2022-08-20 | Hella Infra Market Pvt Ltd |  | 46800
2022-08-23 | BUCON READYMIX LLP |  | 363100.08
2022-08-25 | BUCON READYMIX LLP |  | 135149.58
2022-08-31 | MAHIMA ENTERPRISES |  | 162374.99
2022-08-31 | MAHIMA ENTERPRISES |  | 177899.99
2022-08-31 | MAHIMA ENTERPRISES |  | 435425
2022-08-31 | MAHIMA ENTERPRISES |  | 873750
2022-08-31 | MAHIMA ENTERPRISES |  | 66600
2022-08-31 | MAHIMA ENTERPRISES |  | 477227.4
2022-08-31 | BUCON READYMIX LLP |  | 38850.01
2022-09-13 | SKY TELECOM |  | 12272
2022-09-14 | GODREJ & BOYCE MFG CO.LTD |  | 47039.52
2022-09-14 | GODREJ & BOYCE MFG CO.LTD |  | 47039.52
2022-09-14 | GODREJ & BOYCE MFG CO.LTD |  | 42930
2022-09-14 | GODREJ & BOYCE MFG CO.LTD |  | 42930
2022-09-14 | GODREJ & BOYCE MFG CO.LTD |  | 42930
2022-09-14 | GODREJ & BOYCE MFG CO.LTD |  | 42930
2022-09-14 | GODREJ & BOYCE MFG CO.LTD |  | 42930
2022-09-14 | GODREJ & BOYCE MFG CO.LTD |  | 42930
2022-09-14 | GODREJ & BOYCE MFG CO.LTD |  | 41729.52
2022-09-14 | GODREJ & BOYCE MFG CO.LTD |  | 47039.52
2022-09-14 | GODREJ & BOYCE MFG CO.LTD |  | 42930
2022-09-14 | GODREJ & BOYCE MFG CO.LTD |  | 41729.52
2022-09-14 | GODREJ & BOYCE MFG CO.LTD |  | 42930
2022-09-14 | GODREJ & BOYCE MFG CO.LTD |  | 42930
2022-09-24 | VEDANT MARKETING |  | 5982.6
2022-09-27 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1748481.76
2022-09-27 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 191091.56
2022-10-01 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2081461
2022-10-07 | POONAM INTERNATIONAL |  | 82559.88
2022-10-10 | MAHIMA ENTERPRISES |  | 950274.99
2022-10-10 | MAHIMA ENTERPRISES |  | 471458.55
2022-10-12 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1999580.8
2022-10-15 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1987796.14
2022-10-17 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1969251.26
2022-10-18 | MAHIMA ENTERPRISES |  | 953149.08
2022-10-28 | ASHISH INFRATECH SYSTEMS |  | 29087
2022-10-31 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1875618.26
2022-10-31 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 81142.7
2022-11-05 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1910824.74
2022-11-09 | KRISHNA TRADING CORPORATION |  | 1003
2022-11-14 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1924066.7
2022-11-14 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1830010.08
2022-11-14 | VEDANT MARKETING |  | 32267.1
2022-11-15 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1884831.7
2022-11-15 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1861627
2022-11-19 | VEDANT MARKETING |  | 27806.7
2022-11-20 | MAHIMA ENTERPRISES |  | 752949.72
2022-11-25 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1882193.22
2022-11-29 | MAHIMA ENTERPRISES |  | 184412.48
2022-12-06 | GODREJ & BOYCE MFG CO.LTD |  | 16799.9
2022-12-08 | POONAM INTERNATIONAL |  | 73556.48
2022-12-08 | VEDANT MARKETING |  | 5982.6
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-10 | GODREJ & BOYCE MFG CO.LTD |  | 47400.04
2022-12-12 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1902425.5
2022-12-15 | GODREJ & BOYCE MFG CO.LTD |  | 40799.64
2022-12-22 | SKY TELECOM |  | 2832
2022-12-23 | VEDANT MARKETING |  | 55259.4
2022-12-24 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 148271.72
2022-12-27 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 947820.84
2022-12-27 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 942553.8
2022-12-27 | KRISHNA TRADING CORPORATION |  | 6596.2
2022-12-31 | GODREJ & BOYCE MFG CO.LTD |  | 12599.92
2022-12-31 | GODREJ & BOYCE MFG CO.LTD |  | 12599.92
2023-01-04 | VEDANT MARKETING |  | 5982.6
2023-01-05 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1730324.86
2023-01-05 | R.K.TRADING CO. |  | 2832
2023-01-08 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1942903.04
2023-01-10 | TEJAL ELECTRICAL |  | 312500.58
2023-01-12 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1967008.08
2023-01-21 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2035293.5
2023-01-24 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2079888.06
2023-01-30 | R.K.TRADERS |  | 6740.16
2023-01-30 | GODREJ & BOYCE MFG CO.LTD |  | 12599.92
2023-01-30 | GODREJ & BOYCE MFG CO.LTD |  | 12599.92
2023-01-30 | GODREJ & BOYCE MFG CO.LTD |  | 12599.92
2023-01-31 | SUPREME GYPSUM PVT LTD |  | 38350
2023-01-31 | GODREJ & BOYCE MFG CO.LTD |  | 12599.92
2023-02-03 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2100038.92
2023-02-06 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2124831.9
2023-02-08 | VEDANT MARKETING |  | 9317.28
2023-02-11 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1921307.86
2023-02-19 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2006541.62
2023-02-25 | VEDANT MARKETING |  | 8796.9
2023-02-25 | WE ARE ONE ENTERPRISES PVT LTD |  | 12900.12
2023-02-28 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1983582.36
2023-02-28 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1759000.04
2023-02-28 | GODREJ & BOYCE MFG CO.LTD |  | 12599.92
2023-02-28 | GODREJ & BOYCE MFG CO.LTD |  | 25199.84
2023-02-28 | GODREJ & BOYCE MFG CO.LTD |  | 16799.9
2023-03-09 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2087534.46
2023-03-09 | EAGLE SALES CORPORATION |  | 86765.4
2023-03-09 | S.S.ENTERPRISES |  | 56050
2023-03-16 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2013655.84
2023-03-21 | VEDANT MARKETING |  | 11611.2
2023-03-25 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 79267.68
2023-03-25 | JYOTI KITCHEN INDUSTRIES PVT LTD |  | 7585
2023-03-25 | HINDUSTAN ASSOCIATES |  | 80683.46
2023-03-26 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1879317.56
2023-03-27 | TEJAL ELECTRICAL |  | 213236.04
2023-03-27 | R.K.TRADING CO. |  | 4248
2023-03-28 | KRISHNA TRADING CORPORATION |  | 17065.76
2023-03-29 | ANUPAM ELECTRICALS |  | 8732
2023-03-30 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1967130.8
2023-03-31 | HITECH CONSTRUCTION AND REPAIRS |  | 43660
2023-03-31 | GODREJ & BOYCE MFG CO.LTD |  | 16799.9
2023-03-31 | GODREJ & BOYCE MFG CO.LTD |  | 16799.9
2023-03-31 | GODREJ & BOYCE MFG CO.LTD |  | 16799.9
2023-04-07 | KRISHNA CERAMICS |  | 6200.01
2023-04-10 | MEHTA PLYWOOD |  | 2360
2023-04-11 | MEHTA PLYWOOD |  | 4370.72
2023-04-12 | SUPREME GYPSUM PVT LTD |  | 38350
2023-04-12 | MEHTA PLYWOOD |  | 42812.76
2023-04-15 | KRISHNA TRADING CORPORATION |  | 6136
2023-04-16 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1941024.48
2023-04-17 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 82629.5
2023-04-19 | SKY TELECOM |  | 39618.5
2023-04-19 | KRISHNA TRADING CORPORATION |  | 625
2023-04-20 | MEHTA PLYWOOD |  | 10289.6
2023-04-21 | GODREJ & BOYCE MFG CO.LTD |  | 12599.92
2023-04-26 | MEHTA PLYWOOD |  | 161.08
2023-04-27 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1990467.66
2023-04-28 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1967556.78
2023-04-29 | GODREJ & BOYCE MFG CO.LTD |  | 12599.92
2023-05-02 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1919113.01
2023-05-05 | EAGLE SALES CORPORATION |  | 143418.64
2023-05-06 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1909894.9
2023-05-09 | SKY TELECOM |  | 15104
2023-05-11 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1881735.38
2023-05-12 | GODREJ & BOYCE MFG CO.LTD |  | 8399.94
2023-05-12 | GODREJ & BOYCE MFG CO.LTD |  | 12599.92
2023-05-12 | GODREJ & BOYCE MFG CO.LTD |  | 8399.94
2023-05-12 | KARRMANYA ENTERPRISE |  | 19822.82
2023-05-14 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1956994.6
2023-05-14 | TEJAL ELECTRICAL |  | 356581.84
2023-05-19 | VEDANT MARKETING |  | 11611.2
2023-05-20 | ANUPAM ELECTRICALS |  | 6962
2023-05-20 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1929618.6
2023-05-25 | HITECH CONSTRUCTION AND REPAIRS |  | 43660
2023-05-26 | VEDANT MARKETING |  | 5982.6
2023-05-26 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 130000.6
2023-05-26 | RECONS BUILDING PRODUCTS PVT.LTD |  | 8400
2023-05-28 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1766437.58
2023-05-29 | GODREJ & BOYCE MFG CO.LTD |  | 12599.92
2023-05-31 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1871049.3
2023-05-31 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1899784.66
2023-06-01 | ARIHANT ELECTRICALS |  | 549999.82
2023-06-02 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1819984.8
2023-06-03 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 75756
2023-06-06 | RECONS BUILDING PRODUCTS PVT.LTD |  | 16800.01
2023-06-08 | RECONS BUILDING PRODUCTS PVT.LTD |  | 33600
2023-06-10 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1875471.94
2023-06-12 | RECONS BUILDING PRODUCTS PVT.LTD |  | 16800
2023-06-12 | KARRMANYA ENTERPRISE |  | 127511.98
2023-06-12 | KARRMANYA ENTERPRISE |  | 8884.22
2023-06-14 | KARRMANYA ENTERPRISE |  | 8556.18
2023-06-15 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 11810.04
2023-06-15 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 58551.6
2023-06-15 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 7051.1
2023-06-16 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1839367.48
2023-06-16 | AXLER WOODWORKS LLP |  | 38392.48
2023-06-19 | RECONS BUILDING PRODUCTS PVT.LTD |  | 12600
2023-06-20 | A TO Z MACHINERY |  | 13233.99
2023-06-23 | VEDANT MARKETING |  | 17239.8
2023-06-26 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 77299.44
2023-06-26 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1816728
2023-06-28 | HINDUSTAN ASSOCIATES |  | 24452.48
2023-06-29 | GODREJ & BOYCE MFG CO.LTD |  | 16799.9
2023-06-30 | SUPREME GYPSUM PVT LTD |  | 38350
2023-06-30 | GODREJ & BOYCE MFG CO.LTD |  | 16799.9
2023-06-30 | GODREJ & BOYCE MFG CO.LTD |  | 20999.88
2023-07-05 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1664921
2023-07-05 | EAGLE SALES CORPORATION |  | 123929.84
2023-07-11 | EAGLE SALES CORPORATION |  | 21211.97
2023-07-12 | HINDUSTAN ASSOCIATES |  | 406552.86
2023-07-14 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1687974.66
2023-07-15 | HEM ENTERPRISE |  | 500154.8
2023-07-22 | R.K.TRADING CO. |  | 2832
2023-07-23 | TEJAL ELECTRICAL |  | 254858.52
2023-07-24 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 70325.64
2023-07-24 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1667494.58
2023-07-27 | GODREJ & BOYCE MFG CO.LTD |  | 12599.92
2023-07-27 | GODREJ & BOYCE MFG CO.LTD |  | 12599.92
2023-07-28 | ANUPAM ELECTRICALS |  | 6962
2023-07-29 | D.R LINKS |  | 45312
2023-07-29 | D.R LINKS |  | 1862.04
2023-07-29 | GODREJ & BOYCE MFG CO.LTD |  | 25199.84
2023-07-31 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1584548.84
2023-08-01 | GODREJ & BOYCE MFG CO.LTD |  | 16799.9
2023-08-03 | TEJAS CERAMICS |  | 23400.01
2023-08-05 | PROFESSIONAL BUILDING CONTRACTOR |  | 24162.86
2023-08-07 | RECONS BUILDING PRODUCTS PVT.LTD |  | 12600.01
2023-08-08 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1713304.54
2023-08-10 | GODREJ & BOYCE MFG CO.LTD |  | 25199.84
2023-08-11 | S.S.ENTERPRISES |  | 28320
2023-08-12 | KRISHNA CERAMICS |  | 16682.26
2023-08-13 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1702407.24
2023-08-14 | RECONS BUILDING PRODUCTS PVT.LTD |  | 6075
2023-08-14 | RECONS BUILDING PRODUCTS PVT.LTD |  | 6073.82
2023-08-16 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 76591.44
2023-08-16 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1698449.52
2023-08-18 | RECONS BUILDING PRODUCTS PVT.LTD |  | 16199.98
2023-08-21 | RECONS BUILDING PRODUCTS PVT.LTD |  | 20249.98
2023-08-22 | RECONS BUILDING PRODUCTS PVT.LTD |  | 20249.98
2023-08-23 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1706845.22
2023-08-28 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1806664.96
2023-08-28 | RECONS BUILDING PRODUCTS PVT.LTD |  | 24300
2023-08-29 | VEDANT MARKETING |  | 28178.4
2023-08-29 | RECONS BUILDING PRODUCTS PVT.LTD |  | 20250
2022-03-17 | KIRIT TRADING COMPANY |  | 90240
2022-03-23 | KARAN ENTERPRISES |  | 71936
2022-03-27 | JKLAKSHMI CEMENT LTD |  | 73472
2022-04-22 | JKLAKSHMI CEMENT LTD |  | 89088
2022-07-25 | SUNTREK CORPORATION |  | 69632
2022-10-28 | JKLAKSHMI CEMENT LTD |  | 161280
2022-10-28 | JKLAKSHMI CEMENT LTD |  | 201600
2022-10-28 | JKLAKSHMI CEMENT LTD |  | 201600
2022-11-04 | JKLAKSHMI CEMENT LTD |  | 65721.6
2022-11-04 | JKLAKSHMI CEMENT LTD |  | 80640
2022-11-07 | JKLAKSHMI CEMENT LTD |  | 80640
2022-11-07 | JKLAKSHMI CEMENT LTD |  | 80640
2022-11-07 | JKLAKSHMI CEMENT LTD |  | 95558.4
2022-11-07 | JKLAKSHMI CEMENT LTD |  | 80640
2022-11-14 | KIRIT TRADING COMPANY |  | 117120
2022-11-14 | KIRIT TRADING COMPANY |  | 117120
2022-11-14 | KIRIT TRADING COMPANY |  | 117120
2022-11-15 | KIRIT TRADING COMPANY |  | 117120
2022-11-15 | KIRIT TRADING COMPANY |  | 117120
2022-11-25 | JKLAKSHMI CEMENT LTD |  | 78080
2022-11-26 | JKLAKSHMI CEMENT LTD |  | 39040
2022-11-27 | JKLAKSHMI CEMENT LTD |  | 78080
2022-11-28 | JKLAKSHMI CEMENT LTD |  | 78080
2022-11-29 | JKLAKSHMI CEMENT LTD |  | 117120
2022-12-06 | KARAN ENTERPRISES |  | 78080
2022-12-06 | KARAN ENTERPRISES |  | 97600
2022-12-06 | KARAN ENTERPRISES |  | 97600
2022-12-06 | KARAN ENTERPRISES |  | 97600
2022-12-07 | KARAN ENTERPRISES |  | 93696
2022-12-17 | JKLAKSHMI CEMENT LTD |  | 99840
2022-12-17 | JKLAKSHMI CEMENT LTD |  | 99840
2022-12-17 | JKLAKSHMI CEMENT LTD |  | 99840
2022-12-17 | JKLAKSHMI CEMENT LTD |  | 99840
2022-12-19 | JKLAKSHMI CEMENT LTD |  | 79872
2022-12-22 | JKLAKSHMI CEMENT LTD |  | 70400
2022-12-23 | JKLAKSHMI CEMENT LTD |  | 117120
2022-12-23 | JKLAKSHMI CEMENT LTD |  | 117120
2022-12-29 | JKLAKSHMI CEMENT LTD |  | 78080
2022-12-30 | JKLAKSHMI CEMENT LTD |  | 97600
2022-12-30 | JKLAKSHMI CEMENT LTD |  | 117120
2022-12-30 | JKLAKSHMI CEMENT LTD |  | 78080
2022-12-31 | JKLAKSHMI CEMENT LTD |  | 97600
2023-01-04 | JKLAKSHMI CEMENT LTD |  | 117120
2023-01-04 | JKLAKSHMI CEMENT LTD |  | 78080
2023-01-05 | JKLAKSHMI CEMENT LTD |  | 97600
2023-01-05 | JKLAKSHMI CEMENT LTD |  | 78080
2023-01-05 | JKLAKSHMI CEMENT LTD |  | 21862.4
2023-01-09 | JKLAKSHMI CEMENT LTD |  | 75737.6
2023-01-10 | KARAN ENTERPRISES |  | 92160
2023-01-10 | KARAN ENTERPRISES |  | 92160
2023-01-12 | KARAN ENTERPRISES |  | 92160
2023-01-13 | KARAN ENTERPRISES |  | 92160
2023-01-13 | KARAN ENTERPRISES |  | 92160
2023-01-18 | KARAN ENTERPRISES |  | 96000
2023-01-18 | KARAN ENTERPRISES |  | 96000
2023-01-18 | KARAN ENTERPRISES |  | 96000
2023-01-19 | KARAN ENTERPRISES |  | 76800
2023-01-19 | KARAN ENTERPRISES |  | 96000
2023-01-21 | KARAN ENTERPRISES |  | 96000
2023-01-21 | KARAN ENTERPRISES |  | 96000
2023-01-25 | KARAN ENTERPRISES |  | 115200
2023-01-28 | KIRIT TRADING COMPANY |  | 117120
2023-01-28 | KIRIT TRADING COMPANY |  | 117120
2023-01-28 | KIRIT TRADING COMPANY |  | 117120
2023-01-30 | JKLAKSHMI CEMENT LTD |  | 69120
2023-02-05 | THE INDIA CEMENTS LIMITED ( KIRIT TRADING) |  | 93696
2023-02-05 | THE INDIA CEMENTS LIMITED ( KIRIT TRADING) |  | 93696
2023-02-06 | THE INDIA CEMENTS LIMITED ( KIRIT TRADING) |  | 93696
2023-02-09 | THE INDIA CEMENTS LIMITED ( KIRIT TRADING) |  | 97600
2023-02-09 | THE INDIA CEMENTS LIMITED ( KIRIT TRADING) |  | 97600
2023-02-15 | THE INDIA CEMENTS LIMITED ( KIRIT TRADING) |  | 514547.2
2023-02-20 | KIRIT TRADING COMPANY |  | 117120
2023-02-20 | KIRIT TRADING COMPANY |  | 107360
2023-02-22 | KIRIT TRADING COMPANY |  | 119072
2023-02-22 | KIRIT TRADING COMPANY |  | 121024
2023-02-22 | KIRIT TRADING COMPANY |  | 121024
2023-02-28 | KIRIT TRADING COMPANY |  | 117120
2023-02-28 | KIRIT TRADING COMPANY |  | 117120
2023-03-03 | THE INDIA CEMENTS LIMITED ( KIRIT TRADING) |  | 117120
2023-03-03 | THE INDIA CEMENTS LIMITED ( KIRIT TRADING) |  | 117120
2023-03-03 | THE INDIA CEMENTS LIMITED ( KIRIT TRADING) |  | 117120
2023-03-04 | THE INDIA CEMENTS LIMITED ( KIRIT TRADING) |  | 242048
2023-03-09 | JKLAKSHMI CEMENT LTD |  | 97600
2023-03-09 | JKLAKSHMI CEMENT LTD |  | 97600
2023-03-10 | JKLAKSHMI CEMENT LTD |  | 39040
2023-03-10 | JKLAKSHMI CEMENT LTD |  | 39040
2023-03-10 | JKLAKSHMI CEMENT LTD |  | 97600
2023-03-10 | JKLAKSHMI CEMENT LTD |  | 97600
2023-03-28 | JKLAKSHMI CEMENT LTD |  | 75520
2023-03-28 | JKLAKSHMI CEMENT LTD |  | 113280
2023-03-28 | JKLAKSHMI CEMENT LTD |  | 75520
2023-03-29 | JKLAKSHMI CEMENT LTD |  | 94400
2023-03-29 | JKLAKSHMI CEMENT LTD |  | 94400
2023-03-30 | JKLAKSHMI CEMENT LTD |  | 113280
2023-04-10 | THE INDIA CEMENTS LIMITED ( KIRIT TRADING) |  | 113280
2023-04-10 | THE INDIA CEMENTS LIMITED ( KIRIT TRADING) |  | 113280
2023-04-10 | THE INDIA CEMENTS LIMITED ( KIRIT TRADING) |  | 113280
2023-04-10 | THE INDIA CEMENTS LIMITED ( KIRIT TRADING) |  | 113280
2023-04-17 | SUNTREK CORPORATION |  | 113280
2023-04-17 | SUNTREK CORPORATION |  | 94400
2023-04-18 | SUNTREK CORPORATION |  | 94400
2023-04-22 | SUNTREK CORPORATION |  | 92800
2023-04-23 | SUNTREK CORPORATION |  | 92800
2023-04-23 | SUNTREK CORPORATION |  | 92800
2023-04-23 | SUNTREK CORPORATION |  | 92800
2023-04-24 | SUNTREK CORPORATION |  | 92800
2023-04-24 | SUNTREK CORPORATION |  | 92800
2023-04-25 | SUNTREK CORPORATION |  | 92800
2023-04-26 | SUNTREK CORPORATION |  | 92800
2023-04-26 | SUNTREK CORPORATION |  | 92800
2023-04-26 | SUNTREK CORPORATION |  | 92800
2023-04-27 | SUNTREK CORPORATION |  | 92800
2023-04-27 | SUNTREK CORPORATION |  | 74240
2023-04-27 | SUNTREK CORPORATION |  | 18560
2023-05-02 | SUNTREK CORPORATION |  | 74240
2023-05-02 | SUNTREK CORPORATION |  | 37120
2023-05-02 | SUNTREK CORPORATION |  | 74240
2023-05-02 | SUNTREK CORPORATION |  | 37120
2023-05-02 | SUNTREK CORPORATION |  | 74240
2023-05-02 | SUNTREK CORPORATION |  | 37120
2023-05-04 | SUNTREK CORPORATION |  | 74240
2023-05-04 | SUNTREK CORPORATION |  | 44544
2023-05-04 | SUNTREK CORPORATION |  | 74240
2023-05-04 | SUNTREK CORPORATION |  | 44544
2023-05-05 | SUNTREK CORPORATION |  | 87603.2
2023-05-05 | SUNTREK CORPORATION |  | 28953.6
2023-05-10 | SUNTREK CORPORATION |  | 111360
2023-05-10 | SUNTREK CORPORATION |  | 111360
2023-05-10 | SUNTREK CORPORATION |  | 111360
2023-05-10 | SUNTREK CORPORATION |  | 92800
2023-05-12 | SUNTREK CORPORATION |  | 92800
2023-05-12 | SUNTREK CORPORATION |  | 74240
2023-05-14 | JKLAKSHMI CEMENT LTD |  | 92800
2023-05-16 | KARAN ENTERPRISES |  | 18560
2023-05-16 | JKLAKSHMI CEMENT LTD |  | 74240
2023-05-16 | JKLAKSHMI CEMENT LTD |  | 92800
2023-05-16 | JKLAKSHMI CEMENT LTD |  | 92800
2023-05-17 | JKLAKSHMI CEMENT LTD |  | 92800
2023-05-19 | JKLAKSHMI CEMENT LTD |  | 111360
2023-05-19 | JKLAKSHMI CEMENT LTD |  | 111360
2023-05-19 | JKLAKSHMI CEMENT LTD |  | 111360
2023-05-19 | JKLAKSHMI CEMENT LTD |  | 148480
2023-05-20 | JKLAKSHMI CEMENT LTD |  | 37120
2023-05-20 | JKLAKSHMI CEMENT LTD |  | 74240
2023-05-20 | JKLAKSHMI CEMENT LTD |  | 74240
2023-05-24 | JKLAKSHMI CEMENT LTD |  | 74240
2023-05-25 | JKLAKSHMI CEMENT LTD |  | 111360
2023-05-25 | JKLAKSHMI CEMENT LTD |  | 74240
2023-05-25 | JKLAKSHMI CEMENT LTD |  | 111360
2023-05-25 | JKLAKSHMI CEMENT LTD |  | 74240
2023-05-29 | JKLAKSHMI CEMENT LTD |  | 92800
2023-05-29 | JKLAKSHMI CEMENT LTD |  | 74240
2023-05-29 | JKLAKSHMI CEMENT LTD |  | 92800
2023-05-29 | JKLAKSHMI CEMENT LTD |  | 111360
2023-06-01 | SUNTREK CORPORATION |  | 91200
2023-06-01 | SUNTREK CORPORATION |  | 91200
2023-06-02 | SUNTREK CORPORATION |  | 91200
2023-06-02 | SUNTREK CORPORATION |  | 91200
2023-06-03 | JKLAKSHMI CEMENT LTD |  | 92800
2023-06-03 | JKLAKSHMI CEMENT LTD |  | 111360
2023-06-04 | JKLAKSHMI CEMENT LTD |  | 92800
2023-06-04 | JKLAKSHMI CEMENT LTD |  | 111360
2023-06-10 | SUNTREK CORPORATION |  | 91200
2023-06-10 | SUNTREK CORPORATION |  | 91200
2023-06-10 | SUNTREK CORPORATION |  | 91200
2023-06-11 | SUNTREK CORPORATION |  | 91200
2023-06-15 | SUNTREK CORPORATION |  | 93440
2023-06-15 | SUNTREK CORPORATION |  | 93440
2023-06-15 | JKLAKSHMI CEMENT LTD |  | 37120
2023-06-18 | JKLAKSHMI CEMENT LTD |  | 112128
2023-06-18 | JKLAKSHMI CEMENT LTD |  | 93440
2023-06-19 | JKLAKSHMI CEMENT LTD |  | 93440
2023-06-19 | JKLAKSHMI CEMENT LTD |  | 74752
2023-06-22 | JKLAKSHMI CEMENT LTD |  | 149504
2023-06-23 | JKLAKSHMI CEMENT LTD |  | 93440
2023-06-23 | JKLAKSHMI CEMENT LTD |  | 93440
2023-06-24 | JKLAKSHMI CEMENT LTD |  | 37376
2023-07-04 | KARAN ENTERPRISES |  | 92800
2023-07-04 | KARAN ENTERPRISES |  | 92800
2023-07-04 | KARAN ENTERPRISES |  | 92800
2023-07-07 | JKLAKSHMI CEMENT LTD |  | 111360
2023-07-07 | JKLAKSHMI CEMENT LTD |  | 74240
2023-07-07 | JKLAKSHMI CEMENT LTD |  | 148480
2023-07-07 | JKLAKSHMI CEMENT LTD |  | 92800
2023-07-07 | JKLAKSHMI CEMENT LTD |  | 92800
2023-07-08 | JKLAKSHMI CEMENT LTD |  | 92800
2023-07-15 | JKLAKSHMI CEMENT LTD |  | 18560
2023-07-17 | JKLAKSHMI CEMENT LTD |  | 91840
2023-07-17 | JKLAKSHMI CEMENT LTD |  | 91840
2023-07-17 | JKLAKSHMI CEMENT LTD |  | 91840
2023-07-17 | JKLAKSHMI CEMENT LTD |  | 91840
2023-07-17 | JKLAKSHMI CEMENT LTD |  | 91840
2023-07-17 | JKLAKSHMI CEMENT LTD |  | 91840
2023-07-19 | JKLAKSHMI CEMENT LTD |  | 84800
2023-07-24 | SUNTREK CORPORATION |  | 110208
2023-07-24 | SUNTREK CORPORATION |  | 110208
2023-07-24 | SUNTREK CORPORATION |  | 110208
2023-07-24 | SUNTREK CORPORATION |  | 110208
2023-07-28 | SUNTREK CORPORATION |  | 73472
2023-07-28 | SUNTREK CORPORATION |  | 110208
2023-08-02 | JKLAKSHMI CEMENT LTD |  | 91840
2023-08-02 | JKLAKSHMI CEMENT LTD |  | 91840
2023-08-04 | JKLAKSHMI CEMENT LTD |  | 91840
2023-08-04 | JKLAKSHMI CEMENT LTD |  | 91840
2023-08-05 | JKLAKSHMI CEMENT LTD |  | 73472
2023-08-05 | JKLAKSHMI CEMENT LTD |  | 110208
2023-08-05 | JKLAKSHMI CEMENT LTD |  | 73472
2023-08-07 | SUNTREK CORPORATION |  | 113280
2023-08-07 | SUNTREK CORPORATION |  | 94400
2023-08-07 | SUNTREK CORPORATION |  | 94400
2023-08-11 | KARAN ENTERPRISES |  | 112128
2023-08-14 | SUNTREK CORPORATION |  | 112512
2023-08-14 | SUNTREK CORPORATION |  | 112512
2023-08-14 | SUNTREK CORPORATION |  | 112512
2023-08-14 | SUNTREK CORPORATION |  | 112512
2023-08-17 | KARAN ENTERPRISES |  | 93440
2023-08-17 | KARAN ENTERPRISES |  | 93440
2023-08-20 | KARAN ENTERPRISES |  | 89702.4
2023-08-20 | KARAN ENTERPRISES |  | 74752
2023-08-21 | KARAN ENTERPRISES |  | 134553.6
2023-08-21 | KARAN ENTERPRISES |  | 112128
2023-08-21 | SUNTREK CORPORATION |  | 91520
2023-08-24 | KARAN ENTERPRISES |  | 149504
2023-08-24 | KARAN ENTERPRISES |  | 93440
2023-08-24 | KARAN ENTERPRISES |  | 93440
2023-08-25 | SUNTREK CORPORATION |  | 84800
2023-08-25 | KARAN ENTERPRISES |  | 149504
2023-08-28 | KARAN ENTERPRISES |  | 75264
2023-08-28 | JKLAKSHMI CEMENT LTD |  | 94080
2023-08-28 | JKLAKSHMI CEMENT LTD |  | 94080
2023-08-28 | KARAN ENTERPRISES |  | 74752
2023-08-28 | KARAN ENTERPRISES |  | 93440
2023-08-28 | KARAN ENTERPRISES |  | 93440
2023-08-28 | KARAN ENTERPRISES |  | 149504
2022-03-14 | SHARADA ENTERPRISES |  | 86041.2
2022-03-31 | SHARADA ENTERPRISES |  | 80871
2022-03-31 | S.H.ENTERPRISES |  | 97276.2
2022-03-31 | S.H.ENTERPRISES |  | 97665.76
2022-03-31 | S.H.ENTERPRISES |  | 96387.9
2022-03-31 | S.H.ENTERPRISES |  | 16915.5
2022-04-15 | S.H.ENTERPRISES |  | 8769.6
2022-04-30 | SHARADA ENTERPRISES |  | 59089.8
2022-05-11 | R.K.TRADING CO. |  | 3937.5
2022-06-01 | OM ENTERPRISES-2 |  | 23626
2022-06-30 | GAURAV TRADING CO. |  | 28350
2022-07-15 | SHARADA ENTERPRISES |  | 16783.2
2022-07-25 | S.S.ENTERPRISES |  | 31185
2022-07-31 | S.H.ENTERPRISES |  | 25458.3
2022-08-15 | S.H.ENTERPRISES |  | 74736.9
2022-08-15 | SHARADA ENTERPRISES |  | 42714
2022-09-10 | S.S.ENTERPRISES |  | 33075
2022-09-30 | SHARADA ENTERPRISES |  | 67586.4
2022-10-29 | JSW CEMENT LIMITED |  | 114000
2022-10-30 | SHIV ENTERPRISES |  | 80356.5
2022-10-31 | SHIV ENTERPRISES |  | 63472.5
2022-10-31 | SHIV ENTERPRISES |  | 89925.16
2022-11-03 | SHIV ENTERPRISES |  | 92191.06
2022-11-03 | SHIV ENTERPRISES |  | 84042
2022-11-03 | SHIV ENTERPRISES |  | 42871.5
2022-11-06 | SHIV ENTERPRISES |  | 67455.16
2022-11-16 | SHIV ENTERPRISES |  | 78183
2022-11-17 | SHIV ENTERPRISES |  | 88150.66
2022-11-17 | SHIV ENTERPRISES |  | 90453.3
2022-11-21 | SHIV ENTERPRISES |  | 78624
2022-11-22 | SHIV ENTERPRISES |  | 27416.02
2022-11-23 | SHIV ENTERPRISES |  | 39312
2022-11-25 | SHIV ENTERPRISES |  | 28111.66
2022-12-01 | SHIV ENTERPRISES |  | 80073
2022-12-09 | SHIV ENTERPRISES |  | 91647
2022-12-11 | SHIV ENTERPRISES |  | 60732
2022-12-11 | SHIV ENTERPRISES |  | 54931.99
2022-12-11 | SHIV ENTERPRISES |  | 79443
2022-12-14 | SHIV ENTERPRISES |  | 99934
2022-12-17 | SHIV ENTERPRISES |  | 77910.99
2022-12-20 | SHIV ENTERPRISES |  | 88896
2022-12-21 | SHIV ENTERPRISES |  | 76099
2022-12-22 | SHIV ENTERPRISES |  | 72331.01
2022-12-26 | SHIV ENTERPRISES |  | 79160
2022-12-28 | SHIV ENTERPRISES |  | 88891
2022-12-29 | AMIT CORPORATION |  | 57456
2022-12-29 | SHIV ENTERPRISES |  | 82593
2022-12-30 | JSW CEMENT LIMITED |  | 114000
2022-12-30 | JSW CEMENT LIMITED |  | 114000
2022-12-30 | SHIV ENTERPRISES |  | 45297
2023-01-04 | SHIV ENTERPRISES |  | 88045.66
2023-01-07 | SHIV ENTERPRISES |  | 89634.3
2023-01-11 | SHIV ENTERPRISES |  | 72898.36
2023-01-15 | SHIV ENTERPRISES |  | 84861
2023-01-15 | SHIV ENTERPRISES |  | 99823.5
2023-01-18 | SHIV ENTERPRISES |  | 71396.32
2023-01-19 | SHIV ENTERPRISES |  | 83727
2023-01-20 | SHIV ENTERPRISES |  | 78844.5
2023-01-21 | JSW CEMENT LIMITED |  | 93300
2023-01-23 | SHIV ENTERPRISES |  | 88432.06
2023-01-26 | SHIV ENTERPRISES |  | 92604.76
2023-01-26 | SHIV ENTERPRISES |  | 94195.5
2023-01-28 | SHIV ENTERPRISES |  | 85428
2023-01-30 | SHIV ENTERPRISES |  | 72895.2
2023-01-31 | SHIV ENTERPRISES |  | 91124.26
2023-02-09 | R.K.TRADING CO. |  | 7560
2023-02-20 | JSW CEMENT LIMITED |  | 58312.5
2023-02-26 | JSW CEMENT LIMITED |  | 116625
2023-03-01 | PROFESSIONAL BUILDING CONTRACTOR |  | 132186.6
2023-03-02 | PROFESSIONAL BUILDING CONTRACTOR |  | 198844.8
2023-03-20 | JSW CEMENT LIMITED |  | 58312.5
2023-03-21 | SHIV ENTERPRISES |  | 76979.7
2023-03-21 | SHIV ENTERPRISES |  | 66056.02
2023-03-21 | SHIV ENTERPRISES |  | 76137.6
2023-03-21 | SHIV ENTERPRISES |  | 91047.6
2023-03-21 | SHIV ENTERPRISES |  | 81402.3
2023-03-21 | SHIV ENTERPRISES |  | 65632.88
2023-03-21 | SHIV ENTERPRISES |  | 67821.08
2023-03-21 | SHIV ENTERPRISES |  | 79263.46
2023-03-21 | SHIV ENTERPRISES |  | 91065.98
2023-03-21 | SHIV ENTERPRISES |  | 87403.06
2023-03-21 | SHIV ENTERPRISES |  | 92645.7
2023-03-21 | SHIV ENTERPRISES |  | 95000.86
2023-03-24 | S.S.ENTERPRISES |  | 33075
2023-03-31 | SHIV ENTERPRISES |  | 80289.3
2023-03-31 | SHIV ENTERPRISES |  | 79605.76
2023-03-31 | SHIV ENTERPRISES |  | 61175.62
2023-03-31 | SHIV ENTERPRISES |  | 72609.6
2023-03-31 | SHIV ENTERPRISES |  | 95678.1
2023-03-31 | SHIV ENTERPRISES |  | 54493.96
2023-03-31 | SHIV ENTERPRISES |  | 78960
2023-03-31 | SHIV ENTERPRISES |  | 76876.8
2023-03-31 | SHIV ENTERPRISES |  | 68569.72
2023-03-31 | SHIV ENTERPRISES |  | 71097.6
2023-04-01 | SHIV ENTERPRISES |  | 66066
2023-04-01 | SHIV ENTERPRISES |  | 33691.36
2023-04-03 | S.S.ENTERPRISES |  | 33075
2023-04-07 | SHIV ENTERPRISES |  | 78828.76
2023-04-15 | SHARADA ENTERPRISES |  | 95759.48
2023-04-17 | S.S.ENTERPRISES |  | 33075
2023-04-30 | SHARADA ENTERPRISES |  | 92209.42
2023-04-30 | SHARADA ENTERPRISES |  | 85954.58
2023-04-30 | SHARADA ENTERPRISES |  | 100661.92
2023-04-30 | SHARADA ENTERPRISES |  | 24780.52
2023-04-30 | SHARADA ENTERPRISES |  | 95443.42
2023-04-30 | SHARADA ENTERPRISES |  | 98015.92
2023-04-30 | SHARADA ENTERPRISES |  | 100661.92
2023-04-30 | SHARADA ENTERPRISES |  | 99272.78
2023-04-30 | SHARADA ENTERPRISES |  | 96825.22
2023-04-30 | SHARADA ENTERPRISES |  | 99272.78
2023-04-30 | SHARADA ENTERPRISES |  | 94826.02
2023-04-30 | SHARADA ENTERPRISES |  | 88641
2023-04-30 | SHARADA ENTERPRISES |  | 86719.5
2023-04-30 | SHARADA ENTERPRISES |  | 89783.92
2023-05-11 | PROFESSIONAL BUILDING CONTRACTOR |  | 117499.2
2023-05-15 | SHARADA ENTERPRISES |  | 89754.52
2023-05-15 | SHARADA ENTERPRISES |  | 99456
2023-05-15 | SHARADA ENTERPRISES |  | 91220.86
2023-05-15 | SHARADA ENTERPRISES |  | 90886.42
2023-05-15 | SHARADA ENTERPRISES |  | 96407.86
2023-05-15 | SHARADA ENTERPRISES |  | 99954.22
2023-05-15 | SHARADA ENTERPRISES |  | 97192.72
2023-05-15 | SHARADA ENTERPRISES |  | 96365.86
2023-05-15 | SHARADA ENTERPRISES |  | 95090.62
2023-05-15 | SHARADA ENTERPRISES |  | 91342.12
2023-05-24 | S.S.ENTERPRISES |  | 32634
2023-05-31 | SHARADA ENTERPRISES |  | 92451.46
2023-05-31 | SHARADA ENTERPRISES |  | 76976.02
2023-05-31 | SHARADA ENTERPRISES |  | 92543.86
2023-05-31 | SHARADA ENTERPRISES |  | 93120.82
2023-05-31 | SHARADA ENTERPRISES |  | 87409.88
2023-05-31 | SHARADA ENTERPRISES |  | 99456.52
2023-05-31 | SHARADA ENTERPRISES |  | 95160.46
2023-05-31 | SHARADA ENTERPRISES |  | 91220.86
2023-05-31 | SHARADA ENTERPRISES |  | 96337.5
2023-05-31 | SHARADA ENTERPRISES |  | 95575.72
2023-05-31 | SHARADA ENTERPRISES |  | 92375.86
2023-05-31 | SHARADA ENTERPRISES |  | 85961.4
2023-05-31 | SHARADA ENTERPRISES |  | 89148.16
2023-05-31 | SHARADA ENTERPRISES |  | 96222.52
2023-05-31 | SHARADA ENTERPRISES |  | 86733.68
2023-05-31 | SHARADA ENTERPRISES |  | 25831.58
2023-06-01 | M/S.SHRIYAA ENTERPRISES |  | 96465.6
2023-06-03 | S.S.ENTERPRISES |  | 33075
2023-06-15 | SHARADA ENTERPRISES |  | 94039.58
2023-06-15 | SHARADA ENTERPRISES |  | 98209.66
2023-06-15 | SHARADA ENTERPRISES |  | 96545.92
2023-06-15 | SHARADA ENTERPRISES |  | 96505.5
2023-06-15 | SHARADA ENTERPRISES |  | 87825.16
2023-06-15 | SHARADA ENTERPRISES |  | 99081.68
2023-06-15 | SHARADA ENTERPRISES |  | 74815.66
2023-06-15 | SHARADA ENTERPRISES |  | 99456.52
2023-06-17 | S.S.ENTERPRISES |  | 33075
2023-06-28 | PROFESSIONAL BUILDING CONTRACTOR |  | 93208.5
2023-06-30 | SHARADA ENTERPRISES |  | 93808.06
2023-06-30 | SHARADA ENTERPRISES |  | 76493.02
2023-06-30 | SHARADA ENTERPRISES |  | 99125.78
2023-06-30 | SHARADA ENTERPRISES |  | 99809.32
2023-06-30 | SHARADA ENTERPRISES |  | 95164.12
2023-06-30 | SHARADA ENTERPRISES |  | 84739.2
2023-06-30 | SHARADA ENTERPRISES |  | 74184.6
2023-06-30 | SHARADA ENTERPRISES |  | 63495.08
2023-07-03 | S.S.ENTERPRISES |  | 33075
2023-07-15 | S.H.ENTERPRISES |  | 96898.72
2023-07-15 | S.H.ENTERPRISES |  | 80454.68
2023-07-15 | S.H.ENTERPRISES |  | 94171.88
2023-07-15 | S.H.ENTERPRISES |  | 98645.92
2023-07-15 | S.H.ENTERPRISES |  | 86573.56
2023-07-15 | S.H.ENTERPRISES |  | 90493.2
2023-07-15 | S.H.ENTERPRISES |  | 99485.92
2023-07-15 | S.H.ENTERPRISES |  | 85961.4
2023-07-15 | S.H.ENTERPRISES |  | 100867.72
2023-07-18 | JANATA SAND SUPPLYING CO. |  | 4725
2023-07-31 | S.H.ENTERPRISES |  | 85961.4
2023-07-31 | S.H.ENTERPRISES |  | 98214.38
2023-07-31 | S.H.ENTERPRISES |  | 88431.52
2023-07-31 | S.H.ENTERPRISES |  | 99158.86
2023-07-31 | S.H.ENTERPRISES |  | 91683.9
2023-07-31 | S.H.ENTERPRISES |  | 91683.9
2023-07-31 | S.H.ENTERPRISES |  | 92371.12
2023-07-31 | S.H.ENTERPRISES |  | 80688.3
2023-07-31 | S.H.ENTERPRISES |  | 90067.42
2023-07-31 | S.H.ENTERPRISES |  | 99405.08
2023-07-31 | S.H.ENTERPRISES |  | 92371.12
2023-07-31 | S.H.ENTERPRISES |  | 69412.88
2023-08-01 | S.S.ENTERPRISES |  | 81301.5
2023-08-05 | PROFESSIONAL BUILDING CONTRACTOR |  | 62139
2023-08-05 | PROFESSIONAL BUILDING CONTRACTOR |  | 179136.3
2023-08-13 | RAJLAXMI CORPORATION |  | 89129.78
2023-08-14 | RAJLAXMI CORPORATION |  | 93760.28
2023-08-15 | RAJLAXMI CORPORATION |  | 70736.4
2023-08-15 | S.H.ENTERPRISES |  | 90493.2
2023-08-15 | S.H.ENTERPRISES |  | 77220.68
2023-08-15 | S.H.ENTERPRISES |  | 88957.06
2023-08-15 | S.H.ENTERPRISES |  | 31612.36
2023-08-15 | S.H.ENTERPRISES |  | 81182.32
2023-08-15 | S.H.ENTERPRISES |  | 96615.76
2023-08-15 | S.H.ENTERPRISES |  | 80818.5
2023-08-15 | S.H.ENTERPRISES |  | 95362.58
2023-08-15 | S.H.ENTERPRISES |  | 87762.68
2023-08-19 | S.S.ENTERPRISES |  | 33705
2023-08-21 | S.S.ENTERPRISES |  | 33705
2023-08-31 | S.H.ENTERPRISES |  | 96615.76
2023-08-31 | S.H.ENTERPRISES |  | 99167.26
2023-08-31 | S.H.ENTERPRISES |  | 90388.2
2023-08-31 | S.H.ENTERPRISES |  | 92371.12
2023-08-31 | S.H.ENTERPRISES |  | 83745.9
2023-08-31 | S.H.ENTERPRISES |  | 96898.72
2023-08-31 | S.H.ENTERPRISES |  | 82557.3
2023-08-31 | S.H.ENTERPRISES |  | 87681.82
2023-08-31 | S.H.ENTERPRISES |  | 78730.58
2023-08-31 | S.H.ENTERPRISES |  | 95362.58
2023-08-31 | S.H.ENTERPRISES |  | 98434.88
2023-08-31 | S.H.ENTERPRISES |  | 80818.5
2023-08-31 | S.H.ENTERPRISES |  | 95362.58
2023-08-31 | S.H.ENTERPRISES |  | 87681.82
2023-08-31 | S.H.ENTERPRISES |  | 78821.4
2023-08-31 | S.H.ENTERPRISES |  | 56392.88
2023-03-31 | MAHAVIR MINERALS |  | 220500
2023-07-21 | MAHAVIR MINERALS |  | 110880
2023-08-18 | MAHAVIR MINERALS |  | 120120
2022-03-02 | A1 STAR TRANSPORT |  | 1200
2022-03-15 | OM ENTERPRISES |  | 140000
2022-04-07 | SHRIKANT REDKAR |  | 64658
2022-04-09 | CHETAN ENTERPRISES |  | 2474000
2022-04-12 | SHRIKANT REDKAR | 7 | 15897
2022-04-14 | SHRIKANT REDKAR | 002 | 35446
2022-04-16 | SHRIKANT REDKAR | 003 | 17850
2022-04-18 | SHRIKANT REDKAR | 004 | 17434
2022-04-22 | SHRIKANT REDKAR | 005 | 15930
2022-04-23 | SHRIKANT REDKAR | 006 | 17707
2022-04-23 | GAURI TRANSPORT | 50 | 20192
2022-04-26 | SHRIKANT REDKAR | 007 | 4100
2022-04-27 | SHRIKANT REDKAR | 008 | 15792
2022-05-03 | SHRIKANT REDKAR |  | 31855
2022-05-04 | SHRIKANT REDKAR |  | 15655
2022-05-13 | SHRIKANT REDKAR |  | 15796
2022-05-18 | CHETAN ENTERPRISES |  | 2606000
2022-06-13 | SHRIKANT REDKAR | 012 | 8661
2022-06-21 | PUJARI TRANSPORT | 167 | 10000
2022-06-22 | SHRIKANT REDKAR | 014 | 6737
2022-06-24 | SHRIKANT REDKAR | 015 | 7515
2022-06-29 | GOPI TRANSPORT |  | 1000000
2022-06-30 | GAURI TRANSPORT | 202 | 19564
2022-07-01 | SHRIKANT REDKAR |  | 17367
2022-07-01 | SHRIKANT REDKAR |  | 14387
2022-07-01 | SHRIKANT REDKAR |  | 10495
2022-07-13 | SHRIKANT REDKAR |  | 14657
2022-08-02 | GOPI TRANSPORT |  | 1500000
2022-08-02 | SHRIKANT REDKAR |  | 14956
2022-08-13 | SHRIKANT REDKAR |  | 10214
2022-08-18 | SHRIKANT REDKAR |  | 16300
2022-09-20 | SHRIKANT REDKAR |  | 14319
2022-10-01 | SHRIKANT REDKAR |  | 14185
2022-10-01 | SHREE KRISHNA TRANSPORT |  | 1500000
2022-10-01 | M SOMA SEKHAR |  | 1500000
2022-10-08 | SAIFAN GAFOOR SHAIKH |  | 1900
2022-10-13 | PUJARI TRANSPORT |  | 20088
2022-10-15 | SHRIKANT REDKAR |  | 11210
2022-10-17 | GAURI TRANSPORT |  | 19614
2022-10-17 | SHRIKANT REDKAR |  | 15733
2022-10-18 | SHRIKANT REDKAR |  | 17854
2022-10-31 | PUJARI TRANSPORT |  | 18442
2022-11-01 | A1 STAR TRANSPORT |  | 23850
2022-11-02 | SHRIKANT REDKAR |  | 12498
2022-11-07 | SHRIKANT REDKAR |  | 14520
2022-11-14 | PUJARI TRANSPORT |  | 17325
2022-11-15 | K.R.ENTERPRISES |  | 18000
2022-11-16 | PUJARI TRANSPORT |  | 18848
2022-11-16 | PUJARI TRANSPORT |  | 18542
2022-11-16 | PUJARI TRANSPORT |  | 18344
2022-11-16 | GAURI TRANSPORT |  | 18572
2022-11-16 | SHRIKANT REDKAR |  | 31426
2022-11-16 | SHRIKANT REDKAR |  | 46397
2022-11-26 | GAURI TRANSPORT |  | 18488
2022-11-27 | SHRIKANT REDKAR |  | 13107
2022-12-01 | A1 STAR TRANSPORT |  | 23150
2022-12-10 | SAIFAN GAFOOR SHAIKH |  | 1500
2022-12-15 | SHRIKANT REDKAR |  | 15781
2022-12-21 | SHRIKANT REDKAR |  | 6320
2022-12-29 | SHRIKANT REDKAR |  | 23160
2023-01-01 | HARIOM CARRIERS |  | 24356
2023-01-01 | GAURI TRANSPORT |  | 1500
2023-01-01 | A1 STAR TRANSPORT |  | 3400
2023-01-01 | A1 STAR TRANSPORT |  | 17850
2023-01-02 | SHRIKANT REDKAR |  | 5976
2023-01-06 | SHRIKANT REDKAR |  | 18814
2023-01-10 | SHRIKANT REDKAR |  | 15208
2023-01-12 | SHRIKANT REDKAR |  | 13620
2023-01-12 | HARIOM CARRIERS |  | 24556
2023-01-14 | SHRIKANT REDKAR |  | 15787
2023-02-01 | PUJARI TRANSPORT |  | 18764
2023-02-03 | SHRIKANT REDKAR |  | 15640
2023-02-03 | SHRIKANT REDKAR |  | 10470
2023-02-05 | SHRIKANT REDKAR |  | 26802
2023-02-08 | SHRIKANT REDKAR |  | 22114
2023-02-13 | SHRIKANT REDKAR |  | 19641
2023-02-13 | SHRIKANT REDKAR |  | 4000
2023-02-13 | A1 STAR TRANSPORT |  | 14400
2023-02-13 | A1 STAR TRANSPORT |  | 17000
2023-02-20 | DINESH S.MISHRA HUF |  | 15968
2023-02-20 | GAURI TRANSPORT |  | 17882
2023-02-20 | PUJARI TRANSPORT |  | 18446
2023-03-01 | SHREE KRISHNA TRANSPORT | 188 | 978168
2023-03-01 | SHRIKANT REDKAR | 3 | 24943
2023-03-01 | SHRIKANT REDKAR | 4 | 18902
2023-03-01 | SHRIKANT REDKAR | 5 | 8896
2023-03-01 | SHRIKANT REDKAR |  | 21479
2023-03-01 | PROFESSIONAL BUILDING CONTRACTOR |  | 2850
2023-03-02 | PROFESSIONAL BUILDING CONTRACTOR |  | 5000
2023-03-11 | SHRIKANT REDKAR |  | 26459
2023-03-13 | A1 STAR TRANSPORT |  | 19800
2023-03-13 | A1 STAR TRANSPORT |  | 5950
2023-03-18 | SHRIKANT REDKAR |  | 18870
2023-03-23 | SHRIKANT REDKAR |  | 4345
2023-03-25 | K.R.ENTERPRISES |  | 34400
2023-03-27 | PUJARI TRANSPORT |  | 18398
2023-03-27 | SHRIKANT REDKAR |  | 19580
2023-03-31 | A1 STAR TRANSPORT |  | 16200
2023-03-31 | SGST ON - REVERSE CHARGE |  | 652939
2023-04-01 | K.R.ENTERPRISES | 565 | 17200
2023-04-02 | SHRIKANT REDKAR | 11 | 23172
2023-04-12 | SHRIKANT REDKAR | 12 | 9064
2023-04-16 | SHRIKANT REDKAR | 13 | 11146
2023-04-18 | SHRIKANT REDKAR | 14 | 15739
2023-04-30 | SHRIKANT REDKAR | 15 | 39319
2023-05-01 | A1 STAR TRANSPORT | 473 | 15300
2023-05-01 | K.R.ENTERPRISES | 590 | 12900
2023-05-05 | SHRIKANT REDKAR | 16 | 19997
2023-05-09 | SHRIKANT REDKAR | 17 | 25297
2023-05-11 | PROFESSIONAL BUILDING CONTRACTOR | NIC-ASH-0523-01 | 2500
2023-05-13 | SHRIKANT REDKAR | 18 | 22421
2023-05-15 | GAURI TRANSPORT | 102 | 18614
2023-05-16 | SHRIKANT REDKAR | 19 | 24900
2023-05-23 | SHRIKANT REDKAR | 20 | 15855
2023-06-01 | K.R.ENTERPRISES | 603 | 21500
2023-06-02 | SHRIKANT REDKAR | 22 | 17823
2023-06-02 | SHRIKANT REDKAR | 22 | 44251
2023-06-06 | SHRIKANT REDKAR | 23 | 19243
2023-06-06 | A1 STAR TRANSPORT | 506 | 34000
2023-06-10 | SHRIKANT REDKAR | 24 | 25406
2023-06-19 | SHRIKANT REDKAR | 25 | 30751
2023-06-28 | PROFESSIONAL BUILDING CONTRACTOR | NIC/ASH-0623-01 | 2000
2023-07-03 | SHRIKANT REDKAR | 26 | 34029
2023-07-05 | A1 STAR TRANSPORT | 517 | 26200
2023-07-07 | SHRIKANT REDKAR | 27 | 22538
2023-07-12 | SHRIKANT REDKAR | 28 | 17575
2023-07-17 | SHRIKANT REDKAR | 29 | 25545
2023-07-26 | SHRIKANT REDKAR | 30 | 27125
2023-07-31 | GAURI TRANSPORT | 252 | 17876
2023-07-31 | A1 STAR TRANSPORT | 541 | 6200
2023-08-01 | K.R.ENTERPRISES | 611 | 30100
2023-08-01 | K.R.ENTERPRISES | 623 | 8600
2023-08-02 | SHRIKANT REDKAR | 31 | 31046
2023-08-05 | PROFESSIONAL BUILDING CONTRACTOR | NIC-ASH-0823-01 | 2000
2023-08-05 | PROFESSIONAL BUILDING CONTRACTOR | NIC-ASH-0823-02 | 2000
2023-08-05 | PROFESSIONAL BUILDING CONTRACTOR | NIC-ASH-0823-03 | 1000
2023-08-09 | SHRIKANT REDKAR | 32 | 32807
2023-08-18 | SHRIKANT REDKAR | 33 | 44225
2023-08-23 | PUJARI TRANSPORT |  | 18548
2023-08-24 | SHRIKANT REDKAR | 34 | 24542
2022-04-26 | ASHOK PAWAR |  | 203750
2022-05-16 | WATER PUMP HIRE SERVICE |  | 24000
2022-06-11 | WATER PUMP HIRE SERVICE |  | 27516
2022-06-22 | THAKKAR ELECTRICAL WORKS |  | 43890
2022-07-03 | RAMASHREY PRAJAPATI |  | 11100
2022-07-08 | WATER PUMP HIRE SERVICE |  | 8000
2022-08-01 | MAHENDRA KAWA HUF |  | 23000
2022-09-01 | SURESH ENTERPRISE |  | 172400
2022-09-11 | WATER PUMP HIRE SERVICE |  | 26400
2022-10-02 | WATER PUMP HIRE SERVICE |  | 20275
2022-10-12 | AMIN WATERPROOFING COMPANY |  | 150000
2022-11-07 | RAMASHREY PRAJAPATI |  | 5130
2022-11-07 | RAMASHREY PRAJAPATI |  | 9912
2022-11-29 | ALPAA ENTERPRISE |  | 300000
2022-12-07 | BHIMJI DEVJI PATEL HUF |  | 1404520
2022-12-08 | NARMADABEN BHIMJI PATEL |  | 1404520
2022-12-09 | JAYESH BHIMJI PATEL HUF |  | 1404520
2022-12-10 | DEV JAYESH CHAUHAN |  | 1404520
2022-12-14 | DEEPTI JAYESH CHAUHAN |  | 1404520
2022-12-22 | WATER PUMP HIRE SERVICE |  | 8000
2023-01-01 | RAMASHREY PRAJAPATI |  | 11916
2023-01-01 | RAMASHREY PRAJAPATI |  | 5508
2023-01-02 | PSP ENTERPRISE |  | 1000000
2023-01-02 | ASHA PRAGARAM BORAVAT |  | 785000
2023-01-03 | SUDIP BISWAS |  | 1000000
2023-01-03 | MONI RAJESH DUBEY |  | 500000
2023-01-07 | BHIMJI DEVJI PATEL HUF |  | 593250
2023-01-08 | NUREJA KHATUN NAYYAR ALAM |  | 250000
2023-01-10 | KABITA HALDER |  | 1000000
2023-01-10 | SHAMIM KHALIL ALAM |  | 250000
2023-01-10 | BIPIN RAMESH CHANDRA TIWARI |  | 790000
2023-01-10 | DEV JAYESH CHAUHAN |  | 594000
2023-01-10 | NARMADABEN BHIMJI PATEL |  | 600000
2023-01-11 | ANAND DEVENDRA TIWARI |  | 250000
2023-01-11 | MOHAN SUDHIR YADAV |  | 250000
2023-01-11 | MODH SHAKIL |  | 250000
2023-01-13 | SNEHAL ANAND TIWARI |  | 500000
2023-01-14 | DEEPTI JAYESH CHAUHAN |  | 592000
2023-01-15 | SADAF HUSSAIN AZIZ MULLA |  | 250000
2023-01-15 | RABITA SATENDER SINGH |  | 525300
2023-01-15 | MONIKA SANJAY BORAWAT |  | 785223
2023-01-15 | JAYESH BHIMJI PATEL HUF |  | 591000
2023-01-19 | ALPAA ENTERPRISE |  | 300000
2023-02-01 | WATER PUMP HIRE SERVICE |  | 8000
2023-02-13 | RAMASHREY PRAJAPATI |  | 11388
2023-02-20 | RAMASHREY PRAJAPATI |  | 10860
2023-03-02 | PROFESSIONAL BUILDING CONTRACTOR |  | 26631
2023-03-16 | RAMASHREY PRAJAPATI |  | 11856
2023-03-23 | ALPAA ENTERPRISE |  | 400000
2023-03-23 | BHANU ENTERPRISE |  | 200000
2023-03-23 | TULSSI & COMPANY |  | 100000
2023-03-24 | RAMASHREY PRAJAPATI |  | 8412
2023-04-17 | RAMASHREY PRAJAPATI |  | 8976
2023-05-11 | PROFESSIONAL BUILDING CONTRACTOR |  | 35901
2023-05-14 | WELCOME ENTERPRISES |  | 100000
2023-05-14 | ALPAA ENTERPRISE |  | 100000
2023-05-14 | BHANU ENTERPRISE |  | 100000
2023-05-14 | TULSSI & COMPANY |  | 50000
2023-05-19 | JAGJIVAN PRASAD MISTRY |  | 100795
2023-06-01 | ALPAA ENTERPRISE |  | 50000
2023-07-01 | BHIMJI DEVJI PATEL HUF |  | 110000
2023-07-01 | JAYESH BHIMJI PATEL HUF |  | 155000
2023-07-01 | DEEPTI JAYESH CHAUHAN |  | 125000
2023-07-01 | DEV JAYESH CHAUHAN |  | 150700
2023-07-01 | PRAVIN DAYALAL PATEL HUF |  | 210000
2023-07-01 | SNEHAL ANAND TIWARI |  | 400000
2023-07-01 | ANAND DEVENDRA TIWARI |  | 300000
2023-07-01 | MUSTAK ALAM |  | 600000
2023-07-01 | SHAMIM KHALIL ALAM |  | 600000
2023-07-01 | MOHD SHAKIL ABDUL MATIN |  | 200000
2023-07-01 | MOHAN SUDHIR YADAV |  | 300000
2023-07-01 | SADAF HUSSAIN AZIZ MULLA |  | 200000
2023-07-01 | MONI RAJESH DUBEY |  | 500000
2023-07-01 | DEEPAK SHIVRAM DARJI |  | 400000
2023-07-01 | MENON SANITATION |  | 700000
2023-07-05 | RAMASHREY PRAJAPATI |  | 13932
2023-07-05 | RAMASHREY PRAJAPATI |  | 13224
2023-07-05 | MAHENDRA KAWA HUF |  | 50000
2023-07-06 | WELCOME ENTERPRISES |  | 75000
2023-07-11 | MAHENDRA KAWA HUF |  | 75000
2023-07-17 | KOMAL ENTERPRISES |  | 46000
2023-07-23 | TULSSI & COMPANY |  | 300000
2023-07-23 | BHANU ENTERPRISE |  | 200000
2023-07-23 | ALPAA ENTERPRISE |  | 200000
2023-07-27 | RAJU NISHAD |  | 9600
2023-08-03 | HANSA R. CHAVDA |  | 200000
2023-08-12 | PROFESSIONAL BUILDING CONTRACTOR |  | 49423
2023-08-16 | RAMASHREY PRAJAPATI |  | 15792
2023-08-28 | HANSA R. CHAVDA |  | 200000
2023-08-28 | MD TAMANE |  | 100000
2022-05-30 | ANU FABRICATORS |  | 295000
2022-06-22 | Patel Borewells | 013 | 92158
2022-06-22 | Patel Borewells | 014 | 90058
2022-06-22 | Patel Borewells | 015 | 109931
2022-06-22 | Patel Borewells | 016 | 98320
2022-10-05 | UNITEDONE CONSTRUCTION |  | 25547442.5
2022-11-19 | Patel Borewells |  | 5900
2023-02-01 | SHREEJI WATER PUMPS & BOREWELL |  | 61301
2023-02-10 | SHREEJI WATER PUMPS & BOREWELL |  | 63484
2023-03-02 | UNITEDONE CONSTRUCTION |  | 5900000
2023-04-10 | UNITEDONE CONSTRUCTION | SSDL/03/23-24 | 10000000.86
2023-05-05 | SHREEJI WATER PUMPS & BOREWELL | 027/2023-2024 | 63248
2023-05-05 | UNITEDONE CONSTRUCTION | SSDL/04/23-24 | 12045000
2023-07-01 | UNITEDONE CONSTRUCTION | SSDL/23-24/06 | 1837200.42
2023-09-05 | RECONS BUILDING PRODUCTS PVT.LTD |  | 59873
2023-09-08 | RECONS BUILDING PRODUCTS PVT.LTD |  | 74242.99
2023-09-08 | RECONS BUILDING PRODUCTS PVT.LTD |  | 64238.98
2023-09-11 | RECONS BUILDING PRODUCTS PVT.LTD |  | 53896.01
2023-09-11 | RECONS BUILDING PRODUCTS PVT.LTD |  | 59873
2023-09-11 | RECONS BUILDING PRODUCTS PVT.LTD |  | 66716
2023-09-12 | RECONS BUILDING PRODUCTS PVT.LTD |  | 68023
2023-09-15 | S.H.ENTERPRISES |  | 65408
2023-09-30 | RECONS BUILDING PRODUCTS PVT.LTD |  | 64511
2023-09-30 | RECONS BUILDING PRODUCTS PVT.LTD |  | 54429.99
2023-09-01 | TEJAL ELECTRICAL |  | 120000.58
2023-09-01 | ICARE LIFE SYSTEM |  | 528286
2023-09-04 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1916950.12
2023-09-04 | HINDUSTAN ASSOCIATES |  | 386247.08
2023-09-05 | HITECH CONSTRUCTION AND REPAIRS |  | 87320
2023-09-08 | KARRMANYA ENTERPRISE |  | 172500.66
2023-09-08 | KARRMANYA ENTERPRISE |  | 27600.2
2023-09-08 | EAGLE SALES CORPORATION |  | 140583.91
2023-09-09 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1861631.72
2023-09-11 | RECONS BUILDING PRODUCTS PVT.LTD |  | 6075
2023-09-13 | GODREJ & BOYCE MFG CO.LTD |  | 12599.92
2023-09-13 | GODREJ & BOYCE MFG CO.LTD |  | 16799.9
2023-09-15 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1838417.58
2023-09-16 | KARRMANYA ENTERPRISE |  | 58255.42
2023-09-16 | KARRMANYA ENTERPRISE |  | 180588.38
2023-09-20 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1874970.44
2023-09-22 | D.R LINKS |  | 5964.9
2023-09-22 | KRISHNA CERAMICS |  | 44368
2023-09-27 | R.K.TRADING CO. |  | 14750
2023-09-30 | RECONS BUILDING PRODUCTS PVT.LTD |  | 10125
2023-09-30 | RECONS BUILDING PRODUCTS PVT.LTD |  | 10125.01
2023-09-03 | JKLAKSHMI CEMENT LTD |  | 101760
2023-09-03 | KARAN ENTERPRISES |  | 93440
2023-09-03 | KARAN ENTERPRISES |  | 93440
2023-09-03 | KARAN ENTERPRISES |  | 93440
2023-09-04 | SUNTREK CORPORATION |  | 75008
2023-09-04 | SUNTREK CORPORATION |  | 37504
2023-09-04 | SUNTREK CORPORATION |  | 75008
2023-09-04 | SUNTREK CORPORATION |  | 27377.92
2023-09-04 | SUNTREK CORPORATION |  | 4875.52
2023-09-05 | KARAN ENTERPRISES |  | 93440
2023-09-12 | JKLAKSHMI CEMENT LTD |  | 92800
2023-09-12 | JKLAKSHMI CEMENT LTD |  | 92800
2023-09-12 | JKLAKSHMI CEMENT LTD |  | 92800
2023-09-12 | JKLAKSHMI CEMENT LTD |  | 92800
2023-09-13 | JKLAKSHMI CEMENT LTD |  | 92800
2023-09-13 | JKLAKSHMI CEMENT LTD |  | 74240
2023-09-13 | JKLAKSHMI CEMENT LTD |  | 92800
2023-09-13 | JKLAKSHMI CEMENT LTD |  | 92800
2023-09-13 | JKLAKSHMI CEMENT LTD |  | 92800
2023-09-15 | JKLAKSHMI CEMENT LTD |  | 74240
2023-09-15 | JKLAKSHMI CEMENT LTD |  | 74240
2023-09-21 | JKLAKSHMI CEMENT LTD |  | 92800
2023-09-22 | JKLAKSHMI CEMENT LTD |  | 92800
2023-09-22 | JKLAKSHMI CEMENT LTD |  | 74240
2023-09-22 | JKLAKSHMI CEMENT LTD |  | 92800
2023-09-22 | JKLAKSHMI CEMENT LTD |  | 92800
2023-09-23 | SUNTREK CORPORATION |  | 88192
2023-09-30 | KARAN ENTERPRISES |  | 91840
2023-09-30 | KARAN ENTERPRISES |  | 91840
2023-09-30 | KARAN ENTERPRISES |  | 91840
2023-09-30 | KARAN ENTERPRISES |  | 91840
2023-09-30 | KARAN ENTERPRISES |  | 73472
2023-09-04 | S.S.ENTERPRISES |  | 33705
2023-09-08 | S.S.ENTERPRISES |  | 33705
2023-09-09 | S.S.ENTERPRISES |  | 33705
2023-09-09 | S.S.ENTERPRISES |  | 33705
2023-09-13 | S.S.ENTERPRISES |  | 33705
2023-09-15 | S.S.ENTERPRISES |  | 33705
2023-09-15 | S.H.ENTERPRISES |  | 97060.42
2023-09-15 | S.H.ENTERPRISES |  | 96615.76
2023-09-15 | S.H.ENTERPRISES |  | 87681.82
2023-09-15 | S.H.ENTERPRISES |  | 96665.1
2023-09-15 | S.H.ENTERPRISES |  | 25831.58
2023-09-15 | S.H.ENTERPRISES |  | 88470.38
2023-09-15 | S.H.ENTERPRISES |  | 93705.16
2023-09-15 | S.H.ENTERPRISES |  | 86491.12
2023-09-15 | S.H.ENTERPRISES |  | 75759.08
2023-09-15 | S.H.ENTERPRISES |  | 92411.56
2023-09-15 | S.H.ENTERPRISES |  | 93705.16
2023-09-21 | S.S.ENTERPRISES |  | 33705
2023-09-24 | S.S.ENTERPRISES |  | 33705
2023-09-24 | S.S.ENTERPRISES |  | 33705
2023-09-30 | S.H.ENTERPRISES |  | 86531.56
2023-09-30 | S.H.ENTERPRISES |  | 80607.46
2023-09-30 | S.H.ENTERPRISES |  | 95494.88
2023-09-11 | MAHAVIR MINERALS |  | 110880
2023-09-01 | VELAVAN TRANSPORT | CHQ NO BILL NO-115 | 8600
2023-09-01 | SHRIKANT REDKAR | CH NO 379017 BILL NO-35 | 28284
2023-09-07 | SHRIKANT REDKAR | CH NO 379017 BILL NO-36 | 27365
2023-09-08 | SHRIKANT REDKAR | CH NO 379017 BILL NO-37 | 12426
2023-09-09 | A1 STAR TRANSPORT | Cheque No Bill No 552 | 36800
2023-09-11 | SHRIKANT REDKAR | CH NO 379017 BILL NO-37 | 21689
2023-09-16 | SHRIKANT REDKAR | CH NO.379048 BILL NO.39 | 24956
2023-09-01 | TULSSI & COMPANY | CHEQ.NO.436198 BILL NO 3/23-24 | 600000
2023-09-01 | BHANU ENTERPRISE | Chqque No Bill No BE/5/23-24 | 200000
2023-09-01 | ALPAA ENTERPRISE | Chqque No Bill No AE/4/23-24 | 400000
2023-09-08 | ALI ASGAR UJJAINWALA | CH.NO. | 138167
2023-09-18 | RAMASHREY PRAJAPATI | CH NO.379040 BILL NO.308 | 11904
2023-09-21 | RAMASHREY PRAJAPATI | CH NO.379040 BILL NO.315 | 11664
2023-09-09 | SHREEJI WATER PUMPS & BOREWELL | Chqque No Bill No 086/2023-2024 | 21417
2023-09-09 | UNITEDONE CONSTRUCTION | Cheque No 380501 | 24999480
2023-09-11 | R. R. ENTERPRISES | CH NO.379042 BILL NO.60 | 23895
| TCS on Goods Purchase |  | 1518
2023-10-01 | R. R. ENTERPRISES |  | 24072
2023-10-05 | R. R. ENTERPRISES | 80 | 30255.2
2023-10-12 | R. R. ENTERPRISES | 84 | 21240
2023-11-08 | UNITEDONE CONSTRUCTION | SSDL/07/23-24 | 14160000
2023-11-16 | R. R. ENTERPRISES | 93 | 16555.4
2023-12-07 | R. R. ENTERPRISES | 103 | 19682.4
2023-10-01 | RECONS BUILDING PRODUCTS PVT.LTD |  | 59203.99
2023-10-01 | RECONS BUILDING PRODUCTS PVT.LTD |  | 53896.01
2023-10-01 | RECONS BUILDING PRODUCTS PVT.LTD |  | 56345
2023-10-01 | RECONS BUILDING PRODUCTS PVT.LTD |  | 58795.01
2023-10-01 | RECONS BUILDING PRODUCTS PVT.LTD |  | 58105
2023-10-01 | RECONS BUILDING PRODUCTS PVT.LTD |  | 42871.99
2023-10-01 | RECONS BUILDING PRODUCTS PVT.LTD |  | 51327
2023-10-01 | RECONS BUILDING PRODUCTS PVT.LTD |  | 58795
2023-10-04 | RECONS BUILDING PRODUCTS PVT.LTD |  | 68530
2023-10-07 | RECONS BUILDING PRODUCTS PVT.LTD |  | 68594
2023-10-12 | RECONS BUILDING PRODUCTS PVT.LTD |  | 67370.01
2023-10-12 | RECONS BUILDING PRODUCTS PVT.LTD |  | 57570.01
2023-10-12 | RECONS BUILDING PRODUCTS PVT.LTD |  | 67370.01
2023-10-13 | RECONS BUILDING PRODUCTS PVT.LTD |  | 59447.99
2023-10-13 | RECONS BUILDING PRODUCTS PVT.LTD |  | 71044
2023-10-16 | RECONS BUILDING PRODUCTS PVT.LTD |  | 69003
2023-10-16 | RECONS BUILDING PRODUCTS PVT.LTD |  | 66145
2023-10-16 | RECONS BUILDING PRODUCTS PVT.LTD |  | 66405
2023-10-16 | RECONS BUILDING PRODUCTS PVT.LTD |  | 56171.99
2023-10-16 | RECONS BUILDING PRODUCTS PVT.LTD |  | 55937.01
2023-10-17 | RECONS BUILDING PRODUCTS PVT.LTD |  | 60427.99
2023-10-17 | RECONS BUILDING PRODUCTS PVT.LTD |  | 67370.01
2023-10-18 | RECONS BUILDING PRODUCTS PVT.LTD |  | 68255
2023-10-19 | RECONS BUILDING PRODUCTS PVT.LTD |  | 52144.01
2023-10-23 | RECONS BUILDING PRODUCTS PVT.LTD |  | 55121
2023-10-28 | RECONS BUILDING PRODUCTS PVT.LTD |  | 56345
2023-10-31 | RECONS BUILDING PRODUCTS PVT.LTD |  | 69683
2023-10-31 | RECONS BUILDING PRODUCTS PVT.LTD |  | 68594
2023-11-02 | RECONS BUILDING PRODUCTS PVT.LTD |  | 64920
2023-11-03 | RECONS BUILDING PRODUCTS PVT.LTD |  | 54429.99
2023-11-06 | RECONS BUILDING PRODUCTS PVT.LTD |  | 67370.01
2023-11-06 | RECONS BUILDING PRODUCTS PVT.LTD |  | 67370.01
2023-11-07 | RECONS BUILDING PRODUCTS PVT.LTD |  | 53896.01
2023-11-11 | UN CORPORATION |  | 68665.69
2023-11-16 | RECONS BUILDING PRODUCTS PVT.LTD |  | 68186
2023-11-16 | RECONS BUILDING PRODUCTS PVT.LTD |  | 73045.01
2023-11-17 | RECONS BUILDING PRODUCTS PVT.LTD |  | 53895.97
2023-11-17 | RECONS BUILDING PRODUCTS PVT.LTD |  | 68255
2023-11-20 | RECONS BUILDING PRODUCTS PVT.LTD |  | 66145.01
2023-11-20 | RECONS BUILDING PRODUCTS PVT.LTD |  | 60020.01
2023-11-21 | RECONS BUILDING PRODUCTS PVT.LTD |  | 53886.01
2023-11-22 | RECONS BUILDING PRODUCTS PVT.LTD |  | 66144.99
2023-11-22 | RECONS BUILDING PRODUCTS PVT.LTD |  | 64920
2023-11-24 | RECONS BUILDING PRODUCTS PVT.LTD |  | 66144.99
2023-11-25 | RECONS BUILDING PRODUCTS PVT.LTD |  | 72121.99
2023-11-27 | RECONS BUILDING PRODUCTS PVT.LTD |  | 66145
2023-12-04 | RECONS BUILDING PRODUCTS PVT.LTD |  | 64508.01
2023-12-09 | RECONS BUILDING PRODUCTS PVT.LTD |  | 59730
2023-12-12 | RECONS BUILDING PRODUCTS PVT.LTD |  | 59461
2023-12-16 | UN CORPORATION |  | 67510.8
2023-12-22 | UN CORPORATION |  | 64575.01
2023-12-23 | UN CORPORATION |  | 64050
2023-12-25 | UN CORPORATION |  | 73106.26
2023-12-28 | RECONS BUILDING PRODUCTS PVT.LTD |  | 64127.01
2023-12-28 | RECONS BUILDING PRODUCTS PVT.LTD |  | 60830.99
2023-12-29 | RECONS BUILDING PRODUCTS PVT.LTD |  | 52945.99
2023-12-31 | RECONS BUILDING PRODUCTS PVT.LTD |  | 69843
2023-12-31 | RECONS BUILDING PRODUCTS PVT.LTD |  | 49188.16
2023-10-01 | HINDUSTAN ASSOCIATES |  | 304040.68
2023-10-01 | HINDUSTAN ASSOCIATES |  | 305771.4
2023-10-01 | HINDUSTAN ASSOCIATES |  | 15499.9
2023-10-01 | KARRMANYA ENTERPRISE |  | 12099.72
2023-10-01 | ANUPAM ELECTRICALS |  | 9221.7
2023-10-01 | RECONS BUILDING PRODUCTS PVT.LTD |  | 10125.01
2023-10-01 | RECONS BUILDING PRODUCTS PVT.LTD |  | 20249.99
2023-10-01 | RECONS BUILDING PRODUCTS PVT.LTD |  | 16199.99
2023-10-01 | RECONS BUILDING PRODUCTS PVT.LTD |  | 20250
2023-10-01 | RECONS BUILDING PRODUCTS PVT.LTD |  | 20250.01
2023-10-01 | RECONS BUILDING PRODUCTS PVT.LTD |  | 10125
2023-10-01 | TEJAL ELECTRICAL |  | 159416.82
2023-10-02 | TEJAS CERAMICS |  | 17999.72
2023-10-03 | D.R LINKS |  | 6018
2023-10-04 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1817230.68
2023-10-06 | KARRMANYA ENTERPRISE |  | 51700.52
2023-10-07 | RECONS BUILDING PRODUCTS PVT.LTD |  | 4050
2023-10-08 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1838882.5
2023-10-13 | VEDANT MARKETING |  | 8796.9
2023-10-14 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1745414.7
2023-10-16 | RECONS BUILDING PRODUCTS PVT.LTD |  | 20249.99
2023-10-17 | VEDANT MARKETING |  | 19470
2023-10-19 | RECONS BUILDING PRODUCTS PVT.LTD |  | 12149.99
2023-10-22 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1677648.48
2023-10-23 | S.S.ENTERPRISES |  | 28320
2023-10-23 | RECONS BUILDING PRODUCTS PVT.LTD |  | 20250
2023-10-26 | ARIHANT ELECTRICALS |  | 97937.16
2023-10-27 | ARIHANT ELECTRICALS |  | 90314.26
2023-10-28 | RECONS BUILDING PRODUCTS PVT.LTD |  | 24300
2023-10-28 | ARIHANT ELECTRICALS |  | 98987.26
2023-10-31 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1730781.52
2023-10-31 | ARIHANT ELECTRICALS |  | 412762.25
2023-11-01 | KONE ELEVATOR INDIA PVT LTD |  | 277740.69
2023-11-01 | KONE ELEVATOR INDIA PVT LTD |  | 302664.9
2023-11-01 | KONE ELEVATOR INDIA PVT LTD |  | 298351.81
2023-11-01 | KONE ELEVATOR INDIA PVT LTD |  | 291430
2023-11-01 | KONE ELEVATOR INDIA PVT LTD |  | 301437.4
2023-11-01 | KONE ELEVATOR INDIA PVT LTD |  | 326230
2023-11-01 | KONE ELEVATOR INDIA PVT LTD |  | 321205.09
2023-11-01 | KONE ELEVATOR INDIA PVT LTD |  | 292347.71
2023-11-01 | KONE ELEVATOR INDIA PVT LTD |  | 319232.31
2023-11-01 | KONE ELEVATOR INDIA PVT LTD |  | 269360.09
2023-11-02 | RECONS BUILDING PRODUCTS PVT.LTD |  | 8100
2023-11-03 | RECONS BUILDING PRODUCTS PVT.LTD |  | 8100.01
2023-11-03 | HEM ENTERPRISE |  | 1006894
2023-11-04 | VEDANT MARKETING |  | 11611.2
2023-11-06 | RECONS BUILDING PRODUCTS PVT.LTD |  | 12149.99
2023-11-07 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1744657.14
2023-11-07 | RECONS BUILDING PRODUCTS PVT.LTD |  | 12149.99
2023-11-11 | KARRMANYA ENTERPRISE |  | 25872.68
2023-11-11 | UN CORPORATION |  | 9750.05
2023-11-17 | KRISHNA CERAMICS |  | 14956.5
2023-11-17 | RECONS BUILDING PRODUCTS PVT.LTD |  | 10125.03
2023-11-19 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1752819.2
2023-11-20 | S.S.ENTERPRISES |  | 28320
2023-11-20 | RECONS BUILDING PRODUCTS PVT.LTD |  | 12149.99
2023-11-20 | RECONS BUILDING PRODUCTS PVT.LTD |  | 12149.99
2023-11-21 | P.R.CRAFT AND DESIGN |  | 37413.31
2023-11-21 | P.R.CRAFT AND DESIGN |  | 58731.36
2023-11-21 | RECONS BUILDING PRODUCTS PVT.LTD |  | 12149.99
2023-11-22 | VEDANT MARKETING |  | 14797.2
2023-11-22 | RECONS BUILDING PRODUCTS PVT.LTD |  | 8100.01
2023-11-22 | RECONS BUILDING PRODUCTS PVT.LTD |  | 8100
2023-11-22 | CHETAN ELECTRICALS & HARDWARE |  | 1073.8
2023-11-22 | P.R.CRAFT AND DESIGN |  | 66173.75
2023-11-22 | P.R.CRAFT AND DESIGN |  | 74314.56
2023-11-22 | CHETAN ELECTRICALS & HARDWARE |  | 93497.3
2023-11-23 | KARRMANYA ENTERPRISE |  | 155232.54
2023-11-24 | RECONS BUILDING PRODUCTS PVT.LTD |  | 6075.01
2023-11-24 | P.R.CRAFT AND DESIGN |  | 77978.1
2023-11-24 | P.R.CRAFT AND DESIGN |  | 83382.34
2023-11-25 | RECONS BUILDING PRODUCTS PVT.LTD |  | 6075.01
2023-11-25 | ANUPAM ELECTRICALS |  | 2301
2023-11-27 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1813359.1
2023-11-27 | ANUPAM ELECTRICALS |  | 6254
2023-11-28 | HINDUSTAN ASSOCIATES |  | 402997.14
2023-11-30 | HINDUSTAN ASSOCIATES |  | 15499.9
2023-12-02 | VEDANT MARKETING |  | 8796.9
2023-12-02 | P.R.CRAFT AND DESIGN |  | 92078.64
2023-12-02 | P.R.CRAFT AND DESIGN |  | 81480.35
2023-12-03 | R.K.TRADING CO. |  | 15646.8
2023-12-03 | CHETAN ELECTRICALS & HARDWARE |  | 5315.9
2023-12-03 | CHETAN ELECTRICALS & HARDWARE |  | 1943.46
2023-12-04 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1604417.68
2023-12-04 | RECONS BUILDING PRODUCTS PVT.LTD |  | 16199.99
2023-12-04 | P.R.CRAFT AND DESIGN |  | 80206.92
2023-12-06 | P.R.CRAFT AND DESIGN |  | 91763.32
2023-12-06 | P.R.CRAFT AND DESIGN |  | 93516.74
2023-12-07 | ANUPAM ELECTRICALS |  | 59590
2023-12-09 | P.R.CRAFT AND DESIGN |  | 72818.74
2023-12-09 | P.R.CRAFT AND DESIGN |  | 79804
2023-12-09 | HINDUSTAN ASSOCIATES |  | 102719.48
2023-12-09 | HINDUSTAN ASSOCIATES |  | 61999.56
2023-12-09 | HINDUSTAN ASSOCIATES |  | 123999.12
2023-12-11 | P.R.CRAFT AND DESIGN |  | 106269.66
2023-12-11 | HINDUSTAN ASSOCIATES |  | 27899.8
2023-12-12 | RECONS BUILDING PRODUCTS PVT.LTD |  | 20250
2023-12-12 | ARIHANT ELECTRICALS |  | 99726.88
2023-12-13 | KRISHNA TRADING CORPORATION |  | 99828
2023-12-13 | D.R LINKS |  | 41696.48
2023-12-13 | ARIHANT ELECTRICALS |  | 98459.2
2023-12-14 | TEJAL ELECTRICAL |  | 299999.66
2023-12-14 | KRISHNA TRADING CORPORATION |  | 17875.7
2023-12-15 | ARIHANT ELECTRICALS |  | 301813.56
2023-12-16 | UN CORPORATION |  | 9749.99
2023-12-17 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1807634.92
2023-12-18 | TEJAS CERAMICS |  | 18000.26
2023-12-19 | D.R LINKS |  | 16614.4
2023-12-19 | KRISHNA TRADING CORPORATION |  | 2212.5
2023-12-20 | S.S.ENTERPRISES |  | 28320
2023-12-21 | HINDUSTAN ASSOCIATES |  | 21699.84
2023-12-21 | VEDANT MARKETING |  | 9699.6
2023-12-22 | UN CORPORATION |  | 19500.1
2023-12-23 | UN CORPORATION |  | 19500
2023-12-24 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1847731.32
2023-12-29 | D.R LINKS |  | 13275
2023-12-29 | D.R LINKS |  | 4633.86
2023-10-01 | JANATA SAND SUPPLYING CO. |  | 1749.76
2023-10-05 | JKLAKSHMI CEMENT LTD |  | 74240
2023-10-05 | JKLAKSHMI CEMENT LTD |  | 74240
2023-10-06 | KARAN ENTERPRISES |  | 84800
2023-10-07 | SUNTREK CORPORATION |  | 78080
2023-10-11 | KARAN ENTERPRISES |  | 117120
2023-10-12 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 96000
2023-10-13 | JKLAKSHMI CEMENT LTD |  | 92800
2023-10-13 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 102400
2023-10-14 | JKLAKSHMI CEMENT LTD |  | 129920
2023-10-20 | JKLAKSHMI CEMENT LTD |  | 102400
2023-10-20 | JKLAKSHMI CEMENT LTD |  | 102400
2023-10-20 | JKLAKSHMI CEMENT LTD |  | 102400
2023-10-20 | JKLAKSHMI CEMENT LTD |  | 102400
2023-10-23 | JANATA SAND SUPPLYING CO. |  | 4000
2023-10-25 | KIRIT TRADING COMPANY |  | 80640
2023-10-25 | KIRIT TRADING COMPANY |  | 80640
2023-10-25 | KIRIT TRADING COMPANY |  | 80640
2023-10-25 | KIRIT TRADING COMPANY |  | 80640
2023-10-25 | KIRIT TRADING COMPANY |  | 80640
2023-10-25 | KIRIT TRADING COMPANY |  | 80640
2023-10-25 | SNEH ENTERPRISE |  | 94400
2023-10-30 | SNEH ENTERPRISE |  | 94400
2023-10-31 | SUNTREK CORPORATION |  | 95155.2
2023-10-31 | SUNTREK CORPORATION |  | 120960
2023-10-31 | SUNTREK CORPORATION |  | 120960
2023-10-31 | KARAN ENTERPRISES |  | 78080
2023-11-02 | JKLAKSHMI CEMENT LTD |  | 92800
2023-11-02 | SUNTREK CORPORATION |  | 80640
2023-11-02 | SUNTREK CORPORATION |  | 40320
2023-11-06 | SUNTREK CORPORATION |  | 120960
2023-11-06 | SUNTREK CORPORATION |  | 120960
2023-11-11 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 120960
2023-11-18 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 120960
2023-11-18 | JKLAKSHMI CEMENT LTD |  | 74240
2023-11-18 | JKLAKSHMI CEMENT LTD |  | 89600
2023-11-21 | JKLAKSHMI CEMENT LTD |  | 96000
2023-11-21 | JKLAKSHMI CEMENT LTD |  | 96000
2023-11-21 | JKLAKSHMI CEMENT LTD |  | 96000
2023-11-23 | KIRIT TRADING COMPANY |  | 78080
2023-11-23 | JKLAKSHMI CEMENT LTD |  | 76800
2023-11-23 | JKLAKSHMI CEMENT LTD |  | 96000
2023-11-27 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 71680
2023-12-01 | SUNTREK CORPORATION |  | 113280
2023-12-01 | SUNTREK CORPORATION |  | 94400
2023-12-01 | SUNTREK CORPORATION |  | 94400
2023-12-02 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 115200
2023-12-02 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 31488
2023-12-02 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 83712
2023-12-02 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 18432
2023-12-02 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 96768
2023-12-02 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 76800
2023-12-03 | JKLAKSHMI CEMENT LTD |  | 88640
2023-12-10 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 113280
2023-12-10 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 75520
2023-12-10 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 75520
2023-12-12 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 88000
2023-12-16 | KIRIT TRADING COMPANY |  | 87360
2023-12-17 | JKLAKSHMI CEMENT LTD |  | 92800
2023-12-17 | JKLAKSHMI CEMENT LTD |  | 18560
2023-12-17 | JKLAKSHMI CEMENT LTD |  | 74240
2023-12-17 | JKLAKSHMI CEMENT LTD |  | 74240
2023-12-17 | JKLAKSHMI CEMENT LTD |  | 74240
2023-12-17 | JKLAKSHMI CEMENT LTD |  | 74240
2023-12-21 | JKLAKSHMI CEMENT LTD |  | 92800
2023-12-21 | JKLAKSHMI CEMENT LTD |  | 92800
2023-12-21 | JKLAKSHMI CEMENT LTD |  | 92800
2023-12-21 | JKLAKSHMI CEMENT LTD |  | 92800
2023-12-22 | JKLAKSHMI CEMENT LTD |  | 37120
2023-12-26 | JKLAKSHMI CEMENT LTD |  | 92800
2023-12-26 | JKLAKSHMI CEMENT LTD |  | 92800
2023-12-26 | KIRIT TRADING COMPANY |  | 104832
2023-12-27 | JKLAKSHMI CEMENT LTD |  | 74240
2023-12-28 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 111360
2023-12-28 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 111360
2023-10-01 | JANATA SAND SUPPLYING CO. |  | 9450
2023-10-02 | S.S.ENTERPRISES |  | 33705
2023-10-03 | S.S.ENTERPRISES |  | 33705
2023-10-03 | S.S.ENTERPRISES |  | 34650
2023-10-03 | S.S.ENTERPRISES |  | 34650
2023-10-06 | S.S.ENTERPRISES |  | 34650
2023-10-08 | AMIT CORPORATION |  | 85583.4
2023-10-08 | AMIT CORPORATION |  | 88369.06
2023-10-08 | AMIT CORPORATION |  | 72438.98
2023-10-10 | RAJLAXMI CORPORATION |  | 91298.02
2023-10-11 | S.S.ENTERPRISES |  | 33705
2023-10-11 | S.S.ENTERPRISES |  | 33705
2023-10-11 | RAJLAXMI CORPORATION |  | 94107.82
2023-10-12 | RAJLAXMI CORPORATION |  | 89243.18
2023-10-13 | RAJLAXMI CORPORATION |  | 93172.28
2023-10-13 | AMIT CORPORATION |  | 90205.5
2023-10-13 | AMIT CORPORATION |  | 85054.2
2023-10-13 | AMIT CORPORATION |  | 35036.4
2023-10-14 | M/S.SHRIYAA ENTERPRISES |  | 85377.6
2023-10-14 | RAJLAXMI CORPORATION |  | 80971.28
2023-10-15 | RAJLAXMI CORPORATION |  | 83349
2023-10-16 | S.S.ENTERPRISES |  | 33705
2023-10-16 | RAJLAXMI CORPORATION |  | 99993.08
2023-10-18 | S.S.ENTERPRISES |  | 33705
2023-10-19 | GLOBAL GYPSUM PVT LTD |  | 115500
2023-10-19 | S.S.ENTERPRISES |  | 34650
2023-10-19 | S.S.ENTERPRISES |  | 33705
2023-10-21 | S.S.ENTERPRISES |  | 34650
2023-10-23 | S.S.ENTERPRISES |  | 34650
2023-10-26 | S.S.ENTERPRISES |  | 34650
2023-10-26 | S.S.ENTERPRISES |  | 34650
2023-10-28 | M/S.SHRIYAA ENTERPRISES |  | 181269.9
2023-10-30 | RAJLAXMI CORPORATION |  | 67149.6
2023-10-30 | S.S.ENTERPRISES |  | 33705
2023-10-31 | M/S.SHRIYAA ENTERPRISES |  | 58926
2023-10-31 | S.H.ENTERPRISES |  | 87641.4
2023-10-31 | S.H.ENTERPRISES |  | 87832.5
2023-10-31 | S.H.ENTERPRISES |  | 89702.02
2023-10-31 | S.H.ENTERPRISES |  | 99576.76
2023-10-31 | S.H.ENTERPRISES |  | 89518.28
2023-10-31 | S.H.ENTERPRISES |  | 59650.5
2023-10-31 | S.S.ENTERPRISES |  | 34650
2023-10-31 | S.S.ENTERPRISES |  | 34650
2023-11-01 | M/S.SHRIYAA ENTERPRISES |  | 64194.9
2023-11-03 | M/S.SHRIYAA ENTERPRISES |  | 38253.6
2023-11-04 | S.S.ENTERPRISES |  | 33705
2023-11-07 | AL-BURHAN SAFETY PRODUCTS |  | 31500
2023-11-07 | SHIV ENTERPRISES |  | 98180.78
2023-11-09 | SHIV ENTERPRISES |  | 80324.48
2023-11-10 | M/S.SHRIYAA ENTERPRISES |  | 150693.9
2023-11-10 | GLOBAL GYPSUM PVT LTD |  | 110880
2023-11-15 | S.H.ENTERPRISES |  | 77020.66
2023-11-16 | S.S.ENTERPRISES |  | 33705
2023-11-17 | M/S.SHRIYAA ENTERPRISES |  | 61645.5
2023-11-20 | S.S.ENTERPRISES |  | 33705
2023-11-24 | M/S.SHRIYAA ENTERPRISES |  | 192912.3
2023-11-27 | RAJLAXMI CORPORATION |  | 83234.56
2023-11-27 | M/S.SHRIYAA ENTERPRISES |  | 62543.26
2023-11-29 | AL-BURHAN SAFETY PRODUCTS |  | 31500
2023-11-30 | M/S.SHRIYAA ENTERPRISES |  | 61545.76
2023-11-30 | M/S.SHRIYAA ENTERPRISES |  | 121907.62
2023-11-30 | S.H.ENTERPRISES |  | 81717.3
2023-11-30 | S.H.ENTERPRISES |  | 28095.34
2023-11-30 | S.H.ENTERPRISES |  | 57881.26
2023-11-30 | S.H.ENTERPRISES |  | 58608.9
2023-11-30 | RAJ TRANSIT INFRA PVT LTD |  | 25831.58
2023-11-30 | RAJLAXMI CORPORATION |  | 90066.9
2023-12-03 | R.K.TRADING CO. |  | 630
2023-12-03 | M/S.SHRIYAA ENTERPRISES |  | 57960
2023-12-06 | RAJLAXMI CORPORATION |  | 80597.48
2023-12-07 | RAJLAXMI CORPORATION |  | 74386.2
2023-12-11 | M/S.SHRIYAA ENTERPRISES |  | 120568.36
2023-12-15 | M/S.SHRIYAA ENTERPRISES |  | 248163.3
2023-12-15 | M/S.SHRIYAA ENTERPRISES |  | 58489.2
2023-12-15 | RAJLAXMI CORPORATION |  | 87995.26
2023-12-15 | S.H.ENTERPRISES |  | 94792.96
2023-12-15 | S.H.ENTERPRISES |  | 92751.22
2023-12-18 | S.S.ENTERPRISES |  | 33705
2023-12-23 | S.S.ENTERPRISES |  | 33075
2023-12-23 | S.S.ENTERPRISES |  | 33075
2023-12-23 | SHIV ENTERPRISES |  | 70715.4
2023-12-26 | SHIV ENTERPRISES |  | 60591.82
2023-12-27 | SHIV ENTERPRISES |  | 55992.82
2023-12-27 | S.S.ENTERPRISES |  | 33075
2023-12-29 | SHIV ENTERPRISES |  | 80330.26
2023-12-29 | SHIV ENTERPRISES |  | 51585.46
2023-12-30 | S.S.ENTERPRISES |  | 33075
2023-12-30 | S.S.ENTERPRISES |  | 33075
2023-12-30 | M/S.SHRIYAA ENTERPRISES |  | 82467
2023-12-30 | M/S.SHRIYAA ENTERPRISES |  | 105204.76
2023-12-30 | M/S.SHRIYAA ENTERPRISES |  | 61051.2
2023-12-31 | S.H.ENTERPRISES |  | 81365.56
2023-12-31 | S.H.ENTERPRISES |  | 86744.18
2023-12-31 | S.H.ENTERPRISES |  | 78059.1
2023-12-31 | S.H.ENTERPRISES |  | 94114.12
2023-12-31 | S.H.ENTERPRISES |  | 60131.92
2023-10-31 | S.H.ENTERPRISES |  | 30952
2023-11-30 | S.H.ENTERPRISES |  | 60844
2023-12-23 | SHREEJI WOODCRAFT PVT LTD |  | 212503.84
2023-12-23 | SHREEJI WOODCRAFT PVT LTD |  | 104434.72
2023-10-06 | MAHAVIR MINERALS |  | 120120
2023-10-28 | MAHAVIR MINERALS |  | 110880
2023-12-12 | MAHAVIR MINERALS |  | 120120
2023-12-21 | MAHAVIR MINERALS |  | 120120
2023-10-01 | SHRIKANT REDKAR | 40 | 34517
2023-10-01 | VELAVAN TRANSPORT | 120 | 38700
2023-10-04 | SHRIKANT REDKAR | 41 | 29958
2023-10-10 | SHRIKANT REDKAR | 42 | 34749
2023-10-15 | SHRIKANT REDKAR | 001 | 43472
2023-10-19 | SHRIKANT REDKAR | 002 | 33710
2023-11-01 | A1 STAR TRANSPORT | 565 | 47000
2023-11-01 | SHRIKANT REDKAR | 003 | 22078
2023-11-01 | VELAVAN TRANSPORT | 124 | 68800
2023-11-04 | SHRIKANT REDKAR | 004 | 15020
2023-11-04 | SHRIKANT REDKAR | 005 | 29475
2023-11-08 | A1 STAR TRANSPORT | 589 | 61200
2023-11-16 | SHRIKANT REDKAR | 006 | 36903
2023-11-20 | SHRIKANT REDKAR | 007 | 36632
2023-11-24 | SHRIKANT REDKAR | 008 | 15550
2023-12-01 | VELAVAN TRANSPORT | 130 | 73100
2023-12-05 | BALAJI TRANSPORT | 460 | 56000
2023-12-05 | SHRIKANT REDKAR | 010 | 27932
2023-12-07 | SHRIKANT REDKAR | 009 | 32478
2023-12-11 | A1 STAR TRANSPORT | 625 | 7000
2023-12-19 | SHRIKANT REDKAR | 012 | 26931
2023-10-01 | HANSA R. CHAVDA |  | 200000
2023-10-01 | KRISHNA R. CHAVDA |  | 100000
2023-10-01 | ALPAA ENTERPRISE |  | 200000
2023-10-01 | BHANU ENTERPRISE |  | 100000
2023-10-01 | TULSSI & COMPANY |  | 100000
2023-10-06 | MAHENDRA KAWA HUF |  | 100000
2023-10-08 | SHUBHAM D VISHWAKARMA |  | 575000
2023-10-12 | RAMASHREY PRAJAPATI |  | 19224
2023-10-12 | RAMASHREY PRAJAPATI |  | 5364
2023-10-16 | WELCOME ENTERPRISES |  | 300000
2023-11-01 | SAVITABEN K.CHAVDA |  | 500000
2023-11-01 | TULSSI & COMPANY |  | 100000
2023-11-01 | TEJAL ENTERPRISE |  | 100000
2023-11-01 | ALPAA ENTERPRISE |  | 100000
2023-11-03 | RAMASHREY PRAJAPATI |  | 5304
2023-11-03 | ALI ASGAR UJJAINWALA |  | 89383
2023-11-08 | ALI ASGAR UJJAINWALA |  | 32414.5
2023-12-01 | TEJAL ENTERPRISE |  | 100000
2023-12-02 | WELCOME ENTERPRISES |  | 150000
2023-12-05 | VISHWANATH G MENON HUF |  | 700000
2023-12-05 | TULSSI & COMPANY |  | 200000
2023-12-05 | BHANU ENTERPRISE |  | 200000
2023-12-10 | ALPAA ENTERPRISE |  | 200000
2023-12-19 | MD TAMANE |  | 200000
2023-12-19 | HANSA R. CHAVDA |  | 200000
2023-12-19 | JAYESH MAHESH BHAI PARMAR |  | 100000
| TCS on goods Purchase |  | 2676
2024-01-03 | RECONS BUILDING PRODUCTS PVT.LTD |  | 6008.01
2024-01-03 | RECONS BUILDING PRODUCTS PVT.LTD |  | 66083.99
2024-01-03 | RECONS BUILDING PRODUCTS PVT.LTD |  | 43934.01
2024-01-04 | RECONS BUILDING PRODUCTS PVT.LTD |  | 67181
2024-01-04 | RECONS BUILDING PRODUCTS PVT.LTD |  | 63877
2024-01-09 | RECONS BUILDING PRODUCTS PVT.LTD |  | 43436
2024-01-09 | RECONS BUILDING PRODUCTS PVT.LTD |  | 58578.01
2024-01-09 | RECONS BUILDING PRODUCTS PVT.LTD |  | 61958
2024-01-09 | RECONS BUILDING PRODUCTS PVT.LTD |  | 55199
2024-01-11 | RECONS BUILDING PRODUCTS PVT.LTD |  | 51819
2024-01-11 | RECONS BUILDING PRODUCTS PVT.LTD |  | 70484
2024-01-11 | RECONS BUILDING PRODUCTS PVT.LTD |  | 68717
2024-02-03 | R.K.TRADING CO. |  | 2912
2024-02-05 | RECONS BUILDING PRODUCTS PVT.LTD |  | 52946
2024-02-05 | RECONS BUILDING PRODUCTS PVT.LTD |  | 69392
2024-02-06 | RECONS BUILDING PRODUCTS PVT.LTD |  | 53463.99
2024-02-08 | AL-BURHAN SAFETY PRODUCTS |  | 13059.2
2024-02-09 | RECONS BUILDING PRODUCTS PVT.LTD |  | 69392
2024-02-13 | AL-BURHAN SAFETY PRODUCTS |  | 10299.52
2024-02-14 | RECONS BUILDING PRODUCTS PVT.LTD |  | 59207
2024-02-14 | RECONS BUILDING PRODUCTS PVT.LTD |  | 61958
2024-02-14 | RECONS BUILDING PRODUCTS PVT.LTD |  | 61582.01
2024-02-14 | RECONS BUILDING PRODUCTS PVT.LTD |  | 57269
2024-02-14 | RECONS BUILDING PRODUCTS PVT.LTD |  | 68717
2024-02-14 | RECONS BUILDING PRODUCTS PVT.LTD |  | 51519
2024-02-14 | RECONS BUILDING PRODUCTS PVT.LTD |  | 62557.99
2024-02-14 | RECONS BUILDING PRODUCTS PVT.LTD |  | 57169.01
2024-02-16 | RECONS BUILDING PRODUCTS PVT.LTD |  | 70969.99
2024-03-03 | AL-BURHAN SAFETY PRODUCTS |  | 3248
2024-03-05 | RECONS BUILDING PRODUCTS PVT.LTD |  | 67589.99
2024-03-07 | RECONS BUILDING PRODUCTS PVT.LTD |  | 42807
2024-03-07 | RECONS BUILDING PRODUCTS PVT.LTD |  | 61460
2024-03-08 | RECONS BUILDING PRODUCTS PVT.LTD |  | 46765
2024-03-12 | RECONS BUILDING PRODUCTS PVT.LTD |  | 62775.01
2024-03-12 | RECONS BUILDING PRODUCTS PVT.LTD |  | 54072
2024-03-15 | S.H.ENTERPRISES |  | 31360
2024-03-30 | RECONS BUILDING PRODUCTS PVT.LTD |  | 68717
2024-03-30 | RECONS BUILDING PRODUCTS PVT.LTD |  | 30040.01
2024-03-30 | RECONS BUILDING PRODUCTS PVT.LTD |  | 60080
2024-03-30 | RECONS BUILDING PRODUCTS PVT.LTD |  | 60830.99
2024-03-30 | RECONS BUILDING PRODUCTS PVT.LTD |  | 62787.99
2024-01-01 | R.K.TRADING CO. |  | 14927
2024-01-01 | ARIHANT ELECTRICALS |  | 97682.76
2024-01-03 | RECONS BUILDING PRODUCTS PVT.LTD |  | 6075.01
2024-01-03 | RECONS BUILDING PRODUCTS PVT.LTD |  | 20249.99
2024-01-03 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1713896.9
2024-01-04 | ANUPAM ELECTRICALS |  | 14248.5
2024-01-04 | KRISHNA TRADING CORPORATION |  | 836.79
2024-01-05 | ARIHANT ELECTRICALS |  | 96243.76
2024-01-06 | KRISHNA TRADING CORPORATION |  | 611.24
2024-01-08 | KRISHNA TRADING CORPORATION |  | 2017.8
2024-01-09 | ARIHANT ELECTRICALS |  | 389434.58
2024-01-09 | KARRMANYA ENTERPRISE |  | 133458
2024-01-09 | KARRMANYA ENTERPRISE |  | 74468.62
2024-01-09 | RECONS BUILDING PRODUCTS PVT.LTD |  | 20250
2024-01-10 | KARRMANYA ENTERPRISE |  | 207000.32
2024-01-10 | ANUPAM ELECTRICALS |  | 8283.6
2024-01-11 | ARIHANT ELECTRICALS |  | 97184.8
2024-01-11 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1735090.88
2024-01-11 | RECONS BUILDING PRODUCTS PVT.LTD |  | 20250
2024-01-12 | SUPREME GYPSUM PVT LTD |  | 95875
2024-01-13 | ARIHANT ELECTRICALS |  | 319453.42
2024-01-16 | AVINASH ENTERPRISE |  | 1399999.2
2024-01-19 | HINDUSTAN ASSOCIATES |  | 27030.26
2024-01-19 | HINDUSTAN ASSOCIATES |  | 21624.2
2024-01-19 | HINDUSTAN ASSOCIATES |  | 453839.8
2024-01-20 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1734430.08
2024-01-23 | VEDANT MARKETING |  | 8796.9
2024-01-24 | VEDANT MARKETING |  | 8796.9
2024-01-24 | KRISHNA TRADING CORPORATION |  | 6490
2024-01-24 | S.S.ENTERPRISES |  | 14573
2024-01-28 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1675008.82
2024-01-29 | ICARE LIFT SYSTEM |  | 124254
2024-01-29 | KRISHNA TRADING CORPORATION |  | 3056.2
2024-02-01 | DILIP PAINT& HARDWARE STORES |  | 7670
2024-02-02 | HITECH CONSTRUCTION AND REPAIRS |  | 43660
2024-02-03 | R.K.TRADING CO. |  | 14750
2024-02-03 | KRISHNA TRADING CORPORATION |  | 974.97
2024-02-04 | PADMAVATI DECOR |  | 290868.12
2024-02-04 | PADMAVATI DECOR |  | 196726.3
2024-02-05 | RECONS BUILDING PRODUCTS PVT.LTD |  | 16200
2024-02-09 | S.S.ENTERPRISES |  | 14573
2024-02-09 | HITECH CONSTRUCTION AND REPAIRS |  | 43660
2024-02-09 | VEDANT MARKETING |  | 44108.4
2024-02-09 | PADMAVATI DECOR |  | 158405.97
2024-02-10 | TEJAL ELECTRICAL |  | 499999.74
2024-02-12 | S.S.ENTERPRISES |  | 14573
2024-02-13 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1719139.64
2024-02-13 | S.S.ENTERPRISES |  | 28320
2024-02-13 | AL-BURHAN SAFETY PRODUCTS |  | 102515.36
2024-02-14 | RECONS BUILDING PRODUCTS PVT.LTD |  | 16199.98
2024-02-14 | RECONS BUILDING PRODUCTS PVT.LTD |  | 10125
2024-02-14 | RECONS BUILDING PRODUCTS PVT.LTD |  | 10125.01
2024-02-14 | S.S.ENTERPRISES |  | 14573
2024-02-14 | VEDANT MARKETING |  | 26479.2
2024-02-14 | ANUPAM ELECTRICALS |  | 58102.02
2024-02-14 | RECONS BUILDING PRODUCTS PVT.LTD |  | 12149.99
2024-02-19 | S.S.ENTERPRISES |  | 28320
2024-02-21 | KARRMANYA ENTERPRISE |  | 274399.56
2024-02-22 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1852441.88
2024-02-26 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1740523.6
2024-02-28 | PEARL CERAMICS |  | 216837.86
2024-02-28 | PEARL CERAMICS |  | 216837.86
2024-03-02 | R.K.TRADING CO. |  | 14160
2024-03-03 | AL-BURHAN SAFETY PRODUCTS |  | 2200
2024-03-05 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1702342.34
2024-03-06 | KARRMANYA ENTERPRISE |  | 22136.8
2024-03-06 | HINDUSTAN ASSOCIATES |  | 650998.92
2024-03-07 | RECONS BUILDING PRODUCTS PVT.LTD |  | 20250
2024-03-08 | RECONS BUILDING PRODUCTS PVT.LTD |  | 20250
2024-03-08 | HINDUSTAN ASSOCIATES |  | 1030748.3
2024-03-12 | ICARE LIFT SYSTEM |  | 299999.66
2024-03-12 | RECONS BUILDING PRODUCTS PVT.LTD |  | 16200
2024-03-12 | P.R.CRAFT AND DESIGN |  | 15312.86
2024-03-12 | KARRMANYA ENTERPRISE |  | 177082.6
2024-03-12 | R.K.TRADERS |  | 2756.48
2024-03-12 | JYOTI KITCHEN INDUSTRIES PVT LTD |  | 137080.12
2024-03-12 | DILIP PAINT& HARDWARE STORES |  | 15340
2024-03-13 | ICARE LIFT SYSTEM |  | 281386.34
2024-03-14 | KARRMANYA ENTERPRISE |  | 2449.68
2024-03-15 | TEJAS CERAMICS |  | 17999.64
2024-03-18 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1749292.18
2024-03-18 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1893466.94
2024-03-18 | ARIHANT ELECTRICALS |  | 90258.68
2024-03-19 | VEDANT MARKETING |  | 8796.9
2024-03-20 | ARIHANT ELECTRICALS |  | 95240.76
2024-03-20 | RISHABH ENTERPRISE |  | 316901.64
2024-03-22 | ARIHANT ELECTRICALS |  | 98825
2024-03-22 | RISHABH ENTERPRISE |  | 285860.86
2024-03-26 | ARIHANT ELECTRICALS |  | 416171.84
2024-03-27 | HINDUSTAN ASSOCIATES |  | 4657.02
2024-03-30 | SIGNARCH |  | 251100.71
2024-03-30 | SIGNARCH |  | 11160.03
2024-03-30 | SIGNARCH |  | 251100.71
2024-03-30 | SIGNARCH |  | 251100.71
2024-03-30 | SIGNARCH |  | 55032.84
2024-03-30 | RISHABH ENTERPRISE |  | 308056.79
2024-03-30 | RISHABH ENTERPRISE |  | 104377.21
2024-03-30 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1734105.58
2024-03-30 | S.S.ENTERPRISES |  | 28320
2024-03-30 | RISHABH ENTERPRISE |  | 339171.89
2024-03-31 | BECS COATING |  | 8300.12
2024-03-31 | BECS COATING |  | 8300.12
2024-01-02 | KIRIT TRADING COMPANY |  | 103680
2024-01-07 | KIRIT TRADING COMPANY |  | 183680
2024-01-07 | KIRIT TRADING COMPANY |  | 183680
2024-01-11 | KIRIT TRADING COMPANY |  | 37120
2024-02-07 | JANATA SAND SUPPLYING CO. |  | 4000
2024-02-09 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 99840
2024-02-13 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 91200
2024-02-13 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 91200
2024-02-13 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 109440
2024-02-13 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 109440
2024-02-14 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 109440
2024-02-14 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 109440
2024-02-14 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 84800
2024-02-14 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 109440
2024-02-14 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 109440
2024-02-14 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 84800
2024-02-14 | JKLAKSHMI CEMENT LTD |  | 72960
2024-02-14 | JKLAKSHMI CEMENT LTD |  | 16960
2024-02-14 | JKLAKSHMI CEMENT LTD |  | 91200
2024-02-14 | JKLAKSHMI CEMENT LTD |  | 84800
2024-02-14 | JKLAKSHMI CEMENT LTD |  | 91200
2024-02-16 | KIRIT TRADING COMPANY |  | 72960
2024-02-16 | KIRIT TRADING COMPANY |  | 91200
2024-02-16 | KIRIT TRADING COMPANY |  | 91200
2024-02-16 | KIRIT TRADING COMPANY |  | 72960
2024-02-16 | KIRIT TRADING COMPANY |  | 72960
2024-02-19 | JKLAKSHMI CEMENT LTD |  | 91200
2024-02-19 | JKLAKSHMI CEMENT LTD |  | 91200
2024-02-19 | JKLAKSHMI CEMENT LTD |  | 72960
2024-02-19 | JKLAKSHMI CEMENT LTD |  | 16960
2024-02-19 | JKLAKSHMI CEMENT LTD |  | 84800
2024-03-06 | JANATA SAND SUPPLYING CO. |  | 3600
2024-03-06 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 90560
2024-03-06 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 47815.68
2024-03-06 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 83200
2024-03-11 | KARAN ENTERPRISES |  | 72448
2024-03-11 | KARAN ENTERPRISES |  | 90560
2024-03-11 | KARAN ENTERPRISES |  | 90560
2024-03-12 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 72960
2024-03-12 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 91200
2024-03-12 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 91200
2024-03-12 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 90560
2024-03-12 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 90560
2024-03-12 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 72448
2024-03-12 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 108672
2024-03-14 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 108672
2024-03-14 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 108672
2024-03-14 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 90560
2024-03-16 | KIRIT TRADING COMPANY |  | 101760
2024-03-30 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 90560
2024-03-30 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 90560
2024-03-30 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 90560
2024-03-30 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 72448
2024-03-31 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 99840
2024-01-04 | GLOBAL GYPSUM PVT LTD |  | 231000
2024-01-08 | M/S.SHRIYAA ENTERPRISES |  | 39984
2024-01-09 | M/S.SHRIYAA ENTERPRISES |  | 39984
2024-01-11 | S.S.ENTERPRISES |  | 33075
2024-01-12 | S.S.ENTERPRISES |  | 33075
2024-01-15 | S.S.ENTERPRISES |  | 33075
2024-01-15 | S.H.ENTERPRISES |  | 84157.5
2024-01-15 | S.H.ENTERPRISES |  | 90710.56
2024-01-15 | S.H.ENTERPRISES |  | 97141.8
2024-01-17 | M/S.SHRIYAA ENTERPRISES |  | 57660.76
2024-01-17 | M/S.SHRIYAA ENTERPRISES |  | 79968
2024-01-17 | S.S.ENTERPRISES |  | 33075
2024-01-17 | S.S.ENTERPRISES |  | 33075
2024-01-18 | M/S.SHRIYAA ENTERPRISES |  | 61120.5
2024-01-20 | S.S.ENTERPRISES |  | 33075
2024-01-24 | S.S.ENTERPRISES |  | 33075
2024-01-30 | M/S.SHRIYAA ENTERPRISES |  | 75465.6
2024-02-02 | S.S.ENTERPRISES |  | 33075
2024-02-03 | R.K.TRADING CO. |  | 27300
2024-02-05 | M/S.SHRIYAA ENTERPRISES |  | 60278.4
2024-02-08 | AL-BURHAN SAFETY PRODUCTS |  | 71177.4
2024-02-12 | GLOBAL GYPSUM PVT LTD |  | 249480
2024-02-12 | M/S.SHRIYAA ENTERPRISES |  | 154291.2
2024-02-12 | M/S.SHRIYAA ENTERPRISES |  | 60568.2
2024-02-14 | SHIV ENTERPRISES |  | 83643
2024-02-14 | SHIV ENTERPRISES |  | 56668.5
2024-02-14 | SHIV ENTERPRISES |  | 92977.5
2024-02-14 | S.H.ENTERPRISES |  | 84595.36
2024-02-14 | S.H.ENTERPRISES |  | 86116.8
2024-02-14 | S.H.ENTERPRISES |  | 53434.5
2024-02-14 | S.H.ENTERPRISES |  | 90751.5
2024-02-14 | S.S.ENTERPRISES |  | 33075
2024-02-14 | S.S.ENTERPRISES |  | 33075
2024-02-14 | GLOBAL GYPSUM PVT LTD |  | 249480
2024-02-14 | GLOBAL GYPSUM PVT LTD |  | 249480
2024-02-15 | S.H.ENTERPRISES |  | 88049.86
2024-02-15 | S.H.ENTERPRISES |  | 92489.26
2024-02-15 | S.H.ENTERPRISES |  | 88898.26
2024-02-15 | S.H.ENTERPRISES |  | 77175
2024-02-15 | S.H.ENTERPRISES |  | 90978.3
2024-02-15 | S.S.ENTERPRISES |  | 33075
2024-02-18 | JANATA SAND SUPPLYING CO. |  | 4725
2024-02-18 | M/S.SHRIYAA ENTERPRISES |  | 60954.6
2024-02-19 | GLOBAL GYPSUM PVT LTD |  | 231000
2024-02-22 | S.S.ENTERPRISES |  | 33075
2024-02-23 | M/S.SHRIYAA ENTERPRISES |  | 60278.4
2024-02-24 | M/S.SHRIYAA ENTERPRISES |  | 39916.8
2024-03-03 | AL-BURHAN SAFETY PRODUCTS |  | 71177.4
2024-03-04 | S.S.ENTERPRISES |  | 33075
2024-03-06 | JANATA SAND SUPPLYING CO. |  | 4725
2024-03-06 | GLOBAL GYPSUM PVT LTD |  | 231000
2024-03-06 | S.S.ENTERPRISES |  | 33075
2024-03-12 | S.S.ENTERPRISES |  | 33075
2024-03-12 | S.S.ENTERPRISES |  | 33075
2024-03-12 | SHIV ENTERPRISES |  | 83091.76
2024-03-12 | SHIV ENTERPRISES |  | 72859.5
2024-03-12 | SHIV ENTERPRISES |  | 83128.5
2024-03-12 | SHIV ENTERPRISES |  | 91591.5
2024-03-12 | M/S.SHRIYAA ENTERPRISES |  | 60471.6
2024-03-12 | S.H.ENTERPRISES |  | 84101.86
2024-03-12 | S.H.ENTERPRISES |  | 96636.76
2024-03-12 | S.H.ENTERPRISES |  | 87171
2024-03-12 | S.H.ENTERPRISES |  | 52405.5
2024-03-12 | S.H.ENTERPRISES |  | 76478.86
2024-03-12 | S.H.ENTERPRISES |  | 74345.26
2024-03-12 | GLOBAL GYPSUM PVT LTD |  | 249480
2024-03-13 | M/S.SHRIYAA ENTERPRISES |  | 52684.8
2024-03-14 | M/S.SHRIYAA ENTERPRISES |  | 121426.2
2024-03-14 | S.S.ENTERPRISES |  | 33075
2024-03-15 | S.H.ENTERPRISES |  | 94027.5
2024-03-15 | S.H.ENTERPRISES |  | 82687.5
2024-03-15 | S.H.ENTERPRISES |  | 83469.76
2024-03-15 | S.H.ENTERPRISES |  | 84924
2024-03-15 | S.H.ENTERPRISES |  | 64706.26
2024-03-15 | S.H.ENTERPRISES |  | 96644.1
2024-03-15 | S.H.ENTERPRISES |  | 23887.5
2024-03-16 | S.S.ENTERPRISES |  | 33075
2024-03-18 | M/S.SHRIYAA ENTERPRISES |  | 78624
2024-03-20 | S.S.ENTERPRISES |  | 33075
2024-03-20 | GLOBAL GYPSUM PVT LTD |  | 249480
2024-03-27 | M/S.SHRIYAA ENTERPRISES |  | 39177.6
2024-03-30 | M/S.SHRIYAA ENTERPRISES |  | 62113.8
2024-03-30 | M/S.SHRIYAA ENTERPRISES |  | 61244.4
2024-03-12 | S.H.ENTERPRISES |  | 28938
2024-03-30 | SHREEJI WOODCRAFT PVT LTD |  | 333362.02
2024-02-14 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 489241.6
2024-02-14 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 489241.6
2024-02-28 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 477432.32
2024-01-01 | MAHAVIR MINERALS |  | 120120
2024-01-11 | MAHAVIR MINERALS |  | 120083.04
2024-01-01 | SANTOSH NARAYANAN KAUNDER |  | 51600
2024-01-01 | CHANDRAKALA VERMA |  | 778000
2024-01-01 | TEJAL ENTERPRISE |  | 100000
2024-01-02 | SADHANA VIKRAM SINGH |  | 1066000
2024-01-02 | RAMASHREY PRAJAPATI |  | 10248
2024-01-02 | RAMASHREY PRAJAPATI |  | 11124
2024-01-03 | ADITYA ASHUTOSH SINGH |  | 464000
2024-01-03 | BHABESH HALDAR HUF |  | 712000
2024-01-03 | NEETA R VARA |  | 532000
2024-01-05 | SATENDER KUMAR B SINGH HUF |  | 641000
2024-01-05 | TULSSI & COMPANY |  | 100000
2024-01-10 | ALPAA ENTERPRISE |  | 200000
2024-01-18 | BHANU ENTERPRISE |  | 100000
2024-01-28 | HANSA R. CHAVDA |  | 50000
2024-01-28 | PUSHPA DEVI |  | 250000
2024-02-01 | RABITA SATENDER SINGH |  | 771000
2024-02-02 | RAJ DEV SINGH |  | 805000
2024-02-03 | NIRBHAY ENTERPRISES |  | 315000
2024-02-03 | NEETA R VARA |  | 251000
2024-02-04 | IMRAN AHMAD KHAN |  | 1002000
2024-02-04 | SHAMSHIR ALAM KHALIL SHAIKH |  | 250000
2024-02-05 | KHELCHAND HANSARAJ MESHRAM |  | 451000
2024-02-05 | TULSSI & COMPANY |  | 200000
2024-02-09 | TIRTH PRAVIN PATEL |  | 665000
2024-02-12 | RAMASHREY PRAJAPATI |  | 9408
2024-02-20 | KOMAL ENTERPRISES |  | 51600
2024-03-01 | PUSHPA DEVI |  | 100000
2024-03-01 | JAYESH MAHESH BHAI PARMAR |  | 200000
2024-03-01 | TEJAL ENTERPRISE |  | 100000
2024-03-04 | RAMASHREY PRAJAPATI |  | 16782
2024-03-07 | KOMAL ENTERPRISES |  | 38700
2024-03-15 | WELCOME ENTERPRISES |  | 300000
2024-01-05 | UNITEDONE CONSTRUCTION |  | 11039000
2024-01-08 | DINESH ENTERPRISES |  | 591593
2024-01-08 | AQUA ENVIRONMENTAL ENGINEERS |  | 212400
2024-02-04 | AQUA ENVIRONMENTAL ENGINEERS |  | 377600
2024-02-09 | R. R. ENTERPRISES |  | 46162
2024-02-13 | DINESH ENTERPRISES |  | 944000
2024-03-05 | DINESH ENTERPRISES |  | 581527
2024-03-12 | R. R. ENTERPRISES |  | 55012
2024-01-01 | SHRIKANT REDKAR |  | 28818
2024-01-01 | VELAVAN TRANSPORT |  | 86000
2024-01-01 | VELAVAN TRANSPORT |  | 30100
2024-01-02 | SHRIKANT REDKAR |  | 32272
2024-01-06 | SHRIKANT REDKAR |  | 35338
2024-01-08 | A1 STAR TRANSPORT |  | 32000
2024-01-08 | SHRIKANT REDKAR |  | 33551
2024-01-08 | BALAJI TRANSPORT |  | 31000
2024-01-12 | SHRIKANT REDKAR |  | 39979
2024-01-23 | SHRIKANT REDKAR |  | 19021
2024-02-01 | VELAVAN TRANSPORT |  | 86000
2024-02-06 | SHRIKANT REDKAR |  | 18530
2024-02-06 | SHRIKANT REDKAR |  | 19784
2024-02-10 | SHRIKANT REDKAR |  | 33152
2024-02-14 | A1 STAR TRANSPORT |  | 25000
2024-02-14 | SHRIKANT REDKAR |  | 29542
2024-02-14 | SHRIKANT REDKAR |  | 21609
2024-02-14 | BALAJI TRANSPORT |  | 35000
2024-02-24 | SHRIKANT REDKAR |  | 28318
2024-02-24 | SHRIKANT REDKAR |  | 42251
2024-03-01 | VELAVAN TRANSPORT |  | 21500
2024-03-02 | SHRIKANT REDKAR |  | 22565
2024-03-12 | BALAJI TRANSPORT |  | 52000
2024-03-12 | SHRIKANT REDKAR |  | 42562
2024-03-16 | SHRIKANT REDKAR |  | 30025
2024-03-27 | A1 STAR TRANSPORT |  | 4000
2024-03-30 | SHRIKANT REDKAR |  | 50338
2024-03-30 | SHRIKANT REDKAR |  | 43894
2024-03-31 | SHRIKANT REDKAR |  | 23775
2024-03-31 | A1 STAR TRANSPORT |  | 3000
2024-04-02 | UN CORPORATION |  | 74592
2024-04-02 | UN CORPORATION |  | 99431.14
2024-04-03 | UN CORPORATION |  | 74592
2024-04-03 | UN CORPORATION |  | 99431.14
2024-04-05 | UN CORPORATION |  | 74567.14
2024-04-15 | SHIV ENTERPRISES |  | 62720
2024-04-16 | UN CORPORATION |  | 74592
2024-04-16 | SHIV ENTERPRISES |  | 62720
2024-04-19 | SHIV ENTERPRISES |  | 62720
2024-04-21 | SHIV ENTERPRISES |  | 62720
2024-04-24 | UN CORPORATION |  | 75096
2024-04-25 | SHIV ENTERPRISES |  | 31360
2024-04-26 | UN CORPORATION |  | 74592
2024-04-30 | SHIV ENTERPRISES |  | 62720
2024-05-06 | UN CORPORATION |  | 74592
2024-05-06 | RECONS BUILDING PRODUCTS PVT.LTD |  | 69198.01
2024-05-08 | UN CORPORATION |  | 99431.14
2024-05-09 | UN CORPORATION |  | 74592
2024-05-09 | RECONS BUILDING PRODUCTS PVT.LTD |  | 64232.99
2024-05-10 | RECONS BUILDING PRODUCTS PVT.LTD |  | 64232.99
2024-05-13 | UN CORPORATION |  | 99431.14
2024-05-14 | UN CORPORATION |  | 99431.14
2024-05-15 | RECONS BUILDING PRODUCTS PVT.LTD |  | 55883.52
2024-05-22 | RECONS BUILDING PRODUCTS PVT.LTD |  | 59638
2024-05-23 | UN CORPORATION |  | 99431.14
2024-05-24 | RECONS BUILDING PRODUCTS PVT.LTD |  | 56612
2024-05-28 | RECONS BUILDING PRODUCTS PVT.LTD |  | 61746
2024-06-10 | RECONS BUILDING PRODUCTS PVT.LTD |  | 49717
2024-06-12 | RECONS BUILDING PRODUCTS PVT.LTD |  | 53854
2024-06-14 | RECONS BUILDING PRODUCTS PVT.LTD |  | 54434.99
2024-06-17 | RECONS BUILDING PRODUCTS PVT.LTD |  | 51169.01
2024-06-17 | RECONS BUILDING PRODUCTS PVT.LTD |  | 59878.99
2024-06-18 | RECONS BUILDING PRODUCTS PVT.LTD |  | 60680.99
2024-04-01 | SIGNARCH |  | -4428.01
2024-04-02 | UN CORPORATION |  | 7800.01
2024-04-02 | UN CORPORATION |  | 7800.01
2024-04-02 | DILIP PAINT& HARDWARE STORES |  | 39330
2024-04-03 | UN CORPORATION |  | 7800.01
2024-04-03 | UN CORPORATION |  | 7800.01
2024-04-03 | R.K.TRADING CO. |  | 14160
2024-04-05 | ICARE LIFT SYSTEM |  | 130154
2024-04-08 | HEM ENTERPRISE |  | 1506506
2024-04-14 | KRISHNA CERAMICS |  | 58410
2024-04-15 | BECS COATING |  | 4236.2
2024-04-15 | KARRMANYA ENTERPRISE |  | 650000.64
2024-04-15 | VEDANT MARKETING |  | 8342.6
2024-04-15 | HITECH CONSTRUCTION AND REPAIRS |  | 64310
2024-04-15 | S.S.ENTERPRISES |  | 28320
2024-04-18 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1829228.92
2024-04-18 | NAVBHARAT HARDWARE STORES |  | 19930.2
2024-04-22 | ICARE LIFT SYSTEM |  | -59000
2024-04-22 | KARRMANYA ENTERPRISE |  | 4294.02
2024-04-23 | RISHABH ENTERPRISE |  | 185970.54
2024-04-24 | KRISHNA CERAMICS |  | 19470
2024-04-26 | UN CORPORATION |  | 7800.01
2024-04-27 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1821430.3
2024-05-01 | DESIGNER HARDWARE |  | 6769.66
2024-05-02 | DESIGNER HARDWARE |  | 33670.12
2024-05-03 | AL-BURHAN SAFETY PRODUCTS |  | 130621.57
2024-05-03 | VEDANT MARKETING |  | 13971.2
2024-05-03 | DESIGNER HARDWARE |  | 70835.4
2024-05-04 | DESIGNER HARDWARE |  | 93352.16
2024-05-06 | DILIP PAINT& HARDWARE STORES |  | 519.2
2024-05-07 | DESIGNER HARDWARE |  | 90883.6
2024-05-08 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1972165.86
2024-05-08 | UN CORPORATION |  | 7800.01
2024-05-08 | DESIGNER HARDWARE |  | 97414.9
2024-05-09 | UN CORPORATION |  | 7800.01
2024-05-09 | VEDANT MARKETING |  | 13947.6
2024-05-09 | DESIGNER HARDWARE |  | 91400.44
2024-05-10 | AXLER WOODWORKS LLP |  | 35282
2024-05-10 | DESIGNER HARDWARE |  | 90088.28
2024-05-10 | DESIGNER HARDWARE |  | 80995.2
2024-05-11 | R.K.TRADING CO. |  | 14160
2024-05-14 | UN CORPORATION |  | 39000.01
2024-05-15 | SHREE KRISHNA IMPEX |  | 35237.99
2024-05-21 | DESIGNER HARDWARE |  | 43612.8
2024-05-22 | SHREE KRISHNA IMPEX |  | 127893.12
2024-05-23 | TEJAS CERAMICS |  | 47999.56
2024-05-23 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1957030
2024-05-23 | UN CORPORATION |  | 15600
2024-05-24 | KRISHNA CERAMICS |  | 15723.5
2024-05-24 | RECONS BUILDING PRODUCTS PVT.LTD |  | 8400
2024-05-25 | SKY TELECOM |  | 2950
2024-05-25 | PAG INTERNATIONAL PVT LTD |  | 3574.22
2024-05-25 | PAG INTERNATIONAL PVT LTD |  | 553.42
2024-05-25 | VEDANT MARKETING |  | 18408
2024-05-28 | NAVBHARAT HARDWARE STORES |  | 53277
2024-05-29 | SHREE KRISHNA IMPEX |  | 127893.12
2024-06-01 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 2079228.44
2024-06-02 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1925190.06
2024-06-03 | S.S.ENTERPRISES |  | 26550
2024-06-04 | KONE ELEVATOR INDIA PVT LTD |  | 1481480.99
2024-06-04 | VEDANT MARKETING |  | 13522.8
2024-06-04 | AL-BURHAN SAFETY PRODUCTS |  | 75704.68
2024-06-05 | HINDUSTAN ASSOCIATES |  | 385803.36
2024-06-06 | P.R.CRAFT AND DESIGN |  | 50977.5
2024-06-06 | P.R.CRAFT AND DESIGN |  | 48195
2024-06-06 | P.R.CRAFT AND DESIGN |  | 258271.6
2024-06-06 | SHREE KRISHNA IMPEX |  | 106813.6
2024-06-07 | P.R.CRAFT AND DESIGN |  | 134121.45
2024-06-07 | P.R.CRAFT AND DESIGN |  | 226860.2
2024-06-07 | P.R.CRAFT AND DESIGN |  | 253036.36
2024-06-10 | P.R.CRAFT AND DESIGN |  | 225115.12
2024-06-10 | RECONS BUILDING PRODUCTS PVT.LTD |  | 16800
2024-06-11 | P.R.CRAFT AND DESIGN |  | 81410.72
2024-06-11 | SHREE KRISHNA IMPEX |  | 101543.72
2024-06-11 | R.K.TRADING CO. |  | 14160
2024-06-12 | S.S.ENTERPRISES |  | 28320
2024-06-12 | RECONS BUILDING PRODUCTS PVT.LTD |  | 10500
2024-06-13 | ARIHANT ELECTRICALS |  | 94377.1
2024-06-13 | SUSHMA CONSTRUCTION STEEL SALES LLP |  | 1832177.74
2024-06-14 | ARIHANT ELECTRICALS |  | 99194.13
2024-06-14 | RECONS BUILDING PRODUCTS PVT.LTD |  | 10500.01
2024-06-15 | ARIHANT ELECTRICALS |  | 95046.64
2024-06-17 | ARIHANT ELECTRICALS |  | 314538.44
2024-06-18 | RECONS BUILDING PRODUCTS PVT.LTD |  | 12600.01
2024-06-22 | AXLER WOODWORKS LLP |  | 1777080
2024-06-26 | NAVBHARAT HARDWARE STORES |  | 312983.2
2024-06-28 | GLOBAL GYPSUM PVT LTD |  | 70800
2024-04-01 | SUNTREK CORPORATION |  | 66560
2024-04-01 | SUNTREK CORPORATION |  | 16640
2024-04-02 | JKLAKSHMI CEMENT LTD |  | 89600
2024-04-02 | JKLAKSHMI CEMENT LTD |  | 89600
2024-04-02 | JKLAKSHMI CEMENT LTD |  | 71680
2024-04-02 | JKLAKSHMI CEMENT LTD |  | 71680
2024-04-02 | JKLAKSHMI CEMENT LTD |  | 71680
2024-04-06 | JKLAKSHMI CEMENT LTD |  | 107520
2024-04-06 | JKLAKSHMI CEMENT LTD |  | 107520
2024-04-06 | JKLAKSHMI CEMENT LTD |  | 107520
2024-04-07 | JKLAKSHMI CEMENT LTD |  | 71680
2024-04-12 | SAKSHI CORPORATION |  | 83200
2024-04-14 | JANATA SAND SUPPLYING CO. |  | 2000
2024-04-15 | JKLAKSHMI CEMENT LTD |  | 16832
2024-04-15 | JKLAKSHMI CEMENT LTD |  | 84160
2024-04-15 | JKLAKSHMI CEMENT LTD |  | 90560
2024-04-21 | KIRIT TRADING COMPANY |  | 100992
2024-04-27 | SAKSHI CORPORATION |  | 84160
2024-04-28 | JKLAKSHMI CEMENT LTD |  | 93184
2024-04-28 | JKLAKSHMI CEMENT LTD |  | 86016
2024-04-28 | JKLAKSHMI CEMENT LTD |  | 89600
2024-04-28 | JKLAKSHMI CEMENT LTD |  | 89600
2024-04-28 | JKLAKSHMI CEMENT LTD |  | 90560
2024-04-30 | JKLAKSHMI CEMENT LTD |  | 35840
2024-05-04 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 71680
2024-05-04 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 71680
2024-05-05 | SAKSHI CORPORATION |  | 83200
2024-05-08 | SAKSHI CORPORATION |  | 82560
2024-05-08 | THE INDIA CEMENTS LIMITED ( KETAN BHAI) |  | 107520
2024-05-12 | SAKSHI CORPORATION |  | 99072
2024-05-12 | SUNTREK CORPORATION |  | 17920
2024-05-12 | SUNTREK CORPORATION |  | 71680
2024-05-12 | SUNTREK CORPORATION |  | 71680
2024-05-12 | SUNTREK CORPORATION |  | 35840
2024-05-12 | SUNTREK CORPORATION |  | 71680
2024-05-12 | SUNTREK CORPORATION |  | 89600
2024-05-12 | SUNTREK CORPORATION |  | 35840
2024-05-18 | JKLAKSHMI CEMENT LTD |  | 88000
2024-05-18 | JKLAKSHMI CEMENT LTD |  | 88000
2024-05-21 | JKLAKSHMI CEMENT LTD |  | 81600
2024-05-21 | JKLAKSHMI CEMENT LTD |  | 16320
2024-05-23 | JKLAKSHMI CEMENT LTD |  | 88000
2024-05-23 | JKLAKSHMI CEMENT LTD |  | 88000
2024-05-23 | JKLAKSHMI CEMENT LTD |  | 97920
2024-05-24 | JKLAKSHMI CEMENT LTD |  | 88000
2024-05-24 | JKLAKSHMI CEMENT LTD |  | 88000
2024-05-25 | JKLAKSHMI CEMENT LTD |  | 70400
2024-05-30 | SUNTREK CORPORATION |  | 70400
2024-05-31 | JKLAKSHMI CEMENT LTD |  | 87040
2024-05-31 | JKLAKSHMI CEMENT LTD |  | 87040
2024-05-31 | JKLAKSHMI CEMENT LTD |  | 87040
2024-05-31 | JKLAKSHMI CEMENT LTD |  | 17408
2024-05-31 | JKLAKSHMI CEMENT LTD |  | 87040
2024-05-31 | JKLAKSHMI CEMENT LTD |  | 17408
2024-06-01 | SUNTREK CORPORATION |  | 35200
2024-06-01 | SUNTREK CORPORATION |  | 70400
2024-06-03 | KARAN ENTERPRISES |  | 97920
2024-06-11 | JKLAKSHMI CEMENT LTD |  | 86400
2024-06-11 | JKLAKSHMI CEMENT LTD |  | 86400
2024-06-12 | SAKSHI CORPORATION |  | 80640
2024-06-19 | SAKSHI CORPORATION |  | 64512
2024-06-20 | JKLAKSHMI CEMENT LTD |  | 86400
2024-06-20 | JKLAKSHMI CEMENT LTD |  | 86400
2024-06-20 | JKLAKSHMI CEMENT LTD |  | 86400
2024-06-20 | JKLAKSHMI CEMENT LTD |  | 86400
2024-06-22 | JKLAKSHMI CEMENT LTD |  | 16128
2024-06-22 | JKLAKSHMI CEMENT LTD |  | 80640
2024-04-01 | S.H.ENTERPRISES |  | 36960
2024-04-08 | S.S.ENTERPRISES |  | 33075
2024-04-11 | M/S.SHRIYAA ENTERPRISES |  | 61630.8
2024-04-14 | JANATA SAND SUPPLYING CO. |  | 4725
2024-04-15 | SHARADA ENTERPRISES |  | 90325.2
2024-04-15 | SHARADA ENTERPRISES |  | 90199.72
2024-04-15 | SHARADA ENTERPRISES |  | 99500.62
2024-04-15 | SHARADA ENTERPRISES |  | 99052.8
2024-04-15 | SHARADA ENTERPRISES |  | 84067.2
2024-04-15 | SHARADA ENTERPRISES |  | 83529.6
2024-04-17 | M/S.SHRIYAA ENTERPRISES |  | 61630.8
2024-04-18 | M/S.SHRIYAA ENTERPRISES |  | 61341
2024-04-19 | S.S.ENTERPRISES |  | 33075
2024-04-22 | GLOBAL GYPSUM PVT LTD |  | 249480
2024-04-23 | M/S.SHRIYAA ENTERPRISES |  | 61147.8
2024-04-25 | S.S.ENTERPRISES |  | 33075
2024-04-26 | M/S.SHRIYAA ENTERPRISES |  | 60471.6
2024-04-27 | SHIV ENTERPRISES |  | 74502.22
2024-04-27 | SHIV ENTERPRISES |  | 77054.26
2024-04-28 | SHIV ENTERPRISES |  | 99805.12
2024-04-28 | SHIV ENTERPRISES |  | 94914.76
2024-04-29 | SHIV ENTERPRISES |  | 71259.3
2024-04-29 | SHIV ENTERPRISES |  | 39312
2024-04-30 | SHARADA ENTERPRISES |  | 48659.1
2024-04-30 | M/S.SHRIYAA ENTERPRISES |  | 60664.8
2024-05-04 | M/S.SHRIYAA ENTERPRISES |  | 60858
2024-05-04 | M/S.SHRIYAA ENTERPRISES |  | 28795.2
2024-05-06 | M/S.SHRIYAA ENTERPRISES |  | 103891.2
2024-05-06 | M/S.SHRIYAA ENTERPRISES |  | 23016
2024-05-07 | S.S.ENTERPRISES |  | 33075
2024-05-07 | S.S.ENTERPRISES |  | 33075
2024-05-09 | S.S.ENTERPRISES |  | 33075
2024-05-11 | M/S.SHRIYAA ENTERPRISES |  | 60858
2024-05-11 | M/S.SHRIYAA ENTERPRISES |  | 39984
2024-05-11 | M/S.SHRIYAA ENTERPRISES |  | 165429.6
2024-05-13 | S.S.ENTERPRISES |  | 33075
2024-05-13 | S.S.ENTERPRISES |  | 60669
2024-05-15 | S.H.ENTERPRISES |  | 59740.8
2024-05-15 | S.H.ENTERPRISES |  | 70425.6
2024-05-15 | S.S.ENTERPRISES |  | 33075
2024-05-16 | M/S.SHRIYAA ENTERPRISES |  | 55003.2
2024-05-16 | M/S.SHRIYAA ENTERPRISES |  | 39984
2024-05-20 | S.S.ENTERPRISES |  | 59157
2024-05-20 | S.S.ENTERPRISES |  | 33075
2024-05-21 | M/S.SHRIYAA ENTERPRISES |  | 158054.4
2024-05-23 | SHIV ENTERPRISES |  | 79443
2024-05-26 | SHIV ENTERPRISES |  | 81900
2024-05-27 | S.S.ENTERPRISES |  | 33075
2024-05-27 | S.S.ENTERPRISES |  | 33075
2024-05-29 | S.S.ENTERPRISES |  | 33075
2024-05-29 | S.S.ENTERPRISES |  | 33075
2024-05-29 | SHIV ENTERPRISES |  | 84015.76
2024-05-31 | M/S.SHRIYAA ENTERPRISES |  | 32457.6
2024-05-31 | M/S.SHRIYAA ENTERPRISES |  | 52684.8
2024-05-31 | M/S.SHRIYAA ENTERPRISES |  | 22444.8
2024-05-31 | S.S.ENTERPRISES |  | 33075
2024-05-31 | SHARADA ENTERPRISES |  | 82891.2
2024-05-31 | SHARADA ENTERPRISES |  | 85612.8
2024-05-31 | SHARADA ENTERPRISES |  | 86822.4
2024-05-31 | SHARADA ENTERPRISES |  | 80102.4
2024-05-31 | SHARADA ENTERPRISES |  | 80482.5
2024-05-31 | SHARADA ENTERPRISES |  | 79340.1
2024-05-31 | SHARADA ENTERPRISES |  | 77112
2024-05-31 | SHIV ENTERPRISES |  | 77122.5
2024-06-03 | M/S.SHRIYAA ENTERPRISES |  | 61341
2024-06-03 | S.S.ENTERPRISES |  | 59535
2024-06-03 | S.S.ENTERPRISES |  | 33075
2024-06-08 | GLOBAL GYPSUM PVT LTD |  | 110880
2024-06-12 | M/S.SHRIYAA ENTERPRISES |  | 61534.2
2024-06-12 | S.S.ENTERPRISES |  | 33075
2024-06-14 | M/S.SHRIYAA ENTERPRISES |  | 130705.06
2024-06-14 | M/S.SHRIYAA ENTERPRISES |  | 25065.6
2024-06-15 | SHARADA ENTERPRISES |  | 95961.6
2024-06-15 | SHARADA ENTERPRISES |  | 75942.3
2024-06-18 | M/S.SHRIYAA ENTERPRISES |  | 60954.6
2024-06-19 | GLOBAL GYPSUM PVT LTD |  | 110880
2024-06-22 | M/S.SHRIYAA ENTERPRISES |  | 61437.6
2024-06-24 | GLOBAL GYPSUM PVT LTD |  | 110880
2024-06-24 | M/S.SHRIYAA ENTERPRISES |  | 61824
2024-06-28 | M/S.SHRIYAA ENTERPRISES |  | 59409
2024-06-28 | M/S.SHRIYAA ENTERPRISES |  | 79296
2024-04-17 | SHREEJI WOODCRAFT PVT LTD |  | 1096103.99
2024-05-31 | SHREEJI WOODCRAFT PVT LTD |  | 753254.01
2024-05-31 | SHREEJI WOODCRAFT PVT LTD |  | 391176.13
2024-06-17 | SHREEJI WOODCRAFT PVT LTD |  | 360541.92
2024-04-01 | R P YADAV TRANSPORT |  | 38000
2024-04-04 | SHRIKANT REDKAR |  | 40929
2024-04-05 | R K ENTERPRISES |  | 68800
2024-05-01 | R P YADAV TRANSPORT |  | 28000
2024-05-02 | SHRIKANT REDKAR |  | 23352
2024-05-02 | SHRIKANT REDKAR |  | 65897
2024-05-03 | SHRIKANT REDKAR |  | 34363
2024-05-09 | SHRIKANT REDKAR |  | 34201
2024-05-15 | A1 STAR TRANSPORT |  | 2200
2024-05-15 | BALAJI TRANSPORT |  | 106000
2024-05-16 | SHRIKANT REDKAR |  | 54843
2024-06-03 | R P YADAV TRANSPORT |  | 56000
2024-06-03 | SHRIKANT REDKAR |  | 38106
2024-06-13 | SHRIKANT REDKAR |  | 26325
2024-06-15 | SHRIKANT REDKAR |  | 22367
2024-06-20 | A1 STAR TRANSPORT |  | 16800
2024-06-20 | SHRIKANT REDKAR |  | 34656
2024-06-20 | BALAJI TRANSPORT |  | 79000
2024-04-01 | HANSA R. CHAVDA |  | 500000
2024-04-01 | SAVITABEN K.CHAVDA |  | 200000
2024-04-01 | PUSHPA DEVI |  | 300000
2024-04-05 | TULSSI & COMPANY |  | 200000
2024-04-05 | BHANU ENTERPRISE |  | 200000
2024-04-10 | ALPAA ENTERPRISE |  | 200000
2024-04-22 | HANSA R. CHAVDA |  | 200000
2024-04-22 | JAYESH MAHESH BHAI PARMAR |  | 200000
2024-05-03 | AL-BURHAN SAFETY PRODUCTS |  | 142785
2024-05-03 | RAMASHREY PRAJAPATI |  | 10752
2024-05-05 | TEJAL ENTERPRISE |  | 100000
2024-05-05 | TULSSI & COMPANY |  | 100000
2024-05-05 | BHANU ENTERPRISE |  | 100000
2024-05-08 | SHUBH FABRICATORS |  | 264895
2024-05-08 | SHUBH FABRICATORS |  | 48642
2024-05-08 | SHUBH FABRICATORS |  | 164000
2024-05-09 | KOMAL ENTERPRISES |  | 137600
2024-05-10 | ALPAA ENTERPRISE |  | 200000
2024-05-12 | PRIYA VISHWAKARMA |  | 501000
2024-05-17 | FATIMA AHSAN KHAN |  | 300000
2024-05-17 | MAJHAR |  | 300000
2024-05-27 | RAJENDRA JAYANTILAL GOHIL |  | 100000
2024-06-04 | AL-BURHAN SAFETY PRODUCTS |  | 84116
2024-06-05 | JAYESH MAHESH BHAI PARMAR |  | 300000
2024-06-08 | WELCOME ENTERPRISES |  | 197000
2024-06-08 | WELCOME ENTERPRISES |  | 186000
2024-06-17 | RAJU NISHAD |  | 232541
2024-03-01 | TEJAL ENTERPRISE |  | 100000
2024-03-04 | RAMASHREY PRAJAPATI |  | 16782
2024-03-07 | KOMAL ENTERPRISES |  | 38700
2024-03-15 | WELCOME ENTERPRISES |  | 300000
2024-04-19 | MUMTAZ ENGINEERING WORKS |  | 231757
2024-05-03 | AL-BURHAN SAFETY PRODUCTS |  | 142785
2024-05-03 | R. R. ENTERPRISES |  | 42338
2024-05-14 | DINESH ENTERPRISES |  | 678500
2024-06-04 | R. R. ENTERPRISES |  | 30704
2024-06-04 | AL-BURHAN SAFETY PRODUCTS |  | 84116
2024-06-07 | SHREEJI WATER PUMPS & BOREWELL |  | 14691
576196381.87

## Professional
SR.NO | PARTICULARS | NATURE |  | DATE | TOTAL AMOUNT
| ACE CONSULTANTS | ARCHITECTURE FEES |  |  | 847456
| KARCH PLANNERS | ARCHITECTURE FEES |  |  | 450000
| KARCH PLANNERS | ARCHITECTURE FEES |  |  | 150000
| KARCH PLANNERS | ARCHITECTURE FEES |  |  | 150000
| KARCH PLANNERS | ARCHITECTURE FEES |  |  | 150000
| KARCH PLANNERS | ARCHITECTURE FEES |  |  | 150000
| KARCH PLANNERS | ARCHITECTURE FEES |  |  | 150000
| KARCH PLANNERS | ARCHITECTURE FEES |  |  | 150000
| KARCH PLANNERS | ARCHITECTURE FEES |  |  | 150000
| KARCH PLANNERS | ARCHITECTURE FEES |  |  | 150000
| DARSHANA INDULKAR | LEGAL AND PROFESSIONAL CHARGES |  | 2021-11-24 | 36000
| PRAMOD KUMAR |  |  | 2022-02-18 | 50000
| KAHAAN PROJECT CONSULTANT |  |  | 2022-02-24 | 236000
| ROHAN ENVIRO ASSOCIATES |  |  | 2022-03-19 | 796500
| Vrinda Nidhin Pillai |  |  | 2022-03-30 | 1000000
| Shalaka D.Sathe |  |  | 2022-03-30 | 900000
| Truptiben M.Bagsariya |  |  | 2022-03-30 | 100000
| Nilofer Abdulla Baig |  |  | 2022-03-30 | 1000000
| CGST ON REVERSE CHARGES |  |  | 2022-03-31 | 6480
| DEEPIKA KAUR CHILOTRA |  | C1/22-23/N1 | 2022-04-01 | 1250000
| ROHAN ENVIRO ASSOCIATES |  | REA/001/2022/23 | 2022-06-10 | 177000
| NM JALMAITRYA LLP |  | NM/PI.22-23/05 | 2022-06-10 | 53100
| KAHAAN PROJECT CONSULTANT |  |  | 2022-08-10 | 472000
| S.J.ASSOCIATES |  |  | 2022-08-31 | 41300
| ROHAN ENVIRO ASSOCIATES |  |  | 2022-10-12 | 708000
| S.J.ASSOCIATES |  |  | 2023-02-03 | 17700
| SHIVMOHAN B.JHA |  |  | 2023-02-06 | 59000
| SHIVMOHAN B.JHA |  |  | 2023-02-18 | 118000
| ROHAN ENVIRO ASSOCIATES |  |  | 2023-03-28 | 177000
| MIHIR NANIWADEKAR |  | 11/2023-24 | 2023-05-05 | 20000
| VASTUKALA CONSLTANTS (I) PVT LTD |  | MUM/2324/MAY/148 | 2023-05-18 | 106200
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2019-08-01 | 2700
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2019-10-09 | 12960
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2019-10-09 | 3240
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2019-11-05 | 48600
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2019-11-08 | 5400
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2019-11-08 | 10800
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2020-02-01 | 3540
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2020-07-01 | 1770
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2020-07-07 | 5900
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2020-11-01 | 5900
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2021-02-01 | 2950
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2021-03-02 | 17700
| DARSHANA INDULKAR | PROFESSIONAL FEES |  | 2021-03-31 | 100000
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2021-05-05 | 2360
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2022-01-03 | 20650
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2022-03-01 | 23600
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2022-03-16 | 7965
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2022-03-21 | 100
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2022-09-01 | 5310
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2023-02-01 | 23600
| YOGESH R.GOSWAMI | PROFESSIONAL FEES |  | 2023-02-01 | 4000
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2023-03-01 | 25960
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2023-03-01 | 36580
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2023-03-01 | 7080
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2023-03-01 | 5310
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2023-03-01 | 35400
| J.J.SANGANEE & CO. | PROFESSIONAL FEES |  | 2023-03-01 | 23600
| YOGESH R.GOSWAMI | PROFESSIONAL FEES | 02/RERA | 2023-08-02 | 3000
| J.J.SANGANEE & CO. | PROFESSIONAL FEES | CO/08-23/03 | 2023-08-02 | 9440
| GLOBAL LAB MATERIAL TESTING PVT LTD | TESTING CHARGES |  | 2022-05-18 | 450
| GLOBAL LAB MATERIAL TESTING PVT LTD | TESTING CHARGES | KRL-44761-189825 | 2022-06-08 | 2700
| GLOBAL LAB MATERIAL TESTING PVT LTD | TESTING CHARGES | KRL-44998-191217 | 2022-06-08 | 1350
| GLOBAL LAB MATERIAL TESTING PVT LTD | TESTING CHARGES | KRL-45286-192241 | 2022-06-16 | 900
| GLOBAL LAB MATERIAL TESTING PVT LTD | TESTING CHARGES |  | 2022-07-01 | 9450
| GLOBAL LAB MATERIAL TESTING PVT LTD | TESTING CHARGES |  | 2022-07-26 | 1800
| GLOBAL LAB MATERIAL TESTING PVT LTD | TESTING CHARGES |  | 2022-07-26 | 450
| GLOBAL LAB MATERIAL TESTING PVT LTD | TESTING CHARGES |  | 2022-07-28 | 450
| GLOBAL LAB MATERIAL TESTING PVT LTD | TESTING CHARGES |  | 2022-07-28 | 450
| GLOBAL LAB MATERIAL TESTING PVT LTD | TESTING CHARGES |  | 2022-07-31 | 1350
| GLOBAL LAB MATERIAL TESTING PVT LTD | TESTING CHARGES |  | 2022-07-31 | 450
| GLOBAL LAB MATERIAL TESTING PVT LTD | TESTING CHARGES |  | 2022-09-17 | 9450
| GLOBAL LAB MATERIAL TESTING PVT LTD | TESTING CHARGES |  | 2022-10-04 | 13950
| GLOBAL LAB MATERIAL TESTING PVT LTD | TESTING CHARGES |  | 2022-11-16 | 15750
| GLOBAL LAB MATERIAL TESTING PVT LTD | TESTING CHARGES |  | 2023-01-21 | 5400
| GLOBAL LAB MATERIAL TESTING PVT LTD | TESTING CHARGES |  | 2023-01-21 | 6750
| LANDMARK CONSULTANTS & ENGG.TECHNOLOGY | TESTING CHARGES |  | 2023-02-13 | 1200
| LANDMARK CONSULTANTS & ENGG.TECHNOLOGY | TESTING CHARGES |  | 2023-02-13 | 1800
| LANDMARK CONSULTANTS & ENGG.TECHNOLOGY | TESTING CHARGES |  | 2023-02-13 | 1800
| LANDMARK CONSULTANTS & ENGG.TECHNOLOGY | TESTING CHARGES |  | 2023-02-13 | 2400
| LANDMARK CONSULTANTS & ENGG.TECHNOLOGY | TESTING CHARGES |  | 2023-02-13 | 4200
| LANDMARK CONSULTANTS & ENGG.TECHNOLOGY | TESTING CHARGES |  | 2023-03-20 | 16200
| GLOBAL LAB MATERIAL TESTING PVT LTD | TESTING CHARGES |  | 2023-03-21 | 1350
| LANDMARK CONSULTANTS & ENGG.TECHNOLOGY | TESTING CHARGES | L-10070 | 2023-05-12 | 2400
| LANDMARK CONSULTANTS & ENGG.TECHNOLOGY | TESTING CHARGES | L-10254 | 2023-05-12 | 3600
| LANDMARK CONSULTANTS & ENGG.TECHNOLOGY | TESTING CHARGES | L-10255 | 2023-05-12 | 1200
| LANDMARK CONSULTANTS & ENGG.TECHNOLOGY | TESTING CHARGES | L-10361 | 2023-05-12 | 3600
| LANDMARK CONSULTANTS & ENGG.TECHNOLOGY | TESTING CHARGES | L-010362 | 2023-05-12 | 2400
| LANDMARK CONSULTANTS & ENGG.TECHNOLOGY | TESTING CHARGES | L-0511 | 2023-08-24 | 21600
| LANDMARK CONSULTANTS & ENGG.TECHNOLOGY | TESTING CHARGES | L-0512 | 2023-08-24 | 10800
| LANDMARK CONSULTANTS & ENGG.TECHNOLOGY | TESTING CHARGES | L-0513 | 2023-08-24 | 15600
| VASTUKALA CONSLTANTS (I) PVT LTD | LEGAL AND PROFESSIONAL CHARGES |  | 2023-09-05 | 236000
| SHIVMOHAN B.JHA | LEGAL AND PROFESSIONAL CHARGES | GST/18/2023-24 | 2023-10-20 | 118000
| VASTUKALA CONSLTANTS (I) PVT LTD | LEGAL AND PROFESSIONAL CHARGES | PG-3227/23-24 | 2023-12-02 | 88500
| LANDMARK CONSULTANTS & ENGG.TECHNOLOGY | TESTING CHARGES | L-0812 | 2023-12-07 | 22200
| LEGAL & PROFESSIONAL CHARGES-KONSHILA |  |  | 2024-03-06 | 35000
| TESTING CHARGES |  |  | 2024-01-03 | 3000
| TESTING CHARGES |  |  | 2024-03-04 | 13800
| PROFESSIONAL FEES - OTHERS (S & A) | SALES & ADMINISTRATIVE EXPENSE |  |  | 58000
| PROFESSIONAL FEES - OTHERS (S & A) | SALES & ADMINISTRATIVE EXPENSE |  |  | 213000
| TESTING CHARGES | CHQ NO-890685 BILL NO:L-0187 |  | 2024-05-10 | 6600
| LEGAL & PROFESSIONAL CHARGES-KONSHILA | CH NO-890671 BILL NO-REF.1633 ADVOCATE |  | 2024-05-03 | 200000
| Vastukala Consultants (I) Pvt. Ltd. | CH NO-890691 BILL NO-MUM/2425/MAY/161 |  | 2024-06-06 | 41300
TOTAL |  |  |  |  | 11473801

## MArketing
SR.NO | PARTICULARS | NATURE |  | DATE | TOTAL AMOUNT
| VIJAY B.VANJARE | BROKAGE & COMMISSION | 001 | 2023-05-10 | 122678
| VIJAY B.VANJARE | BROKAGE & COMMISSION | 002 | 2023-05-20 | 181319
| VIJAY B.VANJARE | BROKAGE & COMMISSION | 003 | 2023-06-22 | 177399
| MR.ANKUR OMPRAKASH SHARMA | BROKAGE & COMMISSION |  | 2023-06-23 | 175299
| VIJAY B.VANJARE | BROKAGE & COMMISSION | 004 | 2023-07-04 | 181345
| VIJAY B.VANJARE | BROKAGE & COMMISSION | 005 | 2023-07-04 | 129093
| RAVINDRA CHAVAN | BROKAGE & COMMISSION | 006 | 2023-07-05 | 129093
| VIJAY B.VANJARE | BROKAGE & COMMISSION | 009 | 2023-07-17 | 184151
| RAVINDRA CHAVAN | BROKAGE & COMMISSION | 010 | 2023-07-18 | 125489
| SWARUP DILIP BURUNKAR | BROKAGE & COMMISSION |  | 2023-07-19 | 105941
| RAVINDRA CHAVAN | BROKAGE & COMMISSION | 011 | 2023-07-19 | 100031
| ABHISHEK S YADAV | BROKAGE & COMMISSION |  | 2023-07-20 | 154236
| PRAKASH DHONDU BHOSLE | BROKAGE & COMMISSION |  | 2023-07-25 | 125489
| VIJAY B.VANJARE | BROKAGE & COMMISSION | 012 | 2023-08-14 | 115489
| VIJAY B.VANJARE | BROKAGE & COMMISSION | 013 | 2023-08-14 | 129093
| SURAJ KUMAR GUPTA | BROKAGE & COMMISSION |  |  | 102336
| BROKAGE & COMMISSION | SALES & ADMINISTRATIVE EXPENSE |  |  | 1698953
TOTAL |  |  |  |  | 3937434

## Admin
SR.NO | PARTICULARS | NATURE | INVOICE NO | DATE | TOTAL AMOUNT
1 | ADANI ELECTRICITY | ELECTRICITY EXPENSES |  | 2022-01-25 | 4070
2 | ADANI ELECTRICITY | ELECTRICITY EXPENSES |  | 2022-03-07 | 1230
3 | ADANI ELECTRICITY | ELECTRICITY EXPENSES |  | 2022-03-21 | 11190
4 | ADANI ELECTRICITY | ELECTRICITY EXPENSES |  | 2022-03-31 | 19120
5 | ADANI ELECTRICITY | ELECTRICITY EXPENSES |  | 2022-05-20 | 28670
6 | ADANI ELECTRICITY | ELECTRICITY EXPENSES |  | 2022-06-20 | 22780
7 | ADANI ELECTRICITY | ELECTRICITY EXPENSES |  | 2022-08-13 | 159390
8 | ADANI ELECTRICITY | ELECTRICITY EXPENSES |  | 2022-09-13 | 96460
9 | ADANI ELECTRICITY | ELECTRICITY EXPENSES |  | 2022-10-08 | 92250
10 | ADANI ELECTRICITY | ELECTRICITY EXPENSES |  | 2022-12-19 | 197120
11 | ADANI ELECTRICITY | ELECTRICITY EXPENSES |  | 2023-01-09 | 139850
12 | ADANI ELECTRICITY | ELECTRICITY EXPENSES |  | 2023-02-22 | 139110
13 | ADANI ELECTRICITY | ELECTRICITY EXPENSES |  | 2023-03-08 | 129740
14 | ADANI ELECTRICITY | ELECTRICITY EXPENSES |  | 2023-03-31 | 119930
15 | ADANI ELECTRICITY | ELECTRICITY EXPENSES |  | 2023-06-09 | 322930
16 | ADANI ELECTRICITY | ELECTRICITY EXPENSES |  | 2023-08-02 | 154820
17 | ADANI ELECTRICITY | ELECTRICITY EXPENSES |  | 2023-08-12 | 154520
| K.L.PATHAK | SECURITY CHARGES |  | 2022-03-01 | 24000
| K.L.PATHAK | SECURITY CHARGES |  | 2022-03-01 | 8000
| K.L.PATHAK | SECURITY CHARGES |  | 2022-03-31 | 32000
| K.L.PATHAK | SECURITY CHARGES |  | 2022-04-30 | 32000
| K.L.PATHAK | SECURITY CHARGES |  | 2022-06-01 | 32000
| K.L.PATHAK | SECURITY CHARGES |  | 2022-07-01 | 36000
| K.L.PATHAK | SECURITY CHARGES |  | 2022-08-02 | 36000
| K.L.PATHAK | SECURITY CHARGES |  | 2022-09-01 | 36000
| K.L.PATHAK | SECURITY CHARGES |  | 2022-10-01 | 36000
| K.L.PATHAK | SECURITY CHARGES |  | 2022-11-01 | 36000
| K.L.PATHAK | SECURITY CHARGES |  | 2022-12-01 | 36000
| K.L.PATHAK | SECURITY CHARGES |  | 2023-01-01 | 36000
| K.L.PATHAK | SECURITY CHARGES |  | 2023-02-01 | 36000
| K.L.PATHAK | SECURITY CHARGES |  | 2023-03-01 | 36000
| K.L.PATHAK | SECURITY CHARGES |  | 2023-03-15 | 8000
| K.L.PATHAK | SECURITY CHARGES |  | 2023-03-15 | 8000
| K.L.PATHAK | SECURITY CHARGES |  | 2023-03-31 | 36000
| SGST ON - REVERSE CHARGE | SECURITY CHARGES |  | 2023-03-31 | 79200
| K.L.PATHAK | SECURITY CHARGES |  | 2023-05-01 | 36000
| K.L.PATHAK | SECURITY CHARGES |  | 2023-06-06 | 36000
| K.L.PATHAK | SECURITY CHARGES |  | 2023-07-01 | 36000
| K.L.PATHAK | SECURITY CHARGES |  | 2023-08-01 | 36000
| SALARY EXPENSES | SALARY PAID TO AVIMANYU GOPAL KHATUA FOR THE MONTH OF JULY 2019 |  | 2019-07-01 | 45000
| SALARY EXPENSES | SALARY PAID TO AVIMANYU GOPAL KHATUA FOR THE MONTH OF JULY 2019 |  | 2019-08-01 | 45000
| SALARY EXPENSES | SACHIN DEVIDAS MAGADE |  | 2019-08-31 | 10645
| SALARY EXPENSES | PAID TO AVIMANYU GOPAL KHATUA FOR THE MONTH OF AUGUST 2019. |  | 2019-09-01 | 45000
| SALARY EXPENSES | AVIMANYU GOPAL KHATUA |  | 2019-09-30 | 45000
| SALARY EXPENSES | SACHIN DEVIDAS MAGADE |  | 2019-09-30 | 30000
| SALARY EXPENSES | BEING SALARY FOR THE MONTH OF OCT 2019. |  | 2019-10-30 | 30000
| SALARY EXPENSES | BEING SALARY FOR THE MONTH OF OCT 2019. |  | 2019-10-31 | 45000
| SALARY EXPENSES | BEING SALARY FOR THE MONTH OF NOV 2019 |  | 2019-11-30 | 45000
| SALARY EXPENSES | BEING SALARY FOR THE MONTH OF NOV 2019. |  | 2019-11-30 | 30000
| SALARY EXPENSES | BEING SALARY FOR THE MONTH OF DEC 2019 |  | 2019-12-31 | 45000
| SALARY EXPENSES | BEING SALARY FOR THE MONTH OF DEC 2019. |  | 2019-12-31 | 30000
| SALARY EXPENSES | BEING SALARY FOR THE MONTH OF JAN 2020 |  | 2020-01-31 | 45000
| SALARY EXPENSES | BEING SALARY FOR THE MONTH OF JAN 2020 |  | 2020-01-31 | 30000
| SALARY EXPENSES | BEING SALARY FOR THE MONTH OF FEB 2020 |  | 2020-02-29 | 13448
| SALARY EXPENSES | BEING SALARY FOR THE MONTH OF FEB 2020 |  | 2020-02-29 | 30000
| SALARY EXPENSES | BEING SALARY FOR THE MONTH OF FEB 2020 |  | 2020-02-29 | 6000
| SALARY EXPENSES | BEING SALARY FOR THE MONTH OF MARCH 2020 (SACHIN MAGADE) |  | 2020-03-31 | 30000
| SALARY EXPENSES | BEING SALARY FOR THE MONTH OF MARCH 2020 (SWATI HIWALKAR) |  | 2020-03-31 | 30000
| SALARY EXPENSES | BEING CLOSING ENTRY |  | 2020-03-31
| SALARY EXPENSES | CH. NO. 000083 SLARY PAID TO SACHIN MAGADE FOR THE MONTH OF MARCH 20 (RS. 30000/- LESS PT. RS. 200/-), APRIL 20 - RS. 24000/- & MAY 20 - RS. 24000/-) |  | 2020-06-10 | 48000
| SALARY EXPENSES | CH. NO. 000082 SLARY PAID TO SWATI HIWALKAR FOR THE MONTH OF MARCH 20 (RS. 30000/- LESS PT. RS. 200/-), APRIL 20 - RS. 24000/- & MAY 20 - RS. 24000/-) |  | 2020-06-10 | 48000
| SALARY EXPENSES | BEING SALARY FOR THE MONTH OF JUNE 2020 |  | 2020-06-30 | 30000
| SALARY EXPENSES | BEING SALARY FOR THE MONTH OF JULY 2020 |  | 2020-07-31 | 30000
| SALARY EXPENSES | BEING SALARY FOR THE MONTH OF AUGUST 2020 |  | 2020-08-31 | 30000
| SALARY EXPENSES | BEING SALARY FOR THE MONTH OF SEPTEMBER 2020 |  | 2020-09-30 | 30000
| SALARY EXPENSES | BEING SALARY FOR THE MONTH OF OCT 2020 |  | 2020-10-31 | 30000
| SALARY EXPENSES | BEING SALARY FOR THE MONTH OF NOV 2020 |  | 2020-11-30 | 30000
| SALARY EXPENSES | BEING SALARY FOR THE MONTH OF DEC 2020 (SWATI HIWALKAR) |  | 2020-12-31 | 30000
| SALARY EXPENSES | BEING SALARY FOR THE MONTH OF JAN 2021 (SWATI HIWALKAR) |  | 2021-01-31 | 30000
| SALARY EXPENSES | BEING SALARY FOR THE MONTH OF FEB 2021 (SWATI HIWALKAR) |  | 2021-02-28 | 30000
| SALARY EXPENSES | CLOSING ENTERY |  | 2021-03-31
| SALARY EXPENSES | CHEQ.NO.015530, PAID TO ANIL SAVARDEKAR FOR APRIL -2021 RS.25000 + MAY 25000+ JUNE 25000) |  | 2021-07-17 | 75000
| SALARY EXPENSES | CHEQ.NO.015539, PAID TO ANIL SAVARDEKAR FOR JULY - 2021. |  | 2021-08-12 | 25000
| SALARY EXPENSES | CHEQ.NO.015541, PAID TO ANIL SAVARDEKAR FOR SEPT - 2021. |  | 2021-09-01 | 25000
| SALARY EXPENSES | CHEQ.NO.015550, PAID TO ANIL SAVARDEKAR FOR SEPT-2021 |  | 2021-10-01 | 25000
| SALARY EXPENSES | CHEQ.NO.015569, PAID TO ANIL SAVARDEKAR FOR OCT-2021 |  | 2021-10-25 | 25000
| SALARY EXPENSES | CHEQ.NO.015578, PAID TO ANIL SAVARDEKAR FOR OCT-2021 |  | 2021-12-01 | 25000
| SALARY EXPENSES | CHEQ.NO.015590, PAID TO ANIL SAVARDEKAR |  | 2022-01-01 | 25000
| SALARY EXPENSES | CHEQ.NO.441514, PAID TO ANIL SAVARDEKAR FOR JANUARY 2022 |  | 2022-02-01 | 25000
| SALARY EXPENSES | CHEQ.NO.449530, PAID TO ANIL SAVARDEKAR FOR FEBRUARY 2022 |  | 2022-03-03 | 25000
| SALARY EXPENSES | CHEQ.NO.449532, PAID TO MAHESH GUPTA FOR FEBRUARY 2022 FOR 18 DAYS SALARY |  | 2022-03-03 | 20571
| SALARY EXPENSES | CHEQ.NO.449533, PAID TO DATTA LAXMAN SARDESAI FEBRUARY 2022 |  | 2022-03-03 | 27000
| SALARY EXPENSES | CH NO 449572 PAID TO ANIL FOR SALARY MONTH OF MARCH 2022 |  | 2022-03-31 | 25000
| SALARY EXPENSES | CH NO 449572 PAID TO MAHESH GUPTA FOR SALARY MONTH OF MARCH 2022 |  | 2022-03-31 | 32000
| SALARY EXPENSES | CH NO 449572 PAID TO DATTA SARDESAI FOR SALARY MONTH OF MARCH 2022 |  | 2022-03-31 | 27000
| SALARY EXPENSES | CH NO 449639. PAID TO JAYVANT VITTHAL PARKAR FOR SALARY MONTH OF MARCH 2022 |  | 2022-03-31 | 16961
| SALARY EXPENSES | CLOSING ENTERY |  | 2022-03-31
| SALARY EXPENSES | CHEQ.NO. 449633. PAID TO ANIL SAVARDEKAR FOR APRIL 2022. |  | 2022-05-05 | 25000
| SALARY EXPENSES | CHEQ.NO.449635, PAID TO MAHESH GUPTA FOR APRIL 2022. |  | 2022-05-05 | 36900
| SALARY EXPENSES | CHEQ.NO.449636, PAID TO DATTA LAXMAN SARDESAI APRIL 2022. |  | 2022-05-05 | 31500
| SALARY EXPENSES | CHEQ.NO.449653, PAID TO JATIN DINESH PANCHAL APRIL 2022. |  | 2022-05-05 | 47000
| SALARY EXPENSES | CHEQ.NO.449638, PAID TO MOHAMMED NAZIMUDDIN APRIL 2022. |  | 2022-05-05 | 43400
| SALARY EXPENSES | CH NO 449640. PAID TO JAYVANT VITTHAL PARKAR FOR SALARY MONTH OF APRIL 2022 |  | 2022-05-05 | 23900
| SALARY EXPENSES | CH NO 449641. PAID TO PAWAN KUMAR GHORELA FOR SALARY MONTH OF APRIL 2022 |  | 2022-05-05 | 19717
| SALARY EXPENSES | CH NO 449642. PAID TO RAGHAVENDRA BISHWAS FOR SALARY MONTH OF APRIL 2022 |  | 2022-05-05 | 3907
| SALARY EXPENSES | CH NO 449643. PAID TO PANKAJ PANDEY FOR SALARY MONTH OF APRIL 2022 |  | 2022-05-05 | 19120
| SALARY EXPENSES | CH NO 449644. PAID TO KALYAN ARUN RANGE FOR SALARY MONTH OF APRIL 2022 |  | 2022-05-05 | 21700
| SALARY EXPENSES | CH NO 449645. PAID TO SATYANARAYAN YADAV FOR SALARY MONTH OF APRIL 2022 |  | 2022-05-05 | 16300
| SALARY EXPENSES | CHEQ.NO. 449656. PAID TO ANIL SAVARDEKAR FOR MAY 2022 |  | 2022-06-01 | 25000
| SALARY EXPENSES | CHEQ.NO.449658, PAID TO MAHESH GUPTA FOR MAY 2022 |  | 2022-06-01 | 36900
| SALARY EXPENSES | CHEQ.NO.449659, PAID TO DATTA LAXMAN SARDESAI MAY 2022 |  | 2022-06-01 | 31500
| SALARY EXPENSES | CHEQ.NO.471113, PAID TO MOHAMMED NAZIMUDDIN MAY 2022 |  | 2022-06-01 | 43400
| SALARY EXPENSES | CH NO 471114. PAID TO JAYVANT VITTHAL PARKAR FOR SALARY MONTH OF MAY 2022 |  | 2022-06-01 | 23900
| SALARY EXPENSES | CH NO 471115. PAID TO PAWAN KUMAR GHORELA FOR SALARY MONTH OF MAY 2022 |  | 2022-06-01 | 45500
| SALARY EXPENSES | CH NO 471117. PAID TO PANKAJ PANDEY FOR SALARY MONTH OF MAY 2022 |  | 2022-06-01 | 23900
| SALARY EXPENSES | CH NO 471118. PAID TO KALYAN ARUN RANGE FOR SALARY MONTH OF MAY 2022 |  | 2022-06-01 | 21700
| SALARY EXPENSES | CH NO 471119. PAID TO SATYANARAYAN YADAV FOR SALARY MONTH OF MAY 2022 |  | 2022-06-01 | 16300
| SALARY EXPENSES | CHEQ.NO.471127, PAID TO JATIN DINESH PANCHAL MAY 2022 |  | 2022-06-04 | 70500
| SALARY EXPENSES | CH.NO. 471128 PAID SALARY TO RAGHVENRA BISHWAS JOINING DATED 27-04-2022 FOR THE MONTH OF MAY 2022 |  | 2022-06-04 | 35750
| SALARY EXPENSES | CHEQ.NO.471154 Being Salay Paid JAYKUMAR S.NAIDU JD 025.05.2022 |  | 2022-07-01 | 23900
| SALARY EXPENSES | CHEQ.NO.471155 Being Salay Paid SHUBHAM SURESH PATEL JD 20.06.2022 |  | 2022-07-01 | 38000
| SALARY EXPENSES | CHEQ.NO.471156 Being Salay Paid ANIL SAVARDEKAR MONTH OF JUNE 2022 |  | 2022-07-01 | 25000
| SALARY EXPENSES | CHEQ.NO.471158 BEING AMOUNT PAID MAHESH GUPTA FOR SALARY MONTH OF JUNE 2022 |  | 2022-07-01 | 36900
| SALARY EXPENSES | CHEQ.NO.471159 BEING AMOUNT PAID DATTA LAXMAN SARDESAI PENDEKAR FOR SALARY MONTH OF JUNE 2022 |  | 2022-07-01 | 31500
| SALARY EXPENSES | CHEQ.NO.471160 BEING AMOUNT PAID JATIN DINESH PANCHAL FOR SALARY MONTH OF JUNE 2022 |  | 2022-07-01 | 70500
| SALARY EXPENSES | CHEQ.NO.471161 BEING AMOUNT PAID MOHAMMED NAZIMUDDIN JD 01.04.2022 FOR SALARY MONTH OF JUNE 2022 |  | 2022-07-01 | 43400
| SALARY EXPENSES | CHEQ.NO.471162 BEING AMOUNT PAID JAYVANT VITHAL PARKAR FOR SALARY MONTH OF JUNE 2022 |  | 2022-07-01 | 23900
| SALARY EXPENSES | CHEQ.NO.471163 BEING AMOUNT PAID PAWAN KUMAR GHORELAFOR SALARY MONTH OF JUNE 2022 |  | 2022-07-01 | 45500
| SALARY EXPENSES | CHEQ.NO.471164 BEING AMOUNT PAID RAGHVENDRA BISHWAS FOR SALARY MONTH OF JUNE 2022 |  | 2022-07-01 | 35750
| SALARY EXPENSES | CHEQ.NO.471165 BEING AMOUNT PAID PANKAJ PANDEY FOR SALARY MONTH OF JUNE 2022 |  | 2022-07-01 | 23900
| SALARY EXPENSES | CHEQ.NO.471166 BEING AMOUNT PAID KALYAN ARUN RANGE FOR SALARY MONTH OF JUNE 2022 |  | 2022-07-01 | 21700
| SALARY EXPENSES | CHEQ.NO.471167 BEING AMOUNT PAID SATYA YADAV FOR SALARY MONTH OF JUNE 2022 |  | 2022-07-01 | 16300
| SALARY EXPENSES | CHEQ.NO.471184 Being Salay Paid Abhijeet Arjune Chirankar JD 06.06.2022 |  | 2022-07-01 | 39600
| SALARY EXPENSES | CH.NO. 471191 PAID SALARY TO EKNATH KHADE |  | 2022-07-14 | 150000
| SALARY EXPENSES | CH.NO. 471192 PAID SALARY TO SARUBAI KHADE |  | 2022-07-14 | 150000
| SALARY EXPENSES | CHEQ.NO. 449717 Being Salay Paid JAYKUMAR S.NAIDU FOR THE MONTH OF JULY 2022 |  | 2022-08-02 | 23900
| SALARY EXPENSES | CHEQ.NO. 449736 Salay Paid EKNATH NAMDEV KHANDE MONTH OF JULY 2022 |  | 2022-08-02 | 75000
| SALARY EXPENSES | CHEQ.NO. 449737 Salay Paid SARUBAI KHADE MONTH OF JULY 2022 |  | 2022-08-02 | 75000
| SALARY EXPENSES | CHEQ.NO. 449720 Salay Paid ABHIJEET ARJUN CHIRANKAR MONTH OF JULY 2022 |  | 2022-08-02 | 47500
| SALARY EXPENSES | CHEQ.NO. 449721 Salay Paid SHUBHAM SURESH PATIL MONTH OF JULY 2022 |  | 2022-08-02 | 14134
| SALARY EXPENSES | CHEQ.NO. 449722 Salay Paid ANIL SAVARDEKAR MONTH OF JULY 2022 |  | 2022-08-02 | 25000
| SALARY EXPENSES | CHEQ.NO. 449724 SALATY PAID MAHESH GUPTA MONTH OF JULY 2022 |  | 2022-08-02 | 36900
| SALARY EXPENSES | CHEQ.NO. 449725 SALATY PAID DATTA LAXMAN SARDESAI PEDNEKAR MONTH OF JULY 2022 |  | 2022-08-02 | 31500
| SALARY EXPENSES | CHEQ.NO. 449726 SALARY PAID JATIN DINESH PANCHAL MONTH OF JULY 2022 |  | 2022-08-02 | 70500
| SALARY EXPENSES | CHEQ.NO. 449727 SALARY PAID MOHAMMED NAZIMUDDIN MONTH OF JULY 2022 |  | 2022-08-02 | 43400
| SALARY EXPENSES | CHEQ.NO. 449728 SALARY PAID JAYVANT VITHAL PARKAR MONTH OF JULY 2022 |  | 2022-08-02 | 23900
| SALARY EXPENSES | CHEQ.NO. 449729 SALARY PAID PAWAN KUMAR GHORELA MONTH OF JULY 2022 |  | 2022-08-02 | 45500
| SALARY EXPENSES | CHEQ.NO. 449730 SALARY PAID RAGHVENDRA BISHWAS MONTH OF JULY 2022 |  | 2022-08-02 | 35750
| SALARY EXPENSES | CHEQ.NO. 449731 SALARY PAID PANKAJ PANDEY MONTH OF JULY 2022 |  | 2022-08-02 | 23900
| SALARY EXPENSES | CHEQ.NO. 449732 SALARY PAID KALYAN ARUN RANGE MONTH OF JULY 2022 |  | 2022-08-02 | 21700
| SALARY EXPENSES | CHEQ.NO. 449733 SALARY SATYANARAYAN YADAV MONTH OF JULY 2022 |  | 2022-08-02 | 16300
| SALARY EXPENSES | CH.NO. 471222 AMOUNT PAID BY ABHIJEET ARJUN CHIRANKAR SALARY MONTH OF AUG 2022 |  | 2022-09-01 | 47500
| SALARY EXPENSES | CH.NO. 471223 AMOUNT PAID BY JAYKUMAR S.NAIDU- SALARY MONTH OF AUG 2022 |  | 2022-09-01 | 23900
| SALARY EXPENSES | CH.NO. 471224 AMOUNT PAID BY SHUBHAM SURESH PATIL-SALARY MONTH OF AUG 2022 |  | 2022-09-01 | 38000
| SALARY EXPENSES | CH.NO. 471225 AMOUNT PAID BY ANIL SAVARDEKAR-SALARY MONTH OF AUG 2022 |  | 2022-09-01 | 25000
| SALARY EXPENSES | CH.NO. 471227 AMOUNT PAID BY MAHESH GUPTA SALARY MONTH OF AUG 2022 |  | 2022-09-01 | 36900
| SALARY EXPENSES | CH.NO. 471228 AMOUNT PAID BY DATTA LAXMAN SARDESAI PENDNEKAR- SALARY MONTH OF AUG 2022 |  | 2022-09-01 | 31500
| SALARY EXPENSES | CH.NO. 471229 AMOUNT PAID BY JATIN DINESH PANCHAL- SALARY MONTH OF AUG 2022 |  | 2022-09-01 | 70500
| SALARY EXPENSES | CH.NO. 471230 AMOUNT PAID BY MOHAMMED NAZIMUDDIN- SALARY MONTH OF AUG 2022 |  | 2022-09-01 | 43400
| SALARY EXPENSES | CH.NO. 471231 AMOUNT PAID BY JAYVANT VITTHAL PARKAR- SALARY MONTH OF AUG 2022 |  | 2022-09-01 | 23900
| SALARY EXPENSES | CH.NO. 471232 AMOUNT PAID BY PAWAN KUMAR GORELA- SALARY MONTH OF AUG 2022 |  | 2022-09-01 | 45500
| SALARY EXPENSES | CH.NO. 471233 AMOUNT PAID BY RAGHVENDRA BISHWAS- SALARY MONTH OF AUG 2022 |  | 2022-09-01 | 35750
| SALARY EXPENSES | CH.NO. 471234 AMOUNT PAID BY PANKAJ PANDEY- SALARY MONTH OF AUG 2022 |  | 2022-09-01 | 23900
| SALARY EXPENSES | CH.NO. 471235 AMOUNT PAID BY KALYAN ARUN RANGE SALARY MONTH OF AUG 2022 |  | 2022-09-01 | 21700
| SALARY EXPENSES | CH.NO. 471236 AMOUNT PAID BY KALYAN ARUN RANGE SALARY MONTH OF AUG 2022 |  | 2022-09-01 | 16300
| SALARY EXPENSES | CH.NO. 471240 AMOUNT PAID BY EKNATH NAMDEV KHANDE SALARY MONTH OF AUG 2022 |  | 2022-09-01 | 75000
| SALARY EXPENSES | CH.NO. 471241 AMOUNT PAID BY SARUBAI KHANDE SALARY MONTH OF AUG 2022 |  | 2022-09-01 | 75000
| SALARY EXPENSES | CH.NO. 471242 AMOUNT PAID BY RAMESH H.DHAKAL SALARY MONTH OF AUG 2022 JOING DATE 22.08.2022 |  | 2022-09-01 | 23387
| SALARY EXPENSES | CH.NO.471281 AMOUNT PAID EKNATH NAMDEV KHADE SALARY MONTH OF SEPT.2022 |  | 2022-10-01 | 75000
| SALARY EXPENSES | CH.NO.471282 AMOUNT PAID SARUBAI KHADE SALARY MONTH OF SEPT.2022 |  | 2022-10-01 | 75000
| SALARY EXPENSES | CH.NO.471284 AMOUNT PAID JAYKUMAR S.NAIDU SALARY MONTH OF SEPT.2022 |  | 2022-10-01 | 23900
| SALARY EXPENSES | CH.NO.471285 AMOUNT PAID SHUBHAM SURESH PATIL- SALARY MONTH OF SEPT.2022 |  | 2022-10-01 | 38000
| SALARY EXPENSES | CH.NO.471286 AMOUNT PAID ANIL SAVARDEKAR- SALARY MONTH OF SEPT.2022 |  | 2022-10-01 | 25000
| SALARY EXPENSES | CH.NO.471288 AMOUNT PAID MAHESH GUPTA FOR SALARY MONTH OF SEPT.2022 |  | 2022-10-01 | 36900
| SALARY EXPENSES | CH.NO.471289 AMOUNT PAID DATTA LAXMAN SARDESAI PEDNEKAR SALARY MONTH OF SEPT.2022 |  | 2022-10-01 | 31500
| SALARY EXPENSES | CH.NO.471290 AMOUNT PAID JATIN DINESH PANCHAL SALARY MONTH OF SEPT.2022 |  | 2022-10-01 | 70500
| SALARY EXPENSES | CH.NO.471291 AMOUNT PAID MOHAMMED NAZIMUDDIN SALARY MONTH OF SEPT.2022 |  | 2022-10-01 | 43400
| SALARY EXPENSES | CH.NO.471292 AMOUNT PAID JAYVANT VITTHAL PARKAR SALARY MONTH OF SEPT.2022 |  | 2022-10-01 | 23900
| SALARY EXPENSES | CH.NO.471293 AMOUNT PAID PAWAN KUMAR GHORELA SALARY MONTH OF SEPT.2022 |  | 2022-10-01 | 45500
| SALARY EXPENSES | CH.NO.471294 AMOUNT PAID RAGHVENDRA BISHWAS SALARY MONTH OF SEPT.2022 |  | 2022-10-01 | 35750
| SALARY EXPENSES | CH.NO.471295 AMOUNT PAID PANKAJ PANDEY SALARY MONTH OF SEPT.2022 |  | 2022-10-01 | 23900
| SALARY EXPENSES | CH.NO.471296 AMOUNT PAID KALYAN ARUN RANGE SALARY MONTH OF SEPT.2022 |  | 2022-10-01 | 21700
| SALARY EXPENSES | CH.NO.471297 AMOUNT PAID RAMESH H DHAKAL SALARY MONTH OF SEPT.2022 |  | 2022-10-01 | 72500
| SALARY EXPENSES | CHEQ. NO. 471204.NEFT AMOUNT PAID BY ABHIJEET ARJUN CHIRANKAR SALARY MONTH OF SEPT 2022 |  | 2022-10-01 | 47500
| SALARY EXPENSES | CHEQ. NO. 471329 AMOUNT PAID EKNATH NAMDEV KHADE FOR SALARY MONTH OF OCT 2022 |  | 2022-11-01 | 75000
| SALARY EXPENSES | CHEQ. NO. 471330 AMOUNT PAID SARUBAI KHADE FOR SALARY MONTH OF OCT 2022 |  | 2022-11-01 | 75000
| SALARY EXPENSES | CHEQ. NO. 471331 AMOUNT PAID ABHIJEET ARJUN CHIRANKAR FOR SALARY MONTH OF OCT 2022 |  | 2022-11-01 | 47500
| SALARY EXPENSES | CHEQ. NO. 471332 AMOUNT PAID JAYKUMAR S NAIDU FOR SALARY MONTH OF OCT 2022 |  | 2022-11-01 | 23900
| SALARY EXPENSES | CHEQ. NO. 471333 AMOUNT PAID SHUBHAM SURESH PATIL FOR SALARY MONTH OF OCT 2022 |  | 2022-11-01 | 38000
| SALARY EXPENSES | CHEQ. NO. 471334 AMOUNT PAID ANIL SAVARDEKAR FOR SALARY MONTH OF OCT 2022 |  | 2022-11-01 | 25000
| SALARY EXPENSES | CHEQ. NO. 471336 AMOUNT PAID MAHESH GUPTA FOR SALARY MONTH OF OCT 2022 |  | 2022-11-01 | 36900
| SALARY EXPENSES | CHEQ. NO. 471337 AMOUNT PAID DATTA LAXMAN SARDESAI PEDNEKAR FOR SALARY MONTH OF OCT 2022 |  | 2022-11-01 | 31500
| SALARY EXPENSES | CHEQ. NO. 471338 AMOUNT PAID JATIN DINESH PANCHAL FOR SALARY MONTH OF OCT 2022 |  | 2022-11-01 | 70500
| SALARY EXPENSES | CHEQ. NO. 471339AMOUNT PAID MOHAMMED NAZIMUDDIN SALARYMONTH OF OCT 2022 |  | 2022-11-01 | 43400
| SALARY EXPENSES | CHEQ. NO. 471340 AMOUNT PAID JAYVANT VITTHAL PARKAR SALARY MONTH OF OCT 2022 |  | 2022-11-01 | 23900
| SALARY EXPENSES | CHEQ. NO. 471341 AMOUNT PAID PAWAN KUMAR GHORELA SALARY MONTH OF OCT 2022 |  | 2022-11-01 | 45500
| SALARY EXPENSES | CHEQ. NO. 471342 AMOUNT PAID RAGHVENDRA BISHWAS SALARY MONTH OF OCT 2022 |  | 2022-11-01 | 35750
| SALARY EXPENSES | CHEQ. NO. 471343 AMOUNT PAID PANKAJ PANDEY SALARY MONTH OF OCT 2022 |  | 2022-11-01 | 23900
| SALARY EXPENSES | CHEQ. NO. 471344 AMOUNT PAID KALYAN ARUN RANGE SALARY MONTH OF OCT 2022 |  | 2022-11-01 | 21700
| SALARY EXPENSES | CHEQ. NO. 471345 AMOUNT PAID RAMESH H DHAKALSALARY MONTH OF OCT 2022 |  | 2022-11-01 | 72500
| SALARY EXPENSES | CH.NO 470632 PAID EKNATH KHADE FOR NOV.2022 |  | 2022-12-01 | 75000
| SALARY EXPENSES | CH.NO 470635 PAID ABHIJEET CHIRANKAR LAST SALARY 45500 + 5000(INCRESE)=49500 FOR NOV 2022 |  | 2022-12-01 | 53700
| SALARY EXPENSES | CH.NO 470633 PAID SARUBAI KHADE FOR NOV 2022 |  | 2022-12-01 | 75000
| SALARY EXPENSES | CH.NO 470636 PAID JAYKUMAR NAIDU FOR NOV 2022 |  | 2022-12-01 | 23900
| SALARY EXPENSES | CH.NO 470637 PAID TO SHUBHAM SURESH PATIL FOR NOV.2022 ( CH REVESE AFTER 3 MONTH RETURN DT 31-03-23 |  | 2022-12-01 | 38000
| SALARY EXPENSES | CH.NO 470638 PAID TO ANIL SAVARDEKAR FOR NOV 2022 |  | 2022-12-01 | 25000
| SALARY EXPENSES | CH.NO 470641 PAID TO DATTA PEDNEKAR FOR NOV.2022 |  | 2022-12-01 | 31500
| SALARY EXPENSES | CH.NO 470640 PAID MAHESH GUPTA FOR NOV 2022 |  | 2022-12-01 | 36900
| SALARY EXPENSES | CH.NO 470644 PAID TO JAYVANT VITTHAL PARKAR FOR NOV 2022 |  | 2022-12-01 | 23900
| SALARY EXPENSES | CH.NO 470643 PAID TO MOHAMMED NAZIMMUDIN FOR NOV.2022 |  | 2022-12-01 | 43400
| SALARY EXPENSES | CH.NO 470645 PAID TO PAWAN GHORELA FOR NOV 2022 |  | 2022-12-01 | 45500
| SALARY EXPENSES | CH.NO 470646 PAID TO RAGHVENDRA BISHWAS |  | 2022-12-01 | 35750
| SALARY EXPENSES | CH.NO 470647 PAID TO PANKAJ PANDEY FOR NOV.2022 |  | 2022-12-01 | 23900
| SALARY EXPENSES | CH.NO 470648 PAID TO KALYAN RANGE FOR NOV 2022 |  | 2022-12-01 | 21700
| SALARY EXPENSES | CH.NO 470649 PAID TO RAMESH H. DHAKAL FOR NOV.2022 |  | 2022-12-01 | 72500
| SALARY EXPENSES | CHEQ. NO. 470650 AMOUNT PAID JATIN DINESH PANCHAL FOR SALARY MONTH OF NOV 2022 |  | 2022-12-01 | 23500
| SALARY EXPENSES | CHEQ. NO. 471477 AMOUNT PAID EKNATH NAMDEV KHADE FOR SALARY MONTH OF DEC 2022 |  | 2023-01-01 | 75000
| SALARY EXPENSES | CHEQ. NO. 470656 AMOUNT PAID SARUBAI KHADE FOR SALARY MONTH OF DEC 2022 |  | 2023-01-01 | 75000
| SALARY EXPENSES | CHEQ. NO. 471519 AMOUNT PAID ABHIJEET ARJUN CHIRANKAR FOR SALARY MONTH OF DEC 2022 |  | 2023-01-01 | 53700
| SALARY EXPENSES | CHEQ. NO. 471480 AMOUNT PAID JAYKUMAR S NAIDU FOR SALARY MONTH OF DEC 2022 |  | 2023-01-01 | 23900
| SALARY EXPENSES | CHEQ. NO. 471482 AMOUNT PAID ANIL SAVARDEKAR FOR SALARY MONTH OF DEC 2022 |  | 2023-01-01 | 25000
| SALARY EXPENSES | CHEQ. NO. 471484 AMOUNT PAID MAHESH GUPTA FOR SALARY MONTH OF DEC 2022 |  | 2023-01-01 | 36900
| SALARY EXPENSES | CHEQ. NO. 471485 AMOUNT PAID DATTA LAXMAN SARDESAI PEDNEKAR FOR SALARY MONTH OF DEC 2022 |  | 2023-01-01 | 31500
| SALARY EXPENSES | CHEQ. NO. 471486 AMOUNT PAID MOHAMMED NAZIMUDDIN FOR SALARY MONTH OF DEC 2022 |  | 2023-01-01 | 43400
| SALARY EXPENSES | CHEQ. NO. 471487 AMOUNT PAID JAYVANT VITTHAL PARKAR FOR SALARY MONTH OF DEC 2022 |  | 2023-01-01 | 23900
| SALARY EXPENSES | CHEQ. NO. 471488 AMOUNT PAID PAWAN KUMAR GHORELA FOR SALARY MONTH OF DEC 2022 |  | 2023-01-01 | 45500
| SALARY EXPENSES | CHEQ. NO. 471489 AMOUNT PAID RAGHVENDRA BISHWAS FOR SALARY MONTH OF DEC 2022 |  | 2023-01-01 | 35750
| SALARY EXPENSES | CHEQ. NO. 471490 AMOUNT PAID PANKAJ PANDEY FOR SALARY MONTH OF DEC 2022 |  | 2023-01-01 | 23900
| SALARY EXPENSES | CHEQ. NO. 471491 AMOUNT PAID KALYAN ARUN RANGE FOR SALARY MONTH OF DEC 2022 |  | 2023-01-01 | 21700
| SALARY EXPENSES | CHEQ. NO. 471492 AMOUNT PAID RAMESH H DHAKAL FOR SALARY MONTH OF DEC 2022 |  | 2023-01-01 | 72500
| SALARY EXPENSES | CH.NO 471493 PAID TO SHUBHAM SURESH PATIL FOR DEC .2022 ( CH. RETURN AFTER 3 MONTHS RETURN DT 31-03-2023) |  | 2023-01-01 | 38000
| SALARY EXPENSES | CH.NO 470659 AC SALARY FOR JAN.2023. PAID TO ABHIJEET CHIRANKAR. |  | 2023-01-21 | 53700
| SALARY EXPENSES | CH.NO 471594 AMOUNT PAID BY EKNATH NAMDEV KHADE FOR SALARY MONTH OF JAN 2023 |  | 2023-02-01 | 75000
| SALARY EXPENSES | CH.NO 471595 AMOUNT PAID BY SARUBAI KHADE FOR SALARY MONTH OF JAN 2023 |  | 2023-02-01 | 75000
| SALARY EXPENSES | CH.NO 471597 AMOUNT PAID BY JAY KUMAR S.NAIDU SALARY MONTH OF JAN 2023 |  | 2023-02-01 | 23900
| SALARY EXPENSES | CH.NO 471598 AMOUNT PAID BY ANIL SAVARDEKAR SALARY MONTH OF JAN 2023 |  | 2023-02-01 | 25000
| SALARY EXPENSES | CH.NO 471600 AMOUNT PAID BY MAHESH GUPTA SALARY MONTH OF JAN 2023 |  | 2023-02-01 | 36900
| SALARY EXPENSES | CH.NO 471601 AMOUNT PAID BY DATTA LAXMAN SARDESAI PEDNEKAR SALARY MONTH OF JAN 2023 |  | 2023-02-01 | 31500
| SALARY EXPENSES | CH.NO 471602 AMOUNT PAID BY MOHAMMED NAZIMUDDIN SALARY MONTH OF JAN 2023 |  | 2023-02-01 | 43400
| SALARY EXPENSES | CH.NO 471603 AMOUNT PAID BY JAYVANT VITTHAL PARKAR SALARY MONTH OF JAN 2023 |  | 2023-02-01 | 23900
| SALARY EXPENSES | CH.NO 471604 AMOUNT PAID BY PAWAN KUMAR GHORELA SALARY MONTH OF JAN 2023 |  | 2023-02-01 | 45500
| SALARY EXPENSES | CH.NO 471605 AMOUNT PAID BY RAGHVENDRA BISHWAS SALARY MONTH OF JAN 2023 |  | 2023-02-01 | 35750
| SALARY EXPENSES | CH.NO 471606 AMOUNT PAID BY PANKAJ PANDEY SALARY MONTH OF JAN 2023 |  | 2023-02-01 | 23900
| SALARY EXPENSES | CH.NO 471607 AMOUNT PAID BY KALYAN ARUN RANGE SALARY MONTH OF JAN 2023 |  | 2023-02-01 | 21700
| SALARY EXPENSES | CH.NO 471608 AMOUNT PAID BY RAMESH H DHAKAL SALARY MONTH OF JAN 2023 |  | 2023-02-01 | 72500
| SALARY EXPENSES | Chqque No 471610 AMOUNT PAID MOHAMMED SAMEER GAHLOT SALARY 40000.00 21JAN 2023 31.01.2023 11DAY @ 14194.00 |  | 2023-02-01 | 14194
| SALARY EXPENSES | Chqque No 470912 AMOUNT PAID NAUFIL M.HAFANI BHURE SALARY 18000.00 - JOINING DATE -22.01.2023. |  | 2023-02-01 | 4839
| SALARY EXPENSES | Chqque No 470926 AMOUNT PAID NAUFIL M.HAFANI BHURE SALARY BALANCE - SALARY - 18,000/- P.M. FOR 10 DAYS 5806/- LESS - P.TAX - 200/- = 5606/- LESS PAID 4639/- ON 01.02.2022 CHEQ. NO. 470912 =967/- BALACE PAID. |  | 2023-02-06 | 967
| SALARY EXPENSES | CH.NO 470997 AMOUNT PAID BY EKNATH NAMDEV KHADE FOR SALARY MONTH OF FEB 2023 |  | 2023-03-01 | 75000
| SALARY EXPENSES | CH.NO 470998 AMOUNT PAID BY SARUBAI KHADE FOR SALARY MONTH OF FEB 2023 |  | 2023-03-01 | 75000
| SALARY EXPENSES | CH.NO 470999 AMOUNT PAID ABHIJEET ARJUNE CHIRANKAR FOR SALARY MONTH OF FEB 2023 |  | 2023-03-01 | 53700
| SALARY EXPENSES | CH.NO 471000 AMOUNT PAID JAYKUMAR S.NAIDU FOR SALARY MONTH OF FEB 2023 |  | 2023-03-01 | 23900
| SALARY EXPENSES | CH.NO 471001 AMOUNT PAID ANIL SAVARDEKAR FOR SALARY MONTH OF FEB 2023 |  | 2023-03-01 | 25000
| SALARY EXPENSES | CH.NO 471003 AMOUNT PAID MAHESH GUPTA FOR SALARY MONTH OF FEB 2023 |  | 2023-03-01 | 36900
| SALARY EXPENSES | CH.NO 471004 AMOUNT PAID DATTA LAXMAN SARDESAI PEDNEKAR FOR SALARY MONTH OF FEB 2023 |  | 2023-03-01 | 31500
| SALARY EXPENSES | CH.NO 471005 AMOUNT PAID MOHAMMED NAZIMUDDIN FOR SALARY MONTH OF FEB 2023 |  | 2023-03-01 | 43400
| SALARY EXPENSES | CH.NO 471006 AMOUNT PAID JAYVANT VITTHAL PARKAR FOR SALARY MONTH OF FEB 2023 |  | 2023-03-01 | 23900
| SALARY EXPENSES | CH.NO 471007 AMOUNT PAID PAWAN KUMAR GHORELA FOR SALARY MONTH OF FEB 2023 |  | 2023-03-01 | 45500
| SALARY EXPENSES | CH.NO 471008 AMOUNT PAID RAGHVENDRA BISHWAS FOR SALARY MONTH OF FEB 2023 |  | 2023-03-01 | 35750
| SALARY EXPENSES | CH.NO 471009 AMOUNT PAID PANKAJ PANDEY FOR SALARY MONTH OF FEB 2023 |  | 2023-03-01 | 23900
| SALARY EXPENSES | CH.NO 471010 AMOUNT PAID KALYAN ARUN RANGE FOR SALARY MONTH OF FEB 2023 |  | 2023-03-01 | 21700
| SALARY EXPENSES | CH.NO 472111 AMOUNT PAID RAMESH H.DHAKAL FOR SALARY MONTH OF FEB 2023 |  | 2023-03-01 | 72500
| SALARY EXPENSES | CH.NO 472112 AMOUNT PAID NAUFIL M.NANIF BHURE SALARY MONTH OF FEB 2023 |  | 2023-03-01 | 18000
| SALARY EXPENSES | CH.NO 472113 AMOUNT PAID MOHAMMED SAMEER GHALOT FOR SALARY MONTH OF FEB 2023 |  | 2023-03-01 | 40000
| SALARY EXPENSES | CH.NO 472114 AMOUNT PAID KIRAN RANBAHADUR DHAKAL FOR SALARY MONTH OF FEB 2023 |  | 2023-03-01 | 20000
| SALARY EXPENSES | CHEQ. NO. 472198 AMOUNT PAID EKNATH NAMDEV KHADE FOR SALARY MONTH OF MARCH 2023 |  | 2023-03-31 | 75000
| SALARY EXPENSES | CHEQ. NO. 472199 AMOUNT PAID SARUBAI EKNATH KHADE FOR SALARY MONTH OF MARCH 2023 |  | 2023-03-31 | 75000
| SALARY EXPENSES | CHEQ. NO. 472200 AMOUNT PAID ABHIJEET ARJUN CHIRANKAR FOR SALARY MONTH OF MARCH 2023 |  | 2023-03-31 | 53700
| SALARY EXPENSES | CHEQ. NO. 472201 AMOUNT PAID JAYKUMAR S.NAIDU FOR SALARY MONTH OF MARCH 2023 |  | 2023-03-31 | 23900
| SALARY EXPENSES | CHEQ. NO. 472202 AMOUNT PAID ANIL SAVARDEKAR FOR SALARY MONTH OF MARCH 2023 |  | 2023-03-31 | 25000
| SALARY EXPENSES | CHEQ. NO. 472203 AMOUNT PAID MAHESH GUPTA FOR SALARY MONTH OF MARCH 2023 |  | 2023-03-31 | 36900
| SALARY EXPENSES | CHEQ. NO. 472204 AMOUNT PAID DATTA KAXMAN SARDESAI PEDNEKAR FOR SALARY MONTH OF MARCH 2023 |  | 2023-03-31 | 31500
| SALARY EXPENSES | CHEQ. NO. 472205 AMOUNT PAID MOHAMMED NAZIMUDDIN FOR SALARY MONTH OF MARCH 2023 |  | 2023-03-31 | 43400
| SALARY EXPENSES | CHEQ. NO. 472206 AMOUNT PAID JAYVANT VITTHAL PARKAR FOR SALARY MONTH OF MARCH 2023 |  | 2023-03-31 | 23900
| SALARY EXPENSES | CHEQ. NO. 472207 AMOUNT PAID PAWAN KUMAR GHORELA FOR SALARY MONTH OF MARCH 2023 |  | 2023-03-31 | 45500
| SALARY EXPENSES | CHEQ. NO. 472208 AMOUNT PAID RAGHVENDRA BISHWAS FOR SALARY MONTH OF MARCH 2023 |  | 2023-03-31 | 35750
| SALARY EXPENSES | CHEQ. NO. 472209 AMOUNT PAID PANKAJ PANDEY FOR SALARY MONTH OF MARCH 2023 |  | 2023-03-31 | 23900
| SALARY EXPENSES | CHEQ. NO. 472411 AMOUNT PAID KALYAN ARUN RANGE FOR SALARY MONTH OF MARCH 2023 |  | 2023-03-31 | 21700
| SALARY EXPENSES | CHEQ. NO. 472412 AMOUNT PAID RAMESH H.DHAKAL FOR SALARY MONTH OF MARCH 2023 |  | 2023-03-31 | 72500
| SALARY EXPENSES | CHEQ. NO. 472413 AMOUNT PAID NAUFIL M NANIF BHURE FOR SALARY MONTH OF MARCH 2023 |  | 2023-03-31 | 18000
| SALARY EXPENSES | CHEQ. NO. 472414 AMOUNT PAID MOHAMMED SAMEER GHALOTE FOR SALARY MONTH OF MARCH 2023 |  | 2023-03-31 | 40000
| SALARY EXPENSES | CHEQ. NO. 472415 AMOUNT PAID KIRAN RANBAHADUR DHAKAL FOR SALARY MONTH OF MARCH 2023 |  | 2023-03-31 | 35000
| SALARY EXPENSES | CH.NO 470637 PAID TO SHUBHAM SURESH PATIL FOR NOV.2022 ( CH REVESE AFTER 3 MONTH RETURN DT 31-03-23 |  | 2023-03-31
| SALARY EXPENSES | CH.NO 471493 PAID TO SHUBHAM SURESH PATIL FOR DEC .2022 ( CH. RETURN AFTER 3 MONTHS RETURN DT 31-03-2023) |  | 2023-03-31
| SALARY EXPENSES | CHQ 470925 ISSUED DT 06-02-2023 (CHQ REVERSE AFTER 3 MONTH, REVERSED DT 31-03-2023) |  | 2023-03-31
| SALARY EXPENSES | CLOSING ENTERY |  | 2023-03-31
| SALARY EXPENSES | CH.NO 472455 AMOUNT PAID EKNATH NAMDEV KHADE FOR SALARY MONTH OF APRIL- 2023 |  | 2023-05-06 | 75000
| SALARY EXPENSES | CH.NO 472456 AMOUNT PAID SARUBAI EKNATH KHADE FOR SALARY MONTH OF APRIL- 2023 |  | 2023-05-06 | 75000
| SALARY EXPENSES | CH.NO 472457 AMOUNT PAID ABHIJEET ARJUNE CHIRANKAR FOR SALARY MONTH OF APRIL- 2023 |  | 2023-05-06 | 62000
| SALARY EXPENSES | CH.NO 472458 AMOUNT PAID JAYKUMAR S.NAIDU FOR SALARY MONTH OF APRIL- 2023 |  | 2023-05-06 | 33850
| SALARY EXPENSES | CH.NO 472459 AMOUNT PAID ANIL SAVARDEKARSALARY MONTH OF APRIL- 2023 |  | 2023-05-06 | 25000
| SALARY EXPENSES | CH.NO 472460 AMOUNT PAID MAHESH GUPTA SALARY MONTH OF APRIL 2023 |  | 2023-05-06 | 40650
| SALARY EXPENSES | CH.NO 472461 AMOUNT PAID DATTA LAXMAN SARDESAI PEDNEKAR FOR SALARY MONTH OF APRIL2023 |  | 2023-05-06 | 34350
| SALARY EXPENSES | CH.NO 472462 AMOUNT PAID MOHAMMED NAZIMUDDIN FOR SALARY MONTH OF APRIL2023 |  | 2023-05-06 | 56100
| SALARY EXPENSES | CH.NO 472463 AMOUNT PAID JAYVANT VITTHAL PARKAR FOR SALARY MONTH OF APRIL2023 |  | 2023-05-06 | 33850
| SALARY EXPENSES | CH.NO 472464 AMOUNT PAID PAWAN KUMAR GHORELA FOR SALARY MONTH OF APRIL2023 |  | 2023-05-06 | 56050
| SALARY EXPENSES | CH.NO 472466 AMOUNT PAID PANKAJ PANDE FOR SALARY MONTH OF APRIL2023 |  | 2023-05-06 | 28100
| SALARY EXPENSES | CH.NO 472467 AMOUNT PAID KALYAN ARUN RANGE SALARY MONTH OF APRIL-2023 |  | 2023-05-06 | 26300
| SALARY EXPENSES | CH.NO 472468 AMOUNT PAID RAMESH H.DHAKAL SALARY MONTH OF APRIL-2023 |  | 2023-05-06 | 85850
| SALARY EXPENSES | CH.NO 472469 AMOUNT PAID NAUFIL M.NANIF SALARY MONTH OF APRIL-2023 |  | 2023-05-06 | 22500
| SALARY EXPENSES | CH.NO 472470 AMOUNT PAID MOHAMMED SAMEER GHALOT MONTH OF APRIL 2023 |  | 2023-05-06 | 45250
| SALARY EXPENSES | CH.NO 472471 AMOUNT PAID KIRAN RANBAHADUR DHAKAL SALARY MONTH OF APRIL 2023 |  | 2023-05-06 | 39250
| SALARY EXPENSES | CH.NO 472465 AMOUNT PAID RAGHVENDRA BISHWAS FOR SALARY MONTH OF APRIL2023 CH.NO 472465 IS CANCEL NEW CH.NO 471027 |  | 2023-05-15 | 44150
| SALARY EXPENSES | CH.NO 472622 AMOUNT PAID EKNATH NAMDEV KHADE FOR SALARY MONTH OF MAY-2023 |  | 2023-06-01 | 75000
| SALARY EXPENSES | CH.NO 472623 AMOUNT PAID SARUBAI EKNATH KHADE FOR SALARY MONTH OF MAY-2023 |  | 2023-06-01 | 75000
| SALARY EXPENSES | CH.NO 472624 AMOUNT PAID ABHIJEET ARJUN CHIRANKAR FOR SALARY MONTH OF MAY-2023 ( EXCESS TDS DEDUCTED NOW RECTIFIED ) |  | 2023-06-01 | 62000
| SALARY EXPENSES | CH.NO 472625 AMOUNT PAID JAYKUMAR S NAIDU FOR SALARY MONTH OF MAY-2023 |  | 2023-06-01 | 33850
| SALARY EXPENSES | CH.NO 472626 AMOUNT PAID ANIL SAVARDEKAR FOR SALARY MONTH OF MAY-2023 |  | 2023-06-01 | 25000
| SALARY EXPENSES | CH.NO 472627 AMOUNT PAID MAHESH GUPTA FOR SALARY MONTH OF MAY-2023 |  | 2023-06-01 | 40650
| SALARY EXPENSES | CH.NO 472628 AMOUNT PAID DATTA LAXMAN SARDESAI PEDNEKAR FOR SALARY MONTH OF MAY-2023 |  | 2023-06-01 | 34350
| SALARY EXPENSES | CH.NO 472629 AMOUNT PAID MOHAMMED NAZIMUDDIN FOR SALARY MONTH OF MAY-2023 |  | 2023-06-01 | 56100
| SALARY EXPENSES | CH.NO 472630 AMOUNT PAID JAYVANT VITTHAL PARKAR FOR SALARY MONTH OF MAY-2023 |  | 2023-06-01 | 33850
| SALARY EXPENSES | CH.NO 472631 AMOUNT PAID PAWAN KUMAR GHORELA FOR SALARY MONTH OF MAY-2023 |  | 2023-06-01 | 56050
| SALARY EXPENSES | CH.NO 472633 AMOUNT PAID RAGHVENDRA BISHWAS FOR SALARY MONTH OF MAY-2023 |  | 2023-06-01 | 44150
| SALARY EXPENSES | CH.NO 472634 AMOUNT PAID PANKAJ PANDEY FOR SALARY MONTH OF MAY-2023 |  | 2023-06-01 | 28100
| SALARY EXPENSES | CH.NO 472635 AMOUNT PAID KALYAN ARUN RANGE FOR SALARY MONTH OF MAY-2023 |  | 2023-06-01 | 26300
| SALARY EXPENSES | CH.NO 472636 AMOUNT PAID RAMESH H.DHAKAL FOR SALARY MONTH OF MAY-2023 |  | 2023-06-01 | 85850
| SALARY EXPENSES | CH.NO 472637 AMOUNT PAID NAUFIL M.NANIF BHURE FOR SALARY MONTH OF MAY-2023 |  | 2023-06-01 | 22500
| SALARY EXPENSES | CH.NO 472638 AMOUNT PAIDMOHAMMED SAMEER GHALOTFOR SALARY MONTH OF MAY-2023 |  | 2023-06-01 | 45250
| SALARY EXPENSES | CH.NO 472639 AMOUNT PAID KIRAN RANBAHADUR DHAKAL FOR SALARY MONTH OF MAY-2023 |  | 2023-06-01 | 39250
| SALARY EXPENSES | CH.NO 472640 AMOUNT PAID DURVA PATIL FOR SALARY MONTH OF MAY-2023 |  | 2023-06-01 | 35000
| SALARY EXPENSES | CH.NO 425995 AMOUNT PAID ABHIJEET ARJUN CHIRANKAR FOR SALARY MONTH OF JUNE-2023 |  | 2023-07-01 | 62000
| SALARY EXPENSES | CH.NO 425996 AMOUNT PAID JAYKUMAR S.NAIDU FOR SALARY MONTH OF JUNE-2023 |  | 2023-07-01 | 33850
| SALARY EXPENSES | CH.NO 425997 AMOUNT PAID ANIL SAVARDEKAR FOR SALARY MONTH OF JUNE-2023 |  | 2023-07-01 | 25000
| SALARY EXPENSES | CH.NO 425998 AMOUNT PAID MAHESH GUPTA FOR SALARY MONTH OF JUNE-2023 |  | 2023-07-01 | 40650
| SALARY EXPENSES | CH.NO 425999 AMOUNT PAID DATTA LAXMAN SARDESAI PEDNEKAR -FOR SALARY MONTH OF JUNE-2023 |  | 2023-07-01 | 34350
| SALARY EXPENSES | CH.NO 426000 AMOUNT PAID MOHAMMED NAZIMUDDIN -FOR SALARY MONTH OF JUNE-2023 |  | 2023-07-01 | 56100
| SALARY EXPENSES | CH.NO 426001 AMOUNT PAID JAYVANT VITHAL PARKAR -FOR SALARY MONTH OF JUNE-2023 |  | 2023-07-01 | 33850
| SALARY EXPENSES | CH.NO 426002 AMOUNT PAID PAWAN KUMAR GHORELA -FOR SALARY MONTH OF JUNE-2023 |  | 2023-07-01 | 56050
| SALARY EXPENSES | CH.NO 426003 AMOUNT PAID RAGHVENDRA BISHWAS -FOR SALARY MONTH OF JUNE-2023 |  | 2023-07-01 | 44150
| SALARY EXPENSES | CH.NO 426004 AMOUNT PAID PANKAJ PANDEY -FOR SALARY MONTH OF JUNE-2023 |  | 2023-07-01 | 28100
| SALARY EXPENSES | CH.NO 426005 AMOUNT PAID KALYAN ARJU RANGE -FOR SALARY MONTH OF JUNE-2023 |  | 2023-07-01 | 26300
| SALARY EXPENSES | CH.NO 426006 AMOUNT PAID RAMESH H.DHAKAL -FOR SALARY MONTH OF JUNE-2023 |  | 2023-07-01 | 85850
| SALARY EXPENSES | CH.NO 426007 AMOUNT PAID NAUFIL M.NANIF BHURE -FOR SALARY MONTH OF JUNE-2023 |  | 2023-07-01 | 22500
| SALARY EXPENSES | CH.NO 426008 AMOUNT PAID MOHAMMED SAMEER GHALOT -FOR SALARY MONTH OF JUNE-2023 |  | 2023-07-01 | 45250
| SALARY EXPENSES | CH.NO 426009 AMOUNT PAID KIRAN RANBAHADUR DHAKAL -FOR SALARY MONTH OF JUNE-2023 |  | 2023-07-01 | 39250
| SALARY EXPENSES | CH.NO 426010 AMOUNT PAID DURVA PATIL -FOR SALARY MONTH OF JUNE-2023 |  | 2023-07-01 | 35000
| SALARY EXPENSES | CH.NO 426011AMOUNT PAID YOUR SELF A/C RTGS EKNATH NAMDEV KHADE -FOR SALARY MONTH OF JUNE-2023 |  | 2023-07-01 | 75000
| SALARY EXPENSES | CH.NO 426012AMOUNT PAID YOUR SELF A/C RTGS SARUBAI EKNATH -FOR SALARY MONTH OF JUNE-2023 |  | 2023-07-01 | 75000
| SALARY EXPENSES | CH.NO 436095 AMOUNT PAID EKNATH NAMDEV KHADE FOR SALARY MONTH OF JULY-2023 |  | 2023-08-01 | 75000
| SALARY EXPENSES | CH.NO 436096 AMOUNT PAID YOUR SELF A/C RTGS SARUBAI EKNATH KHADE FOR SALARY MONTH OF JULY-2023 |  | 2023-08-01 | 75000
| SALARY EXPENSES | CH.NO 436097 AMOUNT PAID ABHIJEET ARJUN CHIRANKAR FOR SALARY MONTH OF JULY-2023 |  | 2023-08-01 | 62000
| SALARY EXPENSES | CH.NO 436098 AMOUNT PAID JAYKUMAR S.NAIDU FOR SALARY MONTH OF JULY-2023 |  | 2023-08-01 | 33850
| SALARY EXPENSES | CH.NO 436100 AMOUNT PAID MAHESH GUPTA- FOR SALARY MONTH OF JULY-2023 |  | 2023-08-01 | 40650
| SALARY EXPENSES | CH.NO 436101 AMOUNT PAID DATTA LAXMAN SARDESAI PEDNEKAR- FOR SALARY MONTH OF JULY-2023 |  | 2023-08-01 | 34350
| SALARY EXPENSES | CH.NO 436102 AMOUNT PAID MOHAMMED NAZIMUDDIN- FOR SALARY MONTH OF JULY-2023 |  | 2023-08-01 | 56100
| SALARY EXPENSES | CH.NO 436103 AMOUNT PAID JAYVANT VITTHAL PARKAR- FOR SALARY MONTH OF JULY-2023 |  | 2023-08-01 | 33850
| SALARY EXPENSES | CH.NO 436104 AMOUNT PAID PAWAN KUMAR GHORELA- FOR SALARY MONTH OF JULY-2023 |  | 2023-08-01 | 56050
| SALARY EXPENSES | CH.NO 436105 AMOUNT PAID RAGHVENDRA BISHWAS- FOR SALARY MONTH OF JULY-2023 |  | 2023-08-01 | 44150
| SALARY EXPENSES | CH.NO 436106 AMOUNT PAID PANKAJ PANDEY- FOR SALARY MONTH OF JULY-2023 |  | 2023-08-01 | 28100
| SALARY EXPENSES | CH.NO 436107 AMOUNT PAID KALYAN ARUN RANGE- FOR SALARY MONTH OF JULY-2023 |  | 2023-08-01 | 26300
| SALARY EXPENSES | CH.NO 436108 AMOUNT PAID RAMESH H.DHAKAL- FOR SALARY MONTH OF JULY-2023 |  | 2023-08-01 | 85850
| SALARY EXPENSES | CH.NO 436109 AMOUNT PAID NAUFIL M.NANIF BHURE- FOR SALARY MONTH OF JULY-2023 |  | 2023-08-01 | 22500
| SALARY EXPENSES | CH.NO 436110 AMOUNT PAID MOHAMMED SAMEER GHALOT- FOR SALARY MONTH OF JULY-2023 |  | 2023-08-01 | 45250
| SALARY EXPENSES | CH.NO 436111 AMOUNT PAID KIRAN RANBAHADUR DHAKAL- FOR SALARY MONTH OF JULY-2023 |  | 2023-08-01 | 39250
| SALARY EXPENSES | CH.NO 436112 AMOUNT PAID DURVA PATIL- FOR SALARY MONTH OF JULY-2023 |  | 2023-08-01 | 35000
| BANK CHARGES | SALES & ADMINISTRATIVE EXPENSES |  |  | 9623.98
| DONATION | SALES & ADMINISTRATIVE EXPENSES |  |  | 3037155
| GENERAL EXPENSES | SALES & ADMINISTRATIVE EXPENSES |  |  | 28650
| INTEREST ON GOVT. DUES | SALES & ADMINISTRATIVE EXPENSES |  |  | 1296
| LATE FILLING FEES | SALES & ADMINISTRATIVE EXPENSES |  |  | 200
| LOAN PROCESING FEES | SALES & ADMINISTRATIVE EXPENSES |  |  | 4321396
| OFFICE RENT | SALES & ADMINISTRATIVE EXPENSES |  |  | 415600
| PRINTING AND STATIONERY | SALES & ADMINISTRATIVE EXPENSES |  |  | 4650
| REPAIRS & MAINTANCES | SALES & ADMINISTRATIVE EXPENSES |  |  | 29179
| RERA APPLICATION FEES | SALES & ADMINISTRATIVE EXPENSES |  |  | 39892
| WELFARE EXPENSES | SALES & ADMINISTRATIVE EXPENSES |  |  | 19380
| Office Expenses | SALES & ADMINISTRATIVE EXPENSES |  |  | 460370
| Professional Fees | SALES & ADMINISTRATIVE EXPENSES |  |  | 1051725
| ADANI ELECTRICITY | ELECTRICITY EXPENSES |  | 2023-09-16 | 170290
| SECURITY CHARGES |  |  | 2023-09-09 | 36000
| STAMPDUTY & REGISTRATION - TDR | STAMP DUTY PAID FOR T.D.R. PURCHASE FROM MAFATALA IND.LTD. |  | 2023-09-23 | 100
| STAMPDUTY & REGISTRATION - TDR | STAMP DUTY PAID FOR T.D.R. PURCHASE FROM MAFATALA IND.LTD. |  | 2023-09-23 | 100
| STAMPDUTY & REGISTRATION - TDR | STAMP DUTY PAID FOR T.D.R. PURCHASE FROM MAFATALA IND.LTD. |  | 2023-09-23 | 500
| STAMPDUTY & REGISTRATION - TDR | STAMP DUTY PAID FOR T.D.R. PURCHASE FROM MAFATALA IND.LTD. |  | 2023-09-23 | 104300
| STAMPDUTY & REGISTRATION - TDR | STAMP DUTY PAID FOR T.D.R. PURCHASE FROM MAFATALA IND.LTD. |  | 2023-09-23 | 100
| STAMPDUTY & REGISTRATION - TDR | STAMP DUTY PAID FOR T.D.R. PURCHASE FROM NEW WORLD LANDMARK LLP. |  | 2023-09-23 | 100
| STAMPDUTY & REGISTRATION - TDR | STAMP DUTY PAID FOR T.D.R. PURCHASE FROM NEW WORLD LANDMARK LLP. |  | 2023-09-23 | 300
| STAMPDUTY & REGISTRATION - TDR | STAMP DUTY PAID FOR T.D.R. PURCHASE FROM NEW WORLD LANDMARK LLP. |  | 2023-09-23 | 23700
| SALARY EXPENSES | CH.NO 436179 AMOUNT PAID EKNATH NAMDEV KHADE FOR SALARY MONTH OF AUG 2023 |  | 2023-09-01 | 75000
| SALARY EXPENSES | CH.NO 436180 AMOUNT PAID YOUR SELF A/C RTGS SARUBAI EKNATH KHADE FOR SALARY MONTH OF AUG 2023 |  | 2023-09-01 | 75000
| SALARY EXPENSES | CH.NO 436181 AMOUNT PAID ABHIJEET ARJUN CHIRANKAR FOR SALARY MONTH OF AUG 2023 |  | 2023-09-01 | 62000
| SALARY EXPENSES | CH.NO 436182 AMOUNT PAID JAYKUMAR S.NAIDU FOR SALARY MONTH OF AUG 2023 |  | 2023-09-01 | 33850
| SALARY EXPENSES | CH.NO 436183 AMOUNT PAID MAHESH GUPTA- FOR SALARY MONTH OF AUG 2023 |  | 2023-09-01 | 40650
| SALARY EXPENSES | CH.NO 436184 AMOUNT PAID DATTA LAXMAN SARDESAI PEDNEKAR- FOR SALARY MONTH OF AUG 2023 |  | 2023-09-01 | 34350
| SALARY EXPENSES | CH.NO 436185 AMOUNT PAID MOHAMMED NAZIMUDDIN- FOR SALARY MONTH OF AUG 2023 |  | 2023-09-01 | 56100
| SALARY EXPENSES | CH.NO 436186 AMOUNT PAID JAYVANT VITTHAL PARKAR- FOR SALARY MONTH OF AUG 2023 |  | 2023-09-01 | 33850
| SALARY EXPENSES | CH.NO 436187 AMOUNT PAID PAWAN KUMAR GHORELA- FOR SALARY MONTH OF AUG 2023 |  | 2023-09-01 | 56050
| SALARY EXPENSES | CH.NO 436188 AMOUNT PAID RAGHVENDRA BISHWAS- FOR SALARY MONTH OF AUG 2023 |  | 2023-09-01 | 44150
| SALARY EXPENSES | CH.NO 436189 AMOUNT PAID PANKAJ PANDEY- FOR SALARY MONTH OF AUG 2023 |  | 2023-09-01 | 28100
| SALARY EXPENSES | CH.NO 436190 AMOUNT PAID KALYAN ARUN RANGE- FOR SALARY MONTH OF AUG 2023 |  | 2023-09-01 | 26300
| SALARY EXPENSES | CH.NO 436191 AMOUNT PAID RAMESH H.DHAKAL- FOR SALARY MONTH OF AUG 2023 |  | 2023-09-01 | 85850
| SALARY EXPENSES | CH.NO 436192 AMOUNT PAID NAUFIL M.NANIF BHURE- FOR SALARY MONTH OF AUG 2023 |  | 2023-09-01 | 22500
| SALARY EXPENSES | CH.NO 436193 AMOUNT PAID MOHAMMED SAMEER GHALOT- FOR SALARY MONTH OF AUG 2023 |  | 2023-09-01 | 45250
| SALARY EXPENSES | CH.NO 436194 AMOUNT PAID KIRAN RANBAHADUR DHAKAL- FOR SALARY MONTH OF AUG 2023 |  | 2023-09-01 | 39250
| SALARY EXPENSES | CH.NO 436195 AMOUNT PAID DURVA PATIL- FOR SALARY MONTH OF AUG 2023 |  | 2023-09-01 | 35000
| SALES & ADMINISTRATIVE EXPENSE | BANK CHARGES |  |  | 702.1
| SALES & ADMINISTRATIVE EXPENSE | DONATIONS |  |  | 291000
| SALES & ADMINISTRATIVE EXPENSE | OFFICE RENT |  |  | 5000
| SALES & ADMINISTRATIVE EXPENSE | WELFARE EXPENSES |  |  | 7130
| INSURANCE |  |  | 2023-09-23 | 805647
| ADANI ELECTRICITY | ELECTRICITY EXPENSES |  | 2023-10-23 | 175390
| ADANI ELECTRICITY | ELECTRICITY EXPENSES |  | 2023-11-21 | 194060
| ADANI ELECTRICITY | ELECTRICITY EXPENSES |  | 2023-12-06 | 182010
| SALARY EXPENSES |  |  | 2023-10-03 | 75000
| SALARY EXPENSES |  |  | 2023-10-03 | 75000
| SALARY EXPENSES |  |  | 2023-10-03 | 62000
| SALARY EXPENSES |  |  | 2023-10-03 | 33850
| SALARY EXPENSES |  |  | 2023-10-03 | 40650
| SALARY EXPENSES |  |  | 2023-10-03 | 34350
| SALARY EXPENSES |  |  | 2023-10-03 | 56100
| SALARY EXPENSES |  |  | 2023-10-03 | 33850
| SALARY EXPENSES |  |  | 2023-10-03 | 56050
| SALARY EXPENSES |  |  | 2023-10-03 | 44150
| SALARY EXPENSES |  |  | 2023-10-03 | 28100
| SALARY EXPENSES |  |  | 2023-10-03 | 26300
| SALARY EXPENSES |  |  | 2023-10-03 | 85850
| SALARY EXPENSES |  |  | 2023-10-03 | 22500
| SALARY EXPENSES |  |  | 2023-10-03 | 45250
| SALARY EXPENSES |  |  | 2023-10-03 | 39250
| SALARY EXPENSES |  |  | 2023-10-03 | 35000
| SALARY EXPENSES |  |  | 2023-11-01 | 75000
| SALARY EXPENSES |  |  | 2023-11-01 | 75000
| SALARY EXPENSES |  |  | 2023-11-01 | 62000
| SALARY EXPENSES |  |  | 2023-11-01 | 33850
| SALARY EXPENSES |  |  | 2023-11-01 | 40650
| SALARY EXPENSES |  |  | 2023-11-01 | 34350
| SALARY EXPENSES |  |  | 2023-11-01 | 56100
| SALARY EXPENSES |  |  | 2023-11-01 | 33850
| SALARY EXPENSES |  |  | 2023-11-01 | 56050
| SALARY EXPENSES |  |  | 2023-11-01 | 44150
| SALARY EXPENSES |  |  | 2023-11-01 | 28100
| SALARY EXPENSES |  |  | 2023-11-01 | 26300
| SALARY EXPENSES |  |  | 2023-11-01 | 85850
| SALARY EXPENSES |  |  | 2023-11-01 | 22500
| SALARY EXPENSES |  |  | 2023-11-01 | 45250
| SALARY EXPENSES |  |  | 2023-11-01 | 39250
| SALARY EXPENSES |  |  | 2023-11-01 | 35000
| SALARY EXPENSES |  |  | 2023-12-01 | 62000
| SALARY EXPENSES |  |  | 2023-12-01 | 22500
| SALARY EXPENSES |  |  | 2023-12-01 | 39250
| SALARY EXPENSES |  |  | 2023-12-01 | 75000
| SALARY EXPENSES |  |  | 2023-12-01 | 75000
| SALARY EXPENSES |  |  | 2023-12-01 | 33850
| SALARY EXPENSES |  |  | 2023-12-01 | 34350
| SALARY EXPENSES |  |  | 2023-12-01 | 56100
| SALARY EXPENSES |  |  | 2023-12-01 | 33850
| SALARY EXPENSES |  |  | 2023-12-01 | 56050
| SALARY EXPENSES |  |  | 2023-12-01 | 44150
| SALARY EXPENSES |  |  | 2023-12-01 | 28100
| SALARY EXPENSES |  |  | 2023-12-01 | 85850
| SALARY EXPENSES |  |  | 2023-12-01 | 45250
| SALARY EXPENSES |  |  | 2023-12-01 | 35000
| SALARY EXPENSES |  |  | 2023-12-01 | 26300
| BANK CHARGES |  |  |  | 5689.44
| DONATIONS |  |  |  | 138008
| INTEREST & LATE FEES ON STATUTORY DUES |  |  |  | 28466
| LATE FILLING FEES |  |  |  | 500
| OFFICE RENT |  |  |  | 5000
| SUNDRY BALANCES W/OFF (NET) |  |  |  | 17.3
| WELFARE EXPENSES |  |  |  | 3810
| K.L.PATHAK | SECURITY CHARGES |  | 2023-10-10 | 36000
| K.L.PATHAK | SECURITY CHARGES |  | 2023-11-01 | 36000
| K.L.PATHAK | SECURITY CHARGES |  | 2023-12-07 | 36000
| BANK CHARGES | SALES & ADMINISTRATIVE EXPENSE |  |  | 2653.21
| CGST FEES | SALES & ADMINISTRATIVE EXPENSE |  |  | 375
| DONATIONS | SALES & ADMINISTRATIVE EXPENSE |  |  | 157000
| GENERAL EXPENSES | SALES & ADMINISTRATIVE EXPENSE |  |  | 3400
| Interest on Govt.Dues | SALES & ADMINISTRATIVE EXPENSE |  |  | 8932
| OFFICE RENT | SALES & ADMINISTRATIVE EXPENSE |  |  | 15000
| PRINTING & STATIONERY EXPENSES-18% | SALES & ADMINISTRATIVE EXPENSE |  |  | 6300
| SGST FEES | SALES & ADMINISTRATIVE EXPENSE |  |  | 375
| WELFARE EXPENSES | SALES & ADMINISTRATIVE EXPENSE |  |  | 15630
| SALARY EXPENSES |  |  | 2024-03-20 | 150000
| SALARY EXPENSES |  |  | 2024-01-01 | 75000
| SALARY EXPENSES |  |  | 2024-01-01 | 75000
| SALARY EXPENSES |  |  | 2024-01-01 | 33850
| SALARY EXPENSES |  |  | 2024-01-01 | 40650
| SALARY EXPENSES |  |  | 2024-01-01 | 34350
| SALARY EXPENSES |  |  | 2024-01-01 | 56100
| SALARY EXPENSES |  |  | 2024-01-01 | 33850
| SALARY EXPENSES |  |  | 2024-01-01 | 56050
| SALARY EXPENSES |  |  | 2024-01-01 | 44150
| SALARY EXPENSES |  |  | 2024-01-01 | 28100
| SALARY EXPENSES |  |  | 2024-01-01 | 26300
| SALARY EXPENSES |  |  | 2024-01-01 | 85850
| SALARY EXPENSES |  |  | 2024-01-01 | 45250
| SALARY EXPENSES |  |  | 2024-01-01 | 39250
| SALARY EXPENSES |  |  | 2024-01-01 | 35000
| SALARY EXPENSES |  |  | 2024-01-01 | 62000
| SALARY EXPENSES |  |  | 2024-01-01 | 22500
| SALARY EXPENSES |  |  | 2024-01-31 | 81300
| SALARY EXPENSES |  |  | 2024-02-01 | 62000
| SALARY EXPENSES |  |  | 2024-02-01 | 22500
| SALARY EXPENSES |  |  | 2024-02-01 | 75000
| SALARY EXPENSES |  |  | 2024-02-01 | 75000
| SALARY EXPENSES |  |  | 2024-02-01 | 33850
| SALARY EXPENSES |  |  | 2024-02-01 | 34350
| SALARY EXPENSES |  |  | 2024-02-01 | 56100
| SALARY EXPENSES |  |  | 2024-02-01 | 33850
| SALARY EXPENSES |  |  | 2024-02-01 | 56050
| SALARY EXPENSES |  |  | 2024-02-01 | 44150
| SALARY EXPENSES |  |  | 2024-02-01 | 28100
| SALARY EXPENSES |  |  | 2024-02-01 | 26300
| SALARY EXPENSES |  |  | 2024-02-01 | 85850
| SALARY EXPENSES |  |  | 2024-02-01 | 45250
| SALARY EXPENSES |  |  | 2024-02-01 | 39250
| SALARY EXPENSES |  |  | 2024-02-01 | 35000
| SALARY EXPENSES |  |  | 2024-03-01 | 62000
| SALARY EXPENSES |  |  | 2024-03-01 | 22500
| SALARY EXPENSES |  |  | 2024-03-01 | 75000
| SALARY EXPENSES |  |  | 2024-03-01 | 75000
| SALARY EXPENSES |  |  | 2024-03-01 | 34350
| SALARY EXPENSES |  |  | 2024-03-01 | 56100
| SALARY EXPENSES |  |  | 2024-03-01 | 28100
| SALARY EXPENSES |  |  | 2024-03-01 | 85850
| SALARY EXPENSES |  |  | 2024-03-01 | 45250
| SALARY EXPENSES |  |  | 2024-03-01 | 35000
| SALARY EXPENSES |  |  | 2024-03-30 | 62000
| SALARY EXPENSES |  |  | 2024-03-30 | 22500
| SALARY EXPENSES |  |  | 2024-03-30 | 75000
| SALARY EXPENSES |  |  | 2024-03-30 | 75000
| SALARY EXPENSES |  |  | 2024-03-30 | 34350
| SALARY EXPENSES |  |  | 2024-03-30 | 56100
| SALARY EXPENSES |  |  | 2024-03-30 | 28100
| SALARY EXPENSES |  |  | 2024-03-30 | 85850
| SALARY EXPENSES |  |  | 2024-03-30 | 45250
| SALARY EXPENSES |  |  | 2024-03-30 | 35000
| SECURITY CHARGES |  |  | 2024-01-08 | 36000
| SECURITY CHARGES |  |  | 2024-02-14 | 36000
| SECURITY CHARGES |  |  | 2024-03-12 | 36000
| OFFICE EXPENSES SITE |  |  | 2024-03-06 | 120000
| INSURANCE |  |  | 2024-01-04 | 20390
| ELECTRICITY EXPENSES - KONSHILA |  |  | 2024-01-08 | 209060
| ELECTRICITY EXPENSES - KONSHILA |  |  | 2024-02-13 | 187550
| ELECTRICITY EXPENSES - KONSHILA |  |  | 2024-03-11 | 205920
| STAFF WELFARE EXPENSES | CH NO-890701 BILL NO-03 UMBRELLA PURCHASED |  | 2024-06-13 | 366500
| SALARY EXPENSES | CH NO-890670 ABHIJEET ARJUN CHIRANKAR SALARY PAID FOR THE MONTH OF APRIL 2024 |  | 2024-05-04 | 70500
| SALARY EXPENSES | CH NO-890670 NAUFIL M NANIF BHURE SALARY PAID FOR THE MONTH OF APRIL 2024 |  | 2024-05-04 | 27000
| SALARY EXPENSES | CH.NO 890670 DURVA PATIL AMOUNT PAID DURVA PATIL- FOR SALARY MONTH OF APRIL 2024 |  | 2024-05-04 | 41000
| SALARY EXPENSES | CH NO- 890669 EKNATH NAMDEV KHADE SALARY PAID FOR THE MONTH OF APRIL 2024 |  | 2024-05-04 | 75000
| SALARY EXPENSES | CH NO- 890669 SARUBHAI EKNATH KHADE SALARY PAID FOR THE MONTH OF APRIL 2024 |  | 2024-05-04 | 75000
| SALARY EXPENSES | CH NO- 890669 DATTA LAXMAN SARDESAI PEDNEKAR SALARY PAID FOR THE MONTH OFAPRIL 2024 |  | 2024-05-04 | 36000
| SALARY EXPENSES | CH NO- 890669 MOHAMMED NAZIMUDDIN SALARY PAID FOR THE MONTH OF APRIL 2024 |  | 2024-05-04 | 65000
| SALARY EXPENSES | CH NO- 890669 PANKAJ PANDEY SALARY PAID FOR THE MONTH OF APRIL 2024 |  | 2024-05-04 | 30250
| SALARY EXPENSES | CH NO- 890669 RAMESH H DHAKAL SALARY PAID FOR THE MONTH OF APRIL 2024 |  | 2024-05-04 | 94000
| SALARY EXPENSES | CH NO- 890669 MOHAMMED SAMEER GHALOT SALARY PAID FOR THE MONTH OF APRIL 2024 |  | 2024-05-04 | 54000
| SALARY EXPENSES | CH NO-890686 ABHIJEET ARJUN CHIRANKAR SALARY PAID FOR THE MONTH OF MAY 2024 |  | 2024-06-06 | 70500
| SALARY EXPENSES | CH NO-890686 NAUFIL M NANIF BHURE SALARY PAID FOR THE MONTH OF MAY 2024 |  | 2024-06-06 | 27000
| SALARY EXPENSES | CH.NO 890686 DURVA PATIL AMOUNT PAID DURVA PATIL- FOR SALARY MONTH OF MAY 2024 |  | 2024-06-06 | 41000
| SALARY EXPENSES | CH NO- 890687 EKNATH NAMDEV KHADE SALARY PAID FOR THE MONTH OF MAY 2024 |  | 2024-06-06 | 75000
| SALARY EXPENSES | CH NO- 890687 SARUBHAI EKNATH KHADE SALARY PAID FOR THE MONTH OF MAY 2024 |  | 2024-06-06 | 75000
| SALARY EXPENSES | CH NO- 890687 DATTA LAXMAN SARDESAI PEDNEKAR SALARY PAID FOR THE MONTH OF MAY 2024 |  | 2024-06-06 | 36000
| SALARY EXPENSES | CH NO- 890687 MOHAMMED NAZIMUDDIN SALARY PAID FOR THE MONTH OF MAY 2024 |  | 2024-06-06 | 65000
| SALARY EXPENSES | CH NO- 890687 PANKAJ PANDEY SALARY PAID FOR THE MONTH OF MAY 2024 |  | 2024-06-06 | 30250
| SALARY EXPENSES | CH NO- 890687 RAMESH H DHAKAL SALARY PAID FOR THE MONTH OF MAY 2024 |  | 2024-06-06 | 94000
| SALARY EXPENSES | CH NO- 890687 MOHAMMED SAMEER GHALOT SALARY PAID FOR THE MONTH OF MAY 2024 |  | 2024-06-06 | 54000
| Property Tax | CH.NO. 890672 PAID TO BMC AG BILL NO. KE2800372410000 PROPERTY TAX FOR THE PERIOD 01.04.2023 TO 31.03.2024 |  | 2024-05-20 | 2538334
| ELECTRICITY EXPENSES - KONSHILA | CH NO 890674 AMOUNT PAID ADANI ELECTRICITY MUMBAI LTD A/C NO 153186207 MONTH OF APRIL 2024 |  | 2024-05-09 | 227130
| ELECTRICITY EXPENSES - KONSHILA | CH NO 890697 AMOUNT PAID ADANI ELECTRICITY MUMBAI LTD A/C NO 153186207 MONTH OF MAY 2024 |  | 2024-06-21 | 263250
| SECURITY CHARGES | CH NO-890666 BILL NO-KLP/24/011 |  | 2024-05-03 | 36000
| BANK CHARGES | SALES & ADMINISTRATIVE EXPENSE |  |  | 6744.88
| CGST FEES | SALES & ADMINISTRATIVE EXPENSE |  |  | 300
| DONATIONS | SALES & ADMINISTRATIVE EXPENSE |  |  | 68000
| Interest on Govt.Dues | SALES & ADMINISTRATIVE EXPENSE |  |  | 5916
| OFFICE RENT | SALES & ADMINISTRATIVE EXPENSE |  |  | 15000
| PRINTING & STATIONERY EXPENSES-18% | SALES & ADMINISTRATIVE EXPENSE |  |  | 1250
| SGST FEES | SALES & ADMINISTRATIVE EXPENSE |  |  | 300
| SUNDRY BALANCES W/OFF (NET) | SALES & ADMINISTRATIVE EXPENSE |  |  | 4.94
| WELFARE EXPENSES | SALES & ADMINISTRATIVE EXPENSE |  |  | 16420
TOTAL |  |  |  |  | 37861391.85

## Interest
Sr. No. | Month | Interest Amount
1 | 2023-09-01 | 726001
2 | 2023-10-01 | 1078554
3 | 2023-11-01 | 1376554
4 | 2023-12-01 | 1443033
5 | 2024-01-01 | 1647636
6 | 2024-02-01 | 1615172
7 | 2024-03-01 | 1884830
8 | 2024-04-01 | 1853096
9 | 2024-05-01 | 2155671
10 | 2024-06-01 | 2085318
15865865

## Construction Area Statement
REHAB BUILDING
Sr. No. | Floor | Total Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | % of work completed | Actual Expenditure till date in ` | Sr. No. | Building | Total Construction Area in Sq. M. | Full Value after completion | % of work completed | Actual Expenditure till date in `
| Exacavation & Piling Work | 5% of Construction cost of building |  |  | 14424730 | 100% | 14424730 | 1 | Rehab Building No. 1 | 14424.73 | 302919330 | 77.42% | 234535260
1 | Ground | 627.92 | 627.92 | 20000 | 12558400 | 50% | 6279200 | 2 | Sale Building | 27417.852 | 814310204 | 57.54% | 468550821.38
2 | 1st | 627.92 | 627.92 | 20000 | 12558400 | 86% | 10800224 |  | Sub Total (A) | 41842.582 | 1117229534 | 62.93% | 703086081.38
3 | 2nd | 627.92 | 627.92 | 20000 | 12558400 | 86% | 10800224 | 3 | Puzzle Parking of Rehab Building in No. | 27 | 6750000 | 0% | 0
4 | 3rd | 584.55 | 584.55 | 20000 | 11691000 | 86% | 10054260 | 4 | Puzzle Parking of Sale Building in No. | 48 | 39000000 | 0% | 0
5 | 4th | 584.55 | 584.55 | 20000 | 11691000 | 86% | 10054260 |  | Sub Total (B) | 75 | 45750000 | 0% | 0
6 | 5th | 584.55 | 584.55 | 20000 | 11691000 | 86% | 10054260 | Total Cost of Construction (A + B) |  |  | 1162979534 | 60.46% | 703086081.38
7 | 6th | 584.55 | 584.55 | 20000 | 11691000 | 86% | 10054260
8 | 7th | 584.55 | 584.55 | 20000 | 11691000 | 86% | 10054260
9 | 8th | 584.66 | 584.66 | 20000 | 11693200 | 86% | 10056152
10 | 9th | 584.55 | 584.55 | 20000 | 11691000 | 86% | 10054260
11 | 10th | 584.55 | 584.55 | 20000 | 11691000 | 86% | 10054260
12 | 11th | 584.55 | 584.55 | 20000 | 11691000 | 86% | 10054260
13 | 12th | 584.55 | 584.55 | 20000 | 11691000 | 86% | 10054260
14 | 13th | 584.55 | 584.55 | 20000 | 11691000 | 70% | 8183700
15 | 14th | 584.55 | 584.55 | 20000 | 11691000 | 72% | 8417520
16 | 15th | 585.3 | 585.3 | 20000 | 11706000 | 72% | 8428320
17 | 16th | 584.55 | 584.55 | 20000 | 11691000 | 72% | 8417520
18 | 17th | 584.55 | 584.55 | 20000 | 11691000 | 72% | 8417520
19 | 18th | 584.55 | 584.55 | 20000 | 11691000 | 72% | 8417520
20 | 19th | 584.55 | 584.55 | 20000 | 11691000 | 72% | 8417520
21 | 20th | 584.55 | 584.55 | 20000 | 11691000 | 70% | 8183700
22 | 21st | 584.55 | 584.55 | 20000 | 11691000 | 70% | 8183700
23 | 22nd | 584.55 | 584.55 | 20000 | 11691000 | 50% | 5845500
24 | 23rd | 584.55 | 584.55 | 20000 | 11691000 | 65% | 7599150
25 | OHT / LMR | 264.56 | 264.56 | 20000 | 5291200 | 60% | 3174720
Total Area in Sq. M. |  | 14424.73 | 14424.73 |  | 302919330 | 77.42% | 234535260
STACK PARKING Nos. |  | 27 |  | 250000 | 6750000
TOTAL COST OF CONSTRUCTION (A + B) |  |  |  |  | 309669330 | 75.74% | 234535260
SALE BUILDING
Sr. No. | Floor | Total Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | % of work completed | Actual Expenditure till date in `
| Exacavation & Piling Work | 5% of Construction cost of building |  |  | 74028200 | 100% | 74028200
1 | Ground | 1138.598 | 1138.598 | 27000 | 30742146 | 50% | 15371073
2 | 1st | 1138.598 | 1138.598 | 27000 | 30742146 | 75% | 23056609.5
3 | 2nd | 1138.598 | 1138.598 | 27000 | 30742146 | 75% | 23056609.5
4 | 3rd | 1131.028 | 1131.028 | 27000 | 30537756 | 75% | 22903317
5 | 4th | 1126.918 | 1126.918 | 27000 | 30426786 | 75% | 22820089.5
6 | 5th | 1126.918 | 1126.918 | 27000 | 30426786 | 75% | 22820089.5
7 | 6th | 1126.918 | 1126.918 | 27000 | 30426786 | 75% | 22820089.5
8 | 7th | 1126.918 | 1126.918 | 27000 | 30426786 | 75% | 22820089.5
9 | 8th | 1139.098 | 1139.098 | 27000 | 30755646 | 75% | 23066734.5
10 | 9th | 1126.918 | 1126.918 | 27000 | 30426786 | 75% | 22820089.5
11 | 10th | 1126.918 | 1126.918 | 27000 | 30426786 | 75% | 22820089.5
12 | 11th | 1126.918 | 1126.918 | 27000 | 30426786 | 55% | 16734732.3
13 | 12th | 1126.918 | 1126.918 | 27000 | 30426786 | 55% | 16734732.3
14 | 13th | 1126.918 | 1126.918 | 27000 | 30426786 | 55% | 16734732.3
15 | 14th | 1126.918 | 1126.918 | 27000 | 30426786 | 55% | 16734732.3
16 | 15th | 1129.808 | 1129.808 | 27000 | 30504816 | 53% | 16167552.48
17 | 16th | 1126.918 | 1126.918 | 27000 | 30426786 | 45% | 13692053.7
18 | 17th | 1126.918 | 563.459 | 27000 | 30426786 | 25% | 7606696.5
19 | 18th | 1126.918 | 563.459 | 27000 | 30426786 | 25% | 7606696.5
20 | 19th | 1126.918 | 563.459 | 27000 | 30426786 | 25% | 7606696.5
21 | 20th | 1126.918 | 563.459 | 27000 | 30426786 | 25% | 7606696.5
22 | 21st | 1126.918 | 563.459 | 27000 | 30426786 | 25% | 7606696.5
23 | 22nd | 1134.508 | 567.254 | 27000 | 30631716 | 25% | 7657929
24 | 23rd | 1134.488 | 567.244 | 27000 | 30631176 | 25% | 7657794
25 | OHT / LMR | 302.44 |  | 27000 | 8165880 |  | 0
Total Area in Sq. M. |  | 27417.852 | 23163.619 |  | 814310204 | 57.54% | 468550821.38
STACK PARKING Nos. |  | 78 |  | 500000 | 39000000
TOTAL COST OF CONSTRUCTION (A + B) |  |  |  |  | 853310204 | 54.91% | 468550821.38