## Final Summary
Project expenses | Estimated Cost as per Cost Vetting | Incurred Cost as per Bill till 30.06.2024 | Incurred Cost as per CA till 30.06.2024 | Incurred Cost as per Bill till 31.03.2024 | Incurred Cost as per CA till 31.03.2024 | Difference between the Bills & CA | Difference between both the Bills | Difference between both CA | Remark
Land Cost | 36.8 | 36.7957 | 36.8 | 36.7957 | 36.8 | -0.00431 | 0 | 0
Rent Cost | 3.85 | 5.2959 | 5.15 | 2.4949 | 2.35 | 0.14589 | 2.801 | 2.8
Construction Cost of Rehab & Amenity Building | 48.5 | 32.6774 | 34.57 | 28.1644 | 29.49 | -1.8926 | 4.513 | 5.08
Construction Cost of Sale Building | 117.27
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 32.43 | 25.7685 | 26.26 | 21.6455 | 21.74 | -0.49152 | 4.123 | 4.52
Architect Cost, RCC & other Professional fees | 8.29 | 2.686 | 2.63 | 2.6561 | 2.61 | 0.055961 | 0.029868 | 0.02
Administrative Expenses | 6.63 | 4.1539 | 8.89 | 3.6082 | 6.77 | 3.5066 | 0.54573 | 2.12
Marketing Expences | 16.77 | 8.2427 |  | 6.2171 |  |  | 2.0256
Interest Cost | 50 | 2.3281 | 2.33 | 1.442 | 1.44 | -0.0019433 | 0.88601 | 0.89
Contingency Cost | 4.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost | 325.51 | 117.9481 | 116.63 | 103.0239 | 101.2 | 1.3181 | 14.9242 | 15.43
|  | 207.5619 | 1.3181 |  | 1.8239
Particulars | Revised Estimated Cost (in Cr.) | 30.06.2024 as per Bill Tally (inclusive of GST) | Cost incurred as %age total cost of that Component | Cost incurred as %age of cost incurred as on 30.06.2024
Land Cost | 36.8 | 36.7957 | 99.99% | 11.3%
Rent Cost | 3.85 | 5.2959 | 137.6% | 1.627%
Construction Cost of Rehab & Amenity Building | 48.5 | 32.6774 | 19.71% | 10.04%
Construction Cost of Sale Building | 117.27
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 32.43 | 25.7685 | 79.46% | 7.916%
Architect Cost, RCC & other Professional fees | 8.29 | 2.686 | 32.4% | 0.8252%
Administrative Expenses | 6.63 | 4.1539 | 62.65% | 1.276%
Marketing Expences | 16.77 | 8.2427 | 49.15% | 2.532%
Interest Cost | 50 | 2.3281 | 4.656% | 0.7152%
Contingency Cost | 4.97 | 0 | 0% | 0%
Total | 325.51 | 117.9481 | 36.23% | 36.23%
Pariculars | 30.06.2024 as per Bill Tally (inclusive of GST) | 31.03.2024 as per Bill Tally (inclusive of GST) | Difference b/w bills of 31.03.2024 & 30.06.2024 | Difference of Cost incurred as %age of cost incurred as on 31.03.2024 & 30.06.2024
Land Cost | 36.7957 | 36.7957 | 0 | 0%
Rent Cost | 5.2959 | 2.4949 | 2.8 | 2.374%
Construction Cost of Rehab & Amenity Building | 32.6774 | 28.1644 | 4.51 | 3.824%
Construction Cost of Sale Building
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 25.7685 | 21.6455 | 4.12 | 3.493%
Architect Cost, RCC & other Professional fees | 2.686 | 2.6561 | 0.03 | 0.02543%
Administrative Expenses | 4.1539 | 3.6082 | 0.55 | 0.4663%
Marketing Expences | 8.2427 | 6.2171 | 2.03 | 1.721%
Interest Cost | 2.3281 | 1.442 | 0.89 | 0.7546%
Contingency Cost | 0 | 0 | 0 | 0%
Total | 117.9481 | 103.0239 | 14.92 | 12.65%

## Summary Sheet
Sr. No. | Particulars | Incurred Cost in ` till 30.06.2024 | Incurred Cost in ` Cr. Till 30.06.2024 | Incurred Cost in ` till 31.03.2024 | Incurred Cost in ` Cr. Till 31.03.2024 | Balance | Balance in Cr.
1 | Land Cost | 367956900 | 36.7957 | 367956900 | 36.7957 | 0 | 0
2 | Rent Cost | 52958946 | 5.2959 | 24949000 | 2.4949 | 28009946 | 2.801
3 | Construction Cost of Rehab & Amenity Building | 326774057 | 32.6774 | 281643876 | 28.1644 | 45130181 | 4.513
4 | Construction Cost of Sale Building
5 | Approval Cost & Stamp Duty | 257684850 | 25.7685 | 216454888 | 21.6455 | 41229962 | 4.123
6 | Professional Cost | 26859615 | 2.686 | 26560935 | 2.6561 | 298680 | 0.029868
7 | Admin Cost | 41539260.4 | 4.1539 | 36081954.48 | 3.6082 | 5457305.92 | 0.54573
8 | Marketing Cost | 82426974 | 8.2427 | 62171450 | 6.2171 | 20255524 | 2.0256
9 | Interest Cost | 23280567 | 2.3281 | 14420469 | 1.442 | 8860098 | 0.88601
| Total | 1179481169.4 | 117.9481 | 1030239472.48 | 103.0239 | 149241696.92 | 14.9242
500000000
476719433

## Land, Stamp Duty and rent c (2)
Stamp Duty & Registration Fees
Sr. No. | Agreement Name | Date | Particulars | Amount | Incurred Amount
1 | Conveyance Deed | 21.12.2018 | Purchase Cost | 350400000 | 350400000
2 |  |  | Stamp Duty | 17520000 | 17520000 | Sr. No. | Particulars
3 |  |  | Reg. Fees | 30000 | 30000 | 1 | No. of Tenants | 58 | Nos
4 |  |  |  | 1900 | 1900 | 2 | No. of Half Loft Tenant | 38 | Nos
5 | Confirmation Deed | 03.04.2019 | Stamp Duty | 500 | 500 | 3 | No. of Full Loft Tenant | 6 | Nos
6 |  |  | Reg. Fees | 1900 | 1900 | 4 | Rent Per Month (Jan 22 to Dec 22) Per Tenant | 16000 | Rupees
7 |  |  |  | 100 | 100 | 5 | Rent per Year (Jan to Dec 22) | 11136000 | Rupees
5 | Rectification Deed | 22.06.2019 | Stamp Duty | 500 | 500 | 6 | Rent per Month (Jan 23 to Dec 23) | 17000 | Rupees
6 |  |  | Reg. Fees | 1900 | 1900 | 7 | Rent per Year (Jan to Dec 23) | 11832000 | Rupees
7 |  |  |  | 100 | 100 | 8 | Rent per Month (Jan 24 to Jun 24) | 18000 | Rupees
| TOTAL |  |  | 367956900 | 367956900 | 9 | Rent per Year (Jan to Jun 24) | 12528000 | Rupees
[6 empty] | 10 | Rent for Full Loft per Tenant | 60000 | Rupees
[6 empty] | 11 | Rent for Full Loft | 360000 | Rupees
[6 empty] | 12 | Rent for Half Loft per tenant | 15000 | Rupees
[6 empty] | 13 | Rent for Half Loft | 570000 | Rupees
[6 empty] | 14 | Shifting Cost per Tenant | 20000 | Rupees
[6 empty] | 15 | Shifting Cost | 1160000 | Rupees
[6 empty] | 16 | Brokerage Cost | 928000 | Rupees
[6 empty] | 17 | TOTAL RENT COST | 38514000 | Rupees

## Rent Cost
|  |  | TOTAL | Till July 2023 | 2023-08-01 | 2023-09-01 | Oct - Dec 23 | Jan - Mar 24 | April - May 24 | 2024-06-01
1 | ANANDI SHANTARAM GAWADE | COMPENSATION | 925000 | 322000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
2 | Anant Shivram Surve | COMPENSATION | 865000 | 262000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
3 | Ankush Shivram Parab | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
4 | Ashadevi Sudama Prasad Mourya | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
5 | Ashok Sakharam Mulik | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
6 | Awadhraj Majadhar Pal | COMPENSATION | 925000 | 322000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
7 | Babbuprasad Amrutlal Gupta | COMPENSATION | 1140000 | 243000 | 17000 | 328000 | 34000 | 51000 | 53000 | 414000
8 | Babulal Jagnarayan Pal | COMPENSATION | 892921 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 426921
9 | Balaram Dagdu Pawar | COMPENSATION | 865000 | 262000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
10 | Bansh Bahadur Dayaram Singh | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
11 | Bhanupratap Ramnaresh Mishra | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
12 | Brahmacharya Dayashankar Shukla | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
13 | Chotelal Tapashi Goud | COMPENSATION | 771000 | 277000 | 17000 | 34000 | 34000 | 97000 | 36000 | 276000
14 | Dattaram Harischandra Dicholkar | COMPENSATION | 880075 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414075
15 | Dhondu Sahdev Katkar | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
16 | DILIP MANOHAR PISE | COMPENSATION | 865000 | 262000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
17 | Dinanath Chandan Prasad Dubey | COMPENSATION | 846000 | 243000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
18 | Doodhnath Awadhnarayan Singh | COMPENSATION | 451028 | 262000 | 17000 | 34000 | 34000 | 51000 | 53000 | 28
19 | Fayaram Baliraj Yadav | COMPENSATION | 928030 | 322000 | 17000 | 34000 | 34000 | 51000 | 53000 | 417030
20 | Ganpat Vishnu Sonar | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
21 | Hargovind Lalbahadur Singh | COMPENSATION | 846000 | 243000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
22 | Harinath Chandanprasad Dubey | COMPENSATION | 511002 | 322000 | 17000 | 34000 | 34000 | 51000 | 53000 | 2
23 | Jahraji Devi Yadav | COMPENSATION | 865000 | 262000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
24 | Kashiram Tukaram Dhumal | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
25 | Kewala Prasad Mishra | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
26 | Manojkumar Awadhraj Pal | COMPENSATION | 925000 | 322000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
27 | Matru Jangee Yadav | COMPENSATION | 930945 | 322000 | 17000 | 34000 | 34000 | 51000 | 53000 | 419945
28 | Mukesh Ganpat Sonar | COMPENSATION | 865000 | 262000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
29 | MURARI FAYARAM YADAV | COMPENSATION | 928129.62 | 322000 | 17000 | 34000 | 34000 | 51000 | 53000 | 417129.62
30 | Parvati Shilajeet Thakur | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
31 | Pawan Kumar Ojha | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
32 | Phulavatidevi | COMPENSATION | 846000 | 243000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
33 | Pradeep Manohar Pise | COMPENSATION | 1271000 | 668000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
34 | Pragati Prakash Shiringarpure | COMPENSATION | 1271000 | 668000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
35 | Prashant Vasant Gawde | COMPENSATION | 1042000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 576000
36 | Prathmesh Shankar Juwale | COMPENSATION | 1027000 | 262000 | 17000 | 34000 | 34000 | 51000 | 53000 | 576000
37 | Pruthvi Sahadev Pal | COMPENSATION | 831000 | 228000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
38 | Rajbali Sahadev Pal | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
39 | Rajkumari Gulabchand Shukla | COMPENSATION | 846000 | 243000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
40 | Rajpati Shivprasad Varma | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
41 | Ramadevi Amrutlal Gupta | COMPENSATION | 865000 | 262000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
42 | Ramadhar Dalmal Yadav | COMPENSATION | 883030.23 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 417030.23
43 | Ramesh Anant Kulkarni | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
44 | Ramkumar Rammurat Yadav | COMPENSATION | 925000 | 322000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
45 | RAMRAJ RAMJIVAN PAL | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
46 | Ravinath Santaram More | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
47 | Sanjay Atma Prasad Mishra | COMPENSATION | 884200 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 418200
48 | Santosh Chintaman Juwale | COMPENSATION | 897083 | 277000 | 34000 | 34000 | 34000 | 51000 | 53000 | 414083
49 | Satyendra Dharmdev Pal | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
50 | Shankar Chintaman Juwale | COMPENSATION | 914000 | 277000 | 51000 | 34000 | 34000 | 51000 | 53000 | 414000
51 | Shivprasad Sitlaprasad Dubey | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
52 | SHUBHANGI D. TULASKAR | COMPENSATION | 863000 | 260000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
53 | Shubhangi Sahdev Kande | COMPENSATION | 880502 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414502
54 | SRAVAN RAM | COMPENSATION | 891000 | 288000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
55 | Sulochana Suryakant Devalkar | COMPENSATION | 863000 | 277000 |  | 34000 | 34000 | 51000 | 53000 | 414000
56 | SUSHILA AMRESH YADAV | COMPENSATION | 840000 | 322000 |  |  |  | 51000 | 53000 | 414000
57 | Vasant Bhaskar Naik | COMPENSATION | 1105000 | 277000 | [5 empty] | 828000
58 | Vasanti Santaram Ghag | COMPENSATION | 691000 | 277000 | [5 empty] | 414000
59 | GULAB CHAND SHUKLA | COMPENSATION | 448000 | 34000 | [5 empty] | 414000
60 | KALINDRI HARIGOVIND SINGH | COMPENSATION | 448000 | 34000 | [5 empty] | 414000
61 | PHULAVATI DAYARAM MOURY | COMPENSATION | 448000 | 34000 | [5 empty] | 414000
62 | Prathvi Sehdev Pal | COMPENSATION | 34000 | 34000
0
0
0
|  |  | 52958945.85 | 17044000 | 969000 | 2164000 | 1870000 | 2902000 | 2951000 | 25058945.85

## TDR & Approval
SR.NO | PARTICULARS | NATURE | DATE | TOTAL AMOUNT
1 | MUNICIPAL TAXES & OTHER CHARGES | CFO SCRUNITY FEES | 2018-12-28 | 1522992
2 | MUNICIPAL TAXES & OTHER CHARGES | REIMBURSEMENT OF FEES | 2020-01-29 | 2420
3 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2020-10-09 | 4000
4 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2020-10-15 | 220000
5 | MUNICIPAL TAXES & OTHER CHARGES | SCRUNITY FEES | 2020-12-14 | 1028581
6 | MUNICIPAL TAXES & OTHER CHARGES | RBI FUND MUMBAI | 2021-03-31 | 280000
7 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-07-21 | 1710000
8 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-08-12 | 36500
9 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-08-12 | 59000
10 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-08-12 | 9000
11 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-08-12 | 19000
12 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-08-12 | 199000
13 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-08-12 | 210100
14 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-08-12 | 20393670
15 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-08-12 | 6742725
16 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-08-12 | 750000
17 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-08-12 | 5000
18 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-08-12 | 4425
19 | MUNICIPAL TAXES & OTHER CHARGES | PAY ORDER REHAB 1 POONAM NAGAR | 2021-09-28 | 2874800
20 | MUNICIPAL TAXES & OTHER CHARGES | PAY ORDER POONAM NAGAR | 2021-10-01 | 564800
21 | MUNICIPAL TAXES & OTHER CHARGES | PAYORDER FOR DEMARCATION | 2021-10-29 | 9420
22 | MUNICIPAL TAXES & OTHER CHARGES | PAY ORDER FOR SRA POONAM NAGAR | 2021-12-04 | 55095105
23 | MUNICIPAL TAXES & OTHER CHARGES | PAY ORDER FOR SRA POONAM NAGAR | 2022-04-19 | 200000
24 | MUNICIPAL TAXES & OTHER CHARGES | PAID TO SCRUTINY FEES | 2022-06-17 | 700000
25 | MUNICIPAL TAXES & OTHER CHARGES | CREDIT CARD FOR AIRPORT AUTHORITY OF INDIA. | 2022-08-06 | 236000
26 | MUNICIPAL TAXES & OTHER CHARGES | ONLINE PAYMENT MADE TO GRASS | 2022-08-20 | 30000
27 | MUNICIPAL TAXES & OTHER CHARGES | CH.NO 450920 | 2022-09-05 | 677520
30 | MUNICIPAL TAXES & OTHER CHARGES | CFO SCRUTINY FEES | 2022-09-07 | 157522
31 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2022-09-23 | 4000
32 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2022-09-30 | 9000
33 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2022-09-30 | 32000
34 | MUNICIPAL TAXES & OTHER CHARGES | BMC PAY ORDER | 2022-11-24 | 42900
35 | MUNICIPAL TAXES & OTHER CHARGES | BMC PAY ORDER | 2022-11-24 | 13900
36 | MUNICIPAL TAXES & OTHER CHARGES | BMC PAY ORDER | 2022-11-24 | 56700
37 | MUNICIPAL TAXES & OTHER CHARGES | TREE CUTING CHARGES | 2022-12-14 | 10000
38 | MUNICIPAL TAXES & OTHER CHARGES | TREE CUTING CHARGES | 2022-12-14 | 255000
39 | MUNICIPAL TAXES & OTHER CHARGES | TREE CUTING CHARGES | 2022-12-14 | 150000
40 | MUNICIPAL TAXES & OTHER CHARGES | PAID AIRPORT AUTHORITY OF INDIA | 2022-12-14 | 2360000
41 | MUNICIPAL TAXES & OTHER CHARGES | PAY ORDER TO SRA AG REHAB | 2023-01-12 | 3015000
42 | MUNICIPAL TAXES & OTHER CHARGES | PAY ORDER TO SRA AG REHAB | 2023-01-12 | 594500
43 | MUNICIPAL TAXES & OTHER CHARGES | PAID TO SRA AG MRTP CHARGES | 2023-01-12 | 3756000
44 | MUNICIPAL TAXES & OTHER CHARGES | PAID TO SRA AG LABOUR CESS FOR POONAM NAGAR | 2023-01-12 | 7713500
45 | MUNICIPAL TAXES & OTHER CHARGES | PAYMENT MADE TO MAHAKANJI | 2023-02-27 | 45912
46 | MUNICIPAL TAXES & OTHER CHARGES | PAYMENT MADE TO GRASS | 2023-02-27 | 366138
47 | MUNICIPAL TAXES & OTHER CHARGES | PAYMENT MADE TO MAHAKANJI | 2023-02-27 | 54329
48 | MUNICIPAL TAXES & OTHER CHARGES | PAYMENT MADE TO GRASS | 2023-02-27 | 433770
49 | MUNICIPAL TAXES & OTHER CHARGES | PAYMENT MADE TO MAHAKANJI | 2023-02-27 | 177526
50 | MUNICIPAL TAXES & OTHER CHARGES | PAYMENT MADE TO GRASS | 2023-02-27 | 1417486
51 | MUNICIPAL TAXES & OTHER CHARGES | CH.NO 450572 AG POONAM NAGAR | 2023-05-15 | 71775
52 | MUNICIPAL TAXES & OTHER CHARGES | CH.NO 450573 POONAM NAGAR CARRIAGE AMOUNT | 2023-05-17 | 31235
53 | MUNICIPAL TAXES & OTHER CHARGES | CH.NO 071903 AG PCO CHARGES NEELKAMAL AMINITIES | 2023-07-05 | 64831
|  | LEGAL CHARGES FOR VERIFICATION | 2023-07-31 | 44522
| MRTP DEVELOPMENT CHARGES | SLUM REHABILITATION AUTHORITY | 2023-04-08 | 4675625
| MRTP DEVELOPMENT CHARGES | SLUM REHABILITATION AUTHORITY | 2023-04-08 | 13935500
| MRTP DEVELOPMENT CHARGES | SLUM REHABILITATION AUTHORITY | 2023-04-08 | 2007750
| MRTP DEVELOPMENT CHARGES | SLUM REHABILITATION AUTHORITY | 2023-04-08 | 2000400
| MRTP DEVELOPMENT CHARGES | SLUM REHABILITATION AUTHORITY | 22/8/23 | 3545500
| MRTP DEVELOPMENT CHARGES | SLUM REHABILITATION AUTHORITY |  | 8000
| MUNICIPAL TAX & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2023-11-22 | 81910
| MUNICIPAL TAX & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2023-12-03 | 64831
|  | SLUM REHABILITATION AUTHORITY | 2023-12-26 | 2000
|  | SLUM REHABILITATION AUTHORITY | 2023-12-26 | 2000
|  | SLUM REHABILITATION AUTHORITY | 2023-12-26 | 4000
| COST OF T.D.R. |  | 2024-02-26 | 2074315
| COST OF T.D.R. |  | 2024-02-29 | 14426207
| COST OF T.D.R. |  | 2024-02-29 | 5822040
| COST OF T.D.R. |  | 2024-03-04 | 63000
| COST OF T.D.R. |  | 2024-03-04 | 433400
| COST OF T.D.R. |  | 2024-03-04 | 175300
| COST OF T.D.R. |  | 2024-03-07 | 24800000
| COST OF T.D.R. |  | 2024-03-14 | 744600
| MUNICIPAL TAX & OTHER CHARGES |  | 2024-02-16 | 21500
| MUNICIPAL TAX & OTHER CHARGES |  | 2024-03-21 | 368749
| MUNICIPAL TAX & OTHER CHARGES |  | 2024-03-21 | 45912
| SLUM REHABILITATION AUTHORITY | CHEQ.NO.071022 INTEREST PAID | 2024-02-28 | 841613
| SLUM REHABILITATION AUTHORITY | CH.NO 071045 | 2024-02-28 | 2000400
| SLUM REHABILITATION AUTHORITY | CH.NO 071039 | 2024-02-28 | 13935500
| SLUM REHABILITATION AUTHORITY | CH.NO 071042 | 2024-02-28 | 2007750
| SLUM REHABILITATION AUTHORITY | CH.NO 071036 | 2024-02-28 | 4675625
| SLUM REHABILITATION AUTHORITY | CHEQ.NO.071025 INTEREST PAID | 2024-02-28 | 2508390
| SLUM REHABILITATION AUTHORITY | CHEQ.NO.071028 INTEREST PAID | 2024-02-28 | 361395
| SLUM REHABILITATION AUTHORITY | CHEQ.NO.071031 INTEREST PAID | 2024-02-28 | 360072
| SLUM REHABILITATION AUTHORITY |  | 2024-06-01 | 51000
| SLUM REHABILITATION AUTHORITY |  | 2024-06-01 | 16322500
| SLUM REHABILITATION AUTHORITY |  | 2024-06-01 | 23000
| MUNICIPAL TAX & OTHER CHARGES |  |  | 90243
| MUNICIPAL TAX & OTHER CHARGES |  |  | 75656
| MUNICIPAL TAX & OTHER CHARGES |  |  | 186829
| MUNICIPAL TAX & OTHER CHARGES |  |  | 23262
| SHIVALIK VENTURES PRIVATE LIMITED- TDR | COST OF TDR |  | 24457472
|  | TOTAL MUNICIPAL TAX CHARGES |  | 257684850

## Construction Cost
PURCHASE- NEELKAMAL REALTY & CONTRUCTION LLP
1/4/18 - 31/7/23
Date | Particular | Total Amount
2022-07-15 | D.R LINKS | 71456
2022-10-10 | SHARADA ENTERPRISES | 65408
2023-03-14 | R.K.TRADERS | 6720
2023-03-31 | OM ENTERPRISES | 64774.08
2023-04-30 | OM ENTERPRISES | 61377.12
2023-05-27 | AMIT CORPORATION | 54880
2023-05-31 | S. H. ENTERPRISES | 61936
2023-06-03 | R.K.TRADING CO. | 3743.6
2023-06-15 | S. H. ENTERPRISES | 64960
2023-07-27 | RECONS BUILDING PRODUCTS PVT.LTD. | 59448
2022-04-18 | SHREEJI WATER PUMPS & BOREWELL | 132460.9
2022-06-18 | ANUPAM ELECTRICALS | 16756
2022-06-23 | SUSHMA CONTRUCTION STEEL SALES LLP | 77864.66
2022-06-25 | SUSHMA CONTRUCTION STEEL SALES LLP | 17792.64
2022-06-25 | ANUPAM ELECTRICALS | 4678.7
2022-07-07 | ANUPAM ELECTRICALS | 1060.82
2022-07-18 | SKY TELECOM | 73396
2022-08-03 | ANUPAM ELECTRICALS | 46621.8
2022-08-22 | KRISHNA TRADING CORPORATION | 13266.74
2022-08-29 | ANUPAM ELECTRICALS | 25649.66
2022-08-31 | SUSHMA CONTRUCTION STEEL SALES LLP | 10521.58
2022-09-01 | KRISHNA TRADING CORPORATION | 4010.77
2022-09-03 | SHREEJI WATER PUMPS & BOREWELL | 65431
2022-09-03 | SHREEJI WATER PUMPS & BOREWELL | 59885
2022-09-03 | SHREEJI WATER PUMPS & BOREWELL | 65431
2022-11-09 | MEHTA PLYWOOD | 4720
2023-02-20 | D.R LINKS | 45593.44
2023-02-25 | ANUPAM ELECTRICALS | 1062
2023-03-09 | ANUPAM ELECTRICALS | 63519.4
2023-03-14 | R.K.TRADERS | 7269.98
2023-03-16 | ANUPAM ELECTRICALS | 47837.2
2023-03-20 | MEHTA PLYWOOD | 4908.8
2023-03-22 | R.K.TRADERS | 7198
2023-03-23 | SUSHMA CONTRUCTION STEEL SALES LLP | 2148160.5
2023-03-24 | SUSHMA CONTRUCTION STEEL SALES LLP | 82052.48
2023-03-29 | ANUPAM ELECTRICALS | 47613
2023-03-30 | SUSHMA CONTRUCTION STEEL SALES LLP | 2171703.86
2023-03-30 | ANUPAM ELECTRICALS | 86022
2023-03-31 | OM SWASTIK ENTERPRISES | 33250.01
2023-04-03 | R.K.TRADERS | 7186.2
2023-04-03 | ANUPAM ELECTRICALS | 31425.76
2023-04-04 | ANUPAM ELECTRICALS | 38899.88
2023-04-04 | D.R LINKS | 22838.9
2023-04-05 | ANUPAM ELECTRICALS | 79281.84
2023-04-05 | KRISHNA CERAMICS | 49600.14
2023-04-06 | ANUPAM ELECTRICALS | 85404.28
2023-04-06 | KRISHNA TRADING CORPORATION | 31388
2023-04-07 | SUSHMA CONTRUCTION STEEL SALES LLP | 2165595
2023-04-07 | ANUPAM ELECTRICALS | 98810.26
2023-04-07 | KRISHNA TRADING CORPORATION | 11298.5
2023-04-08 | SUSHMA CONTRUCTION STEEL SALES LLP | 2190731.36
2023-04-10 | SUSHMA CONTRUCTION STEEL SALES LLP | 2026465.92
2023-04-10 | YESKAY INDUSTRIES | 36580
2023-04-11 | SUSHMA CONTRUCTION STEEL SALES LLP | 81608.8
2023-04-12 | SKY TELECOM | 29618
2023-04-14 | SUSHMA CONTRUCTION STEEL SALES LLP | 2220017.78
2023-04-15 | WEATHER COOL SERVICES | 9451.8
2023-04-17 | ANUPAM ELECTRICALS | 51079.84
2023-04-19 | VEDANT MARKETING | 54516
2023-04-20 | TEJAS CERAMICS | 5960.18
2023-04-24 | ANUPAM ELECTRICALS | 13776.74
2023-04-24 | VEDANT MARKETING | 89090
2023-04-25 | ANUPAM ELECTRICALS | 24724.54
2023-04-27 | KRISHNA TRADING CORPORATION | 62000.09
2023-05-02 | ANUPAM ELECTRICALS | 29665.2
2023-05-03 | VEDANT MARKETING | 53454
2023-05-04 | R.K.TRADING CO. | 3793.7
2023-05-05 | VEDANT MARKETING | 89090
2023-05-05 | SUSHMA CONTRUCTION STEEL SALES LLP | 2132342.6
2023-05-06 | VEDANT MARKETING | 178180
2023-05-08 | MEHTA PLYWOOD | 339.84
2023-05-10 | SUSHMA CONTRUCTION STEEL SALES LLP | 2138807.82
2023-05-12 | KRISHNA TRADING CORPORATION | 6903
2023-05-14 | SUSHMA CONTRUCTION STEEL SALES LLP | 2182202.32
2023-05-17 | VEDANT MARKETING | 142780
2023-05-18 | SUSHMA CONTRUCTION STEEL SALES LLP | 2170598.2
2023-05-19 | VEDANT MARKETING | 5982.6
2023-05-20 | R.K.TRADING CO. | 3894
2023-05-21 | SUSHMA CONTRUCTION STEEL SALES LLP | 81427.08
2023-05-23 | OM SWASTIK ENTERPRISES | 275400.08
2023-05-30 | SHREE DEV STEEL WORKS | 156940
2023-05-30 | VEDANT MARKETING | 178180
2023-05-31 | SEACOM SERVICES | 27376
2023-06-01 | SUSHMA CONTRUCTION STEEL SALES LLP | 2175891.68
2023-06-01 | ANUPAM ELECTRICALS | 73768.88
2023-06-01 | SUSHMA CONTRUCTION STEEL SALES LLP | 2187199.62
2023-06-02 | SAROVAR TRADING CO | 45312
2023-06-02 | SAROVAR TRADING CO | 45312
2023-06-02 | SAROVAR TRADING CO | 45312
2023-06-02 | SAROVAR TRADING CO | 45312
2023-06-02 | SAROVAR TRADING CO | 45312
2023-06-02 | SAROVAR TRADING CO | 45312
2023-06-02 | SAROVAR TRADING CO | 45312
2023-06-02 | SAROVAR TRADING CO | 45312
2023-06-02 | SAROVAR TRADING CO | 52864
2023-06-02 | SAROVAR TRADING CO | 52864
2023-06-02 | SAROVAR TRADING CO | 45312
2023-06-02 | SAROVAR TRADING CO | 45312
2023-06-02 | SAROVAR TRADING CO | 45312
2023-06-02 | SAROVAR TRADING CO | 45312
2023-06-02 | SAROVAR TRADING CO | 45312
2023-06-02 | SAROVAR TRADING CO | 45312
2023-06-02 | SAROVAR TRADING CO | 45312
2023-06-02 | SAROVAR TRADING CO | 45312
2023-06-02 | SAROVAR TRADING CO | 45312
2023-06-02 | SAROVAR TRADING CO | 45312
2023-06-02 | SAROVAR TRADING CO | 45312
2023-06-02 | SAROVAR TRADING CO | 45312
2023-06-02 | SAROVAR TRADING CO | 45312
2023-06-02 | SAROVAR TRADING CO | 45312
2023-06-02 | SAROVAR TRADING CO | 45312
2023-06-02 | ANUPAM ELECTRICALS | 80474.12
2023-06-03 | ANUPAM ELECTRICALS | 83872.74
2023-06-05 | FIRETRONICS SAFETY SYSTEMS | 88500
2023-06-10 | SUSHMA CONTRUCTION STEEL SALES LLP | 2141110
2023-06-12 | R.K.TRADERS | 4956
2023-06-14 | GENIUS TRACTOR COMPANY | 6643.45
2023-06-14 | UMA SERVICES | 15458
2023-06-15 | ANUPAM ELECTRICALS | 9617
2023-06-16 | SRK ENGINEERING SERVICES | 25346.4
2023-06-16 | SKY TELECOM | 51212
2023-06-20 | SUSHMA CONTRUCTION STEEL SALES LLP | 6955.04
2023-06-20 | SUSHMA CONTRUCTION STEEL SALES LLP | 96737.82
2023-06-20 | SUSHMA CONTRUCTION STEEL SALES LLP | 38646.32
2023-06-27 | UMA SERVICES | 2360
2023-06-29 | MAHIMA ENTERPRISES | 1326403.78
2023-07-03 | UMA SERVICES | 2360
2023-07-10 | SHREE TECHNOCHEM | 59000
2023-07-12 | KRISHNA TRADING CORPORATION | 4606.6
2023-07-15 | SUSHMA CONTRUCTION STEEL SALES LLP | 1796916.98
2023-07-17 | ANUPAM ELECTRICALS | 32855.92
2023-07-25 | SUSHMA CONTRUCTION STEEL SALES LLP | 70325.64
2023-07-27 | RECONS BUILDING PRODUCTS PVT.LTD. | 4200
2023-07-28 | ANUPAM ELECTRICALS | 35016.5
2020-01-13 | KIRIT TRADING COMPANY | 13888
2023-03-18 | SUNTREK CORPORATION | 115200
2023-03-24 | SUNTREK CORPORATION | 114048
2023-03-26 | SUNTREK CORPORATION | 114048
2023-03-27 | SUNTREK CORPORATION | 188800
2023-03-31 | SUNTREK CORPORATION | 151040
2023-03-31 | SUNTREK CORPORATION | 37760
2023-04-04 | J.K.LAKSHMI CEMENT (KETANBHAI) | 115200
2023-04-04 | J.K.LAKSHMI CEMENT (KETANBHAI) | 76800
2023-04-09 | THE INDIA CEMENTS LIMITED | 94400
2023-04-09 | THE INDIA CEMENTS LIMITED | 94400
2023-04-15 | WEATHER COOL SERVICES | 32000
2023-04-17 | J.K.LAKSHMI CEMENT (KETANBHAI) | 115200
2023-04-22 | THE INDIA CEMENTS LIMITED | 111360
2023-04-22 | THE INDIA CEMENTS LIMITED | 111360
2023-04-22 | THE INDIA CEMENTS LIMITED | 111360
2023-04-22 | THE INDIA CEMENTS LIMITED | 111360
2023-04-22 | THE INDIA CEMENTS LIMITED | 111360
2023-04-26 | THE INDIA CEMENTS LIMITED | 92800
2023-04-26 | THE INDIA CEMENTS LIMITED | 92800
2023-04-29 | THE INDIA CEMENTS LIMITED | 111360
2023-04-29 | THE INDIA CEMENTS LIMITED | 111360
2023-04-29 | THE INDIA CEMENTS LIMITED | 111360
2023-04-29 | THE INDIA CEMENTS LIMITED | 111360
2023-04-29 | THE INDIA CEMENTS LIMITED | 111360
2023-05-06 | THE INDIA CEMENTS LIMITED | 111360
2023-05-06 | THE INDIA CEMENTS LIMITED | 111360
2023-05-06 | THE INDIA CEMENTS LIMITED | 111360
2023-05-06 | THE INDIA CEMENTS LIMITED | 111360
2023-05-06 | THE INDIA CEMENTS LIMITED | 111360
2023-05-06 | THE INDIA CEMENTS LIMITED | 111360
2023-05-06 | THE INDIA CEMENTS LIMITED | 111360
2023-05-06 | THE INDIA CEMENTS LIMITED | 111360
2023-05-08 | THE INDIA CEMENTS LIMITED | 92800
2023-05-08 | THE INDIA CEMENTS LIMITED | 92800
2023-05-08 | THE INDIA CEMENTS LIMITED | 111360
2023-05-08 | THE INDIA CEMENTS LIMITED | 111360
2023-05-13 | KARAN ENTERPRISES | 74240
2023-05-16 | KARAN ENTERPRISES | 148480
2023-05-16 | KARAN ENTERPRISES | 148480
2023-05-16 | KARAN ENTERPRISES | 148480
2023-05-16 | KARAN ENTERPRISES | 185600
2023-05-16 | KARAN ENTERPRISES | 148480
2023-05-16 | KARAN ENTERPRISES | 92800
2023-05-17 | KARAN ENTERPRISES | 185600
2023-05-17 | KARAN ENTERPRISES | 148480
2023-05-17 | KARAN ENTERPRISES | 185600
2023-05-17 | KARAN ENTERPRISES | 185600
2023-05-20 | KARAN ENTERPRISES | 74240
2023-05-21 | THE INDIA CEMENTS LIMITED | 92800
2023-05-21 | THE INDIA CEMENTS LIMITED | 92800
2023-05-27 | THE INDIA CEMENTS LIMITED | 222720
2023-05-29 | J.K.LAKSHMI CEMENT (KETANBHAI) | 74240
2023-05-29 | J.K.LAKSHMI CEMENT (KETANBHAI) | 148480
2023-05-29 | J.K.LAKSHMI CEMENT (KETANBHAI) | 148480
2023-05-29 | J.K.LAKSHMI CEMENT (KETANBHAI) | 148480
2023-05-29 | J.K.LAKSHMI CEMENT (KETANBHAI) | 148480
2023-05-29 | J.K.LAKSHMI CEMENT (KETANBHAI) | 74240
2023-05-29 | J.K.LAKSHMI CEMENT (KETANBHAI) | 111360
2023-05-30 | J.K.LAKSHMI CEMENT (KETANBHAI) | 185600
2023-05-31 | J.K.LAKSHMI CEMENT (KETANBHAI) | 74240
2023-06-01 | THE INDIA CEMENTS LIMITED | 185600
2023-06-01 | THE INDIA CEMENTS LIMITED | 185600
2023-06-17 | J.K.LAKSHMI CEMENT (KETANBHAI) | 93440
2023-06-17 | J.K.LAKSHMI CEMENT (KETANBHAI) | 93440
2023-06-20 | THE INDIA CEMENTS LIMITED | 224256
2023-06-24 | THE INDIA CEMENTS LIMITED | 112128
2023-06-24 | THE INDIA CEMENTS LIMITED | 112128
2023-07-01 | THE INDIA CEMENTS LIMITED | 93440
2023-07-01 | THE INDIA CEMENTS LIMITED | 93440
2023-07-08 | THE INDIA CEMENTS LIMITED | 92800
2023-07-08 | THE INDIA CEMENTS LIMITED | 92800
2023-07-11 | THE INDIA CEMENTS LIMITED | 111360
2023-07-12 | THE INDIA CEMENTS LIMITED | 111360
2023-07-12 | THE INDIA CEMENTS LIMITED | 111360
2023-07-12 | THE INDIA CEMENTS LIMITED | 111360
2023-07-15 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 185600
2023-07-28 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 91840
2023-07-28 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 183680
2023-07-28 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 183680
2023-07-28 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 91840
2019-08-31 | PANCHANKUR STONE QUARY | 8531.26
2019-12-31 | GAURAV TRADING CO. | 12311.26
2019-12-31 | SHARADA ENTERPRISES | 25552.8
2020-01-15 | SHARADA ENTERPRISES | 55666.8
2020-01-31 | GAURAV TRADING CO. | 7185
2020-02-29 | OM ENTERPRISES | 24024
2020-11-30 | OM ENTERPRISES | 33075
2020-11-30 | SHARADA ENTERPRISES | 26082
2020-12-31 | OM ENTERPRISES | 21117.6
2020-12-31 | OM ENTERPRISES | 70978.96
2020-12-31 | S. H. ENTERPRISES | 26460
2021-01-31 | OM ENTERPRISES | 33075
2022-10-31 | DHANAAJI ENTERPRISES | 4357.5
2022-11-15 | DHANAAJI ENTERPRISES | 4147.5
2023-03-13 | RAJLAXMI CORPORATION | 27540.46
2023-03-27 | AMIT CORPORATION | 89838
2023-03-30 | AMIT CORPORATION | 26068.36
2023-03-31 | S. H. ENTERPRISES | 48567.76
2023-03-31 | SHARADA ENTERPRISES | 52409.7
2023-03-31 | RAJLAXMI CORPORATION | 52943.1
2023-03-31 | ADINATH ENTERPRISES | 72377.56
2023-04-05 | AMIT CORPORATION | 28182
2023-04-08 | JSW CEMENT LIMITED | 59625
2023-04-09 | RAJLAXMI CORPORATION | 32263.88
2023-04-15 | NEER TRADING CO. | 24210.9
2023-04-15 | RAJ TRANSIT INFRA PVT LTD | 127554
2023-04-24 | ADINATH ENTERPRISES | 17321.86
2023-04-24 | AMIT CORPORATION | 87387.3
2023-04-25 | HARMAN ENGINEERING WORKS | 13393.28
2023-04-25 | RAJLAXMI CORPORATION | 100641.98
2023-04-26 | AMIT CORPORATION | 87845.62
2023-04-29 | SHIV ENTERPRISES | 50652.52
2023-04-30 | S. H. ENTERPRISES | 101164.36
2023-04-30 | S. H. ENTERPRISES | 78788.32
2023-04-30 | S. H. ENTERPRISES | 80890.42
2023-04-30 | S. H. ENTERPRISES | 36948.46
2023-04-30 | OM ENTERPRISES | 43942.5
2023-04-30 | NEER TRADING CO. | 43489.96
2023-04-30 | AMIT CORPORATION | 75929.18
2023-04-30 | AMIT CORPORATION | 28059.68
2023-04-30 | ADINATH ENTERPRISES | 30723
2023-04-30 | RAJ TRANSIT INFRA PVT LTD | 103592.48
2023-05-02 | JSW CEMENT LIMITED | 119250
2023-05-03 | JSW CEMENT LIMITED | 119250
2023-05-04 | R.K.TRADING CO. | 7245
2023-05-05 | HARMAN ENGINEERING WORKS | 65336.26
2023-05-05 | S.S.ENTERPRISES | 33075
2023-05-06 | AMIT CORPORATION | 87081.76
2023-05-07 | AMIT CORPORATION | 98096.26
2023-05-10 | JSW CEMENT LIMITED | 119250
2023-05-10 | AMIT CORPORATION | 83771.62
2023-05-13 | AMIT CORPORATION | 94975.12
2023-05-15 | JSW CEMENT LIMITED | 119250
2023-05-15 | RAJ TRANSIT INFRA PVT LTD | 109620
2023-05-15 | ADINATH ENTERPRISES | 31161.9
2023-05-15 | OM ENTERPRISES | 26884.2
2023-05-15 | S. H. ENTERPRISES | 103447.58
2023-05-15 | S. H. ENTERPRISES | 91764.76
2023-05-15 | S. H. ENTERPRISES | 97456.8
2023-05-15 | S. H. ENTERPRISES | 85943.56
2023-05-15 | S. H. ENTERPRISES | 101749.72
2023-05-15 | S. H. ENTERPRISES | 96827.86
2023-05-15 | S. H. ENTERPRISES | 99954.22
2023-05-15 | S. H. ENTERPRISES | 99165.68
2023-05-15 | S. H. ENTERPRISES | 103002.9
2023-05-15 | AMIT CORPORATION | 64036.88
2023-05-20 | R.K.TRADING CO. | 7245
2023-05-20 | JSW CEMENT LIMITED | 119250
2023-05-23 | SHIV ENTERPRISES | 24578.4
2023-05-24 | HARMAN ENGINEERING WORKS | 59990.7
2023-05-28 | AMIT CORPORATION | 95382.52
2023-05-28 | AMIT CORPORATION | 79513.88
2023-05-29 | JSW CEMENT LIMITED | 119250
2023-05-30 | M/S.SHRIYAA ENTERPRISES | 65417.1
2023-05-31 | S. H. ENTERPRISES | 98118.3
2023-05-31 | S. H. ENTERPRISES | 95925.38
2023-05-31 | S. H. ENTERPRISES | 102937.8
2023-05-31 | S. H. ENTERPRISES | 99768.9
2023-05-31 | S. H. ENTERPRISES | 92427.82
2023-05-31 | S. H. ENTERPRISES | 37582.64
2023-05-31 | S. H. ENTERPRISES | 33086.02
2023-05-31 | OM ENTERPRISES | 54195.76
2023-05-31 | RAJLAXMI CORPORATION | 157754.1
2023-05-31 | RAJ TRANSIT INFRA PVT LTD | 116887.58
2023-06-02 | JSW CEMENT LIMITED | 119250
2023-06-14 | ADINATH ENTERPRISES | 69244.36
2023-06-14 | HARMAN ENGINEERING WORKS | 35494.72
2023-06-15 | S. H. ENTERPRISES | 94271.1
2023-06-15 | S. H. ENTERPRISES | 98313.6
2023-06-15 | S. H. ENTERPRISES | 32744.26
2023-06-15 | S. H. ENTERPRISES | 94166.62
2023-06-21 | AMIT CORPORATION | 94813.42
2023-06-23 | JSW CEMENT LIMITED | 119250
2023-06-24 | HARMAN ENGINEERING WORKS | 27771.98
2023-06-25 | AMIT CORPORATION | 95472.3
2023-06-28 | RAJLAXMI CORPORATION | 96299.18
2023-06-30 | NEER TRADING CO. | 31329.9
2023-06-30 | S. H. ENTERPRISES | 94905.3
2023-06-30 | S. H. ENTERPRISES | 73671.16
2023-06-30 | S. H. ENTERPRISES | 37582.66
2023-06-30 | M/S.SHRIYAA ENTERPRISES | 44251.2
2023-07-08 | AMIT CORPORATION | 96625.72
2023-07-13 | AMIT CORPORATION | 92168.48
2023-07-15 | ADINATH ENTERPRISES | 23580.9
2023-07-15 | RAJ TRANSIT INFRA PVT LTD | 30605.92
2023-07-18 | M/S.SHRIYAA ENTERPRISES | 87998.4
2023-07-22 | RAJLAXMI CORPORATION | 50571.68
2023-07-23 | AMIT CORPORATION | 97215.82
2023-07-31 | AMIT CORPORATION | 52202.32
2023-04-30 | THE INDIA CEMENTS LIMITED | 489241.6
2022-04-01 | K.S.HIRING | 18600
2022-06-20 | Thakkar Electrical Works | 18000
2022-12-28 | H. A. NADAR | 674925
2023-03-04 | Thakkar Electrical Works | 15000
2023-03-09 | ROHIT SHUKLA | 100000
2023-03-16 | PREET DESAI | 29000
2023-03-16 | SADHANA MISHRA | 29000
2023-03-16 | NITIN SHENGDE | 29000
2023-03-16 | SUFIYAN JAMADAR | 29000
2023-03-16 | AMIT KUMAR | 29000
2023-03-20 | ANIL MANI HUF | 29000
2023-03-25 | G C CREATION | 1500000
2023-03-25 | SHAMBHO GROUPS OF COMPANYS | 1500000
2023-04-01 | VANDANA RAJARAM POL | 25000
2023-04-02 | REHAN ENTERPRISES | 178480
2023-04-03 | SADHANA MISHRA | 29000
2023-04-03 | SUFIYAN JAMADAR | 29000
2023-04-03 | PREET DESAI | 29000
2023-04-03 | NITIN SHENGDE | 29000
2023-04-03 | AMIT KUMAR | 29000
2023-04-03 | ROHIT SHUKLA | 500000
2023-04-03 | ROHIT SHUKLA | 29250
2023-04-03 | ROHIT SHUKLA | 175000
2023-04-06 | HARMAN ENGINEERING WORKS | 30723
2023-04-10 | INDIAN FABRICATORS | 250000
2023-04-21 | RAMASHREY PRAJAPATI | 15136
2023-04-28 | AKAR CONSTRUCTION COMPANY | 2950000
2023-04-29 | INDIAN FABRICATORS | 355440.5
2023-05-05 | WATER PUMP HIRE SERVICE | 16565
2023-05-15 | Thakkar Electrical Works | 15000
2023-05-22 | AKAR CONSTRUCTION COMPANY | 2360000
2023-05-26 | ADITYA CRANE SERVICE | 79562
2023-06-08 | WATER PUMP HIRE SERVICE | 23366
2023-06-17 | AKAR CONSTRUCTION COMPANY | 2950000
2023-06-24 | WELCOME ENTERPRIESES | 150000
2023-06-30 | WATER PUMP HIRE SERVICE | 21000
2023-07-07 | YOGENDRA PANDEY | 1000000
2023-07-07 | AKAR CONSTRUCTION COMPANY | 944000
2023-07-07 | MOHAMMAD ABUL HAYAT | 500000
2023-07-11 | MUNNI TAUFIK SHAIKH | 700000
2023-07-24 | ROHIT SHUKLA | 145000
2023-07-24 | ROHIT SHUKLA | 145000
2023-08-01 | VIDHI CONSTRUCTIONS | 830661
2023-08-05 | VIDHI CONSTRUCTIONS | 1900980
2023-08-14 | VIDHI CONSTRUCTIONS | 4195301
2023-08-22 | AKAR CONSTRUCTION COMPANY | 10030000
2023-09-01 | HEMANT B. AMANAG | 700000
2023-09-01 | SULABAI AMANAGE | 700000
2023-09-01 | KAMLADEVI CHAMPALAL GOWANI | 700000
2023-09-01 | YOGESH B.SAHU | 1125000
2023-09-02 | INDIAN FABRICATORS | 13100
2023-09-02 | INDIAN FABRICATORS | 230915
2023-09-02 | REHAN ENTERPRISES | 111734
2023-09-18 | RAMASHREY PRAJAPATI | 13224
2023-09-30 | WATER PUMP HIRE SERVICE | 23250
2023-09-30 | GUNVANTRAI M SONI | 82600
2023-08-14 | RECONS BUILDING PRODUCTS PVT.LTD. | 67485.6
2023-08-14 | RECONS BUILDING PRODUCTS PVT.LTD. | 60060
2023-08-18 | RECONS BUILDING PRODUCTS PVT.LTD. | 67616.64
2023-08-21 | RECONS BUILDING PRODUCTS PVT.LTD. | 72727
2023-08-22 | RECONS BUILDING PRODUCTS PVT.LTD. | 20249.6
2023-08-29 | RECONS BUILDING PRODUCTS PVT.LTD. | 53857
2023-08-31 | RECONS BUILDING PRODUCTS PVT.LTD. | 53511.01
2023-08-05 | SUSHMA CONTRUCTION STEEL SALES LLP | 1924329.84
2023-08-08 | SUSHMA CONTRUCTION STEEL SALES LLP | 2164195.52
2023-08-08 | SHREEJI WATER PUMPS & BOREWELL | 24603
2023-08-08 | SHREE TECHNOCHEM | 53100
2023-08-08 | SHREE TECHNOCHEM | 53100
2023-08-09 | SUSHMA CONTRUCTION STEEL SALES LLP | 1598162.5
2023-08-12 | ANUPAM ELECTRICALS | 4277.5
2023-08-14 | RECONS BUILDING PRODUCTS PVT.LTD. | 5669.9
2023-08-14 | RECONS BUILDING PRODUCTS PVT.LTD. | 6074.64
2023-08-16 | ANUPAM ELECTRICALS | 25606
2023-08-16 | SHREE TECHNOCHEM | 66375
2023-08-16 | ANUPAM ELECTRICALS | 26172.4
2023-08-17 | SUSHMA CONTRUCTION STEEL SALES LLP | 1700265.54
2023-08-17 | SUSHMA CONTRUCTION STEEL SALES LLP | 78064.08
2023-08-21 | SUSHMA CONTRUCTION STEEL SALES LLP | 1971592.38
2023-08-23 | SUSHMA CONTRUCTION STEEL SALES LLP | 1987354.82
2023-08-26 | R.K.TRADERS | 5310
2023-08-27 | SHREE TECHNOCHEM | 132750
2023-08-28 | ANUPAM ELECTRICALS | 22462.48
2023-08-31 | RECONS BUILDING PRODUCTS PVT.LTD. | 10181.04
2023-08-04 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 183680
2023-08-12 | KARAN ENTERPRISES | 93440
2023-08-16 | KARAN ENTERPRISES | 93440
2023-08-16 | KARAN ENTERPRISES | 93440
2023-08-16 | KARAN ENTERPRISES | 74752
2023-08-16 | KARAN ENTERPRISES | 93440
2023-08-16 | KARAN ENTERPRISES | 93440
2023-08-18 | KARAN ENTERPRISES | 93440
2023-08-18 | KARAN ENTERPRISES | 93440
2023-08-22 | SUNTREK CORPORATION | 75008
2023-08-22 | SUNTREK CORPORATION | 44254.72
2023-08-22 | SUNTREK CORPORATION | 75008
2023-08-22 | SUNTREK CORPORATION | 37504
2023-08-26 | THE INDIA CEMENTS LIMITED | 228774.4
2023-08-26 | THE INDIA CEMENTS LIMITED | 228774.4
2023-08-31 | THE INDIA CEMENTS LIMITED | 232524.8
2023-08-31 | THE INDIA CEMENTS LIMITED | 232524.8
2023-08-04 | JSW CEMENT LIMITED | 119250
2023-08-06 | AMIT CORPORATION | 59465.18
2023-08-15 | ADINATH ENTERPRISES | 24019.8
2023-08-15 | SHARADA ENTERPRISES | 90493.72
2023-08-15 | SHARADA ENTERPRISES | 94759.88
2023-08-15 | SHARADA ENTERPRISES | 93270.46
2023-08-15 | SHARADA ENTERPRISES | 83058.68
2023-08-16 | AMIT CORPORATION | 67605.3
2023-08-21 | HARMAN ENGINEERING WORKS | 90349.88
2023-08-21 | SHARADA ENTERPRISES | 96490.28
2023-08-21 | SHARADA ENTERPRISES | 83048.18
2023-08-21 | SHARADA ENTERPRISES | 63143.86
2023-08-23 | JSW CEMENT LIMITED | 119250
2023-08-25 | R.K.TRADING CO. | 11550
2023-08-29 | AMIT CORPORATION | 95130
2023-08-31 | SHARADA ENTERPRISES | 84003.16
2023-08-31 | SHARADA ENTERPRISES | 95755.8
2023-08-31 | SHARADA ENTERPRISES | 83160.52
2023-08-31 | SHARADA ENTERPRISES | 73896.9
2023-08-31 | SHARADA ENTERPRISES | 73896.9
2023-08-31 | SHARADA ENTERPRISES | 41198.32
2023-08-31 | RAJ TRANSIT INFRA PVT LTD | 25589.02
2023-08-31 | RAJLAXMI CORPORATION | 92159.56
2023-09-04 | RECONS BUILDING PRODUCTS PVT.LTD. | 54206.88
2023-09-07 | RECONS BUILDING PRODUCTS PVT.LTD. | 62506.08
2023-09-08 | RECONS BUILDING PRODUCTS PVT.LTD. | 57788.64
2023-09-12 | RECONS BUILDING PRODUCTS PVT.LTD. | 128419.08
2023-09-16 | SNEH ENTERPRISE | 82869.48
2023-09-16 | SNEH ENTERPRISE | 82043.88
2023-09-04 | RECONS BUILDING PRODUCTS PVT.LTD. | 6075.01
2023-09-07 | RECONS BUILDING PRODUCTS PVT.LTD. | 6075.01
2023-09-08 | RECONS BUILDING PRODUCTS PVT.LTD. | 6075.01
2023-09-12 | RECONS BUILDING PRODUCTS PVT.LTD. | 2025.01
2023-09-13 | SUSHMA CONTRUCTION STEEL SALES LLP | 76691.74
2023-09-16 | SNEH ENTERPRISE | 21249.44
2023-09-24 | SUSHMA CONTRUCTION STEEL SALES LLP | 2153671.1
2023-09-30 | LANDMARK CONSULTANTS & ENGG. TECHNOLOGY | 13098
2023-09-08 | THE INDIA CEMENTS LIMITED | 232524.8
2023-09-13 | SUNTREK CORPORATION | 74240
2023-09-13 | SUNTREK CORPORATION | 18560
2023-09-13 | SUNTREK CORPORATION | 74240
2023-09-13 | SUNTREK CORPORATION | 31923.2
2023-09-13 | THE INDIA CEMENTS LIMITED | 222720
2023-09-16 | SUNTREK CORPORATION | 74240
2023-09-16 | SUNTREK CORPORATION | 31923.2
2023-09-16 | SUNTREK CORPORATION | 74240
2023-09-16 | SUNTREK CORPORATION | 18560
2023-09-16 | SUNTREK CORPORATION | 74240
2023-09-16 | SUNTREK CORPORATION | 18560
2023-09-16 | SUNTREK CORPORATION | 74240
2023-09-16 | SUNTREK CORPORATION | 18560
2023-09-06 | M/S.SHRIYAA ENTERPRISES | 43540.88
2023-09-07 | JSW CEMENT LIMITED | 119250
2023-09-15 | ADINATH ENTERPRISES | 48318.9
2023-09-15 | M/S.SHRIYAA ENTERPRISES | 71549.62
2023-09-15 | CHIRAG ENTERPRISES | 55500.9
2023-10-02 | SAKSHI CORPORATION | 142829
2023-10-15 | SAKSHI CORPORATION | 135703.8
2023-10-18 | SAKSHI CORPORATION | 138739.1
2023-10-19 | SAKSHI CORPORATION | 139927.2
2023-11-07 | SAKSHI CORPORATION | 171607.52
2023-11-25 | SAKSHI CORPORATION | 163944.7
2023-12-05 | SHARADA ENTERPRISES | 65408
2023-12-07 | UN CORPORATION | 181602
2023-12-15 | UN CORPORATION | 150052.5
2023-10-02 | SAKSHI CORPORATION | 10624.72
2023-10-07 | SUSHMA CONTRUCTION STEEL SALES LLP | 2095621
2023-10-07 | SHREE TECHNOCHEM | 66375
2023-10-09 | CHANDRAKANT ELECTRICAL & CONTRACTOR | 41944.76
2023-10-10 | KRISHNA TRADING CORPORATION | 4860.91
2023-10-10 | KRISHNA CERAMICS | 8024
2023-10-15 | SAKSHI CORPORATION | 21249.44
2023-10-16 | SUSHMA CONTRUCTION STEEL SALES LLP | 2129374.9
2023-10-17 | ANUPAM ELECTRICALS | 9221.7
2023-10-18 | SAKSHI CORPORATION | 16999.56
2023-10-18 | SHREE TECHNOCHEM | 132750
2023-10-19 | SAKSHI CORPORATION | 16999.56
2023-10-20 | GLOBAL GYPSUM PVT LTD | 28320
2023-10-26 | KRISHNA TRADING CORPORATION | 12272
2023-10-31 | SUSHMA CONTRUCTION STEEL SALES LLP | 2021151.2
2023-11-03 | R.K.TRADING CO. | 5959
2023-11-06 | SUSHMA CONTRUCTION STEEL SALES LLP | 70540.4
2023-11-06 | SUSHMA CONTRUCTION STEEL SALES LLP | 2039045.9
2023-11-06 | SHREE TECHNOCHEM | 66375
2023-11-07 | SAKSHI CORPORATION | 12749.66
2023-11-07 | HITECH CONSTRUCTIONS AND REPAIRS | 17464
2023-11-17 | VEDANT MARKETING | 51566
2023-11-18 | HITECH CONSTRUCTIONS AND REPAIRS | 26196
2023-11-20 | CHANDRAKANT ELECTRICAL & CONTRACTOR | 544179.42
2023-11-20 | GLOBAL GYPSUM PVT LTD | 14160
2023-11-22 | SUSHMA CONTRUCTION STEEL SALES LLP | 2056705.78
2023-11-25 | SAKSHI CORPORATION | 38249
2023-11-29 | VEDANT MARKETING | 51566
2023-11-30 | KRISHNA TRADING CORPORATION | 19045.37
2023-12-03 | R.K.TRADING CO. | 9735
2023-12-05 | VEDANT MARKETING | 72251.4
2023-12-06 | SUSHMA CONTRUCTION STEEL SALES LLP | 2085384.5
2023-12-07 | UN CORPORATION | 17550
2023-12-08 | GLOBAL GYPSUM PVT LTD | 28320
2023-12-09 | HITECH CONSTRUCTIONS AND REPAIRS | 5782
2023-12-11 | SUSHMA CONTRUCTION STEEL SALES LLP | 2042485.6
2023-12-15 | UN CORPORATION | 17550.09
2023-12-15 | VEDANT MARKETING | 53159
2023-12-19 | SUSHMA CONTRUCTION STEEL SALES LLP | 2040102
2023-12-24 | SUSHMA CONTRUCTION STEEL SALES LLP | 1961732.3
2023-12-30 | SUSHMA CONTRUCTION STEEL SALES LLP | 2073134.92
2023-10-05 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 185600
2023-10-06 | KIRIT TRADING COMPANY | 78080
2023-10-06 | KIRIT TRADING COMPANY | 78080
2023-10-06 | KIRIT TRADING COMPANY | 78080
2023-10-06 | KIRIT TRADING COMPANY | 78080
2023-10-06 | KIRIT TRADING COMPANY | 78080
2023-10-06 | KIRIT TRADING COMPANY | 242048
2023-10-08 | THE INDIA CEMENTS LIMITED | 225024
2023-10-13 | KIRIT TRADING COMPANY | 78080
2023-10-18 | SNEH ENTERPRISE | 111360
2023-10-20 | KIRIT TRADING COMPANY | 201600
2023-10-21 | KIRIT TRADING COMPANY | 201600
2023-10-24 | KIRIT TRADING COMPANY | 201600
2023-10-24 | KIRIT TRADING COMPANY | 201600
2023-10-28 | KIRIT TRADING COMPANY | 100800
2023-10-31 | KIRIT TRADING COMPANY | 201600
2023-10-31 | KIRIT TRADING COMPANY | 120960
2023-11-01 | KIRIT TRADING COMPANY | 72576
2023-11-06 | SUNTREK CORPORATION | 120960
2023-11-06 | SUNTREK CORPORATION | 120960
2023-11-06 | SUNTREK CORPORATION | 120960
2023-11-06 | SUNTREK CORPORATION | 120960
2023-11-08 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 91200
2023-11-08 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 18240
2023-11-08 | THE INDIA CEMENTS LIMITED | 100800
2023-11-08 | THE INDIA CEMENTS LIMITED | 100800
2023-11-09 | THE INDIA CEMENTS LIMITED | 249984
2023-11-16 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 117120
2023-11-16 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 117120
2023-11-17 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 156160
2023-11-17 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 195200
2023-11-23 | KIRIT TRADING COMPANY | 195200
2023-11-23 | KIRIT TRADING COMPANY | 195200
2023-11-24 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 188800
2023-11-24 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 188800
2023-11-26 | KIRIT TRADING COMPANY | 88640
2023-12-01 | KIRIT TRADING COMPANY | 106368
2023-12-04 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 94400
2023-12-04 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 94400
2023-12-04 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 94400
2023-12-04 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 94400
2023-12-04 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 94400
2023-12-04 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 94400
2023-12-05 | THE INDIA CEMENTS LIMITED | 96000
2023-12-05 | THE INDIA CEMENTS LIMITED | 96000
2023-12-05 | THE INDIA CEMENTS LIMITED | 115200
2023-12-06 | THE INDIA CEMENTS LIMITED | 76800
2023-12-12 | KIRIT TRADING COMPANY | 188800
2023-12-12 | KIRIT TRADING COMPANY | 188800
2023-12-12 | KIRIT TRADING COMPANY | 188800
2023-12-13 | THE INDIA CEMENTS LIMITED | 105600
2023-12-17 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 92800
2023-12-17 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 92800
2023-12-19 | KIRIT TRADING COMPANY | 104832
2023-10-02 | AMIT CORPORATION | 90888
2023-10-02 | AMIT CORPORATION | 60471.08
2023-10-02 | AMIT CORPORATION | 31531.5
2023-10-07 | HARMAN ENGINEERING WORKS | 55301.4
2023-10-09 | M/S.SHRIYAA ENTERPRISES | 31288.96
2023-10-11 | HARMAN ENGINEERING WORKS | 38601.16
2023-10-13 | RAJLAXMI CORPORATION | 82709.56
2023-10-15 | RAJ TRANSIT INFRA PVT LTD | 23850.76
2023-10-15 | SHARADA ENTERPRISES | 77355.08
2023-10-15 | ADINATH ENTERPRISES | 33795.3
2023-10-16 | M/S.SHRIYAA ENTERPRISES | 116366.26
2023-10-17 | JSW CEMENT LIMITED | 119249.56
2023-10-19 | M/S.SHRIYAA ENTERPRISES | 78435
2023-10-20 | HARMAN ENGINEERING WORKS | 94545.68
2023-10-21 | GLOBAL GYPSUM PVT LTD | 231000
2023-10-24 | M/S.SHRIYAA ENTERPRISES | 82956.82
2023-10-30 | RAJLAXMI CORPORATION | 38703
2023-10-31 | HARMAN ENGINEERING WORKS | 77040.08
2023-10-31 | SHARADA ENTERPRISES | 96575.32
2023-10-31 | SHARADA ENTERPRISES | 78664.96
2023-10-31 | RAJ TRANSIT INFRA PVT LTD | 32501.7
2023-10-31 | CHIRAG ENTERPRISES | 34673.1
2023-10-31 | OM ENTERPRISES | 27449.62
2023-11-01 | M/S.SHRIYAA ENTERPRISES | 38346.52
2023-11-03 | R.K.TRADING CO. | 27300
2023-11-04 | JSW CEMENT LIMITED | 119249.56
2023-11-06 | HARMAN ENGINEERING WORKS | 77791.36
2023-11-10 | RAJLAXMI CORPORATION | 85216.42
2023-11-15 | ADINATH ENTERPRISES | 33715.5
2023-11-15 | RAJ TRANSIT INFRA PVT LTD | 23446.5
2023-11-20 | M/S.SHRIYAA ENTERPRISES | 30844.28
2023-11-20 | M/S.SHRIYAA ENTERPRISES | 58581.6
2023-11-21 | JSW CEMENT LIMITED | 121875
2023-11-22 | M/S.SHRIYAA ENTERPRISES | 62443.5
2023-11-22 | GLOBAL GYPSUM PVT LTD | 231000
2023-11-23 | RAJ TRANSIT INFRA PVT LTD | 48752.56
2023-11-24 | M/S.SHRIYAA ENTERPRISES | 75623.62
2023-11-25 | HARMAN ENGINEERING WORKS | 80254.12
2023-11-28 | RAJLAXMI CORPORATION | 68109.3
2023-11-30 | M/S.SHRIYAA ENTERPRISES | 61316.86
2023-11-30 | ADINATH ENTERPRISES | 31920
2023-12-03 | R.K.TRADING CO. | 27300
2023-12-05 | GLOBAL GYPSUM PVT LTD | 249480
2023-12-05 | JSW CEMENT LIMITED | 121875
2023-12-05 | M/S.SHRIYAA ENTERPRISES | 58396.8
2023-12-05 | SHARADA ENTERPRISES | 35533.58
2023-12-05 | SHARADA ENTERPRISES | 63399
2023-12-05 | SHARADA ENTERPRISES | 87318
2023-12-05 | SHARADA ENTERPRISES | 84841.06
2023-12-05 | SHARADA ENTERPRISES | 38550.22
2023-12-07 | M/S.SHRIYAA ENTERPRISES | 76692
2023-12-11 | JSW CEMENT LIMITED | 121875
2023-12-12 | M/S.SHRIYAA ENTERPRISES | 78909.6
2023-12-14 | HARMAN ENGINEERING WORKS | 37937.02
2023-12-15 | M/S.SHRIYAA ENTERPRISES | 109033.58
2023-12-15 | RAJ TRANSIT INFRA PVT LTD | 22611.76
2023-12-18 | M/S.SHRIYAA ENTERPRISES | 57103
2023-12-18 | M/S.SHRIYAA ENTERPRISES | 64167.08
2023-10-10 | WATER PUMP HIRE SERVICE | 10000
2023-10-16 | RAMASHREY PRAJAPATI | 16584
2023-10-16 | RAMASHREY PRAJAPATI | 2064
2023-10-21 | PRABHAKAR C.DUDHBHATE | 200000
2023-11-06 | WATER PUMP HIRE SERVICE | 5000
2023-11-20 | PRABHAKAR C.DUDHBHATE | 300000
2023-12-04 | CHANDULAL GOVIND PATEL | 1000000
2023-12-04 | SHIV PUJAN | 600000
2023-12-04 | RAM BHARAT | 400000
2023-12-04 | SHAMSER KHAN | 700000
2023-12-04 | NIDA MUJEEB SHAIKH | 800000
2023-12-04 | MANOJ KUMAR | 500000
2023-12-05 | WATER PUMP HIRE SERVICE | 5000
2023-12-19 | BHAVANI ENTERPRISES | 200000
2023-10-18 | SHREEJI WATER PUMPS & BOREWELL | 61500
2023-11-09 | AKAR CONSTRUCTION COMPANY | 2500000
2023-12-04 | AKAR CONSTRUCTION COMPANY | 847458
2023-08-31 | AKAR CONSTRUCTION COMPANY | 23600000
2023-08-01 | AJIT KUMAR BOIPAL | 291060
2023-08-02 | DHRUVALAL GAURI PRASAD | 181440
2023-08-03 | GUNARAM BOIPAL | 295680
2023-08-04 | DIPESH GOHIL | 97650
2023-08-05 | SADHU CHARAN BOIPAI | 291060
2023-08-06 | DEVILAL PURTY | 100800
2023-08-07 | ABHINAY KUMAR | 253260
2023-08-09 | ANSARI ATIQ SHAKEEL | 76800
2023-08-10 | SK ANUWAR | 31200
2023-08-11 | RUPAL DILIP TANK | 25200
2023-08-11 | UDAY KUMAR | 151680
2023-08-12 | WATER PUMP HIRE SERVICE | 4332
2023-08-12 | BEHRA GUIYA | 109800
2023-08-16 | RAMASHREY PRAJAPATI | 5976
2023-08-22 | MOHAMMED SHOAIB BHATI | 1250000
2023-08-22 | BHAVESH M SENGHANI | 1250000
2023-09-30 | SAKSHI CORPORATION | 178471.88
2023-09-26 | THE INDIA CEMENTS LIMITED | 111360
2023-09-06 | M/S.SHRIYAA ENTERPRISES | 43540.88
2023-09-15 | SHARADA ENTERPRISES | 97585.96
2023-09-15 | SHARADA ENTERPRISES | 79525.96
2023-09-15 | SHARADA ENTERPRISES | 79206.22
2023-09-15 | SHARADA ENTERPRISES | 81307.8
2023-09-21 | RAJLAXMI CORPORATION | 90147.76
2023-09-28 | M/S.SHRIYAA ENTERPRISES | 56758.28
2023-09-29 | JSW CEMENT LIMITED | 119250
2023-09-30 | ADINATH ENTERPRISES | 23940
2023-09-30 | M/S.SHRIYAA ENTERPRISES | 34934.56
2023-09-30 | RAJLAXMI CORPORATION | 86832.9
2023-09-30 | SHARADA ENTERPRISES | 83197.28
2023-09-30 | SHARADA ENTERPRISES | 89389.66
2023-09-30 | SHARADA ENTERPRISES | 53573.1
2023-09-08 | ANUPAM ELECTRICALS | 10804.08
2023-09-17 | SHREE TECHNOCHEM | 106200
2023-09-23 | ANUPAM ELECTRICALS | 1198.88
2023-09-28 | THE INDIA CEMENTS LIMITED | 489241.6
2024-01-02 | WATER PUMP HIRE SERVICE | 5000
2024-01-10 | ADITYA CRANE SERVICE | 2500
2024-01-15 | WELCOME ENTERPRIESES | 250000
2024-01-15 | PRABHAKAR C.DUDHBHATE | 250000
2024-01-16 | BHAVANI ENTERPRISES | 400000
2024-01-29 | RUDRA PLUMPBING SYSTEM | 500000
2024-02-01 | WATER PUMP HIRE SERVICE | 5000
2024-02-10 | RAMASHREY PRAJAPATI | 14616
2024-02-12 | NIDA MUJEEB SHAIKH | 220800
2024-02-12 | MD ABRAR AHAMAD | 223250
2024-02-12 | KAJAL DAS | 957000
2024-02-12 | FATIMA JAVED SHAIKH | 225000
2024-02-12 | JAVED KATHALU SHAIKH | 220000
2024-02-12 | MUJEEB KHATALU SHAIKH | 250200
2024-02-12 | MD AALIM | 210200
2024-02-12 | MD NIYAZ | 225500
2024-02-12 | CHHOTAN RAY | 234050
2024-02-12 | SABROJ MAUSAM ALI AHMAD | 200500
2024-02-12 | GAURAV BHARAT JABUANI | 500000
2024-02-12 | DHARMENDRAKUMAR BHIMANI | 957000
2024-02-15 | BHAVANI ENTERPRISES | 500000
2024-02-18 | S D ENTERPRISES | 469865
2024-02-19 | HEMANI BHARAT JABUANI | 650000
2024-02-19 | BHAVESH M SENGHANI HUF | 850000
2024-02-19 | MANISHA JITENDRA RAMJIYANI | 650000
2024-03-01 | WATER PUMP HIRE SERVICE | 5000
2024-03-02 | RAMASHREY PRAJAPATI | 7800
2024-03-04 | PANKAJ PAYARCHAND JAIN | 200693
2024-03-13 | SHAIKH MUSHTAQ SHAIKH ISAQ | 220800
2024-03-13 | PREMILABEN VIJAY RAMJIYANI | 576500
2024-03-13 | POOJA D VISHWAKARMA | 216211
2024-03-15 | WELCOME ENTERPRIESES | 400000
2024-03-15 | PRABHAKAR C.DUDHBHATE | 600000
2024-03-15 | S D ENTERPRISES | 499000
2024-03-15 | MD KAMRUL HAK | 292043
2024-03-15 | CHHOTAN RAY | 292043
2024-03-15 | PRAVIND ASHOK KUMAR | 322493
2024-03-15 | ANGAD YADAV | 322493
2024-03-15 | RAVEENDRA KUMAR PRAJAPATI | 322493
2024-03-15 | VISHWANATH RAJKUMAR GUPTA | 322493
2024-03-15 | MANOJ KUMAR | 322493
2024-03-15 | KAJAL DAS | 202467
2024-03-15 | MD NIYAZ | 292043
2024-03-15 | HEMANI BHARAT JABUANI | 600000
2024-03-15 | MUJEEB KHATALU SHAIKH | 508848
2024-03-15 | FATIMA JAVED SHAIKH | 508848
2024-03-15 | BHARAT SOMJI PATEL | 500000
2024-03-15 | SABROJ MAUSAM ALI AHMAD | 200000
2024-03-15 | BHAVANI ENTERPRISES | 500000
2024-03-15 | DHARMENDRAKUMAR BHIMANI | 322493
2024-03-26 | MD AALIM | 223250
2024-03-26 | NIKHIL SHASHIKANT WAGHMARE | 850000
2024-03-31 | HARI OM INTERIOR | 36200
2024-03-31 | MANISHA V PATEL | 35185
2024-03-31 | MANISHA V PATEL | 64569
2024-03-31 | MANISHA V PATEL | 43852
2024-01-15 | AKAR CONSTRUCTION COMPANY | 1271186
2024-02-13 | AKAR CONSTRUCTION COMPANY | 2118644
2024-02-15 | UNITEDONE CONSTRUCTION | 3805084.75
2024-02-22 | TEJVEER ENTERPRISE | 1000000
2024-02-24 | SAMAYPRA INFRA PROJECT PVT LTD | 200693
2024-03-01 | SIDDHIVINAYAKCREATIONS FACADE PVT LTD | 296133.89
2024-03-01 | AVINASH ENTERPRISE | 500000
2024-03-15 | AKAR CONSTRUCTION COMPANY | 4240000
2024-03-15 | UNITEDONE CONSTRUCTION | 8450136
2024-03-21 | AVINASH VISWANATH MENON | 500000
2024-01-01 | SHARADA ENTERPRISES | 64601.6
2024-01-01 | SHARADA ENTERPRISES | 61936
2024-01-08 | UN CORPORATION | 182371.5
2024-01-08 | UN CORPORATION | 169301.44
2024-01-08 | AL-BURHAN SAFETY PRODUCTS | 5040
2024-01-12 | AL-BURHAN SAFETY PRODUCTS | 6440
2024-01-23 | UN CORPORATION | 157106.26
2024-01-25 | M/S.SHRIYAA ENTERPRISES | 61824
2024-02-14 | UN CORPORATION | 146301.18
2024-02-14 | UN CORPORATION | 138270.59
2024-02-15 | UN CORPORATION | 134662.49
2024-02-15 | SHARADA ENTERPRISES | 62720
2024-02-15 | SHARADA ENTERPRISES | 61936
2024-02-22 | UN CORPORATION | 144272.69
2024-03-06 | UN CORPORATION | 183141.01
2024-03-08 | UN CORPORATION | 122607
2024-03-13 | UN CORPORATION | 184680
2024-03-13 | SHARADA ENTERPRISES | 61936
2024-03-13 | R.K.TRADERS | 1680
2024-03-26 | SHARADA ENTERPRISES | 62720
2024-03-26 | SHARADA ENTERPRISES | 31360
2024-03-30 | UN CORPORATION | 164160.01
2024-03-30 | UN CORPORATION | 158388.75
2024-01-11 | UN CORPORATION | 156208.5
2024-01-15 | SHARADA ENTERPRISES | 62596.8
2024-01-22 | UN CORPORATION | 151334.99
2024-01-01 | THE INDIA CEMENTS LIMITED | 75520
2024-01-01 | THE INDIA CEMENTS LIMITED | 113280
2024-01-01 | JANATA SAND SUPPLYING CO. | 1799.94
2024-01-01 | KIRIT TRADING COMPANY | 104832
2024-01-01 | THE INDIA CEMENTS LIMITED | 111360
2024-01-01 | THE INDIA CEMENTS LIMITED | 111360
2024-01-01 | THE INDIA CEMENTS LIMITED | 111360
2024-01-01 | THE INDIA CEMENTS LIMITED | 96512
2024-01-01 | THE INDIA CEMENTS LIMITED | 89088
2024-01-01 | THE INDIA CEMENTS LIMITED | 37120
2024-01-01 | THE INDIA CEMENTS LIMITED | 259840
2024-01-01 | THE INDIA CEMENTS LIMITED | 111360
2024-01-03 | KIRIT TRADING COMPANY | 183680
2024-01-03 | KIRIT TRADING COMPANY | 227763.2
2024-01-04 | KIRIT TRADING COMPANY | 183680
2024-01-07 | KIRIT TRADING COMPANY | 103680
2024-01-07 | KIRIT TRADING COMPANY | 183680
2024-01-09 | SAKSHI CORPORATION | 84800
2024-01-11 | KIRIT TRADING COMPANY | 227763.2
2024-01-11 | KIRIT TRADING COMPANY | 183680
2024-01-11 | KIRIT TRADING COMPANY | 73472
2024-01-12 | KIRIT TRADING COMPANY | 183680
2024-01-12 | KIRIT TRADING COMPANY | 73472
2024-01-17 | JANATA SAND SUPPLYING CO. | 1799.94
2024-01-22 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 91840
2024-01-22 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 91840
2024-01-22 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 91840
2024-01-22 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 91840
2024-02-01 | KARAN ENTERPRISES | 73472
2024-02-05 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 16960
2024-02-05 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 84800
2024-02-06 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 42681.6
2024-02-08 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 145920
2024-02-08 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 145920
2024-02-08 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 91200
2024-02-08 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 91200
2024-02-08 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 91200
2024-02-09 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 91200
2024-02-09 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 18240
2024-02-13 | THE INDIA CEMENTS LIMITED | 99840
2024-02-15 | THE INDIA CEMENTS LIMITED | 101760
2024-02-15 | THE INDIA CEMENTS LIMITED | 111360
2024-02-15 | THE INDIA CEMENTS LIMITED | 111360
2024-02-15 | THE INDIA CEMENTS LIMITED | 111360
2024-02-15 | THE INDIA CEMENTS LIMITED | 111360
2024-02-15 | THE INDIA CEMENTS LIMITED | 111360
2024-02-15 | THE INDIA CEMENTS LIMITED | 111360
2024-02-15 | THE INDIA CEMENTS LIMITED | 74240
2024-02-15 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 16960
2024-02-15 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 84800
2024-02-15 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 91200
2024-02-15 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 91200
2024-02-15 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 91200
2024-02-15 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 91200
2024-02-15 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 91200
2024-02-15 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 91200
2024-02-15 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 91200
2024-02-15 | KIRIT TRADING COMPANY | 72960
2024-02-15 | KIRIT TRADING COMPANY | 72960
2024-02-15 | KIRIT TRADING COMPANY | 72960
2024-02-15 | KIRIT TRADING COMPANY | 145920
2024-02-15 | KIRIT TRADING COMPANY | 72960
2024-02-15 | KIRIT TRADING COMPANY | 109440
2024-02-15 | KIRIT TRADING COMPANY | 109440
2024-02-17 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 54720
2024-02-17 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 18240
2024-02-20 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 16960
2024-02-20 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 84800
2024-02-25 | KIRIT TRADING COMPANY | 72704
2024-02-25 | KIRIT TRADING COMPANY | 72704
2024-02-25 | KIRIT TRADING COMPANY | 72704
2024-02-25 | KIRIT TRADING COMPANY | 72704
2024-02-26 | KIRIT TRADING COMPANY | 159948.8
2024-02-26 | KIRIT TRADING COMPANY | 109056
2024-02-26 | KIRIT TRADING COMPANY | 145408
2024-03-06 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 18112
2024-03-06 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 90560
2024-03-06 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 90560
2024-03-06 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 90560
2024-03-06 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 90560
2024-03-06 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 90560
2024-03-06 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 90560
2024-03-06 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 90560
2024-03-13 | KIRIT TRADING COMPANY | 101760
2024-03-14 | KIRIT TRADING COMPANY | 181120
2024-03-14 | KIRIT TRADING COMPANY | 181120
2024-03-22 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 90560
2024-03-22 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 90560
2024-03-22 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 39846.4
2024-03-23 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 90560
2024-03-23 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 90560
2024-03-23 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 90560
2024-03-23 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 90560
2024-03-23 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 90560
2024-03-23 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 50713.6
2024-03-26 | KARAN ENTERPRISES | 72448
2024-03-30 | THE INDIA CEMENTS LIMITED | 99840
2024-01-01 | JSW CEMENT LIMITED | 121875
2024-01-01 | JANATA SAND SUPPLYING CO. | 7087.5
2024-01-01 | GLOBAL GYPSUM PVT LTD | 231000
2024-01-01 | RAJLAXMI CORPORATION | 90873.3
2024-01-01 | RAJLAXMI CORPORATION | 72066.76
2024-01-01 | RAJLAXMI CORPORATION | 69976.2
2024-01-01 | RAJLAXMI CORPORATION | 72309.82
2024-01-01 | RAJ TRANSIT INFRA PVT LTD | 45760.06
2024-01-01 | SHARADA ENTERPRISES | 97795.96
2024-01-01 | SHARADA ENTERPRISES | 34147.58
2024-01-01 | SHARADA ENTERPRISES | 93750.82
2024-01-01 | SHARADA ENTERPRISES | 92391.08
2024-01-01 | SHARADA ENTERPRISES | 36696.46
2024-01-01 | SHARADA ENTERPRISES | 99740.02
2024-01-01 | SHARADA ENTERPRISES | 79564.28
2024-01-01 | ADINATH ENTERPRISES | 128080.06
2024-01-01 | M/S.SHRIYAA ENTERPRISES | 98621.26
2024-01-02 | H P CORPORATION | 84495.6
2024-01-03 | JSW CEMENT LIMITED | 121875
2024-01-04 | HARMAN ENGINEERING WORKS | 21845.26
2024-01-08 | JSW CEMENT LIMITED | 121875
2024-01-08 | OM ENTERPRISES | 100846.2
2024-01-08 | AL-BURHAN SAFETY PRODUCTS | 71177.4
2024-01-08 | M/S.SHRIYAA ENTERPRISES | 34492.5
2024-01-09 | S.S.ENTERPRISES | 71979.6
2024-01-09 | JANATA SAND SUPPLYING CO. | 9450
2024-01-11 | GLOBAL GYPSUM PVT LTD | 249480
2024-01-12 | AL-BURHAN SAFETY PRODUCTS | 59314.5
2024-01-15 | RAJ TRANSIT INFRA PVT LTD | 23850.76
2024-01-15 | SHARADA ENTERPRISES | 36066.46
2024-01-15 | SHARADA ENTERPRISES | 92373.76
2024-01-15 | SHARADA ENTERPRISES | 26055.76
2024-01-15 | SHARADA ENTERPRISES | 94608.16
2024-01-15 | SHARADA ENTERPRISES | 96256.66
2024-01-15 | ADINATH ENTERPRISES | 98843.86
2024-01-16 | JSW CEMENT LIMITED | 121875
2024-01-18 | M/S.SHRIYAA ENTERPRISES | 100080.76
2024-01-20 | S.S.ENTERPRISES | 33075
2024-01-22 | H P CORPORATION | 93051
2024-01-24 | JSW CEMENT LIMITED | 119250
2024-01-25 | OM ENTERPRISES | 29142.76
2024-01-28 | JSW CEMENT LIMITED | 121875
2024-01-30 | M/S.SHRIYAA ENTERPRISES | 123238.5
2024-02-03 | R.K.TRADING CO. | 20475
2024-02-04 | JANATA SAND SUPPLYING CO. | 9450
2024-02-05 | GLOBAL GYPSUM PVT LTD | 249480
2024-02-09 | JSW CEMENT LIMITED | 124500
2024-02-12 | M/S.SHRIYAA ENTERPRISES | 65394
2024-02-14 | H P CORPORATION | 90669.6
2024-02-15 | H P CORPORATION | 82966.8
2024-02-15 | OM ENTERPRISES | 57918
2024-02-15 | ADINATH ENTERPRISES | 29694
2024-02-15 | SHARADA ENTERPRISES | 91775.26
2024-02-15 | SHARADA ENTERPRISES | 28040.26
2024-02-15 | SHARADA ENTERPRISES | 89286.76
2024-02-15 | SHARADA ENTERPRISES | 92384.26
2024-02-15 | SHARADA ENTERPRISES | 98385
2024-02-15 | SHARADA ENTERPRISES | 81348.76
2024-02-15 | S.S.ENTERPRISES | 85995
2024-02-15 | M/S.SHRIYAA ENTERPRISES | 35059.5
2024-02-15 | M/S.SHRIYAA ENTERPRISES | 22197
2024-02-15 | SHIV ENTERPRISES | 61661.26
2024-02-15 | SHIV ENTERPRISES | 63504
2024-02-15 | SHIV ENTERPRISES | 91966.88
2024-02-15 | RAJLAXMI CORPORATION | 85821.76
2024-02-15 | OM ENTERPRISES | 56358.76
2024-02-15 | M/S.SHRIYAA ENTERPRISES | 26827.5
2024-02-15 | SHARADA ENTERPRISES | 23997.76
2024-02-15 | SHARADA ENTERPRISES | 95828.26
2024-02-15 | SHARADA ENTERPRISES | 29547
2024-02-15 | SHARADA ENTERPRISES | 26643.76
2024-02-17 | S.S.ENTERPRISES | 71376.9
2024-02-18 | M/S.SHRIYAA ENTERPRISES | 37185.76
2024-02-19 | JSW CEMENT LIMITED | 124500
2024-02-21 | JANATA SAND SUPPLYING CO. | 7087.5
2024-02-21 | M/S.SHRIYAA ENTERPRISES | 27268.5
2024-02-29 | SHIV ENTERPRISES | 89822.26
2024-03-03 | JSW CEMENT LIMITED | 124500
2024-03-05 | GLOBAL GYPSUM PVT LTD | 249480
2024-03-06 | H P CORPORATION | 84054.6
2024-03-13 | SHARADA ENTERPRISES | 33831
2024-03-13 | SHARADA ENTERPRISES | 93812.26
2024-03-13 | SHARADA ENTERPRISES | 69363
2024-03-13 | SHARADA ENTERPRISES | 72812.26
2024-03-13 | SHARADA ENTERPRISES | 84259.36
2024-03-13 | H P CORPORATION | 95167.8
2024-03-13 | OM ENTERPRISES | 28995.76
2024-03-13 | SHIV ENTERPRISES | 98610.76
2024-03-13 | SHIV ENTERPRISES | 92510.26
2024-03-13 | SHIV ENTERPRISES | 69977.26
2024-03-13 | SHIV ENTERPRISES | 22895.26
2024-03-13 | CHIRAG ENTERPRISES | 28628.26
2024-03-13 | ADINATH ENTERPRISES | 58763.26
2024-03-15 | ADINATH ENTERPRISES | 29032.5
2024-03-18 | M/S.SHRIYAA ENTERPRISES | 22197
2024-03-26 | SHARADA ENTERPRISES | 91518
2024-03-26 | SHARADA ENTERPRISES | 29988
2024-03-26 | SHARADA ENTERPRISES | 95371.52
2024-03-26 | SHARADA ENTERPRISES | 64149.76
2024-03-26 | SHARADA ENTERPRISES | 51228.46
2024-03-27 | M/S.SHRIYAA ENTERPRISES | 83223
2024-03-30 | GLOBAL GYPSUM PVT LTD | 249480
2024-03-30 | JSW CEMENT LIMITED | 124500
2024-03-30 | M/S.SHRIYAA ENTERPRISES | 63598.5
2024-03-30 | OM ENTERPRISES | 69205.5
2024-03-31 | OM ENTERPRISES | 70434
2024-03-30 | SHREEJI WOODCRAFT PVT LTD | 866812.07
2024-03-30 | SHREEJI WOODCRAFT PVT LTD | 79501.32
2024-03-30 | SHREEJI WOODCRAFT PVT LTD | 398335.1
2024-03-30 | SHREEJI WOODCRAFT PVT LTD | 664797.84
2024-01-01 | ANUPAM ELECTRICALS | 7611
2024-01-01 | VEDANT MARKETING | 102837
2024-01-01 | VEDANT MARKETING | 32284.8
2024-01-01 | HITECH CONSTRUCTIONS AND REPAIRS | 43660
2024-01-01 | R.K.TRADING CO. | 7080
2024-01-03 | KARRMANYA ENTERPRISE | 761241.6
2024-01-03 | KARRMANYA ENTERPRISE | 45916.16
2024-01-05 | VEDANT MARKETING | 32284.8
2024-01-06 | KARRMANYA ENTERPRISE | 370829.16
2024-01-08 | UN CORPORATION | 19500
2024-01-08 | AL-BURHAN SAFETY PRODUCTS | 22854.24
2024-01-08 | ANUPAM ELECTRICALS | 10856
2024-01-08 | AQUA ENVIRONMENTAL ENGINEERS | 212400
2024-01-09 | SUSHMA CONTRUCTION STEEL SALES LLP | 1945447.12
2024-01-09 | KRISHNA TRADING CORPORATION | 62955.36
2024-01-09 | VEDANT MARKETING | 82446.6
2024-01-09 | KARRMANYA ENTERPRISE | 339915.52
2024-01-11 | UN CORPORATION | 19500
2024-01-11 | KRISHNA TRADING CORPORATION | 79591
2024-01-12 | KARRMANYA ENTERPRISE | 15406.08
2024-01-12 | AL-BURHAN SAFETY PRODUCTS | 48406.56
2024-01-13 | KARRMANYA ENTERPRISE | 86099.88
2024-01-15 | CHANDRAKANT ELECTRICAL & CONTRACTOR | 984903.04
2024-01-15 | CHANDRAKANT ELECTRICAL & CONTRACTOR | 742085.48
2024-01-16 | SUSHMA CONTRUCTION STEEL SALES LLP | 2011810.32
2024-01-16 | VEDANT MARKETING | 61879.2
2024-01-18 | BAADSHAH STEEL | 419372
2024-01-18 | R.K.TRADERS | 7646.4
2024-01-20 | S.S.ENTERPRISES | 56050
2024-01-21 | SUSHMA CONTRUCTION STEEL SALES LLP | 2002948.52
2024-01-22 | UN CORPORATION | 19500
2024-01-22 | KARRMANYA ENTERPRISE | 3600
2024-01-22 | KARRMANYA ENTERPRISE | 397991.58
2024-01-23 | KARRMANYA ENTERPRISE | 13520
2024-01-23 | UN CORPORATION | 19500
2024-01-23 | VEDANT MARKETING | 82446.6
2024-01-24 | KARRMANYA ENTERPRISE | 875071.48
2024-01-27 | BAADSHAH STEEL | 801220
2024-02-03 | S.S.ENTERPRISES | 56050
2024-02-05 | TEJAS CERAMICS | 20699.56
2024-02-06 | SUSHMA CONTRUCTION STEEL SALES LLP | 2007155.22
2024-02-10 | KARRMANYA ENTERPRISE | 66890.66
2024-02-13 | SUSHMA CONTRUCTION STEEL SALES LLP | 2077451.36
2024-02-14 | UN CORPORATION | 19500
2024-02-14 | UN CORPORATION | 19500
2024-02-15 | VEDANT MARKETING | 108465.6
2024-02-15 | KRISHNA TRADING CORPORATION | 91119.6
2024-02-15 | KRISHNA CERAMICS | 18054
2024-02-15 | MEHTA PLYWOOD | 26998.4
2024-02-15 | BAADSHAH STEEL | 1183540
2024-02-15 | GLOBAL GYPSUM PVT LTD | 14160
2024-02-19 | SUSHMA CONTRUCTION STEEL SALES LLP | 65914.8
2024-02-19 | SUSHMA CONTRUCTION STEEL SALES LLP | 2003229.36
2024-02-20 | VEDANT MARKETING | 102837
2024-02-20 | KARRMANYA ENTERPRISE | 19420.44
2024-02-22 | UN CORPORATION | 19500
2024-02-26 | KRISHNA TRADING CORPORATION | 64696.46
2024-02-28 | SUSHMA CONTRUCTION STEEL SALES LLP | 2106618.6
2024-03-04 | TEJAS CERAMICS | 90999.53
2024-03-04 | VEDANT MARKETING | 102837
2024-03-06 | UN CORPORATION | 19500
2024-03-08 | UN CORPORATION | 19500
2024-03-09 | SUSHMA CONTRUCTION STEEL SALES LLP | 2072080
2024-03-13 | UN CORPORATION | 19500
2024-03-13 | S.S.ENTERPRISES | 56050
2024-03-13 | BECS COATING | 8354.4
2024-03-13 | KARRMANYA ENTERPRISE | 15360.06
2024-03-13 | KARRMANYA ENTERPRISE | -1593
2024-03-13 | KARRMANYA ENTERPRISE | -69241.22
2024-03-13 | SKY TELECOM | 19765
2024-03-13 | SKY TELECOM | 26756.5
2024-03-13 | SKY TELECOM | 4484
2024-03-13 | KARRMANYA ENTERPRISE | 21594
2024-03-14 | D.R LINKS | 111598.5
2024-03-15 | CHANDRAKANT ELECTRICAL & CONTRACTOR | 880939.72
2024-03-15 | CHANDRAKANT ELECTRICAL & CONTRACTOR | 934228
2024-03-15 | KARRMANYA ENTERPRISE | 7767.94
2024-03-15 | TEJAS CERAMICS | 12600
2024-03-15 | KARRMANYA ENTERPRISE | 74525.26
2024-03-17 | SUSHMA CONTRUCTION STEEL SALES LLP | 2122142.68
2024-03-19 | KARRMANYA ENTERPRISE | 315151.34
2024-03-26 | VEDANT MARKETING | 123227.4
2024-03-30 | KRISHNA TRADING CORPORATION | 159300
2024-03-30 | UN CORPORATION | 9749.99
2024-03-30 | UN CORPORATION | 9749.99
2024-03-30 | GLOBAL GYPSUM PVT LTD | 33984
2024-03-30 | KRISHNA TRADING CORPORATION | 42214.5
2024-03-31 | SUSHMA CONTRUCTION STEEL SALES LLP | 2080349.44
2024-03-31 | H V ENTERPRISE | 185257.06
2024-03-31 | DILIP PAINT & HARDWARE STORES | 72134.58
2024-04-04 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 179200
2024-04-13 | JANATA SAND SUPPLYING CO. | 1799.94
2024-04-14 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 16832
2024-04-14 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 84160
2024-04-14 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 181120
2024-04-20 | THE INDIA CEMENTS LIMITED | 65664
2024-04-21 | THE INDIA CEMENTS LIMITED | 102144
2024-04-21 | THE INDIA CEMENTS LIMITED | 102144
2024-04-21 | THE INDIA CEMENTS LIMITED | 102144
2024-04-21 | THE INDIA CEMENTS LIMITED | 109440
2024-04-21 | THE INDIA CEMENTS LIMITED | 109440
2024-04-21 | THE INDIA CEMENTS LIMITED | 109440
2024-04-21 | THE INDIA CEMENTS LIMITED | 102144
2024-05-07 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 89600
2024-05-07 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 89600
2024-05-07 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 89600
2024-05-07 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 89600
2024-05-12 | KIRIT TRADING COMPANY | 250880
2024-05-12 | KIRIT TRADING COMPANY | 179200
2024-05-13 | WEATHER COOL SERVICES | 210000.02
2024-05-15 | KIRIT TRADING COMPANY | 176000
2024-05-15 | KIRIT TRADING COMPANY | 176000
2024-05-16 | ZEE ELECTRONICS | 41499.12
2024-05-16 | KARAN ENTERPRISES | 97920
2024-05-21 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 176000
2024-05-21 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 176000
2024-05-21 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 176000
2024-05-24 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 176000
2024-05-24 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 176000
2024-05-25 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 176000
2024-05-26 | SUNTREK CORPORATION | 35200
2024-05-26 | SUNTREK CORPORATION | 70400
2024-05-28 | THE INDIA CEMENTS LIMITED | 105600
2024-05-31 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 87040
2024-05-31 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 87040
2024-05-31 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 87040
2024-05-31 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 87040
2024-04-02 | JSW CEMENT LIMITED | 124500
2024-04-03 | R.K.TRADING CO. | 37170
2024-04-08 | M/S.SHRIYAA ENTERPRISES | 36842.4
2024-04-10 | SHIV ENTERPRISES | 76826.4
2024-04-15 | M/S.SHRIYAA ENTERPRISES | 57173.56
2024-04-15 | CHIRAG ENTERPRISES | 26739.3
2024-04-15 | NEER TRADING CO. | 64921.5
2024-04-15 | S. H. ENTERPRISES | 92628.38
2024-04-15 | S. H. ENTERPRISES | 74457.6
2024-04-15 | S. H. ENTERPRISES | 32886
2024-04-16 | AL-BURHAN SAFETY PRODUCTS | 2850.06
2024-04-17 | M/S.SHRIYAA ENTERPRISES | 27239.1
2024-04-25 | SHIV ENTERPRISES | 29400
2024-04-25 | SHIV ENTERPRISES | 79468.2
2024-04-27 | SHIV ENTERPRISES | 25168.5
2024-04-28 | GLOBAL GYPSUM PVT LTD | 249480
2024-04-30 | NEER TRADING CO. | 35945.7
2024-04-30 | SHARADA ENTERPRISES | 59103.46
2024-04-30 | S. H. ENTERPRISES | 95241.82
2024-04-30 | S. H. ENTERPRISES | 57959.48
2024-04-30 | S. H. ENTERPRISES | 81312
2024-05-11 | M/S.SHRIYAA ENTERPRISES | 33824.7
2024-05-11 | NEER TRADING CO. | 115483.2
2024-05-14 | JSW CEMENT LIMITED | 127125
2024-05-15 | NEER TRADING CO. | 62781.6
2024-05-15 | S. H. ENTERPRISES | 85564.5
2024-05-15 | S. H. ENTERPRISES | 88384.8
2024-05-15 | S. H. ENTERPRISES | 91030.8
2024-05-15 | S. H. ENTERPRISES | 53904.9
2024-05-15 | OM ENTERPRISES | 144391.8
2024-05-18 | M/S.SHRIYAA ENTERPRISES | 57460.2
2024-05-20 | JSW CEMENT LIMITED | 127125
2024-05-25 | NEER TRADING CO. | 121371.6
2024-05-29 | GLOBAL GYPSUM PVT LTD | 249480
2024-05-31 | NEER TRADING CO. | 62178.9
2024-05-31 | SHARADA ENTERPRISES | 80797.5
2024-05-31 | SHARADA ENTERPRISES | 88580.1
2024-05-31 | SHARADA ENTERPRISES | 83382.6
2024-05-31 | SHARADA ENTERPRISES | 78409.8
2024-05-31 | SHARADA ENTERPRISES | 80864.7
2024-05-31 | SHARADA ENTERPRISES | 98548.8
2024-05-31 | SHARADA ENTERPRISES | 22041.6
2024-05-31 | OM ENTERPRISES | 126774.9
2024-04-15 | UN CORPORATION | 191092.49
2024-04-15 | S. H. ENTERPRISES | 62720
2024-04-15 | S. H. ENTERPRISES | 62328
2024-04-16 | UN CORPORATION | 164160.01
2024-04-16 | AL-BURHAN SAFETY PRODUCTS | 12019.84
2024-04-24 | R.K.TRADING CO. | 3360
2024-05-11 | UN CORPORATION | 152360.4
2024-05-24 | UN CORPORATION | 166724.4
2024-05-27 | UN CORPORATION | 169290
2024-04-01 | DILIP PAINT & HARDWARE STORES | 73949.42
2024-04-01 | SMT POOJA C. SHAH | 5900
2024-04-02 | KRISHNA TRADING CORPORATION | 94164
2024-04-03 | KARRMANYA ENTERPRISE | 125438.72
2024-04-03 | KARRMANYA ENTERPRISE | 8500.72
2024-04-04 | HEM ENTERPRISE | 188800
2024-04-05 | KRISHNA CERAMICS | 212400
2024-04-06 | KRISHNA TRADING CORPORATION | 93810
2024-04-06 | VEDANT MARKETING | 123227.4
2024-04-12 | D.R LINKS | 38444.4
2024-04-12 | D.R LINKS | 15222
2024-04-12 | D.R LINKS | 3026.7
2024-04-12 | Siddhivinayak Electrical & Hardware | 126006.3
2024-04-15 | DINESH ENTERPRISES | 408971.43
2024-04-15 | UN CORPORATION | 9749.99
2024-04-15 | S.S.ENTERPRISES | 28320
2024-04-16 | UN CORPORATION | 9749.99
2024-04-16 | AL-BURHAN SAFETY PRODUCTS | 67293.04
2024-04-18 | SUSHMA CONTRUCTION STEEL SALES LLP | 2210999.04
2024-04-22 | KARRMANYA ENTERPRISE | 23348.66
2024-04-23 | UNIQUE SPACE INTERIOR | 590000
2024-04-23 | KRISHNA TRADING CORPORATION | 125888.3
2024-04-24 | JONES LANG LASALLE PROPERTY CONSULTANTS INDIA PVT | 759299.32
2024-04-24 | R.K.TRADING CO. | 118
2024-04-25 | KARRMANYA ENTERPRISE | 2024.88
2024-04-25 | KRISHNA CERAMICS | 3658
2024-04-27 | SAMAYPRA INFRA PROJECT PVT LTD | 531817.74
2024-04-30 | D.R LINKS | 55412.8
2024-04-30 | D.R LINKS | 2076.8
2024-05-01 | AVINASH ENTERPRISE | 590000
2024-05-01 | SMT POOJA C. SHAH | 5900
2024-05-03 | NAVBHARAT HARDWARE STORES | 75661.6
2024-05-04 | TEJAS CERAMICS | 4200.22
2024-05-04 | SKY TELECOM | 65136
2024-05-07 | LANDMARK CONSULTANTS & ENGG. TECHNOLOGY | 9912
2024-05-07 | D.R LINKS | 34043
2024-05-08 | SKY TELECOM | 37406
2024-05-10 | WEATHER COOL SERVICES | 20698
2024-05-11 | VEDANT MARKETING | 51684
2024-05-11 | UN CORPORATION | 19500
2024-05-12 | SUSHMA CONTRUCTION STEEL SALES LLP | 2222237.36
2024-05-13 | CHANDRAKANT ELECTRICAL & CONTRACTOR | 481419.36
2024-05-13 | D.R LINKS | 9227.6
2024-05-15 | AKAR CONSTRUCTION COMPANY | 4999999.84
2024-05-15 | ROYAL GLASS HOUSE | 160000.16
2024-05-15 | HITECH CONSTRUCTIONS AND REPAIRS | 98884
2024-05-15 | KRISHNA TRADING CORPORATION | 34302.6
2024-05-15 | KRISHNA TRADING CORPORATION | 56864.2
2024-05-16 | ZEE ELECTRONICS | 15000.01
2024-05-16 | RAJ ALUMINIUM | 295944
2024-05-16 | KRISHNA TRADING CORPORATION | 18755.8
2024-05-16 | D.R LINKS | 83308
2024-05-17 | GYPSO INDIA | 708000.04
2024-05-18 | SUSHMA CONTRUCTION STEEL SALES LLP | 2336154.56
2024-05-18 | D.R LINKS | 56647.08
2024-05-18 | R.K.TRADERS | 4012
2024-05-20 | SUSHMA CONTRUCTION STEEL SALES LLP | 2185280.94
2024-05-21 | VEDANT MARKETING | 123227.4
2024-05-23 | NAVBHARAT HARDWARE STORES | 8466.5
2024-05-24 | S.S.ENTERPRISES | 28320
2024-05-24 | UN CORPORATION | 19500
2024-05-27 | UN CORPORATION | 19500
2024-05-30 | KRISHNA TRADING CORPORATION | 9442.36
2024-05-30 | KRISHNA TRADING CORPORATION | 140869
2024-05-31 | AXLER WOODWORKS LLP | 224206.99
2024-06-02 | SUNTREK CORPORATION | 70400
2024-06-02 | SUNTREK CORPORATION | 26048
2024-06-02 | SUNTREK CORPORATION | 26048
2024-06-02 | SUNTREK CORPORATION | 24640
2024-06-02 | SUNTREK CORPORATION | 70400
2024-06-02 | SUNTREK CORPORATION | 70400
2024-06-02 | SUNTREK CORPORATION | 1408
2024-06-09 | SUNTREK CORPORATION | 23674.88
2024-06-09 | SUNTREK CORPORATION | 69632
2024-06-09 | SUNTREK CORPORATION | 69632
2024-06-09 | SUNTREK CORPORATION | 34816
2024-06-09 | SUNTREK CORPORATION | 69632
2024-06-09 | SUNTREK CORPORATION | 34816
2024-06-10 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 172800
2024-06-10 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 172800
2024-06-10 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 172800
2024-06-11 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 17280
2024-06-11 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 86400
2024-06-22 | THE INDIA CEMENTS LIMITED | 103680
2024-06-22 | THE INDIA CEMENTS LIMITED | 86400
2024-06-22 | THE INDIA CEMENTS LIMITED | 79488
2024-06-22 | THE INDIA CEMENTS LIMITED | 76032
2024-06-02 | JSW CEMENT LIMITED | 127125
2024-06-08 | JSW CEMENT LIMITED | 127125
2024-06-13 | NEER TRADING CO. | 53726.4
2024-06-15 | S. H. ENTERPRISES | 78733.2
2024-06-15 | S. H. ENTERPRISES | 88993.8
2024-06-15 | S. H. ENTERPRISES | 85457.4
2024-06-15 | S. H. ENTERPRISES | 81471.6
2024-06-15 | S. H. ENTERPRISES | 80973.9
2024-06-15 | S. H. ENTERPRISES | 92366.4
2024-06-15 | S. H. ENTERPRISES | 95904.9
2024-06-15 | S. H. ENTERPRISES | 90098.4
2024-06-15 | S. H. ENTERPRISES | 25872
2024-06-15 | JSW CEMENT LIMITED | 127125
2024-06-15 | S.S.ENTERPRISES | 84577.5
2024-06-29 | JSW CEMENT LIMITED | 127125
2024-06-29 | R.K.TRADING CO. | 25725
2024-06-30 | SHARADA ENTERPRISES | 76251
2024-06-30 | SHARADA ENTERPRISES | 25200
2024-06-05 | UN CORPORATION | 126711
2024-06-30 | SHARADA ENTERPRISES | 62720
2024-06-01 | VEDANT MARKETING | 123227.4
2024-06-01 | SMT POOJA C. SHAH | 5900
2024-06-03 | SUSHMA CONTRUCTION STEEL SALES LLP | 2162524.64
2024-06-04 | R.R. ENTERPRISES | 1982.4
2024-06-05 | UN CORPORATION | 11699.99
2024-06-07 | P.R.CRAFT AND DESIGN | 143770.31
2024-06-08 | SUSHMA CONTRUCTION STEEL SALES LLP | 2239055.9
2024-06-08 | P.R.CRAFT AND DESIGN | 258271.6
2024-06-10 | D.R LINKS | 83072
2024-06-10 | P.R.CRAFT AND DESIGN | 235585.58
2024-06-11 | SUSHMA CONTRUCTION STEEL SALES LLP | 2062134.96
2024-06-11 | P.R.CRAFT AND DESIGN | 117400.85
2024-06-11 | H V ENTERPRISE | 9345.6
2024-06-13 | VEDANT MARKETING | 61879.2
2024-06-15 | D.R LINKS | 11682
2024-06-15 | KARRMANYA ENTERPRISE | 71732.99
2024-06-16 | KRISHNA TRADING CORPORATION | 41111.2
2024-06-18 | ANUPAM ELECTRICALS | 1121
2024-06-19 | SHREEJI WATER PUMPS & BOREWELL | 100300
2024-06-19 | JONES LANG LASALLE PROPERTY CONSULTANTS INDIA PVT | 1938138.2
2024-06-19 | DILIP PAINT & HARDWARE STORES | 61776.54
2024-06-21 | S.S.ENTERPRISES | 28320
2024-06-23 | SUSHMA CONTRUCTION STEEL SALES LLP | 2028381.06
2024-06-23 | KRISHNA TRADING CORPORATION | 18691.2
2024-06-25 | KRISHNA TRADING CORPORATION | 3635.58
2024-06-29 | KRISHNA TRADING CORPORATION | 36698
2024-06-30 | NAVBHARAT HARDWARE STORES | 37099.2
326774057.24

## Professional
SR.NO | PARTICULARS | NATURE | DATE | TOTAL AMOUNT
| MEHTA & CO. | LEGAL AND PROFESSIONAL FEES | 2020-01-10 | 2000000
| S.J.ASSOCIATES | LEGAL AND PROFESSIONAL FEES | 2020-01-23 | 44800
| S.J.ASSOCIATES | LEGAL AND PROFESSIONAL FEES | 2021-03-19 | 37800
| S.J.ASSOCIATES | LEGAL AND PROFESSIONAL FEES | 2021-04-08 | 8850
| GEOTECH ENTERPRISES | LEGAL AND PROFESSIONAL FEES | 2021-10-22 | 115640
| ROHAN ENVIRO ASSOSIATES | LEGAL AND PROFESSIONAL FEES | 2022-03-17 | 796500
| Manish Kumar V.Bagsariya | LEGAL AND PROFESSIONAL FEES | 2022-03-30 | 900000
| Nidhin Narayan Pillai | LEGAL AND PROFESSIONAL FEES | 2022-03-30 | 1400000
| Abdulla M.Baig | LEGAL AND PROFESSIONAL FEES | 2022-03-30 | 900000
| S.J.ASSOCIATES | LEGAL AND PROFESSIONAL FEES | 2022-07-09 | 10030
| ENGARC ASSOCIATS | LEGAL AND PROFESSIONAL FEES | 2022-08-24 | 88500
| RAGHOBA BHAGWAN GOVEKAR | LEGAL AND PROFESSIONAL FEES | 2022-10-10 | 60000
| ROHAN ENVIRO ASSOSIATES | LEGAL AND PROFESSIONAL FEES | 2022-12-01 | 177000
| ROHAN ENVIRO ASSOSIATES | LEGAL AND PROFESSIONAL FEES | 2022-12-01 | 708000
| ENVIRO ENGINEERING SERVICES | LEGAL AND PROFESSIONAL FEES | 2022-12-01 | 59000
| RAGHOBA BHAGWAN GOVEKAR | LEGAL AND PROFESSIONAL FEES | 2023-01-12 | 104000
| RAGHOBA BHAGWAN GOVEKAR | LEGAL AND PROFESSIONAL FEES | 2023-01-16 | 100000
| DARSHANA INDULKAR | LEGAL AND PROFESSIONAL FEES | 2023-02-02 | 230000
| SHIVMOHAN B.JHA | LEGAL AND PROFESSIONAL FEES | 2023-02-06 | 118000
| SHALAKA D.SATHE | LEGAL AND PROFESSIONAL FEES | 2023-03-03 | 1000000
| NILOFER ABDULLA BAIG | LEGAL AND PROFESSIONAL FEES | 2023-03-03 | 1000000
| RAGHOBA BHAGWAN GOVEKAR | LEGAL AND PROFESSIONAL FEES | 2023-03-20 | 170000
| SWATI RAGHOBA GOVEKAR | LEGAL AND PROFESSIONAL FEES | 2023-03-20 | 360000
| ROHAN ENVIRO ASSOSIATES | LEGAL AND PROFESSIONAL FEES | 2023-03-28 | 177000
| VASTUKAL CONSULTANTS (I) PVT LTD | LEGAL AND PROFESSIONAL FEES | 2023-05-18 | 413000
| VASTUKAL CONSULTANTS (I) PVT LTD | LEGAL AND PROFESSIONAL FEES | 2023-05-18 | 135700
| CRISIL Ratings Ltd. | LEGAL AND PROFESSIONAL FEES | 2023-05-23 | 318600
| AJIT SURVEYORS | LEGAL AND PROFESSIONAL FEES | 2023-07-18 | 24000
| Professional fees |  |  | 285965
| PROFESSIONAL CHARGES - WITH GST | OTHER EXPENSES |  | 5900
| VASTUKAL CONSULTANTS (I) PVT LTD | LEGAL AND PROFESSIONAL FEES- WITH GST | 2023-05-09 | 88500
| PROFESSIONAL FEES OF C.A. |  | 2023-12-01 | 5900
| PROFESSIONAL FEES OF C.A. |  | 2023-12-01 | 29500
| TESTING CHARGES |  | 2023-10-01 | 11100
| TESTING CHARGES |  | 2023-11-09 | 6300
| TESTING CHARGES |  | 2023-04-12 | 49800
| TESTING CHARGES |  | 2023-05-09 | 1350
| TESTING CHARGES |  | 2023-09-08 | 10800
| TESTING CHARGES |  | 2023-09-08 | 5400
| PROFESSIONAL FEES OF C.A. | OTHER EXPENSES |  | 104000
| KASHMIRA K PATEL | LEGAL AND PROFESSIONAL FEES | 2024-03-20 | 1000000
| Abdulla M.Baig | LEGAL AND PROFESSIONAL FEES | 2024-03-20 | 1900000
| SHAILESH C AKBARI | LEGAL AND PROFESSIONAL FEES | 2024-03-20 | 1900000
| SHALAKA D.SATHE | LEGAL AND PROFESSIONAL FEES | 2024-03-20 | 1000000
| PRAGNA J PATEL | LEGAL AND PROFESSIONAL FEES | 2024-03-20 | 1000000
| NILOFER ABDULLA BAIG | LEGAL AND PROFESSIONAL FEES | 2024-03-20 | 1000000
| MIT J PATEL | LEGAL AND PROFESSIONAL FEES | 2024-03-20 | 1000000
| Manish Kumar V.Bagsariya | LEGAL AND PROFESSIONAL FEES | 2024-03-20 | 1900000
| Nidhin Narayan Pillai | LEGAL AND PROFESSIONAL FEES | 2024-03-20 | 1900000
| KAUSHIK B PATEL | LEGAL AND PROFESSIONAL FEES | 2024-03-20 | 1900000
| VASTUKAL CONSULTANTS (I) PVT LTD | LEGAL AND PROFESSIONAL FEES | 2024-06-06 | 41300
| VASTUKAL CONSULTANTS (I) PVT LTD | LEGAL AND PROFESSIONAL FEES | 2024-06-06 | 41300
| CRISIL Ratings Ltd. | LEGAL AND PROFESSIONAL FEES | 2024-06-06 | 207680
| LANDMARK CONSULTANTS & ENGG. TECHNOLOGY | TESTING CHARGES |  | 8400
TOTAL |  |  |  | 26859615

## MArketing
SR.NO | PARTICULARS | NATURE | DATE | TOTAL AMOUNT
| MINESH N. SHAH (LOAN) |  | 2021-08-03 | 500
| STAMP DUTY | OTHER EXPENSES |  | 2518200
| COMMISSION AND BROKERAGE | OTHER EXPENSES |  | 552100
| STAMP DUTY | OTHER EXPENSES |  | 6110500
| COMMISSION AND BROKERAGE | OTHER EXPENSES |  | 1016728
| STAMP DUTY |  | 2023-05-29 | 493000
| STAMP DUTY |  | 2023-05-29 | 330800
| STAMP DUTY |  | 2023-05-29 | 334000
| STAMP DUTY |  | 2023-05-29 | 330800
| STAMP DUTY |  | 2023-06-28 | 1284600
| STAMP DUTY |  | 2023-06-28 | 1267200
| STAMP DUTY |  | 2023-06-28 | 469100
| STAMP DUTY |  | 2023-06-28 | 1491200
| STAMP DUTY |  | 2023-06-28 | 1008400
| STAMP DUTY |  | 2023-07-06 | 1238100
| STAMP DUTY |  | 2023-07-06 | 1291700
| STAMP DUTY |  | 2023-07-13 | 1104900
| STAMP DUTY |  | 2023-07-27 | 1018400
| STAMP DUTY |  | 2023-07-31 | 30000
| STAMP DUTY |  | 2023-08-19 | 1794000
| STAMP DUTY |  | 2023-08-21 | 2301500
| STAMP DUTY |  | 2023-08-21 | 2015000
| STAMP DUTY |  | 2023-09-08 | 1066300
| STAMP DUTY |  | 2023-09-08 | 1451900
| STAMP DUTY |  | 2023-10-10 | 1736200
| STAMP DUTY |  | 2023-10-10 | 1277100
| STAMP DUTY |  | 2023-10-10 | 698100
| STAMP DUTY |  | 2023-10-16 | 30000
| STAMP DUTY |  | 2023-10-19 | 30000
| STAMP DUTY |  | 2023-11-01 | 1068300
| STAMP DUTY |  | 2023-11-09 | 1277100
| STAMP DUTY |  | 2023-11-09 | 1282200
| STAMP DUTY |  | 2023-11-10 | 1262600
| STAMP DUTY |  | 2023-11-16 | 1220600
| STAMP DUTY |  | 2023-11-16 | 1245500
| STAMP DUTY |  | 2023-12-04 | 1773000
| STAMP DUTY |  | 2023-12-21 | 1311500
| COMMISSION AND BROKERAGE |  |  | 3661666
| STAMP DUTY & REGISTRATION FEE | OTHER EXPENSES |  | 10480860
| COMMISSION AND BROKERAGE | OTHER EXPENSES |  | 3297796
| COMMISSION AND BROKERAGE |  |  | 1642490
| STAMP DUTY & REGISTRATION FEE |  |  | 1874000
| ADVERTISEMENT EXPENSES |  |  | 202500
| COMMISSION AND BROKERAGE |  |  | 583140
| COMMISSION AND BROKERAGE |  |  | 643474
| COMMISSION AND BROKERAGE |  |  | 475800
| COMMISSION AND BROKERAGE |  |  | 400000
| COMMISSION AND BROKERAGE |  |  | 382020
| COMMISSION AND BROKERAGE |  |  | 390970
| COMMISSION AND BROKERAGE |  |  | 636400
| STAMP DUTY & REGISTRATION FEE |  |  | 1893000
| STAMP DUTY & REGISTRATION FEE |  |  | 1279700
| STAMP DUTY & REGISTRATION FEE |  |  | 1550500
| STAMP DUTY & REGISTRATION FEE |  |  | 1251130
| STAMP DUTY & REGISTRATION FEE |  |  | 1298300
| STAMP DUTY & REGISTRATION FEE |  |  | 1800000
| STAMP DUTY & REGISTRATION FEE |  |  | 1264800
| STAMP DUTY & REGISTRATION FEE |  |  | 1442300
| STAMP DUTY & REGISTRATION FEE |  |  | 1245000
TOTAL |  |  |  | 82426974

## Admin
SR.NO | PARTICULARS | NATURE | INVOICE NO | DATE | TOTAL AMOUNT
| WATER CHARGES |  |  | 2023-01-03 | 27500
| WATER CHARGES |  |  | 2023-01-03 | 27500
| WATER CHARGES |  |  | 2023-01-03 | 27500
| A1 STAR TRANSPORT | TRANSPORT CHARGES |  | 2021-01-09 | 4200
| A1 STAR TRANSPORT | TRANSPORT CHARGES |  | 2021-12-15 | 2400
| SGST OUTWARD REVERSE CHARGE | TRANSPORT CHARGES |  | 2022-03-31 | 120
| SWASTIK ENTERPRISES | TRANSPORT CHARGES |  | 2023-03-21 | 12000
| NEW NATIONAL MOTOR TRANSPORT CO. | TRANSPORT CHARGES |  | 2023-03-24 | 18000
| SWASTIK ENTERPRISES | TRANSPORT CHARGES |  | 2023-03-31 | 10000
| CGST INPUT REVERSE CHARGE | TRANSPORT CHARGES |  | 2023-03-31 | 2000
| SHREE KRISHNA TRANSPORT | TRANSPORT CHARGES |  | 2023-04-04 | 130800
| ANUPAM ELECTRICALS | TRANSPORT CHARGES |  | 2023-04-06 | 6300
| GAURI TRANSPORT | TRANSPORT CHARGES |  | 2023-05-15 | 20978
| A1 STAR TRANSPORT | TRANSPORT CHARGES |  | 2023-06-06 | 11000
| A1 STAR TRANSPORT | TRANSPORT CHARGES |  | 2023-07-08 | 20000
| ADANI ELECTRICITY | ELECTRICITY CHARGES |  | 2022-06-09 | 5470
| ADANI ELECTRICITY | ELECTRICITY CHARGES |  | 2022-09-23 | 27390
| ADANI ELECTRICITY | ELECTRICITY CHARGES |  | 2022-09-28 | 7500
| ADANI ELECTRICITY | ELECTRICITY CHARGES |  | 2022-11-02 | 2430
| ADANI ELECTRICITY | ELECTRICITY CHARGES |  | 2022-12-19 | 2730
| ADANI ELECTRICITY | ELECTRICITY CHARGES |  | 2023-02-02 | 3450
| ADANI ELECTRICITY | ELECTRICITY CHARGES |  | 2023-03-13 | 29190
| ADANI ELECTRICITY | ELECTRICITY CHARGES |  | 2023-04-07 | 4960
| ADANI ELECTRICITY | ELECTRICITY CHARGES |  | 2023-05-19 | 144700
| ADANI ELECTRICITY | ELECTRICITY CHARGES |  | 2023-05-19 | 22660
| ADANI ELECTRICITY | ELECTRICITY CHARGES |  | 2023-07-27 | 114850
| K.L.PATHAK | SECURITY SERVICES | KLP/23/08 | 2023-04-13 | 40000
| K.L.PATHAK | SECURITY SERVICES | KLP/23/039 | 2023-06-06 | 40000
| K.L.PATHAK | SECURITY SERVICES | KLP/23/068 | 2023-06-08 | 40000
| COOLIE & CARTAGE EXP |  |  |  | 240500
| LATE FILING FEES |  |  |  | 200
| MOTORCAR EXPENSES |  |  |  | 56532
| REOAIR & MAINTENANCE CHARGES |  |  |  | 2520
| REPAIR AND MAINTENACE CHARGES |  |  |  | 4500
| SALARY |  |  |  | 779879
| TESTING CHARGES |  |  |  | 51150
| WELFARE EXPENSES |  |  | 2023-04-02 | 5150
| office Rent expenses |  |  |  | 265000
| Gernal expenses |  |  |  | 85743
| others |  |  |  | 148571
| ELECTRICITY CHARGES |  |  | 2023-08-07 | 238640
| ELECTRICITY CHARGES |  |  | 2023-08-07 | 47300
| K.L.PATHAK | SECURITY CHARGES |  | 2023-04-08 | 44333
| PUJARI TRANSPORT | TRANSPORT CHARGES |  | 2023-07-08 | 20792
| PUJARI TRANSPORT | TRANSPORT CHARGES |  | 2023-11-08 | 17186
| BANK CHARGES | OTHER EXPENSES |  |  | 1010660.8
| COOLIE & CARTAGE EXP | OTHER EXPENSES |  |  | 176772
| Labour Charges | OTHER EXPENSES |  |  | 4415938
| LOAN PROCESING CHARGES | OTHER EXPENSES |  |  | 10976596
| OFFICE RENT EXPENSES | OTHER EXPENSES |  |  | 5000
| REPAIR & MAINTENANCE CHARGES | OTHER EXPENSES |  |  | 8850
| ELECTRICITY CHARGES |  |  | 2023-09-21 | 82350
| ELECTRICITY CHARGES |  |  | 2023-09-21 | 61990
| ELECTRICITY CHARGES |  |  | 2023-09-27 | 24820
| ELECTRICITY CHARGES |  |  | 2023-09-27 | 143508
| A1 STAR TRANSPORT | TRANSPORT CHARGES |  | 2023-01-09 | 1000
| A1 STAR TRANSPORT | TRANSPORT CHARGES |  | 2023-01-09 | 26000
| K.L.PATHAK | SECURITY SERVICES |  | 2023-01-09 | 49032
| BANK CHARGES | OTHER EXPENSES |  |  | 25101
| COOLIE AND CARTAGE | OTHER EXPENSES |  |  | 25101
| OFFICE RENT CHARGES | OTHER EXPENSES |  |  | 5000
| WELFARE EXPENSES | OTHER EXPENSES |  | 2023-09-01 | 3600
| DONATION |  |  |  | 15000
| BANK CHARGES | OTHER EXPENSES |  |  | 2594.16
| COMMISSION AND BROKERAGE | OTHER EXPENSES |  |  | 2092838
| MOTOR CAR EXPENSES | OTHER EXPENSES |  |  | 18844
| OFFICE RENT EXPENSES | OTHER EXPENSES |  |  | 5000
| FILLING FEES | OTHER EXPENSES |  |  | 400
| LATE FILING FEES | OTHER EXPENSES |  |  | 8450
| RERA APPLICATION FEES | OTHER EXPENSES |  |  | 8386.6
| PROPERTY TAX |  |  | 2023-10-25 | 773667
| PROPERTY TAX |  |  | 2023-10-25 | 29597
| WELFARE EXPENSES |  |  | 2023-10-01 | 4500
| WELFARE EXPENSES |  |  | 2023-11-01 | 2700
| SECURITY SERVICES |  | KLP/23/0127 | 2023-10-16 | 52333
| SECURITY SERVICES |  | KLP/23/0152 | 2023-11-01 | 52258
| SECURITY SERVICES |  | KLP/23/0172 | 2023-12-01 | 50000
| CHANDRAKANT ELECTRICAL & CONTRACTOR | TRANSPORT CHARGES | 05 | 2023-10-09 | 480
| A1 STAR TRANSPORT | TRANSPORT CHARGES | 573 | 2023-10-16 | 1000
| NAIDU TRANSPORT | TRANSPORT CHARGES | 99 | 2023-11-07 | 700000
| VAISHALI ENTERPRISES | TRANSPORT CHARGES | 12 | 2023-11-08 | 700000
| SHREE KRISHNA TRANSPORT | TRANSPORT CHARGES | 101 | 2023-11-08 | 700000
| A1 STAR TRANSPORT | TRANSPORT CHARGES | 585 | 2023-11-08 | 1000
| ELECTRICITY CHARGES |  |  | 2023-10-23 | 64580
| ELECTRICITY CHARGES |  |  | 2023-10-23 | 83200
| ELECTRICITY CHARGES |  |  | 2023-12-26 | 188300
| COOLIE & CARTAGE EXP |  |  | 2023-10-10 | 60209
| COOLIE & CARTAGE EXP |  |  | 2023-10-10 | 115800
| COOLIE & CARTAGE EXP |  |  | 2023-11-08 | 107241
| COOLIE & CARTAGE EXP |  |  | 2023-12-20 | 129300
| BANK CHARGES | OTHER EXPENSES |  |  | 2594.16
| COMMISSION AND BROKERAGE | OTHER EXPENSES |  |  | 2092838
| MOTOR CAR EXPENSES | OTHER EXPENSES |  |  | 18844
| OFFICE RENT EXPENSES | OTHER EXPENSES |  |  | 5000
| FILLING FEES | OTHER EXPENSES |  |  | 400
| LATE FILING FEES | OTHER EXPENSES |  |  | 8450
| RERA APPLICATION FEES | OTHER EXPENSES |  |  | 8386.6
| SALARY |  |  | 2023-05-08 | 44700
| SALARY |  |  | 2023-05-08 | 37900
| SALARY |  |  | 2023-05-08 | 83150
| SALARY |  |  | 2023-05-11 | 4060
| SALARY |  |  | 2023-05-11 | 34493
| SALARY |  |  | 2023-05-11 | 23550
| SALARY |  |  | 2023-06-01 | 44700
| SALARY |  |  | 2023-06-01 | 37900
| SALARY |  |  | 2023-06-01 | 83150
| SALARY |  |  | 2023-06-01 | 20300
| SALARY |  |  | 2023-06-01 | 39800
| SALARY |  |  | 2023-06-01 | 23550
| SALARY |  |  | 2023-06-01 | 23226
| SALARY |  |  | 2023-07-01 | 44700
| SALARY |  |  | 2023-07-01 | 37900
| SALARY |  |  | 2023-07-01 | 83150
| SALARY |  |  | 2023-07-01 | 20300
| SALARY |  |  | 2023-07-01 | 39800
| SALARY |  |  | 2023-07-01 | 23550
| SALARY |  |  | 2023-07-01 | 30000
| SALARY |  |  | 2023-08-01 | 44700
| SALARY |  |  | 2023-08-01 | 37900
| SALARY |  |  | 2023-08-01 | 83150
| SALARY |  |  | 2023-08-01 | 20300
| SALARY |  |  | 2023-08-01 | 39800
| SALARY |  |  | 2023-08-01 | 23550
| SALARY |  |  | 2023-08-01 | 30000
| SALARY |  |  | 2023-08-17 | 65000
| SALARY |  |  | 2023-09-01 | 65000
| SALARY |  |  | 2023-09-01 | 44700
| SALARY |  |  | 2023-09-01 | 83150
| SALARY |  |  | 2023-09-01 | 20300
| SALARY |  |  | 2023-09-01 | 39800
| SALARY |  |  | 2023-09-01 | 23550
| SALARY |  |  | 2023-09-18 | 37900
| SALARY |  |  | 2023-10-03 | 65000
| SALARY |  |  | 2023-10-03 | 44700
| SALARY |  |  | 2023-10-03 | 37900
| SALARY |  |  | 2023-10-03 | 83150
| SALARY |  |  | 2023-10-03 | 20300
| SALARY |  |  | 2023-10-03 | 39800
| SALARY |  |  | 2023-10-03 | 23550
| SALARY |  |  | 2023-11-01 | 65000
| SALARY |  |  | 2023-11-01 | 44700
| SALARY |  |  | 2023-11-01 | 37900
| SALARY |  |  | 2023-11-01 | 83150
| SALARY |  |  | 2023-11-01 | 39800
| SALARY |  |  | 2023-11-01 | 23550
| SALARY |  |  | 2023-11-01 | 5323
| SALARY |  |  | 2023-12-01 | 37900
| SALARY |  |  | 2023-12-01 | 23550
| SALARY |  |  | 2023-12-01 | 65000
| SALARY |  |  | 2023-12-01 | 44700
| SALARY |  |  | 2023-12-01 | 83150
| SALARY |  |  | 2023-12-01 | 39800
| SALARY |  |  | 2023-12-01 | 15000
| BANK CHARGES |  |  |  | 35810
| General Expenses |  |  |  | 17700
| MOTOR CAR EXPENSES |  |  |  | 113064
| OFFICE RENT EXPENSES |  |  |  | 35000
| Printing & Stationary |  |  |  | 6240
| WELFARE EXPENSES |  |  | 2023-07-01 | 5890
| WELFARE EXPENSES |  |  | 2023-05-01 | 23360
| K.L.PATHAK | SECURITY SERVICES |  | 2023-10-16 | 52333
| K.L.PATHAK | SECURITY SERVICES |  | 2023-11-01 | 52258
| K.L.PATHAK | SECURITY SERVICES |  | 2023-12-01 | 50000
| Insurance Charges |  |  |  | 912207
| CGST FEES | SALES & ADMINISTRATIVE EXPENSES |  |  | 375
| Company Professional Tax -PTEC | SALES & ADMINISTRATIVE EXPENSES |  |  | 5000
| INTERNET CHARGES | SALES & ADMINISTRATIVE EXPENSES |  |  | 9200
| RERA APPLICATION FEES | SALES & ADMINISTRATIVE EXPENSES |  |  | 50082.6
| SALARY | SALES & ADMINISTRATIVE EXPENSES |  |  | 1403980
| SGST FEES | SALES & ADMINISTRATIVE EXPENSES |  |  | 375
| SUNDRY BALANCE W/OFF (NET) | SALES & ADMINISTRATIVE EXPENSES |  |  | 10.45
| GENERAL EXPENSES | OTHER EXPENSES |  |  | 7300
| MOTOR CAR EXPENSES | OTHER EXPENSES |  |  | 37688
| OFFICE RENT EXPENSES | OTHER EXPENSES |  |  | 15000
| BANK CHARGES | OTHER EXPENSES |  |  | 1989.11
| M.P.WATER SUPPLIER | WELFARE EXPENSES |  | 2024-03-27 | 11700
| K.L.PATHAK | SECURITY SERVICES |  | 2024-01-08 | 50000
| K.L.PATHAK | SECURITY SERVICES |  | 2024-02-15 | 50000
| K.L.PATHAK | SECURITY SERVICES |  | 2024-03-13 | 50000
| A1 STAR TRANSPORT | TRANSPORT CHARGES |  | 2024-01-01 | 6000
| A1 STAR TRANSPORT | TRANSPORT CHARGES |  | 2024-01-08 | 4000
| CHANDRAKANT ELECTRICAL & CONTRACTOR | TRANSPORT CHARGES |  | 2024-01-15 | 3200
| CHANDRAKANT ELECTRICAL & CONTRACTOR | TRANSPORT CHARGES |  | 2024-01-15 | 1850
| K R ENTERPRISES | TRANSPORT CHARGES |  | 2024-02-01 | 120400
| K R ENTERPRISES | TRANSPORT CHARGES |  | 2024-02-01 | 94600
| A1 STAR TRANSPORT | TRANSPORT CHARGES |  | 2024-02-15 | 21200
| VAISHALI ENTERPRISES | TRANSPORT CHARGES |  | 2024-02-15 | 234000
| K R ENTERPRISES | TRANSPORT CHARGES |  | 2024-03-01 | 47300
| K R ENTERPRISES | TRANSPORT CHARGES |  | 2024-03-01 | 94600
| CHANDRAKANT ELECTRICAL & CONTRACTOR | TRANSPORT CHARGES |  | 2024-03-15 | 1850
| CHANDRAKANT ELECTRICAL & CONTRACTOR | TRANSPORT CHARGES |  | 2024-03-15 | 1850
| A1 STAR TRANSPORT | TRANSPORT CHARGES |  | 2024-03-27 | 5000
| SANKET TRANSPORT | TRANSPORT CHARGES |  | 2024-03-28 | 29800
| SANKET TRANSPORT | TRANSPORT CHARGES |  | 2024-03-28 | 29000
| SHREE KRISHNA ENTERPRISES | TRANSPORT CHARGES |  | 2024-03-30 | 221100
| A1 STAR TRANSPORT | TRANSPORT CHARGES |  | 2024-03-31 | 3000
| ELECTRICITY CHARGES |  |  | 2024-01-05 | 27832
| ELECTRICITY CHARGES |  |  | 2024-01-05 | 38965
| ELECTRICITY CHARGES |  |  | 2024-01-05 | 38965
| ELECTRICITY CHARGES |  |  | 2024-01-11 | 300190
| ELECTRICITY CHARGES |  |  | 2024-01-16 | 94880
| ELECTRICITY CHARGES |  |  | 2024-03-11 | 265530
| ELECTRICITY CHARGES |  |  | 2024-03-22 | 266630
| ELECTRICITY CHARGES |  |  | 2024-03-22 | 175500
| VAIBHAV KISAN SUTAR | COOLIE & CARTAGE EXP |  | 2024-01-24 | 233307
| VAIBHAV KISAN SUTAR | COOLIE & CARTAGE EXP |  | 2024-02-29 | 207860
| VAIBHAV KISAN SUTAR | COOLIE & CARTAGE EXP |  | 2024-03-27 | 175858
| INSURANCE CHARGES |  |  | 2024-01-04 | 20390
| CH.NO 071475 AMOUNT PAID RAHUL V KANOJIYA FOR SALARY MONTH OF MAY 2024 |  |  |  | 51000
| CH.NO 071476 SALARY PAID AJAYKUMAR JIVANBHAI PATEL FOR SALARY MONTH OF MAY 2024 |  |  |  | 75750
| CH.NO 071476 AMOUNT PAID SAIFALIKHAN ANEES FOR SALARY MONTH OF MAY 2024 |  |  |  | 51500
| CH.NO 071476 AMOUNT PAID GANESH G.KAMBLE FOR SALARY MONTH OF MAY 2024 |  |  |  | 84500
| CH.NO 071476 AMOUNT PAID ANIKET BANSHRAJ SINGH FOR SALARY MONTH OF MAY 2024 |  |  |  | 51500
| CH.NO 071476 AMOUNT PAID DIPESH R DHAKAL FOR SALARY MONTH OF MAY 2024 |  |  |  | 27250
| CH.NO 071476 AMOUNT PAID NEERAJ YADAV FOR SALARY MONTH OF MAY 2024 |  |  |  | 20500
| CH.NO 071476 AMOUNT PAID MOHAMMED ISRAN RAR FOR SALARY MONTH OF MAY 2024 |  |  |  | 31000
| CH.NO 071476 AMOUNT PAID SACHIN ASHOK PIWHAL FOR SALARY MONTH OF MAY 2024 |  |  |  | 17000
| PTEC |  |  |  | 2500
| BANK CHARGES |  |  |  | 460.2
| OFFICE RENT EXPENSES |  |  |  | 5000
| ELECTRICITY CHARGES |  |  |  | 215630
| ELECTRICITY CHARGES |  |  |  | 90950
| ELECTRICITY CHARGES |  |  |  | 7610
| COOLIE & CARTAGE EXP |  |  |  | 105615
| WELFARE EXPENSES |  |  |  | 17400
| CH.NO 071468 AMOUNT PAID RAHUL V KANOJIYA FOR SALARY MONTH OF APRIL 2024 |  |  | 2024-05-04 | 51000
| CH.NO 071469 SALARY PAID AJAYKUMAR JIVANBHAI PATEL FOR SALARY MONTH OF APRIL 2024 |  |  | 2024-05-04 | 75750
| CH.NO 071469 AMOUNT PAID SAIFALIKHAN ANEES FOR SALARY MONTH OF APRIL 2024 |  |  | 2024-05-04 | 51500
| CH.NO 071469 AMOUNT PAID GANESH G.KAMBLE FOR SALARY MONTH OF APRIL 2024 |  |  | 2024-05-04 | 84500
| CH.NO 071469 AMOUNT PAID ANIKET BANSHRAJ SINGH FOR SALARY MONTH OF APRIL 2024 |  |  | 2024-05-04 | 51500
| CH.NO 071469 AMOUNT PAID DIPESH R DHAKAL FOR SALARY MONTH OF APRIL 2024 |  |  | 2024-05-04 | 27250
| CH.NO 071469 AMOUNT PAID NEERAJ YADAV FOR SALARY MONTH OF APRIL 2024 |  |  | 2024-05-04 | 20500
| CH.NO 071469 AMOUNT PAID MOHAMMED ISRAN RAR FOR SALARY MONTH OF APRIL 2024 |  |  | 2024-05-04 | 31000
| CH.NO 071218 AMOUNT PAID SACHIN ASHOK PIWHAL FOR SALARY MONTH OF APRIL 2024 |  |  | 2024-05-08 | 17000
| BANK CHARGES | OTHER EXPENSES |  |  | 1420.72
| GENERAL EXPENSES | OTHER EXPENSES |  |  | 12900
| MOTOR CAR EXPENSES | OTHER EXPENSES |  |  | 18844
| OFFICE RENT EXPENSES | OTHER EXPENSES |  |  | 10000
| PROPERTY TAX |  |  |  | 145988
| PROPERTY TAX |  |  |  | 3816066
| WELFARE EXPENSES |  |  |  | 10440
| VAIBHAV KISAN SUTAR | COOLIE & CARTAGE EXP |  |  | 99482
| K.L.PATHAK | SECURITY SERVICES |  |  | 77000
TOTAL |  |  |  |  | 41539260.4

## Interest
Sr. No. | Month | Interest Amount
| 31/-8/23 | 326663
| 30/09/23 | 1614621
1 | 2023-10-01 | 1771561
| 2023-11-01 | 1820958
| 2023-12-01 | 1965871
| 2024-01-01 | 2065940
| 2024-02-01 | 2178946
| 2024-03-01 | 2675909
| 2024-04-01 | 2861346
| 2024-05-01 | 3047941
| 2024-06-01 | 2950811
23280567

## Construction Area Statement (4)
AMENITY BUILDING No. 2
Sr. No. | Floor | Total Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | Percentage of work completed | Actual Expenditure till date in ` | Sr. No. | Building | Total Construction Area in Sq. M. | Cost of Construction | % of work completed | Actual Expenditure till date in `
1 | Excavation & Piling Work | 10% of Construction Cost of Building |  |  | 5554035 | 100% | 5554035 | 1 | Amenity Building No. 2 | 2057.05 | 61094385 | 100% | 61094385
2 | Ground | 476.44 | 476.44 | 27000 | 12863880 | 100% | 12863880 | 2 | Rehab Building No. 1 | 12066.9356 | 358387987.2 | 10.49% | 37596995.52
3 | 1st | 508.48 | 508.48 | 27000 | 13728960 | 100% | 13728960 | 3 | Sale Building | 30990.9475 | 1022701268 | 38.8% | 396782674
4 | 2nd | 508.48 | 508.48 | 27000 | 13728960 | 100% | 13728960 |  | Sub Total (A) | 45114.9331 | 1442183640.2 | 34.36% | 495474054.52
5 | 3rd | 508.48 | 508.48 | 27000 | 13728960 | 100% | 13728960 | 4 | Puzzle Parking of Rehab Building in No. | 131 | 65500000 | 0% | 0
6 | OHT / LMR | 55.17 | 55.17 | 27000 | 1489590 | 100% | 1489590 | 5 | Puzzle Parking of Sale Building in No. | 300 | 150000000 | 0% | 0
TOTAL COST OF CONSTRUCTION |  | 2057.05 | 2057.05 |  | 61094385 | 100% | 61094385 |  | Sub Total (B) | 431 | 215500000 | 0% | 0
[8 empty] | Total Cost of Construction (A + B) |  |  | 1657683640.2 | 29.89% | 495474054.52
REHAB BUILDING No. 1
Sr. No. | Floor | Total Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | Percentage of work completed | Actual Expenditure till date in `
| Excavation & Piling Work | 10% of Construction Cost of Building |  |  | 32580726 | 100% | 32580726
1 | Ground | 464.4694 |  | 27000 | 12540673.8 | 40% | 5016269.52
2 | 1st | 478.0194 |  | 27000 | 12906523.8 |  | 0
3 | 2nd | 486.6394 |  | 27000 | 13139263.8 |  | 0
4 | 3rd | 505.0894 |  | 27000 | 13637413.8 |  | 0
5 | 4th | 505.0894 |  | 27000 | 13637413.8 |  | 0
6 | 5th | 505.0894 |  | 27000 | 13637413.8 |  | 0
7 | 6th | 505.0894 |  | 27000 | 13637413.8 |  | 0
8 | 7th | 505.0894 |  | 27000 | 13637413.8 |  | 0
9 | 8th | 505.0894 |  | 27000 | 13637413.8 |  | 0
10 | 9th | 505.0894 |  | 27000 | 13637413.8 |  | 0
11 | 10th | 505.0894 |  | 27000 | 13637413.8 |  | 0
12 | 11th | 505.0894 |  | 27000 | 13637413.8 |  | 0
13 | 12th | 505.0894 |  | 27000 | 13637413.8
14 | 13th | 505.0894 |  | 27000 | 13637413.8 |  | 0
15 | 14th | 505.0894 |  | 27000 | 13637413.8 |  | 0
16 | 15th | 505.0894 |  | 27000 | 13637413.8 |  | 0
17 | 16th | 505.0894 |  | 27000 | 13637413.8 |  | 0
18 | 17th | 505.0894 |  | 27000 | 13637413.8 |  | 0
19 | 18th | 505.0894 |  | 27000 | 13637413.8 |  | 0
20 | 19th | 505.0894 |  | 27000 | 13637413.8 |  | 0
21 | 20th | 505.0894 |  | 27000 | 13637413.8 |  | 0
22 | 21st | 505.0894 |  | 27000 | 13637413.8 |  | 0
23 | 22nd | 505.0894 |  | 27000 | 13637413.8 |  | 0
24 | 23rd | 505.0894 |  | 27000 | 13637413.8 |  | 0
25 | OHT / LMR | 30.93 |  | 27000 | 835110 |  | 0
Sub - Total (A) |  | 12066.9356 | 0 |  | 358387987.2 | 10.49% | 37596995.52
PUZZLE PARKING Nos. (B) |  | 131 |  | 500000 | 65500000 |  | 0
TOTAL COST OF CONSTRUCTION (A + B) |  |  |  |  | 423887987.2 | 8.87% | 37596995.52
SALE BUILDING
Sr. No. | Floor | Total Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | Percentage of work completed | Actual Expenditure till date in `
| Excavation & Piling Work | 10% of Construction Cost of Building |  |  | 92972843 | 50% | 46486421.5
1 | Ground | 1877.0625 | 1877.0625 | 30000 | 56311875 | 90% | 50680687.5
2 | 1st | 1877.0587 | 938.5294 | 30000 | 56311762.5 | 70% | 39418233.75
3 | 2nd | 1877.0587 | 938.5294 | 30000 | 56311762.5 | 50% | 28155881.25
4 | 3rd | 1771.1225 | 885.5612 | 30000 | 53133675 | 50% | 26566837.5
5 | 4th | 1654.655 | 827.3275 | 30000 | 49639650 | 60% | 29783790
6 | 5th | 1484.685 | 1484.685 | 30000 | 44540550 | 70% | 31178385
7 | 6th | 1484.685 | 1484.685 | 30000 | 44540550 | 70% | 31178385
8 | 7th | 1484.685 | 1484.685 | 30000 | 44540550 | 60% | 26724330
9 | 8th | 1468.395 | 1468.395 | 30000 | 44051850 | 50% | 22025925
10 | 9th | 1484.685 | 1484.685 | 30000 | 44540550 | 50% | 22270275
11 | 10th | 1484.685 | 1484.685 | 30000 | 44540550 | 50% | 22270275
12 | 11th | 1484.685 | 1484.685 | 30000 | 44540550 | 45% | 20043247.5
13 | 12th | 1484.685 |  | 30000 | 44540550 |  | 0
14 | 13th | 1484.685 |  | 30000 | 44540550 |  | 0
15 | 14th | 1484.685 |  | 30000 | 44540550 |  | 0
16 | 15th | 1498.465 |  | 30000 | 44953950 |  | 0
17 | 16th | 1484.685 |  | 30000 | 44540550 |  | 0
18 | 17th | 1484.685 |  | 30000 | 44540550 |  | 0
19 | 18th | 1484.685 |  | 30000 | 44540550 |  | 0
20 | 19th | 990.59 |  | 30000 | 29717700 |  | 0
21 | OHT / LMR | 160.32 |  | 30000 | 4809600 |  | 0
Sub - Total (A) |  | 30990.9475 | 15843.515 |  | 1022701268 | 38.8% | 396782674
PUZZLE PARKING Nos. (B) |  | 300 |  | 500000 | 150000000 |  | 0
TOTAL COST OF CONSTRUCTION (A + B) |  |  |  |  | 1172701268 | 33.83% | 396782674