## Sheet1
Sr. No. | Particulars | Estimate Amount as per Cost Vetting Report | Actual Percentage work completed as on 26.07.2024 | Actual Amount to be incurred as on 26.07.2024 | Remark
1 | RCC Construction of Staff Quarters followed by brickwork, plastering, windows and doors | 2336400 | 80% | 1869120 | RCC slab, brickwork & plaster work is completed.
Windows & Doors work is Pending.
2 | RCC Construction of Office Room followed by brickwork, plastering, windows and doors | 376420 | 80% | 301136 | RCC slab, brickwork & plaster work is completed.
Windows & Doors work is Pending.
3 | Plinth levelling and Backfilling | 2548800 | 100% | 2548800 | Work Completed.
4 | Retaining Wall | 1411575 | 100% | 1411575 | Work Completed.
5 | RCC Construction of Electrical Room followed by brickwork, plastering, windows and doors | 531000 | 80% | 424800 | RCC slab, brickwork & plaster work is completed.
Windows & Doors work is Pending.
6 | RCC Construction of Toilet Blocks followed by brickwork, plastering, windows and doors, Tiling work upto 9 ft. | 377600 | 70% | 264320 | RCC slab, brickwork & plaster work is completed.
Flooring, Windows & Doors work is Pending.
7 | Attached Toilets | 89680 | 0% | 0 | Work not started yet
8 | Solar Panel | 129800 | 0% | 0 | Work not started yet
9 | Electrical Work | 143650 | 0% | 0 | Work not started yet
Total |  | 7944925 |  | 6819751