## Summary
Project expenses | Incurred Cost as on 30.06.2024 in ` | To be Incurred Cost in ` | Total Cost (` in Cr.) | Total in `
Land Cost | 0.72408 | 0 | 0.72408 | 7240750 | 1.1019
Rent Cost | 1.42 | 4.2792 | 5.6992 | 56992000 | 8.6727
Construction Cost for Rehab cum Sale Building | 0.1097 | 34.7728 | 34.8825 | 348824935 | 53.0823 | 0.3145%
Approval Cost | 12.3183 | 1.6678 | 13.9861 | 139861175 | 21.2833
Professional Charges | 0.2848 | 1.4593 | 1.7441 | 17441247 | 2.6541
Admin Cost | 0.0489 | 2.044 | 2.0929 | 20929496 | 3.1849
Marketing Cost | 0 | 1.5386 | 1.5386 | 15385504 | 2.3413
Interest Cost | 0 | 4 | 4 | 40000000 | 6.087 | Give the confirmation
Contingency Cost | 0 | 1.0465 | 1.0465 | 10464748 | 1.5925
Total Cost | 14.9058 | 50.8082 | 65.714 | 657139855 | 100
Particulars | No. of Units | Total Carpet Area in Sq. Ft. | Rate in ` | Mkt. Value in ` | Received Amount in ` | Receivable Amount in `
Unsold Flat | 58 | 28369.706 | 21000 | 595763826.84 | 0 | 0
Proposed Unsold Flat | 16 | 8262.4464 | 21000 | 173511374.4
Tenant Flat | 32 | 17648.9773 | 0 | 0 | 0 | 0
Total | 106 | 54281.1298 |  | 769275201.24 | 0 | 0
Total Income from Sale in Cr. |  |  |  | 76.9275 | 0 | 0
Particulars | Amount ( ` in Cr.)
Gross Estimated Revenue | 76.9275
Less: Total projected Expenses | 65.714
Estimated Surplus | 11.2135
Project Cost and Developer Profit
Developer Profit @ 30% of estimated surplus | 3.36
Net Surplus (3-4) | 7.8535
PV (discounted @ 8% for 4 years) | 5.7726
Add:
Expenses already incurred as on date | 14.9058
(as per the certified Trial Balance Sheet of the project)
Less: | 0
Present Value of the project potential as on Date | 20.6784
The realizable value of the property | 18.6105
Distress value of the property | 16.5427

## Land & Stamp Duty & Rent Cost
Land Cost Description
Sr. No. | Date | Document Name | Description | Total Cost | Incurred Cost | Sr. | Particulars |  | Unit
1 | 28.08.2023 | Developer Agreement | Stamp Duty | 7205050 | 7205050 | 1 | No. of Tenants | 32 | Nos.
2 |  |  | Reg. Fees | 30000 | 30000 | 2 | Rent per Month per tenant (1st Year) | 25000 | Rupees
3 |  |  |  | 4400 | 4400 | 3 | Rent for 12 months (1st Year) | 9600000 | Rupees
4 | 28.08.2023 | Power of Attorney Agreement | Stamp Duty | 500 | 500 | 4 | Rent per Month per tenant (2nd Year) | 26000 | Rupees
5 |  |  | Reg. Fees | 100 | 100 | 5 | Rent for 12 months (2nd Year) | 9984000 | Rupees
6 |  |  |  | 700 | 700 | 6 | Rent per Month per tenant (3rd Year) | 27000 | Rupees
Total |  |  |  | 7240750 | 7240750 | 7 | Rent for 12 months (3rd Year) | 10368000 | Rupees
[6 empty] | 8 | Hardship Cost per tenant | 800000 | Rupees
[6 empty] | 9 | Total Hardship Cost | 25600000 | Rupees
[6 empty] | 10 | Shifting Charges per Tenant | 20000 | Rupees
[6 empty] | 11 | Total Shifting Charges per Tenant | 640000 | Rupees
[6 empty] | 12 | Brokerage Cost per tenant | 25000 | Rupees
[6 empty] | 13 | Total Brokerage Cost | 800000 | Rupees
[6 empty] | Total Rent Cost (3 + 5 + 7 + 9) |  | 56992000 | Rupees

## Approval Cost
Sr. No. | Particulars | Estimated Cost (Rs.)
1 | Scrutiny Fees | 12100
2 | BMC | 47200
3 | BMC Regal Apartment | 114841
4 | BMC for Sewerage | 96314
5 | Duty of DOC Voluntarily Tax | 7205050
6 | NOC Proposed Fees | 5530
7 | BMC Building Permission Cell | 49648416
8 | Labour Charge | 15800860
9 | Assistant Accounts Officer / Mumbai Board | 65928994
10 | Fire Service Fees | 127400
11 | Fire NOC | 874470
Total |  | 139861175

## Construction Area
COST OF CONSTRUCTION
Sr. No | Floors | Built Up Area in Sq. M. | Staircase Area in Sq. M. | Other Area in Sq. M. | Refuge Area in Sq. M. | Parking Tower in Sq. M. | Total Area in Sq. M.
1 | Part Basement Floor | 0 | 64.79 | 208.8103 | 0 | 55.352 | 328.9523
2 | Ground Floor | 2.87 | 64.79 | 267.74 | 0 | 68.2001 | 403.6001
3 | 1st Floor | 179.88 | 64.79 | 90.73 | 0 | 68.2001 | 403.6001
4 | 2nd Floor | 270.61 | 62.17 | 0 | 0 | 68.2001 | 400.9801 | -2.62
5 | 3rd Floor | 270.61 | 62.17 | 0 | 0 | 68.2001 | 400.9801
6 | 4th Floor | 270.61 | 62.17 | 0 | 0 | 68.2001 | 400.9801
7 | 5th Floor | 270.61 | 62.17 | 0 | 0 | 68.2001 | 400.9801
8 | 6th Floor | 270.61 | 62.17 | 0 | 0 | 68.2001 | 400.9801
9 | 7th Floor | 270.61 | 62.17 | 0 | 0 | 68.2001 | 400.9801
10 | 8th Floor | 198.16 | 62.17 | 0 | 73.16 | 68.2001 | 401.6901
11 | 9th Floor | 270.61 | 62.17 | 0 | 0 | 68.2001 | 400.9801
12 | 10th Floor | 270.61 | 62.17 | 0 | 0 | 68.2001 | 400.9801
13 | 11th Floor | 270.61 | 62.17 | 0 | 0 | 68.2001 | 400.9801
14 | 12th Floor | 270.61 | 62.17 | 0 | 0 | 68.2001 | 400.9801
15 | 13th Floor | 270.61 | 62.17 | 0 | 0 | 68.2001 | 400.9801
16 | 14th Floor | 270.61 | 62.17 | 0 | 0 | 68.2001 | 400.9801
17 | 15th Floor | 218.81 | 62.17 | 0 | 52.51 | 68.2001 | 401.6901
18 | 16th Floor | 270.61 | 62.17 | 0 | 0 | 68.2001 | 400.9801
19 | 17th Floor | 270.61 | 62.17 | 0 | 0 | 68.2001 | 400.9801
20 | 18th Floor | 270.61 | 62.17 | 0 | 0 | 68.2001 | 400.9801
21 | 19th Floor | 270.61 | 62.17 | 0 | 0 | 68.2001 | 400.9801
22 | 20th Floor | 270.61 | 62.17 | 0 | 0 | 68.2001 | 400.9801
23 | 21st Floor | 270.61 | 62.17 | 0 | 0 | 68.2001 | 400.9801
24 | 22nd Floor | 270.61 | 63.74 | 0 | 0 | 68.2001 | 402.5501
25 | Terrace | 0 | 0 | 63.74 | 0 | 68.2001 | 131.9401
Total |  | 5741.31 | 1501.51 | 631.0203 | 125.67 | 1692.1544 | 9691.6647 | 104321.0788
No. of Stack Car Parking | [6 empty] | 58
Rate per Sq. M. for Cost of Construction | [6 empty] | 30000
Rate per Stack Car Parking | [6 empty] | 500000
Cost of Construction | [6 empty] | 290749941
Cost of Stack Car Parking | [6 empty] | 29000000
Cost of Deep Excavation & Piling (10% of COC) | [6 empty] | 29074994
Total Cost of Construction | [6 empty] | 348824935

## Area Statement
Sr. No. | Floor No. | Flat No. | Comp. | RERA Carpet Area (in Sq. M.) | RERA Carpet Area (in Sq. Ft.) | Built - Up Area (in Sq. Ft.) | Sold / Unsold / Tenant Inventory List
1 | Basement |  | Tank | 0 | 0 | 0 | Tank
2 | Ground Floor |  | Meter Room | 0 | 0 | 0 | Meter Room
3 | Ground Floor |  | Society Office | 0 | 0 | 0 | Society Office
4 | 1st Floor | 101 | Fitness Centre | 0 | 0 | 0 | Fitness Centre
5 | 1st Floor | 102 | Fitness Centre | 0 | 0 | 0 | Fitness Centre
6 | 1st Floor | 103 | 2 BHK | 51.25 | 551.655 | 606.8205 | Tenant
7 | 1st Floor | 104 | 2 BHK | 51.18 | 550.9015 | 605.9917 | Tenant
8 | 1st Floor | 105 | 2 BHK | 51.28 | 551.9779 | 607.1757 | Tenant
9 | 2nd Floor | 201 | 1 BHK | 41.42 | 445.8449 | 490.4294 | Unsold
10 | 2nd Floor | 202 | 1 BHK | 40.71 | 438.2024 | 482.0227 | Unsold
11 | 2nd Floor | 203 | 2 BHK | 51.25 | 551.655 | 606.8205 | Tenant
12 | 2nd Floor | 204 | 2 BHK | 51.18 | 550.9015 | 605.9917 | Tenant
13 | 2nd Floor | 205 | 2 BHK | 51.28 | 551.9779 | 607.1757 | Tenant
14 | 3rd Floor | 301 | 1 BHK | 41.42 | 445.8449 | 490.4294 | Unsold
15 | 3rd Floor | 302 | 1 BHK | 40.71 | 438.2024 | 482.0227 | Unsold
16 | 3rd Floor | 303 | 2 BHK | 51.25 | 551.655 | 606.8205 | Tenant
17 | 3rd Floor | 304 | 2 BHK | 51.18 | 550.9015 | 605.9917 | Tenant
18 | 3rd Floor | 305 | 2 BHK | 51.28 | 551.9779 | 607.1757 | Tenant
19 | 4th Floor | 401 | 1 BHK | 41.42 | 445.8449 | 490.4294 | Unsold
20 | 4th Floor | 402 | 1 BHK | 40.71 | 438.2024 | 482.0227 | Unsold
21 | 4th Floor | 403 | 2 BHK | 51.25 | 551.655 | 606.8205 | Tenant
22 | 4th Floor | 404 | 2 BHK | 51.18 | 550.9015 | 605.9917 | Tenant
23 | 4th Floor | 405 | 2 BHK | 51.28 | 551.9779 | 607.1757 | Tenant
24 | 5th Floor | 501 | 1 BHK | 41.42 | 445.8449 | 490.4294 | Unsold
25 | 5th Floor | 502 | 1 BHK | 40.71 | 438.2024 | 482.0227 | Unsold
26 | 5th Floor | 503 | 2 BHK | 51.25 | 551.655 | 606.8205 | Tenant
27 | 5th Floor | 504 | 2 BHK | 51.18 | 550.9015 | 605.9917 | Tenant
28 | 5th Floor | 505 | 2 BHK | 51.28 | 551.9779 | 607.1757 | Tenant
29 | 6th Floor | 601 | 1 BHK | 41.42 | 445.8449 | 490.4294 | Unsold
30 | 6th Floor | 602 | 1 BHK | 40.71 | 438.2024 | 482.0227 | Unsold
31 | 6th Floor | 603 | 2 BHK | 51.25 | 551.655 | 606.8205 | Tenant
32 | 6th Floor | 604 | 2 BHK | 51.18 | 550.9015 | 605.9917 | Tenant
33 | 6th Floor | 605 | 2 BHK | 51.28 | 551.9779 | 607.1757 | Tenant
34 | 7th Floor | 701 | 1 BHK | 41.42 | 445.8449 | 490.4294 | Unsold
35 | 7th Floor | 702 | 1 BHK | 40.71 | 438.2024 | 482.0227 | Unsold
36 | 7th Floor | 703 | 2 BHK | 51.25 | 551.655 | 606.8205 | Tenant
37 | 7th Floor | 704 | 2 BHK | 51.18 | 550.9015 | 605.9917 | Tenant
38 | 7th Floor | 705 | 2 BHK | 51.28 | 551.9779 | 607.1757 | Tenant
39 | 8th Floor | 801 | 1 BHK | 41.42 | 445.8449 | 490.4294 | Unsold
40 | 8th Floor | 802 | 1 BHK | 40.71 | 438.2024 | 482.0227 | Unsold
41 | 8th Floor | 803 | Refuge | 0 | 0 | 0 | Refuge
42 | 8th Floor | 804 | 1 BHK | 39.61 | 426.362 | 468.9982 | Unsold
43 | 8th Floor | 805 | 2 BHK | 51.28 | 551.9779 | 607.1757 | Tenant
44 | 9th Floor | 901 | 1 BHK | 41.42 | 445.8449 | 490.4294 | Unsold
45 | 9th Floor | 902 | 1 BHK | 40.71 | 438.2024 | 482.0227 | Unsold
46 | 9th Floor | 903 | 2 BHK | 51.25 | 551.655 | 606.8205 | Tenant
47 | 9th Floor | 904 | 2 BHK | 51.18 | 550.9015 | 605.9917 | Tenant
48 | 9th Floor | 905 | 2 BHK | 51.28 | 551.9779 | 607.1757 | Tenant
49 | 10th Floor | 1001 | 1 BHK | 41.42 | 445.8449 | 490.4294 | Unsold
50 | 10th Floor | 1002 | 1 BHK | 40.71 | 438.2024 | 482.0227 | Unsold
51 | 10th Floor | 1003 | 2 BHK | 51.25 | 551.655 | 606.8205 | Tenant
52 | 10th Floor | 1004 | 2 BHK | 51.18 | 550.9015 | 605.9917 | Tenant
53 | 10th Floor | 1005 | 2 BHK | 51.28 | 551.9779 | 607.1757 | Tenant
54 | 11th Floor | 1101 | 1 BHK | 41.42 | 445.8449 | 490.4294 | Unsold
55 | 11th Floor | 1102 | 1 BHK | 40.71 | 438.2024 | 482.0227 | Unsold
56 | 11th Floor | 1103 | 2 BHK | 51.25 | 551.655 | 606.8205 | Tenant
57 | 11th Floor | 1104 | 2 BHK | 51.18 | 550.9015 | 605.9917 | Tenant
58 | 11th Floor | 1105 | 2 BHK | 51.28 | 551.9779 | 607.1757 | Tenant
59 | 12th Floor | 1201 | 1 BHK | 41.42 | 445.8449 | 490.4294 | Unsold
60 | 12th Floor | 1202 | 1 BHK | 40.71 | 438.2024 | 482.0227 | Unsold
61 | 12th Floor | 1203 | 2 BHK | 51.25 | 551.655 | 606.8205 | Tenant
62 | 12th Floor | 1204 | 2 BHK | 53.17 | 572.3219 | 629.5541 | Unsold
63 | 12th Floor | 1205 | 2 BHK | 53.36 | 574.367 | 631.8037 | Unsold
64 | 13th Floor | 1301 | 1 BHK | 41.42 | 445.8449 | 490.4294 | Unsold
65 | 13th Floor | 1302 | 1 BHK | 40.71 | 438.2024 | 482.0227 | Unsold
66 | 13th Floor | 1303 | 2 BHK | 53.4 | 574.7976 | 632.2774 | Unsold
67 | 13th Floor | 1304 | 2 BHK | 53.17 | 572.3219 | 629.5541 | Unsold
68 | 13th Floor | 1305 | 2 BHK | 53.36 | 574.367 | 631.8037 | Unsold
69 | 14th Floor | 1401 | 1 BHK | 41.42 | 445.8449 | 490.4294 | Unsold
70 | 14th Floor | 1402 | 1 BHK | 40.71 | 438.2024 | 482.0227 | Unsold
71 | 14th Floor | 1403 | 2 BHK | 53.4 | 574.7976 | 632.2774 | Unsold
72 | 14th Floor | 1404 | 2 BHK | 53.17 | 572.3219 | 629.5541 | Unsold
73 | 14th Floor | 1405 | 2 BHK | 53.36 | 574.367 | 631.8037 | Unsold
74 | 15th Floor | 1501 | 1 BHK | 41.42 | 445.8449 | 490.4294 | Unsold
75 | 15th Floor | 1502 | 1 BHK | 40.71 | 438.2024 | 482.0227 | Unsold
76 | 15th Floor | 1503 | Refuge | 0 | 0 | 0 | Refuge
77 | 15th Floor | 1504 | 1 BHK | 39.61 | 426.362 | 468.9982 | Unsold
78 | 15th Floor | 1505 | 2 BHK | 53.36 | 574.367 | 631.8037 | Unsold
79 | 16th Floor | 1601 | 1 BHK | 41.42 | 445.8449 | 490.4294 | Unsold
80 | 16th Floor | 1602 | 1 BHK | 40.71 | 438.2024 | 482.0227 | Unsold
81 | 16th Floor | 1603 | 2 BHK | 53.4 | 574.7976 | 632.2774 | Unsold
82 | 16th Floor | 1604 | 2 BHK | 53.17 | 572.3219 | 629.5541 | Unsold
83 | 16th Floor | 1605 | 2 BHK | 53.36 | 574.367 | 631.8037 | Unsold
84 | 17th Floor | 1701 | 1 BHK | 41.42 | 445.8449 | 490.4294 | Unsold
85 | 17th Floor | 1702 | 1 BHK | 40.71 | 438.2024 | 482.0227 | Unsold
86 | 17th Floor | 1703 | 2 BHK | 53.4 | 574.7976 | 632.2774 | Unsold
87 | 17th Floor | 1704 | 2 BHK | 53.17 | 572.3219 | 629.5541 | Unsold
88 | 17th Floor | 1705 | 2 BHK | 53.36 | 574.367 | 631.8037 | Unsold
89 | 18th Floor | 1801 | 1 BHK | 41.42 | 445.8449 | 490.4294 | Unsold
90 | 18th Floor | 1802 | 1 BHK | 40.71 | 438.2024 | 482.0227 | Unsold
91 | 18th Floor | 1803 | 2 BHK | 53.4 | 574.7976 | 632.2774 | Unsold
92 | 18th Floor | 1804 | 2 BHK | 53.17 | 572.3219 | 629.5541 | Unsold
93 | 18th Floor | 1805 | 2 BHK | 53.36 | 574.367 | 631.8037 | Unsold
94 | 19th Floor | 1901 | 1 BHK | 41.42 | 445.8449 | 490.4294 | Unsold
95 | 19th Floor | 1902 | 1 BHK | 40.71 | 438.2024 | 482.0227 | Unsold
96 | 19th Floor | 1903 | 2 BHK | 53.4 | 574.7976 | 632.2774 | Unsold
97 | 19th Floor | 1904 | 2 BHK | 53.17 | 572.3219 | 629.5541 | Unsold
98 | 19th Floor | 1905 | 2 BHK | 53.36 | 574.367 | 631.8037 | Unsold
99 | 20th Floor | 2001 | 1 BHK | 41.42 | 445.8449 | 490.4294 | Unsold
100 | 20th Floor | 2002 | 1 BHK | 40.71 | 438.2024 | 482.0227 | Unsold
101 | 20th Floor | 2003 | 2 BHK | 53.4 | 574.7976 | 632.2774 | Unsold
102 | 20th Floor | 2004 | 2 BHK | 53.17 | 572.3219 | 629.5541 | Unsold
103 | 20th Floor | 2005 | 2 BHK | 53.36 | 574.367 | 631.8037 | Unsold
104 | 21st Floor | 2101 | 1 BHK | 41.42 | 445.8449 | 490.4294 | Unsold
105 | 21st Floor | 2102 | 1 BHK | 40.71 | 438.2024 | 482.0227 | Unsold
106 | 21st Floor | 2103 | 2 BHK | 53.4 | 574.7976 | 632.2774 | Unsold
107 | 21st Floor | 2104 | 2 BHK | 53.17 | 572.3219 | 629.5541 | Unsold
108 | 21st Floor | 2105 | 2 BHK | 53.36 | 574.367 | 631.8037 | Unsold
109 | 22nd Floor | 2201 | 1 BHK | 41.42 | 445.8449 | 490.4294 | Unsold
110 | 22nd Floor | 2202 | 1 BHK | 40.71 | 438.2024 | 482.0227 | Unsold
111 | 22nd Floor | 2203 | 2 BHK | 53.4 | 574.7976 | 632.2774 | Unsold
112 | 22nd Floor | 2204 | 2 BHK | 53.17 | 572.3219 | 629.5541 | Unsold
113 | 22nd Floor | 2205 | 2 BHK | 53.36 | 574.367 | 631.8037 | Unsold
Total |  |  |  | 5042.84 | 54281.1298 | 59709.2427

## Unsold Flat Inventory
Unsold Flat Inventory | [8 empty] | Proposed Unsold Flat Inventory
Sr. No. | Floor No. | Flat No. | Comp. | RERA Carpet Area (in Sq. M.) | RERA Carpet Area (in Sq. Ft.) | Built - Up Area (in Sq. Ft.) | Rate / Sq. Ft. on Carpet Area | Value in ` | Sr. No. | Floor No. | Flat No. | Comp. | RERA Carpet Area (in Sq. M.) | RERA Carpet Area (in Sq. Ft.) | Built - Up Area (in Sq. Ft.) | Rate / Sq. Ft. on Carpet Area | Value in `
1 | 2nd Floor | 201 | 1 BHK | 41.42 | 445.8449 | 490.4294 | 21000 | 9362742 | 1 | 19th Floor | 1901 | 1 BHK | 41.42 | 445.8449 | 490.4294 | 21000 | 9362742
2 | 2nd Floor | 202 | 1 BHK | 40.71 | 438.2024 | 482.0227 | 21000 | 9202251 | 2 | 20th Floor | 2001 | 1 BHK | 41.42 | 445.8449 | 490.4294 | 21000 | 9362742
3 | 3rd Floor | 301 | 1 BHK | 41.42 | 445.8449 | 490.4294 | 21000 | 9362742 | 3 | 20th Floor | 2002 | 1 BHK | 40.71 | 438.2024 | 482.0227 | 21000 | 9202251
4 | 3rd Floor | 302 | 1 BHK | 40.71 | 438.2024 | 482.0227 | 21000 | 9202251 | 4 | 20th Floor | 2003 | 2 BHK | 53.4 | 574.7976 | 632.2774 | 21000 | 12070750
5 | 4th Floor | 401 | 1 BHK | 41.42 | 445.8449 | 490.4294 | 21000 | 9362742 | 5 | 20th Floor | 2004 | 2 BHK | 53.17 | 572.3219 | 629.5541 | 21000 | 12018759
6 | 4th Floor | 402 | 1 BHK | 40.71 | 438.2024 | 482.0227 | 21000 | 9202251 | 6 | 20th Floor | 2005 | 2 BHK | 53.36 | 574.367 | 631.8037 | 21000 | 12061708
7 | 5th Floor | 501 | 1 BHK | 41.42 | 445.8449 | 490.4294 | 21000 | 9362742 | 7 | 21st Floor | 2101 | 1 BHK | 41.42 | 445.8449 | 490.4294 | 21000 | 9362742
8 | 5th Floor | 502 | 1 BHK | 40.71 | 438.2024 | 482.0227 | 21000 | 9202251 | 8 | 21st Floor | 2102 | 1 BHK | 40.71 | 438.2024 | 482.0227 | 21000 | 9202251
9 | 6th Floor | 601 | 1 BHK | 41.42 | 445.8449 | 490.4294 | 21000 | 9362742 | 9 | 21st Floor | 2103 | 2 BHK | 53.4 | 574.7976 | 632.2774 | 21000 | 12070750
10 | 6th Floor | 602 | 1 BHK | 40.71 | 438.2024 | 482.0227 | 21000 | 9202251 | 10 | 21st Floor | 2104 | 2 BHK | 53.17 | 572.3219 | 629.5541 | 21000 | 12018759
11 | 7th Floor | 701 | 1 BHK | 41.42 | 445.8449 | 490.4294 | 21000 | 9362742 | 11 | 21st Floor | 2105 | 2 BHK | 53.36 | 574.367 | 631.8037 | 21000 | 12061708
12 | 7th Floor | 702 | 1 BHK | 40.71 | 438.2024 | 482.0227 | 21000 | 9202251 | 12 | 22nd Floor | 2201 | 1 BHK | 41.42 | 445.8449 | 490.4294 | 21000 | 9362742
13 | 8th Floor | 801 | 1 BHK | 41.42 | 445.8449 | 490.4294 | 21000 | 9362742 | 13 | 22nd Floor | 2202 | 1 BHK | 40.71 | 438.2024 | 482.0227 | 21000 | 9202251
14 | 8th Floor | 802 | 1 BHK | 40.71 | 438.2024 | 482.0227 | 21000 | 9202251 | 14 | 22nd Floor | 2203 | 2 BHK | 53.4 | 574.7976 | 632.2774 | 21000 | 12070750
15 | 8th Floor | 804 | 1 BHK | 39.61 | 426.362 | 468.9982 | 21000 | 8953603 | 15 | 22nd Floor | 2204 | 2 BHK | 53.17 | 572.3219 | 629.5541 | 21000 | 12018759
16 | 9th Floor | 901 | 1 BHK | 41.42 | 445.8449 | 490.4294 | 21000 | 9362742 | 16 | 22nd Floor | 2205 | 2 BHK | 53.36 | 574.367 | 631.8037 | 21000 | 12061708
17 | 9th Floor | 902 | 1 BHK | 40.71 | 438.2024 | 482.0227 | 21000 | 9202251 | TOTAL |  |  |  | 767.6 | 8262.4464 | 9088.691 |  | 173511372
18 | 10th Floor | 1001 | 1 BHK | 41.42 | 445.8449 | 490.4294 | 21000 | 9362742
19 | 10th Floor | 1002 | 1 BHK | 40.71 | 438.2024 | 482.0227 | 21000 | 9202251
20 | 11th Floor | 1101 | 1 BHK | 41.42 | 445.8449 | 490.4294 | 21000 | 9362742
21 | 11th Floor | 1102 | 1 BHK | 40.71 | 438.2024 | 482.0227 | 21000 | 9202251
22 | 12th Floor | 1201 | 1 BHK | 41.42 | 445.8449 | 490.4294 | 21000 | 9362742
23 | 12th Floor | 1202 | 1 BHK | 40.71 | 438.2024 | 482.0227 | 21000 | 9202251
24 | 12th Floor | 1204 | 2 BHK | 53.17 | 572.3219 | 629.5541 | 21000 | 12018759
25 | 12th Floor | 1205 | 2 BHK | 53.36 | 574.367 | 631.8037 | 21000 | 12061708
26 | 13th Floor | 1301 | 1 BHK | 41.42 | 445.8449 | 490.4294 | 21000 | 9362742
27 | 13th Floor | 1302 | 1 BHK | 40.71 | 438.2024 | 482.0227 | 21000 | 9202251
28 | 13th Floor | 1303 | 2 BHK | 53.4 | 574.7976 | 632.2774 | 21000 | 12070750
29 | 13th Floor | 1304 | 2 BHK | 53.17 | 572.3219 | 629.5541 | 21000 | 12018759
30 | 13th Floor | 1305 | 2 BHK | 53.36 | 574.367 | 631.8037 | 21000 | 12061708
31 | 14th Floor | 1401 | 1 BHK | 41.42 | 445.8449 | 490.4294 | 21000 | 9362742
32 | 14th Floor | 1402 | 1 BHK | 40.71 | 438.2024 | 482.0227 | 21000 | 9202251
33 | 14th Floor | 1403 | 2 BHK | 53.4 | 574.7976 | 632.2774 | 21000 | 12070750
34 | 14th Floor | 1404 | 2 BHK | 53.17 | 572.3219 | 629.5541 | 21000 | 12018759
35 | 14th Floor | 1405 | 2 BHK | 53.36 | 574.367 | 631.8037 | 21000 | 12061708
36 | 15th Floor | 1501 | 1 BHK | 41.42 | 445.8449 | 490.4294 | 21000 | 9362742
37 | 15th Floor | 1502 | 1 BHK | 40.71 | 438.2024 | 482.0227 | 21000 | 9202251
38 | 15th Floor | 1504 | 1 BHK | 39.61 | 426.362 | 468.9982 | 21000 | 8953603
39 | 15th Floor | 1505 | 2 BHK | 53.36 | 574.367 | 631.8037 | 21000 | 12061708
40 | 16th Floor | 1601 | 1 BHK | 41.42 | 445.8449 | 490.4294 | 21000 | 9362742
41 | 16th Floor | 1602 | 1 BHK | 40.71 | 438.2024 | 482.0227 | 21000 | 9202251
42 | 16th Floor | 1603 | 2 BHK | 53.4 | 574.7976 | 632.2774 | 21000 | 12070750
43 | 16th Floor | 1604 | 2 BHK | 53.17 | 572.3219 | 629.5541 | 21000 | 12018759
44 | 16th Floor | 1605 | 2 BHK | 53.36 | 574.367 | 631.8037 | 21000 | 12061708
45 | 17th Floor | 1701 | 1 BHK | 41.42 | 445.8449 | 490.4294 | 21000 | 9362742
46 | 17th Floor | 1702 | 1 BHK | 40.71 | 438.2024 | 482.0227 | 21000 | 9202251
47 | 17th Floor | 1703 | 2 BHK | 53.4 | 574.7976 | 632.2774 | 21000 | 12070750
48 | 17th Floor | 1704 | 2 BHK | 53.17 | 572.3219 | 629.5541 | 21000 | 12018759
49 | 17th Floor | 1705 | 2 BHK | 53.36 | 574.367 | 631.8037 | 21000 | 12061708
50 | 18th Floor | 1801 | 1 BHK | 41.42 | 445.8449 | 490.4294 | 21000 | 9362742
51 | 18th Floor | 1802 | 1 BHK | 40.71 | 438.2024 | 482.0227 | 21000 | 9202251
52 | 18th Floor | 1803 | 2 BHK | 53.4 | 574.7976 | 632.2774 | 21000 | 12070750
53 | 18th Floor | 1804 | 2 BHK | 53.17 | 572.3219 | 629.5541 | 21000 | 12018759
54 | 18th Floor | 1805 | 2 BHK | 53.36 | 574.367 | 631.8037 | 21000 | 12061708
55 | 19th Floor | 1902 | 1 BHK | 40.71 | 438.2024 | 482.0227 | 21000 | 9202251
56 | 19th Floor | 1903 | 2 BHK | 53.4 | 574.7976 | 632.2774 | 21000 | 12070750
57 | 19th Floor | 1904 | 2 BHK | 53.17 | 572.3219 | 629.5541 | 21000 | 12018759
58 | 19th Floor | 1905 | 2 BHK | 53.36 | 574.367 | 631.8037 | 21000 | 12061708
TOTAL |  |  |  | 2635.61 | 28369.706 | 31206.6766 |  | 595763815

## Tenant Flat Inventory
Sr. No. | Floor No. | Flat No. | Comp. | RERA Carpet Area (in Sq. M.) | RERA Carpet Area (in Sq. Ft.) | Built - Up Area (in Sq. Ft.)
1 | 1st Floor | 103 | 2 BHK | 51.25 | 551.655 | 606.8205
2 | 1st Floor | 104 | 2 BHK | 51.18 | 550.9015 | 605.9917
3 | 1st Floor | 105 | 2 BHK | 51.28 | 551.9779 | 607.1757
4 | 2nd Floor | 203 | 2 BHK | 51.25 | 551.655 | 606.8205
5 | 2nd Floor | 204 | 2 BHK | 51.18 | 550.9015 | 605.9917
6 | 2nd Floor | 205 | 2 BHK | 51.28 | 551.9779 | 607.1757
7 | 3rd Floor | 303 | 2 BHK | 51.25 | 551.655 | 606.8205
8 | 3rd Floor | 304 | 2 BHK | 51.18 | 550.9015 | 605.9917
9 | 3rd Floor | 305 | 2 BHK | 51.28 | 551.9779 | 607.1757
10 | 4th Floor | 403 | 2 BHK | 51.25 | 551.655 | 606.8205
11 | 4th Floor | 404 | 2 BHK | 51.18 | 550.9015 | 605.9917
12 | 4th Floor | 405 | 2 BHK | 51.28 | 551.9779 | 607.1757
13 | 5th Floor | 503 | 2 BHK | 51.25 | 551.655 | 606.8205
14 | 5th Floor | 504 | 2 BHK | 51.18 | 550.9015 | 605.9917
15 | 5th Floor | 505 | 2 BHK | 51.28 | 551.9779 | 607.1757
16 | 6th Floor | 603 | 2 BHK | 51.25 | 551.655 | 606.8205
17 | 6th Floor | 604 | 2 BHK | 51.18 | 550.9015 | 605.9917
18 | 6th Floor | 605 | 2 BHK | 51.28 | 551.9779 | 607.1757
19 | 7th Floor | 703 | 2 BHK | 51.25 | 551.655 | 606.8205
20 | 7th Floor | 704 | 2 BHK | 51.18 | 550.9015 | 605.9917
21 | 7th Floor | 705 | 2 BHK | 51.28 | 551.9779 | 607.1757
22 | 8th Floor | 805 | 2 BHK | 51.28 | 551.9779 | 607.1757
23 | 9th Floor | 903 | 2 BHK | 51.25 | 551.655 | 606.8205
24 | 9th Floor | 904 | 2 BHK | 51.18 | 550.9015 | 605.9917
25 | 9th Floor | 905 | 2 BHK | 51.28 | 551.9779 | 607.1757
26 | 10th Floor | 1003 | 2 BHK | 51.25 | 551.655 | 606.8205
27 | 10th Floor | 1004 | 2 BHK | 51.18 | 550.9015 | 605.9917
28 | 10th Floor | 1005 | 2 BHK | 51.28 | 551.9779 | 607.1757
29 | 11th Floor | 1103 | 2 BHK | 51.25 | 551.655 | 606.8205
30 | 11th Floor | 1104 | 2 BHK | 51.18 | 550.9015 | 605.9917
31 | 11th Floor | 1105 | 2 BHK | 51.28 | 551.9779 | 607.1757
32 | 12th Floor | 1203 | 2 BHK | 51.25 | 551.655 | 606.8205
TOTAL |  |  |  | 1639.63 | 17648.9773 | 19413.8751

## Sheet1
58970
795.58
46915352.6

## PC
Stagewise pecentage of work completion
Sr. | Particulars | Percentage
| Extra 10% for Excavation & Piling Work | 10 | 9.091% | 9.091%
1 | RCC Footing/Foundation | 5 | 4.545% | 4.545%
2 | RCC Plinth | 5 | 4.545% | 4.545%
3 | Full Building RCC | 40 | 36.36% | 7.905%
4 | Internal Brick work | 7 | 6.364% | 0.5534%
5 | External Brickwork | 7 | 6.364% | 0.5534%
6 | Internal plastering | 3.5 | 3.182%
7 | External plastering | 3.5 | 3.182%
8 | Doors & Windows | 5 | 4.545%
9 | Flooring, Tiling, Kitchen Platform | 10 | 9.091%
10 | Internal painting | 1.5 | 1.364%
11 | External painting | 1.5 | 1.364%
12 | Electrification, plumbing & Sanitary installation | 5 | 4.545%
13 | Lift Installation | 2 | 1.818%
14 | Passage, Staircase & Lobby development | 2 | 1.818%
15 | External developments / Final finishing work | 2 | 1.818%
|  | 110 | 100%

## Sheet3
16600000
697
23816.3558

## Sheet4
15900000
728
21840.6593

## Sheet5
18200000
827
22007.2551

## Sheet6
12400000
617
20097.2447

## Sheet7
9687000
478.89
20228.0273

## Sheet2 (hidden)
Floor | Flat No. | Carpet Area | Balcony Area | Cuboard Area | Terrace
1 | 1 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
| 2 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
2 | 1 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
| 2 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
| 3 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
| 4 | 52.05 | 5.615 | 5.76 | 4.8575 | 560.2662 | 60.4399 | 62.0006 | 52.2861 | 734.9928
3 | 1 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
| 2 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
| 3 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
| 4 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
4 | 1 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
| 2 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
| 3 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
| 4 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
5 | 1 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
| 2 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
| 3 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
| 4 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
6 | 1 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
| 2 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
| 3 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
| 4 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
7 | 1 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
| 2 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
| 3 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
| 4 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
8 | 1 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
| 2 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
| 3 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
| 4 | 52.05 | 5.615 | 5.76 |  | 560.2662 | 60.4399 | 62.0006 |  | 682.7067
9 | 1 | 55.81 | 6.5925 | 5.76 |  | 600.7388 | 70.9617 | 62.0006 |  | 733.7011
| 2 | 55.81 | 6.5925 | 5.76 |  | 600.7388 | 70.9617 | 62.0006 |  | 733.7011
| 3 | 55.81 | 6.5925 | 5.76 |  | 600.7388 | 70.9617 | 62.0006 |  | 733.7011
| 4 | 55.81 | 6.5925 | 5.76 |  | 600.7388 | 70.9617 | 62.0006 |  | 733.7011
10 | 1 | 55.81 | 6.5925 | 5.76 |  | 600.7388 | 70.9617 | 62.0006 |  | 733.7011
| 2 | 55.81 | 6.5925 | 5.76 |  | 600.7388 | 70.9617 | 62.0006 |  | 733.7011
| 3 | 55.81 | 6.5925 | 5.76 |  | 600.7388 | 70.9617 | 62.0006 |  | 733.7011
| 4 | 55.81 | 6.5925 | 5.76 |  | 600.7388 | 70.9617 | 62.0006 |  | 733.7011
11 | 1 | 61.95 | 6.45 | 4.32 |  | 666.8298 | 69.4278 | 46.5005 |  | 782.7581
| 2 | 61.95 | 6.45 | 4.32 |  | 666.8298 | 69.4278 | 46.5005 |  | 782.7581
| 3 | 61.95 | 6.45 | 4.32 |  | 666.8298 | 69.4278 | 46.5005 |  | 782.7581
| 4 | 61.95 | 6.45 | 4.32 |  | 666.8298 | 69.4278 | 46.5005 |  | 782.7581
12 | 1 | 61.05 | 6.45 | 4.32 |  | 657.1422 | 69.4278 | 46.5005 |  | 773.0705
| 2 | 63.29 | 6.93 | 4.32 |  | 681.2536 | 74.5945 | 46.5005 |  | 802.3486
| 3 | 63.29 | 6.93 | 4.32 |  | 681.2536 | 74.5945 | 46.5005 |  | 802.3486
| 4 | 61.05 | 6.45 | 4.32 |  | 657.1422 | 69.4278 | 46.5005 |  | 773.0705
13 | 1 | 69.84 | 6.93 | 4.32 |  | 751.7578 | 74.5945 | 46.5005 |  | 872.8528
| 2 | 63.29 | 6.93 | 4.32 |  | 681.2536 | 74.5945 | 46.5005 |  | 802.3486
| 3 | 63.29 | 6.93 | 4.32 |  | 681.2536 | 74.5945 | 46.5005 |  | 802.3486
| 4 | 69.84 | 6.93 | 4.32 |  | 751.7578 | 74.5945 | 46.5005 |  | 872.8528
14 | 1 | 69.84 | 8.37 | 4.32 |  | 751.7578 | 90.0947 | 46.5005 |  | 888.3529
| 2 | 68.4 | 6.93 | 4.32 |  | 736.2576 | 74.5945 | 46.5005 |  | 857.3526
| 3 | 68.4 | 6.93 | 4.32 |  | 736.2576 | 74.5945 | 46.5005 |  | 857.3526
| 4 | 69.84 | 8.37 | 4.32 |  | 751.7578 | 90.0947 | 46.5005 |  | 888.3529
15 | 1 | [8 empty] | 39526.7804
2
3
4
16 | 1
2
3
4
1
2
3
4
1
2
3
4
1
2
3
4
1
2
3
4
1
2
3
4
1
2
3
4