## Final Summary
Project expenses | Estimated Cost as per Cost Vetting | Incurred Cost as per Bill till 30.06.2024 | Incurred Cost as per CA till 30.06.2024 | Incurred Cost as per Bill till 31.03.2024 | Incurred Cost as per CA till 31.03.2024 | Difference between the Bills & CA | Difference between both the Bills | Difference between both CA | Remark
Land Cost | 2.86 | 2.8588 | 2.86 | 2.8588 | 2.86 | -0.00122 | 0 | 0
Rent Cost | 41.2 | 20.8096 | 20.81 | 20.16 | 20.16 | -0.0004 | 0.6496 | 0.65
Construction Cost of PTC Building | 14.95 | 6.7005 | 6.7 | 6.25 | 6.25 | 0.000525 | 0.45051 | 0.45
Construction Cost of Rehab cum Sale Building | 155.63 | 99.9685 | 99.97 | 98.4269 | 96.17 | -0.0015288 | 1.5416 | 3.8
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 31.15 | 24.6691 | 24.67 | 22.7068 | 22.71 | -0.0009 | 1.9623 | 1.96
Architect Cost, RCC & other Professional fees | 2.56 | 1.25 | 1.25 | 1.1 | 1.1 | 1.5e-05 | 0.15001 | 0.15
Administrative Expenses | 4.26 | 2.1411 | 2.14 | 1.6501 | 1.65 | 0.001055 | 0.49093 | 0.49
Marketing Expences | 8.09 | 5.1107 | 5.11 | 4.6505 | 4.65 | 0.0007235 | 0.46027 | 0.46
Interest Cost | 23.99 | 2.8755 | 2.88 | 1.44 | 1.44 | -0.0044935 | 1.4355 | 1.44
Contingency Cost | 5.12 | 0 | 0 |  | 0 | 0 | 0 | 0
Total Cost | 289.81 | 166.3838 | 166.39 | 159.243 | 156.99 | -0.0062238 | 7.1407 | 9.4 | DSRA Amount is not accounted in LIE Report
|  | 123.4262 | 57.41%
Particulars | Revised Estimated Cost (in Cr.) | Incurred Cost as per bills till 30.06.2024 | Cost incurred as %age total cost of that Component | Cost incurred as %age of cost incurred as on 30.06.2024
Land Cost | 2.86 | 2.8588 | 99.96% | 0.9864%
Rent Cost | 41.2 | 20.8096 | 50.51% | 7.18%
Construction Cost of Rehab & Amenity Building | 14.95 | 6.7005 | 44.82% | 2.312%
Construction Cost of Sale Building | 155.63 | 99.9685 | 64.23% | 34.49%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 31.15 | 24.6691 | 79.19% | 8.512%
Architect Cost, RCC & other Professional fees | 2.56 | 1.25 | 48.83% | 0.4313%
Administrative Expenses | 4.26 | 2.1411 | 50.26% | 0.7388%
Marketing Expences | 8.09 | 5.1107 | 63.17% | 1.763%
Interest Cost | 23.99 | 2.88 | 12.01% | 0.9938%
Contingency Cost | 5.12 | 0 | 0% | 0%
Total | 289.81 | 166.3883 | 57.41% | 57.41%
Pariculars | 30.06.2024 as per Physical status of the project | 31.03.2024 as per Physical status of the project | Difference b/w bills of 31.03.2024 & 30.06.2024 | Difference of Cost incurred as %age of cost incurred as on 31.03.2024 & 30.06.2024
Land Cost | 2.8588 | 2.8588 | 0 | 0%
Rent Cost | 20.8096 | 20.16 | 0.65 | 0.3907%
Construction Cost of Rehab & Amenity Building | 6.7005 | 6.25 | 0.45 | 0.2705%
Construction Cost of Sale Building | 99.9685 | 98.4269 | 1.54 | 0.9256%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 24.6691 | 22.7068 | 1.96 | 1.178%
Architect Cost, RCC & other Professional fees | 1.25 | 1.1 | 0.15 | 0.09015%
Administrative Expenses | 2.1411 | 1.6501 | 0.49 | 0.2945%
Marketing Expences | 5.1107 | 4.6505 | 0.46 | 0.2765%
Interest Cost | 2.8755 | 1.44 | 1.44 | 0.8655%
Contingency Cost | 0 | 0 | 0 | 0%
Total | 166.3838 | 159.243 | 7.14 | 4.291%

## Summary Sheet
Sr. No. | Particulars | Incurred Cost in ` till 30.06.2024 | Incurred Cost in ` Cr. Till 30.06.2024 | Incurred Cost in ` till 31.03.2024 | Incurred Cost in ` Cr. Till 31.03.2024 | Balance | Balance in Cr.
1 | Land Cost | 28587800 | 2.8588 | 28587800 | 2.8588 | 0 | 0
2 | Rent Cost | 208096000 | 20.8096 | 201600000 | 20.16 | 6496000 | 0.6496
3 | Construction Cost of PTC Building | 67005250 | 6.7005 | 62500155 | 6.25 | 4505095 | 0.45051
4 | Construction Cost of Sale Building | 999684712 | 99.9685 | 984268703 | 98.4269 | 15416009 | 1.5416
5 | Approval Cost & Stamp Duty | 246691000 | 24.6691 | 227068000 | 22.7068 | 19623000 | 1.9623
6 | Professional Cost | 12500150 | 1.25 | 11000025 | 1.1 | 1500125 | 0.15001
7 | Admin Cost | 21410550 | 2.1411 | 16501235 | 1.6501 | 4909315 | 0.49093
8 | Marketing Cost | 51107235 | 5.1107 | 46504535 | 4.6505 | 4602700 | 0.46027
9 | Interest Cost | 28755065 | 2.8755 | 14400000 | 1.44 | 14355065 | 1.4355
| Total | 1663837762 | 166.3838 | 1592430453 | 159.243 | 71407309 | 7.1407
239900000
211144935
81349102.22
82.37%

## Bills Details
Sr. No. | Vendor Name | Customer Name | Invoice Date | Invoice Number | Invoice Amt | Project Name | Description of Material
TILL 31.10.2023 |  |  |  |  | 457549549
1 | Sheetal Shourya Enterprises | DGS Township Pvt Ltd | 2023-11-17 | 01 | 2500000 | Sheetal Regalia | Plinth
2 | Avenue Imperial Construction LLP | DGS Township Pvt Ltd | 2023-11-18 | DGS/ AE/07/2023-24 | 10000000 | Sheetal Regalia | RCC work
3 | Om Infrastructure | DGS Township Pvt Ltd | 2023-11-22 | 9 | 30000000 | Sheetal Regalia | Slab Completed 1st to 3rd slab
4 | Om Infrastructure | DGS Township Pvt Ltd | 2023-11-23 | 10 | 59000000 | Sheetal Regalia | Labour work slab completed, Extra Beam work, U G Tank
20 | Anupam Hardware | DGS Township Pvt Ltd | 2023-12-05 | 09818 | 22606 | Sheetal Regalia | Flex Cable ISI 4 * 4 core Polycab & PVC Green Breded Pipe
22 | Anupam Hardware | DGS Township Pvt Ltd | 2023-11-09 | 08870 | 27140 | Sheetal Regalia | Pipe C Heavy 40MM
23 | Anupam Hardware | DGS Township Pvt Ltd | 2023-11-08 | 08828 | 10798 | Sheetal Regalia | CPVC Pipe SDR, Elbow 90 Degree, Ball Valve, Tee ISI 20 MM, Coupling ISI 40MM, Barrel Nepple, Ball Valve Brass Heavy & others
24 | Anupam Hardware | DGS Township Pvt Ltd | 2023-11-17 | 09067 | 25077 | Sheetal Regalia | Wires HOU, Flex Cable ISI
35 | J K Water Supply | DGS Township Pvt Ltd | 2023-11-30 | 478 | 91500 | Sheetal Regalia
36 | Jaiswal Plaster | DGS Township Pvt Ltd | 2023-11-08 |  | 290289 | Sheetal Regalia | Gypsum Celing, Vertical Patta, Wall Dhada POP, Patra POP, etc.
37 | JSW Cement Limited | DGS Township Pvt Ltd | 2023-11-02 | MH23030967116 | 121875 | Sheetal Regalia | GGBS-HDPE Bag
38 | JSW Cement Limited | DGS Township Pvt Ltd | 2023-11-07 | MH2303099454 | 121875 | Sheetal Regalia | GGBS-HDPE Bag
39 | JSW Cement Limited | DGS Township Pvt Ltd | 2023-11-19 | MH2303105295 | 121875 | Sheetal Regalia | GGBS-HDPE Bag
40 | JSW Cement Limited | DGS Township Pvt Ltd | 2023-11-19 | MH2303105306 | 121875 | Sheetal Regalia | GGBS-HDPE Bag
41 | JSW Cement Limited | DGS Township Pvt Ltd | 2023-11-25 | MH2303108765 | 121875 | Sheetal Regalia | GGBS-HDPE Bag
42 | JSW Cement Limited | DGS Township Pvt Ltd | 2023-11-01 | MH2303096689 | 121875 | Sheetal Regalia | GGBS-HDPE Bag
43 | JSW Cement Limited | DGS Township Pvt Ltd | 2023-11-03 | MH2303097628 | 121875 | Sheetal Regalia | GGBS-HDPE Bag
44 | JSW Cement Limited | DGS Township Pvt Ltd | 2023-11-13 | MH2303102121 | 121875 | Sheetal Regalia | GGBS-HDPE Bag
45 | JSW Cement Limited | DGS Township Pvt Ltd | 2023-11-06 | MH230399164 | 121875 | Sheetal Regalia | GGBS-HDPE Bag
46 | JSW Cement Limited | DGS Township Pvt Ltd | 2023-11-04 | MH2303097986 | 121875 | Sheetal Regalia | GGBS-HDPE Bag
47 | JSW Cement Limited | DGS Township Pvt Ltd | 2023-11-12 | MH2303102078 | 121875 | Sheetal Regalia | GGBS-HDPE Bag
48 | JSW Cement Limited | DGS Township Pvt Ltd | 2023-11-26 | MH2303109443 | 121875 | Sheetal Regalia | GGBS-HDPE Bag
49 | JSW Cement Limited | DGS Township Pvt Ltd | 2023-11-29 | MH2303111297 | 121875 | Sheetal Regalia | GGBS-HDPE Bag
50 | Rachana Glass Inc | DGS Township Pvt Ltd | 2023-11-23 | 98 | 53806 | Sheetal Regalia | 12mm Clear Toughen Glass + Cep and Frosted Film
53 | Rushabh Trading Company | DGS Township Pvt Ltd | 2023-11-30 | 198 | 32834 | Sheetal Regalia | Crush Sand
54 | Rushabh Trading Company | DGS Township Pvt Ltd | 2023-11-15 | 186 | 225635 | Sheetal Regalia | Crush Sand, Metal I & II
62 | Saurabh Enterprise | DGS Township Pvt Ltd | 2023-11-21 | 279 | 51684 | Sheetal Regalia | Ap Apcocrete
76 | SS Aggregates | DGS Township Pvt Ltd | 2023-11-30 | SS/105/2023-24 | 620922 | Sheetal Regalia | Crush Sand, Metal 1 VSI, Metal 2 VSI
79 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2023-11-01 | ASC534/23-24 | 1749232 | Sheetal Regalia | T.M.T. Bars 12mm, 16mm, 20mm, 25mm
80 | S K Traders | DGS Township Pvt Ltd | 2023-11-25 | SK/557/23-24 | 214400 | Sheetal Regalia | OPC53
81 | S K Traders | DGS Township Pvt Ltd | 2023-11-22 | SK/554/23-24 | 185774 | Sheetal Regalia | AAC Fly Ash Block, Magic Bond Joint Mortar
82 | S K Traders | DGS Township Pvt Ltd | 2023-11-30 | SK/574/23-24 | 211200 | Sheetal Regalia | OPC53
| S K Traders | DGS Township Pvt Ltd | 27/10/2023 | SK/494/23-24 | 211200 | Sheetal Regalia | OPC 53
| S K Traders | DGS Township Pvt Ltd | 2023-11-10 | SK/464/23-24 | 208000 | Sheetal Regalia | OPC 53
| S K Traders | DGS Township Pvt Ltd | 27/10/2023 | SK/496/23-24 | 211200 | Sheetal Regalia | OPC 53
| Sudha Sales Corporation | DGS Township Pvt.Ltd | 24/10/2023 | SSC/109 | 109056 | Sheetal Regalia | OPC 53 Grade,Birla Shakti Cement
93 | S K Traders | DGS Township Pvt Ltd | 21/11/2023 | SK/553/23-24 | 214400 | Sheetal Regalia | OPC 53
102 | S K Traders | DGS Township Pvt Ltd | 29/11/2023 | SK/570/23-24 | 211200 | Sheetal Regalia | OPC 53
120 | Raj Transit Infra Pvt Ltd | DGS Township Pvt Ltd | 2023-11-30 | 23-24/02584 | 646134 | Sheetal Regalia | C Sand - Brass, Metal 1 & 2 Brass
150 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2023-12-28 | PI/ASC870/23-24 | 17707660 | Sheetal Regalia | TMT Bars 08mm, 10mm, 12mm, 16mm, 20mm, 25mm
154 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2023-12-21 | ASC723/23-24 | 1908328 | Sheetal Regalia | TMT Bars 08mm, 10mm, 12mm, 16mm, M.S. Wire
155 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2023-12-23 | ASC737/23-24 | 1885760 | Sheetal Regalia | TMT Bars 08mm, 10mm, 12mm, 16mm, 20mm, 25mm
156 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2023-12-24 | ASC739/23-24 | 1913048 | Sheetal Regalia | TMT Bars 08mm, 10mm, 12mm, 16mm, 20mm, 25mm, M.S. Wire
158 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2023-11-09 | ASC561/23-24 | 1904338 | Sheetal Regalia | TMT Bars 08mm, 10mm, 12mm, 25mm
159 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2023-11-20 | ASC587/23-24 | 61425 | Sheetal Regalia | Shade Net Green 10 Bundles
160 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2023-11-21 | ASC593/23-24 | 1622070 | Sheetal Regalia | TMT Bars 10mm, 16mm, 20mm, 25mm
161 | Om Infrastructure | DGS Township Pvt Ltd | 2023-12-15 | 11 | 30000000 | Sheetal Regalia | Slab
162 | Om Infrastructure | DGS Township Pvt Ltd | 2023-12-16 | 12 | 23600000 | Sheetal Regalia | Slab
163 | Om Infrastructure | DGS Township Pvt Ltd | 2023-12-31 | 15 | 50000000 | Sheetal Regalia | Slab
166 | S K Traders | DGS Township Pvt Ltd | 2023-11-24 | SK/555/23-24 | 3254296 | Sheetal Regalia | 1C x 1.5sqmm H/W FR 1C x 1sqmm H/W FR 1C x 2.5sqmm H/W FR 1C x 4sqmm H/W FR 1C x 6sqmm H/W FR SC x 4.00mm FR INS Flexi Cable 200 Mtr SC X 6.00mm CU FR INS Flex Cable Footlight 4m 24 W Led Street Light 36 W Led Street Light 60 W Led Street Light ECO 11 W Led Panel Light 12 W 13 lN 1 Led Panel Light 3 W Led Panel Light
167 | S K Traders | DGS Township Pvt Ltd | 2023-11-24 | SK/556/23-24 | 3000787 | Sheetal Regalia | 11W Round Economy Led Pannel CDL 12W 13 In 1 Led Panel Light 14W Led Panel Light 15W Led Circular Led CDL 15W Led Panel Light 24W Led Street Light 36W Led Street Light 36W Led Street Light Heavy 3W Led COB Light 3W Led COB Light 3W Led Square Panel CDL 6W Led COB LIght Regulator Sub Meter
168 | S K Traders | DGS Township Pvt Ltd | 2023-11-25 | SK/560/23-24 | 3254369 | Sheetal Regalia | Pvc Insu 1.5sqmm Pvc lnsu lsqmm Pvc lnsu 2.5sqmm 1C x 1.5sqmm H/W FR 1C x 1sqmm H/W FR 1C x 6sqmm H/W FR
169 | SK Traders | DGS Township Pvt Ltd |  |  | 15009000 | Sheetal Regalia | Opc-53 Grade (28%), PPC Cement (28%), AAC FIy Ash Block (600 x 200 x 125) (12%
170 | S K Traders | DGS Township Pvt Ltd | 2023-11-25 | SK/561/23-24 | 3063717 | Sheetal Regalia | lC x 1.5sqmm H/W FR lC x 1sqmm H/W FR lC x 2.5sqmm H/W FR lC x 4sqmm H/W FR lC x 6sqmm H/W FR
175 | S K Traders | DGS Township Pvt Ltd | 2023-11-04 | SK/514/23-24 | 214400 | Sheetal Regalia | Opc53
176 | S K Traders | DGS Township Pvt Ltd | 2023-11-04 | SK/517/23-24 | 214400 | Sheetal Regalia | Opc53
177 | S K Traders | DGS Township Pvt Ltd | 2023-11-06 | SK/521/23-24 | 39060 | Sheetal Regalia | Hessian Cloth
178 | S K Traders | DGS Township Pvt Ltd | 2023-11-09 | SK/532/23-24 | 31080 | Sheetal Regalia | Wrap Knit Fabrics
179 | S K Traders | DGS Township Pvt Ltd | 2023-11-09 | SK/533/23-24 | 214400 | Sheetal Regalia | Opc53
180 | S K Traders | DGS Township Pvt Ltd | 2023-11-09 | SK/534/23-24 | 85760 | Sheetal Regalia | Opc53
181 | S K Traders | DGS Township Pvt Ltd | 2023-11-09 | SK/535/23-24 | 128640 | Sheetal Regalia | Opc53
182 | S K Traders | DGS Township Pvt Ltd | 2023-11-14 | SK/539/23-24 | 50400 | Sheetal Regalia | Wrap Knit Fabrics
183 | S K Traders | DGS Township Pvt Ltd | 2023-11-14 | SK/541/23-24 | 214400 | Sheetal Regalia | Opc53
184 | S K Traders | DGS Township Pvt Ltd | 2023-11-15 | SK/542/23-24 | 107200 | Sheetal Regalia | Opc53
185 | S K Traders | DGS Township Pvt Ltd | 2023-11-15 | SK/543/23-24 | 107200 | Sheetal Regalia | Opc53
222 | S K Traders | DGS Township Pvt Ltd | 2023-11-01 | SK/510/23-24 | 8576 | Sheetal Regalia | Opc53
228 | S K Traders | DGS Township Pvt Ltd | 2023-11-01 | SK/506/23-24 | 85760 | Sheetal Regalia | Opc53
229 | S K Traders | DGS Township Pvt Ltd | 2023-11-01 | SK/504/23-24 | 214400 | Sheetal Regalia | Opc53
238 | S K Traders | DGS Township Pvt Ltd | 2023-11-01 | SK/505/23-24 | 128640 | Sheetal Regalia | Opc53
239 | S K Traders | DGS Township Pvt Ltd | 2023-11-03 | SK/513/23-24 | 214400 | Sheetal Regalia | Opc53
290 | S K Traders | DGS Township Pvt Ltd | 2023-11-23 |  | 62408438 | Sheetal Regalia | 11W ROUND ECONOMY LED PANEL CDL, 12W 3 IN 1 LED PANEL LIGHT, 14W LED PANEL LIGHT, 15W LED CIRCULAR PANEL CDL, 15W LED PANEL LIGHT, 24W LED STREET LIGHT, 36W LED STREET LIGHT, 36W LED STREET LIGHT HEAVY, 3W LED COB LIGHT, 3W LED SOUARE PANEL CDL, 6W LED COB LIGHT, 6W LED PANEL LIGHT, LED LIGHT 1,+4 LED, LED LIGHT 20 LED, LED LIGHT 36 LED, PVC INSU 1.5 SO MM, PVC INSU 1 SQ MM, PVC INSU 2.5 SQ MM, 1C X ,I.sSOMM H/W FR, 1C X 1 SOMM HW FR, lC X 6SQ['MM H/W FR, REGULATOR, SUB METER, 1C X l.5SQMM HW FR etc
356 | B. Mittal & Co. | DGS Township Pvt Ltd | 2023-12-13 | BM23240237 | 1948410 | Sheetal Regalia | TMT Rebar, MS Binding Wire
357 | B. Mittal & Co. | DGS Township Pvt Ltd | 2023-11-30 | BM23240218 | 1942691 | Sheetal Regalia | TMT Rebar, MS Binding Wire
359 | B. Mittal & Co. | DGS Township Pvt Ltd | 2023-12-11 | BM23240235 | 1916683 | Sheetal Regalia | TMT Rebar
360 | B. Mittal & Co. | DGS Township Pvt Ltd | 2023-11-17 | BM23240196 | 1779530 | Sheetal Regalia | TMT Rebar, MS Binding Wire
361 | B. Mittal & Co. | DGS Township Pvt Ltd | 2023-11-26 | BM23240210 | 1903961 | Sheetal Regalia | TMT Rebar
362 | B. Mittal & Co. | DGS Township Pvt Ltd | 2023-11-05 | BM23240183 | 1736577 | Sheetal Regalia | TMT Rebar
2 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-01-04 | ASC788/23-24 | 1888605 | Sheetal Regalia | TMT Bars-08mm,10 mm,16 mm,20mm,25mm
3 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-01-08 | ASC803/23-24 | 1865450 | Sheetal Regalia | TMT Bars-08mm,10 mm,20mm,25mm
4 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-01-06 | ASC800/23-24 | 1879386 | Sheetal Regalia | TMT Bars-08mm,10 mm,20mm,25mm
5 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-03-11 | ASC1135/23-24 | 1939718 | Sheetal Regalia | TMT Bars-08mm,10 mm,12mm,20mm,16mm, M.S Wire
8 | Aayush Enterprises | DGS Township Pvt Ltd | 2024-03-04 | 732 | 15281 | Sheetal Regalia | Magni Grout
9 | Aayush Enterprises | DGS Township Pvt Ltd | 2024-01-30 | 654 | 7965 | Sheetal Regalia | Magni Grout
10 | Aayush Enterprises | DGS Township Pvt Ltd | 2024-01-31 | 658 | 13157 | Sheetal Regalia | Dr.Fixit Pidicrete Urp 50kg
11 | Aayush Enterprises | DGS Township Pvt Ltd | 2024-01-31 | 659 | 7965 | Sheetal Regalia | Magni Grout
12 | Aayush Enterprises | DGS Township Pvt Ltd | 2024-03-12 | 744 | 16815 | Sheetal Regalia | Faiber Mesh
18 | Anupam Hardware | DGS Township Pvt Ltd | 2024-02-05 | 12659 | 11078 | Sheetal Regalia | Pipe Easyfit Sch- 80 Upvc 1" ^Prince,Coupler Easyfit Upvc 1" ^Prince,Elbow Easyfit Upvc 1" Aprince,U Bolts Gi 1/4 X 1,Solvent Tin 705 Upvc 118ml ^Astral,Single Tee Swr Pvc,Bend, 45 Swr Pvc 110mm ^Prince 110mm ^Prince,Mta Easyfit Upvc 1" ^Prince,Pump Boster Aqua Gold 100 1hp^Crompton
19 | Anupam Hardware | DGS Township Pvt Ltd | 2024-02-24 | 13610 | 9529 | Sheetal Regalia | Pipe C-Heavy 80mm Gi/C 3" ^Steelman,Plug 80mm Gi 3,Pipe C-Heavy 32mm Gi/C 1.1/4" ^Steelman,Plug 32mm Gi 1.1/4
20 | Anupam Hardware | DGS Township Pvt Ltd | 2024-01-31 | 12408 | 58840 | Sheetal Regalia | Flex Cable Isi 2.5 X 2core ^Polycab,Mcb Catetron C Lighting Fp 63 A ^Indo Kapp,Wires Hou Flex/300mtr 1.5sq.Mm ^Polycab,Combined Ss (Box) 6 X 16a ^Anchor,Insulating Tape Pvc 6mtr ^Anchor
21 | Anupam Hardware | DGS Township Pvt Ltd | 2024-03-02 | 13970 | 19338 | Sheetal Regalia | Pipe Easyfit Sch- 80 Upvc 1.1/4" ^Prince,Coupler Easyfit Upvc 1.1/4" ^Prince,Ball Valve Easyfit Upvc 1.1/4" ^Prince,Ball Valve Easyfit Upvc 1.1/2" ^Prince,Reducer Tee Easyfit,Mta Brass Easyfit Upvc 1.1/2" ^Prince Upvc 1.1/2 X 1.1/4"Prince,Reducer Easyfit Upvc 1.1/2 X 1.1/4" ^Prince,Union Isi 50mm Gi 2,Barrel Nepple. Gi 2 X 6,Pipe Easyfit Sch-80 Upvc 1.1/2" ^Prince,Araldite Hv 953 Hardener 800gm,Araldite Aw 106 Resin 1kgm
22 | Anupam Hardware | DGS Township Pvt Ltd | 2024-03-03 | 14004 | 26548 | Sheetal Regalia | Combined Double With Box 6 X 16a,Mcb Box Metal 4way ^Nizwa,Wires Hou Flex/300mtr 1.5sq.Mm^Polycab,Flex Cable Isi 2.5 X 2core ^Polycab
23 | Anupam Hardware | DGS Township Pvt Ltd | 2024-01-07 | 11306 | 45004 | Sheetal Regalia | Combined Ss Box Typ 6 X 16a,Flex Cable Isi 1.5 X 2core ^Polycab,Led Flat Light 200w ^Carron,Insulating Tape Pvc 6mtr ^Anchor,Wires Hou Flex/300mtr 1.5sq.Mm^Polycab
24 | Anupam Hardware | DGS Township Pvt Ltd | 2024-01-25 | 12162 | 23352 | Sheetal Regalia | Flex Cable Isi 4 X 4core ^Feltek,Elbow Isi 40mm Gi 1.1/2,Coupling Isi 40mm Gi 1.1/2,Barrel Nepple. Gi 1.1/2 X 12,Barrel Nepple. Gi 1.1/2 X 6,D/Nipple Isi 40mm Gi 1.1/2,Bushing Gi 2 X 1.1/2,Ball Valve 40mm Ci 1.1/2" ^Hammer,Holdtite 200gms,Sun Juth,Pipe Easyfit Sch-80 Upvc 1.1/2" ^Prince,Coupler Easyfit Upvc 1.1/2" ^Prince,Reducer Tee Easyfit Upvc 1.1/2 X 1/2"^Prince,Endcap Easyfit Upvc 1.1/2" ^Prince,Elbow Easyfit Upvc 1.1/2" ^Prince,Mta Brass Easyfit Upvc 1.1/2" ^Prince,Pipe Easyfit Sch-80 Upvc 1/2" ^Prince,Solvent Tin 705 Upvc 237ml ^Astral,U Bolts Gi 1/4 X 1 1/2
25 | Anupam Hardware | DGS Township Pvt Ltd | 2024-02-24 | 13648 | 18718 | Sheetal Regalia | Pipe C-Heavy 80mm Gi/C 3" ^Steelman,Bend "C" 80mm Gi 3,Coupling Isi 80mm Gi 3,Die Gutka 3 ^Inder,Die Ratchet Handle 2.1/2 X 3" ^Inder,Plug 80mm Gi 3
26 | Anupam Hardware | DGS Township Pvt Ltd | 2024-02-26 | 13711 | 3421 | Sheetal Regalia | Pipe Wrenches 36" ^Taparia
27 | B.Mittal & Co. | DGS Township Pvt Ltd | 2024-02-19 | BM23240314 | 1869049 | Sheetal Regalia | TMT Rebar-8 mm,10mm,16mm,20mm,25mm
28 | B.Mittal & Co. | DGS Township Pvt Ltd | 2024-01-20 | BM23240274 | 1958420 | Sheetal Regalia | TMT Rebar-8 mm,10mm,20mm
29 | B.Mittal & Co. | DGS Township Pvt Ltd | 2024-02-16 | BM23240308 | 1883140 | Sheetal Regalia | TMT Rebar-8 mm,10mm,20mm,25mm
30 | B.Mittal & Co. | DGS Township Pvt Ltd | 2024-01-11 | BM23240258 | 1673134 | Sheetal Regalia | TMT Rebar-8 mm,10mm,20mm,25mm,32mm
31 | Bajrang Drilling | DGS Township Pvt Ltd | 2024-03-01 | 562 | 13723 | Sheetal Regalia | Core cutting in RCC
32 | Bluemax Engineering Corp | DGS Township Pvt Ltd | 2024-01-08 | BEC/23-24/174 | 8000 | Sheetal Regalia | Borewell Pumpset Removing and Refitting
33 | BMCC Enterprises | DGS Township Pvt Ltd | 2024-01-19 | 1095 | 34125 | Sheetal Regalia | Crush Sand
38 | Global Lab | DGS Township Pvt Ltd | 2024-01-04 | BVI-31201-259276 | 6372 | Sheetal Regalia | Concrete Cube-compressive strenghts-Test
39 | Janki Devi Prajapati | DGS Township Pvt Ltd | 2024-02-01 | 327 | 6312 | Sheetal Regalia | RCC Cover Block-40mm,20mm,230mm 300mm konda path
40 | Janki Devi Prajapati | DGS Township Pvt Ltd | 2024-02-19 | 358 | 11844 | Sheetal Regalia | RCC Cover Block-40mm,20mm,Path
44 | J.K Water Supply | DGS Township Pvt Ltd | 2024-02-29 | 533 | 28500 | Sheetal Regalia
45 | J.K Water Supply | DGS Township Pvt Ltd | 2024-01-31 | 509 | 69000 | Sheetal Regalia | Constuction Water
49 | JSW Cement Ltd. | DGS Township Pvt Ltd | 2024-02-19 | MH2303155729 | 124500 | Sheetal Regalia | FG-03-GGBS-BG-HD-500 Bags
50 | JSW Cement Ltd. | DGS Township Pvt Ltd | 2024-03-26 | MH2303175817 | 124500 | Sheetal Regalia | FG-03-GGBS-BG-HD-500 Bags
51 | JSW Cement Ltd. | DGS Township Pvt Ltd | 2024-03-26 | MH2303175964 | 124500 | Sheetal Regalia | FG-03-GGBS-BG-HD-500 Bags
52 | JSW Cement Ltd. | DGS Township Pvt Ltd | 2024-03-27 | MH2303176385 | 124500 | Sheetal Regalia | FG-03-GGBS-BG-HD-500 Bags
53 | JSW Cement Ltd. | DGS Township Pvt Ltd | 2024-03-27 | MH2303176416 | 124500 | Sheetal Regalia | FG-03-GGBS-BG-HD-500 Bags
54 | JSW Cement Ltd. | DGS Township Pvt Ltd | 2024-01-08 | MH2303133327 | 121875 | Sheetal Regalia | FG-03-GGBS-BG-HD-500 Bags
55 | JSW Cement Ltd. | DGS Township Pvt Ltd | 2024-02-15 | MH2303154059 | 124500 | Sheetal Regalia | FG-03-GGBS-BG-HD-500 Bags
56 | JSW Cement Ltd. | DGS Township Pvt Ltd | 2024-01-04 | MH2303130706 | 121875 | Sheetal Regalia | FG-03-GGBS-BG-HD-500 Bags
57 | JSW Cement Ltd. | DGS Township Pvt Ltd | 2024-01-08 | MH2303133099 | 121875 | Sheetal Regalia | FG-03-GGBS-BG-HD-500 Bags
58 | JSW Cement Ltd. | DGS Township Pvt Ltd | 2024-01-09 | MH2303133990 | 121875 | Sheetal Regalia | FG-03-GGBS-BG-HD-500 Bags
59 | JSW Cement Ltd. | DGS Township Pvt Ltd | 2024-01-12 | MH2303134766 | 121875 | Sheetal Regalia | FG-03-GGBS-BG-HD-500 Bags
60 | JSW Cement Ltd. | DGS Township Pvt Ltd | 2024-01-20 | MH2303139243 | 121875 | Sheetal Regalia | FG-03-GGBS-BG-HD-500 Bags
61 | JSW Cement Ltd. | DGS Township Pvt Ltd | 2024-01-29 | MH2303143761 | 121875 | Sheetal Regalia | FG-03-GGBS-BG-HD-500 Bags
62 | JSW Cement Ltd. | DGS Township Pvt Ltd | 2024-02-13 | MH2303152714 | 124500 | Sheetal Regalia | FG-03-GGBS-BG-HD-500 Bags
65 | JSW Cement Ltd. | DGS Township Pvt Ltd | 2024-01-05 | MH2303131247 | 121875 | Sheetal Regalia | FG-03-GGBS-BG-HD-500 Bags
66 | JSW Cement Ltd. | DGS Township Pvt Ltd | 2024-01-20 | MH2303139036 | 121875 | Sheetal Regalia | FG-03-GGBS-BG-HD-500 Bags
67 | JSW Cement Ltd. | DGS Township Pvt Ltd | 2024-01-22 | MH2303140310 | 121875 | Sheetal Regalia | FG-03-GGBS-BG-HD-500 Bags
68 | JSW Cement Ltd. | DGS Township Pvt Ltd | 2024-02-13 | MH2303152655 | 124500 | Sheetal Regalia | FG-03-GGBS-BG-HD-500 Bags
69 | JSW Cement Ltd. | DGS Township Pvt Ltd | 2024-02-10 | MH2303150956 | 124500 | Sheetal Regalia | FG-03-GGBS-BG-HD-500 Bags
70 | JSW Cement Ltd. | DGS Township Pvt Ltd | 2024-02-10 | MH2303150966 | 124500 | Sheetal Regalia | FG-03-GGBS-BG-HD-500 Bags
72 | Maatangi Enterprises | DGS Township Pvt Ltd | 2024-03-16 | 379 | 93310 | Sheetal Regalia | Black Granite(X/53)
75 | Om Infrastructure | DGS Township Pvt Ltd | 2024-01-13 | 13 | 30000000 | Sheetal Regalia | Slab
76 | Om Infrastructure | DGS Township Pvt Ltd | 2024-01-13 | 14 | 23600000 | Sheetal Regalia | Slab
77 | Om Infrastructure | DGS Township Pvt Ltd | 2024-03-05 | 15 | 72710436 | Sheetal Regalia | Slab
83 | Om sai Fabrication | DGS Township Pvt Ltd | 2024-01-02 |  | 367027 | Sheetal Regalia | Raising of G.l. Sheet surrounding the building by excavating pit, 5"x 3" ISMB erection & fixing of G.l.Sheet
84 | Pratik Enterprises | DGS Township Pvt Ltd | 2024-01-15 | 23-24/JAN/569 | 35129 | Sheetal Regalia | Metal-10 MM(BRS)
85 | Pratik Enterprises | DGS Township Pvt Ltd | 2024-01-31 | 23-24/JAN/589 | 111871 | Sheetal Regalia | Metal-10 MM(BRS),Crush Sand
86 | Pratik Enterprises | DGS Township Pvt Ltd | 2024-02-15 | 23-24/FEB/639 | 79200 | Sheetal Regalia | Crush Sand(BRS)
88 | Pratik Enterprises | DGS Township Pvt Ltd | 2024-01-15 | 23-24/JAN/574 | 35932 | Sheetal Regalia | Crush Sand(BRS)
89 | Raj Transit Infra Pvt.Ltd. | DGS Township Pvt Ltd | 2024-01-31 | 23-24/03049 | 178661 | Sheetal Regalia | C Sand-Brass,Metal 1-Brass,Metal 2-Brass
90 | Raj Transit Infra Pvt.Ltd. | DGS Township Pvt Ltd | 2024-02-29 | 23-24/03253 | 227165 | Sheetal Regalia | C Sand-Brass,Metal 1-Brass,Metal 2-Brass,Ultramod Plaster Sand-Brass
91 | Raj Transit Infra Pvt.Ltd. | DGS Township Pvt Ltd | 2024-02-15 | 23-24/03125 | 316796 | Sheetal Regalia | C Sand-Brass,Metal 1-Brass,Metal 2-Brass
92 | Raj Transit Infra Pvt.Ltd. | DGS Township Pvt Ltd | 2024-03-15 | 23-24/03391 | 201369 | Sheetal Regalia | C Sand-Brass,Metal 1-Brass,Metal 2-Brass,Ultramod Plaster Sand-Brass
93 | Raj Transit Infra Pvt.Ltd. | DGS Township Pvt Ltd | 2024-03-31 | 23-24/03552 | 250279 | Sheetal Regalia | C Sand-Brass,Metal 1-Brass,Metal 2-Brass,Ultramod Plaster Sand-Brass
95 | Raj Transit Infra Pvt.Ltd. | DGS Township Pvt Ltd | 2024-01-15 | 23-24/02882 | 238606 | Sheetal Regalia | C Sand-Brass,Metal 1-Brass,Metal 2-Brass
96 | Rajesh Singh Water Pump Hiring | DGS Township Pvt Ltd | 2024-03-06 | 346 | 13500 |  | HP Water Pump
97 | Rajesh Singh Water Pump Hiring | DGS Township Pvt Ltd | 2024-02-07 | 222 | 13500 | Sheetal Regalia | HP Water Pump
98 | Rajesh Singh Water Pump Hiring | DGS Township Pvt Ltd | 2024-01-02 | 117 | 13500 | Sheetal Regalia | HP Water Pump
99 | R C Safety Products | DGS Township Pvt Ltd | 2024-01-19 | RC/23-24/291 | 20025 | Sheetal Regalia | Safety Shoes-AC 9006,Safety Shoes-AC 9005
100 | R C Safety Products | DGS Township Pvt Ltd | 2024-01-09 | RC/23-24/221 | 1888 | Sheetal Regalia | Safety Shoes-Centuar slip on
101 | R C Safety Products | DGS Township Pvt Ltd | 2024-03-07 | RC/23-24/343 | 5581 | Sheetal Regalia | Safety Helmet-Ratchet fitting,Shoes-AC 9005
102 | R C Safety Products | DGS Township Pvt Ltd | 2024-02-14 | RC/23-24/321 | 4673 | Sheetal Regalia | Safety Shoes-AC 9006
103 | R C Safety Products | DGS Township Pvt Ltd | 2024-01-09 | RC/23-24/221 | 1888 | Sheetal Regalia | Safety Shoes-Centuar slip on
104 | R C Safety Products | DGS Township Pvt Ltd | 2024-01-19 | RC/23-24/292 | 1982 | Sheetal Regalia | Safety Shoes-Centuar slip on
105 | R C Safety Products | DGS Township Pvt Ltd | 2024-01-09 | RC/23-24/212 | 19018 | Sheetal Regalia | Safety Shoes-AC 9006,Safety Shoes-AC 9005
112 | R S Enterprises | DGS Township Pvt Ltd | 2024-01-23 | 2.022e+44 | 95703 | Sheetal Regalia | Steel onloding,Block
114 | Rushabh Trading Co. | DGS Township Pvt Ltd | 2024-01-15 | 240 | 384703 | Sheetal Regalia | Crush Sand,Metal 1&Metal 2
115 | Rushabh Trading Co. | DGS Township Pvt Ltd | 2024-01-31 | 261 | 160109 | Sheetal Regalia | Crush Sand,Metal 1&Metal 2
116 | Rushabh Trading Co. | DGS Township Pvt Ltd | 2024-01-31 | 268 | 182469 | Sheetal Regalia | Crush Sand,Metal 1&Metal 2
118 | Saikot Mondal | DGS Township Pvt Ltd | 2024-01-16 | 763 | 17136 | Sheetal Regalia | Black back flex print with fitting
119 | Shamsad Alam | DGS Township Pvt Ltd | 2024-03-02 | 6 | 19035 | Sheetal Regalia | Labour Charges Agro shed net,Labour Charges Agro shed
120 | Shamsad Alam | DGS Township Pvt Ltd | 2024-01-10 | 125 | 12684 | Sheetal Regalia | Labour Charges Agro shed net,Labour Charges
121 | Shamsad Alam | DGS Township Pvt Ltd | 2024-02-05 | 150 | 20158 | Sheetal Regalia | Labour Charges Agro shed net,Labour Charges floors repairing of below nets
122 | Santosh Vishwakarma | DGS Township Pvt Ltd | 2024-02-19 |  | 28000 | Sheetal Regalia | Aluminium doors
123 | Saurabh Enterprises | DGS Township Pvt Ltd | 2024-03-08 | 395 | 23010 | Sheetal Regalia | A P Antihack
124 | Saurabh Enterprises | DGS Township Pvt Ltd | 2024-01-08 | 329 | 11800 | Sheetal Regalia | A P Antihack,Roff white addesive
125 | Saurabh Enterprises | DGS Township Pvt Ltd | 2024-01-11 | 336 | 9794 | Sheetal Regalia | Sika Microcrete
126 | Schindler | DGS Township Pvt Ltd | 2024-02-02 | C12700399009 | 200600 | Sheetal Regalia | Composite Supply Of Works Contract In Relation To Immovable Property supply & Installation, Repair & Maintenance Of Elevators & Escalators
127 | Schindler | DGS Township Pvt Ltd | 2024-02-02 | C12700399010 | 200600 | Sheetal Regalia | Composite Supply Of Works Contract In Relation To Immovable Property supply & Installation, Repair & Maintenance Of Elevators & Escalators
128 | Schindler | DGS Township Pvt Ltd | 2024-01-31 | C!2700398663 | 141600 | Sheetal Regalia | Composite Supply Of Works Contract In Relation To Immovable Property supply & Installation, Repair & Maintenance Of Elevators & Escalators
129 | Schindler | DGS Township Pvt Ltd | 2024-01-31 | C12700398664 | 141600 | Sheetal Regalia | Composite Supply Of Works Contract In Relation To Immovable Property supply & Installation, Repair & Maintenance Of Elevators & Escalators
130 | Schindler | DGS Township Pvt Ltd | 2024-01-31 | C12700398665 | 147500 | Sheetal Regalia | Composite Supply Of Works Contract In Relation To Immovable Property supply & Installation, Repair & Maintenance Of Elevators & Escalators
131 | Schindler | DGS Township Pvt Ltd | 2024-01-31 | C12700398666 | 147500 | Sheetal Regalia | Composite Supply Of Works Contract In Relation To Immovable Property supply & Installation, Repair & Maintenance Of Elevators & Escalators
132 | Sea Industries | DGS Township Pvt Ltd | 2024-02-20 | 196 | 89267 | Sheetal Regalia | Dynamon SX222 250 Kg
133 | Sea Industries | DGS Township Pvt Ltd | 2024-02-10 | 192 | 111392 | Sheetal Regalia | Dynamon SX222 250 Kg
136 | Sea Industries | DGS Township Pvt Ltd | 2024-01-04 | 173 | 89621 | Sheetal Regalia | Dynamon SX222
137 | Sea Industries | DGS Township Pvt Ltd | 2024-01-08 | 177 | 133281 | Sheetal Regalia | Dynamon SX222 250 Kg
138 | Sea Industries | DGS Township Pvt Ltd | 2024-02-05 | 189 | 111510 | Sheetal Regalia | Dynamon SX222
139 | Shabbir pipe fitting | DGS Township Pvt Ltd | 2024-02-11 | SPF/103/23-24 | 7852 | Sheetal Regalia | Orisapam White,P Trap Bandle
140 | Shabbir pipe fitting | DGS Township Pvt Ltd | 2024-02-03 | SPF/088/23-24 | 5739 | Sheetal Regalia | 110mm Swr Pipe 3'D/s,11Omm Swr Plain Bend 90,110mm Swr Door Bend,110mm Swr Plain Tee,Rubber Lubricant 250gms,M.S R.Nails 1.112,75mm Swr NahaniTrap WO Jalli,G.l U.Bracket7"x2",G.l U.Bolt 114 4*
141 | Sheetal Shourya Enterprises | DGS Township Pvt Ltd | 2024-02-27 | 4 | 2500000 | Sheetal Regalia | Plinth
142 | Shree Ganesh Electricals | DGS Township Pvt Ltd | 2024-01-29 |  | 404483 | Sheetal Regalia | Slab conduiting work for 1st to E level slab for 20mm pipe
143 | Shree Sai Plumbing Works | DGS Township Pvt Ltd | 2024-03-24 | 88 | 318100 | Sheetal Regalia | Cr. Slop bathroom,Consil Work
144 | Shree Sai Plumbing Works | DGS Township Pvt Ltd | 2024-01-04 | 85 | 82600 | Sheetal Regalia | Sale Office,4 bath+1 kitchen+4 drainage work,Civil office+1 bathrrom
145 | S K Kawasar Ali | DGS Township Pvt Ltd | 2024-01-06 | 2 | 46800 | Sheetal Regalia | Paver block fixing,Department supply M/C
146 | SS Aggregates | DGS Township Pvt Ltd | 2024-02-29 | SS/172/2023-24 | 93488 | Sheetal Regalia | Crush Sand, Metal 1 VSI,Metal 2 VSI
147 | SS Aggregates | DGS Township Pvt Ltd | 2024-02-15 | SS/167/2023-24 | 206606 | Sheetal Regalia | Crush Sand, Metal 1 VSI,Metal 2 VSI
149 | SS Aggregates | DGS Township Pvt Ltd | 2024-01-15 | SS/135/2023-24 | 215863 | Sheetal Regalia | Crush Sand, Metal 1 VSI,Metal 2 VSI
150 | SS Aggregates | DGS Township Pvt Ltd | 2024-01-31 | SS/142/2023-24 | 189756 | Sheetal Regalia | Crush Sand, Metal 1 VSI,Metal 2 VSI
151 | Sudha Sales Corporation | DGS Township Pvt Ltd | 2024-03-17 | SSC/160 | 92160 | Sheetal Regalia | PPC, Birla shakti cement
152 | Sudha Sales Corporation | DGS Township Pvt Ltd | 2024-01-19 | SSC/140 | 206080 | Sheetal Regalia | OPC 53 Grade, Birla shakti cement
153 | Sudha Sales Corporation | DGS Township Pvt Ltd | 2024-02-11 | SSC/148 | 206080 | Sheetal Regalia | OPC 53 Grade, Birla shakti cement
154 | Sudha Sales Corporation | DGS Township Pvt Ltd | 2024-03-17 | SSC/161 | 102400 | Sheetal Regalia | OPC 53 Grade, Birla shakti cement
155 | Sudha Sales Corporation | DGS Township Pvt Ltd | 2024-03-17 | SSC/162 | 122880 | Sheetal Regalia | OPC 53 Grade, Birla shakti cement
156 | Sudha Sales Corporation | DGS Township Pvt Ltd | 2024-03-28 | SSC/165 | 96000 | Sheetal Regalia | PPC, Birla shakti cement
157 | Swami Samartha Enterprises | DGS Township Pvt Ltd | 2024-01-08 |  | 106149 | Sheetal Regalia | Steel onloding,Block
158 | T.H Construction | DGS Township Pvt Ltd | 2024-01-31 | 124 | 16800 | Sheetal Regalia | Excavation work for plot boundry fabrication work
159 | T.H Construction | DGS Township Pvt Ltd | 2024-01-31 | 124 | 16800 | Sheetal Regalia | Excavation work for plot boundry fabrication work
160 | Ultra Tech Cement Limited | DGS Township Pvt Ltd | 2024-01-04 | 8310921645 | 94400 | Sheetal Regalia | OPC 53
161 | Ultra Tech Cement Limited | DGS Township Pvt Ltd | 2024-01-04 | 8310921646 | 94400 | Sheetal Regalia | OPC 53
162 | Ultra Tech Cement Limited | DGS Township Pvt Ltd | 2024-01-04 | 8310921647 | 94400 | Sheetal Regalia | OPC 53
163 | Ultra Tech Cement Limited | DGS Township Pvt Ltd | 2024-01-04 | 8310921652 | 94400 | Sheetal Regalia | OPC 53
164 | Ultra Tech Cement Limited | DGS Township Pvt Ltd | 2024-02-04 | 8310930196 | 94400 | Sheetal Regalia | OPC 53
165 | Umika Enterprises | DGS Township Pvt Ltd | 2024-01-01 | 19 | 94400 | Sheetal Regalia | 25 mm dia coupler
166 | Umika Enterprises | DGS Township Pvt Ltd | 2024-01-03 | 22 | 121778 | Sheetal Regalia | 20 mm threading dia one side,20 mm threading dia both side,25 mm threading dia one side,25 mm threading dia both side
168 | Umika Enterprises | DGS Township Pvt Ltd | 2024-03-02 | 26 | 64664 | Sheetal Regalia | 20 mm dia coupler,25 mm dia coupler
169 | Umika Enterprises | DGS Township Pvt Ltd | 2024-03-03 | 27 | 82441 | Sheetal Regalia | 20 mm threading dia both side,25 mm threading dia both side
170 | Umika Enterprises | DGS Township Pvt Ltd | 2024-03-07 | 33 | 23600 | Sheetal Regalia | 20 mm dia coupler,25 mm dia coupler
171 | Umika Enterprises | DGS Township Pvt Ltd | 2024-03-08 | 34 | 94400 | Sheetal Regalia | 20 mm dia coupler,25 mm dia coupler
172 | Umika Enterprises | DGS Township Pvt Ltd | 2024-01-02 | 20 | 91048 | Sheetal Regalia | 20 mm dia coupler,25 mm dia coupler
173 | Umika Enterprises | DGS Township Pvt Ltd | 2024-01-03 | 21 | 88500 | Sheetal Regalia | 20 mm dia coupler,25 mm dia coupler
174 | Umika Enterprises | DGS Township Pvt Ltd | 2024-02-02 | 23 | 66080 | Sheetal Regalia | 20 mm dia coupler
175 | Umika Enterprises | DGS Township Pvt Ltd | 2024-02-03 | 24 | 70800 | Sheetal Regalia | 25 mm dia coupler
176 | Umika Enterprises | DGS Township Pvt Ltd | 2024-02-03 | 25 | 123144 | Sheetal Regalia | 20 mm threading dia both side,25 mm threading dia both side
177 | Vansh Engineering works | DGS Township Pvt Ltd | 2024-02-28 | 65 | 114238 | Sheetal Regalia | Paraller coupler 20 mm,Paraller coupler 25mm,
178 | Vansh Engineering works | DGS Township Pvt Ltd | 2024-02-29 | 71 | 66021 | Sheetal Regalia | Rebar Threading 20mm,Rebar Threading 25mm
178 | Vansh Engineering works | DGS Township Pvt Ltd | 2024-03-31 | 73 | 28320 | Sheetal Regalia | Paraller coupler 20 mm,Paraller coupler 25mm,
179 | Vansh Engineering works | DGS Township Pvt Ltd | 2024-01-31 | 61 | 49262 | Sheetal Regalia | Rebar Threading 20mm,Rebar Threading 25mm
180 | Wagaj Enterprises | DGS Township Pvt Ltd | 2024-03-09 | 004/2024 | 887000 | Sheetal Regalia | Removing of debris & Supplying of Red Earth, Maure, Building Material, Earth Filling & Cutting Work.
181 | Wagaj Enterprises | DGS Township Pvt Ltd | 2024-01-10 | 002/2024 | 48100 | Sheetal Regalia | Removing of debris & Supplying of Red Earth, Maure, Building Material, Earth Filling & Cutting Work.
182 | Wagaj Enterprises | DGS Township Pvt Ltd | 2024-02-01 | 003/2024 | 60000 | Sheetal Regalia | Removing of debris & Supplying of Red Earth, Maure, Building Material, Earth Filling & Cutting Work.
183 | Greenact | DGS Township Pvt Ltd | 2024-03-18 | 101 | 295000 | Sheetal Regalia | Against for Deatail design engineering Preparation of shop Drawing and documents for submission to MoEF and Structural design
185 | We are one enterprises | DGS Township Pvt Ltd | 2024-03-22 | E/4800/23-24 | 199131 | Sheetal Regalia | ACC Block Cemer,Block joining mortar
186 | S K Traders | DGS Township Pvt Ltd | 2024-03-28 | SK/836/23-24 | 134400 | Sheetal Regalia | Tuff AAC Block
196 | S K Traders | DGS Township Pvt Ltd | 2024-01-03 | SK/650/23-24 | 100800 | Sheetal Regalia | Opc 53
197 | S K Traders | DGS Township Pvt Ltd | 2024-01-03 | SK/651/23-24 | 100800 | Sheetal Regalia | Opc 53
198 | S K Traders | DGS Township Pvt Ltd | 2024-01-03 | SK/652/23-24 | 141120 | Sheetal Regalia | Opc 53
199 | S K Traders | DGS Township Pvt Ltd | 2024-01-06 | SK/658/23-24 | 201600 | Sheetal Regalia | Opc 53
200 | S K Traders | DGS Township Pvt Ltd | 2024-01-07 | SK/664/23-24 | 182980 | Sheetal Regalia | AAC Fly ash block,Magic bond joint mortar
201 | S K Traders | DGS Township Pvt Ltd | 2024-01-09 | SK/670/23-24 | 16638 | Sheetal Regalia | Tufhose White Braided 25mm
202 | S K Traders | DGS Township Pvt Ltd | 2024-01-09 | SK/671/23-24 | 50400 | Sheetal Regalia | Wrap Knit Fabrics
203 | S K Traders | DGS Township Pvt Ltd | 2024-01-09 | SK/675/23-24 | 152985 | Sheetal Regalia | AAC Fly ash block,Magic bond joint mortar
204 | S K Traders | DGS Township Pvt Ltd | 2024-01-09 | SK/676/23-24 | 198400 | Sheetal Regalia | Opc 53
205 | S K Traders | DGS Township Pvt Ltd | 2024-01-18 | SK/691/23-24 | 198400 | Sheetal Regalia | Opc 53
206 | S K Traders | DGS Township Pvt Ltd | 2024-01-20 | SK/693/23-24 | 201600 | Sheetal Regalia | Opc 53
207 | S K Traders | DGS Township Pvt Ltd | 2024-01-21 | SK/700/23-24 | 201600 | Sheetal Regalia | Opc 53
208 | S K Traders | DGS Township Pvt Ltd | 2024-01-30 | SK/718/23-24 | 201600 | Sheetal Regalia | Opc 53
209 | S K Traders | DGS Township Pvt Ltd | 2024-02-12 | SK/743/23-24 | 99200 | Sheetal Regalia | Opc 53
210 | S K Traders | DGS Township Pvt Ltd | 2024-02-12 | SK/744/23-24 | 99200 | Sheetal Regalia | Opc 53
211 | S K Traders | DGS Township Pvt Ltd | 2024-02-12 | SK/747/23-24 | 141120 | Sheetal Regalia | TUFF AAC Block
212 | S K Traders | DGS Township Pvt Ltd | 2024-02-12 | SK/748/23-24 | 130368 | Sheetal Regalia | TUFF AAC Block
215 | S K Traders | DGS Township Pvt Ltd | 2024-01-01 | SK/649/23-24 | 183444 | Sheetal Regalia | AAC Fly ash block,Magic bond joint mortar
216 | S K Traders | DGS Township Pvt Ltd | 2024-02-15 | SK/753/23-24 | 10915 | Sheetal Regalia | Mortar tuff easyfix
217 | S K Traders | DGS Township Pvt Ltd | 2024-02-15 | SK/754/23-24 | 10915 | Sheetal Regalia | Mortar tuff easyfix
218 | S K Traders | DGS Township Pvt Ltd | 2024-02-16 | SK/757/23-24 | 195200 | Sheetal Regalia | Opc 53
219 | S K Traders | DGS Township Pvt Ltd | 2024-02-18 | SK/758/23-24 | 71232 | Sheetal Regalia | TUFF AAC Block
220 | S K Traders | DGS Township Pvt Ltd | 2024-02-18 | SK/759/23-24 | 141120 | Sheetal Regalia | TUFF AAC Block
221 | S K Traders | DGS Township Pvt Ltd | 2024-02-20 | SK/762/23-24 | 134400 | Sheetal Regalia | TUFF AAC Block
222 | S K Traders | DGS Township Pvt Ltd | 2024-02-22 | SK/767/23-24 | 10915 | Sheetal Regalia | Mortar tuff easyfix
223 | S K Traders | DGS Township Pvt Ltd | 2024-02-22 | SK/768/23-24 | 10915 | Sheetal Regalia | Mortar tuff easyfix
224 | S K Traders | DGS Township Pvt Ltd | 2024-02-22 | SK/770/23-24 | 10915 | Sheetal Regalia | Mortar tuff easyfix
225 | S K Traders | DGS Township Pvt Ltd | 2024-02-22 | SK/771/23-24 | 10915 | Sheetal Regalia | Mortar tuff easyfix
226 | S K Traders | DGS Township Pvt Ltd | 2024-02-25 | SK/782/23-24 | 86016 | Sheetal Regalia | PPC
227 | S K Traders | DGS Township Pvt Ltd | 2024-02-27 | SK/785/23-24 | 141120 | Sheetal Regalia | TUFF AAC Block
228 | S K Traders | DGS Township Pvt Ltd | 2024-03-27 | SK/835/23-24 | 10915 | Sheetal Regalia | Mortar tuff easyfix
229 | S K Traders | DGS Township Pvt Ltd | 2024-03-19 | SK/816/23-24 | 134400 | Sheetal Regalia | TUFF AAC Block
230 | S K Traders | DGS Township Pvt Ltd | 2024-03-19 | SK/820/23-24 | 134400 | Sheetal Regalia | TUFF AAC Block
231 | S K Traders | DGS Township Pvt Ltd | 2024-03-19 | SK/821/23-24 | 10915 | Sheetal Regalia | Mortar tuff easyfix
232 | S K Traders | DGS Township Pvt Ltd | 2024-03-19 | SK/824/23-24 | 10915 | Sheetal Regalia | Mortar tuff easyfix
233 | S K Traders | DGS Township Pvt Ltd | 2024-03-24 | SK/833/23-24 | 195200 | Sheetal Regalia | Opc 53
234 | S K Traders | DGS Township Pvt Ltd | 2024-03-24 | SK/834/23-24 | 195200 | Sheetal Regalia | Opc 53
235 | S K Traders | DGS Township Pvt Ltd | 2024-02-16 | SK/756/23-24 | 195200 | Sheetal Regalia | Opc 53
236 | Saurabh Enterprise |  | 2024-04-01 |  | 12000 |  | Chemical Material
237 | Anupam Hardware |  | 2024-04-02 |  | 21098.25 |  | Electric And Hardware Material
238 | S.K Traders |  | 2024-04-06 |  | 44373.81 |  | Hardware Material
239 | Sudha Sales Corporation |  | 2024-04-06 |  | 72000 |  | Cement
240 | S.K Traders |  | 2024-04-07 |  | 152500 |  | Hardware Material
241 | Sea Industries |  | 2024-04-07 |  | 92500 |  | Chemical Material
242 | S.K Traders |  | 2024-04-08 |  | 152500 |  | Hardware Material
243 | Sudha Sales Corporation |  | 2024-04-09 |  | 80000 |  | Cement
244 | Sudha Sales Corporation |  | 2024-04-09 |  | 80000 |  | Cement
245 | S.K Traders |  | 2024-04-10 |  | 91500 |  | Hardware Material
246 | S.K Traders |  | 2024-04-10 |  | 152500 |  | Hardware Material
247 | S.K Traders |  | 2024-04-10 |  | 61000 |  | Hardware Material
248 | Maharashtra Trading Co. |  | 2024-04-10 |  | 108527 |  | Plumbing Material
249 | Sea Industries |  | 2024-04-11 |  | 222000 |  | Chemical Material
250 | Aayush Enterprises-Chemical |  | 2024-04-13 |  | 20700 |  | Chemical Material
251 | Shabbir Pipe Fitting |  | 2024-04-13 |  | 32850.66 |  | Plumbing Material
252 | SS Aggregates |  | 2024-04-15 |  | 393770 |  | C Sand, Metal, Rubble & Ultramod Plaster Sand
253 | Maatangi Enterprrises |  | 2024-04-15 |  | 4444 |  | Black Granite & Marble
254 | Rushabh Trading Co, |  | 2024-04-15 |  | 130801 |  | C Sand, Metal, Rubble & Ultramod Plaster Sand
255 | Sudha Sales Corporation |  | 2024-04-17 |  | 75000 |  | Cement
256 | S.K Traders |  | 2024-04-20 |  | 61000 |  | Hardware Material
257 | S.K Traders |  | 2024-04-20 |  | 76250 |  | Hardware Material
258 | S.K Traders |  | 2024-04-20 |  | 61000 |  | Hardware Material
259 | S.K Traders |  | 2024-04-20 |  | 61000 |  | Hardware Material
260 | S.K Traders |  | 2024-04-20 |  | 76250 |  | Hardware Material
261 | Shabbir Pipe Fitting |  | 2024-04-20 |  | 5670 |  | Plumbing Material
262 | Aetreum Concrete |  | 2024-04-20 |  | 1196600 |  | Rmc (Ready-Mix Concrete)
263 | Fine Steel Corporation |  | 2024-04-21 |  | 1555708.38 |  | Steel
264 | Oracle Granito Ltd |  | 2024-04-23 |  | 528550 |  | Tiles, Granite, Ceramic
265 | Aayush Enterprises-Chemical |  | 2024-04-23 |  | 12000 |  | Chemical Material
266 | Saurabh Enterprise |  | 2024-04-23 |  | 4800 |  | Chemical Material
267 | Vintage Traders |  | 2024-04-24 |  | 128196 |  | GGBS (Ground Granulated Blastfurnace Slag)
268 | Oracle Granito Ltd |  | 2024-04-25 |  | 538160 |  | Tiles, Granite, Ceramic
269 | Shreeji Granite |  | 2024-04-25 |  | 96356.25 |  | Tiles, Granite, Ceramic
270 | JSW Cement Limited |  | 2024-04-25 |  | 118571.5 |  | GGBS (Ground Granulated Blastfurnace Slag)
271 | Fine Steel Corporation |  | 2024-04-25 |  | 1546732.67 |  | Steel
272 | Saurabh Enterprise |  | 2024-04-26 |  | 19500 |  | Chemical Material
273 | S.K Traders |  | 2024-04-26 |  | 152500 |  | Hardware Material
274 | Fine Steel Corporation |  | 2024-04-27 |  | 1530228.2 |  | Steel
275 | Maharashtra Trading Co. |  | 2024-04-27 |  | 20654 |  | Plumbing Material
276 | Fine Steel Corporation |  | 2024-04-29 |  | 1531402.49 |  | Steel
277 | Aayush Enterprises-Chemical |  | 2024-04-29 |  | 12750 |  | Chemical Material
278 | Laxmi Enterprises |  | 2024-04-30 |  | 30544 |  | C Sand, Metal, Rubble & Ultramod Plaster Sand
279 | SS Aggregates |  | 2024-04-30 |  | 249182 |  | C Sand, Metal, Rubble & Ultramod Plaster Sand
280 | S.K Traders |  | 2024-04-30 |  | 9250 |  | Hardware Material
281 | S.K Traders |  | 2024-05-01 |  | 117000 |  | Hardware Material
282 | Bhagwati Ferro Metal Private Limited |  | 2024-05-02 |  | 2158328 |  | Steel
283 | Umika Enterprises |  | 2024-05-05 |  | 58000 |  | Coupler, Labour Work
284 | Mahadev Traders |  | 2024-05-06 |  | 62980 |  | Binding Wire
285 | Umika Enterprises |  | 2024-05-06 |  | 90000 |  | Coupler, Labour Work
286 | Sudha Sales Corporation |  | 2024-05-06 |  | 75000 |  | Cement
287 | Saurabh Enterprise |  | 2024-05-07 |  | 16860 |  | Chemical Material
288 | JSW Cement Limited |  | 2024-05-07 |  | 121071.42 |  | GGBS (Ground Granulated Blastfurnace Slag)
289 | S.K Traders |  | 2024-05-07 |  | 152500 |  | Hardware Material
290 | Shabbir Pipe Fitting |  | 2024-05-07 |  | 19800 |  | Plumbing Material
291 | S.K Traders |  | 2024-05-08 |  | 47600 |  | Hardware Material
292 | S.K Traders |  | 2024-05-08 |  | 152500 |  | Hardware Material
293 | Anupam Hardware |  | 2024-05-10 |  | 8367.63 |  | Electric And Hardware Material
294 | Shabbir Pipe Fitting |  | 2024-05-10 |  | 390683.19 |  | Plumbing Material
295 | S.K Traders |  | 2024-05-10 |  | 152500 |  | Hardware Material
296 | Umika Enterprises |  | 2024-05-10 |  | 64000 |  | Coupler, Labour Work
297 | Vansh Engineering Works (Material) |  | 2024-05-10 |  | 76000 |  | Coupler
298 | JSW Cement Limited |  | 2024-05-10 |  | 121071.42 |  | GGBS (Ground Granulated Blastfurnace Slag)
299 | S.K Traders |  | 2024-05-11 |  | 152500 |  | Hardware Material
300 | JSW Cement Limited |  | 2024-05-12 |  | 121071.42 |  | GGBS (Ground Granulated Blastfurnace Slag)
301 | Anupam Hardware |  | 2024-05-13 |  | 24314.6 |  | Electric And Hardware Material
302 | Sea Industries |  | 2024-05-14 |  | 296000 |  | Chemical Material
303 | Aayush Enterprises-Chemical |  | 2024-05-14 |  | 11400 |  | Chemical Material
304 | JSW Cement Limited |  | 2024-05-15 |  | 121071.42 |  | GGBS (Ground Granulated Blastfurnace Slag)
305 | Fine Steel Corporation |  | 2024-05-15 |  | 1557383.72 |  | Steel
306 | SS Aggregates |  | 2024-05-15 |  | 307602 |  | C Sand, Metal, Rubble & Ultramod Plaster Sand
307 | Aetreum Concrete |  | 2024-05-15 |  | 130200 |  | Rmc (Ready-Mix Concrete)
308 | Sudha Sales Corporation |  | 2024-05-16 |  | 73750 |  | Cement
309 | Schindler India Private Limited |  | 2024-05-16 |  | 750000 |  | Elevator (With Installation)
310 | Schindler India Private Limited |  | 2024-05-16 |  | 720000 |  | Elevator (With Installation)
311 | Schindler India Private Limited |  | 2024-05-16 |  | 1020000 |  | Elevator (With Installation)
312 | Schindler India Private Limited |  | 2024-05-16 |  | 1020000 |  | Elevator (With Installation)
313 | Schindler India Private Limited |  | 2024-05-16 |  | 750000 |  | Elevator (With Installation)
314 | Schindler India Private Limited |  | 2024-05-16 |  | 720000 |  | Elevator (With Installation)
315 | S.K Traders |  | 2024-05-16 |  | 152500 |  | Hardware Material
316 | Fine Steel Corporation |  | 2024-05-17 |  | 1572746.43 |  | Steel
317 | JSW Cement Limited |  | 2024-05-18 |  | 121071.5 |  | GGBS (Ground Granulated Blastfurnace Slag)
318 | Saurabh Enterprise |  | 2024-05-18 |  | 21600 |  | Chemical Material
319 | S.K Traders |  | 2024-05-19 |  | 45018 |  | Hardware Material
320 | Sea Industries |  | 2024-05-21 |  | 148000 |  | Chemical Material
321 | S.K Traders |  | 2024-05-21 |  | 152500 |  | Hardware Material
322 | S.K Traders |  | 2024-05-21 |  | 152500 |  | Hardware Material
323 | Saurabh Enterprise |  | 2024-05-22 |  | 2250 |  | Chemical Material
324 | S.K Traders |  | 2024-05-23 |  | 144300 |  | Hardware Material
325 | S.K Traders |  | 2024-05-23 |  | 13440 |  | Hardware Material
326 | Shreeji Granite |  | 2024-05-23 |  | 33220 |  | Tiles, Granite, Ceramic
327 | S.K Traders |  | 2024-05-24 |  | 38000 |  | Hardware Material
328 | Shabbir Pipe Fitting |  | 2024-05-24 |  | 32670 |  | Plumbing Material
329 | JSW Cement Limited |  | 2024-05-25 |  | 121071.42 |  | GGBS (Ground Granulated Blastfurnace Slag)
330 | Icare Lift System |  | 2024-05-26 |  | 514000 |  | Construction Lift (With Installation)
331 | Mahadev Traders |  | 2024-05-27 |  | 73440 |  | Binding Wire
332 | Anupam Hardware |  | 2024-06-01 |  | 6725.05 |  | Electric And Hardware Material
333 | S.K Traders |  | 2024-06-01 |  | 152500 |  | Hardware Material
334 | S.K Traders |  | 2024-06-01 |  | 152500 |  | Hardware Material
335 | S.K Traders |  | 2024-06-01 |  | 152500 |  | Hardware Material
336 | Aayush Enterprises-Chemical |  | 2024-06-01 |  | 15000 |  | Chemical Material
337 | JSW Cement Limited |  | 2024-06-01 |  | 121071.42 |  | GGBS (Ground Granulated Blastfurnace Slag)
338 | JSW Cement Limited |  | 2024-06-01 |  | 121071.42 |  | GGBS (Ground Granulated Blastfurnace Slag)
339 | JSW Cement Limited |  | 2024-06-01 |  | 121071.42 |  | GGBS (Ground Granulated Blastfurnace Slag)
340 | Sudha Sales Corporation |  | 2024-06-01 |  | 51660 |  | Cement
341 | Sudha Sales Corporation |  | 2024-06-01 |  | 73750 |  | Cement
342 | Sudha Sales Corporation |  | 2024-06-01 |  | 94500 |  | Cement
343 | Sudha Sales Corporation |  | 2024-06-01 |  | 94500 |  | Cement
344 | Sudha Sales Corporation |  | 2024-06-01 |  | 117810 |  | Cement
345 | Saurabh Enterprise |  | 2024-06-01 |  | 19500 |  | Chemical Material
346 | Neeraj Steel Sales |  | 2024-06-01 |  | 1540860.16 |  | Steel
347 | Saurabh Enterprise |  | 2024-06-01 |  | 3850 |  | Chemical Material
348 | Raj Transit Infra Pvt Ltd |  | 2024-06-01 |  | 539365 |  | C Sand, Metal, Rubble & Ultramod Plaster Sand
349 | Raj Transit Infra Pvt Ltd |  | 2024-06-01 |  | 274877 |  | C Sand, Metal, Rubble & Ultramod Plaster Sand
350 | SS Aggregates |  | 2024-06-01 |  | 460494 |  | C Sand, Metal, Rubble & Ultramod Plaster Sand
351 | Pratik Enterprises |  | 2024-06-01 |  | 223783 |  | C Sand, Metal, Rubble & Ultramod Plaster Sand
352 | Rushabh Trading Co, |  | 2024-06-01 |  | 296025 |  | C Sand, Metal, Rubble & Ultramod Plaster Sand
353 | R C Safety Products |  | 2024-06-01 |  | 9480 |  | Safety Shoes, Helmet, Safty Products.
354 | Aayush Enterprises-Chemical |  | 2024-06-01 |  | 42000 |  | Chemical Material
355 | JSW Cement Limited |  | 2024-06-02 |  | 121071.42 |  | GGBS (Ground Granulated Blastfurnace Slag)
356 | JSW Cement Limited |  | 2024-06-02 |  | 121071.42 |  | GGBS (Ground Granulated Blastfurnace Slag)
357 | Umika Enterprises |  | 2024-06-02 |  | 74000 |  | Coupler, Labour Work
358 | Neeraj Steel Sales |  | 2024-06-03 |  | 1531935.58 |  | Steel
359 | JSW Cement Limited |  | 2024-06-03 |  | 121071.42 |  | GGBS (Ground Granulated Blastfurnace Slag)
360 | Shabbir Pipe Fitting |  | 2024-06-03 |  | 358464.14 |  | Plumbing Material
361 | S.K Traders |  | 2024-06-04 |  | 91500 |  | Hardware Material
362 | S.K Traders |  | 2024-06-04 |  | 91500 |  | Hardware Material
363 | S.K Traders |  | 2024-06-04 |  | 122000 |  | Hardware Material
364 | S.K Traders |  | 2024-06-04 |  | 71250 |  | Hardware Material
365 | Vintage Traders |  | 2024-06-04 |  | 168767.5 |  | GGBS (Ground Granulated Blastfurnace Slag)
366 | S.K Traders |  | 2024-06-05 |  | 152500 |  | Hardware Material
367 | JSW Cement Limited |  | 2024-06-05 |  | 121071.42 |  | GGBS (Ground Granulated Blastfurnace Slag)
368 | S.K Traders |  | 2024-06-05 |  | 152500 |  | Hardware Material
369 | Umika Enterprises |  | 2024-06-05 |  | 40000 |  | Coupler, Labour Work
370 | JSW Cement Limited |  | 2024-06-06 |  | 121071.42 |  | GGBS (Ground Granulated Blastfurnace Slag)
371 | Shabbir Pipe Fitting |  | 2024-06-08 |  | 32670 |  | Plumbing Material
372 | Oracle Granito Ltd |  | 2024-06-08 |  | 523745 |  | Tiles, Granite, Ceramic
373 | Umika Enterprises |  | 2024-06-09 |  | 40000 |  | Coupler, Labour Work
374 | Sea Industries |  | 2024-06-10 |  | 222000 |  | Chemical Material
375 | S.K Traders |  | 2024-06-10 |  | 152500 |  | Hardware Material
376 | Vansh Engineering Works (Material) |  | 2024-06-10 |  | 76000 |  | Coupler
377 | R C Safety Products |  | 2024-06-10 |  | 3400 |  | Safety Shoes, Helmet, Safty Products.
378 | Shabbir Pipe Fitting |  | 2024-06-11 |  | 350192.6 |  | Plumbing Material
379 | BMCC Enterprises |  | 2024-06-11 |  | 31980 |  | C Sand, Metal, Rubble & Ultramod Plaster Sand
380 | Oracle Granito Ltd |  | 2024-06-12 |  | 528550 |  | Tiles, Granite, Ceramic
381 | Shabbir Pipe Fitting |  | 2024-06-13 |  | 63256.01 |  | Plumbing Material
382 | Shreeji Granite |  | 2024-06-15 |  | 34056.77 |  | Tiles, Granite, Ceramic
383 | JSW Cement Limited |  | 2024-06-15 |  | 121071.42 |  | GGBS (Ground Granulated Blastfurnace Slag)
384 | JSW Cement Limited |  | 2024-06-15 |  | 121071.42 |  | GGBS (Ground Granulated Blastfurnace Slag)
385 | S.K Traders |  | 2024-06-15 |  | 68400 |  | Hardware Material
386 | SS Aggregates |  | 2024-06-15 |  | 89870 |  | C Sand, Metal, Rubble & Ultramod Plaster Sand
387 | Raj Transit Infra Pvt Ltd |  | 2024-06-15 |  | 428667 |  | C Sand, Metal, Rubble & Ultramod Plaster Sand
388 | S.K Traders |  | 2024-06-17 |  | 120965.25 |  | Hardware Material
389 | JSW Cement Limited |  | 2024-06-17 |  | 121071.42 |  | GGBS (Ground Granulated Blastfurnace Slag)
390 | JSW Cement Limited |  | 2024-06-21 |  | 121071.5 |  | GGBS (Ground Granulated Blastfurnace Slag)
999684711.56

## Land, Stamp Duty and rent cost
Stamp Duty & Registration Fees
Sr. No. | Agreement Name | Date | Particulars | Amount | Incurred Amoun | August 21 - July22 | 12
1 | Development Agreement | 2022-07-15 | Stamp Duty | 28554200 | 28554200 | August 22 - June 23 | 10
2 |  |  | Reg. Fees | 30000 | 30000 | July 23 - August 24 | 14
3 |  |  |  | 2000 | 2000 | Sept 24 - July 25 | 11
5 | SupplementaryAttorney | 2021-09-26 | Stamp Duty | 500 | 500 | August 25 - June 26 | 11
6 | Power of Attorney | 2021-04-27 |  | 1100 | 1100 | July 26 - Sept 26 | 3
| TOTAL |  |  | 28587800 | 28587800
Sr. No. | Particulars
1 | No. of Tenants | 216 | Nos.
2 | Total Carpet Area in Sq. Ft. | 68006 | Sq. Ft.
3 | Rent per Sq. Ft. per month for first 22 Months | 60 | Rupees
4 | Rent per month for first 22 Months | 4080360 | Rupees
5 | Rent for 22 Months | 89767920 | Rupees
6 | Rent per Sq. Ft. per Month for 23 to 36 Months | 66 | Rupees
7 | Rent per month for 23 to 36 Months | 4488396 | Rupees
8 | Rent for 14 Months | 62837544 | Rupees
9 | Rent per Sq. Ft. per Month for next 11 month | 72.6 | Rupees
10 | Rent per month for till next 11 month | 4937236 | Rupees
11 | Rent for 11 Months | 54309596 | Rupees
12 | Rent per Sq. Ft. per Month for next 11 month | 79.86 | Rupees
13 | Rent per month for till next 11 month | 5430959 | Rupees
14 | Rent for 11 Months | 59740549 | Rupees
15 | Rent per Sq. Ft. per Month for next 3 month | 87.846 | Rupees
16 | Rent per month for till next 3 month | 5974055 | Rupees
17 | Rent for 3 Months | 17922165 | Rupees
18 | Brokerage | 4080360 | Rupees
19 | Hardship 1000 per Sq. Ft. | 68006000 | Rupees
20 | Shifting Charges | 4320000 | Rupees
| Additional corpus fund | 51004500 | Rupees
21 | Total Rent Cost | 411988634 | Rupees

## Construction Area sale building
| As per concession drawing plan |  | As per amended approved plan |  |  |  |  | As per concession drawing Plan | As per amended approved plan
Sr. | Floor As per previous concession plan | Total Construction Area in Sq. Ft. | Floor As per Amended approved plan | Total Construction Area in Sq. Ft. | Difference Area in Sq. Ft. | Completed Area in Sq. Ft. | Rate per Sq. Ft. | Full Value after completion | Full Value after completion | % of work completed | Actual Expenditure till date in `
1 | Ground Floor | 28543.5446 | Ground Floor | 33799.9288 | 5256.3841 | 33799.9288 | 2850 | 81349102.224 | 96329796.966 | 85% | 81880327.4211
2 | 1st Commerical Floor | 29453.2103 | 1st Commerical Floor | 34362.0248 | 4908.8146 | 34362.0248 | 2850 | 83941649.298 | 97931770.794 | 80% | 78345416.6352
3 | 2nd Podium Floor | 36741.0669 | 2nd Commerical Floor | 34702.9207 | -2038.1462 | 34702.9207 | 2850 | 104712040.6582 | 98903324.052 | 75% | 74177493.039
4 | 3rd Podium Floor | 36741.0303 | 1st Podium Floor | 37280.5758 | 539.5455 | 37280.5758 | 2850 | 104711936.355 | 106249641.03 | 70% | 74374748.721
5 | 4th Podium Floor | 36741.0303 | 2nd Podium Floor | 37280.5758 | 539.5455 | 37280.5758 | 2850 | 104711936.355 | 106249641.03 | 70% | 74374748.721
6 | 5th Podium Floor | 6424.2781 | 3rd Podium Floor | 37280.5758 | 30856.2977 | 37280.5758 | 2850 | 18309192.642 | 106249641.03 | 70% | 74374748.721
7 | 1st Habitable Floor | 14132.4862 | 4th E - Level Floor | 34900.5478 | 20768.0616 | 34900.5478 | 2850 | 40277585.556 | 99466561.116 | 50% | 49733280.558
8 | 2nd Habitable Floor | 17783.5273 | 1st Habitable Floor | 16459.9859 | -1323.5414 | 16459.9859 | 2850 | 50683052.862 | 46910959.758 | 50% | 23455479.879
9 | 3rd Habitable Floor | 17783.5273 | 2nd Habitable Floor | 16459.9859 | -1323.5414 | 16459.9859 | 2850 | 50683052.862 | 46910959.758 | 50% | 23455479.879
10 | 4th Habitable Floor | 17788.694 | 3rd Habitable Floor | 16459.9859 | -1328.7082 | 16459.9859 | 2850 | 50697778.014 | 46910959.758 | 50% | 23455479.879
11 | 5th Habitable Floor | 17788.694 | 4th Habitable Floor | 16504.5488 | -1284.1452 | 16504.5488 | 2850 | 50697778.014 | 47037964.194 | 50% | 23518982.097
12 | 6th Habitable Floor | 17836.9168 | 5th Habitable Floor | 16956.8521 | -880.0646 | 16956.8521 | 2850 | 50835212.766 | 48327028.542 | 40% | 19330811.4168
13 | 7th Habitable Floor | 17897.9486 | 6th Habitable Floor | 17038.228 | -859.7207 |  | 2850 | 51009153.624 | 48558949.686
14 | 8th Habitable Floor | 14356.485 | 7th Habitable Floor | 17038.228 | 2681.743 |  | 2850 | 40915982.25 | 48558949.686
15 | 9th Habitable Floor | 18014.0922 | 8th Habitable Floor | 17885.57 | -128.5222 |  | 2850 | 51340162.77 | 50973874.614
16 | 10th Habitable Floor | 18125.6072 | 9th Habitable Floor | 18037.4501 | -88.1572 |  | 2850 | 51657980.634 | 51406732.728
17 | 11th Habitable Floor | 18125.6072 | 10th Habitable Floor | 18037.4501 | -88.1572 |  | 2850 | 51657980.634 | 51406732.728
18 | 12th Habitable Floor | 18125.6072 | 11th Habitable Floor | 18037.4501 | -88.1572 |  | 2850 | 51657980.634 | 51406732.728
19 | 13th Habitable Floor | 18125.6072 | 12th Habitable Floor | 18037.4501 | -88.1572 |  | 2850 | 51657980.634 | 51406732.728
20 | 14th Habitable Floor | 18125.6072 | 13th Habitable Floor | 18037.4501 | -88.1572 |  | 2850 | 51657980.634 | 51406732.728
21 | 15th Habitable Floor | 17205.3929 | 14th Habitable Floor | 18037.4501 | 832.0572 |  | 2850 | 49035369.708 | 51406732.728
22 | 16th Habitable Floor | 18125.6072 | 15th Habitable Floor | 18231.8479 | 106.2407 |  | 2850 | 51657980.634 | 51960766.572
23 | 17th Habitable Floor | 18125.6072 | 16th Habitable Floor | 18037.4501 | -88.1572 |  | 2850 | 51657980.634 | 51406732.728
24 | 18th Habitable Floor | 18125.6072 | 17th Habitable Floor | 18037.4501 | -88.1572 |  | 2850 | 51657980.634 | 51406732.728
25 | 19th Habitable Floor | 18125.6072 | 18th Habitable Floor | 18037.4501 | -88.1572 |  | 2850 | 51657980.634 | 51406732.728
26 | 20th Habitable Floor | 18125.6072 | 19th Habitable Floor | 18037.4501 | -88.1572 |  | 2850 | 51657980.634 | 51406732.728
27 | 21st Habitable Floor | 14873.157 | 20th (Part) Habitable Floor | 8222.4043 | -6650.7527 |  | 2850 | 42388497.45 | 23433852.312
28 | Terrace / OHT | 4721.3057 | Terrace / OHT | 4799.56 | 78.2543 |  | 2850 | 13455721.188 | 13678745.886
TOTAL |  | 546082.46 |  | 596038.847 | 49956.3871 | 332448.5081 |  | 1556335010.9362 | 1698710714 | 39.87% | 620476997 | 39.87%
[9 empty] | 142375703.0638 |  | 115000000 | Mivan Material
[10 empty] | 47.26% | 735476997 | 47.26%
[11 empty] | 116000000 | Material Onsite
[10 empty] | 54.71% | 851476997 | 54.71%
[10 empty] | 64.23% | 999684712 | 64.23%
[11 empty] | 148207715 | Advance Payment

## Sheet1
Sr. | Floor | Total Construction Area in Sq. Ft. | Completed Area in Sq. Ft. | Rate per Sq. Ft. | Full Value after completion | % of work completed | Actual Expenditure till date in `
1 | Ground Floor + 1st to 23rd Floor | 74747 | 0 | 2000 | 149494000 | 35% | 52322900
TOTAL |  | 74747 | 0 |  | 149494000 | 35% | 52322900