## Final Summary
Project expenses | Project Cost as per Sanction Letter | Incurred Cost as per Bill till 31.08.2024 | Incurred Cost as per CA till 25.06.2024 | Difference between the Bills & CA | Difference between both the Bills | Difference between both CA | Remark
Land Cost (Upfront Fees, Stamp Duty & Other Charges) | 33.5 | 33.409 | 33.41 | -0.001
Construction Cost | 84.89 | 6.0805 | 2.75 | 3.3305 |  |  | Only Construction Cost related bills are considered without Taxes amount
P&M Utilities | 127.66 | 0 | 0 | 0
Design, Approval Cost & Other Cost | 15 | 8.8167 | 8.8 | 0.016697
Consultancy Fees, Preliminary & Pre - Operative Exp. | 22.47 | 17.2482 | 12.59 | 4.6582 |  |  | Security Bill, Prof. bills & other admin cost are considered in this header
Contingency Cost | 10.63 | 0 | 0 | 0
Bank Guarantee against FD | 1.25 | 0 | 0 | 0
Interest Cost During Construction | 26.23 | 0.020002 | 3.33 | -3.31 |  |  | Only interest cost is considered by us and ca has considered the bank processing charges in interest cost head
Total Cost | 321.63 | 65.5744 | 60.88 | 4.6944 | 0 | 0
|  | 256.0556 |  | 18.93%
Particulars | Project Cost as per Sanction Letter | Reasonable Cost certified by VICPL till 31.08.2024 | Cost incurred as %age total cost of that Component | Cost incurred as %age of cost incurred as on 31.08.2024 | % project cost
Land Cost (Upfront Fees, Stamp Duty & Other Charges) | 33.5 | 33.409 | 99.73% | 10.39% | 10.42%
Construction Cost | 84.89 | 6.0805 | 7.163% | 1.891% | 26.39%
P&M Utilities | 127.66 | 0 | 0% | 0% | 39.69%
Design, Approval Cost & Other Cost | 15 | 8.8167 | 58.78% | 2.741% | 4.664%
Consultancy Fees, Preliminary & Pre - Operative Exp. | 22.47 | 17.2482 | 76.76% | 5.363% | 6.986%
Contingency Cost | 10.63 | 0 | 0% | 0% | 3.305%
Bank Guarantee against FD | 1.25 | 0 | 0% | 0% | 0.3886%
Interest Cost During Construction | 26.23 | 0.020002 | 0.07626% | 0.006219% | 8.155%
Total | 321.63 | 65.5744 | 20.39% | 20.39% | 100%
Pariculars | 31.08.2024 as per Bill Tally (inclusive of GST) | CA Certificate till 25.06.2024 | Difference b/w bills of 31.08.2024 & CA Certificate | Difference of Cost incurred as %age of cost incurred as on 31.08.2024 & CA Certificate
Land Cost (Upfront Fees, Stamp Duty & Other Charges) | 33.409 | 33.41 | 0 | 0%
Construction Cost | 6.0805 | 2.75
P&M Utilities | 0 | 0 | -2.75 | -4.194%
Design, Approval Cost & Other Cost | 8.8167 | 8.8 | 0.02 | 0.0305%
Consultancy Fees, Preliminary & Pre - Operative Exp. | 17.2482 | 12.59 | 4.66 | 7.106%
Contingency Cost | 0 | 0 | 0 | 0%
Bank Guarantee against FD | 0 | 0 | 0 | 0%
Interest Cost During Construction | 0.020002 | 3.33 | -3.31 | -5.048%
Total | 65.5744 | 60.88 | 4.69 | 7.152%

## Construction Area
Construction Cost
Sr. | Particulars | Area in Sq. Ft. | Rate / Sq. Ft. | Construction Cost in ` | Completed Area in Sq. M. | % of work completed | Actual Expenditure till date in `
I | Civil & Structure Works
1 | Structure Works | 280100 | 1100 | 308110000 |  |  | 0
2 | Masonry And Screed Works | 280100 | 240 | 67224000 |  |  | 0
3 | Soil Nailing Works | 280100 | 5 | 1400500 |  |  | 0
4 | Shore Pilling | 280100 | 10 | 2801000 |  |  | 0
5 | Plinth construction for tented Villas | 280100 | 25 | 7002500 |  |  | 0
6 | Retaining Walls in landscape areas | 280100 | 145 | 40614500 |  |  | 0
7 | Allowance for site attendance | 280100 | 101 | 28290100 |  |  | 0
Total Civil & Structure Work Cost |  |  |  | 455442600 |  | 0% | 0
II | Façade Works
1 | Glazing | 58352 | 985 | 57476720 |  |  | 0
2 | Cladding | 51743 | 175 | 9055025 |  |  | 0
3 | Banquet & Pre - function Canopy | 4187 | 1460 | 6113020 |  |  | 0
4 | Arrival | 11302 | 765 | 8646030 |  |  | 0
5 | Hanger | 3692 | 1020 | 3765840 |  |  | 0
6 | Kids Club & Play | 7223 | 435 | 3142005 |  |  | 0
7 | Trells | 3606 | 775 | 2794650 |  |  | 0
8 | GRC Screen | 55079 | 465 | 25611735 |  |  | 0
9 | Painting | 122893 | 185 | 22735205 |  |  | 0
10 | Façade Lighting |  |  | 1660000 |  |  | 0
Total Façade Work Cost |  |  |  | 141000230 |  | 0% | 0
III | External Works
1 | Boundary Wall | 280100 | 4 | 1120400 |  |  | 0
2 | Terrace Balustrades | 280100 | 9 | 2520900 |  |  | 0
3 | Roof Terrace | 280100 | 85 | 23808500 |  |  | 0
4 | Hardscape | 280100 | 65 | 18206500 |  |  | 0
5 | Walkway | 280100 | 8 | 2240800 |  |  | 0
6 | Deck | 280100 | 17 | 4761700 |  |  | 0
7 | Soft Scape Area | 280100 | 32 | 8963200 |  |  | 0
8 | Buggy Path | 280100 | 18 | 5041800 |  |  | 0
9 | Pool and water bodies | 280100 | 40 | 11204000 |  |  | 0
10 | Great Grand Stair | 280100 | 40 | 11204000 |  |  | 0
11 | Kerb Stone | 280100 | 3 | 840300 |  |  | 0
12 | Cliff Pool, Deck & Bar, | 280100 | 45 | 12604500 |  |  | 0
13 | Cliff Pool, Deck & Bar, Steppingstones | 280100 | 14 | 3921400 |  |  | 0
14 | Creepers | 280100 | 12 | 3361200 |  |  | 0
15 | Kids Area | 280100 | 7 | 1960700 |  |  | 0
16 | Gate | 280100 | 5 | 1400500 |  |  | 0
17 | External Lighting | 280100 | 25 | 7002500 |  |  | 0
18 | Miscellaneous (For Fixed Furniture / Pots, etc.) | 280100 | 10 | 2801000 |  |  | 0
Total External Work Cost |  |  |  | 122963900 |  | 0% | 0
SUB - TOTAL CONSTRUCTION COST (I + II + III) |  |  |  | 719406730 |  | 0% | 0
18% GST Amount on Sub - Total Construction Cost |  |  |  | 129493211 | 0 |  | 0
TOTAL CONSTRUCTION COST |  |  |  | 848899941 |  | 0% | 0

## P&M Utilities
P&M Utilities Cost
Sr. | Particulars | Area in Sq. Ft. | Rate / Sq. Ft. | Construction Cost in ` | Completed Area in Sq. M. | % of work completed | Actual Expenditure till date in `
I | Hotel BOH Areas
1 | Hotel BOH Areas | 28180 | 655 | 18457900 |  |  | 0
2 | NON - AC Area | 17922 | 459 | 8226198 |  |  | 0
3 | Hotel MEP Areas | 21485 | 401 | 8615485 |  |  | 0
Total Hotel BOH Areas Cost |  |  |  | 35299583 |  | 0% | 0
II | Hotel Pubilc Area & F&B
1 | Lobby | 6372 | 2890 | 18415080 |  |  | 0
2 | Banquet Hall | 8547 | 2890 | 24700830 |  |  | 0
3 | Pre - Function Area | 5845 | 2315 | 13531175 |  |  | 0
4 | Meeting Room | 1991 | 1850 | 3683350 |  |  | 0
5 | Restaurant | 6512 | 4050 | 26373600 |  |  | 0
6 | Outdoor F&B Areas | 4790 | 1740 | 8334600 |  |  | 0
7 | Spa | 5909 | 3240 | 19145160 |  |  | 0
8 | Public Area Circulation | 334 | 2160 | 721440 |  |  | 0
9 | Lift Car Interiors | 43 | 38555 | 1657865 |  |  | 0
Total Hotel Public Area & F&B Cost |  |  |  | 116563100 |  | 0% | 0
III | Guest Room
1 | Hill Rooms (Higher Unit) | 25102 | 3300 | 82836600 |  |  | 0
2 | Hill Rooms (Lower Unit) | 21506 | 3500 | 75271000 |  |  | 0
3 | Sea Room | 14467 | 3500 | 50634500 |  |  | 0
4 | Garden Room | 11195 | 3100 | 34704500 |  |  | 0
5 | Tented Villas | 11840 | 3500 | 41440000 |  |  | 0 | 1883636.3636
Total Guest Room Cost |  |  |  | 284886600 |  | 0% | 0
IV | Loose & Fixed Furniture
A | Hotel BOH Areas
1 | Hotel BOH Areas | 28180 | 35 | 986300 |  |  | 0
2 | Hotel MEP Areas | 21485 | 20 | 429700 |  |  | 0
3 | Lobby | 6372 | 970 | 6180840 |  |  | 0
4 | Banquet Hall | 8547 | 970 | 8290590 |  |  | 0
5 | Pre - Function Area | 5845 | 770 | 4500650 |  |  | 0
6 | Meeting Room | 1991 | 470 | 935770 |  |  | 0
7 | Restaurant | 6512 | 1350 | 8791200 |  |  | 0
8 | Outdoor F&B Areas | 4790 | 580 | 2778200 |  |  | 0
B | Guest Rooms
1 | Hill Rooms (Higher Unit) | 25102 | 1150 | 28867300 |  |  | 0
2 | Hill Rooms (Lower Unit) | 21506 | 1150 | 24731900 |  |  | 0
3 | Sea Room | 14467 | 1160 | 16781720 |  |  | 0
4 | Garden Room | 11195 | 1030 | 11530850 |  |  | 0
5 | Tented Villas | 11840 | 1170 | 13852800 |  |  | 0 | 629672.7273
Total Loose & Furniture Cost |  |  |  | 128657820 |  | 0% | 0
V | Corridor and Lift Lobby
1 | Corridor and Lift Lobby | 41872 | 1230 | 51502560 |  |  | 0
Total Corridor and Lift Lobby Cost |  |  |  | 51502560 |  | 0% | 0
VI | Internal Signage @ way finding
1 | Guest Rooms | 280100 | 3 | 840300 |  |  | 0
2 | Guest Room Corridors | 280100 | 4 | 1120400 |  |  | 0
3 | Public | 280100 | 2 | 560200 |  |  | 0
4 | Outdoor & Pathway | 280100 | 3 | 840300 |  |  | 0
5 | Main Hotel Signages | 280100 | 5 | 1400500 |  |  | 0
Total Internal Signage @ way finding Cost |  |  |  | 4761700 |  | 0% | 0
VII | MEP Services
1 | HVAC Works | 280100 | 224 | 62742400 |  |  | 0
2 | Electrical | 280100 | 291 | 81509100 |  |  | 0
3 | Plumbing & Sanitary Systems | 280100 | 292 | 81789200 |  |  | 0
4 | HVAC + Electrical + Plumbing for tented villas and hilltop rooms | 280100 | 48 | 13444800 |  |  | 0
5 | Fire Fighting System | 280100 | 81 | 22688100 |  |  | 0
6 | Extra Low Voltage | 280100 | 101 | 28290100 |  |  | 0
7 | Audio Visual | 280100 | 60 | 16806000 |  |  | 0
8 | IT Network and Software | 280100 | 90 | 25209000 |  |  | 0
Total MEP Services Cost |  |  |  | 332478700 |  | 0% | 0
VIII | Elevators
1 | Elevators | 280100 | 60 | 16806000 |  |  | 0
Total Elevators Cost |  |  |  | 16806000 |  | 0% | 0
IX | Specialized Building Equipment
1 | Hotel Kitchen Equipment | 280100 | 160 | 44816000 |  |  | 0
2 | Hotel Laundry | 280100 | 36 | 10083600 |  |  | 0
3 | Hotel Gym + SPA | 280100 | 30 | 8403000 |  |  | 0
4 | Hotel Secuirty | 280100 | 30 | 8403000 |  |  | 0
5 | Façade Cleaning | 280100 | 3 | 840300 |  |  | 0
6 | Solar Panel - Electrical | 280100 | 3 | 840300 |  |  | 0
7 | Solar Panel - Water Heating | 280100 | 5 | 1400500 |  |  | 0
Total Specialized Building Equipment Cost |  |  |  | 74786700 |  | 0% | 0
X | Hotel OS&E
1 | Hotel OS&E | 280100 | 130 | 36413000 |  |  | 0
Total Hotel OS&E Cost |  |  |  | 36413000 |  | 0% | 0
SUB - TOTAL P&M UTILITIES COST (I + II + III) |  |  |  | 1082155763 |  | 0% | 0
18% GST Amount on Sub - Total P&M Utilities Cost |  |  |  | 194788037 |  |  | 0
TOTAL P&M UTILITIES COST |  |  |  | 1276943800 |  | 0% | 0

## Summary Sheet
Sr. No. | Particulars | Incurred Cost in ` till 31.08.2024 as per bill | Incurred Cost in ` Cr. Till 31.08.2024 | Incurred Cost in ` till 25.06.2024 as per CA | Incurred Cost in ` Cr. till 25.06.2024 as per CA | Balance | Balance in Cr.
1 | Land Cost (Upfront Fees, Stamp Duty & Other Charges) | 334090000 | 33.409 |  | 0 | 334090000 | 33.409
2 | Construction Cost | 60805075 | 6.0805 |  | 0 | 60805075 | 6.0805
3 | P&M Utilities | 0 | 0 |  |  | 0 | 0
4 | Design, Approval Cost & Other Cost | 88166968 | 8.8167 |  |  | 88166968 | 8.8167
5 | Consultancy Fees, Preliminary & Pre - Operative Exp. | 172482173 | 17.2482 |  | 0 | 172482173 | 17.2482
6 | Contingency Cost | 0 | 0 |  | 0 | 0 | 0
7 | Interest Cost During Construction | 200018 | 0.020002 |  | 0 | 200018 | 0.020002
| Total | 655744234 | 65.5744 | 0 | 0 | 655744234 | 65.5744
262300000
262099982

## Land Cost
Land Cost Description
Sr. No. | Date | Description | Total Cost in ` | Incurred Cost in `
1 | 2017-03-07 | 10% Upfront Concession Fees | 32200000 | 32200000
2 | 2018-01-12 | 90% Upfront Concession Fees | 297360000 | 297360000
3 | 2024-06-10 | Consultancy Fees | 4530000 | 4530000
Total |  |  | 334090000 | 334090000

## TDR & Approval
Sr. | PARTICULARS | TOTAL AMOUNT
1 | Gram Panchayat NOC | 9246422
2 | Electricity Permission | 181576
3 | Pollution Control NOC | 427128
4 | Reimbursement of Expenses | 700092.55
5 | ROC Filing Fees | 125015
6 | Sanad Payment | 47383200
7 | TCP Payment | 23726034
8 | GTDC LTD | 6377500
TOTAL |  | 88166968

## Construction Cost Bills
Sr. | Invoice Date | Invoice No. | Vendor Name | Description | Basic Amount in ` | GST Amount in ` | Total Amount
1 | 2024-04-27 | YKBINF/24-25/PI001 | YKB Infra Pvt. Ltd. | Material cost of profile sheet & labour cost of fabrication with screws | 4255075 | 765914 | 5020989
2 | 2024-08-09 | YKB/24-25/PI005 | YKB Developers & Consultants | Construction Services | 30000000 | 5400000 | 35400000
3 | 2023-11-18 | YKB/23-24/005 | YKB Developers & Consultants | Construction Services | 26550000 | 4779000 | 31329000
Grand Total |  |  |  |  | 60805075 | 10944914 | 71749989

## P&M Utilities Bills
Sr. | Invoice Date | Invoice No. | Vendor Name | Description | Gross Total
1 |  |  |  |  | 0
Grand Total |  |  |  |  | 0

## CPPOE
CONSULTANCY FEES, PRELIMINARY & PRE-OPERATIVE EXP
Consultancy Fees and Preliminary & Pre-Operative Exp. | Equity | Debt | Total
Aditya Environmental Services Pvt Ltd | 1035819 |  | 1035819
Alila Hotels & Resorts Pte Ltd | 7140141 |  | 7140141
Amay A. Phadte | 375000 |  | 375000
Amithkumar Ashok Kotharkar | 248500 | 206150 | 454650
AON FinTech Private Limited | 230000 |  | 230000
Arnav Narain | 280900 |  | 280900
Ascentis India Projects Pvt Ltd | 8963340 |  | 8963340
Atulkumar Trivedi | 45000 | 45000 | 90000
Bharat M. Soni | 100000 |  | 100000
Bharat Infrastructure & Engineering Ltd | 9000000 |  | 9000000
Burega Farnell (L.A.) PTE. LTD | 6673842 |  | 6673842
Care Advisory Research and Training Limited | 100000 |  | 100000
Centbank Financial Services Limited | 686357 |  | 686357
Chandan Parab Design | 590000 |  | 590000
CRISIL Limited | 365000 |  | 365000
D.V.Mane Associates LLP | 75000 |  | 75000
DESIGNERS GROUP | 2602500 | 141240 | 2743740
DUN & BRADSTREET INFORMATION SERVICES INDIA PVT LTD | 515000 |  | 515000
EDG Design- Asia Pte Ltd | 2864680 |  | 2864680
FinMen Advisors Pvt Ltd | 1650000 |  | 1650000
Fyrprotek Fire & Life Safety Consultants | 100000 |  | 100000
Gangotri Groundwater Consultants | 17797 |  | 17797
GMD Consultants | 75000 |  | 75000
Goldrush Capital Services Pvt Ltd | 300000 |  | 300000
Grune Designs Private Limited | 2270440 | 280260 | 2550700
HIGHTEC ENGINEERS | 70000 |  | 70000
HPG Consulting India Pvt Ltd | 977500 |  | 977500
HSA Advocates | 250000 |  | 250000
IMPCE Consultants Pvt Ltd | 112500 |  | 112500
Impress Pmc | 412500 | 847500 | 1260000
INFOMERICS VALUATION AND RATING PRIVATE LIMITED | 1320000 |  | 1320000
Infotronics Integrators (India) Pvt Ltd | 3475 |  | 3475
Ishaan Patkar | 755253 |  | 755253
Jayantilal Thakkar Associates | 20000 |  | 20000
Jhaveri & Jhaveri | 85000 |  | 85000
Jones Lang LaSallePropertyConsultants(India)Pvt Ltd | 900000 |  | 900000
Joshi Engineering Consultancy | 145000 |  | 145000
Kagrana & Associates | 465750 |  | 465750
Kaizen Design Solutions | 100000 |  | 100000
Kavin Gulati | 2282500 |  | 2282500
Ketan Dand | 16000 |  | 16000
KLD Consulting Pte Ltd | 3021518 |  | 3021518
Krishnakant A. Pandat | 25000 |  | 25000
LEXICON LAW PARTNERS | 800000 |  | 800000
Light @ Work Desige Consultants Pvt Ltd |  | 663750 | 663750
Link Legal | 502712 |  | 502712
Meghnath Navlani | 50000 |  | 50000
Modern Surveyors | 214500 |  | 214500
N. Somasundaram | 74250 |  | 74250
N.K.Singhai & Associates | 50700 | 10600 | 61300
Orbit Law Services | 75615 |  | 75615
Paresh Gaitonde | 2223000 |  | 2223000
Pool Water Concepts Pvt Ltd | 90000 |  | 90000
PRADEEP NAMDEO CHAVAN | 53000 |  | 53000
Pradip Shukla & Co. | 20000 | 30000 | 50000
Pranit Mahesh Ponkshe | 27500 |  | 27500
Pravin Kulkarni & Association | 6000 |  | 6000
Punjab National Bank Account No. 3502002100040041 | 27778 |  | 27778
Rendercard Pvt Ltd | 46000 |  | 46000
S & M Hospitality Private Limited | 382742 |  | 382742
S. S. Gupta Chartered Accountant | 915000 |  | 915000
Sai Krupa Solutions | 4400 |  | 4400
Santosh R.Shetty & Associates | 50000 |  | 50000
Shivan Desai | 250000 |  | 250000
Sidhpura Consultancy | 3100000 | 380000 | 3480000
SM Studio | 120000 |  | 120000
SNG AND PARTNERS | 1200000 |  | 1200000
Stratfin Services | 4000000 | 7500000 | 11500000
Suresh C. Maniar & Associates | 539500 | 11800 | 551300
THE INDIAN HOTELS COMAPNY LIMITED |  | 3240000 | 3240000
Thite Valuers & Engineers Pvt. Ltd. | 5775 |  | 5775
Unitech Engineers | 377385 |  | 377385
Urbnarc Pte Ltd | 30374395 |  | 30374395
Vastukala Consultants (I) Pvt. Ltd. | 7500 | 23500 | 31000
VCNS GLOBAL |  | 128400 | 128400
Vibha Patni & Associates | 15000 |  | 15000
Whitby Wood Pritamdasani Consulting Engineers Pl | 1890000 |  | 1890000
SBICAP TRUSTEE COMPANY LIMITED | 415220 |  | 415220
INFOMERICS VALUATION AND RATING PRIVATE LIMITED | 9000 |  | 9000
Xteria | 25000 |  | 25000
Mahimtura Consultants Pvt Ltd. | 192674 | 0 | 192674
Assured Advertising & Media Pvt LTd | 77660 | 32340 | 110000
Commission & Brokarage | 25000 |  | 25000
Conveyance & Travelling | 177776 |  | 177776
Conveyance & Travelling | 24900 |  | 24900
Demat Account Charges | 13520 |  | 13520
Electricity Charges | 65426 |  | 65426
Filing Fees | 23187 |  | 23187
Franking Charges | 1400 |  | 1400
GST Exps | 820565 | 247437 | 1068002
Infotronics Integrators (India) Pvt Ltd | 5425 |  | 5425
Infotronics Integrators (India) Pvt Ltd | 2500 |  | 2500
Infotronics Integrators (India) Pvt Ltd | 2500 |  | 2500
Interest on GST | 367319 |  | 367319
Interest on Tds | 4010706 |  | 4010706
Interest Paid on Service Tax | 51 |  | 51
Late Filing Fees for GST | 55530 |  | 55530
LEI Registration Exp. | 11649 |  | 11649
Link Intime India Private Limited | 5000 |  | 5000
Membership & Subcription Charges | 74750 |  | 74750
Miscelleneous Expenses | 19227 |  | 19227
Notary & Other Charges | 1200 |  | 1200
Office General Expenses | 40194.25 |  | 40194.25
Oil, Petrol & Diesel Expenses | 10146 |  | 10146
Postage, Tele. & Courier Charges | 134957 |  | 134957
Preference Share Issue Expenses | 868723.26 |  | 868723.26
Professional Tax (Company) | 2500 |  | 2500
Re-Imbursement of Expenese | 10000 |  | 10000
Rent -A- Car | 150210 |  | 150210
Rent Paid | 75000 |  | 75000
Repairing & Maintenance (Car) | 10164 |  | 10164
ROC Filing Exp. | 12000 |  | 12000
Round Off | 7.64 |  | 7.64
Site Expenses | 38674 |  | 38674
Site Expenses | 27738 |  | 27738
Telephone Expenses | 15719 |  | 15719
Travelling Expenses | 457221 |  | 457221
Salary | 4340791 | 485698 | 4826489
Print Engi Chem Pvt Ltd | 44843 | 924 | 45767
Bank charges | 272849.02 |  | 272849.02
Urbnarc Pte Ltd | 1252650 | 0 | 1252650
Bank commission | 2646330.93 |  | 2646330.93
Stamp Duty | 4358583 |  | 4358583
Processing Fees | 30427561.91 |  | 30427561.91
D FAB CABIN | 562000 |  | 562000
Divine Air | 125458 |  | 125458
Cobra Pro Tech Security Services and Fire Safe | 136754 | 108842 | 245596
AJAY RAMKRISHAN KHAMKAR (STUDIODIGIDREM) |  | 35820 | 35820
CONFEDERATION OF INDIA INDUSTRY |  | 24780 | 24780
SAMCO WATER TECHNOLOGIES | 810000 |  | 810000
Vivish Technologies Private Limited | 20807.8 |  | 20807.8
TOTAL | 158038132 | 14444041 | 172482173

## Contingency
Sr. | Particulars | Amount
1 |  | 0
2
TOTAL |  | 0

## Interest Cost
Sr. | Period | Amount
1 | 2024-08-31 | 200018
2
TOTAL |  | 200018