## Final Summary
Project expenses | Estimated Cost as per Cost Vetting | Incurred Cost as per Bill till 30.06.2024 | Incurred Cost as per CA till 30.06.2024 | Incurred Cost as per Bill till 31.03.2024 | Incurred Cost as per CA till 31.03.2024 | Difference between the Bills & CA | Difference between both the Bills | Difference between both CA | Remark
Land Cost | 6.37 | 6.3694 | 6.53 | 6.3694 | 6.53 | -0.16064 | 0 | 0
Payment payable to Rehab Tenants Alter Accommodation | 16.31 | 11.21 | 11.21 | 10.64 | 10.64 | 0 | 0.56997 | 0.57
Construction Cost of Building | 57.79 | 47.8374 | 52.17 | 44.26 | 47.72 | -4.3326 | 3.5774 | 4.45
Approval Cost Of Fungible Cost & Development cess premium | 5.29 | 5.0004 | 5 | 5.0004 | 5 | 0.0004215 | 0 | 0
Professional Cost | 2.31 | 2.2595 | 2.26 | 2.1101 | 2.11 | -0.000525 | 0.14941 | 0.15
Admin Cost | 2.89 | 2.4001 | 2.4 | 2.2046 | 2.2 |  | 0.19549 | 0.2
Marketing Cost | 2.55 | 2.4497 | 2.45 | 2.3026 | 2.3 |  | 0.14718 | 0.15
Interest Cost | 9.72 | 3.9189 | 3.92 | 3.15 | 3.15 | -0.001065 | 0.76892 | 0.77
Contingous Cost | 1.73 | 1.2099 | 1.21 | 0.91 | 0.91 | -0.0001225 | 0.29988 | 0.3
Total Cost | 104.96 | 82.6553 | 87.15 | 76.947 | 80.56 | -4.4945 | 5.7083 | 6.59
|  | 22.3047 | 83.03%
Particulars | Revised Estimated Cost (in Cr.) | 30.06.2024 as per Bill Tally (inclusive of GST) | Cost incurred as %age total cost of that Component | Cost incurred as %age of cost incurred as on 31.03.2024
Land Cost | 6.37 | 6.3694 | 99.99% | 6.068%
Payment payable to Rehab Tenants Alter Accommodation | 16.31 | 11.21 | 68.73% | 10.68%
Construction Cost of Building | 57.79 | 47.8374 | 82.78% | 45.58%
Approval Cost Of Fungible Cost & Development cess premium | 5.29 | 5.0004 | 94.53% | 4.764%
Professional Cost | 2.31 | 2.2595 | 97.81% | 2.153%
Admin Cost | 2.89 | 2.4001 | 83.05% | 2.287%
Marketing Cost | 2.55 | 2.4497 | 96.07% | 2.334%
Interest Cost | 9.72 | 3.9189 | 40.32% | 3.734%
Contingous Cost | 1.73 | 1.2099 | 69.94% | 1.153%
Total | 104.96 | 82.6553 | 78.75% | 78.75%
Pariculars | 30.06.2024 as per Bill Tally (inclusive of GST) | 31.03.2024 as per Bill Tally (inclusive of GST) | Difference b/w bills of 31.03.2024 & 30.06.2024 | Difference of Cost incurred as %age of cost incurred as on 30.06.2024 & 31.03.2024
Land Cost | 6.3694 | 6.3694 | 0 | 0%
Payment payable to Rehab Tenants Alter Accommodation | 11.21 | 10.64 | 0.57 | 0.6896%
Construction Cost of Building | 47.8374 | 44.26 | 3.58 | 4.331%
Approval Cost Of Fungible Cost & Development cess premium | 5.0004 | 5.0004 | 0 | 0%
Professional Cost | 2.2595 | 2.1101 | 0.15 | 0.1815%
Admin Cost | 2.4001 | 2.2046 | 0.2 | 0.242%
Marketing Cost | 2.4497 | 2.3026 | 0.15 | 0.1815%
Interest Cost | 3.9189 | 3.15 | 0.77 | 0.9316%
Contingous Cost | 1.2099 | 0.91 | 0.3 | 0.363%
Total | 82.6553 | 76.947 | 5.71 | 6.908%

## Plinth Area
WING B & C
Sr. No. | Floor | Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | Percentage of work completed | Actual Expenditure till date in ` | Sr. No. | Particulars | Construction Area in Sq. M. | Full Value after completion | Percentage of work completed | Actual Expenditure till date in `
1 | Excavation |  |  |  | 30618420 | 100% | 30618420 | 1 | Wing B & C | 10206.14 | 306184200 | 69.9% | 214036230
2 | Ground Floor | 279.8 | 279.8 | 30000 | 8394000 | 50% | 4197000 | 2 | Wing D | 5888.74 | 176662200 | 76.27% | 134748909
3 | 1st Floor | 349.9 | 349.9 | 30000 | 10497000 | 70% | 7347900 | Sub Total of construction Cost |  | 16094.88 | 482846400 | 72.24% | 348785139
4 | 2nd Floor | 451.11 | 451.11 | 30000 | 13533300 | 70% | 9473310 | 3 | Stack Parking in Wing B & C | 84 | 37800000 | 0% | 0
5 | 3rd Floor | 451.11 | 451.11 | 30000 | 13533300 | 70% | 9473310 | 4 | Stack Parking in Wing D | 20 | 37800000 | 0% | 0
6 | 4th Floor | 451.11 | 451.11 | 30000 | 13533300 | 70% | 9473310 | Sub Total of Stack Parking |  | 104 | 75600000 | 0% | 0
7 | 5th Floor | 451.11 | 451.11 | 30000 | 13533300 | 70% | 9473310 | TOTAL Cost of Construction |  |  | 558446400 | 62.46% | 348785139
8 | 6th Floor | 451.11 | 451.11 | 30000 | 13533300 | 70% | 9473310 |  |  |  | 55.8446 |  | 34.8785
9 | 7th Floor | 451.11 | 451.11 | 30000 | 13533300 | 70% | 9473310 | [5 empty] | 47.84
10 | 8th Floor | 451.11 | 451.11 | 30000 | 13533300 | 70% | 9473310 | [5 empty] | 12.9615
11 | 9th Floor | 451.11 | 451.11 | 30000 | 13533300 | 70% | 9473310 | [5 empty] | 7.7315
12 | 10th Floor | 451.11 | 451.11 | 30000 | 13533300 | 70% | 9473310 | [5 empty] | 42.61
13 | 11th Floor | 451.11 | 451.11 | 30000 | 13533300 | 60% | 8119980 | [5 empty] | 76.3%
14 | 12th Floor | 451.11 | 451.11 | 30000 | 13533300 | 60% | 8119980
15 | 13th Floor | 451.11 | 451.11 | 30000 | 13533300 | 60% | 8119980
16 | 14th Floor | 451.11 | 451.11 | 30000 | 13533300 | 60% | 8119980
17 | 15th Floor | 451.11 | 451.11 | 30000 | 13533300 | 50% | 6766650
18 | 16th Floor | 451.11 | 451.11 | 30000 | 13533300 | 50% | 6766650
19 | 17th Floor | 451.11 | 451.11 | 30000 | 13533300 | 50% | 6766650
20 | 18th Floor | 451.11 | 451.11 | 30000 | 13533300 | 50% | 6766650
21 | 19th Floor | 451.11 | 451.11 | 30000 | 13533300 | 50% | 6766650
22 | 20th Floor | 451.11 | 451.11 | 30000 | 13533300 | 50% | 6766650
23 | 21st Floor | 451.11 | 451.11 | 30000 | 13533300 | 50% | 6766650
24 | 22nd Floor | 451.11 | 451.11 | 30000 | 13533300 | 50% | 6766650
25 | Terrace / OHT / LMR | 103.13 | 0 | 30000 | 3093900 | 0% | 0
SUB - TOTAL |  | 10206.14 | 10103.01 |  | 306184200 | 69.9% | 214036230
Stack Parking |  | 84 |  | 450000 | 37800000 | 0%
TOTAL |  |  |  |  | 343984200 | 62.22% | 214036230
WING B & C
Sr. No. | Floor | Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | Percentage of work completed | Actual Expenditure till date in `
1 | Excavation |  |  |  | 17666220 | 100% | 17666220
2 | Ground Floor | 107.32 | 107.32 | 30000 | 3219600 | 50% | 1609800
3 | 1st Floor | 261.31 | 261.31 | 30000 | 7839300 | 70% | 5487510
4 | 2nd Floor | 261.31 | 261.31 | 30000 | 7839300 | 70% | 5487510
5 | 3rd Floor | 261.31 | 261.31 | 30000 | 7839300 | 75% | 5879475
6 | 4th Floor | 261.31 | 261.31 | 30000 | 7839300 | 78% | 6114654
7 | 5th Floor | 261.31 | 261.31 | 30000 | 7839300 | 78% | 6114654
8 | 6th Floor | 261.31 | 261.31 | 30000 | 7839300 | 78% | 6114654
9 | 7th Floor | 261.31 | 261.31 | 30000 | 7839300 | 78% | 6114654
10 | 8th Floor | 261.31 | 261.31 | 30000 | 7839300 | 78% | 6114654
11 | 9th Floor | 261.31 | 261.31 | 30000 | 7839300 | 78% | 6114654
12 | 10th Floor | 261.31 | 261.31 | 30000 | 7839300 | 78% | 6114654
13 | 11th Floor | 261.31 | 261.31 | 30000 | 7839300 | 78% | 6114654
14 | 12th Floor | 261.31 | 261.31 | 30000 | 7839300 | 78% | 6114654
15 | 13th Floor | 261.31 | 261.31 | 30000 | 7839300 | 78% | 6114654
16 | 14th Floor | 261.31 | 261.31 | 30000 | 7839300 | 78% | 6114654
17 | 15th Floor | 261.31 | 261.31 | 30000 | 7839300 | 50% | 3919650
18 | 16th Floor | 261.31 | 261.31 | 30000 | 7839300 | 50% | 3919650
19 | 17th Floor | 261.31 | 261.31 | 30000 | 7839300 | 50% | 3919650
20 | 18th Floor | 261.31 | 261.31 | 30000 | 7839300 | 50% | 3919650
21 | 19th Floor | 261.31 | 261.31 | 30000 | 7839300 | 50% | 3919650
22 | 20th Floor | 261.31 | 261.31 | 30000 | 7839300 | 50% | 3919650
23 | 21st Floor | 261.31 | 261.31 | 30000 | 7839300 | 50% | 3919650
24 | 22nd Floor | 261.31 | 261.31 | 30000 | 7839300 | 50% | 3919650
25 | Terrace / OHT / LMR | 32.6 | 0 | 30000 | 978000 | 0% | 0
SUB - TOTAL |  | 5888.74 | 5856.14 |  | 176662200 | 76.27% | 134748909
Stack Parking |  | 84 |  | 450000 | 37800000 | 0%
TOTAL |  |  |  |  | 214462200 | 62.83% | 134748909

## Summary Sheet
Sr. No. | Particulars | Incurred Cost in ` till 30.06.2024 | Incurred Cost in ` Cr. Till 30.06.2024 | Incurred Cost in ` till 31.03.2024 | Incurred Cost in ` Cr. Till 31.03.2024 | Balance | Balance in Cr.
1 | Land Cost | 63693621 | 6.3694 | 63693621 | 6.3694 | 0 | 0
2 | Rent Cost | 112100000 | 11.21 | 106400320 | 10.64 | 5699680 | 0.56997
3 | Construction Cost of Rehab & Amenity Building | 478374265 | 47.8374 | 442600045 | 44.26 | 35774220 | 3.5774
4 | Construction Cost of Sale Building
5 | Approval Cost & Stamp Duty | 50004215 | 5.0004 | 50004215 | 5.0004 | 0 | 0
6 | Professional Cost | 22594750 | 2.2595 | 21100675 | 2.1101 | 1494075 | 0.14941
7 | Admin Cost | 24000550 | 2.4001 | 22045654 | 2.2046 | 1954896 | 0.19549
8 | Marketing Cost | 24497500 | 2.4497 | 23025672 | 2.3026 | 1471828 | 0.14718
9 | Interest Cost | 39189350 | 3.9189 | 31500120 | 3.15 | 7689230 | 0.76892
10 | Contingency Cost | 12098775 | 1.2099 | 9100000 | 0.91 | 2998775 | 0.29988
| Total | 826553026 | 82.6553 | 769470322 | 76.947 | 57082704 | 5.7083
97200000
58010650
| Project expenses | Incurred Cost as per CA till 31.03.2024 | Incurred Cost as per CA till 31.12.2023 | Net
| Land Cost | 6.53 | 6.53 | 0
| Payment payable to Rehab Tenants Alter Accommodation | 10.64 | 9.34 | 1.3
| Construction Cost of Building | 43.77 | 38.14 | 5.63
| Approval Cost Of Fungible Cost & Development cess premium | 5 | 4.9 | 0.1
| Professional Cost | 2.11 | 1.98 | 0.13
| Admin Cost | 2.2 | 2.2 | 0
| Marketing Cost | 2.3 | 2.3 | 0
| Interest Cost | 3.15 | 2.43 | 0.72
| Contingous Cost | 0.91 | 0.91 | 0
| Advances to Vendors | 3.95 | 2.62 | 1.33
| DSRA | 1.87 | 0.5 | 1.37
| Total Cost | 82.43 | 71.85 | 10.58