## Final Summary
Project expenses | Estimated Cost as per Cost Vetting | Incurred Cost as per Bill till 30.06.2024 | Incurred Cost as per CA till 30.06.2024 | Incurred Cost as per Bill till 31.03.2024 | Incurred Cost as per CA till 31.03.2024 | Difference between the Bills & CA | Difference between both the Bills | Difference between both CA
Land Cost | 0.34 | 0.33572 | 0.34 | 0.33572 | 0.34 | -0.0042775 | 0 | 0
Rent Cost | 1.84 | 1.7524 | 1.76 | 1.5537 | 1.55 | -0.007623 | 0.1987 | 0.21
TDR Cost | 0.61 | 1.0817 | 1.08 | 1.0817 | 1.08 | 0.0016961 | 0 | 0
Construction Cost of Sale Building | 11.41 | 11.5144 | 12.14 | 9.834 | 11.5 | -0.62559 | 1.6804 | 0.64
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 4.5 | 5.701 | 4.62 | 5.6997 | 4.6 | 1.081 | 0.001335 | 0.02
Architect Cost, RCC & other Professional fees | 0.34 | 0.69299 | 1 | 0.59608 | 0.98 | 0.26459 | 0.0969 | 0.02
Administrative Expenses | 0.46 | 0.5428 |  | 0.39312 |  |  | 0.14968
Marketing Expences | 0.55 | 0.02881 |  | 0.02681 |  |  | 0.002
Interest Cost | 0.85 | 0.30108 | 0.3 | 0.2232 | 0.27 | 0.0010793 | 0.077876 | 0.03
Contingency Cost | 0.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost | 21.13 | 21.9509 | 21.24 | 19.744 | 20.32 | 0.71087 | 2.2069 | 0.92
|  | -0.82087 | -0.71087
Particulars | Revised Estimated Cost (in Cr.) | 30.06.2024 as per Bill Tally (inclusive of GST) | Cost incurred as %age total cost of that Component | Cost incurred as %age of cost incurred as on 30.06.2024
Land Cost | 0.34 | 0.33572 | 98.74% | 1.589%
Rent Cost | 1.84 | 1.7524 | 95.24% | 8.293%
TDR Cost | 0.61 | 1.0817 | 177.3% | 5.119%
Construction Cost of Sale Building | 11.41 | 11.5144 | 100.9% | 54.49%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 4.5 | 5.701 | 126.7% | 26.98%
Architect Cost, RCC & other Professional fees | 0.34 | 0.69299 | 203.8% | 3.28%
Administrative Expenses | 0.46 | 0.5428 | 118% | 2.569%
Marketing Expences | 0.55 | 0.02881 | 5.238% | 0.1363%
Interest Cost | 0.85 | 0.30108 | 35.42% | 1.425%
Contingency Cost | 0.23 | 0 | 0% | 0%
Total | 21.13 | 21.9509 | 103.9% | 103.9%
Pariculars | 30.06.2024 as per Bill Tally (inclusive of GST) | 31.03.2024 as per Bill Tally (inclusive of GST) | Difference b/w bills of 30.06.2024 & 31.03.2024 | Difference of Cost incurred as %age of cost incurred as on 30.06.2024 & 31.03.2024
Land Cost | 0.33572 | 0.33572 | 0 | 0%
Rent Cost | 1.7524 | 1.5537 | 0.2 | 0.9111%
TDR Cost | 1.0817 | 1.0817 | 0 | 0%
Construction Cost of Sale Building | 11.5144 | 9.834 | 1.68 | 7.653%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 5.701 | 5.6997 | 0 | 0%
Architect Cost, RCC & other Professional fees | 0.69299 | 0.59608 | 0.1 | 0.4556%
Administrative Expenses | 0.5428 | 0.39312 | 0.15 | 0.6833%
Marketing Expences | 0.02881 | 0.02681 | 0 | 0%
Interest Cost | 0.30108 | 0.2232 | 0.08 | 0.3645%
Contingency Cost | 0 | 0 | 0 | 0%
Total | 21.9509 | 19.744 | 2.21 | 10.07%

## Summary Sheet
Sr. No. | Particulars | Incurred Cost in ` till 31.03.2024 | Incurred Cost in ` Cr. Till 31.03.2024 | Incurred Cost in ` till 31.03.2024 | Incurred Cost in ` Cr. Till 31.03.2024 | Balance | Balance in Cr.
1 | Land Cost | 3357225 | 0.33572 | 3357225 | 0.33572 | 0 | 0
2 | Rent Cost | 17523770 | 1.7524 | 15536746 | 1.5537 | 1987024 | 0.1987
3 | TDR Cost | 10816961.5 | 1.0817 | 10816961.5 | 1.0817 | 0 | 0
4 | Construction Cost | 115144092 | 11.5144 | 98340427 | 9.834 | 16803665 | 1.6804 | 127278700 | 13.2023
5 | Approval Cost & Stamp Duty | 57009949.3 | 5.701 | 56996599.3 | 5.6997 | 13350 | 0.001335
6 | Professional Cost | 6929854 | 0.69299 | 5960850 | 0.59608 | 969004 | 0.0969
7 | Admin Cost | 5427974.81 | 0.5428 | 3931187.16 | 0.39312 | 1496787.65 | 0.14968
8 | Marketing Cost | 288100 | 0.02881 | 268100 | 0.02681 | 20000 | 0.002
9 | Interest Cost | 3010793 | 0.30108 | 2232034 | 0.2232 | 778759 | 0.077876
| Total | 219508719.61 | 21.9509 | 197440129.96 | 19.744 | 22068589.65 | 2.2069
8500000
5489207

## Land, Rent, TDR, Approval
Land Cost Description | [7 empty] | TDR Cost
Sr. No. | Date | Document Name | Description | Total Cost | Incurred Cost |  | Sr. No. | Description | Incurred Cost
1 | 16.02.2022 | Developer Agreement | Stamp Duty | 3325725 | 3325725 |  |  | TDR PURCHASE | 10238932
2 |  |  | Reg. Fees | 30000 | 30000 |  | 2 | Stamp Duty | 578029.5
3 |  | Power Attorney |  | 1500 | 1500
Total |  |  |  | 3357225 | 3357225 |  | Total |  | 10816961.5
Sr. No. | 6. MCGM Approval Costs |  | 5. Premium Costs
| Plot Size (sq Mt) | 868.17 | Plot Size (sq Mt) | 868.17
| FSI | 2.2 | FSI | 0.5 | 67145
| Net Area | 1909.974 | Net Area | 434.085
| Net Area (sq Mt i.e. *10.764) | 20558.9601 | Premium Factor | 0.5
| Rate per Sft (Rs.) | 2000 | Land Rate (Rs.) | 49200
| Total Approval Cost | 41117920.272 | Total Premium Cost | 10678491
45000000
2188.8267
Sr. No. | Tenant No. | Old Carpet Area in Sq. Ft. | New Carpet Area in Sq. Ft. | Rate per Sq. Ft. on CA | Rent per Month | Rent per Year | Rate per Sq. Ft. on CA | Rent per Month | Shifting Charges | Brokerage Charges | Total
1 | Resi 1 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
2 | Resi 2 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
3 | Resi 3 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
4 | Resi 4 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
5 | Resi 5 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
6 | Resi 6 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
7 | Resi 7 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
8 | Resi 8 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
9 | Resi 9 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
10 | Resi 10 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
11 | Resi 11 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
12 | Resi 12 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
13 | Resi 13 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
14 | Resi 14 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
15 | Resi 15 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
16 | Resi 16 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
17 | Resi 17 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
18 | Resi 18 | 450 | 549 | 55 | 24750 | 297000 | 60.5 | 27225 | 20000 | 24750 | #REF!
19 | Comm 1 | 295 | 359.9 | 90 | 26550 | 318600 | 99 | 29205 | 20000 | 26550 | #REF!
20 | Comm 2 | 295 | 359.9 | 90 | 26550 | 318600 | 99 | 29205 | 20000 | 26550 | #REF!
21 | Comm 3 | 295 | 359.9 | 90 | 26550 | 318600 | 99 | 29205 | 20000 | 26550 | #REF!
22 | Comm 4 | 295 | 359.9 | 90 | 26550 | 318600 | 99 | 29205 | 20000 | 26550 | #REF!
23 | Comm 5 | 109 | 132.98 | 90 | 9810 | 117720 | 99 | 10791 | 20000 | 9810 | #REF!
24 | Comm 6 | 385 | 0 | 90 | 34650 | 415800 | 99 | 38115 | 20000 | 34650 | #REF!
|  | 9774 | 11454.58 |  | 596160 | 7153920 |  | 655776 | 480000 | 596160 | #REF!
[6 empty] | 7153920 |  |  |  |  | #REF! | 240000 | 596160
#REF!

## Rent Cost
RENT PAID-COMMERCIAL to Tenant | 1662138
RENT PAID- RESIDENTIAL to Tenant | 6869250
Brokerage Paid To Tenant (To take Flat on rent) | 534960
CORPUS FUND -PAID to Tenant | 1100000
TRANSPORT CHARGES PAID TO TENENT | 440000
RENT PAID-COMMERCIAL to Tenant | 665280
RENT PAID- RESIDENTIAL to Tenant | 2423025
RENT PAID-COMMERCIAL to Tenant | 399168
RENT PAID- RESIDENTIAL to Tenant | 1442925
RENT PAID-COMMERCIAL to Tenant | 418846
RENT PAID- RESIDENTIAL to Tenant | 1568178
17523770
S

## TDR & Approval
SR.NO | PARTICULARS | TOTAL AMOUNT
| BMC PAYMENT-CFO PAYMENT | 385236
| FUNGIBLE PREMIUM PAID | 7100
| HE NOC /PCO NOC | 94200
| M.C.G.M DD/ORDER PAY | 48386911.5
| PROPERTY TAX PAID | 497391
| REVALIDATION CHARGES | 22800
| REVISED CONCESSION CHARGES-SCRUTINY FEES | 19400
| SWM NOC | 26500
| Scrutiny Fees for TDR & ACCOMODATION | 16016
| Roc Expenses | 10000
| Survay Remark Fees | 11048
| LAXMAN SUTHAR (PARKING REMARK) NOC | 9900
| FUNGIBLE PREMIUM PAID | 1208441.8
| HE NOC /PCO NOC | 67065
| M.C.G.M DD/ORDER PAY | 6164590
| M.C.G.M DD/ORDER PAY | 70000
| SWM NOC | 13350
57009949.3

## Material & Labour
Date | Particulars | Amount
2023-05-15 | Suman Kanoria | 2500000 | Date | Particulars | Gross Total
2023-04-10 | Narottam Granites Pvt Ltd | 1000000 |  | Construction Cost-Advance to Contractor (J.R Infra) | 2640000
2023-06-20 | Anjaneya Star India Pvt Ltd | 3100000 |  | Building Material Purchase | 3521729.32
2023-06-05 | Narottam Granites Pvt Ltd | 376000 |  | BOREWELL WORK | 161908
2023-06-03 | Magnium Steel Company | 1716197 |  | ELECTRIC WORK | 27625
2023-06-05 | Narottam Granites Pvt Ltd | 184305 |  | Water Licencing & Plumber Contract Work | 182500
2023-07-15 | Narottam Granites Pvt Ltd | 25050000
2023-06-24 | Shreenanth Plywood | 63026
2023-06-20 | Shreenanth Plywood | 143724 |  |  | 6533762.32
2023-07-01 | Shreenanth Plywood | 38477
| Building Material Purchase | 4957535
| BOREWELL WORK | 549611
| BUILDING MATERIAL PURCHASE | 1227240
| Construction Cost | 20621263
| ELECTRIC WORK | 89040
| LABOUR CHARGES | 1005610
| Payment to Electric Contractor | 38262
| Water Licencing & Plumber Contract Work | 28000
| Building Material Purchase | 2537902
| BUILDING MATERIAL PURCHASE | 164643
| LABOUR CHARGES | 1117764
| LIFT CONTARCT | 2315160
| MATERIAL WITH LABOUR CHARGES | 678571
| R.C.C. Work ( Construction Expenses) | 30639819
| Tower Car Parking- Material | 746232
| Building Material Purchase | 2051636
| BOREWELL WORK | 16678
| BUILDING MATERIAL PURCHASE | 244458
| LABOUR CHARGES | 1099344
| LIFT CONTARCT | 1157580
| MATERIAL WITH LABOUR CHARGES | 501275
| CONSTRUCTION EXPENSES | 9184740
115144092
0

## Professional
SR.NO | PARTICULARS | TOTAL AMOUNT
1 | Civil Aviation Noc | 81420
4 | CONSULTANCY FEES PAID | 1902550
5 | PROFESSIONAL FEES EXPENSES | 3861580
6 | PROFESSIONAL FEES EXPENSES | 115300
7 | CONSULTANCY FEES PAID | 100000
8 | PROFESSIONAL FEES EXPENSES | 869004
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
32
TOTAL |  | 6929854

## MArketing
SR.NO | PARTICULARS | TOTAL AMOUNT
| STAMP DUTY AND REGISTRATION CHARGES | 91100
| Advertising Charges | 2000
| Brokerage | 75000
| BROKERAGE PAID- BUSINESS LEAD | 100000
| Shailesh M Ingale- Brokerage | 20000
TOTAL |  | 288100

## Admin
SR.NO | PARTICULARS | TOTAL AMOUNT
| Horticulture Expenses | 10000
| MCGM WATER CHARGES | 107100
| Payment to Electric Contractor | 52156
| SECURITY SERVICE CHARGE | 263045
| STAFF SALARY | 753149
| ACCOUNTING CHARGES | 12500
| Advertising Charges | 22619
| AUDIT FEES | 8850
| Bank Charges | 32171.64
| DONATION PAID | 9000
| Electricity Charges (Site) | 98560
| Expenses for Project | 34870
| INTEREST PAID ON TDS | 6241
| JANTA INSURANCE POLICY | 36155
| MEMBERSHIP FEES PAID | 76700
| Office Exp | 3200
| PRINTING & STATIONERY | 238550
| REPAIRS & MAINTENANCE | 5000
| Rera Registration Fees and Other Charges | 18292.8
| ROUNDING OFF | 435.5
| Staff Salary | 143276
| STAFF WELFARE | 5248
| Sundry Expenses | 40725.55
| COMMISSION PAID ON SBI LOAN PROCESS | 781986
| Staff Salary | 294437
| Bank Charges | 1697.39
| Electricity Charges (Site) | 115600
| INTEREST PAID ON TDS | 316
| PRINTING & STATIONERY | 12966
| MCGM WATER CHARGES | 23800
| SECURITY SERVICE CHARGE | 90000
| Insurance | 213177
| STAFF SALARY | 150945
| Bank Charges | 31911.28
| Electricity Charges (Site) | 106210
| MEMBERSHIP FEES PAID | 11800
| PRINTING & STATIONERY | 10729
| Roc Expenses | 3068
| Survay Remark Fees | 15000
| SECURITY SERVICE CHARGE | 54000
| MCGM WATER CHARGES | 35700
| STAFF SALARY | 147210
| Bank Charges | 3605.65
| Electricity Charges (Site) | 94530
| INTEREST PAID ON TDS | 18302
| PRINTING & STATIONERY | 10303
| GST PAID | 1128036
| BANK GUARANTEE CHARGES | 5101
| MCGM WATER CHARGES | 35700
| SECURITY SERVICE CHARGE | 54000
TOTAL |  | 5427974.81

## Interest
Sr. No. | Month | Interest Amount
| 2023-06-01 | 9357
| 2023-07-01 | 291649
| 2023-08-01 | 322489
| 2023-09-01 | 343268
| 2023-10-01 | 343288
| 2023-11-01 | 238412
| 2023-12-01 | 246692
| 2024-03-01 | 436879
| 2024-06-01 | 778759
3010793

## Construction Area Statement
Sr. No. | Floor | Total Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | Percentage of work completed | Actual Expenditure till date in `
1 | Excavation Cost |  |  |  |  | 100% | 0
2 | Basement | 51.85 | 51.85 | 30000 | 1555500 | 70% | 1088850
3 | Ground | 246.44 | 246.44 | 30000 | 7393200 | 75% | 5544900
4 | 1st | 241.65 | 241.65 | 30000 | 7249500 | 81% | 5872095
5 | 2nd | 241.65 | 241.65 | 30000 | 7249500 | 81% | 5872095
6 | 3rd | 241.65 | 241.65 | 30000 | 7249500 | 81% | 5872095
7 | 4th | 241.65 | 241.65 | 30000 | 7249500 | 81% | 5872095
8 | 5th | 241.65 | 241.65 | 30000 | 7249500 | 81% | 5872095
9 | 6th | 241.65 | 241.65 | 30000 | 7249500 | 81% | 5872095
10 | 7th | 241.65 | 241.65 | 30000 | 7249500 | 81% | 5872095
11 | 8th | 241.67 | 241.67 | 30000 | 7250100 | 81% | 5872581
12 | 9th | 241.65 | 241.65 | 30000 | 7249500 | 81% | 5872095
13 | 10th | 241.65 | 241.65 | 30000 | 7249500 | 81% | 5872095
14 | 11th | 241.65 | 241.65 | 30000 | 7249500 | 81% | 5872095
15 | 12th | 241.65 | 241.65 | 30000 | 7249500 | 81% | 5872095
16 | Terrace | 38.89 | 38.89 | 30000 | 1166700 | 81% | 945027
Sub - Total (A) |  | 3237 | 3237 |  | 97110000 | 80.37% | 78044403
STACK PARKING Nos. |  | 34 |  | 500000 | 17000000 |  | 0
TOTAL COST OF CONSTRUCTION (A + B) |  |  |  |  | 114110000 | 68.39% | 78044403
36065597