## Project Details
S. no. | Particulars | Details
1 | Type of Development | Residential
2 | Total Tenants units | 105 Units
Total allotted to members (existing tenants) – 64 units
Total Unsold – 41 units
3 | Total Residential Area – Rehab building | 1 Building consit of four wings say A, B, C & D
4 | Total no. of units available for sale | 41 units
5 | Total Sale carpet area | 97165.77 SQ Ft. (Carpet area – RERA)
6 | Net Area available for sale | 36197.98 SQ Ft (Carpet area – RERA)
7 | No. of sale Tower – commercial | Not applicable
8 | No. of Residential Tower | 1 Building consit of four wings say A, B, C & D
9 | Structure Planned till – sale commercial | Ground, Slab1, Slab2, Slab3, Slab4, Slab5, Slab6, Slab7, Slab8, Slab9.
10 | Structure constructed till – sale commercial | Ground, Slab1, Slab2, Slab3, Slab4, Slab5, Slab6, Slab7, Slab8, Slab9.
11 | Structure Planned till – Residential | B1 + 10 floors each of four wings
12 | Structure constructed till – Residential | Ground, Slab1, Slab2, Slab3, Slab4, Slab5, Slab6, Slab7, Slab8, Slab9.
13 | Structure planned and constructed till – PTC* | Ground, Slab1, Slab2, Slab3, Slab4.

## Costing
COST & MEANS OF FINANCE |  |  |  |  | Rs. In Lakhs
Sr No | Cost Particulars | Total | Cost incurred | Balance Cost | % total
1 | Land Cost | 0 | 0 | 0 | 0%
2 | Plan approval | 0 | 0 | 0 | 0%
3 | Construction cost | 8826 | 4566 | 4260 | 48.27%
4 | Administration + Overheads | 789 | 740 | 49 | 6.21%
5 | Sales & Marketing exps | 0 | 0 | 0 | 0%
7 | Professional Fees | 311 | 299 | 12 | 3.859%
8 | Finance Cost | 499 | 468 | 31 | 6.212%
Total Project Cost |  | 10425 | 6073 | 4352
Sr No | Means of Finance | Total | Brought as on | Balance | % total
2024-07-31
1 | Promoters Contribution | 4945 | 4945 | 0 | 0%
2 | Booking Money | 0 | 0 | 0 | 0%
3 | Loan amount | 1625 | 234 | 1391 | 85.6%
Project Synopsis (Vikram Delite CHSL) (as on 31-07-2024):
Units | Particulars | Details
No. of Units | Sold. | 63 | (out of 63, 62 are tenant allotment and 1 is Outside Sale)
| Unsold. | 42
Others (if applicable)
| Total | 105
Carpet Area (in sqft) | Sold to Exisitng Tenants | 10989.43
| Sold to Outsiders | 681.9
| Unsold | 37035.44
| Reserved for Existing Tenants (Old Carpet Area plus 45% Free Area) | 48459
| Total | 97165.77
| % Sold | 12.01%
Sales (Rs. In lakhs) | Rec D | 968
| Receivable | 10189.1456
| Total | 11157.1456
| Future RecV | 0
Cost (Rs. In lakhs) | Total | 10425
| Incurred | 6073
| Balance | 4352
| Inc. % | 41.75%
Project Surplus (Rs. In lakhs) | Surplus | 732.1456
Valuation (Rs. In lakhs)
Loan o/s (Rs. In lakhs) |  | 23400
Loan undisbursed (Rs. In lakhs) |  | 139100
Fresh Proposed facility (Rs. In lakhs) |  | 115700

## Flats details
Sold & Unsold Status (Area in Sqft; Amt Rs. in lakhs)
Particulars | No. of Units | Carpet Area | AV | Demand Raised ( In lakhs) | RecD | RecV | RecD %
(In Lakhs)
Sold to exisitng Tenants | 62 | 10989.43 | 2612.3726 | 1698.0422 | 880 | 818.0422 | 48.18%
Residential | 62 | 10989.43 | 2612.3726 | 1698.0422 | 880 | 818.0422 | 0.48176
Sold to Outsiders | 1 | 681.9 | 136.38 | 88.647 | 88.65 | 47.73 | 53.84%
Unsold | 42 | 37035.44 | 9231.3093 | 0 | 0 | 0 | 0
Residential | 43 | 37717.34 | 9367.6893 | 88.647 | 88.65 | 47.73 | 0.53843
Grand Total | 105 | 48706.77 | 11980.0619 | 1786.6892 | 968.65 | 865.7722 | 1.0202

## Sheet4 (hidden)
Scheme Description
Scheme Name

## Sales
Sales Velocity (Area in Sqft; Amt Rs. in lakhs)
Particulars | No. of Units | Carpet Area | AV | RecD | RecV | RecD % | ASP
2023-24
Dec | [5 empty] | 0%
Jan | [5 empty] | 0%
Feb | [5 empty] | 0%
Mar | 41 | 10989 | 1698.0422 | 880 | 818.0422 | 51.82% | 20000
2023-24 |  |  | 0 | 0 | 0 | 0%
Apr |  |  | 818.0422 | 0 | 818.0422 | 0%
May |  |  | 965 | 0 | 965 | 0%
Jun |  |  |  | 0 | 0 | 0%
July | 1 | 681.9 | 752 | 88.65 | 663.35 | 11.79% | 22234
August |  |  | 187 | 0 | 187 | 0%
September | 17 | 10672 | 174 | 0 | 174 | 0%
October | 46 | 23609.1 | 752 | 0 | 752 | 0% | 21000
November |  |  | 187 | 0 | 187 | 0%
December |  |  | 4973 | 0 | 4973 | 0%
January |  |  | 651.065 | 0 | 651.065 | 0%
February | [5 empty] | 0%
March
Total | 105 | 45952 | 11157.1494 | 968.65 | 10188.4994

## Construction
Building Name | A | B | C | D | MHADA
Approved Floors | 10 | 10 | 10 | 10 | NA
Proposed Floors | 10 | 10 | 10 | 10 | NA
Construction stage | 80% | 80% | 80% | 80% | NA
Current SOC | 40% | 40% | 40% | 40% | NA
Weighted Avg. SOC | 50%