## Ghatkopar project budget
SHREE RAMKRISHN ENTERPRISES
SR No. | Annexures | As per OLD Budget |  |  | As per Revised Budget |  |  | As per Actual- as on July-23 | Balance to be spent
Sr. no. | Particulars | Quantity | Rate | Rs. (in Cr) | Quantity | Rate | Rs. (in Crores) | Rs. (in Crores) | Rs. (in Crores) |  |  | Enhanced FSI
1 | Total RCC-Material | 40444 | #REF! | #REF! | 45952 | 35.4718 | 16.3 | 14.8765 | 1.4235
2 | Total RCC-labour | 40444 | #REF! | #REF! | 45952 | 19.4333 | 8.93 | 3.324 | 5.606
3 | Total Finishing Cost | 40444 | #REF! | #REF! | 45952 | 35.7765 | 16.44 | 0.45557 | 15.9844
4 | Cost of Nala | 40444 | #REF! | #REF! | 45952 | 5.6146 | 2.58 | 2.58 | 0
5 | Excavation | 40444 | #REF! | #REF! | 45952 | 2.121 | 0.97464 | 0.97464 | 0
6 | Market TDR (50%) | 40444 | 1371.8253 | 5.5482 | 45952 | 12.0739 | 5.5482 | 5.5482 | 0
7 | BMC TDR (50%) | 40444 | #REF! | #REF! | 45952 | 1.8291 | 0.84049 | 0.6 | 0.24049
CHANGES IN MCGM PAYMENT
8 | Fungible FSI | 40444 | #REF! | #REF! | 45952 | 5.0039 | 2.2994 | 0.5295 | 1.7699 | Fungible FSI | 3.412 | 3.412 | 0
[10 empty] | Premium Staircase / lift to BMC | 1.5288 | 1.5288 | 0
9 | Premium Staircase / lift to BMC | 40444 | #REF! | #REF! | 45952 | 3.3527 | 1.5406 | 1.54 | 0.0006326 | IOD Deposit | 0.00728 | 0.00728 | 0
[10 empty] | Labour Welfare Cess | 0 | 0 | 0
10 | Development Charges to BMC | 40444 | #REF! | #REF! | 45952 | 4.5458 | 2.0889 | 0.5382 | 1.5507 | TOTAL | 11.9578 | 11.9578 | 0
11 | Other BMC-IOD Cond | 40444 | #REF! | #REF! | 45952 | 5.9435 | 2.7312 | 1.6145 | 1.1167 | Pest Control - for 2yrs | 0.025
[10 empty] | Sanitary Officers | 0.01
12 | Property Tax ( LUC) | 40444 | #REF! | #REF! | 45952 | 3.2758 | 1.5053 | 0.5845 | 0.92078 | CC revalidation | 0.001
[10 empty] | Road Demarcation | 0.015
13 | BMC - Segregating Distance Deficiency Premium | 40444 | #REF! | #REF! | 45952 | 1.2469 | 0.57298 | 0 | 0.57298
[10 empty] | TOTAL | 0.101
14 | Temp Accom, brokerage & Transportation | 40444 | #REF! | #REF! | 45952 | 34.3244 | 15.7728 | 12.68 | 3.0928
15 | Corpus Fund | 40444 | #REF! | #REF! | 45952 | 10.9897 | 5.05 | 0.6433 | 4.4067
16 | Admin cost | 40444 | #REF! | #REF! | 45952 | 17.3782 | 7.9856 | 4.6067 | 3.3789
17 | Bank Gurantee | 40444 | 37.0883 | 0.15 | 45952 | 0.914 | 0.42 | 0.42 | 0
18 | Interest Cost | 40444 | #REF! | #REF! | 45952 | 8.0519 | 3.7 | 3.6106 | 0.0894
19 | Stamp Duty & Registration Cost on DA | 40444 | #REF! | #REF! | 45952 | 3.2177 | 1.4786 | 0.48 | 0.9986
20 | Professional Fees | 40444 | #REF! | #REF! | 45952 | 10.8374 | 4.98 | 2.61 | 2.37
21 | GST on Constrution & DA | 40444 | #REF! | #REF! | 45952 | 5.4705 | 2.5138 | 2.5138 | 0
| Total Project Cost | 40444 | #REF! | #REF! | 45952 | 226.8726 | 104.2525 | 60.73 | 43.5224
| Sale - Area |  |  |  | 45952 | 24280 | 111.5715
| ++ Before Income Tax -- Sale - Total Cost |  |  |  |  | 21000 | 7.319
| Income Tax @ 35% |  |  |  |  | 7350 | 2.5616
| ++ |  |  |  |  | 13650 | 4.7573

## 2. CF Working final
3 | CASHFLOW STATEMENT | ACTUAL FIGURES |  |  |  |  | EXPECTED BUDGET | [6 empty] | Rs. (in Crores)
Sr. No | Particulars | Total Exp. upto March-2023 (Plinth level) | Apr 2023 to March 2024 | Month 1-2-3 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Total from Feb-24 to Jan-25 | Grand Total
|  |  |  | Stilt to slab 6 | Slab 7-9 Brickwork | Slab 10 Brickwork | Slab 11 Brickwork | Ois Tank/Brickwork | Finishing | Finishing | Finishing | Possession
|  |  |  | April-May 24 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01
EVENTS
| Opening Balance (A) | 0 | 0.44748 | 0.60243 | 0.49243 | 0.99243 | 0.44243 | 0.67717 | 0.87485 | 4.4874 | 2.7273 | 50.9976 | 0.60243 | 0
RECEIPTS:- (B)
1 | Promoters Contribution | 45.4537 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -49.4537 | -49.4537 | 1.38e-05
2 | Kotak Mahindra Bank Fund Utilized / Repay | 0 | 0.6125 | 0.415 | 1.41 | -0.1 | 3 | 10.6625 | 0 | -4 | 0 | -12 | -0.6125 | 1.1102e-15
3 | Society Sales (10517 sq ft) | 0 | 3.73 | 2.435 | 0.935 | 1.71 | 4.88 | 2.1 | 0 | 3.16 | 0 | 2.084 | 17.304 | 21.034
4 | Sale to outsiders -Phase 1 (682 sq ft) | 0 | 0 | 0.68 | 0.205 | 0 | 0.26996 | 0 | 0 | 0.06999 | 0.14008 | 0 | 1.365 | 1.365
5 | Sale to outsiders -Phase 2 (7093 sq ft) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.6401 | 0 | 10 | 10 | 21.6401 | 21.6401
6 | Sale to outsiders -Phase 3 (7619 sq ft) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 12 | 16 | 16
7 | Sale to outsiders -Balance (23000 sq ft) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.32 | 0 | 38.7665 | 2.3672 | 49.4537 | 49.4537
8 | Legal & Develpoment ( Total 425/- x 48911 sq ft) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0787 | 2.0787 | 2.0787
| TOTAL RECEIPTS ( A + B ) | 45.4537 | 8.3425 | 3.53 | 2.55 | 1.61 | 8.15 | 13.7625 | 8.9601 | 3.23 | 48.9065 | -32.9238 | 57.7753 | 111.5715
| TOTAL ( A + B ) | 45.4537 | 8.79 | 4.1324 | 3.0424 | 2.6024 | 8.5924 | 14.4397 | 9.835 | 7.7173 | 51.6339 | 18.0738 | 58.3777 | 111.5715
LESS : PAYMENTS:-
1 | RCC-Material + Nala Cost + Excavation + GST | 9.2418 | 1.565 | 2.1 | 1.19 | 0.78 | 1.58 | 4.33 | 0.0677 | 0 | 0 | 0 | 10.0477 | 20.8545
2 | RCC-labour | 1.3378 | 0.805 | 0.56 | 0.38 | 0.24 | 1.29 | 3.9 | 0 | 0 | 0 | 0 | 6.37 | 8.5128
3 | Finishing Cost - Material | 0 | 0.01 | 0.04 | 0.04 | 0.32 | 2.9 | 3.97 | 3.97 | 3.69 | 0 | 0 | 14.93 | 14.94
4 | Finishing Cost - Labour | 0 | 0 | 0.02 | 0.01 | 0.03 | 1.49 | 0.63 | 0.63 | 0.63 | 0 | 0 | 3.44 | 3.44
5 | BMC Payments +Property Tax ( LUC) | 7.8505 | 3.73 | 0.16 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 8.551 | 8.731 | 20.3115
6 | Temp Accom, brokerage & Transportation | 12.6409 | 0.45 | 0.43 | 0.2 | 0.26 | 0.30521 | 0.30521 | 0.30521 | 0.30521 | 0.30521 | 0.2663 | 2.6824 | 15.7733
7 | Corpus Fund | 0.64328 | 0 | 0.04 | 0.07 | 0.365 | 0 | 0 | 0 | 0 | 0 | 2.0396 | 2.5146 | 3.1579
8 | Admin cost | 5.9746 | 1.08 | 0.17 | 0.08 | 0.085 | 0.17 | 0.11 | 0.1147 | 0.1148 | 0.0903 | 0.0509 | 0.9857 | 8.0403
9 | Bank Gurantee / Interest Cost + Stamp Duty & Registration on DA | 4.4302 | 0.14 | 0.035 | 0.02 | 0.045 | 0.12 | 0.13 | 0.13 | 0.12 | 0.1108 | 0.1537 | 0.8645 | 5.4347
10 | Professional Fees | 2.5771 | 0.26 | 0.085 | 0.04 | 0.035 | 0.06 | 0.1896 | 0.13 | 0.13 | 0.13 | 0.0033 | 0.8029 | 3.64
11 | Advances given | 0.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.31 | -0.31 | 0
12 | Startup Cost | 0 | 0.14755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14755
| TOTAL PAYMENTS ( C ) | 45.0062 | 8.1875 | 3.64 | 2.05 | 2.16 | 7.9152 | 13.5648 | 5.3476 | 4.99 | 0.63631 | 10.7548 | 51.0588 | 104.2525
| Total Cash Outflow / Fund Available (A+B-C) | 0.44748 | 0.60243 | 0.49243 | 0.99243 | 0.44243 | 0.67717 | 0.87485 | 4.4874 | 2.7273 | 50.9976 | 7.319 |  | 7.319
PROFIT