## Final Summary
Project expenses | Estimated Cost as per Santionced Letter | Revised Cost as per TEV Report | Incurred Cost as per Bill till 31.03.2024 | Incurred Cost as per CA till 31.03.2024 | Incurred Cost as per Bill till 15.10.2023 | Incurred Cost as per CA till 15.10.2023 | Difference between both Bills | Difference between both CA | Difference between the Bills & CA | Reasonable Cost certified by VICPL till 15.10.2023 |  | Remark | Justification
Land Cost | 6.89 | 6.89 | 6.8961 | 6.89 | 6.8961 | 6.89 | 0 | 0 | 0.006116 | As per Agreement | 6.89
Construction Cost of Building (including Civil work, Plumbing and Sanitation & Electrification, etc.) | 27.63 | 46.04 | 39.6902 | 43.87 | 32.1987 | 27.72 | 7.4916 | 16.15 | -4.1798 | As per Bills | 39.6902 | Advance Payment against PG Invoice | COC is increase due to 40% additional area in amended plan and price Increase
Plant and Machinery | 9.5 | 13.29 | 12.7078 | 9.63 | 7.1579 | 6.29 | 5.5499 | 3.34 | 3.0778 | As per Bills | 12.7078 |  | P&M is increase due to 40% additional area in amended plan and STP & Kitchen equip. cost is going much higher side.
Furniture and Fixture | 9.08 | 13.85 | 9.8916 | 8.75 | 2.9559 | 2.6 | 6.9357 | 6.15 | 1.1416 | As per Bills | 9.8916 |  | FF is increase due to 40% additional area in amended plan
Approval & TDR Cost | 5 | 5.71 | 4.7461 | 5.9 | 4.7461 | 5.68 | 0 | 0.22 | -1.1539 | As per Bills | 4.7461
Architect Cost, RCC & other Professional fees | 1.17 | 2.49 | 1.4307 | 1.64 | 1.158 | 1.21 | 0.2727 | 0.43 | -0.20929 | As per Bills | 1.4307
Contingencies Expences | 1.38 | 1.46 | 1.2611 | 0 | 0.5723 | 0 | 0.68881 | 0 | 1.2611 | As per Bills | 1.2611 | Bank loan processing fees & stamp duty are not considered by the CA
Interest Cost | 3.89 | 5.22 | 2.911 | 2.79 | 1.5906 | 1.26 | 1.3204 | 1.53 | 0.121 | As per Bills | 2.911
Total Cost | 64.54 | 94.95 | 79.5346 | 79.47 | 57.2755 | 51.65 | 22.2591 | 27.82 | 0.064621 | 0 | 79.5285
|  |  | 15.4154 | 83.76% | 7.2645 | 83.7% |  |  |  |  | 83.76% | 14.9885
Particulars | 24.9 | 17 | 41.9 | Loan Amount |  |  |  | Margin | Client Contribution
Hard Cost (Land Cost + COC + PM + FF) | 53.1 | 80.07 | 69.1796 | 58.83% | 40.6984 | 36.74 | 32.4396 | 61.09%
Interest Cost | 3.89 | 5.22 | 2.911 | 21.85% | 2.91 | 0.0010048
Soft Cost (Approval + Professional + Continegency) | 7.55 | 9.66 | 7.4379 | 100% | 7.4379 | 0
| 64.54 | 94.95 | 79.5285 |  | 51.0463 | 36.741
Particulars | Cost as per TEV Report | Revised Cost as per 1st LIE Report | Reasonable Cost certified by VICPL till 31.03.2024 | Cost incurred as %age total cost of that Component | Cost incurred as %age of cost incurred as on 31.03.2024 | % project cost
Land Cost | 6.89 | 6.89 | 6.8961 | 100.1% | 7.263% | 7.256% | 100%
Construction Cost of Building (including Civil work, Plumbing and Sanitation & Electrification, etc.) | 27.63 | 46.04 | 39.6902 | 86.21% | 41.8% | 48.49% | 166.6%
Plant and Machinery | 9.5 | 13.29 | 12.7078 | 95.62% | 13.38% | 14% | 139.9%
Furniture and Fixture | 9.08 | 13.85 | 9.8916 | 71.42% | 10.42% | 14.59% | 152.5%
Approval & TDR Cost | 5 | 5.71 | 4.7461 | 83.12% | 4.999% | 6.014% | 114.2%
Architect Cost, RCC & other Professional fees | 1.17 | 2.49 | 1.4307 | 57.46% | 1.507% | 2.622% | 212.8%
Contingencies Expences | 1.38 | 1.46 | 1.2611 | 86.38% | 1.328% | 1.538% | 105.8%
Interest Cost | 3.89 | 5.22 | 2.911 | 55.77% | 3.066% | 5.498% | 134.2%
Total | 64.54 | 94.95 | 79.5346 | 83.76% | 83.76% | 100% | 147.1%
Pariculars | 31.03.2024 as per Bill Tally (inclusive of GST) | 15.10.2023 as per Bill Tally (inclusive of GST) | Difference b/w bills of 31.03.2023 & CA Certificate | Difference of Cost incurred as %age of cost incurred as on 31.03.2023 & CA Certificate
Land Cost | 6.8961 | 6.8961 | 0 | 0%
Construction Cost of Building (including Civil work, Plumbing and Sanitation & Electrification, etc.) | 39.6902 | 32.1987
Plant and Machinery | 12.7078 | 7.1579 | -19.49 | -24.51%
Furniture and Fixture | 9.8916 | 2.9559 | 6.94 | 8.726%
Approval & TDR Cost | 4.7461 | 4.7461 | 0 | 0%
Architect Cost, RCC & other Professional fees | 1.4307 | 1.158 | 0.27 | 0.3395%
Contingencies Expences | 1.2611 | 0.5723 | 0.69 | 0.8675%
Interest Cost | 2.911 | 1.5906 | 1.32 | 1.66%
Total | 79.5346 | 57.2755 | 22.26 | 27.99%

## Construction Area
Construction Cost
Floors | FSI Area in Sq. M. | Non - FSI Area in Sq. M. | Total Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Revised Rate / Sq. M. | Full Value after completion | Percentage of work completed | Actual Expenditure till date in `
Basement - 2 | 120.52 | 1494.08 | 1614.6 | 1614.6 | 20069 | 26080 | 42108768 | 95% | 40003329.6
Basement - 1 | 435.78 | 1221.76 | 1657.54 | 1657.54 | 20069 | 26080 | 43228643.2 | 95% | 41067211.04
Lower Ground Floor | 402.51 | 1185.65 | 1588.16 | 1588.16 | 20069 | 26080 | 41419212.8 | 95% | 39348252.16
Ground Floor | 791.05 | 168.43 | 959.48 | 959.48 | 20069 | 26080 | 25023238.4 | 95% | 23772076.48
1st Floor | 503.79 | 160.63 | 664.42 | 664.42 | 20069 | 26080 | 17328073.6 | 95% | 16461669.92
2nd Floor | 689.37 | 203.18 | 892.55 | 892.55 | 20069 | 26080 | 23277704 | 95% | 22113818.8
3rd Floor | 696.83 | 203.18 | 900.01 | 900.01 | 20069 | 26080 | 23472260.8 | 85% | 19951421.68
4th Floor | 573.42 | 203.18 | 776.6 | 776.6 | 20069 | 26080 | 20253728 | 85% | 17215668.8
5th Floor | 573.42 | 203.18 | 776.6 | 776.6 | 20069 | 26080 | 20253728 | 85% | 17215668.8
6th Floor | 573.42 | 194.9 | 768.32 | 768.32 | 20069 | 26080 | 20037785.6 | 85% | 17032117.76
7th Floor | 573.42 | 194.9 | 768.32 | 768.32 | 20069 | 26080 | 20037785.6 | 95% | 19035896.32
8th Floor | 573.42 | 194.9 | 768.32 | 768.32 | 20069 | 26080 | 20037785.6 | 95% | 19035896.32
9th Floor | 573.42 | 203.18 | 776.6 | 776.6 | 20069 | 26080 | 20253728 | 95% | 19241041.6
10th Floor | 578.3 | 203.18 | 781.48 | 781.48 | 20069 | 26080 | 20380998.4 | 95% | 19361948.48
11th Floor | 823.32 | 194.9 | 1018.22 | 1018.22 | 20069 | 26080 | 26555177.6 | 95% | 25227418.72
12th Floor | 1233.66 | 194.9 | 1428.56 | 1428.56 | 20069 | 26080 | 37256844.8 | 95% | 35394002.56
13th Floor | 553.61 | 203.18 | 756.79 | 756.79 | 20069 | 26080 | 19737083.2 | 95% | 18750229.04
Terrace & OHT | 28.56 | 728.23 | 756.79 | 756.79 | 20069 | 26080 | 19737083.2 | 85% | 16776520.72
TOTAL | 10297.82 | 7355.54 | 17653.36 | 17653.36 |  |  | 460399628.8 | 92.75% | 427004188.8
7299.61 | 460399975.0774 | 1.4107 | #NAME? | 354300000
20069.8337
Plant & Machinery | [6 empty] | 13740.09
Particulars | Revised Estimate | Previous TEV | Percentage of work completed | Actual Expenditure till date in ` |  |  | 276300000
Air - Conditioning | 45907000 | 34000000 | 97.15% | 44599711.8 |  | 135% | 20109.0386
Lifts | 15694000 | 14000000 | 75.83% | 11901180 |  | 112.1%
Kitchen & Refrigeration Equipments | 17999000 | 10000000 | 167.4% | 30123591 |  | 180%
Gym Equipments | 1350000 | 1000000 | 0% | 0 |  | 135%
Fire Fighting Equipments, Sprinkler & Smoke Detector Systems | 11046000 | 8000000 | 142.6% | 15748032 |  | 138.1%
DG Set | 9450000 | 7000000 | 227.9% | 21537781 |  | 135%
Sewage Treatment Plant | 1988000 | 1000000 | 49.86% | 991200 |  | 198.8%
ELV Systems | 12017000 | 8000000 | 0% | 0 |  | 150.2%
IT Equipemnts & Software | 12000000 | 8000000 | 18.13% | 2176015 |  | 150%
Crockery, Cutlery & Glassware | 2700000 | 2000000 | 0% | 0 |  | 135%
Housekeeping Supplies, Linens & Uniform | 2700000 | 2000000 | 0% | 0 |  | 135%
TOTAL | 132851000 | 95000000 | 95.65% | 127077510.8
Furniture and Fixtures
Particulars | Revised Estimate | Previous TEV | Percentage of work completed | Actual Expenditure till date in `
FF for 125 keys | 55000000 | 42800000 | 169.2% | 93034229.4 | 1.869% | 128.5%
FF for Restaurant | 10000000 | 6000000 | 0% | 0 |  | 166.7%
FF for Banquet | 6000000 | 6000000 | 5.9% | 354000 |  | 100%
FF for Reception | 8000000 | 6000000 | 0% | 0 |  | 133.3%
FF for Meeting Rooms | 7500000 | 0 | 0% | 0 |  | #DIV/0!
FF for Roof Top Bar | 4000000 | 0 | 0% | 0 |  | #DIV/0!
FF for Other Public Area | 25000000 | 10000000 | 0% | 0 |  | 250%
FF for BOH | 23000000 | 20000000 | 24.03% | 5528011 |  | 115%
TOTAL | 138500000 | 90800000 | 71.42% | 98916240.4 |  | 152.5%

## otis lift
otixs | 52ni8536 | 2613500
| 52ni8535 | 2613500
| 52ni8534 | 2591000
| 52ni8533 | 2591000
| 52ni8532 | 2591000
13000000
2340000
15340000

## Summary Sheet
Sr. No. | Particulars | Incurred Cost in ` till 15.10.2023 as per bill | Incurred Cost in ` Cr. Till 15.10.2023 | Incurred Cost in ` till 15.10.2023 as per bill | Incurred Cost in ` Cr. Till 15.10.2023 | Balance | Balance in Cr.
1 | Land Cost | 68961160 | 6.8961 | 68961160 | 6.8961 | 0 | 0
2 | Construction Cost | 396902344.09 | 39.6902 | 321986503.53 | 32.1987 | 74915840.56 | 7.4916 | 127278700 | 58.8597
| P& M | 127077510.8 | 12.7078 | 71578838.88 | 7.1579
| F&F | 98916240.4 | 9.8916 | 29558759.08 | 2.9559
3 | Approval Cost & Stamp Duty | 47460776 | 4.7461 | 47460776 | 4.7461 | 0 | 0
4 | Professional Cost | 14307091 | 1.4307 | 11580111 | 1.158 | 2726980 | 0.2727
5 | Admin Cost | 12611039 | 1.2611 | 5722961 | 0.5723 | 6888078 | 0.68881
7 | Interest Cost | 29110048.28 | 2.911 | 15905688 | 1.5906 | 13204360.28 | 1.3204
| Total | 795346209.57 | 79.5346 | 572754797.49 | 57.2755 | 97735258.84 | 9.7735
414669840.29
|  | 52200000 |  | 181926683 | 233891076
|  | 23089951.72 |  | 177402371.71 | 51964393
|  |  |  | 359329054.71 | 3376392.58
562732.0967

## Land Cost
Land Cost Description
Sr. No. | Date | Particulars | Description | Total Cost | Incurred Cost
1 | 16.02.2016 | Survey No. 804/A/9/1 | Purchase Cost | 32500000 | 32500000
2 |  |  | Stamp Duty | 1950000 | 1950000
3 |  |  | Reg. Fees | 30000 | 30000
4 |  |  |  | 580 | 580
5 | 16.02.2016 | Survey No. 804/A/9/2 | Purchase Cost | 32500000 | 32500000
6 |  |  | Stamp Duty | 1950000 | 1950000
7 |  |  | Reg. Fees | 30000 | 30000
8 |  |  |  | 580 | 580
Total |  |  |  | 68961160 | 68961160

## TDR & Approval
SR.NO | PARTICULARS | TOTAL AMOUNT | As per CA
1 | Nasik Municipal Corporation | 6397342 | 6397342
2 | RCSPL (PF) | 59000 | 59000
3 | Happy Home Developers | 590000 | 590000
4 | Nashik Municipal Corporation | 94490 | 94490
5 | Nashik Municipal Corporation | 21597190 | 21597190
6 | Nashik Municipal Corporation | 518544 | 518544
7 | Nashik Municipal Corporation | 12050 | 12050
8 | TDR Corporation | 17500000 | 17500000
9 | Ministry of Corporate | 642160 | 642160
10 | Maharashtra Pollution Control Board | 50000
11
12
|  | 47460776 | 47410776

## Material 16.10.2023 to 31.03.20
Sr.No. | Party Name | Description | Invoice No. | Date | Amount ₹
1 | Amita Construction | Providing & applying Dr.Fixit Bathseal & Bathroom Screeding | GST 033-2023-24 | 2023-10-27 | 631390
2 | Bhattad Brothers | Readiplast Project | 23-24/1296 | 2023-10-29 | 5750
3 | Bhattad Brothers | Fixoblock 40 Kg | 23-24/1816 | 2023-12-15 | 6750
4 | Bhattad Brothers | Readiplast Project0 | 23-24/1883 | 2023-12-26 | 2300
5 | Keec (I) Pvt.Ltd | HT works, Rising Mains, DG Set, LT Panels, Distribution Boards, Vables & Trays, Conduit Wiring, Kitchen Wiring, Light Fixtures, Earthing, External Lighting Vabling Excluding Light Fixtures | GM2/2324 | 2023-12-30 | 14750000
6 | Gordhandas Khialds & Bros. | White Createx Dholpur 25 Kg | 4633/23-24 | 2023-10-17 | 32525
7 | Gordhandas Khialds & Bros. | Basecoat Duralife 20 Ltr | 4878/23-24 | 2023-10-27 | 78540
8 | Gordhandas Khialds & Bros. | White Project TruCare Wall Putty Siprema 40 Kg | 5090/23-24 | 2023-11-04 | 18375
9 | Gordhandas Khialds & Bros. | White Fillin Putty 40 Kg | 5464/23-24 | 2023-11-20 | 13500
10 | Gordhandas Khialds & Bros. | White Createx Dholpur 25 Kg | 5562/23-24 | 2023-11-24 | 13010
11 | Gordhandas Khialds & Bros. | Project ACE Suprema 20 Ltr | 5563/23-24 | 2023-11-24 | 29800
12 | Gordhandas Khialds & Bros. | White Exterior Wall Putty 40 Kg | 5767/23-24 | 2023-12-04 | 18375
13 | Gordhandas Khialds & Bros. | Basecoat Duralife 20 Ltr | 6298/23-24 | 2023-12-27 | 78540
16 | Pooja Dimond Tools Sales & Services | Mapsi Set In 40Kg, Freight & Cartage & Hamali Local | 1639 | 2023-10-28 | 40416
17 | Pooja Dimond Tools Sales & Services | Mapsi Set In 40Kg, Freight & Cartage & Hamali Local | 1666 | 2023-11-01 | 40416
18 | Pooja Dimond Tools Sales & Services | Mapsi Set In 40Kg, Freight & Cartage & Hamali Local | 1709 | 2023-11-04 | 133777
19 | Pooja Dimond Tools Sales & Services | Resina 943 S 1 Kg, Indurete BM30H 300GM | 1723 | 2023-11-06 | 2250
20 | Pooja Dimond Tools Sales & Services | Resina 943 S 1 Kg, Indurete BM30H 300GM | 1823 | 2023-12-01 | 4500
21 | Pooja Dimond Tools Sales & Services | Vetra 20 Gm, Roff Cera Clean 5 Ltr | 1853 | 2023-12-02 | 4200
22 | Pooja Dimond Tools Sales & Services | Keracolour SF 130 1 Kg, Keracolour SF 112 1 Kg | 1857 | 2023-12-04 | 1000
23 | Pooja Dimond Tools Sales & Services | Resina 943 S 1 Kg | 2032 | 2023-12-25 | 6355
24 | Pooja Dimond Tools Sales & Services | Mapsi Set In 40Kg, Freight & Cartage & Hamali Local | 2053 | 2023-12-29 | 67478
28 | Shree Bhagawati Enterprises | Wastage & Scrap | SBE/1299 | 2023-10-29 | 26260
29 | Shree Bhagawati Enterprises | Ecolite AAC Block 625 x 240 x 110 mm, Ecolite AAC Block 625 x 240 x 150 mm | SBE/1309 | 2023-10-31 | 60769
30 | Shree Bhagawati Enterprises | Wastage & Scrap | SBE/1593 | 2023-12-25 | 27092
31 | S I Engineering | Plumbing Work | GT/24 | 2023-11-07 | 236202
41 | Amita Construction | Providing & applying Dr.Fixit Bathseal & Bathroom Screeding | GST 033-2023-24 | 2023-10-27 | 631390
42 | S I Engineering | Plumbing Work | Performa | 2024-01-04 | 1500000
46 | Bhattad Brothers | Waterproofing Materials | Performa | 2024-01-05 | 903280
47 | Granite Point | Quartz | Performa | 2023-11-28 | 83756
48 | Modwin Networks | Passive | MUM/PI/2324/76 | 2024-01-02 | 11942553
49 | S.R Services | Steel Doors | SR-23-24/06-12/fpbs | 2023-12-07 | 240384
51 | Welspun Global Brands Limited | MTO, Skirting, T Profile, Q Round, Installation |  |  | 2705023
52 | Amita Construction | Providing & applying Dr.Fixit Bathseal & Bathroom Screeding | GST-046-2023-24 | 2024-01-27 | 714347
53 | Amita Construction | Providing & applying Dr.Fixit Bathseal & Bathroom Screeding | GST- 033-2023-24 | 2023-10-27 | 631390
54 | Atlas Ceramics World LLP | SCD, CCR WFMTP 150 Marble Tile Prime | 1177/2023-24 | 2023-11-25 | 141659
55 | Bhattad Brothers | Readiplast Project, Fixoblock 40 Kg | 23-24/2089 | 2024-01-19 | 6900
60 | Jadhav Electricals | ACE Bright 14W | BAL/0533/23-24 | 2023-10-30 | 15049
61 | JSA Enterprise | River Sand | 119 | 2024-01-10 | 121012
62 | Mamata Building Materials | PPC Cement | MBM2311/INV0768 | 2023-11-29 | 70000
63 | Mamata Building Materials | PPC Cement | MBM2401/INV0692 | 2024-01-16 | 10200
64 | Mamata Building Materials | PPC Cement | MBM2401/INV0696 | 2024-01-16 | 34000
65 | Mamata Building Materials | PPC Cement | MBM2310/INV1003 | 2023-10-26 | 93750
66 | Gordhandas Khialds & Bros. | Basecoat Duralife 20 Ltr | 4634/23-24 | 2023-10-17 | 52360
69 | Gordhandas Khialds & Bros. | Apex Suprema PAB21 20Ltr | 6459/23-24 | 2024-01-02 | 14490
70 | Gordhandas Khialds & Bros. | Black PGE 20Ltr | 6760/23-24 | 2024-01-02 | 4790
71 | Gordhandas Khialds & Bros. | Dsigner Shade Ultima Protek UP1 4Ltr | 6605/23-24 | 2024-01-08 | 46815
72 | Gordhandas Khialds & Bros. | BR White Ultima Protek 20 Ltr | 6615/23-24 | 2024-01-08 | 45705
73 | Gordhandas Khialds & Bros. | Apex Suprema PAB21 20Ltr | 6649/23-24 | 2024-01-10 | 14490
74 | Gordhandas Khialds & Bros. | Dsigner Shade Ultima Protek UP1 4Ltr | 6674/23-24 | 2024-01-11 | 46815
75 | Gordhandas Khialds & Bros. | BR White Ultima Protek 20 Ltr | 6687/23-24 | 2024-01-12 | 45705
76 | Gordhandas Khialds & Bros. | Basecoat Duralife 20 Ltr | 6739/23-24 | 2024-01-15 | 10472
77 | Gordhandas Khialds & Bros. | BR White Ultima Protek 20 Ltr | 6837/23-24 | 2024-01-19 | 45705
78 | Gordhandas Khialds & Bros. | Dsigner Shade Ultima Protek UP1 4Ltr | 6835/23-24 | 2024-01-19 | 93630
79 | Gordhandas Khialds & Bros. | Basecoat Duralife 20 Ltr | 6836/23-24 | 2024-01-19 | 41888
80 | Gordhandas Khialds & Bros. | White Project TruCare Putty Suprema 40 Kg | 7049/23-24 | 2024-01-29 | 14700
81 | Gordhandas Khialds & Bros. | Basecoat Duralife 20 Ltr | 7249/23-24 | 2024-02-06 | 26180
82 | Gordhandas Khialds & Bros. | Dsigner Shade Ultima Protek UP1 4Ltr | 7279/23-24 | 2024-02-07 | 46575
83 | Gordhandas Khialds & Bros. | White Createx Dholpur 25 Kg | 7460/23-24 | 2024-02-15 | 32525
84 | Keec (I) Pvt.Ltd | Supply of Electrical Item as per Annexure | GM/2223/RA3 | 2024-02-09 | 2197471.64
85 | Keec (I) Pvt.Ltd | Supply of Electrical Item as per Annexure | GM/2223/RA4 | 2024-02-09 | 43860
86 | Keec (I) Pvt.Ltd | Supply of Electrical Item as per Annexure | GM/2223/RA5 | 2024-02-09 | 1495449
87 | Keec (I) Pvt.Ltd | Supply of Electrical Item as per Annexure | GM1/2324/RA2 | 2024-02-13 | 1149821
88 | Keec (I) Pvt.Ltd | Supply of Electrical Item as per Annexure | GM1/2324/RA3 | 2024-02-13 | 3212817
89 | Keec (I) Pvt.Ltd | Supply of Electrical Item as per Annexure | GM1/2324/RA4 | 2024-02-13 | 4069634
90 | Keec (I) Pvt.Ltd | Supply of Electrical Item as per Annexure | GM1/2324/RA5 | 2024-02-13 | 9536256
91 | Keec (I) Pvt.Ltd | Supply of Electrical Item as per Annexure | GM1/2324/RA6 | 2024-03-22 | 4627266
92 | Keec (I) Pvt.Ltd | Supply of Electrical Item as per Annexure | GR/2324/RA1 | 2024-02-09 | 214519
93 | Keec (I) Pvt.Ltd | Supply of Electrical Item as per Annexure | GR/2324/RA2 | 2024-02-09 | 244732
94 | Keec (I) Pvt.Ltd | Supply of Electrical Item as per Annexure | GM1/2324/RA1 | 2024-02-13 | 11104404
95 | Keec (I) Pvt.Ltd | Supply of Electrical Item as per Annexure | WIRE/2324/RA1 | 2024-02-09 | 240633
110 | Alchemist Associates | 24 mm DGU Glass | 2023-2024/63 | 2024-02-28 | 3448994
111 | Amita Construction | Providing & applying Dr.Fixit Bathseal & Bathroom Screeding | GST 047-2023-24 | 2024-02-24 | 252021
116 | Bhattad Brothers | CIPOXY 16 D Hardner 20L | 23-24/2116 | 2024-01-23 | 27900
117 | Bhattad Brothers | Dr. Fixit Bathseal | 23-24/2068 | 2024-01-17 | 106875
118 | Bhattad Brothers | CIPOXY 16 D Hardner 20L | 23-24/2069 | 2024-01-17 | 27900
119 | Bhattad Brothers | CIPOXY 16 D Hardner 20L | 23-24/2189 | 2024-02-02 | 111600
120 | Bhattad Brothers | Fixoblock 40 Kg | 23-24/2482 | 2024-03-09 | 4500
121 | Designer Cincrete Pvt Ltd | RMC M-20 Grade | DCPLDK2324/07740 | 2024-03-12 | 18500
122 | Designer Cincrete Pvt Ltd | RMC M-20 Grade | DCPLDK2324/07814 | 2024-03-14 | 20812
123 | Designer Cincrete Pvt Ltd | RMC M-20 Grade | DCPLDK2324/012392 | 2024-03-12 | 34688
124 | Designer Cincrete Pvt Ltd | RMC M-20 Grade | DCPLDK2324/012398 | 2024-03-12 | 20812
125 | Ensys Engineers Pvt Ltd | Water treatment Plant | 23-24/165 | 2024-03-31 | 2967700
126 | Ensys Engineers Pvt Ltd | Hot Water System | 23-24/164 | 2024-03-31 | 2968880
127 | Flyiocrete Creen Concrete LLP | Flyocrete Brokan | TLG/23-24/8685 | 2024-03-05 | 9740
128 | Ganesh Contractor | Tile Labour LumSum | 56 | 2024-02-13 | 600000
129 | Granite Point | Marble Quartz | 333 | 2023-12-23 | 83756
130 | Granite Point | Marble Quartz | 438 | 2024-02-28 | 757786
131 | GreenAct | Advance Along with work order for Design, supply | 98 | 2024-03-14 | 165200
132 | Heena Enterprises | Salted Concrete Crey | 368 | 2024-02-15 | 317456
134 | Jadhav Electricals | Polycab | BAL/0357/23-24 | 2023-10-16 | 12532
135 | Jadhav Electricals | 14W CW B22 | BAL/0533/23-24 | 2023-10-30 | 15049
136 | Jadhav Electricals | 20W LED | BAL/0534/23-24 | 2023-10-30 | 58328
137 | Jadhav Electricals | Slimline Next CDL 20W | BAL/1735/23-24 | 2024-01-12 | 1800
138 | JSA Enterprise | River Sand | 127 | 2024-03-21 | 59729
139 | Mamata Building Materials | PPC Cement | MBM2401/INV0760 | 2024-01-18 | 33500
140 | Mamata Building Materials | PPC Cement | MBM2403/INV0152 | 2024-03-04 | 67000
144 | Gordhandas Khialds & Bros. | White Project ACE Suprema 20 Ltr | 7809/23-24 | 2024-02-27 | 48175
145 | Gordhandas Khialds & Bros. | DS AP APCO GLS ENML EB1 19.8 Ltr | 7861/23-24 | 2024-02-29 | 5175
146 | Gordhandas Khialds & Bros. | Designer Shade Ultima Protech UP1 4 Ltr | 8494/23-24 | 2024-03-21 | 46575
147 | Gordhandas Khialds & Bros. | Designer Shade Ultima Protech UP1 4 Ltr | 7458/23-24 | 2024-02-15 | 93150
148 | Gordhandas Khialds & Bros. | White Fillin Putty 40 Kg | 8054/23-24 | 2024-03-06 | 13500
149 | Gordhandas Khialds & Bros. | Ultraprotechsup PSBSCT 20 Ltr | 8797/23-24 | 2024-03-31 | 52360
150 | N K Trading Co. | 3/4" Curing Pipe, 3/4" Tubing Connector, Hose Clip, Dr. Fixit Super Latex 5 Ltr, Birla White Cement 5 Kg | 23-24/527 | 2024-03-01 | 13869
152 | Pooja Dimond Tools Sales & Services | Mapsi Set In 40Kg | 2598 | 2024-02-27 | 55085
163 | Shivshambo Infraprojects Pvt Ltd | RMC M15 | RMC/23-24/21453 | 2024-03-23 | 29050
164 | Shivshambo Infraprojects Pvt Ltd | RMC M15 | RMC/23-24/21435 | 2024-03-23 | 29050
165 | Shivshambo Infraprojects Pvt Ltd | RMC M25 | RMC/23-24/21688 | 2024-03-28 | 32900
166 | Shivshambo Infraprojects Pvt Ltd | RMC M15 | RMC/23-24/21707 | 2024-03-28 | 32900
167 | Shree Bhagawati Enterprises | Wastage & Scrap | SBE/2067 | 2024-03-11 | 31000
168 | Gaurav Ceramics Studio | 24" x 6" Tiles | GCS/286/23-24 | 2024-02-16 | 502090
169 | Shri Parasnath Exports | Marble Slabs | SPN/1672/23-24 | 2024-03-17 | 716543
170 | Shivshambo Infraprojects Pvt Ltd | RMC M25 | RMC/23-24/21699 | 2024-03-28 | 32900
172 | Spectrum Lights | Track, Spare Part | 330/23-24 | 2024-02-23 | 140277
173 | Spectrum Lights | Down Light | 340/23-24 | 2024-03-20 | 1558975
174 | Spectrum Lights | Down Light, LED Light, Driver, Aluminium Chanel Patti | 329/23-24 | 2024-02-23 | 950032
175 | S R Services | Steel Doorset | SR/0115/2023-24 | 2024-03-20 | 801281
176 | TBK Deepgiri Tile Bath Kitchen P. Ltd | 1200 x 600 Runa Grigio Scuro | 23-24/5246 | 2024-02-07 | 528000
177 | Ultra Firetech Systems Pvt Ltd | Cable | SC/23-24/083 | 2024-01-22 | 630930
178 | Ultra Firetech Systems Pvt Ltd | Speaker, Fire Alarm Control Panel, Repeater Panel | SC/23-24/087 | 2024-02-12 | 787086
179 | Ultra Firetech Systems Pvt Ltd | Speaker, Fire Alarm Control Panel, Repeater Panel | SC/23-24/093 | 2024-03-09 | 698367
180 | Ultra Firetech Systems Pvt Ltd | Hooter Cum Strobe, Fire Fighters Telephone Jack | SC/23-24/098 | 2024-03-18 | 79656
181 | Universal Bricks | Red Bricks 4" | 271 | 2024-02-25 | 89600
182 | Universal Bricks | Red Bricks 4", 6" | 274 | 2024-03-09 | 45024
183 | Universal Bricks | Red Bricks 4" | 273 | 2024-03-03 | 71680
184 | Universal Bricks | Red Bricks 4", 6" | 277 | 2024-03-17 | 45024
185 | Universal Bricks | Crusher, Aggregate, Artificial Sand | 275 | 2024-03-09 | 32130
186 | Universal Bricks | Red Bricks 6" | 280 | 2024-03-26 | 27104
187 | Universal Bricks | Artificial Sand | 279 | 2024-03-18 | 7980
95314496.64

## Material 01.04.23 to 15.10.2023
Gillani Hospitality Private Limited
WIP Report Annexure from 01/04/2023 to 15/10/2023
| Particulars | Nature of Work | Amount Paid (in Rs.) | Column1
| Shah Machineries | Repairs & Maintenance | 14500
| Alchemist Associates | Installation of Window & Façade Work | 3800000
| Amita Construction | Waterproofing work | 610055
| Arihant Ceramics | Supply of Ceramics | 410395
| Arihant Steel Point Pvt. Ltd | Supply of Steel | 1530790
| Atlas Ceramics World LLP | Supply of Sanitary Materials | 1700475
| Bhattad Brothers | Supply of Fibre Plaster | 60850
| Ceramic Traders | Supply of Ceramics | 95120
| Claystone Granito Pvt Ltd | Supply of tiles | 571249
| G Shoppee | Supply of Drainage Material | 239609
| Heena Enterprises | Supply of tiles | 1087265
| Infinity Fibre World | Supply of Cables | 173460
| Jyotirling Enterprises | External Texture work & Paints | 590000
| Lancosa Ceramics LLP | Supply of Tiles | 316950
| Mamata Bulding Materials | Supply of Cement | 1045000
| M/S Hari Om Steel | Supply of Steel | 896454
| N K Trading Co | Plumbing Material | 38114
| Patwa Associates | Engineering Advisory Services | 733530
| Pelican Ceramic Industries Pvt Ltd | Supply of Ceramics | 369996
| Pooja Diamonds Tools Sales & Services | Supply of Adhesive | 221462
| Shree Bhagwati Enterprises | Block Work | 701341
| S I Engineering | Plumbing Material | 7236858.54
| Suchit Steel | Supply of Steel | 1864597
| TBK Deepgiri Tile Bath Kitchen Pvt. Ltd | Supply of Tiles | 528000
| Ultratech Cement | Supply of Cements | 1740000
| Varda Constructions | RCC Work | 11800000
| Maharashtra Aluminium Centre | Rectangular Tube | 47407
| M/S Gordhandas Khialdas & Bros | Supply of Wall Putty & Paints | 540905
| Shri Parasnath Limited | Supply of Marble | 1571819
| Fibre House | Supply of Toilets | 35400
| Granite Point | Supply of Granite & Marble | 246973
| Jyoti India KitchenSink Pvt Ltd | Supply of Sinks | 24696
| Diamond Plate Profiles | Supply of Marble | 668659
| Total |  | 41511929.54
Note: Expenditure is considered on Payment basis.

## Advance Payment Sheet
Name | Work | Amount
Alchemist Associates | Installation of Window & Façade Work | 6506069 | PG Advance Payment
Amita Construction | Waterproofing work | 1256350 | PG Advance Payment
SI Engineering | Plumbing Material | 4602944 | PG Advance Payment
Varda Constructions | RCC Work | 14895000 | PG Advance Payment
TOTAL |  | 27260363

## MATERIAL 01.04.21 TO 31.03.23
Particulars | Gross Total
A K Electricals | 12008
Alchemist Associates | 5195087
Amita Construction | 882604
Anand Ceramics | 35511
Apex India | 49442
ARC Technocon Pvt Ltd | 289221
Arihant Ceramics | 759864.5
Arihant Steel Point Pvt. Ltd | 1414737.9
Atharva Enterprises | 139016
Atlas Ceramics World LLP | 1488947
Bharat Enterprises | 14993
Bhattad Brothers | 52986
Ceramic Traders | 82816
Chinmay Enterprises | 5560
Claystone Granito Pvt Ltd | 208147
Devendra Electricals | 51093
Dhandai Enterprises | 37702
Diamond Traders | 5750
Drashti veneers | 5299
Fabwell Industries | 215000
Flyocrete Green Concrete LLP | 21948
GM2 & Co | 8980
Gorana Facade Solutions | 63307
G Shoppee | 212543
GSW Infra Solutions | 127440
Hari Krupa Granite | 197884
Harsiddhi Ceramics | 13500
Hatim Traders | 9004.58
Heena Enterprises | 3428027
Indoline Industries Pvt Ltd | 656340
Jadhav Electricals | 258261
JSA Enterprises | 110409.6
JT Marble & Granite LLP | 671420
KEEC (I) Pvt. Ltd | 4322713
King Koil | 12980
Lancosa Ceramics LLP | 800354
Make Infracon | 103512.75
Mamata Bulding Materials | 2087570
Modwin Networks Pvt Ltd | 3997336
MS Architectural solutions | 146396
M/s Hari Om Steel | 162897
N A Enterprises | 7020
Nasik Cables & Electricals | 12327
Nishu Glass | 16520
N K Trading Co | 92992
Patwa Associates | 1498910
Plywood Corporation | 167002
Pooja Diamonds Tools Sales & Services | 255598
Post Tension Services (Gujarat) LLP | 1483198
Prince Aly Khan Hospital | 1610000
Sagar Lifts | 454300
SAM ENTERPRISES | 27224
Shah Machinery Stores | 14500
Shanti Metal Industries | 28320
Shelar Enterprises | 750000
Shivang Hardware | 17559.98
Shree Bhagwati Enterprises | 1624193
Shree Manek Kitchen Equipments Pvt Ltd | 5672203
Shreem Corporation | 302080
S I Engineering | 7695729
Spectrum Lights | 42540
Suchit Steel | 12174987
Trinetra Carpets | 69196
TVG Tradelink LLP | 17492
Ultra Firetech Systems Pvt Ltd | 1727691
Ultratech Cement | 3440000
Vaishali Vishwanath Gupte | 3000
Varda Constructions | 53041000
Vishwakarma Concept Studio | 12381.6
Welspun Global | 62663
Wyntronix Innovations Pvt Ltd | 31683
Maharashtra Aluminium Centre | 47407
M/s Gordhandas Khialdas & Bros | 187590
Zubair Interior | 472000
ACC Cements | 484000
Anant Extrushion | 121501
Arihant Steel | 309541
Croma Traders | 108529
Delta Mechanical & Electrical Industries | 250717
Designer Concrete | 515532
Fabweil | 415000
Gayatri Enterprises | 7145
Ginni Spectra | 31692
Hans Electrical | 96109
Hemant Sales Corporation | 4186240
Jadhav Electricals | 42732
Marnta Building Material | 277649
Modern Electro Enterprises | 2053
MSEDCL | 3566270
N K Trading Company | 429054
Om Traders | 44500
Pooja Trading | 128762
Post Tension Services Gujarat LLP | 3395032
Sandesh Enterprise | 69615
Shah Machinery Stores | 54900
Shree Bhazwati Enterprises | 240534
Suchit Steel | 30849509
Ultratech Cement Limited | 13544300
Urwish Engineers | 309000
VTrans Ltd. | 3580
Vaishavi Electricals | 31545
Vardha Constructions | 43366700
Vardha Constructions | 1613000
Miscellaneous Exp | 2260
Ensys | 6900640
Grand Total | 232815554.91

## Plant & Machinery
Air Conditioning |  | Lift |  | Kitchen |  | DG Set |  | Fire Fighting |  | IT |  | STP
Particulars | Amount | Particulars | Amount | Particulars | Amount | Particulars | Amount | Particulars | Amount | Particulars | Amount | Particulars | Amount
Ventus Airconditioning Pvt. Ltd | 14019649.8 | OTIS | 9604728 |  |  | KEEC (I) Pvt. Ltd | 6017781 | Sneha Enterprise | 3589055 | Modwin Networks Pvt Ltd | 2176015 | Green Act | 991200
|  | Otis | 2296452 | Shree Manek Kitchen Equipments Pvt Ltd | 5542010 | Prince Aly Khan Hospital | 2700000 | Sneha Enterprise | 2286594
Ventus Airconditioning Pvt. Ltd | 5613603 |  |  | Shree Manek Kitchen Equipments Pvt. Ltd | 6085102 | KEEC (I) Pvt. Ltd | 11800000 | Ultra Firetech Systems Pvt Ltd | 2520818
Prince Aly Khan Hospital | 500000 |  |  | Shree Manek Kitchen Equipments Pvt. Ltd | 158887 | Voltamp Transformers LTD | 1020000 | Sneha Enterprises | 1007897
Ventus Airconditioning Pvt Ltd | 2219275 |  |  | Shree Manek Kitchen Equipments Pvt. Ltd | 1200945 |  |  | Sneha Enterprises | 4790842
Ventus Airconditioning Pvt Ltd | 2522565 |  |  | Shree Manek Kitchen Equipments Pvt. Ltd | 4639198 |  |  | Sneha Enterprises | 1552826
Ventus Airconditioning Pvt Ltd | 52002 |  |  | Shree Manek Kitchen Equipments Pvt. Ltd | 3411379
Ventus Airconditioning Pvt Ltd | 1254373 |  |  | Shree Manek Kitchen Equipments Pvt. Ltd | 6085102
Ventus Airconditioning Pvt Ltd | 587704 |  |  | Shree Manek Kitchen Equipments Pvt. Ltd | 776232
Ventus Airconditioning Pvt Ltd | 3603664 |  |  | Shree Manek Kitchen Equipments Pvt. Ltd | 1524678
Ventus Airconditioning Pvt Ltd | 74289 |  |  | Shree Manek Kitchen Equipments Pvt. Ltd | 80261
Ventus Airconditioning Pvt Ltd | 1704135 |  |  | Shree Manek Kitchen Equipments Pvt. Ltd | 619797
Ventus Airconditioning Pvt Ltd | 1100450
Ventus Airconditioning Pvt Ltd | 3425526
Ventus Airconditioning Pvt Ltd | 1522476
Ventus Airconditioning Pvt Ltd | 6400000
TOTAL | 44599711.8 | TOTAL | 11901180 | TOTAL | 30123591 | TOTAL | 21537781 | TOTAL | 15748032 | TOTAL | 2176015 | TOTAL | 991200
Ventus Airconditioning Pvt. Ltd. | 4062302.08 |  |  | Shree Manek Kitchen Equipments Pvt Ltd. | 4536228

## F & F
Keys
Particulars | Descriptions | Amount
Raghbir Interiors Pvt Ltd | Interior works | 9454574
Shree Karni Interior | Supply of Labour of Interior | 732780
Zahra Interiors Pvt. Ltd | Supply of Labour for Interior | 315980
Euronics Industries Pvt Ltd | Supply of Hand Dryers | 238950
Raghbir Interiors Pvt Ltd | Interior | 11450173
Raghbir Interiors Pvt Ltd | Adhoc Payment against work in progress | 5900000
Shivam Interior | Adhoc Payment against work in progress | 1180000
Apex India | Vingcard RFID Locking System Advance | 1042530
A to Z Lifestyle (India) Pvt. Ltd. | Interior Materials | 1849106
Spectrum Lights | Light Pannels & Bulbs | 950025
Arihant Ceramics | Tile Adhesive MYK Lativrete 315 Grey | 34890
Arihant Ceramics | Tile Adhesive MYK Lativrete 315 Grey | 217191
Atlas Ceramics World LLP | TBG04202BB-T | 65844
Atlas Ceramics World LLP | DB505R-1A | 22897
Pelican Ceramic Industries Pvt Ltd | Acid/Alkali Resistant Tiles | 158112
Raghbir Interiors Pvt Ltd | Joinery & Carpentry Services | 2184139
Raghbir Interiors Pvt Ltd | Joinery & Carpentry Services | 19257538
Raghbir Interiors Pvt Ltd | Painting Services, General Cleaning Services | 1168954
Raghbir Interiors Pvt Ltd | Joinery & Carpentry Services, Painting Services, General Cleaning Services | 25018643
Atlas Ceramics World LLP | CCR WFMTP 150 Marble tile prime | 131216
Atlas Ceramics World LLP | Console Lacatory | 65844
Atlas Ceramics World LLP | Faucet | 53737
Atlas Ceramics World LLP | Tiles | 4690500
A to Z Lifestyle (India) Pvt. Ltd. | Interior Materials | 2014495
Phonenix | Carpet | 3173990.4
Trineta Carpets | Carpet | 1662121
TOTAL |  | 93034229.4
Raghbir Interiors Pvt. Ltd. | Interior | 9440000
Banquet
Particulars | Descriptions | Amount
Haffle India Private Limited | Banquet Foldable Partition | 354000
TOTAL |  | 354000
BOH
Particulars | Descriptions | Amount
Green Edge Technologies Pvt Ltd | Building Automation Solutions | 2950000
Green Edge Technologies Pvt Ltd | Building Automation Solutions | 987347
Green Edge Technologies Pvt Ltd | Building Automation Solutions | 1590664
TOTAL |  | 5528011

## Professional
SR.NO | PARTICULARS | TOTAL AMOUNT as bill | As per CA
1 | Arnav Buildcon | 181720 | 181720
2 | Earthscapes Consultancy Pvt Ltd | 383500 | 383500
3 | Kitchen Solutions. Com | 236000 | 236000
4 | Love of Light | 179200 | 179200
5 | Marriott Int'l Design & Const | 2384820 | 2384820
6 | Radiant Consulting Engineers | 584100 | 584100
7 | Reza Kabul Architects Pvt. Ltd. | 1277645 | 1277645
8 | Diwanji & Associates | 20960 | 0
9 | Civil Tech | 198592 | 198592
10 | Durocrete Engineering Services Pvt. Ltd. | 5262 | 5262
11 | ELV Design Solutions | 70000 | 70000
12 | Four Points Sheraton | 3206457 | 3206457
13 | Hydro Mechanical | 118000 | 118000
14 | Kishore Jain | 218000 | 218000
15 | Mitcon Consultancy & Engineering Services | 177000 | 177000
16 | Reza kahul | 871430 | 871430
17 | Manish Nayak | 8000 | 8000
18 | Kallur Subramaniam Ayyadurai | 50000
19 | Kallur Subramaniam Ayyadurai | 13000
20 | Resurgent India Limited | 204475 |  | TEV Report
21 | Vastukala Consultants Pvt. Ltd. | 55000 |  | MPCB Consultant
| Radiant Consulting Engineers | 129800 |  | Design Consultancy
| Siddharth Kheria | 1007150 |  | ROC Charges
| Patwa Associates | 183490
| Patwa Associates | 183490
| Studio August | 708000
| Vastukala Consultants (I) Pvt. Ltd. | 41300
| Reza Kabul Architect | 1180000
| Vastukala Consultants (I) Pvt. Ltd. | 41300
| VCNS Global | 389400
22
TOTAL |  | 14307091 | 10099726

## Admin
SR.NO | PARTICULARS | TOTAL AMOUNT | As per CA
1 | American Express Bakery | 17758 | 0
2 | BinarySoft | 21240 | 0
3 | Food Crafterz | 5410 | 0
4 | Global Sales Corporation | 4860 | 0
5 | MSEB | 1142660 | 1142660
6 | The Eastern Tea Company Limited | 8780 | 0
7 | Open Eye Security Services | 56640 | 56640
8 | VCNS Global | 129800 | 129800
9 | VCNS Global | 422400 | 422400
| Loan Processing Fees | 1616010
| Loan Processing Fees | 29500
| Loan Processing Fees | 4720
| Loan Processing Fees | 41300
| Stamp Duty & Reg. Fees | 766000
| Loan Processing Fees | 500000
| Nasik Municipal Corporation | 34383 |  | Municipal Taxes
| MSEB | 921500 |  | Electricity Expense
| Maharashtra State Electricity Dist. Co. Ltd. | 141930
| Maharashtra State Electricity Dist. Co. Ltd. | 121260
| Maharashtra State Electricity Dist. Co. Ltd. | 117750
| Maharashtra State Electricity Dist. Co. Ltd. | 147870
| Reliable Security & Services | 145330
| Reliable Security & Services | 141030
| Reliable Security & Services | 141600
| Reliable Security & Services | 140001
| Reliable Security & Services | 138847
| Modwin Networks | 157542
| Modwin Networks | 3299870
| Modwin Networks | 2195048
TOTAL |  | 12611039 | 1751500

## Interest
Sr. No. | Month | Interest Amount | As per CA
| 01.04.17 to 25.03.2022 |  |  | L&T | 31416068 | 31416068
1 | 01.04.22 to 31.03.2023 | 4502126 | 4502126
| 01/4/23 to 15/10/23 | 11403562 | 11403562
| 16/10/23 to 31/03/2024 | 13204360.28
|  | 29110048.28 | 15905688
| 05-9-23 to 04-10-23 | 82099
| 05-08-23 to 04-09-23 | 69361
| 5-7-23 to 4-8-23 | 54053
| 5-6-23 to 4-7-23 | 37072
| 05-5-23 to 4-6-23 | 26885
| 05-4-23 to 04-5-23 | 25808
| 5-3-23 to 4-4-23 | 24456
| 5-9-23 to 4-10-23 | 1777887
| 05-9-23 to 04-10-23 | 1836598
| 05-08-23 to 04-09-23 | 1267568
| 5-7-23 to 4-8-23 | 1536419
| 5-6-23 to 4-7-23 | 1685137
| 05-5-23 to 4-6-23 | 1830240
| 05-4-23 to 04-5-23 | 1149979
11403562