## Final Summary
Project expenses | Estimated Cost as per Cost Vetting | Incurred Cost as per Bill till 30.06.2024 | Incurred Cost as per CA till 29.02.2024 | Incurred Cost as per Bill till 30.03.2024 | Incurred Cost as per CA till 29.02.2024 | Difference between the Bills & CA | Difference between both the Bills | Difference between both CA | Remark
Land Cost | 1.56 | 1.5647 | 1.56 | 1.5647 | 1.56 | 0.004742 | 0 | 0
Rent Cost | 14.71 | 11.3165 | 11.32 | 8.2791 | 8.28 | -0.0035 | 3.0374 | 3.04
Construction Cost of Rehab cum Sale Building | 57.23 | 26.8655 | 22.47 | 20.2824 | 8.31 | 4.3955 | 6.5832 | 14.16
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 27.73 | 28.7098 | 28.71 | 19.5446 | 19.54 | -0.000155 | 9.1652 | 9.17
Architect Cost, RCC & other Professional fees | 1.14 | 0.87052 | 0.87 | 0.6978 | 0.7 | 0.000525 | 0.17273 | 0.17
Administrative Expenses | 2.86 | 1.3995 | 1.4 | 0.5804 | 0.58 | -0.000525 | 0.81907 | 0.82
Marketing Expences | 2.75 | 1.0915 | 1.09 | 0.9114 | 0.91 | 0.0015 | 0.1801 | 0.18
Interest Cost | 8.49 | 0.5 | 0.5 | 0 | 0 | 0 | 0.5 | 0.5
Total Cost | 116.47 | 72.3181 | 67.92 | 51.8604 | 39.88 | 4.3981 | 20.4577 | 28.04 | DSRA Amount is not accounted in LIE Report
|  | 44.1519 | 48.55
Particulars | Revised Estimated Cost (in Cr.) | Incurred Cost as per Bill till 30.06.2024 | Cost incurred as %age total cost of that Component | Cost incurred as %age of cost incurred as 30.06.2024 CA Certificate
Land Cost | 1.56 | 1.5647 | 100.3% | 1.343%
Rent Cost | 14.71 | 11.3165 | 76.93% | 9.716%
Construction Cost of Sale Building | 57.23 | 26.8655 | 46.94% | 23.07%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 27.73 | 28.7098 | 103.5% | 24.65%
Architect Cost, RCC & other Professional fees | 1.14 | 0.87052 | 76.36% | 0.7474%
Administrative Expenses | 2.86 | 1.3995 | 48.93% | 1.202%
Marketing Expences | 2.75 | 1.0915 | 39.69% | 0.9372%
Interest Cost | 8.49 | 0.5 | 5.889% | 0.4293%
Total | 116.47 | 72.3181 | 62.09% | 62.09%
Pariculars | 30.06.2024 as per bill | 30.03.2024 as per bill | Difference b/w bills of 30.03.2024 & 30.06.2024 | Difference of Cost incurred as %age of cost incurred as on 30.03.2024 & 30.06.2024
Land Cost | 1.5647 | 1.5647 | 0 | 0%
Rent Cost | 11.3165 | 8.2791 | 3.04 | 4.204%
Construction Cost of Sale Building | 26.8655 | 20.2824 | 6.58 | 9.099%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 28.7098 | 19.5446 | 9.17 | 12.68%
Architect Cost, RCC & other Professional fees | 0.87052 | 0.6978 | 0.17 | 0.2351%
Administrative Expenses | 1.3995 | 0.5804 | 0.82 | 1.134%
Marketing Expences | 1.0915 | 0.9114 | 0.18 | 0.2489%
Interest Cost | 0.5 | 0 | 0.5 | 0.6914%
Total | 72.3181 | 51.8604 | 20.46 | 28.29%

## Summary Sheet
Sr. No. | Particulars | Incurred Cost in ` till 30.06.2024 | Incurred Cost in ` Cr. Till 30.06.2024 | Incurred Cost in ` till 30.03.2024 | Incurred Cost in ` Cr. Till 30.03.2024 | Balance | Balance in Cr.
1 | Land Cost | 15647420 | 1.5647 | 15647420 | 1.5647 | 0 | 0
2 | Rent Cost | 113165000 | 11.3165 | 82790820 | 8.2791 | 30374180 | 3.0374
4 | Construction Cost of Sale Building | 268655404 | 26.8655 | 202823885 | 20.2824 | 65831519 | 6.5832
5 | Approval Cost & Stamp Duty | 287098450 | 28.7098 | 195446000 | 19.5446 | 91652450 | 9.1652
6 | Professional Cost | 8705250 | 0.87052 | 6978000 | 0.6978 | 1727250 | 0.17272
7 | Admin Cost | 13994750 | 1.3995 | 5804000 | 0.5804 | 8190750 | 0.81907
8 | Marketing Cost | 10915000 | 1.0915 | 9114000 | 0.9114 | 1801000 | 0.1801
9 | Interest Cost | 5000000 | 0.5 | 0 | 0 | 5000000 | 0.5
| Total | 723181274 | 72.3181 | 518604125 | 51.8604 | 204577149 | 20.4577
|  | 702533854 |  |  |  |  | 19.9577
84900000
79900000

## Land, Stamp Duty and rent cost
Stamp Duty & Registration Fees
Sr. No. | Agreement Name | Date | Particulars | Amount | Incurred Amount |  | August 21 - July22 | 12
1 | Development Agreement | 2019-03-27 | Stamp Duty | 14497980 | 14497980 |  | August 22 - June 23 | 10
2 |  |  | Reg. Fees | 30000 | 30000 |  | July 23 - August 24 | 14
3 |  |  |  | 2000 | 2000 |  | Sept 24 - July 25 | 11
4 | Rectification Cum Supplementary Deed | 2022-04-29 | Stamp Duty | 1086200 | 1086200 |  | August 25 - June 26 | 11
5 |  |  | Reg. Fees | 30000 | 30000
6 | Special Power of Attorney | 2021-03-27 | Stamp Duty | 500 | 500
7 |  |  | Reg. Fees | 740 | 740 |  | July 26 - Sept 26 | 3
| TOTAL |  |  | 15647420 | 15647420
Sr. No. | Particulars | Commercial Shops | Commercial Offices | Residental Flat | Total | Units
1 | No. of Tenants | 4 | 9 | 48 | 61 | Nos.
2 | Rent per tenant per month for April 23 to Feb 24 | 110000 | 50000 | 40000 |  | Rupees
3 | Rent per year for April 23 to Feb 24 | 4840000 | 4950000 | 21120000 | 30910000 | Rupees
4 | Rent per tenants per month for March 24 to Jan 25 | 121000 | 55000 | 44000 |  | Rupees
5 | Rent per year for March 24 to Jan 25 | 5324000 | 5445000 | 23232000 | 34001000 | Rupees
6 | Rent per tenants per month for Feb 25 to March 25 | 133100 | 60500 | 0 |  | Rupees
7 | Rent per year for Feb 25 to March 25 | 1064800 | 1089000 | 0 | 2153800 | Rupees
8 | Rent per tenants per month for Feb 25 to Dec 25 | 0 | 0 | 48400 |  | Rupees
9 | Rent per year for Feb 25 to Dec 25 | 0 | 0 | 25555200 | 25555200 | Rupees
10 | Rent per tenants per month for Jan 26 to Mar 26 | 0 | 0 | 53240 |  | Rupees
11 | Rent per year for Jan 26 to Mar 26 | 0 | 0 | 7666560 | 7666560 | Rupees
12 | Corpus Fund per Tenant | 800000 | 700000 | 700000 |  | Rupees
13 | Total Corpus Fund | 3200000 | 6300000 | 33600000 | 43100000 | Rupees
14 | Shifting Charges per Tenant | 15000 | 15000 | 15000 |  | Rupees
15 | Total Shifting Charges | 60000 | 135000 | 720000 | 915000 | Rupees
16 | Brokerage Cost | 440000 | 450000 | 1920000 | 2810000 | Rupees
17 | Total Rent Cost (3 + 5 + 7 + 9 + 11 + 13 + 15 + 16) | 14928800 | 18369000 | 113813760 | 147111560 | Rupees

## Sheetal Ekta_Tax Invoices
M/s. DGS Township Private Limited
Sheetal Ekta
Sr. No. | Vendor Name | Customer Name | Invoice Date | Invoice Number | Invoice Amount | Project Name | Description of Material
1 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2023-08-13 | ASC302/23-24 | 1765445 | Sheetal Ekta | T.M.T. Bars 10mm, 12mm, 20mm, 32mm,M.S Wire
2 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2023-09-23 | ASC409/23-24 | 1752115 | Sheetal Ekta | T.M.T. Bars 08mm, 12mm,16mm, 20mm, 32mm, TCS on Sales
3 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2023-10-19 | ASC482/23-24 | 1806562 | Sheetal Ekta | T.M.T. Bars 08mm, 10mm,12mm, 16mm, 20mm, 25mm, TCS on Sales
4 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-02-16 | ASC991/23-24 | 1647889 | Sheetal Ekta | T.M.T. Bars 25mm, 32mm
5 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-02-10 | ASC963/23-24 | 144727 | Sheetal Ekta | M.S Pipe
6 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-01-11 | ASC828/23-24 | 195314 | Sheetal Ekta | M.S Plate
7 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-03-27 | PI/ASC1227/23-24 | 47241294 | Sheetal Ekta | 08mm, 10mm, 12mm, 16mm, 20mm, 25mm & 32mm TMT Bars
8 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-02-27 | ASC1046/23-24 | 1551254 | Sheetal Ekta | T.M.T. Bars 08mm, 10mm,16mm, 20mm,
9 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-01-11 | ASC826/23-24 | 121490 | Sheetal Ekta | M.S Structure,M.S Pipe
10 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-02-07 | ASC951/23-24 | 1777556 | Sheetal Ekta | T.M.T. Bars 08mm, 10mm,12mm, 16mm, 20mm, 25mm
11 | B. Mittal & Co. | DGS Township Pvt Ltd | 2023-11-23 | BM23240206 | 1788957 | Sheetal Ekta | TMT Rebar 08mm,10mm,25mm,32mm,MS Binding wire
12 | B. Mittal & Co. | DGS Township Pvt Ltd | 2023-12-25 | BM23240248 | 1820517 | Sheetal Ekta | TMT Rebar 08mm,12mm,16mm,25mm,32mm,MS Binding wire
13 | B. Mittal & Co. | DGS Township Pvt Ltd | 2024-03-07 | BM23240344 | 1745973 | Sheetal Ekta | TMT Rebar 16mm,20mm,25mm,32mm
14 | B. Mittal & Co. | DGS Township Pvt Ltd | 2023-11-01 | BM23240178 | 1928057 | Sheetal Ekta | TMT Rebar 08mm,12mm,16mm,20mm,25mm,32mm
15 | B. Mittal & Co. | DGS Township Pvt Ltd | 2023-11-09 | BM23240188 | 1860010 | Sheetal Ekta | TMT Rebar 08mm,12mm,16mm,20mm,25mm,32mm
16 | Fine Steel corporation | DGS Township Pvt Ltd | 2023-07-01 | FSC/23-24/25 | 1731227 | Sheetal Ekta | Thermex,TMT Bar 08mm,10mm,12mm,20mm
17 | Fine Steel corporation | DGS Township Pvt Ltd | 2023-06-21 | FSC/23-24/20 | 1819704 | Sheetal Ekta | Thermex,TMT Bar 25mm,G.M.S Wire
18 | Fine Steel corporation | DGS Township Pvt Ltd | 2023-06-24 | FSC/23-24/21 | 1776767 | Sheetal Ekta | Thermex,TMT Bar 25mm
19 | Fine Steel corporation | DGS Township Pvt Ltd | 2023-07-07 | FSC/23-24/27 | 1685839 | Sheetal Ekta | Thermex,TMT Bar 08mm,12mm,32mm
20 | Fine Steel corporation | DGS Township Pvt Ltd | 2023-09-18 | FSC/23-24/46 | 1817448 | Sheetal Ekta | Thermex,TMT Bar 08mm,25mm,32mm
21 | Fine Steel corporation | DGS Township Pvt Ltd | 2023-11-28 | FSC/23-24/74 | 337008 | Sheetal Ekta | PPGI Sheets,MS pipe
22 | Fine Steel corporation | DGS Township Pvt Ltd | 2023-08-04 | FSC/23-24/29 | 1692594 | Sheetal Ekta | Thermex,TMT Bar 12mm,16mm,20mm,25mm
23 | Kratos Concrete | DGS Township Pvt Ltd | 2023-08-31 | 381 | 1244039 | Sheetal Ekta | M 40
24 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-08-24 | AC/23-24/0830 | 2080779 | Sheetal Ekta | M40,M60
25 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-01-29 | AC/23-24/1899 | 92556 | Sheetal Ekta | OPC Without Pump Tax Rate
26 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-07-17 | AC/23-24/0347 | 355416 | Sheetal Ekta | M40 Fiber
27 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-06-30 | AC/23-24/0669 | 233434 | Sheetal Ekta | M 15
28 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-07-17 | AC/23-24/0709 | 2528032 | Sheetal Ekta | M 40 Fiber, Pumping Charges
29 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-07-29 | AC/23-24/0743 | 154025 | Sheetal Ekta | M40,M60
30 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-07-31 | AC/23-24/0760 | 158680 | Sheetal Ekta | M60
31 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-10-20 | AC/23-24/1092 | 411968 | Sheetal Ekta | RMC M-60 OPC,Under load
32 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-02-14 | AC/23-24/2016 | 79709 | Sheetal Ekta | RMC M-15
33 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-12-22 | AC/23-24/1552 | 748061 | Sheetal Ekta | RMC M-60,RMC M-40,Pumping Charges
34 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-01-08 | AC/23-24/1709 | 123576 | Sheetal Ekta | RMC M-60,RMC M-40,RMC M-15
35 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-01-10 | AC/23-24/1737 | 111068 | Sheetal Ekta | RMC M-40
36 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-01-20 | AC/23-24/1842 | 74045 | Sheetal Ekta | RMC M-40
37 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-01-15 | AC/23-24/1779 | 213182 | Sheetal Ekta | RMC M-40, RMC M-20
38 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-01-19 | AC/23-24/1820 | 252933 | Sheetal Ekta | RMC M-40, RMC M-20,Under Load
39 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-08-24 | AC/23-24/0409 | 439279 | Sheetal Ekta | M40
40 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-08-16 | AC/23-24/0791 | 556977 | Sheetal Ekta | M40,M60
41 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-08-16 | AC/23-24/0792 | 221950 | Sheetal Ekta | M 15
42 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-08-29 | AC/23-24/0845 | 464667 | Sheetal Ekta | M60, Pumping Charges
43 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-08-31 | AC/23-24/0863 | 117000 | Sheetal Ekta | M60
44 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-08-31 | AC/23-24/0871 | 144000 | Sheetal Ekta | M60
45 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-09-10 | AC/23-24/0895 | 581022 | Sheetal Ekta | M40, M60
46 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-11-05 | AC/23-24/1210 | 229436 | Sheetal Ekta | RMC M-60 OPC
47 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-10-26 | AC/23-24/1123 | 898260 | Sheetal Ekta | RMC M-60 & M-40 OPC, RMC M4O OPC, Pumping Charges, Under load
48 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-10-11 | AC/23-24/1030 | 625488 | Sheetal Ekta | RMC M-60 & M-40 OPC, RMC M4O OPC, Pumping Charges, Under load
49 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-09-30 | AC/23-24/0971 | 44430 | Sheetal Ekta | M40
50 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-09-30 | AC/23-24/0971 | 333246 | Sheetal Ekta | M40, M60
51 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-09-20 | AC/23-24/0932 | 442589 | Sheetal Ekta | M40, M60
52 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-10-07 | AC/23-24/1003 | 372976 | Sheetal Ekta | RMC M-60 & M-40 OPC
53 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-10-31 | AC/23-24/1155 | 511692 | Sheetal Ekta | RMC M-60 & M-40 OPC, Under load
54 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-10-17 | AC/23-24/1063 | 787856 | Sheetal Ekta | RMC M-60 & M-40 OPC, RMC M4O OPC, Pumping Charges
55 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-12-08 | AC/23-24/1399 | 264099 | Sheetal Ekta | RMC M-60 OPC, Under Road
56 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-11-30 | AC/23-24/1355 | 193668 | Sheetal Ekta | RMC M-60 OPC, Under Road
57 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-11-25 | AC/23-24/1328 | 74045 | Sheetal Ekta | RMC M-60 OPC
58 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-11-25 | AC/23-24/1316 | 238434 | Sheetal Ekta | RMC M-60 OPC
59 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-11-20 | AC/23-24/1282 | 195069 | Sheetal Ekta | RMC M-60 & M-20 OPC, RMC M4O OPC, Under Road
60 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-11-15 | AC/23-24/1267 | 37170 | Sheetal Ekta | RMC M-60 OPC, Under Road
61 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-11-10 | AC/23-24/1252 | 1022145 | Sheetal Ekta | RMC M-60 & M-40 OPC, RMC M4O OPC, Pumping Charges, Under load
62 | S K Traders | DGS Township Pvt Ltd | 2023-06-13 | SK/137/23-24 | 26437 | Sheetal Ekta | Ind Wire 4 Sqmm x 4 core, MCB 63 Amp ABB, MCB Box 2-4 Way
63 | S K Traders | DGS Township Pvt Ltd | 2023-06-29 | SK/138/23-24 | 42000 | Sheetal Ekta | Safety Net
64 | S K Traders | DGS Township Pvt Ltd | 2023-07-07 | SK/211/23-24 | 16048 | Sheetal Ekta | Led Light Fitting
65 | S K Traders | DGS Township Pvt Ltd | 2023-12-04 | SK/578/23-24 | 174182 | Sheetal Ekta | AAC Fly Ash Block
66 | S K Traders | DGS Township Pvt Ltd | 2023-09-12 | SK/378/23-24 | 65021 | Sheetal Ekta | Aluminium Arm Cable, SFU 400 amp Enclouser, Busbar 200 amp, 200 & 100 Amp Main Switch Kew, Aluminium Lugs 120, 70 & 50 spmm, HRC Fuse 400 A
67 | S K Traders | DGS Township Pvt Ltd | 2023-12-09 | SK/5898/23-24 | 89088 | Sheetal Ekta | PPC
68 | S K Traders | DGS Township Pvt Ltd | 2023-12-10 | SK/590/23-24 | 179021 | Sheetal Ekta | AAC Fly Ash Block
69 | S K Traders | DGS Township Pvt Ltd | 2023-10-15 | SK/609/23-24 | 69521 | Sheetal Ekta | 200mm Foamlit 3mtr Pipe SN4, 110 & 75mm Swr Pipe l0', 75mm Swr Nahani Trap WO Jali, Pvc Solvent 500m1
70 | S K Traders | DGS Township Pvt Ltd | 2024-01-21 | SK/697/23-24 | 5458 | Sheetal Ekta | C I Plate 1x1, Gi Pipe, C I Funnel, Bentonite Powder, Copper Wires 8 swg
71 | S K Traders | DGS Township Pvt Ltd | 2023-11-19 | SK/551/23-24 | 79360 | Sheetal Ekta | PPC
72 | S K Traders | DGS Township Pvt Ltd | 2023-09-21 | SK/412/23-24 | 2354 | Sheetal Ekta | 23" Orrisa Pan White, P-Trap Sada
73 | S K Traders | DGS Township Pvt Ltd | 2023-11-16 | SK/545/23-24 | 147168 | Sheetal Ekta | AAC Fly Ash Block
74 | S K Traders | DGS Township Pvt Ltd | 2023-11-01 | SK/507/23-24 | 150460 | Sheetal Ekta | AAC Fly Ash Block, Magic Bond Joint Mortar
75 | S K Traders | DGS Township Pvt Ltd | 2023-11-14 | SK/540/23-24 | 24938 | Sheetal Ekta | Wrap Knit Fabrics
76 | S K Traders | DGS Township Pvt Ltd | 2023-12-21 | SK/618/23-24 | 10266 | Sheetal Ekta | JQR (069) Concealed Body
77 | S K Traders | DGS Township Pvt Ltd | 2023-12-18 | SK/612/23-24 | 111360 | Sheetal Ekta | PPC
78 | S K Traders | DGS Township Pvt Ltd | 2023-12-21 | SK/620/23-24 | 23697 | Sheetal Ekta | 40mm Swr Plpe 10"'B" Type,40mm Agri Elbow, 75mm Swr Pipe 2', Pvc Solvent 250m1, 3/4" Gpvc Elbow 90, 3/4" Cpvc Tee, l/2" Gpvc Threaded End Plug, 3/4"x1/2" Cpvc Brass Elbow 90, 3/4" x l/2" Cpvc Brass MTA, 314'xll2" Cpvc Brass Tee, Cpvc Solvent Coment 473m1
79 | S K Traders | DGS Township Pvt Ltd | 2023-12-25 | SK/634/23-24 | 87552 | Sheetal Ekta | PPC
80 | S K Traders | DGS Township Pvt Ltd | 2023-12-27 | SK/636/23-24 | 75630 | Sheetal Ekta | AAG Fly Ash Block
81 | S K Traders | DGS Township Pvt Ltd | 2024-01-05 | SK/656/23-24 | 109440 | Sheetal Ekta | PPC
82 | S K Traders | DGS Township Pvt Ltd | 2024-01-07 | SK/666/23-24 | 11139 | Sheetal Ekta | Cascade Chair Bracket
83 | S K Traders | DGS Township Pvt Ltd | 2024-01-14 | SK/683/23-24 | 87552 | Sheetal Ekta | PPC
84 | S K Traders | DGS Township Pvt Ltd | 2024-01-21 | SK/696/23-24 | 22050 | Sheetal Ekta | Copper Arm Cable, Bulkhead Metal, Led Bulb 9w, ABB Switch 6A, Gang Box 3w, ABB MCB 16AMP 2 POLE, ABB Mcb 25A4P
85 | S K Traders | DGS Township Pvt Ltd | 2024-01-21 | SK/699/23-24 | 8909 | Sheetal Ekta | SW x BSP Elbow 2000 PSI, Forge Socket Ext Hvy Bsp M.S 15mm, Spc Erw C Class Elbow 80,65,50,40,32,25 mm
86 | S K Traders | DGS Township Pvt Ltd | 2024-01-23 | SK/705/23-24 | 49376 | Sheetal Ekta | 110 & 75mm Swr Pipe 10' , 110 & 75mm Swr Pipe 4' , 110 & 75mm Swr Single Y Plain , 110&75 mm Swr Door Bend , 110&75 mm Swr Plain Bend 90, 110&75 mm Swr Plain Bend 45, 75mm Swr Plain Tee, Rubber Lubricant 500 Gm, G.I.U Bracket , G.I.U Bolt
87 | S K Traders | DGS Township Pvt Ltd | 2024-01-30 | SK/719/23-24 | 109440 | Sheetal Ekta | PPC
88 | S K Traders | DGS Township Pvt Ltd | 2024-01-10 | SK/678/23-24 | 149282 | Sheetal Ekta | AAC Fly Ash Btock, Magic Bond Joint Mortar
89 | S K Traders | DGS Township Pvt Ltd | 2024-01-31 | SK/728/23-24 | 67984 | Sheetal Ekta | TUFF AAC Block
90 | S K Traders | DGS Township Pvt Ltd | 2023-06-03 | SK/114/23-24 | 25404 | Sheetal Ekta | Mcb Four Pole 100A, Mcb Box 2-4 way, Busbar 63amp, 100amp Main switch Kew, 100/200 Amp Neutal
91 | S K Traders | DGS Township Pvt Ltd | 2023-06-16 | SK/227/23-24 | 16992 | Sheetal Ekta | Round water Tank 2000 Ltr
92 | S K Traders | DGS Township Pvt Ltd | 2023-08-06 | SK/259/23-24 | 33276 | Sheetal Ekta | ISI Cube Mould 150mm
93 | S K Traders | DGS Township Pvt Ltd | 2023-08-09 | SK/275/23-24 | 24397 | Sheetal Ekta | 2HP 1ph sub Pump, stator
94 | S K Traders | DGS Township Pvt Ltd | 2023-10-04 | SK/443/23-24 | 15582 | Sheetal Ekta | Hessian Cloth
95 | S K Traders | DGS Township Pvt Ltd | 2023-11-21 | SK/552/23-24 | 150458 | Sheetal Ekta | AAC Fly Ash Btock, Magic Bond Joint Mortar
96 | Neeraj Steel Sales | DGS Township Pvt Ltd | 2023-08-16 | 361/23-24 | 1776884 | Sheetal Ekta | TMT BARS
97 | Neeraj Steel Sales | DGS Township Pvt Ltd | 2023-10-08 | 529/23-24 | 1947976 | Sheetal Ekta | TMT BARS
98 | Neeraj Steel Sales | DGS Township Pvt Ltd | 2023-10-05 | 710/23-24 | 1752482 | Sheetal Ekta | TMT BARS
99 | Neeraj Steel Sales | DGS Township Pvt Ltd | 2023-10-25 | 603/23-24 | 1885754 | Sheetal Ekta | TMT BARS
100 | Vastu RMC LLP | DGS Township Pvt Ltd | 2024-02-18 | VRMCG/2324/00149 | 1929964 | Sheetal Ekta | M-60 Pumpable
101 | Malik Steels Corporation | DGS Township Pvt Ltd | 2023-07-12 | MSC/23-24/49 | 2087205 | Sheetal Ekta | 08 mm, 25mm,32ms TMT Bar
102 | Umika Enterprises | DGS Township Pvt Ltd | 2024-03-04 | 28 | 64994 | Sheetal Ekta | 32mm, 25mm & 20mm dia Coupler
103 | Umika Enterprises | DGS Township Pvt Ltd | 2024-03-05 | 29 | 59660 | Sheetal Ekta | 32mm & 25mm dia Coupler, 32/25mm dia Reducer Coupler
104 | Umika Enterprises | DGS Township Pvt Ltd | 2024-03-06 | 30 | 69242 | Sheetal Ekta | 32mm dia cold forged coupler, 32/25 mm dia cold forged coupler reducer
105 | Umika Enterprises | DGS Township Pvt Ltd | 2024-03-07 | 31 | 76855 | Sheetal Ekta | 25mm & 22mm dia Coupler, 25/20mm dia Cold forged Reducer Coupler
106 | Umika Enterprises | DGS Township Pvt Ltd | 2024-03-07 | 32 | 53451 | Sheetal Ekta | 32mm, 25mm & 20mm dia cold forged threading both side
107 | A-1 Fabrication | DGS Township Pvt Ltd | 2024-03-12 |  | 3227412 | Sheetal Ekta | Glazing, Opnable, Louvers, ACP Chajja Column, ACP Board, Sliding, Sliding Openable, Bathroom Louvers, Scaffolding
108 | A-1 Fabrication | DGS Township Pvt Ltd | 2024-03-12 |  | 1955856 | Sheetal Ekta | Platform, Top Chajja, Borad, Shutter, MS Channel, MS Plate, Labour Charges, L Frame 2x2 Angle, MS Tappa 10" Deep, SS Railing, M.S.Sheet, Tempo Bhada, Platform Repairing, Platform & Bucckel Roof Wire with Labour, Tank Sidi
109 | Avenue Imperial Construction LLP | DGS Township Pvt Ltd | 2024-03-27 | DGS/AE/06/2023-24 | 35400000 | Sheetal Ekta | RCC Work of Building
110 | Evolve Construction | DGS Township Pvt Ltd | 2023-10-16 | DGS/01/WO/Sheetal Ekta/2023 | 15000000 | Sheetal Ekta | Aluminium Form Work
111 | Evolve Construction | DGS Township Pvt Ltd | 2023-10-24 | 30/2023-24 | 975000 | Sheetal Ekta | Construction of Residential Complex
112 | Evolve Construction | DGS Township Pvt Ltd | 2023-12-22 | 41/2023-24 | 781541 | Sheetal Ekta | Construction of Residential Complex
113 | Evolve Construction | DGS Township Pvt Ltd | 2024-03-22 | 57/2023-24 | 11100000 | Sheetal Ekta | Construction of Residential Complex
114 | Mahakal Enterprises | DGS Township Pvt Ltd | 2024-03-28 | PERFORMA/01/23-24 | 11682590 | Sheetal Ekta | 08mm, 10mm, 12mm, 16mm & 20mm TMT Bars
115 | Saurabh Steel Corporation | DGS Township Pvt Ltd | 2024-03-28 | PRO/001/2023-24 | 12301500 | Sheetal Ekta | 08mm, 12mm, 16mm & 20mm TMT Bars
116 | Shree Ganesh Electricals | DGS Township Pvt Ltd | 2024-02-26 | 7 | 205544 | Sheetal Ekta | Electrical Work
117 | SK Kawsar Ali Civil Contractor | DGS Township Pvt Ltd | 2024-03-20 | 2 | 564385 | Sheetal Ekta | Window Framing Work, Border Patti Fixing, Tappa Fixing, Raizer Cutting With Fixing, Grove Making For Tappa, Champering Work, Wall Tiles Fixing, Umbra Patti Fixing, Dhar Polish Work, Passage Flooring Tiles, 2nd Floor (6 Room) Flooring Tiles (1600*800), Tiles Skirting Work, Granite Fixing, Nali Traf Cutting, Pavor Flooring, Department Supply,
118 | Saurabh Enterprise | DGS Township Pvt Ltd | 2024-04-01 | 5 | 14444 | Sheetal Ekta | Sika Microcrete 4 & AP Apcocrete
119 | Umika Enterprises | DGS Township Pvt Ltd | 2024-04-02 | 2 | 54006 | Sheetal Ekta | 25 mm dia Coupler & 20 mm dia Coupler
120 | Umika Enterprises | DGS Township Pvt Ltd | 2024-04-03 | 4 | 129084 | Sheetal Ekta | Cold Forged Threading Both Side 20 mm dia, 25 mm dia, 32 mm dia & 20 mm dia oneside
121 | Umika Enterprises | DGS Township Pvt Ltd | 2024-04-03 | 3 | 84062 | Sheetal Ekta | 32 mm dia Cold Forged Coupler & 25 mm dia Cold Forged Coupler
122 | Saurabh Enterprise | DGS Township Pvt Ltd | 2024-04-08 | 15 | 21158 | Sheetal Ekta | Ap Cemcrete
123 | BMCC Enterprise | DGS Township Pvt Ltd | 2024-04-22 | 1278 | 61425 | Sheetal Ekta | Crush Sand, Metal Mix & Plaster Sand
124 | M R Pigeon Net | DGS Township Pvt Ltd | 2024-04-22 | 8 | 47381 | Sheetal Ekta | Agro Shade Net 75% BDL
125 | BMCC Enterprise | DGS Township Pvt Ltd | 2024-04-30 | 1295 | 45675 | Sheetal Ekta | C Sand, P Sand & Metal Mix
126 | Umika Enterprises | DGS Township Pvt Ltd | 2024-05-05 | 12 | 84039 | Sheetal Ekta | 20 mm dia Cold Forged Coupler, 25 mm dia Cold Forged Coupler, 32/25 mm dia reducer & 25/20 mm dia reducer
127 | Umika Enterprises | DGS Township Pvt Ltd | 2024-05-06 | 14 | 32096 | Sheetal Ekta | 25 mm dia Cold Forged Coupler
128 | Vintage Traders | DGS Township Pvt Ltd | 2024-05-06 | 047 | 148425 | Sheetal Ekta | Flyash Blocks & Joint Morter
129 | Umika Enterprises | DGS Township Pvt Ltd | 2024-05-10 | 16 | 48144 | Sheetal Ekta | 25 mm dia Cold Forged Coupler
130 | Anupam Hardware | DGS Township Pvt Ltd | 2024-05-13 | 01746 | 9947 | Sheetal Ekta | LED Flat Light & PVC Green Breded Pipe
131 | S. V. & Co. | DGS Township Pvt Ltd | 2024-05-14 | 83/24-25 | 3474 | Sheetal Ekta | Flexo Board
132 | B. Mittal & Co. | DGS Township Pvt Ltd | 2024-05-20 | BM24250082 | 2055284 | Sheetal Ekta | TMT Rebar
133 | BMCC Enterprise | DGS Township Pvt Ltd | 2024-05-24 | 1335 | 23310 | Sheetal Ekta | C Sand, P Sand & Metal Mix
134 | Anupam Hardware | DGS Township Pvt Ltd | 2024-05-25 | 02311 | 11862 | Sheetal Ekta | Pipe Easyfit SCH- 80 & others
135 | S K Traders | DGS Township Pvt Ltd | 2024-05-28 | SK/114/24-25 | 216742 | Sheetal Ekta | Aluminium Arm Cable & others
136 | B. Mittal & Co. | DGS Township Pvt Ltd | 2024-05-28 | BM24250104 | 1993876 | Sheetal Ekta | TMT Rebar
137 | Anupam Hardware | DGS Township Pvt Ltd | 2024-05-22 | 02158 | 20432 | Sheetal Ekta | Earthing Strip & others
138 | Salim Timber Corporation | DGS Township Pvt Ltd | 2024-05-16 | 82/2024-2025 | 8095 | Sheetal Ekta | Timbers Frame
139 | S K Traders | DGS Township Pvt Ltd | 2024-05-30 | SK/121/24-25 | 135828 | Sheetal Ekta | TUFF AAC Block
140 | S K Traders | DGS Township Pvt Ltd | 2024-05-27 | SK/115/24-25 | 41008 | Sheetal Ekta | Aluminium Lugs & others
141 | S K Traders | DGS Township Pvt Ltd | 2024-05-31 | SK/123/24-25 | 17464 | Sheetal Ekta | Mortar Tuff Easyfix
142 | Ramkishan Prajapati | DGS Township Pvt Ltd | 2024-06-01 | 755 | 27350 | Sheetal Ekta | 40 mm round & others
143 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-747 | 53808 | Sheetal Ekta | M60- Supercrete
144 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-748 | 53808 | Sheetal Ekta | M60- Supercrete
145 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-749 | 53808 | Sheetal Ekta | M60- Supercrete
146 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-750 | 53808 | Sheetal Ekta | M60- Supercrete
147 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-762 | 53808 | Sheetal Ekta | M60- Supercrete
148 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP1-783 | 53808 | Sheetal Ekta | M60- Supercrete
149 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-789 | 53808 | Sheetal Ekta | M60- Supercrete
150 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP1-786 | 53808 | Sheetal Ekta | M60- Supercrete
151 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-765 | 53808 | Sheetal Ekta | M60- Supercrete
152 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-764 | 53808 | Sheetal Ekta | M60- Supercrete
153 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-763 | 53808 | Sheetal Ekta | M60- Supercrete
154 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-746 | 53808 | Sheetal Ekta | M60- Supercrete
155 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-767 | 53808 | Sheetal Ekta | M60- Supercrete
156 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-768 | 53808 | Sheetal Ekta | M60- Supercrete
157 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-790 | 53808 | Sheetal Ekta | M60- Supercrete
158 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-794 | 53808 | Sheetal Ekta | M60- Supercrete
159 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-793 | 53808 | Sheetal Ekta | M60- Supercrete
160 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-769 | 53808 | Sheetal Ekta | M60- Supercrete
161 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-795 | 53808 | Sheetal Ekta | M60- Supercrete
162 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-770 | 53808 | Sheetal Ekta | M60- Supercrete
163 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-796 | 49324 | Sheetal Ekta | M60- Supercrete
164 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-797 | 53808 | Sheetal Ekta | M60- Supercrete
165 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-799 | 53808 | Sheetal Ekta | M60- Supercrete
166 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-771 | 53808 | Sheetal Ekta | M60- Supercrete
167 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-798 | 53808 | Sheetal Ekta | M60- Supercrete
168 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-772 | 53808 | Sheetal Ekta | M60- Supercrete
169 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-773 | 53808 | Sheetal Ekta | M60- Supercrete
170 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-800 | 53808 | Sheetal Ekta | M60- Supercrete
171 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-801 | 53808 | Sheetal Ekta | M60- Supercrete
172 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-802 | 53808 | Sheetal Ekta | M60- Supercrete
173 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-803 | 53808 | Sheetal Ekta | M60- Supercrete
174 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-806 | 53808 | Sheetal Ekta | M60- Supercrete
175 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-780 | 53808 | Sheetal Ekta | M60- Supercrete
176 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-807 | 53808 | Sheetal Ekta | M60- Supercrete
177 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-810 | 58292 | Sheetal Ekta | M60- Supercrete
178 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP1-787 | 53808 | Sheetal Ekta | M60- Supercrete
179 | Umika Enterprises | DGS Township Pvt Ltd | 2024-06-02 | 22 | 59354 | Sheetal Ekta | Cold Forged Coupler 20 mm dia, 25 mm dia & 32 mm dia
180 | Umika Enterprises | DGS Township Pvt Ltd | 2024-06-03 | 24 | 35140 | Sheetal Ekta | Cold Forged Coupler 25 mm dia & 32/25 mm dia
181 | Umika Enterprises | DGS Township Pvt Ltd | 2024-06-04 | 26 | 70179 | Sheetal Ekta | Cold Forged Coupler 20 mm dia, 25 mm dia & 25/20 mm dia
182 | Mahadev Traders | DGS Township Pvt Ltd | 2024-06-06 | 68 | 85054 | Sheetal Ekta | M. S. Binding Wire
183 | S. V. & Co. | DGS Township Pvt Ltd | 2024-06-10 | 187/24-25 | 10547 | Sheetal Ekta | Flexo Board & other
184 | Jai Durga Transport | DGS Township Pvt Ltd | 2024-04-01 | 4451 | 11800 | Sheetal Ekta | Boring Water
185 | Vinod Yadav | DGS Township Pvt Ltd | 2024-04-02 | 1010 | 14500 | Sheetal Ekta | Steel Shifting
186 | Evolve Construction | DGS Township Pvt Ltd | 2024-04-08 | 2/2024-25 | 11800000 | Sheetal Ekta | RA Bill 03
187 | Brahmadev | DGS Township Pvt Ltd | 2024-04-07 | 003 | 6720 | Sheetal Ekta | Meter room cement sheet
188 | Shravan Sahani | DGS Township Pvt Ltd | 2024-04-07 |  | 14400 | Sheetal Ekta | 12 Frame and others
189 | Rukmani G.Chouhan | DGS Township Pvt Ltd | 2024-04-16 |  | 4200 | Sheetal Ekta | Labour
190 | SRSBM Lab Testing Pvt.Ltd. | DGS Township Pvt Ltd | 2024-04-16 | MRT-27006 | 3304 | Sheetal Ekta | Concrete Cube ( Compressive Strength)
191 | Jai Durga Transport | DGS Township Pvt Ltd | 2024-05-01 | 4501 | 18000 | Sheetal Ekta | Boring Water, Drinking Water
192 | Poonam D. Jha | DGS Township Pvt Ltd | 2024-04-30 | 423 | 18000 | Sheetal Ekta | Rabbit
193 | Umika Enterprises | DGS Township Pvt Ltd | 2024-05-04 | 10 | 44259 | Sheetal Ekta | 25 mm dia cold forged one side , 25 mm dia forged both side, 20 mm dia forged
194 | Vinod Yadav | DGS Township Pvt Ltd | 2024-05-05 | 1012 | 14500 | Sheetal Ekta | Steel Shifting, Block
195 | Rajesh Singh Water pump hiring | DGS Township Pvt Ltd | 2024-05-14 | 598 | 5000 | Sheetal Ekta | HP Pump
196 | Rajesh Singh Water pump hiring | DGS Township Pvt Ltd | 2024-05-14 | 465 | 10000 | Sheetal Ekta | HP Pump
197 | Abhay Facility Service | DGS Township Pvt Ltd | 2024-06-01 | AFS/867/2024 | 92040 | Sheetal Ekta | Secuirty head guars, Liftman
198 | Jai Durga Transport | DGS Township Pvt Ltd | 2024-06-01 | 4551 | 42200 | Sheetal Ekta | Boring Water, Drinking Water
199 | Maharaja Enterprises | DGS Township Pvt Ltd | 2024-05-31 | 8330 | 7830 | Sheetal Ekta | Bottles
200 | Vinod Yadav | DGS Township Pvt Ltd | 2024-06-03 | 1013 | 29000 | Sheetal Ekta | Steel Shifting, Block
201 | Umika Enterprises | DGS Township Pvt Ltd | 2024-06-04 | 27 | 123715 | Sheetal Ekta | 25 mm dia cold forged one side , 25 mm dia forged both side, 20 mm dia forged, 32 mm dia forged
202 | Rajesh Singh Water pump hiring | DGS Township Pvt Ltd | 2024-06-16 | 630 | 5000 | Sheetal Ekta | HP Pump
203 | Janki Devi Prajapati | DGS Township Pvt Ltd | 2024-06-16 | 473 | 10100 | Sheetal Ekta | 40 mm round block, 25 mm square block, Transport charges
204 | Om Infrastrcuture | DGS Township Pvt Ltd | 2024-06-19 | OM/008/2024-25 | 15000000 | Sheetal Ekta | Labour Work
205 | Avenue Imperial Construction LLP | DGS Township Pvt Ltd | 2024-05-05 | DGS/AE/04/2024-25 | 15000000 | Sheetal Ekta | RCC Work of Building
206 | Mahibuddin | DGS Township Pvt Ltd | 2024-06-05 |  | 36235 | Sheetal Ekta | Labour Charges
207 | Saikat Mondal | DGS Township Pvt Ltd | 2024-06-05 | 790 | 7200 | Sheetal Ekta | glass sticker with pasting
208 | Saikat Mondal | DGS Township Pvt Ltd | 2024-06-05 | 785 | 81200 | Sheetal Ekta | Acrylic letter, Logo 2 pic
209 | Anupam Hardware | DGS Township Pvt Ltd | 2024-04-02 | 00059 | 6348 | Sheetal Ekta | Wires House Flex 1.5 SQ MM & others
210 | Shree Krushna Electrical & Hardware | DGS Township Pvt Ltd | 2024-04-10 | 370 | 13800 | Sheetal Ekta | Water Tank 2000 L & Tampo
211 | S K Traders | DGS Township Pvt Ltd | 2024-04-14 | SK/033/24-25 | 87552 | Sheetal Ekta | PPC Birla Shakti
212 | Maatangi Enterprises | DGS Township Pvt Ltd | 2024-04-15 | 385 | 10561 | Sheetal Ekta | Black Granite
213 | S K Traders | DGS Township Pvt Ltd | 2024-04-17 | SK/035/24-25 | 150866 | Sheetal Ekta | AAC Fly Ash Block & Magic Bond Joint Mortar
214 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-04-19 | ASC066/24-25 | 1945990 | Sheetal Ekta | TMT BARS 8 mm, 12 mm, 16 mm, 20 mm & 25 mm
215 | S K Traders | DGS Township Pvt Ltd | 2024-04-19 | SK/041/24-25 | 16184 | Sheetal Ekta | Reducer Socket MS ERW 80*40 mm & others
216 | S K Traders | DGS Township Pvt Ltd | 2024-04-22 | SK/047/24-25 | 36657 | Sheetal Ekta | Butterfly Valve & others
217 | Shree Krushna Electrical & Hardware | DGS Township Pvt Ltd | 2024-04-22 | 378 | 3580 | Sheetal Ekta | P Draw, 110 mm Albow & others
218 | Anupam Hardware | DGS Township Pvt Ltd | 2024-04-25 | 01036 | 19612 | Sheetal Ekta | Vertical Tank Black 2000 ltr & Others
219 | Saurabh Enterprise | DGS Township Pvt Ltd | 2024-04-27 | 51 | 24485 | Sheetal Ekta | AP Antihack
220 | Anupam Hardware | DGS Township Pvt Ltd | 2024-04-28 | 01136 | 24619 | Sheetal Ekta | Pump Mono Mik-22-18 2HP & Other
221 | Schindler India Pvt Ltd | DGS Township Pvt Ltd | 2024-04-29 | CI2700413089 | 147500 | Sheetal Ekta | Installation, Repair & Maintenance of Elevators & Escalators
222 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-04-09 | AC/24-25/0011 | 1995734 | Sheetal Ekta | M-60 Mivan & others
223 | Shree Krushna Electrical & Hardware | DGS Township Pvt Ltd | 2024-06-25 | 006 | 20300 | Sheetal Ekta | Tube Light, Flood light, Ploycab core, Metal Socket single phase
224 | Neeraj Steel Sales | DGS Township Pvt Ltd | 2024-06-08 | 203/24-25 | 2066752 | Sheetal Ekta | TMT BARS- 8mm, 10mm, 12mm, 16mm, 20mm, 25mm, 32mm
225 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-05-21 | 24-25/0011 | 5808 | Sheetal Ekta | Pumping Charges
226 | M R Pigeon Net | DGS Township Pvt Ltd | 2024-06-01 |  | 145 | Sheetal Ekta | TDS on Labour
227 | City Elevators Private Limited | DGS Township Pvt Ltd | 2024-06-05 |  | 86580 | Sheetal Ekta
228 | Anupam Hardware | DGS Township Pvt Ltd | 2024-06-21 |  | 46360 | Sheetal Ekta
229 | Anupam Hardware | DGS Township Pvt Ltd | 2024-05-23 |  | 46460 | Sheetal Ekta
230 | B S Fire Protection | DGS Township Pvt Ltd | 2024-05-10 |  | 590000 | Sheetal Ekta | Labour Charges
231 | Seema Dipak Alaskar | DGS Township Pvt Ltd | 2024-04-30 |  | 57842 | Sheetal Ekta | 08mm, 10mm, 12mm, 16mm & 20mm TMT Bars
232 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-04-30 |  | 492061 | Sheetal Ekta
233 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-04-30 |  | 467460 | Sheetal Ekta
234 | Saurabh Steel Corporation | DGS Township Pvt Ltd | 2024-04-30 |  | 615075 | Sheetal Ekta
235 | Shree Krushna Electrical & Hardware | DGS Township Pvt Ltd | 2024-04-09 |  | 14650 | Sheetal Ekta
236 | Mahakal Enterprises | DGS Township Pvt Ltd | 2024-04-30 |  | 584130 | Sheetal Ekta
237 | Bajarang Drilling | DGS Township Pvt Ltd | 2024-06-07 | 06 | 18337 | Sheetal Ekta | Bill for Core cutting, Drilling hole in RCC along with electric portable machine
238 | Poonam D. Jha | DGS Township Pvt Ltd | 2024-06-30 | 515 | 13500 | Sheetal Ekta | Rabbit
239 | Shri Krihsna Electrical & Hardware | DGS Township Pvt Ltd | 2024-06-30 | 014 | 695 | Sheetal Ekta | L Hall Pass & Anchor Faszar
240 | Aayush Enterprises | DGS Township Pvt Ltd | 2024-06-28 | 188 | 1392 | Sheetal Ekta | FAIBER MESH (HSN7019)
241 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-06-10 | AC/24-25/0514 | 1951631 | Sheetal Ekta | M-60 MIVAN OPC Without Pump, M-60 MIVAN OPC With Pump, Pumping Charges
242 | BMCC Enterprise | DGS Township Pvt Ltd | 2024-06-28 | 1409 | 33075 | Sheetal Ekta | Plaster Sand, Metal Mix, Crush Sand
243 | R.R Enterprises | DGS Township Pvt Ltd | 2024-06-16 | 12 | 1997834 | Sheetal Ekta | RMC M-60 FREE FLOW, SLURRY
244 | Salim Timber Corporation | DGS Township Pvt Ltd | 2024-06-22 | 136/2024-2025 | 52510 | Sheetal Ekta | Timbers Frame
245 | R.R Enterprises | DGS Township Pvt Ltd | 2024-06-30 | 16 | 2027235 | Sheetal Ekta | RMC M-60 FREE FLOW, SLURRY
246 | Ramkishan Prajapati | DGS Township Pvt Ltd | 2024-06-15 | 770 | 40000 | Sheetal Ekta | RCC Chember cover with frame, 600x900, Transport
247 | Shabbir Pipe Fitting | DGS Township Pvt Ltd | 2024-06-15 | SPF/064/24-25 | 43176 | Sheetal Ekta | Steelman 6" G.I C Class
248 | Vintage Traders | DGS Township Pvt Ltd | 2024-06-18 | VT/24-25/36 | 143847 | Sheetal Ekta | Fly Ash Block, Joining Mortor
249
| Total |  |  |  | 268655404

## Construction Area sale building
Sr. | Floor | Total Construction Area in Sq. M. | Completed Area in Sq. Ft. | Rate per Sq. Ft. | Full Value after completion | % of work completed | Actual Expenditure till date in `
1 | Exacavation Cost |  |  |  | 24608686 | 100% | 24608686
2 | Basement Floor | 438.7364 | 438.7364 | 30000 | 13162092 | 98% | 12898850.16
3 | Ground Floor | 486.0664 | 486.0664 | 30000 | 14581992 | 98% | 14290352.16
4 | 1st Floor | 514.0664 | 514.0664 | 30000 | 15421992 | 98% | 15113552.16
5 | 2nd Floor | 514.0664 | 514.0664 | 30000 | 15421992 | 98% | 15113552.16
6 | 3rd Floor | 514.0664 | 514.0664 | 30000 | 15421992 | 75% | 11566494
7 | 4th Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 63% | 8676543.96
8 | 5th Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 63% | 8676543.96
9 | 6th Floor | 465.64 | 465.64 | 30000 | 13969200 | 63% | 8800596
10 | 7th Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 60% | 8263375.2
11 | 8th Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 60% | 8263375.2
12 | 9th Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 60% | 8263375.2
13 | 10th Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 60% | 8263375.2
14 | 11th Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 60% | 8263375.2
15 | 12th Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 55% | 7574760.6
16 | 13th Floor | 465.64 | 465.64 | 30000 | 13969200 | 55% | 7683060
17 | 14th Floor | 459.0764 |  | 30000 | 13772292
18 | 15th Floor | 459.0764 |  | 30000 | 13772292
19 | 16th Floor | 459.0764 |  | 30000 | 13772292
20 | 17th Floor | 459.0764 |  | 30000 | 13772292
21 | 18th Floor | 459.0764 |  | 30000 | 13772292
22 | 19th Floor | 459.0764 |  | 30000 | 13772292
23 | 20th Floor | 468.19 |  | 30000 | 14045700
24 | 21st Floor | 459.0764 |  | 30000 | 13772292
25 | 22nd Floor | 459.0764 |  | 30000 | 13772292
26 | 23rd Floor | 459.0764 |  | 30000 | 13772292
27 | 24th Floor | 460.45 |  | 30000 | 13813500
28 | 25th Floor | 460.45 |  | 30000 | 13813500
29 | 26th Floor | 460.45 |  | 30000 | 13813500
30 | 27th Floor | 467.98 |  | 30000 | 14039400
31 | 28th Floor | 462.33 |  | 30000 | 13869900
32 | 29th Floor | 462.33 |  | 30000 | 13869900
33 | 30th Floor | 462.33 |  | 30000 | 13869900
34 | 31st Floor | 462.33 |  | 30000 | 13869900
35 | 32nd Floor | 462.33 |  | 30000 | 13869900
36 | 33rd Floor | 459.65 |  | 30000 | 13789500
37 | Terrace / OHT | 114.39 |  | 30000 | 3431700
38 | Sub Total | 16405.7908 | 7070.8932 |  | 516782410 | 34.12% | 176319867
39 | Parking | 111 |  | 500000 | 55500000
TOTAL |  |  | 7070.8932 |  | 572282410 | 30.81% | 176319867
[6 empty] | 27.51% | 78710394
[6 empty] | 33.19% | 13625143
[6 empty] | 46.94% | 268655404 | 26.8655
[7 empty] | 46.94% | 20.18
-6.6855

## Sheet1
Sr. No. | Vendor Name | Customer Name | Invoice Date | Invoice Number | Invoice Amount | Project Name | Description of Material
118 | Saurabh Enterprise | DGS Township Pvt Ltd | 2024-04-01 | 5 | 14444 | Sheetal Ekta | Sika Microcrete 4 & AP Apcocrete
119 | Umika Enterprises | DGS Township Pvt Ltd | 2024-04-02 | 2 | 54006 | Sheetal Ekta | 25 mm dia Coupler & 20 mm dia Coupler
120 | Umika Enterprises | DGS Township Pvt Ltd | 2024-04-03 | 4 | 129084 | Sheetal Ekta | Cold Forged Threading Both Side 20 mm dia, 25 mm dia, 32 mm dia & 20 mm dia oneside
121 | Umika Enterprises | DGS Township Pvt Ltd | 2024-04-03 | 3 | 84062 | Sheetal Ekta | 32 mm dia Cold Forged Coupler & 25 mm dia Cold Forged Coupler
122 | Saurabh Enterprise | DGS Township Pvt Ltd | 2024-04-08 | 15 | 21158 | Sheetal Ekta | Ap Cemcrete
123 | BMCC Enterprise | DGS Township Pvt Ltd | 2024-04-22 | 1278 | 61425 | Sheetal Ekta | Crush Sand, Metal Mix & Plaster Sand
124 | M R Pigeon Net | DGS Township Pvt Ltd | 2024-04-22 | 8 | 47381 | Sheetal Ekta | Agro Shade Net 75% BDL
125 | BMCC Enterprise | DGS Township Pvt Ltd | 2024-04-30 | 1295 | 45675 | Sheetal Ekta | C Sand, P Sand & Metal Mix
126 | Umika Enterprises | DGS Township Pvt Ltd | 2024-05-05 | 12 | 84039 | Sheetal Ekta | 20 mm dia Cold Forged Coupler, 25 mm dia Cold Forged Coupler, 32/25 mm dia reducer & 25/20 mm dia reducer
127 | Umika Enterprises | DGS Township Pvt Ltd | 2024-05-06 | 14 | 32096 | Sheetal Ekta | 25 mm dia Cold Forged Coupler
128 | Vintage Traders | DGS Township Pvt Ltd | 2024-05-06 | 047 | 148425 | Sheetal Ekta | Flyash Blocks & Joint Morter
129 | Umika Enterprises | DGS Township Pvt Ltd | 2024-05-10 | 16 | 48144 | Sheetal Ekta | 25 mm dia Cold Forged Coupler
130 | Anupam Hardware | DGS Township Pvt Ltd | 2024-05-13 | 01746 | 9947 | Sheetal Ekta | LED Flat Light & PVC Green Breded Pipe
131 | S. V. & Co. | DGS Township Pvt Ltd | 2024-05-14 | 83/24-25 | 3474 | Sheetal Ekta | Flexo Board
132 | B. Mittal & Co. | DGS Township Pvt Ltd | 2024-05-20 | BM24250082 | 2055284 | Sheetal Ekta | TMT Rebar
133 | BMCC Enterprise | DGS Township Pvt Ltd | 2024-05-24 | 1335 | 23310 | Sheetal Ekta | C Sand, P Sand & Metal Mix
134 | Anupam Hardware | DGS Township Pvt Ltd | 2024-05-25 | 02311 | 11862 | Sheetal Ekta | Pipe Easyfit SCH- 80 & others
135 | S K Traders | DGS Township Pvt Ltd | 2024-05-28 | SK/114/24-25 | 216742 | Sheetal Ekta | Aluminium Arm Cable & others
136 | B. Mittal & Co. | DGS Township Pvt Ltd | 2024-05-28 | BM24250104 | 1993876 | Sheetal Ekta | TMT Rebar
137 | Anupam Hardware | DGS Township Pvt Ltd | 2024-05-22 | 02158 | 20432 | Sheetal Ekta | Earthing Strip & others
138 | Salim Timber Corporation | DGS Township Pvt Ltd | 2024-05-16 | 82/2024-2025 | 8095 | Sheetal Ekta | Timbers Frame
139 | S K Traders | DGS Township Pvt Ltd | 2024-05-30 | SK/121/24-25 | 135828 | Sheetal Ekta | TUFF AAC Block
140 | S K Traders | DGS Township Pvt Ltd | 2024-05-27 | SK/115/24-25 | 41008 | Sheetal Ekta | Aluminium Lugs & others
141 | S K Traders | DGS Township Pvt Ltd | 2024-05-31 | SK/123/24-25 | 17464 | Sheetal Ekta | Mortar Tuff Easyfix
142 | Ramkishan Prajapati | DGS Township Pvt Ltd | 2024-06-01 | 755 | 27350 | Sheetal Ekta | 40 mm round & others
143 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-747 | 53808 | Sheetal Ekta | M60- Supercrete
144 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-748 | 53808 | Sheetal Ekta | M60- Supercrete
145 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-749 | 53808 | Sheetal Ekta | M60- Supercrete
146 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-750 | 53808 | Sheetal Ekta | M60- Supercrete
147 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-762 | 53808 | Sheetal Ekta | M60- Supercrete
148 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP1-783 | 53808 | Sheetal Ekta | M60- Supercrete
149 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-789 | 53808 | Sheetal Ekta | M60- Supercrete
150 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP1-786 | 53808 | Sheetal Ekta | M60- Supercrete
151 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-765 | 53808 | Sheetal Ekta | M60- Supercrete
152 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-764 | 53808 | Sheetal Ekta | M60- Supercrete
153 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-763 | 53808 | Sheetal Ekta | M60- Supercrete
154 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-746 | 53808 | Sheetal Ekta | M60- Supercrete
155 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-767 | 53808 | Sheetal Ekta | M60- Supercrete
156 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-768 | 53808 | Sheetal Ekta | M60- Supercrete
157 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-790 | 53808 | Sheetal Ekta | M60- Supercrete
158 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-794 | 53808 | Sheetal Ekta | M60- Supercrete
159 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-793 | 53808 | Sheetal Ekta | M60- Supercrete
160 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-769 | 53808 | Sheetal Ekta | M60- Supercrete
161 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-795 | 53808 | Sheetal Ekta | M60- Supercrete
162 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-770 | 53808 | Sheetal Ekta | M60- Supercrete
163 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-796 | 49324 | Sheetal Ekta | M60- Supercrete
164 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-797 | 53808 | Sheetal Ekta | M60- Supercrete
165 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-799 | 53808 | Sheetal Ekta | M60- Supercrete
166 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-771 | 53808 | Sheetal Ekta | M60- Supercrete
167 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-798 | 53808 | Sheetal Ekta | M60- Supercrete
168 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-772 | 53808 | Sheetal Ekta | M60- Supercrete
169 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-773 | 53808 | Sheetal Ekta | M60- Supercrete
170 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-800 | 53808 | Sheetal Ekta | M60- Supercrete
171 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-801 | 53808 | Sheetal Ekta | M60- Supercrete
172 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-802 | 53808 | Sheetal Ekta | M60- Supercrete
173 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-803 | 53808 | Sheetal Ekta | M60- Supercrete
174 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-806 | 53808 | Sheetal Ekta | M60- Supercrete
175 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-780 | 53808 | Sheetal Ekta | M60- Supercrete
176 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-807 | 53808 | Sheetal Ekta | M60- Supercrete
177 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-810 | 58292 | Sheetal Ekta | M60- Supercrete
178 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP1-787 | 53808 | Sheetal Ekta | M60- Supercrete
179 | Umika Enterprises | DGS Township Pvt Ltd | 2024-06-02 | 22 | 59354 | Sheetal Ekta | Cold Forged Coupler 20 mm dia, 25 mm dia & 32 mm dia
180 | Umika Enterprises | DGS Township Pvt Ltd | 2024-06-03 | 24 | 35140 | Sheetal Ekta | Cold Forged Coupler 25 mm dia & 32/25 mm dia
181 | Umika Enterprises | DGS Township Pvt Ltd | 2024-06-04 | 26 | 70179 | Sheetal Ekta | Cold Forged Coupler 20 mm dia, 25 mm dia & 25/20 mm dia
182 | Mahadev Traders | DGS Township Pvt Ltd | 2024-06-06 | 68 | 85054 | Sheetal Ekta | M. S. Binding Wire
183 | S. V. & Co. | DGS Township Pvt Ltd | 2024-06-10 | 187/24-25 | 10547 | Sheetal Ekta | Flexo Board & other
185 | Jai Durga Transport | DGS Township Pvt Ltd | 2024-04-01 | 4451 | 11800 | Sheetal Ekta | Boring Water
186 | Vinod Yadav | DGS Township Pvt Ltd | 2024-04-02 | 1010 | 14500 | Sheetal Ekta | Steel Shifting
187 | Evolve Construction | DGS Township Pvt Ltd | 2024-04-08 | 2/2024-25 | 11800000 | Sheetal Ekta | RA Bill 03
188 | Brahmadev | DGS Township Pvt Ltd | 2024-04-07 | 003 | 6720 | Sheetal Ekta | Meter room cement sheet
189 | Shravan Sahani | DGS Township Pvt Ltd | 2024-04-07 |  | 14400 | Sheetal Ekta | 12 Frame and others
190 | Rukmani G.Chouhan | DGS Township Pvt Ltd | 2024-04-16 |  | 4200 | Sheetal Ekta | Labour
191 | SRSBM Lab Testing Pvt.Ltd. | DGS Township Pvt Ltd | 2024-04-16 | MRT-27006 | 3304 | Sheetal Ekta | Concrete Cube ( Compressive Strength)
193 | Jai Durga Transport | DGS Township Pvt Ltd | 2024-05-01 | 4501 | 18000 | Sheetal Ekta | Boring Water, Drinking Water
194 | Poonam D. Jha | DGS Township Pvt Ltd | 2024-04-30 | 423 | 18000 | Sheetal Ekta | Rabbit
195 | Umika Enterprises | DGS Township Pvt Ltd | 2024-05-04 | 10 | 44259 | Sheetal Ekta | 25 mm dia cold forged one side , 25 mm dia forged both side, 20 mm dia forged
196 | Vinod Yadav | DGS Township Pvt Ltd | 2024-05-05 | 1012 | 14500 | Sheetal Ekta | Steel Shifting, Block
197 | Rajesh Singh Water pump hiring | DGS Township Pvt Ltd | 2024-05-14 | 598 | 5000 | Sheetal Ekta | HP Pump
198 | Rajesh Singh Water pump hiring | DGS Township Pvt Ltd | 2024-05-14 | 465 | 10000 | Sheetal Ekta | HP Pump
199 | Abhay Facility Service | DGS Township Pvt Ltd | 2024-06-01 | AFS/867/2024 | 92040 | Sheetal Ekta | Secuirty head guars, Liftman
202 | Jai Durga Transport | DGS Township Pvt Ltd | 2024-06-01 | 4551 | 42200 | Sheetal Ekta | Boring Water, Drinking Water
203 | Maharaja Enterprises | DGS Township Pvt Ltd | 2024-05-31 | 8330 | 7830 | Sheetal Ekta | Bottles
204 | Vinod Yadav | DGS Township Pvt Ltd | 2024-06-03 | 1013 | 29000 | Sheetal Ekta | Steel Shifting, Block
205 | Umika Enterprises | DGS Township Pvt Ltd | 2024-06-04 | 27 | 123715 | Sheetal Ekta | 25 mm dia cold forged one side , 25 mm dia forged both side, 20 mm dia forged, 32 mm dia forged
206 | Rajesh Singh Water pump hiring | DGS Township Pvt Ltd | 2024-06-16 | 630 | 5000 | Sheetal Ekta | HP Pump
207 | Janki Devi Prajapati | DGS Township Pvt Ltd | 2024-06-16 | 473 | 10100 | Sheetal Ekta | 40 mm round block, 25 mm square block, Transport charges
208 | Om Infrastrcuture | DGS Township Pvt Ltd | 2024-06-19 | OM/008/2024-25 | 15000000 | Sheetal Ekta | Labour Work
209 | Avenue Imperial Construction LLP | DGS Township Pvt Ltd | 2024-05-05 | DGS/AE/04/2024-25 | 15000000 | Sheetal Ekta | RCC Work of Building
210 | Mahibuddin | DGS Township Pvt Ltd | 2024-06-05 |  | 36235 | Sheetal Ekta | Labour Charges
211 | Saikat Mondal | DGS Township Pvt Ltd | 2024-06-05 | 790 | 7200 | Sheetal Ekta | glass sticker with pasting
212 | Saikat Mondal | DGS Township Pvt Ltd | 2024-06-05 | 785 | 81200 | Sheetal Ekta | Acrylic letter, Logo 2 pic
213 | Anupam Hardware | DGS Township Pvt Ltd | 2024-04-02 | 00059 | 6348 | Sheetal Ekta | Wires House Flex 1.5 SQ MM & others
214 | Shree Krushna Electrical & Hardware | DGS Township Pvt Ltd | 2024-04-10 | 370 | 13800 | Sheetal Ekta | Water Tank 2000 L & Tampo
215 | S K Traders | DGS Township Pvt Ltd | 2024-04-14 | SK/033/24-25 | 87552 | Sheetal Ekta | PPC Birla Shakti
216 | Maatangi Enterprises | DGS Township Pvt Ltd | 2024-04-15 | 385 | 10561 | Sheetal Ekta | Black Granite
217 | S K Traders | DGS Township Pvt Ltd | 2024-04-17 | SK/035/24-25 | 150866 | Sheetal Ekta | AAC Fly Ash Block & Magic Bond Joint Mortar
218 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-04-19 | ASC066/24-25 | 1945990 | Sheetal Ekta | TMT BARS 8 mm, 12 mm, 16 mm, 20 mm & 25 mm
219 | S K Traders | DGS Township Pvt Ltd | 2024-04-19 | SK/041/24-25 | 16184 | Sheetal Ekta | Reducer Socket MS ERW 80*40 mm & others
220 | S K Traders | DGS Township Pvt Ltd | 2024-04-22 | SK/047/24-25 | 36657 | Sheetal Ekta | Butterfly Valve & others
221 | Shree Krushna Electrical & Hardware | DGS Township Pvt Ltd | 2024-04-22 | 378 | 3580 | Sheetal Ekta | P Draw, 110 mm Albow & others
222 | Anupam Hardware | DGS Township Pvt Ltd | 2024-04-25 | 01036 | 19612 | Sheetal Ekta | Vertical Tank Black 2000 ltr & Others
223 | Saurabh Enterprise | DGS Township Pvt Ltd | 2024-04-27 | 51 | 24485 | Sheetal Ekta | AP Antihack
224 | Anupam Hardware | DGS Township Pvt Ltd | 2024-04-28 | 01136 | 24619 | Sheetal Ekta | Pump Mono Mik-22-18 2HP & Other
225 | Schindler India Pvt Ltd | DGS Township Pvt Ltd | 2024-04-29 | CI2700413089 | 147500 | Sheetal Ekta | Installation, Repair & Maintenance of Elevators & Escalators
226 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-04-09 | AC/24-25/0011 | 1995734 | Sheetal Ekta | M-60 Mivan & others
227 | Shree Krushna Electrical & Hardware | DGS Township Pvt Ltd | 2024-06-25 | 006 | 20300 | Sheetal Ekta | Tube Light, Flood light, Ploycab core, Metal Socket single phase
228 | Neeraj Steel Sales | DGS Township Pvt Ltd | 2024-06-08 | 203/24-25 | 2066752 | Sheetal Ekta | TMT BARS- 8mm, 10mm, 12mm, 16mm, 20mm, 25mm, 32mm
229 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-05-21 | 24-25/0011 | 5808 | Sheetal Ekta | Pumping Charges
233 | M R Pigeon Net | DGS Township Pvt Ltd | 2024-06-01 |  | 145 | Sheetal Ekta | TDS on Labour
239 | City Elevators Private Limited | DGS Township Pvt Ltd | 2024-06-05 |  | 86580 | Sheetal Ekta
241 | Anupam Hardware | DGS Township Pvt Ltd | 2024-06-21 |  | 46360 | Sheetal Ekta
244 | Anupam Hardware | DGS Township Pvt Ltd | 2024-05-23 |  | 46460 | Sheetal Ekta
247 | B S Fire Protection | DGS Township Pvt Ltd | 2024-05-10 |  | 590000 | Sheetal Ekta | Labour Charges
251 | Seema Dipak Alaskar | DGS Township Pvt Ltd | 2024-04-30 |  | 57842 | Sheetal Ekta | 08mm, 10mm, 12mm, 16mm & 20mm TMT Bars
252 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-04-30 |  | 492061 | Sheetal Ekta
253 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-04-30 |  | 467460 | Sheetal Ekta
254 | Saurabh Steel Corporation | DGS Township Pvt Ltd | 2024-04-30 |  | 615075 | Sheetal Ekta
258 | Shree Krushna Electrical & Hardware | DGS Township Pvt Ltd | 2024-04-09 |  | 14650 | Sheetal Ekta
259 | Mahakal Enterprises | DGS Township Pvt Ltd | 2024-04-30 |  | 584130 | Sheetal Ekta
267 | Bajarang Drilling | DGS Township Pvt Ltd | 2024-06-07 | 06 | 18337 | Sheetal Ekta | Bill for Core cutting, Drilling hole in RCC along with electric portable machine
292 | Poonam D. Jha | DGS Township Pvt Ltd | 2024-06-30 | 515 | 13500 | Sheetal Ekta | Rabbit
303 | Shri Krihsna Electrical & Hardware | DGS Township Pvt Ltd | 2024-06-30 | 014 | 695 | Sheetal Ekta | L Hall Pass & Anchor Faszar
307 | Aayush Enterprises | DGS Township Pvt Ltd | 2024-06-28 | 188 | 1392 | Sheetal Ekta | FAIBER MESH (HSN7019)
308 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-06-10 | AC/24-25/0514 | 1951631 | Sheetal Ekta | M-60 MIVAN OPC Without Pump, M-60 MIVAN OPC With Pump, Pumping Charges
311 | BMCC Enterprise | DGS Township Pvt Ltd | 2024-06-28 | 1409 | 33075 | Sheetal Ekta | Plaster Sand, Metal Mix, Crush Sand
323 | R.R Enterprises | DGS Township Pvt Ltd | 2024-06-16 | 12 | 1997834 | Sheetal Ekta | RMC M-60 FREE FLOW, SLURRY
327 | Salim Timber Corporation | DGS Township Pvt Ltd | 2024-06-22 | 136/2024-2025 | 52510 | Sheetal Ekta | Timbers Frame
347 | R.R Enterprises | DGS Township Pvt Ltd | 2024-06-30 | 16 | 2027235 | Sheetal Ekta | RMC M-60 FREE FLOW, SLURRY
348 | Ramkishan Prajapati | DGS Township Pvt Ltd | 2024-06-15 | 770 | 40000 | Sheetal Ekta | RCC Chember cover with frame, 600x900, Transport
362 | Shabbir Pipe Fitting | DGS Township Pvt Ltd | 2024-06-15 | SPF/064/24-25 | 43176 | Sheetal Ekta | Steelman 6" G.I C Class
368 | Vintage Traders | DGS Township Pvt Ltd | 2024-06-18 | VT/24-25/36 | 143847 | Sheetal Ekta | Fly Ash Block, Joining Mortor
65831519