## Final Summary
Project expenses | Estimated Cost as per Cost Vetting | Incurred Cost as per Bill till 30.09.2024 | Incurred Cost as per CA till 30.09.2024 | Incurred Cost as per Bill till 30.06.2024 | Incurred Cost as per CA till 30.06.2024 | Difference between the Bills & CA | Difference between both the Bills | Difference between both CA | Remark
Land Cost | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 4.3e-05 | 0 | 0
Construction Cost of Sale Building | 55.81 | 33.6696 | 34.95 | 22.8046 | 23.56 | -1.2804 | 10.865 | 11.39
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 13.02 | 10.6006 | 10.6 | 10.6006 | 10.6 | 0.0006165 | 0 | 0
Architect Cost, RCC & other Professional fees | 0.56 | 0.34809 | 0.11 | 0.3342 | 0.33 | 0.23809 | 0.013891 | -0.22
On- site expenditure for development / Advance for Project / Administrative Cost / Fixed Assets | 3.07 | 1.7127 | 0.5 | 0.99875 | 0.25 | 1.2127 | 0.71399 | 0.25 | .
Marketing Expenses | 5.35 | 0.76217 | 0.76 | 0.44553 | 0.64 | 0.002168 | 0.31663 | 0.12
Interest Cost | 6.91 | 0.5355 | 0.54 | 0.091327 | 0.09 | -0.0044974 | 0.44418 | 0.45
Total Cost | 97.22 | 60.1288 | 59.96 | 47.7751 | 47.97 | 0.16877 | 12.3537 | 11.99
|  | 37.0912 | 0.16877 | 61.67%
Particulars | Revised Estimated Cost (in Cr.) | 30.09.2024 as per Bill Tally (inclusive of GST) | Cost incurred as %age total cost of that Component | Cost incurred as %age of cost incurred as on 30.09.2024
Land Cost | 12.5 | 12.5 | 100% | 12.86%
Construction Cost | 55.81 | 33.6696 | 60.33% | 34.63%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 13.02 | 10.6006 | 81.42% | 10.9%
Architect Cost, RCC & other Professional fees | 0.56 | 0.34809 | 62.16% | 0.358%
On- site expenditure for development / Advance for Project/ Administrative Cost/ Fixed Assets | 3.07 | 1.7127 | 55.79% | 1.762%
Marketing Expenses | 5.35 | 0.76217 | 14.25% | 0.784%
Interest Cost | 6.91 | 0.5355 | 7.75% | 0.5508%
Total | 97.22 | 60.1288 | 61.85% | 61.85%
Pariculars | 30.09.2024 as per Bill Tally (inclusive of GST) | 30.06.2024 as per Bill Tally (inclusive of GST) | Difference b/w bills of 30.09.2024 & 30.06.2024 | Difference of Cost incurred as %age of cost incurred as on 30.09.2024 & 30.06.2024
Land Cost | 12.5 | 12.5 | 0 | 0%
Construction Cost | 33.6696 | 22.8046 | 10.87 | 18.08%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 10.6006 | 10.6006 | 0 | 0%
Architect Cost, RCC & other Professional fees | 0.34809 | 0.3342 | 0.01 | 0.01663%
On- site expenditure for development / Advance for Project/ Administrative Cost/ Fixed Assets | 1.7127 | 0.99875 | 0.71 | 1.181%
Marketing Expenses | 0.76217 | 0.44553 | 0.32 | 0.5322%
Interest Cost | 0.5355 | 0.091327 | 0.44 | 0.7318%
Total | 60.1288 | 47.7751 | 12.35 | 100%

## Summary Sheet
Sr. No. | Particulars | Incurred Cost in ` till 30.09.2024 | Incurred Cost in ` Cr. Till 30.09.2024 | Incurred Cost in ` till 30.06.2024 | Incurred Cost in ` Cr. Till 30.06.2024 | Balance | Balance in Cr.
1 | Land Cost | 125000430 | 12.5 | 125000430 | 12.5 | 0 | 0
3 | Construction Cost | 336696122.29 | 33.6696 | 228045859.92 | 22.8046 | 108650262.37 | 10.865
4 | Approval Cost & Stamp Duty | 106006165 | 10.6006 | 106006165 | 10.6006 | 0 | 0
5 | Professional Cost | 3480878.33 | 0.34809 | 3341970 | 0.3342 | 138908.33 | 0.013891
6 | Admin Cost | 17127383.62 | 1.7127 | 9987468.78 | 0.99875 | 7139914.84 | 0.71399
7 | Marketing Cost | 7621680 | 0.76217 | 4455348 | 0.44553 | 3166332 | 0.31663
8 | Interest Cost | 5355026 | 0.5355 | 913270 | 0.091327 | 4441756 | 0.44418
| Total | 601287685.24 | 60.1288 | 477750511.7 | 47.7751 | 123537173.54 | 12.3537
69100000
63744974
|  | 470932229.24 |  |  |  |  | 11.9095

## Land
S.No | Land Cost: | Amount (in Rs.)
1 | Payment to Land Owners | 437153000
2 | Payment to Tenants | 304088299
741241299
3 | Stamp Duty | 38602044
68564179
| Total Land Cost | 848407522
Note: | The Stamp duty at 5% of total cost incurred i.e. 74.12 cr is approx 3.86 crs which has been paid.
S.No | Particulars | Land Cost (in Rs.) | BUA | % of Land Covered
1 | Arena ( Commercial ) | 219607901.47 | 16122.03 | 28.16%
2 | One Meraki -Wing A & B | 198240325.86 | 14171.63 | 24.75%
3 | One Meraki -Wing C | 125000430.49 | 7223.11 | 12.62%
| One Meraki -Wing D) | 135144430.49 | 7223.11 | 12.62%
4 | One Meraki -Wing E | 79841530.97 | 5861.39 | 10.24%
4 | Platina | 90572902.7 | 6649.21 | 11.61%
|  | 848407521.98 | 57250.48 | 100%
Additional Stamp Duty Cost inccured for One Meraki -Wing A & B = 52,00,000
So the total land cost = 19,30,40,325/- + 52,00,000/- = Rs. 19,82,00,000/-
| One Meraki | 198240325.86
| Stamp Duty | 5200000
| Total Land Cost | 125000430.49

## Approval Cost Details
Cost of Approvals/Liaisioning (Rs. 13.02 crore):
Sr. No. | Nature of Charges | Estimated Cost (Rs.) | Estimated Cost (Rs. In crs )
1 | Scrutiny Fees (New Proposals U/S 337 & 342 | 1400000 | 0.14
2 | Development Cess 33(7) | 42500000 | 4.25
3 | Premium for Staircase, Lift, Lift Lobby area | 10000000 | 1
4 | Premium for .50 % Addition F.S.I | 2700000 | 0.27
5 | Premium for Fungible F.S.I | 14000000 | 1.4
6 | I.O.D Deposit | 100000 | 0.01
7 | Premium for deficiency in Open Space | 300000 | 0.03
8 | Labour Welfare Cess (ADM -1% ) | 300000 | 0.03
9 | Other deficiency Premium | 3500000 | 0.35
10 | Miscellaneous | 37500000 | 3.75
11 | 5% Premium for TDR Utilizations | 2000000 | 0.2
12 | Labour Welfare Cess (Tax/Fund - 99% ) | 2800000 | 0.28
13 | Permissible additional 0.50 F.S.I Dharavi redevelopment project (DRP) | 100000 | 0.01
14 | Premium for paved/ perforated RG | 5000000 | 0.5
15 | Premium for conversion of zone from I to R/ C reg 14 B | 5500000 | 0.55
16 | MSRDC share towards Fungible FSI reg 31(3) | 2500000 | 0.25
17 | MSRDC Share towards 0.50 Addi. FSI reg 30 | 1400000 | 0.14
| Total cost of Approval / Liaisioning | 130200000 | 13.02
| Cost Inccured till 31.03.2024 | 106006165

## CONSTRUCTION COST 30.09.2024
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
04T2 CONSTRUCTION COST
Group Summary
1-Jul-24 to 30-Sep-24
Particulars | Amount | D WING | C WING | Considered by VICPL
4T2 CEMENT | 13787499.76 | 1760000 | 12027499.76
4T2 CEMENT BLOCKS | 1868199.01 | 0 | 1868199.01
4T2 CHEMICAL MATERIAL | 1234534.21 | 513450 | 721084.21
4T2 CIVIL WORK | 71000 | 0 | 71000
4T2 ELECTRICITY CHAGRES | 55593 | 0 | 55593
4T2 ELECTRIC MATERIAL | 704018.9 | 51152 | 652866.9
4T2 FABRICATION MATERIALS | 560764 | 493650 | 67114
4T2 FIRE FITIING MATERIAL | 2519607.3 | 0 | 2519607.3
4T2 FIRE FITTING EQUIPMENTS | 41708 | 14258 | 27450
4T2 GRILL & FABRICATION LABOUR | 259510 | 239710 | 19800
4T2 GST CREDIT REVERSAL | 13276451.87 | 0 | 13276451.87
4T2 LABOUR CHARGES | 16313335.5 | 265450 | 16047885.5
4T2 LIFT | 19080071.9 | 0 | 19080071.9
4T2 MISCL EXPENSES | 356642.93 | 89920 | 266722.93
4T2 MIVAN MATERIAL | 1976624 | 333341 | 1643283
4T2 PLANT AND MACHINERY | 4342.18 | 0 | 4342.18
4T2 PLUMBING LABOUR | 39096 | 0 | 39096
4T2 PLUMBING MATERIAL | 489155.9 | 72480 | 416675.9
4T2 READY MIX | 1004466.03 | 21204 | 983262.03
4T2 REPAIRS & SERVICES | 94005 | 14350 | 79655
4T2 SAFETY NET EXPS | 4800 | 4800 | 0
4T2 SAFETY NET FIXING | 53180 | 10220 | 42960
4T2 SAND | 10808541.97 | 1173235.91 | 9635306.06
4T2 SOIL TESTING | 89300 | 63500 | 25800
4T2 STEEL | 23478721.26 | 4066590 | 19412131.26
4T2 TRANSPORT CHARGES | 500 | 0 | 500
4T2 UNLOADING CHARGES | 709373 | 369634 | 339739
4T2 VENTILATION MATERIALS | 1947215.56 | 0 | 1947215.56
4T2 WATER CHARGES | 830070 | 2520 | 827550
SBI INT | 4441756 | 0 | 4441756 | 4441756
LOAN PROCESSING CHARGES | 75871.34 | 0 | 75871.34 | 75871.34
4T2 PROFESSIONAL FEES | 113108.33 | 56554.165 | 56554.165 | 113108.33
ADMIN & OTHERS | 5013111.5 | 0 | 5013111.5
| 0 | 0 | 0
Grand Total | 121302174.45 | 9616019.075 | 111686155.375 | 4630735.67
Particulars | Amount
4T2 CWING - CEMENT BLOCKS | 268143
4T2 ANCHOR WORK & LABOUR CHGS | 883950
4T2 BOREWELL | 51130
4T2 CABLES | 97212.39
4T2 CARPENTER | 89275
4T2 CEMENT | 15952385.5
4T2 CEMENT BLOCKS | 146210
4T2 CHEMICAL MATERIAL | 3084400
4T2 ELECTRICITY CHAGRES | 63903
4T2 ELECTRIC MATERIAL | 1652779.61
4T2 EXCAVATION LABOUR CHARGES | 1500000
4T2 GRILL & FABRICATION LABOUR | 684560
4T2 HARDWARE | 36780
4T2 LABOUR CHARGES | 22000739.5
4T2 MISCL EXPENSES | 564580.8
4T2 MIVAN MATERIAL | 503600
4T2 PLANT AND MACHINERY | 2146105.76
4T2 PLUMBING MATERIAL | 199546.72
4T2 READY MIX | 545327.46
4T2 REPAIRS & SERVICES | 118460
4T2 SAND | 12879902.98
4T2 SOIL TESTING | 68100
4T2 STEEL | 32177611
4T2 TRANSPORT CHARGES | 24000
4T2 UNLOADING CHARGES | 406863
4T2 WATER CHARGES | 1164500
LOAN PROCESSING CHARGES | #REF!
PO-RENOVATION UNITED LLP | 16000000
Grand Total | #REF!

## 04T2 CONSTRUCTION COST
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
04T2 CONSTRUCTION COST
Group Summary
1-Apr-01 to 31-Mar-24
Particulars | Amount
4T2 ANCHOR WORK & LABOUR CHGS | 3645500
4T2 CEMENT | 30619028.1
4T2 CEMENT BLOCKS | 6028119.77
4T2 CHEMICAL MATERIAL | 4243134.21
4T2 ELECTRIC MATERIAL | 2893383.25
4T2 EXCAVATION LABOUR CHARGES | 3500000
4T2 FABRICATION MATERAILS | 919601
4T2 FIRE FITTING EQUIPMENTS | 66932
4T2 FREIGHT - W/O GST | 4000
4T2 GRILL & FABRICATION LABOUR | 1062150
4T2 HARDWARE | 59558
4T2 LABOUR CHARGES | 58854730
4T2 MARBLE | 338050
4T2 MIVAN MATERIAL | 4864071
4T2 PLUMBING MATERIAL | 1777958.64
4T2 READY MIX | 2830060.18
4T2 REPAIRS & SERVICES | 410279
4T2 SAFETY NET EXPS | 769660
4T2 SAND | 23968127.19
4T2 STEEL | 68005245.26
4T2 PLANT AND MACHINERY | 2150447.94
4T2 MISCL EXPENSES | 831303.73
4T2 CARPENTER | 89275
4T2 CABLES | 97212.39
4T2 BOREWELL | 51130
4T2 CIVIL WORK | 71000
4T2 GST | 13276451.87
4T2 LIFT | 19080071.9
4T2 PLUMBING LABOUR | 39096
4T2 SAFETY NET FIXING | 42960
4T2 FIRE FITTING MATERIAL | 2519607.3
PO-HITACHI BUILDING SYSTEMS CO. LTD.-PO- WORK ORDER | 17095680
S- FORM INDIA PVT LTD | 3098482
ATRI BUILDTECH | 10000000
ZC TOTAL FOUNDATION | 610530
RENOVATION UNITED LLP - T2 | 38500000
HITACHI LIFT INDIA PVT LTD | 262845
JSW CEMENT LIMITED - PADMAVATI | 1315224
MAICO VENTILATION PVT LTD | 4939341.56
ALIKRAFT ENGINEERS PRIVATE LIMITED | 526280
BHARAT ENGINEERS | 2093743
UNIQUE LOGISTIC SOLUTIONS (I) PVT. LTD | 5145853
Grand Total | 336696122.29

## 4T2 ANCHOR WORK & LABOUR CHGS
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 ANCHOR WORK & LABOUR CHGS
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2022-12-06 | ZC TOTAL FOUNDATION(AEUPP8891C) | Pur - T2 | 099/TF/22-23 | 793750
2022-12-06 | ZC TOTAL FOUNDATION(AEUPP8891C) | Pur - T2 | 100/TF/22-23 | 191250
2023-03-20 | ZC TOTAL FOUNDATION(AEUPP8891C) | Pur - T2 | 142/TF/22-23 | 495000
2023-03-20 | ZC TOTAL FOUNDATION(AEUPP8891C) | Pur - T2 | 141/TF/22-23 | 488300
2023-04-26 | ZC TOTAL FOUNDATION(AEUPP8891C) | Pur - T2 | 009/TF/23-24 | 454750
2023-06-12 | ZC TOTAL FOUNDATION(AEUPP8891C) | Pur - T2 | TF/23-24/029 | 338500
2024-05-06 | ZC TOTAL FOUNDATION(AEUPP8891C) | Pur - T2 | TF/24-25/018 | 256700
2024-06-05 | ZC TOTAL FOUNDATION(AEUPP8891C) | Pur - T2 | TF/24-25/032 | 627250
TOTAL |  |  |  | 3645500

## 4T2 CEMENT
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 CEMENT
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2024-02-05 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310930491 | 87000
2024-03-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310939438 | 116000
2024-03-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310939450 | 29000
2024-03-09 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2303166795 | 116071.42
2024-03-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310940800 | 58000
2024-03-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310940799 | 87000
2024-03-15 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310941204 | 145000
2024-03-19 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2303172385 | 116071.42
2024-03-19 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310942851 | 145000
2024-03-19 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310942826 | 145000
2024-03-20 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310942897 | 145000
2024-03-22 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310943578 | 87000
2024-03-22 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310943600 | 58000
2024-03-24 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310944362 | 145000
2024-03-24 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310944183 | 145000
2024-03-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310945295 | 87000
2024-03-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310945294 | 58000
2024-03-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310945293 | 87000
2024-03-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310945296 | 58000
2024-03-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310945420 | 145000
2024-03-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310945484 | 145000
2024-03-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310945496 | 145000
2024-03-31 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310946406 | 72500
2024-03-31 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310946187 | 145000
2024-03-31 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310946405 | 72500
2024-04-16 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310949771 | 76250
2024-04-16 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310949733 | 76250
2024-04-16 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310949785 | 76250
2024-04-16 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310949790 | 76250
2024-04-16 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310949734 | 76250
2024-04-16 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310949750 | 76250
2024-04-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310949815 | 61000
2024-04-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310949889 | 76250
2024-04-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310949814 | 152500
2024-04-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310949840 | 91500
2024-04-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310949920 | 76250
2024-04-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310949835 | 152500
2024-04-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310951210 | 75000
2024-04-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310951213 | 75000
2024-04-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310951216 | 75000
2024-04-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310951219 | 75000
2024-04-23 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310951220 | 75000
2024-04-24 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310951246 | 75000
2024-04-30 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310952787 | 145000
2024-04-30 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310952796 | 145000
2024-04-30 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310952799 | 145000
2024-04-30 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310952804 | 145000
2024-04-30 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310952807 | 145000
2024-04-30 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310952903 | 145000
2024-05-01 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403016748 | 116071.42
2024-05-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310954820 | 57000
2024-05-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310954819 | 57000
2024-05-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310954821 | 57000
2024-05-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310954737 | 5700
2024-05-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310954733 | 68400
2024-05-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310954734 | 68400
2024-05-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310954741 | 68400
2024-05-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310954742 | 62700
2024-05-08 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310954744 | 57000
2024-05-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310954942 | 57000
2024-05-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310954897 | 85500
2024-05-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310954896 | 57000
2024-05-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310954870 | 85500
2024-05-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310954871 | 85500
2024-05-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310954872 | 57000
2024-05-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310954839 | 57000
2024-05-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310954838 | 17100
2024-05-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310954882 | 57000
2024-05-09 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310954837 | 68400
2024-05-12 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310955722 | 85500
2024-05-12 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310955724 | 57000
2024-05-12 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310955725 | 85500
2024-05-12 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310955720 | 57000
2024-05-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310955836 | 85500
2024-05-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310955877 | 85500
2024-05-14 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310956276 | 57000
2024-05-14 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310956272 | 57000
2024-05-14 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310956224 | 85500
2024-05-14 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310956226 | 85500
2024-05-14 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310956242 | 85500
2024-05-14 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310956239 | 85500
2024-05-14 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310956225 | 57000
2024-05-14 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310956227 | 57000
2024-05-14 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310956136 | 57000
2024-05-14 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310956134 | 57000
2024-05-16 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310956732 | 142500
2024-05-16 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310956680 | 142500
2024-05-16 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310956682 | 142500
2024-05-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310956836 | 71250
2024-05-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310956838 | 71250
2024-05-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310956837 | 71250
2024-05-18 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310957077 | 71250
2024-05-18 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403025903 | 118571.42
2024-05-18 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403025891 | 118571.42
2024-05-18 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403015757 | 116071.42
2024-05-19 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403026055 | 118571.42
2024-05-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310957829 | 57000
2024-05-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310957831 | 57000
2024-05-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310957830 | 57000
2024-05-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310957833 | 57000
2024-05-21 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310957832 | 57000
2024-05-22 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310958193 | 57000
2024-05-22 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310958194 | 14250
2024-05-22 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310958074 | 57000
2024-05-22 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310958034 | 71250
2024-05-22 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310958073 | 57000
2024-05-22 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403027711 | 118571.42
2024-05-22 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403027725 | 118571.42
2024-05-22 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310958153 | 85500
2024-05-22 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310958154 | 85500
2024-05-25 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310958912 | 56000
2024-05-25 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310958910 | 84000
2024-05-25 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310958917 | 84000
2024-05-25 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310958918 | 56000
2024-05-27 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310959342 | 140000
2024-05-27 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310959341 | 112000
2024-05-27 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310959440 | 140000
2024-05-27 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310959488 | 140000
2024-05-27 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310959503 | 28000
2024-05-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310959888 | 140000
2024-05-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310959890 | 140000
2024-05-28 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310959946 | 140000
2024-05-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310960093 | 140000
2024-05-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310960236 | 84000
2024-05-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310960243 | 56000
2024-05-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310960250 | 84000
2024-05-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310960252 | 56000
2024-05-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310960315 | 56000
2024-05-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310960316 | 56000
2024-05-30 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310960571 | 56000
2024-05-30 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310960570 | 28000
2024-05-30 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310960450 | 140000
2024-05-30 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310960442 | 140000
2024-05-30 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310960568 | 84000
2024-05-30 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403032152 | 118571.42
2024-05-30 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403031926 | 118571.42
2024-05-30 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403031930 | 118571.42
2024-05-31 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310960658 | 140000
2024-05-31 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310960645 | 140000
2024-05-31 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403032786 | 118571.42
2024-06-02 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403034080 | 118571.42
2024-06-02 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403033830 | 118571.42
2024-06-02 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403034095 | 118571.42
2024-06-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310961380 | 140840
2024-06-03 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310961383 | 139160
2024-06-05 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310961930 | 70000
2024-06-05 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310961951 | 70000
2024-06-05 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310961980 | 84000
2024-06-05 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310961982 | 84000
2024-06-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310962072 | 56000
2024-06-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310962073 | 56000
2024-06-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310962050 | 56000
2024-06-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310962052 | 14000
2024-06-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310962078 | 56000
2024-06-06 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310962081 | 14000
2024-06-07 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403036666 | 118571.42
2024-06-07 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403036588 | 118571.42
2024-06-07 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403034041 | 118571.42
2024-06-10 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310963285 | 140000
2024-06-12 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403039101 | 118571.42
2024-06-12 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403039233 | 118571.42
2024-06-12 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310963588 | 28000
2024-06-13 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403039441 | 118571.42
2024-06-13 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403039424 | 118571.42
2024-06-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310963990 | 112000
2024-06-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310964036 | 28000
2024-06-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310964037 | 112000
2024-06-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310964039 | 28000
2024-06-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310964040 | 112000
2024-06-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310964042 | 28000
2024-06-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310964043 | 84000
2024-06-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310964044 | 56000
2024-06-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310964045 | 56000
2024-06-13 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310964047 | 56000
2024-06-15 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310964512 | 60000
2024-06-15 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310964510 | 90000
2024-06-16 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310964669 | 90000
2024-06-16 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310964681 | 150000
2024-06-16 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310964810 | 60000
2024-06-16 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310964811 | 150000
2024-06-16 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310964812 | 120000
2024-06-16 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310964674 | 150000
2024-06-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310964844 | 120000
2024-06-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310964851 | 150000
2024-06-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310964856 | 30000
2024-06-17 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310964857 | 30000
2024-06-17 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403041691 | 118571.42
2024-06-17 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403041793 | 118571.42
2024-06-24 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310966128 | 70000
2024-06-24 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310966166 | 56000
2024-06-24 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310966165 | 56000
2024-06-24 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310966124 | 70000
2024-06-24 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310966126 | 70000
2024-06-24 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310966177 | 70000
2024-06-24 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310966176 | 70000
2024-06-24 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310966125 | 70000
2024-06-24 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310966057 | 70000
2024-06-24 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310966058 | 70000
2024-06-24 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310966066 | 56000
2024-06-24 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310966067 | 56000
2024-06-24 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310966068 | 56000
2024-06-25 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403045550 | 118571.42
2024-06-25 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - T2 | MH2403045588 | 118571.42
2024-06-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310967199 | 84000
2024-06-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310967204 | 84000
2024-06-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310967201 | 84000
2024-06-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310967209 | 56000
2024-06-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310967203 | 84000
2024-06-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310967208 | 56000
2024-06-29 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310967211 | 56000
2024-06-30 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310967230 | 56000
2024-06-30 | ULTRATECH CEMENT LIMITED - PADMAVATI MARKETING | Pur - T2 | 8310967342 | 112000
TOTAL |  |  |  | 18591528.34

## 4T2 CEMENT BLOCKS
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 CEMENT BLOCKS
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2023-05-02 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303012343 | 111071.42
2023-05-02 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303012326 | 111071.42
2023-05-04 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303012920 | 111071.42
2023-05-09 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303014774 | 111071.42
2023-05-11 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303015767 | 111071.42
2023-05-11 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303015669 | 111071.42
2023-05-15 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303017441 | 111071.42
2023-05-15 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303017440 | 111071.42
2023-05-18 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303018311 | 111071.42
2023-05-18 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303018307 | 111071.42
2023-05-23 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303020440 | 111071.42
2023-05-29 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303022708 | 111071.42
2023-05-30 | SUPERIOR CONCRETE PRODUCTS LLP(ACSFS6816L) | Pur - C2 | SCPL/23-24/0273 | 56900
2023-06-02 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303024481 | 111071.42
2023-06-03 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303024780 | 111071.42
2023-06-04 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303025243 | 111071.42
2023-06-06 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303025918 | 111071.42
2023-06-06 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303026090 | 111071.42
2023-06-14 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303029796 | 111071.42
2023-06-14 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303029839 | 111071.42
2023-06-25 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303034800 | 111071.42
2023-08-09 | SUPERIOR CONCRETE PRODUCTS LLP(ACSFS6816L) | Pur - C2 | SCPL/23-24/0542 | 33200
2023-09-14 | SUPERIOR CONCRETE PRODUCTS LLP(ACSFS6816L) | Pur - C2 | SCPL/23-24/0697 | 25100
2023-10-14 | SUPERIOR CONCRETE PRODUCTS LLP(ACSFS6816L) | Pur - C2 | SCPL/23-24/0818 | 54180
2023-11-04 | SUPERIOR CONCRETE PRODUCTS LLP(ACSFS6816L) | Pur - C2 | SCPL/23-24/0908 | 25350
2023-12-01 | SRSBM LAB TESTING PVT LTD(ABACS8249K) | Debit Note | MRT-19656 | -600
2023-12-15 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303120214 | 113571.42
2023-12-19 | SUPERIOR CONCRETE PRODUCTS LLP(ACSFS6816L) | Pur - C2 | SCPL/23-24/1061 | 42880
2023-12-19 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - C2 | TC07412324 | 146966
2023-12-25 | CHOICE BUILDMART | Pur - C2 | CB2325 | 20000
2023-12-26 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303126219 | 113571.42
2023-12-26 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303126255 | 113571.42
2023-12-26 | SRSBM LAB TESTING PVT LTD(ABACS8249K) | Pur - C2 | MRT-19656/1 | 600
2023-12-30 | GODREJ & BOYCE MFG CO LTD(AAACG1395D) | Pur - C2 | 1000NAI20012913 | 39200
2023-12-30 | GODREJ & BOYCE MFG CO LTD(AAACG1395D) | Pur - C2 | 1000NAI20012916 | 58800
2024-01-05 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303131325 | 113571.42
2024-02-06 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - C2 | TC08832324 | 120795
2024-02-13 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303152793 | 116071.42
2024-02-13 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303152804 | 116071.42
2024-02-27 | SUPERIOR CONCRETE PRODUCTS LLP(ACSFS6816L) | Pur - C2 | SCPL/23-24/1347 | 49570
2024-02-28 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303161030 | 116071.42
2024-02-28 | JSW CEMENT LIMITED - PADMAVATI(AABCJ6731B) | Pur - C2 | MH2303160923 | 116071.42
2024-03-06 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - C2 | TC09392324 | 116130
2024-03-10 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - C2 | TC09422324 | 116640
2024-03-16 | BIGBLOC CONSTRUCTION LTD(FOR BLOCK SECURITY DEPOSIT) | Pur - C2 | TC09542324 | 114210
TOTAL |  |  |  | 4159920.76

## 4T2 CHEMICAL MATERIAL
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 CHEMICAL MATERIAL
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2023-08-23 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T2 | VM/23-24/1394 | 93600
2023-10-12 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T2 | VM/23-24/1911 | 187200
2024-02-19 | KAVLES PRESSURE CONCRETE PVT LTD(AABCK8239K) | Pur - T2 | KPC/MEJ1/23-24 | 88900
2024-03-16 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T2 | VM/23-24/3523 | 38250
2024-03-27 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T2 | VM/23-24/3612 | 29700
2024-04-04 | KDM CHEMICALS AND RESEARCH PVT LTD | Pur - T2 | 13 | 504000
2024-04-22 | APPLE CHEMIE INDIA PVT LTD | Pur - T2 | ACM-III/2425/047 | 426000
2024-05-11 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T2 | VM/24-25/0407 | 144000
2024-05-14 | APPLE CHEMIE INDIA PVT LTD | Pur - T2 | ACM-III/2425/114 | 355000
2024-05-21 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T2 | VM/24-25/0491 | 216000
2024-05-31 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T2 | VM/24-25/0611 | 144000
2024-06-06 | APPLE CHEMIE INDIA PVT LTD | Pur - T2 | ACM-III/2425/191 | 355000
2024-06-12 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T2 | VM/24-25/0733 | 216000
2024-06-21 | KDM CHEMICALS AND RESEARCH PVT LTD | Pur - T2 | 296 | 504000
2024-06-25 | SRSBM LAB TESTING PVT LTD(ABACS8249K) | Pur - T2 | MRT-29809 | 2200
2024-06-25 | SRSBM LAB TESTING PVT LTD(ABACS8249K) | Pur - T2 | MRT-29739 | 2200
2024-06-27 | M/s VEDANT MARKETING(AANFV8458J) | Pur - T2 | VM/24-25/0886 | 216000
TOTAL |  |  |  | 3522050

## 4T2 ELECTRIC MATERIAL
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 ELECTRIC MATERIAL
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2023-04-21 | N.K.TRADING CO.(AJEPP2160M) | Pur - T2 | 10753 | 3250
2023-07-18 | EAGLE SALES CORPORATION(AAAFE2557J) | Pur - T2 | 2/795-23/24 | 33040.74
2023-12-16 | N.K.TRADING CO.(AJEPP2160M) | Pur - T2 | 11399 | 46630
2024-02-06 | EAGLE SALES CORPORATION(AAAFE2557J) | Pur - T2 | 1/16880-23/24 | 107131.2
2024-02-16 | BHARAT ENGINEERS | Pur - T2 | 2657/2023-2024 | 100800
2024-02-16 | BHARAT ENGINEERS | Pur - T2 | 2658/2023-2024 | 68780
2024-02-17 | BHARAT ENGINEERS | Pur - T2 | 2673/2023-2024 | 43700
2024-02-20 | EAGLE SALES CORPORATION(AAAFE2557J) | Pur - T2 | 1/17708-23/24 | 11604.8
2024-03-23 | N.K.TRADING CO.(AJEPP2160M) | Pur - T2 | 11634 | 172800
2024-04-06 | N.K.TRADING CO.(AJEPP2160M) | Pur - T2 | 11714 | 81230
2024-05-18 | N.K.TRADING CO.(AJEPP2160M) | Pur - T2 | 11829 | 1026905.21
2024-05-21 | BHARAT ENGINEERS | Pur - T2 | 578/2024-2025 | 24500
2024-05-21 | BHARAT ENGINEERS | Pur - T2 | 588/2024-2025 | 100800
2024-05-22 | BHARAT ENGINEERS | Pur - T2 | 596/2024-2025 | 120000
2024-05-24 | N.K.TRADING CO.(AJEPP2160M) | Pur - T2 | 11845 | 477.5
2024-05-27 | N.K.TRADING CO.(AJEPP2160M) | Pur - T2 | 11854 | 21644.8
2024-05-28 | N.K.TRADING CO.(AJEPP2160M) | Pur - T2 | 11859 | 55700
2024-05-28 | N.K.TRADING CO.(AJEPP2160M) | Pur - T2 | 11861 | 600
2024-05-30 | EAGLE SALES CORPORATION(AAAFE2557J) | Pur - T2 | 2/581-24/25 | 56790.88
2024-06-04 | N.K.TRADING CO.(AJEPP2160M) | Pur - T2 | 11879 | 25200
2024-06-05 | N.K.TRADING CO.(AJEPP2160M) | Pur - T2 | 11885 | 38739.22
2024-06-13 | N.K.TRADING CO.(AJEPP2160M) | Pur - T2 | 11904 | 34192
2024-06-15 | N.K.TRADING CO.(AJEPP2160M) | Pur - T2 | 11908 | 36400
2024-06-15 | N.K.TRADING CO.(AJEPP2160M) | Pur - T2 | 11909 | 7100
2024-06-26 | N.K.TRADING CO.(AJEPP2160M) | Pur - T2 | 11941 | 18000
2024-06-29 | N.K.TRADING CO.(AJEPP2160M) | Pur - T2 | 11949 | 4500
TOTAL |  |  |  | 2240516.35

## 4T2 EXCAVATION LABOUR CHARGES
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 EXCAVATION LABOUR CHARGES
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2024-03-09 | ZC SEVEN HILLS CONSTRUCTIONS - GARDENS(ALFPR2696M) | Pur - T2 | 025/23-24 | 2000000
2024-04-09 | ZC SEVEN HILLS CONSTRUCTIONS - T2 | Pur - T2 | 001/2024-25 | 1500000
3500000

## 4T2 FABRICATION MATERAILS
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 FABRICATION MATERAILS
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2023-08-24 | ZC PARMAR KHIMJI MAVJI & CO(AALPP8208L) | Pur - T2 | 50/23-24 | 106401
2024-03-26 | ZC PARMAR KHIMJI MAVJI & CO(AALPP8208L) | Pur - T2 | 168-23-24 | 746086
852487

## 4T2 FIRE FITTING EQUIPMENTS
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 FIRE FITTING EQUIPMENTS
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2024-03-06 | ARYAN FIRE SAFETY AND SOLUTIONS | Pur - T2 | 171 | 39482
39482 |  |  |  | 39482

## 4T2 FREIGHT - W O GST
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 FREIGHT - W/O GST
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2023-05-09 | REAL INDUSTRIES(ACGPM3884J) | Pur - T2 | 0028/23-24 | 4000
4000 |  |  |  | 4000

## 4T2 GRILL & FABRICATION LABOUR
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 GRILL & FABRICATION LABOUR
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2023-04-26 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 186 | 87820
2023-04-26 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 187 | 39150
2023-11-01 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 221 | 22800
2024-03-02 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 239 | 19600
2024-03-02 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 240 | 26520
2024-03-02 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 241 | 25500
2024-03-02 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 242 | 36700
2024-03-02 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 243 | 21500
2024-03-02 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 244 | 47800
2024-03-02 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 245 | 23500
2024-03-02 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 246 | 6900
2024-05-01 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 250 | 30100
2024-05-01 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 251 | 18880
2024-05-01 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 252 | 122600
2024-05-01 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 253 | 23500
2024-05-01 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 254 | 158000
2024-05-01 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 255 | 11560
2024-05-01 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 247 | 40600
2024-05-01 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 248 | 16400
2024-05-01 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 249 | 30000
2024-06-11 | ZC RATAN S JAWALE(AHXPJ5701H) | Pur - T2 | 278 | 232920
TOTAL |  |  |  | 1042350

## 4T2 HARDWARE
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 HARDWARE
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2023-05-18 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T2 | 72 | 1510
2023-07-21 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T2 | 168 | 2998
2023-10-16 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T2 | 288 | 1725
2023-10-17 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T2 | 289 | 4710
2023-10-17 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T2 | 290 | 700
2023-10-19 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T2 | 295 | 4435
2023-10-22 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T2 | 305 | 3140
2023-10-26 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T2 | 309 | 2130
2024-02-29 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T2 | 471 | 1430
2024-04-12 | JYOTI HARDWARE STORES(AAAFJ1248F) | Pur - T2 | 4321 | 28900
2024-06-13 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T2 | 85 | 2080
2024-06-14 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T2 | 86 | 2563
2024-06-30 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T2 | 110 | 3237
TOTAL |  |  |  | 59558

## 4T2 LABOUR CHARGES
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 LABOUR CHARGES
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2023-04-05 | ZC UTRACON STRUCTURAL SYSTEMS PVT LTD - ONE MERAKI(AAACU6685L-M) | Pur - T2 | MH/2324/M012 | 58000
2023-04-24 | ZC ATRI BUILDTECH - RESI -T2 | Pur - T2 | CD/001 | 2500000
2023-05-23 | ZC ATRI BUILDTECH - RESI -T2 | Pur - T2 | CD/002 | 9082700
2023-08-02 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T2 | 215 | 56672
2023-08-02 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T2 | 214 | 56672
2023-08-21 | ZC UCON PT STRUCTURAL SYSTEM PVT LTD | Pur - T2 | MH/2324/M356 | 18000
2023-08-31 | ZC ATRI BUILDTECH - RESI -T2 | Debit Note | CD/002 | -9082700 | 9082700
2023-08-31 | ZC ATRI BUILDTECH - RESI -T2 | Pur - T2 | CD/002 | 9082700
2023-08-31 | ZC ATRI BUILDTECH - RESI -T2 | Pur - T2 | CD/003 | 8823100
2023-09-26 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T2 | 224 | 64050
2023-10-12 | ZC UCON PT STRUCTURAL SYSTEM PVT LTD | Pur - T2 | MH/2324/264 | 13000
2023-10-30 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T2 | 234 | 64050
2023-10-30 | ZC MORE ELECTRICAL & ENGINEERING WORKS(AHJPM9415D) | Pur - T2 | 233 | 64050
2023-12-01 | ZC ATRI BUILDTECH - RESI -T2 | Debit Note | T2/CD/002 | -5850 | 5850
2023-12-01 | ZC ATRI BUILDTECH - RESI -T2 | Debit Note | T2/CD/003 | -19067 | 19067
2023-12-01 | ZC ATRI BUILDTECH - RESI -T2 | Debit Note | T2/CD/004 | -25000 | 25000
2023-12-01 | ZC ATRI BUILDTECH - RESI -T2 | Debit Note | T2/CD/005 | -3417 | 3417
2023-12-04 | ZC ATRI BUILDTECH - RESI -T2 | Debit Note | T2/CD/0016 | -12500 | 12500
2024-02-28 | ZC ATRI BUILDTECH - RESI -T2 | Debit Note | T2/CD/0017 | -4230 | 4230
2024-02-28 | ZC ATRI BUILDTECH - RESI -T2 | Debit Note | T2/CD/0018 | -3350 | 3350
2024-02-28 | ZC ATRI BUILDTECH - RESI -T2 | Debit Note | T2/CD/0019 | -12500 | 12500
2024-02-28 | ZC ATRI BUILDTECH - RESI -T2 | Debit Note | T2/CD/0020 | -30850 | 30850
2024-03-12 | ZC JSA CONSTRUCTION(BHSPM4751L-P) | Pur - T2 | 03 | 122575
2024-04-08 | ZC JSA CONSTRUCTION(BHSPM4751L-P) | Pur - T2 |  | 53500
2024-04-18 | ZC SHIVANYA CONSTRUCTION(AIMPC3289R) | Pur - T2 | SC/02,24-25 | 67837.5
2024-04-22 | ZC ATRI BUILDTECH - RESI -T2 | Debit Note | T2/CD/0021 | -13210 | 13210
2024-04-22 | ZC ATRI BUILDTECH - RESI -T2 | Debit Note | T2/CD/0022 | -1850 | 1850
2024-05-02 | ZC ATRI BUILDTECH - RESI -T2 | Pur - T2 | CD/004 | 5000000
2024-05-17 | ZC ATRI BUILDTECH - RESI -T2 | Pur - T2 | CD/006 | 5000000
2024-05-27 | ZC ATRI BUILDTECH - RESI -T2 | Pur - T2 | CD/005 | 5000000
2024-06-01 | ZC SUNRISE EARTH MOVERS(AAFPC0470K) | Pur - T2 | SEM/24-25/0015 | 94900
2024-06-11 | ZC ATRI BUILDTECH - RESI -T2 | Pur - T2 | CD/007 | 3500000
2024-06-18 | ZC ATRI BUILDTECH - RESI -T2 | Pur - T2 | CD/008 | 3299562
42806844.5

## 4T2 MARBLE
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 MARBLE
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date | Particulars |  | Vch Type | Vch No. | Bank Date | Debit | Credit
2024-03-01 | Cr | CHIMAN GRANITE MARBLE | Pur - T2 | 105 |  | 189050
2024-03-11 | Cr | CHIMAN GRANITE MARBLE | Pur - T2 | 126 |  | 149000
338050 | [5 empty] | 338050

## 4T2 MIVAN MATERIAL
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 MIVAN MATERIAL
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2024-02-01 | DEEPSHIKHA ENTERPRISES | Pur - T2 | 398 | 972370
2024-02-01 | DEEPSHIKHA ENTERPRISES | Pur - T2 | 399 | 620365
2024-02-01 | DEEPSHIKHA ENTERPRISES | Pur - T2 | 400 | 29696
2024-02-09 | DEEPSHIKHA ENTERPRISES | Pur - T2 | 412 | 118132
2024-02-19 | DEEPSHIKHA ENTERPRISES | Pur - T2 | 417 | 333800
2024-02-19 | DEEPSHIKHA ENTERPRISES | Pur - T2 | 423 | 174200
2024-02-20 | DEEPSHIKHA ENTERPRISES | Pur - T2 | 424 | 247625
2024-03-31 | DEEPSHIKHA ENTERPRISES | Pur - T2 | 476** | 221000
2024-05-20 | DEEPSHIKHA ENTERPRISES | Pur - T2 | 73 | 138000
2024-05-27 | DEEPSHIKHA ENTERPRISES | Pur - T2 | 84 | 28000
2024-05-29 | DEEPSHIKHA ENTERPRISES | Pur - T2 | 87 | 43600
2024-06-06 | DEEPSHIKHA ENTERPRISES | Pur - T2 | 100 | 82500
2024-06-08 | DEEPSHIKHA ENTERPRISES | Pur - T2 | 103 | 26000
2024-06-12 | DEEPSHIKHA ENTERPRISES | Pur - T2 | 114 | 113000
2024-06-15 | DEEPSHIKHA ENTERPRISES | Pur - T2 | 124 | 72500
Total |  |  |  | 3220788

## 4T2 PLUMBING MATERIAL
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 PLUMBING MATERIAL
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2023-05-09 | REAL INDUSTRIES(ACGPM3884J) | Pur - T2 | 0028/23-24 | 285090
2023-05-09 | REAL INDUSTRIES(ACGPM3884J) | Pur - T2 | 0029/23-24 | 44275
2023-10-14 | A.B. AJMERA & CO(AAVFA0036B) | Pur - T2 | 105/2023-24 | 80617.22
2023-12-16 | KANERIA PLAST PVT LTD(AAFCK1826N) | Pur - T2 | KP/7917/23-24 | 155700
2023-12-20 | KANERIA PLAST PVT LTD(AAFCK1826N) | Pur - T2 | KP/8040/23-24 | 130500
2023-12-22 | KANERIA PLAST PVT LTD(AAFCK1826N) | Pur - T2 | KP/8104/23-24 | 121500
2023-12-22 | KANERIA PLAST PVT LTD(AAFCK1826N) | Pur - T2 | KP/8084/23-24 | 156600
2023-12-24 | KANERIA PLAST PVT LTD(AAFCK1826N) | Pur - T2 | KP/8151/23-24 | 160200
2024-03-30 | LIDCO BUILDING TECHNOLOGIES LLP | Pur - T2 | LIDCO/1310/23-24 | 27253.8
2024-04-20 | G.R. ENTERPRISE | Pur - T2 | 017/2024-25 | 68800
2024-05-27 | G.R. ENTERPRISE | Pur - T2 | 1172/2024-25 | 14500
2024-05-30 | MEHTA ENTERPRISES(AABPJ3814A) | Pur - T2 | 65 | 6208
2024-06-06 | BHARAT ENGINEERS | Pur - T2 | 748/2024-2025 | 23400
2024-06-08 | BHARAT ENGINEERS | Pur - T2 | 760/2024-2025 | 23400
2024-06-10 | BHARAT ENGINEERS | Pur - T2 | 769/2024-2025 | 18900
2024-06-21 | K B AJMERA AND CO(AAHFK5132C) | Pur - T2 | 999 | 8148.48
2024-06-24 | ATMASS ENTERPRISES(AAAFA2582R) | Pur - T2 | 43424 | 18820
2024-06-25 | K B AJMERA AND CO(AAHFK5132C) | Pur - T2 | 1055 | 17370.24
TOTAL |  |  |  | 1361282.74

## 4T2 READY MIX
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 READY MIX
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2023-05-20 | BNC EQUIPMENT INDIA PVT.LTD | Pur - T2 | 1000/23-24-142 | 4350
2024-02-22 | BNC EQUIPMENT INDIA PVT.LTD | Pur - T2 | 1000/23-24-1009 | 8387.67
2024-02-22 | BNC EQUIPMENT INDIA PVT.LTD | Pur - T2 | 1000/23-24-1010 | 20989.17
2024-03-19 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T2 | NE/0096/23-24 | 1249144.78
2024-03-21 | BNC EQUIPMENT INDIA PVT.LTD | Pur - T2 | 1000/23-24-1132 | 13195.77
2024-03-27 | BNC EQUIPMENT INDIA PVT.LTD | Pur - T2 | 1000/23-24-1160 | 5403.3
2024-04-17 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T2 | NE/0007/24-25 | 183148
2024-04-23 | BNC EQUIPMENT INDIA PVT.LTD | Pur - T2 | 1000/24-25-62 | 21390
2024-04-25 | BNC EQUIPMENT INDIA PVT.LTD | Pur - T2 | 1000/24-25-77 | 17187.33
2024-05-30 | BNC EQUIPMENT INDIA PVT.LTD | Pur - T2 | 1000/24-25-62 | 1553.1
2024-06-18 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T2 | NE/0025/24-25 | 20600
2024-06-21 | BNC EQUIPMENT INDIA PVT.LTD | Pur - T2 | 1000/24-25-322 | 126778.53
2024-06-21 | BNC EQUIPMENT INDIA PVT.LTD | Pur - T2 | 1000/24-25-323 | 31945.5
2024-06-28 | PADMAVATI MARKETING(ADPPJ4722Q) | Pur - T2 | PM/459/24-25 | 142725
Total |  |  |  | 1846798.15

## 4T2 REPAIRS & SERVICES
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 REPAIRS & SERVICES
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2023-08-05 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3487 | 15800
2023-08-18 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3497 | 4650
2023-08-25 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3500 | 7500
2023-08-29 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3504 | 12500
2023-11-02 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3526 | 19067
2023-11-02 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3527 | 25000
2023-11-02 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3528 | 3417
2023-11-06 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3536 | 8650
2023-11-17 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3539 | 5850
2023-11-26 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3550 | 12500
2023-11-27 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3551 | 28800
2023-11-29 | AQUARIUS ENGINEERS PVT LTD(AACCA2748L) | Pur - T2 | 2301S0496 | 5000
2023-12-04 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3553 | 12500
2024-02-28 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3571 | 3350
2024-02-28 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3572 | 4230
2024-02-28 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3573 | 30850
2024-02-28 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3574 | 12500
2024-04-14 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3601 | 13210
2024-04-14 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3602 | 1850
2024-04-20 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3606 | 27260
2024-05-08 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3609 | 12500
2024-05-08 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3610 | 3350
2024-05-20 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3615 | 9200
2024-06-03 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3630 | 9000
2024-06-03 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3631 | 13640
2024-06-13 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3634 | 5200
2024-06-13 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3635 | 5060
2024-06-13 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3636 | 4250
2024-06-17 | MAURYA ELECTRICAL WORKS | Pur - T2 | 3638 | 13940
Total |  |  |  | 330624

## 4T2 SAFETY NET EXPS
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 SAFETY NET EXPS
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date | Particulars |  | Vch Type | Vch No. | Bank Date | Debit | Credit
2023-04-03 | Cr | TUSHAR STEEL(AAEPK3479R) | Pur - T2 | TS/003 |  | 57786
2023-04-24 | Cr | TUSHAR STEEL(AAEPK3479R) | Pur - T2 | TS/022 |  | 34794
2024-01-12 | Cr | G.R. ENTERPRISE | Pur - T2 | 256/23-24 |  | 2600
2024-03-13 | Cr | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T2 | K16989 |  | 198730
2024-03-18 | Cr | G.R. ENTERPRISE | Pur - T2 | 327 |  | 4600
2024-03-27 | Cr | G.R. ENTERPRISE | Pur - T2 | 340 |  | 83000
2024-03-27 | Cr | G.R. ENTERPRISE | Pur - T2 | 341 |  | 82360
2024-03-28 | Cr | G.R. ENTERPRISE | Pur - T2 | 342 |  | 82160
2024-03-28 | Cr | G.R. ENTERPRISE | Pur - T2 | 343 |  | 86200
2024-03-29 | Cr | G.R. ENTERPRISE | Pur - T2 | 344 |  | 59420
2024-03-29 | Cr | G.R. ENTERPRISE | Pur - T2 | 345 |  | 78010
769660 | [5 empty] | 769660

## 4T2 SAND
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 SAND
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2023-05-02 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T2 | NE/0006/23-24 | 96449.2
2023-06-30 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T2 | NE/0029/23-24 | 131457.42
2024-01-15 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T2 | NE/0076/23-24 | 1225011.53
2024-04-02 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T2 | NE/0002/24-25 | 2547224.18
2024-04-30 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T2 | NE/0012/24-25 | 1038511.02
2024-05-18 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T2 | NE/0016/24-25 | 1615158.65
2024-05-31 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T2 | NE/021/24-25 | 2423661.87
2024-06-18 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T2 | NE/0024/24-25 | 3030487.31
2024-06-30 | NEEV ENTERPRISE(AAQFN6654B) | Pur - T2 | NE/0030/24-25 | 2224859.95
TOTAL |  |  |  | 14332821.13

## 4T2 STEEL
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 STEEL
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2023-04-06 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B60 | 2362258
2023-04-08 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B84 | 2308680
2023-04-15 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B157 | 801450
2023-04-15 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B156 | 1214460
2023-05-09 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T2 | K9300 | 1052940
2023-10-14 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B1659 | 1739820
2024-02-23 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B2716 | 2068580
2024-03-01 | BAKKA STEEL(AYMPK4501E) | Pur - T2 | B2B1014 | 99300
2024-03-07 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B2859 | 2109975
2024-03-12 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T2 | K16929 | 425830
2024-03-22 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B3001 | 2095830
2024-03-23 | BAKKA STEEL(AYMPK4501E) | Pur - T2 | BS1065 | 136380
2024-04-22 | BAKKA STEEL(AYMPK4501E) | Pur - T2 | BS60 | 115000
2024-04-26 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B231 | 1960634
2024-04-26 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B229 | 279531
2024-05-03 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B292 | 2209893
2024-05-04 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T2 | K18427 | 710675
2024-05-08 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T2 | K18527 | 141600
2024-05-10 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B343 | 2281710
2024-05-10 | BAKKA STEEL(AYMPK4501E) | Pur - T2 | B2B109 | 238050
2024-05-10 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T2 | K18589 | 1086624
2024-05-14 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B373 | 2265760
2024-05-15 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B384 | 1132880
2024-05-15 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B383 | 1138310
2024-05-22 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B478 | 2288906
2024-05-23 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T2 | K18916 | 142500
2024-05-27 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B517 | 2268176
2024-06-03 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B579 | 2236538
2024-06-06 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B603 | 1299684
2024-06-06 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B604 | 938968
2024-06-12 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B666 | 1152276
2024-06-12 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B667 | 1127049
2024-06-18 | SHUBH M L SHAH & SONS STEEL PRIVATE LIMITED(AACCK5531B) | Pur - T2 | K19583 | 689716
2024-06-19 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B738 | 2214121
2024-06-26 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B799 | 2125830
2024-06-26 | SHRI GOPESHWAR STEELS(ABOFS0913P) | Pur - T2 | B2B803 | 2133180
TOTAL |  |  |  | 48593114

## 4T2 PLANT AND MACHINERY
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 PLANT AND MACHINERY
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-24 to 30-Jun-24
Date |  | Vch Type | Vch No. | Debit | Credit
2024-04-20 | PUTZMEISTER INDIA PVT LTD(AABCP1503H) | Pur - T2 | 240066 | 2075000
2024-06-14 | HILTI (INDIA) PVT LTD.(AAACH3583Q) | Pur - T2 | HI27-13889-2024 | 71105.76
Total |  |  |  | 2146105.76

## 4T2 CARPENTER
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 CARPENTER
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-24 to 30-Jun-24
Date |  | Vch Type | Vch No. | Debit | Credit
2024-05-01 | ZC SANSKRITI INTERIOR(BEAPJ0659F) | Pur - T2 | 056 | 89275
TOTAl |  |  |  | 89275

## 4T2 CABLES
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 CABLES
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-24 to 30-Jun-24
Date |  | Vch Type | Vch No. | Debit | Credit
2024-06-15 | PRABHAT CABLES PVT LTD(AAFCP4022K) | Pur - T2 | P/004842/24-25 | 97212.39
TOTAL |  |  |  | 97212.39

## 4T2 BOREWELL
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 BOREWELL
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-24 to 30-Jun-24
Date |  | Vch Type | Vch No. | Debit | Credit
2024-06-06 | ZC HARISH SALIAN(CGMPS3315Q) | Pur - T2 | 105 | 25690
2024-06-06 | ZC HARISH SALIAN(CGMPS3315Q) | Pur - T2 | 106 | 25440
TOTAL |  |  |  | 51130

## 4T2 MISCL EXPENSES
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 MISCL EXPENSES
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-24 to 30-Jun-24
Date |  | Vch Type | Vch No. | Debit | Credit
2024-05-01 | BAHRI AUTO SERVICE | Pur - T2 | 82 | 55260
2024-05-27 | MAHAVIR PLASTICS | Pur - T2 | 5522 | 66144
2024-05-31 | BAHRI AUTO SERVICE | Pur - T2 | 151 | 92100
2024-06-01 | PAUL COLD INDUSTRIES | Pur - T2 | PAUL/2024-25/088 | 42000
2024-06-05 | SAMRUDDHI ENGINEERS | Pur - T2 | SE/24-25/536 | 1500
2024-06-06 | GLOBETREK ENGINEERING CORPORATION | Pur - T2 | GTEC/24-25/057 | 29600
2024-06-10 | ZC RAMESH CRANE SERVICE(BAUPG1205J) | Pur - T2 | 917 | 99200
2024-06-11 | BAHRI AUTO SERVICE | Pur - T2 | 165 | 92100
2024-06-11 | SAMRUDDHI ENGINEERS | Pur - T2 | SE/24-25/587 | 1500
2024-06-11 | SAMRUDDHI ENGINEERS | Pur - T2 | SE/24-25/586 | 1500
2024-06-15 | SAMRUDDHI ENGINEERS | Pur - T2 | SE/24-25/625 | 3000
2024-06-17 | HEMALI,ADITI & FALGUNI INDUSTRIES(AAAFH2234D) | Pur - T2 | 247/24-25 | 80676.8
TOTAL |  |  |  | 564580.8

## Summary Professional
Sr. No. | Particulars | Amount
1 | Professional | 1439378.33
2 | Architect | 1934400
3 | Soil testing | 107100
TOTAL |  | 3480878.33

## 4T2 PROFESSIONAL FEES
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 PROFESSIONAL FEES
Ledger Account
( 09T2 LAISONING & PROFESSIONAL FEES )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2023-05-04 | ZP KAPURE & KAPURE(AAPFK3547F) | Pur - T2 | KK/2023/24/35 | 20000
2024-01-22 | ZP P R CONSULTANTS(AAHFP1742P) | Pur - T2 | PRC/2023-24/149 | 266270
2024-03-01 | ZPL VASMUM LEGAL(AAPFV6380F) | Pur - T2 | SBI/MHL/001 | 175000
2024-03-14 | ZPL SNG & PARTNERS(ACUPG6247R) | Pur - T2 | RE/303/23-24 | 200000
2024-04-01 | ZP RUSHIRAJ GARJE | Pur - T2 | RG/196/24-25 | 30000
2024-04-08 | ZP VENTURX PROJECTS SERVICES LLP | Pur - T2 | VPSL/2023-24/281 | 130000
2024-05-06 | ZP VENTURX PROJECTS SERVICES LLP | Pur - T2 | VPSL/2024-25/289 | 65000
2024-05-08 | ZP SBICAP TRUSTEE COMPANY LTD | Pur - T2 | SCHRG/24-25/1681 | 75000
2024-06-03 | ZP VENTURX PROJECTS SERVICES LLP | Pur - T2 | VPSL/2024-25/294 | 65000
2024-06-24 | ZP INFOMERICS VALUATION AND RATING PRIVATE LIMITED | Pur - T2 | 1684 | 300000
2024-07-31 | ZP VASTUKALA CONSULTANTS (I) PVT LTD | Pur - T2 | MUM/2425/JUL/286 | 20000
2024-08-07 | ZP AMIN R RATNANI | Pur - T2 | R/26/24-25 | 5000
2024-09-04 | ZP VENTURX PROJECTS SERVICES LLP | Pur - T2 | VPSL/2024-25/342 | 65000
2024-09-30 | ZP STATE BANK OF INDIA - T2 | Pur - T2 | T0924272O14711 | 23108.33
TOTAL |  |  |  | 1439378.33

## 4T2 SOIL TESTING
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 SOIL TESTING
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2023-06-25 | ZP F M TESTING LAB(AOMPP6000R) | Pur - T2 | 0864 | 13200
2024-05-26 | ZP F M TESTING LAB(AOMPP6000R) | Pur - T2 | 0424 | 42100
2024-06-23 | ZP F M TESTING LAB(AOMPP6000R) | Pur - T2 | 0846 | 26000
TOTAL |  |  |  | 81300

## 4T2 ARCHITECT & ENGG FEES
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 ARCHITECT & ENGG FEES
Ledger Account
( 09T2 LAISONING & PROFESSIONAL FEES )
1-Apr-22 to 31-Mar-24
Date | Particulars |  | Vch Type | Vch No. | Bank Date | Debit | Credit
2023-06-26 | Cr | ZP SHANGHVI & ASSOCIATES CONSULTANTS PVT LTD(AALCS3411K) | Pur - T2 | SACPL/095/22-23 |  | 1934400
1934400 | [5 empty] | 1934400

## Summary Admin
Sr. No. | Particulars | Amount
1 | Water Charges | 2035250
2 | Bank Processing Fees | 8292624.12
3 | Unloading Charges | 746602
4 | Transport Charges | 24500
5 | Electricity Charges | 119496
6 | Cleaning Charges | 895800
| Salary | 5013111.5
TOTAL |  | 17127383.62

## 4T2 WATER CHARGES
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 WATER CHARGES
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-22 to 31-Mar-24
Date |  | Vch Type | Vch No. | Debit | Credit
2024-01-08 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T2 | 1520 | 43200
2024-04-04 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T2 | 1630 | 177800
2024-04-04 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T2 | 1631 | 58900
2024-05-07 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T2 | 1662 | 57000
2024-05-07 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T2 | 1664 | 175700
2024-05-07 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T2 | 1663 | 169100
2024-05-10 | NEW TRIMURTI WATER SUPPLIER | Pur - T2 | 146 | 4200
2024-06-03 | NEW TRIMURTI WATER SUPPLIER | Pur - T2 | 179 | 4500
2024-06-18 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T2 | 1676 | 207100
2024-06-18 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T2 | 1675 | 251300
2024-06-18 | ASHTA VINAYAK WATER SUPPLIERS | Pur - T2 | 1677 | 58900
TOTAL |  |  |  | 1207700
2024-03-30 | 2Z STATE BANK OF INDIA - 6965-ESCROW ACCOUNT ONE MERAKI WING C & WING D -30%(42038426965) | Payment | ESBTER | 1355500
E-STAMP PAPER 1355500/- FOR MORTGAGE CUM LOAN AGREEMENT WITH STATE BANK OF INDIA FOR 45 Cr PAID 1 Loan agreement Rs.600/- 2 Guarantee Agreement Rs.600/- 3 Hypothecation Agreement Rs.13,51,500/-(0.3% of loan amount+1500) 4 Escrow agreement Rs.200/- 5 Arrangement letter Rs.500/- 6 Memorandum of Understanding Rs.500/- 7 Security Trustee Agreement Rs.1600/- TOTAL Rs.13,55,500/-
2024-03-31 | 2Z PUNJAB NATIONAL BANK - 0077002102302129(0077002102302129) | Payment | STAMP DUTY +REG | 1365000
STAMP DUTY 1350000/- + REGISTRATION 15000/- FOR MORTGAGE CUM LOAN AGREEMENT WITH STATE BANK OF INDIA FOR 45 Cr PAID
2024-04-30 | ZP STATE BANK OF INDIA - T2 | Pur - T2 | T0424272O16175 | 5400000
BILL BOOKS AS PER GST DATA
2024-04-30 | ZP STATE BANK OF INDIA - T2 | Pur - T2 | T0424272O16176 | 62000
BILL BOOKS AS PER GST DATA
2024-06-30 | ZP STATE BANK OF INDIA - T2 | Pur - T2 | T0624272O16567 | 16252.78
BILL BOOKS AS PER GST DATA
2024-04-03 | AMIN R RATNANI | Pur - T2 | R/02/24-25 | 2200
TOWARDS DOCUMENTS HANDLING CHRGES AS ACTUAL OF REGISTRATION OF MORTGAGE DEED BETWEEN MERAKI HABITATS LLP & SBICAP TRUSTEE COMPANY LTD REGISTERED UNDER KRL5-8735-2024
2024-04-03 | ZP AMIN R RATNANI | Pur - T2 | R/05/24-25 | 10000
TOWARDS DOCUMENTS HANDLING CHRGES AS ACTUAL OF REGISTRATION OF MORTGAGE DEED BETWEEN MERAKI HABITATS LLP & SBICAP TRUSTEE COMPANY LTD REGISTERED UNDER KRL5-8735-2024
2024-04-17 | ZP AMIN R RATNANI | Pur - T2 | R/07/24-25 | 5000
TOWARDS DOCUMENTS HANDLING CHRGES AS ACTUAL OF REGISTRATION OF RECTIFICATION DEED BETWEEN MERAKI HABITATS LLP & SBICAP TRUSTEE COMPANY LTD REGISTERED UNDER KRL5-9647-2024
2024-04-17 | AMIN R RATNANI | Pur - T2 | R/07/24-25 | 800
TOWARDS DOCUMENTS HANDLING CHRGES AS ACTUAL OF REGISTRATION OF RECTIFICATION DEED BETWEEN MERAKI HABITATS LLP & SBICAP TRUSTEE COMPANY LTD REGISTERED UNDER KRL5-9647-2024 ( DEBIT NOTE R/07)
2024-07-31 | ZP STATE BANK OF INDIA - T2 | Pur - T2 | T0724272O16960 | 1575
BILL BOOKS AS PER GST DATA
2024-07-31 | ZP STATE BANK OF INDIA - T2 | Pur - T2 | T0724272O16961 | 100
BILL BOOKS AS PER GST DATA
2024-08-31 | ZP STATE BANK OF INDIA - T2 | Pur - T2 | T0824272O15840 | 30608.78
BILL BOOKS AS PER GST DATA
2024-08-31 | ZP STATE BANK OF INDIA - T2 | Pur - T2 | T0824272O15841 | 43587.56
BILL BOOKS AS PER GST DATA
8292624.12

## 4T2 UNLOADING CHARGES
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 UNLOADING CHARGES
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-24 to 30-Jun-24
Date |  | Vch Type | Vch No. | Debit | Credit
2024-05-25 | ZC DAIVIK ENTERPRISES(AAABD6286F) | Pur - T2 | 08 | 117926
2024-06-27 | ZC DAIVIK ENTERPRISES(AAABD6286F) | Pur - T2 | 09 | 288937
TOTAL |  |  |  | 406863

## 4T2 TRANSPORT CHARGES
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 TRANSPORT CHARGES
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-24 to 30-Jun-24
Date |  | Vch Type | Vch No. | Debit | Credit
2024-05-01 | SHARADA TRANSPORT | Pur - T2 | 275 | 24000
TOTAL |  |  |  | 24000

## 4T2 ELECTRICITY CHAGRES
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 ELECTRICITY CHAGRES
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-01 to 30-Jun-24
Date |  | Vch Type | Vch No. | Bank Date | Debit | Credit
2024-04-12 | 2Z STATE BANK OF INDIA - 6965-ESCROW ACCOUNT ONE MERAKI WING C & WING D -30% | Payment | CMS | 2024-04-12 | 17383
2024-05-06 | 2Z STATE BANK OF INDIA - 6965-ESCROW ACCOUNT ONE MERAKI WING C & WING D -30% | Payment | CMS | 2024-05-06 | 21650
2024-05-06 | 2Z STATE BANK OF INDIA - 6965-ESCROW ACCOUNT ONE MERAKI WING C & WING D -30% | Payment | CMS | 2024-05-06 | 21650
2024-05-31 | 2Z STATE BANK OF INDIA - 6965-ESCROW ACCOUNT ONE MERAKI WING C & WING D -30% | Payment | CMS | 2024-06-03 | 3220
TOTAL |  |  |  |  | 63903

## 4T2 CLEANING CHARGES
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 CLEANING CHARGES
Ledger Account
( 04T2 CONSTRUCTION COST )
1-Apr-01 to 30-Jun-24
Date |  | Vch Type | Vch No. | Credit
2024-05-21 | ZC TOTAL FOUNDATION(AEUPP8891C) | Journal |  | 33900
2024-06-14 | ZC TOTAL FOUNDATION(AEUPP8891C) | Journal | 690300 | 34350
TOTAL |  |  |  | 68250

## Marketing
MERAKI HABITATS LLP
(Formerly Known As Shiv Sabari Developers)
505 MERAKI ARENA
SION TROMBAY ROAD OPP R K STUDIO
CHEMBUR MUMBAI-400 071
CIN: AAZ-9591
4T2 STAMP DUTY & REGISTRATION CHARGES
Ledger Account
( 01T2 LAND COST )
1-Apr-01 to 31-Mar-24
Date | Particulars |  | Vch Type | Vch No. | Bank Date | Debit | Credit
2023-03-25 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2023-03-25 | 30000
REG.FEES 30,000 PAID FOR SALE DEED - VINODKUMAR TANDEL ON OUR BEHALF
2023-03-25 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2023-03-25 | 698000
FOR REG.FEES 30,0000 & STAMP DUTY 6,68,000/- PAID FOR SURRENDER OF TENANCY - VINODKUMAR TANDEL ON OUR BEHALF
2023-03-31 | Cr | ZP AMIN R RATNANI | Pur - T2 | R/44/22-23 |  | 10000
TOWARDS REGISTRATION OF AGREEMENT ON ALLOTMENT BASIS BETWEEN MERAKI HABITATS LLP & M/S. BHAYANI INVESTMENTS, REGISTERES UNDER KRL5-6513-2023
2023-03-31 | Cr | AMIN R RATNANI | Pur - T2 | R/44/22-23 |  | 2800
TOWARDS REGISTRATION OF AGREEMENT ON ALLOTMENT BASIS BETWEEN MERAKI HABITATS LLP & M/S. BHAYANI INVESTMENTS, REGISTERES UNDER KRL5-6513-2023 DEBIT NOTE
2023-03-31 | Cr | AMIN R RATNANI | Pur - T2 | R/41/22-23 |  | 1000
TOWARDS DOCUMENTS HANDLING CHARGES ACTUAL FOR REGISTRATION OF SURRENDER OF LEASE BETWEEN MEARKI HABITATS LLP & MR . VINODKUMAR DAHYABHAI TANDEL , REGISTERED UNDER KRL5-6395-2023
2023-03-31 | Cr | ZP AMIN R RATNANI | Pur - T2 | R/41/22-23 |  | 10000
TOWARDS REGISTRATION OF SURRENDER OF LEASE BETWEEN MEARKI HABITATS LLP & MR . VINODKUMAR DAHYABHAI TANDEL , REGISTERED UNDER KRL5-6395-2023
2023-03-31 | Cr | ZP AMIN R RATNANI | Pur - T2 | R/43/22-23 |  | 5000
TOWARDS REGISTRATION OF SALE DEED BETWEEN MR. SHEETAL ANIL GANDHI & MR. VINODKUMAR DAHYABHAI TANDEL , REGISTERED UNDER KRL5-6392-2023
2023-03-31 | Cr | AMIN R RATNANI | Pur - T2 | R/43/22-23 |  | 520
TOWARDS DOCUEMENTS HANDLING CHARGES AS ACTUAL SALE DEED BETWEEN MR. SHEETAL ANIL GANDHI & MR. VINODKUMAR DAHYABHAI TANDEL , REGISTERED UNDER KRL5-6392-2023 DEBIT NOTE
2023-03-31 | Dr | 22 WORK IN PROGRESS - TOWER - 2 | Journal |  |  | 757320 | 757320
TRFD & CLOSED
2023-04-27 | Cr | ZP AMIN R RATNANI | Pur - T2 | R/01/23-24 |  | 5000
TOWARDS REGISTRATION OF DEED OF RECTIFICATION BETWEEN MR SHEETAL ANI GANDHI & VINOD KUMAR DAHYABHAI TANDEL REGISTERED UNDER KRL5 -8263-2023
2023-04-27 | Cr | AMIN R RATNANI | Pur - T2 | R/01/23-24 |  | 800
TOWARDS REGISTRATION OF DEED OF RECTIFICATION BETWEEN MR SHEETAL ANI GANDHI & VINOD KUMAR DAHYABHAI TANDEL REGISTERED UNDER KRL5 -8263-2023 DEBIT NOTE
2023-08-07 | Cr | ZS VISHAL MAHADU TAPAL | Journal | REG FEES + STAMP DUTY |  | 96000
FOR STAMP DUTY 80,000/- & REGS.FEES 16,000 PAID FOR SURRENDER OF TENANCY - JAYSAWAR FULCHAND ON OUR BEHALF
2023-08-11 | Cr | AMIN R RATNANI | Pur - T2 | R/22/23-24 |  | 4240
DEBIT NOTE RS.4241/-, TOWARDS DOCUMENTS HANDELING CHARGES AS ACTUAL OF REGISTRATION OF FOUR NOS. SURRENDER OF TENANCY BETWEEN MERAKI AND MR BABLU JAYSWAR
2023-08-21 | Cr | ZP AMIN R RATNANI | Pur - T2 | R/22/23-24 |  | 20000
TOWARDS REGISTRATION OF SURRENDER OF TENANCY BETWEEN MR.BABLU JAYSAWAR, MR LUCKY JAYASWAR & MR MANJU JAISWAL UNDER KRL1-16590-20236, KRL1-16591-2023, KRL1-16595-2023 & KRL1-16593-2023
2023-08-22 | Cr | ZS VISHAL MAHADU TAPAL | Journal | REG FEES + STAMP DUTY |  | 30012
FOR STAMP DUTY 25,000/- & REGS.FEES 5,000 PAID FOR SURRENDER OF TENANCY - SHAIKH RUBINA MOHSIN ON OUR BEHALF ( BK CHGS 12)
2023-08-22 | Cr | ZS VISHAL MAHADU TAPAL | Journal | REG FEES + STAMP DUTY |  | 30012
FOR STAMP DUTY 25,000/- & REGS.FEES 5,000 PAID FOR SURRENDER OF TENANCY - SHABANA RAFIQ KHAN ON OUR BEHALF ( BK CHGS 12)
2023-08-23 | Cr | ZP AMIN R RATNANI | Pur - T2 | R/23/23-24 |  | 10000
TOWARDS REGISTRATION OF SURRENDER OF TENANCY , CONSULTATION FEES , KRL5-17860-2023, KRL5-117858-2023
2023-08-24 | Cr | ZS VISHAL MAHADU TAPAL | Journal | REG FEES + STAMP DUTY |  | 330012
FOR STAMP DUTY 3,00,000/- & REGS.FEES 30,000 PAID FOR SURRENDER OF TENANCY - BADRUNISHA YASIN CHAVAN & AKRAM YASIN CHAVAN ON OUR BEHALF ( BK CHGS 12)
2023-08-29 | Cr | ZP AMIN R RATNANI | Pur - T2 | R/24/23-24 |  | 5000
BILL NO - R/24/23-24, CONSULTATION FEES TOWARDS REGISTERATION OF TWO NO.S AGREEMENT FOR SALE BETWEEN MERAKI HABITATS LLP AND MRS BANDRUNISHA YASIN CHAVAN & MR AKRAM YASIN CHAVAN REGISTERED UNDER KRL5-181172-2023
2023-08-29 | Cr | AMIN R RATNANI | Pur - T2 | R/24/23-24 |  | 960
DEBIT NOTE FOR DOCUMNET HANDLING CHARGES OF REGISTRATION FOR ONE MERAKI C & D WING
2023-10-20 | Cr | ZS VISHAL MAHADU TAPAL | Journal | REG FEES + STAMP DUTY |  | 280012
FOR STAMP DUTY 2,50,000/- & REGS.FEES 30,000 PAID FOR SURRENDER OF TENANCY - AYUB KHAN ON OUR BEHALF ( BK 12)
2024-01-11 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2024-01-11 | 500000
FOR STAMP DUTY 4,70,000/- & REGS.FEES 30,000 PAID FOR SURRENDER OF TENANCY - HAFIJA ABBAS KHAN ON OUR BEHALF
2024-01-30 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2024-01-30 | 90000
FOR STAMP DUTY 75,000/- & REGS.FEES 15,000 PAID FOR SURRENDER OF TENANCY - SHAQUIB SHAFIQUE SHAIKH ON OUR BEHALF
2024-01-30 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2024-01-30 | 90000
FOR STAMP DUTY 75,000/- & REGS.FEES 15,000 PAID FOR SURRENDER OF TENANCY - SHAHBAZ SHAFIQUE SHAIKH ON OUR BEHALF
2024-01-30 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2024-01-30 | 90000
FOR STAMP DUTY 75,000/- & REGS.FEES 15,000 PAID FOR SURRENDER OF TENANCY - SHAHNAWAZ SHAFIQUE SHAIKH ON OUR BEHALF
2024-01-30 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2024-01-30 | 90000
FOR STAMP DUTY 75,000/- & REGS.FEES 15,000 PAID FOR SURRENDER OF TENANCY - ASMABI SHAFIQUE SHAIKH ON OUR BEHALF
2024-02-01 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2024-02-01 | 150000
FOR STAMP DUTY 125,000/- & REGS.FEES 25,000 PAID FOR SURRENDER OF TENANCY - JAVED NASRUBHAI SAYED ON OUR BEHALF
2024-02-01 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2024-02-01 | 150000
FOR STAMP DUTY 125,000/- & REGS.FEES 25,000 PAID FOR SURRENDER OF TENANCY - IMARAN NASRUBHAI SAYED ON OUR BEHALF
2024-02-01 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2024-02-01 | 150000
FOR STAMP DUTY 125,000/- & REGS.FEES 25,000 PAID FOR SURRENDER OF TENANCY - MOSIM NASRUBHAI SAYED ON OUR BEHALF
2024-02-01 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2024-02-01 | 150000
FOR STAMP DUTY 125,000/- & REGS.FEES 25,000 PAID FOR SURRENDER OF TENANCY - YAKUB K SAYED ON OUR BEHALF
2024-02-04 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY | 2024-02-04 | 150000
FOR STAMP DUTY 125,000/- & REGS.FEES 25,000 PAID FOR SURRENDER OF TENANCY - MEHBOOB KHAN ON OUR BEHALF
2024-02-07 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY - C308 CENTRIO | 2024-02-07 | 239000
FOR STAMP DUTY 209,000/- & REGS.FEES 30,000 PAID FOR SALE OF AGRREEMENT - MEHBOOB KHAN ON OUR BEHALF -CENTRIO BY MJ SHAH C-308
2024-02-07 | Cr | 2Z PUNJAB NATIONAL BANK - 0077002102302129 | Payment | REG FEES + STAMP DUTY - C307 CENTRIO | 2024-02-07 | 239000
FOR STAMP DUTY 209,000/- & REGS.FEES 30,000 PAID FOR SALE OF AGRREEMENT - CHAND MEHBOOB KHAN ON OUR BEHALF -CENTRIO BY MJ SHAH C-307
2024-02-23 | Cr | ZP AMIN R RATNANI | Pur - T2 | R/57/23-24 |  | 20000
TOWARDS REGISTRATION OF 4 NOS. SURRENDER OF TENANCY BETWEEN MERAKI HABITATS LLP AND 1) MR. SHAILESH HARI GHADSE, 2) MRS MINALI CHANDDRAKANT PISE, 3) MR DAYAL CHANDRAKANT PISE AND 4) MR ROHTI CHANDRAKANT PISE ALL REGISTERED UNDER KRL5-3680-2024, KRL5-4581-2024, KRL5-4580-2024 AND KRL5-4582-2024
2024-02-23 | Cr | AMIN R RATNANI | Pur - T2 | R/57/23-24 |  | 4100
TOWARDS DOCUMENTS HANDLING CHARGES AS ACTUAL OF REGISTRATION OF 4 NOS. SURRENDER OF TENANCY BETWEEN MERAKI HABITATS LLP AND 1) MR. SHAILESH HARI GHADSE, 2) MRS MINALI CHANDDRAKANT PISE, 3) MR DAYAL CHANDRAKANT PISE AND 4) MR ROHTI CHANDRAKANT PISE ALL REGISTERED UNDER KRL5-3680-2024, KRL5-4581-2024, KRL5-4580-2024 AND KRL5-4582-2024
2024-03-01 | Cr | ZP AMIN R RATNANI | Pur - T2 | R/60/23-24 |  | 10000
TOWARDS REGISTRATION OF 2 NOS. OF AGREEMENT FOR SIDE BETWEEN MERAKI HABITATS LLP AND 1) NEETU SINGH AND 2) MS. RANJEETA SINGH, REGISTERED UNDER KRL5-5295-2024 & KRL5-5300-2024
2024-03-01 | Cr | AMIN R RATNANI | Pur - T2 | R/60/23-24 |  | 6560
TOWARDS DOCUMENTS HANDLING CHARGES AS ACTUAL OF REGISTRATION OF 2 NOS. OF AGREEMENT FOR SALE BETWEEN MERAKI HABITATS LLP AND 1) MS. NEETU SINGH AND 2) MS. RANJEETA SINGH, REGISTERED UNDER KRL5-5295-2024 &KRL5-5300-2024.
|  | 4T2 STAMP DUTY & REGISTRATION CHARGES for 3rd Quarter |  |  |  | 3166332
7621680
7621680

## Approval Cost
Annexure II
Sr. No | Nature of Charges - One Meraki - Wing A & Wing B | Paid Date | Receipt Amount
1 | PAID TO MCGM FOR SCRUTINY FEES 80500 + DEBRIS REMOVAL 20200 + I.O.D. DEPOSIT 10100 + ( BK CHGS1308 ) - One Meraki | 2021-06-21 | 55400
2 | PAID TO MCGM FOR SCRUTINY FEES - RESIDENANCE | 2021-06-29 | 418600
3 | PAID FOR DEMAND NOTE CFO NOC - BLDG - 1 ( 545546 + CHGS 12 ) | 2021-10-11 | 272773
4 | PAID TO MCGM FOR SCRUTINY FEES - SWD | 2021-10-13 | 129500
5 | PAID TO MCGM FOR REVALIDATIONS - SWD | 2021-10-13 | 388400
6 | PAID FOR DEMAND NOTE CFO NOC - BLDG - 1 ( 1004340 + CHGS 12 ) | 2021-11-02 | 502176
7 | PAID FOR MCGM BLDG NO.1 SCRUTINY FEES ( NEW PROPOSALS U/S 337 & 342 ) FEES 13750 + ONLINE CHARGES 163 | 2021-12-08 | 6875
8 | PAID FOR MCGM BLDG NO.1 SCRUTINY FEES FOR TDR & ACCOM RESERVATION UTILISATION FEES 13750 + ONLINE CHARGES 12 | 2021-12-09 | 285503
9 | PAID FOR MCGM BLDG NO.1 SCRUTINY FEES FOR TDR UTILISATION FEES 159800 + ONLINE CHARGES 12 | 2021-12-13 | 79900
10 | Scrutiny Fees (New Proposals U/S 337 & 342 | 2021-12-23 | 2790000
11 | Development Cess 33(7) | 2021-12-23 | 5708100
12 | Premium for Staircase, Lift, Lift Lobby area | 2021-12-23 | 23360125
13 | Premium for .50 % Addition F.S.I | 2021-12-23 | 5437350
14 | Premium for Fungible F.S.I | 2021-12-23 | 32650325
15 | I.O.D Deposit | 2021-12-23 | 142350
16 | Premium for deficiency in Open Space | 2021-12-23 | 3460850
17 | Labour Welfare Cess (ADM -1% ) | 2021-12-23 | 40050
18 | Other deficiency Premium | 2021-12-23 | 201450
19 | 5% Premium for TDR Utilizations | 2021-12-23 | 7675050
20 | Labour Welfare Cess (Tax/Fund - 99% ) | 2021-12-23 | 3960600
21 | Permissible additional 0.50 F.S.I Dharavi redevelopment project (DRP) | 2021-12-23 | 5437350
22 | Premium for paved/ perforated RG | 2021-12-23 | 105200
23 | Premium for conversion of zone from I to R/ C reg 14 B | 2021-12-23 | 10647175
24 | MSRDC share towards Fungible FSI reg 31(3) | 2021-12-23 | 13060125
25 | MSRDC Share towards 0.50 Addi. FSI reg 30 | 2021-12-23 | 5437350
26 | 25% SHARE GOVT 0.50 FSI CHE ES 0840 M W 337 NEW | 2021-12-23 | 5437306.5
27 | 30% SHARE GOVT FUNGIBLE AREA CHE ES 0840 M W 337 NEW | 2021-12-23 | 19590187
28 | MCGM-PROPERTY TAX-MW090744307000- APR/MAR'21 (SABARI GARDENS) | 2021-12-29 | 1970122
29 | 50% SHARE GOVT AS PER REG 14B OF DCPR 2034 FOR I TO R FILE NO CHE ES 0840 M W 337 NEW | 2021-12-30 | 5323587.5
30 | PAID FOR LOC TAX - MCGM | 2022-03-21 | 3950000
| TOTAL - A |  | 158523780
1 | MARKET TDR -MAHAAVIR ASSOCIATES - | 2021-06-07 | 1750000
2 | MARKET TDR -MAHAAVIR ASSOCIATES - | 2021-06-07 | 2800000
3 | MARKET TDR -RELIABLE BUILDERS DEVELOPERS | 2021-11-23 | 16982567.5
4 | MARKET TDR-ENTIRE ESTATES PRIVATE LIMITED | 2021-11-25 | 56550000
| TOTAL - B |  | 78082567.5
| TOTAL - A+B |  | 236606347.5
1 | Balance Cost for Approval |  | 13300000
| TOTAL - A+B+C |  | 249906347.5

## Interest
Sr. No. | Particulars | Amount | Amount in ` Cr. | Amount | Amount in ` Cr. | Balance | Balance in Cr.
| 2024-04-01 | 41453 |  |  |  | 41453 | 0
| 2024-05-01 | 243784 |  |  |  | 243784 | 0
| 2024-06-01 | 628033 |  |  |  | 628033 | 0
| 2024-07-01 | 1271480 |  |  |  | 1271480 | 0
| 2024-08-01 | 1463731 |  |  |  | 1463731 | 0
| 2024-09-01 | 1706545 |  |  |  | 1706545 | 0
|  | 5355026 | 0 | 0 | 0 | 5355026 | 0

## Construction Area of Sale Build
Summary of Cost of Construction
Plinth Area Calculation
Sr. No | Floor Nos. | Total Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | Percentage of work completed | Actual Expenditure till date in `
1 | Excavation |  |  |  | 50738418 | 100% | 50738418
2 | Basement 1 | 1761.59 | 1761.59 | 30000 | 52847700 | 50% | 26423850
3 | Basement 2 | 1761.59 | 1761.59 | 30000 | 52847700 | 50% | 26423850
4 | Basement 3 | 1761.59 | 1761.59 | 30000 | 52847700 | 50% | 26423850
5 | Ground Floor | 1860.68 | 1860.68 | 30000 | 55820400 | 50% | 27910200
6 | 1st Podium Floor | 794.1 | 794.1 | 30000 | 23823000 | 50% | 11911500
7 | 2nd Floor | 496.756 | 496.756 | 30000 | 14902680 | 65% | 9686742
8 | 3rd Floor | 496.756 | 496.756 | 30000 | 14902680 | 65% | 9686742
9 | 4th Floor | 496.756 | 496.756 | 30000 | 14902680 | 65% | 9686742
10 | 5th Floor | 496.756 | 496.756 | 30000 | 14902680 | 65% | 9686742
11 | 6th Floor | 496.756 | 496.756 | 30000 | 14902680 | 65% | 9686742
12 | 7th Floor | 491.46 | 491.46 | 30000 | 14743800 | 58% | 8551404
13 | 8th Floor | 498.306 | 498.306 | 30000 | 14949180 | 65% | 9716967
14 | 9th Floor | 496.756 | 496.756 | 30000 | 14902680 | 65% | 9686742
15 | 10th Floor | 496.756 | 496.756 | 30000 | 14902680 | 62% | 9239661.6
16 | 11th Floor | 496.756 | 496.756 | 30000 | 14902680 | 58% | 8643554.4
17 | 12th Floor | 496.756 | 496.756 | 30000 | 14902680 | 50% | 7451340
18 | 13th Floor | 496.756 | 496.756 | 30000 | 14902680 | 50% | 7451340
19 | 14th Floor | 491.45 | 491.45 | 30000 | 14743500 | 40% | 5897400
20 | 15th Floor | 498.306 |  | 30000 | 14949180 | 0% | 0
21 | 16th Floor | 496.756 |  | 30000 | 14902680 | 0% | 0
22 | 17th Floor | 496.756 |  | 30000 | 14902680 | 0% | 0
23 | 18th Floor | 496.756 |  | 30000 | 14902680 | 0% | 0
24 | 19th Floor | 496.756 |  | 30000 | 14902680 | 0% | 0
25 | Terrace | 39.15 |  | 30000 | 1174500 | 0% | 0
Total |  | 16912.806 | 14388.326 |  | 558122598 | 51.05% | 284903787
|  |  | 0.85074 |  |  |  | 28.4904

## Construction Area (2)
COST OF CONSTRUCTION WING C
Sr. No | Floor Nos. | Built Up Area in Sq. M. | Balcony/FB/ Terrace Area/ Chhajja in Sq. M. | Staircase & Lift Area in Sq. M. | REFUGE AREA in Sq. M. | Stlit Area in Sq. M. | Meter Room/ Electric room / DG Room area in Sq. M. | Lobby Area in Sq. M. | Other Area/ Gents Toilet/Fitness Centre in Sq. M. | Total Area in Sq. M.
1 | Basement 1 | 0 | 0 | 0 | 0 | 1761.59 | 0 | 0 | 0 | 1761.59 | 18961.7548
2 | Basement 2 | 0 | 0 | 0 | 0 | 1761.59 | 0 | 0 | 0 | 1761.59 | 18961.7548
3 | Basement 3 | 0 | 0 | 0 | 0 | 1761.59 | 0 | 0 | 0 | 1761.59 | 18961.7548
4 | Ground Floor | 0 | 0 | 72.4 | 0 | 1717.52 | 70.76 | 0 | 0 | 1860.68 | 20028.3595
5 | 1st Podium Floor | 86.08 | 0 | 72.4 | 0 | 0 | 0 | 0 | 635.62 | 794.1 | 8547.6924
6 | 2nd Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
7 | 3rd Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
8 | 4th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
9 | 5th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
10 | 6th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
11 | 7th Floor | 302.21 | 2.04 | 71.12 | 112.72 | 0 | 0 | 0 | 3.37 | 491.46 | 5290.0754
12 | 8th Floor | 414.92 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 498.306 | 5363.7658
13 | 9th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
14 | 10th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
15 | 11th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
16 | 12th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
17 | 13th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
18 | 14th Floor | 304.13 | 2.04 | 71.12 | 110.79 | 0 | 0 | - | 3.37 | 491.45 | 5289.9678
19 | 15th Floor | 414.92 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 498.306 | 5363.7658
20 | 16th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
21 | 17th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
22 | 18th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
23 | 19th Floor | 413.37 | 12.266 | 71.12 | 0 | 0 | 0 | 0 | 0 | 496.756 | 5347.0816
24 | Terrace | 0 | 0 | 39.15 | 0 | 0 | 0 | 0 | 0 | 39.15 | 421.4106
| Total | 7309.44 | 200.336 | 1464.11 | 223.51 | 7002.29 | 70.76 | 0 | 642.36 | 16912.806 | 182049.4438
|  | 78678.8122 | [7 empty] | 30000 | 3000
[10 empty] | 507384180 | 546148331
[9 empty] | 10% of Excavation | 50738418 | 54614833
[9 empty] | TOTAL | 558122598 | 600763164