## Final Summary
Project expenses | Estimated Cost as per Cost Vetting | Incurred Cost as per Bill till 31.08.2024 | Incurred Cost as per CA till 31.08.2024 | Incurred Cost as per Bill till 31.12.2022 | Incurred Cost as per CA till 31.12.2022 | Difference between the Bills & CA | Difference between both the Bills | Difference between both CA | Remark
Land Cost | 23.3 | 23.2984 | 23.3 |  |  | -0.001636
Construction Cost of Sale Building | 63.92 | 11.4892 | 11.48 |  |  | 0.0092025
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 0.75 | 0 | 0
Architect Cost, RCC & other Professional fees | 0.64 | 0.097375 | 0.72 |  |  | 0.13344
Administrative Expenses | 3.2 | 0.69807
Marketing Expences | 2.75 | 0.057992
Interest Cost | 12.04 | 0.18253 | 0.18 |  |  | 0.0025344
Contingency Cost | 1.92 | 0 | 0 |  |  | 0
Total Cost | 108.52 | 35.8235 | 35.68 | 0 | 0 | 0.14354 | 0 | 0
|  | 72.6965 | 32.88%
Particulars | Revised Estimated Cost (in Cr.) | 31.08.2024 as per Bill Tally (inclusive of GST) | Cost incurred as %age total cost of that Component | Cost incurred as %age of cost incurred as on 31.08.2024
Land Cost | 23.3 | 23.2984 | 99.99% | 21.47%
Construction Cost of Sale Building | 63.92 | 11.4892 | 17.97% | 10.59%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 0.75 | 0 | 0% | 0%
Architect Cost, RCC & other Professional fees | 0.64 | 0.097375 | 15.21% | 0.08973%
Administrative Expenses | 3.2 | 0.69807 | 21.81% | 0.6433%
Marketing Expences | 2.75 | 0.057992 | 2.109% | 0.05344%
Interest Cost | 12.04 | 0.18253 | 1.516% | 0.1682%
Contingency Cost | 1.92 | 0 | 0% | 0%
Total | 108.52 | 35.8235 | 33.01% | 33.01%
Pariculars | 31.08.2024 as per Bill Tally (inclusive of GST) | CA Certificate till 30.09.2024 | Difference b/w bills of 31.08.2024 & CA Certificate | Difference of Cost incurred as %age of cost incurred as on 31.08.2024 & CA Certificate
Land Cost | 23.2984 | 23.3 | 0 | 0%
Construction Cost of Sale Building | 11.4892 | 11.48 | 0.01 | 0.02791%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 0 | 0 | 0 | 0%
Architect Cost, RCC & other Professional fees | 0.097375 | 0.72 | 0.13344 | 0.3725%
Administrative Expenses | 0.69807
Marketing Expences | 0.057992
Interest Cost | 0.18253 | 0.18 | 0 | 0%
Contingency Cost | 0 | 0 | 0 | 0%
Total | 35.8235 | 35.68 | 0.14 | 0.3908%

## Summary Sheet
Sr. No. | Particulars | Incurred Cost in ` till 31.08.2024 | Incurred Cost in ` Cr. Till 31.08.2024 | Incurred Cost in ` till 31.12.2022 | Incurred Cost in ` Cr. Till 31.12.2022 | Balance | Balance in Cr.
1 | Land Cost | 232983640 | 23.2984 |  |  | 232983640 | 23.2984
2 | Construction Cost | 114892025 | 11.4892 |  |  | 114892025 | 11.4892 | 127278700 | 90.2681
3 | Approval Cost | 0 | 0 |  |  | 0 | 0
4 | Professional Cost | 973748 | 0.097375 |  |  | 973748 | 0.097375
5 | Admin Cost | 6980694 | 0.69807 |  |  | 6980694 | 0.69807
6 | Marketing Cost | 579924 | 0.057992 |  |  | 579924 | 0.057992
7 | Interest Cost | 1825344 | 0.18253 |  |  | 1825344 | 0.18253
| Total | 358235375 | 35.8235 | 0 | 0 | 358235375 | 35.8235
120400000
118574656
|  | 123426391 | 12.3426 |  |  | 123426391 | 12.3426

## Land, Stamp Duty and rent cost
Land Cost (Including SD & RF)
Sr. No. | Agreement Name | Date | Particulars | Amount | Incurred Amount
1 | Development Agreement | 2024-05-01 | Purchase Cost | 220000000 | 220000000
2 |  |  | Stamp Duty | 12950600 | 12950600
3 |  |  | Reg. Fees | 30000 | 30000
4 |  |  |  | 1760 | 1760
5 | Power of Attorney | 2024-05-01 | Stamp Duty | 500 | 500
6 |  |  | Reg. Fees | 680 | 680
7 |  |  |  | 100 | 100
| TOTAL |  |  | 232983640 | 232983640

## Construction
Date | Particulars | Voucher Type | Supplier Invoice No. | GSTIN/UIN | Gross Total | CGST | SGST | Round | Purchase (Blossom C&D) | Other Cost | IGST | Transportation Cost
2024-04-01 | Ultratech Cement Limited | Purchase | 8310946556 | 27AAACL6442L1ZA | 117216 | 12820.5 | 12820.5 |  | 91575
2024-04-01 | Ultratech Cement Limited | Purchase | 8310946557 | 27AAACL6442L1ZA | 58784 | 6429.5 | 6429.5 |  | 45925
2024-04-01 | BECS Coating | Purchase | 005/24-25 | 27AZFPS5857B1Z4 | 17388 | 1326.21 | 1326.21 | -0.02 | 14735.6
2024-04-05 | Pramanik Centre | Purchase | 1 | 27ABJPJ5084F1ZJ | 4500 | 322.24 | 322.24 | -0.02 | 3855.54
2024-04-06 | Vardhaman Enterprises | Purchase | 24-25/APR/BLK/03 | 27AARFV6828L1Z7 | 141781 | 7595.43 | 7595.43 | -0.32 | 126590.46
2024-04-07 | Meera Corporation | Purchase | 679 | 27ACQPG6852L1ZY | 53550 | 1275 | 1275 |  | 51000
2024-04-07 | Meera Corporation | Purchase | 678 | 27ACQPG6852L1ZY | 59922 | 1426.73 | 1426.73 | -0.46 | 57069
2024-04-08 | Ultratech Cement Limited | Purchase | 8303445801 | 27AAACL6442L1ZA | 79360 | 8680 | 8680 |  | 62000
2024-04-08 | BECS Coating | Purchase | 075/24-25 | 27AZFPS5857B1Z4 | 56819 | 4333.68 | 4333.68 | -0.36 | 48152
2024-04-09 | Ultratech Cement Limited | Purchase | 8303445869 | 27AAACL6442L1ZA | 79360 | 8680 | 8680 |  | 62000
2024-04-11 | Shri Gurudev Electricals | Purchase | 69 2024/25 | 27ATLPS9954M1ZH | 13767 | 1049.99 | 1049.99 | 0.46 | 11666.56
2024-04-15 | Nilkanth Associate | Purchase | 05 | 27ALUPP8078Q1ZM | 24098 | 573.75 | 573.75 | 0.5 | 22950
2024-04-15 | Shivam Stone | Purchase | SS/24-25/012 | 27ABPPM2467B1ZL | 8400 | 200 | 200 |  | 8000
2024-04-19 | Bharti Electric & Hardware Stores | Purchase | 43 | 27AKQPM1737L1ZL | 1159 | 88.38 | 88.38 | 0.24 | 982
2024-04-20 | Bansari Steel Traders | Purchase | 07/24-25 | 27ABDPS0174K1ZG | 1457091 | 111134.03 | 111134.03 | 0.44 | 1234822.5
2024-04-27 | Vardhaman Enterprises | Purchase | 24-25/APR/BLK/07 | 27AARFV6828L1Z7 | 156193 | 8367.5 | 8367.5 | -0.22 | 139458.22
2024-04-28 | Meera Corporation | Purchase | 717 | 27ACQPG6852L1ZY | 33045 | 2520.36 | 2520.36 | 0.28 | 28004
2024-04-28 | National Marble & Granites | Purchase | 37 | 27AYBPM9767H1ZV | 75009 | 5721.03 | 5721.03 | -0.06 | 63567
2024-04-29 | JSW Cement Limited | Purchase | MH2403015275 | 27AABCJ6731B1ZW | 125750 | 2994.05 | 2994.05 |  | 119761.9
2024-04-29 | JSW Cement Limited | Purchase | MH2403015267 | 27AABCJ6731B1ZW | 125750 | 2994.05 | 2994.05 |  | 119761.9
2024-04-29 | Pramanik Centre | Purchase | 12 | 27ABJPJ5084F1ZJ | 3000 | 228.81 | 228.81 |  | 2542.38
2024-04-30 | M.M. Transport | Purchase | 110 |  | 30240 |  |  |  | 30240
2024-04-30 | Patil Transport Co. | Purchase | 014/24-25 | 27ANQPP9895H2ZT | 76495 | 1821.3 | 1821.3 | 0.4 | 72852
2024-04-30 | Vardhaman Enterprises | Purchase | 24-25/APR/BLK/09 | 27AARFV6828L1Z7 | 86250 | 6578.39 | 6578.39 |  | 73093.22
2024-04-30 | Hari Om Transport Co. | Purchase | 30 |  | 32350 |  |  |  | 32350
2024-04-30 | Hari Om Transport Co. | Purchase | 31 |  | 29100 |  |  |  | 29100
2024-05-01 | Meera Corporation | Purchase | 724 | 27ACQPG6852L1ZY | 13395 | 1021.64 | 1021.64 | 0.12 | 11351.6
2024-05-01 | MD Azizul Haque Water Supply | Purchase | 176 |  | 7600 |  |  |  | 7600
2024-05-02 | Ultratech Cement Limited | Purchase | 8310953157 | 27AAACL6442L1ZA | 91200 | 9975 | 9975 |  | 71250
2024-05-06 | Ultratech Cement Limited | Purchase | 8310954085 | 27AAACL6442L1ZA | 113280 | 12390 | 12390 |  | 88500
2024-05-06 | Ultratech Cement Limited | Purchase | 8310954086 | 27AAACL6442L1ZA | 75520 | 8260 | 8260 |  | 59000
2024-05-06 | Ultratech Cement Limited | Purchase | 8310954089 | 27AAACL6442L1ZA | 113280 | 12390 | 12390 |  | 88500
2024-05-06 | Ultratech Cement Limited | Purchase | 8310954090 | 27AAACL6442L1ZA | 75520 | 8260 | 8260 |  | 59000
2024-05-10 | Vardhaman Enterprises | Purchase | 24-25/MAY/BLK/08 | 27AARFV6828L1Z7 | 52300 | 3988.99 | 3988.99 | -0.01 | 44322.03
2024-05-12 | National Marble & Granites | Purchase | 63 | 27AYBPM9767H1ZV | 39803 | 3035.79 | 3035.79 | 0.42 | 33731
2024-05-13 | National Marble & Granites | Purchase | 65 | 27AYBPM9767H1ZV | 29172 | 2224.98 | 2224.98 | 0.04 | 24722
2024-05-14 | JSW Cement Limited | Purchase | MH2403023651 | 27AABCJ6731B1ZW | 128375 | 3056.55 | 3056.55 |  | 122261.9
2024-05-15 | Nilkanth Associate | Purchase | 22 | 27ALUPP8078Q1ZM | 36400 | 1950 | 1950 |  | 32500
2024-05-15 | Nilkanth Associate | Purchase | 23 | 27ALUPP8078Q1ZM | 57670 | 1373.1 | 1373.1 | -0.2 | 54924
2024-05-15 | Shivam Stone | Purchase | SS/24-25/073 | 27ABPPM2467B1ZL | 48720 | 1160 | 1160 |  | 46400
2024-05-16 | Ultratech Cement Limited | Purchase | 8310956522 | 27AAACL6442L1ZA | 192000 | 21000 | 21000 |  | 150000
2024-05-16 | Meera Corporation | Purchase | 763 | 27ACQPG6852L1ZY | 95813 | 2281.26 | 2281.26 | -0.02 | 91250.5
2024-05-20 | New Baaj Water Suppliers | Purchase | 119 |  | 93000 |  |  |  | 93000
2024-05-20 | Shri Gurudev Electricals | Purchase | 209 2024/25 | 27ATLPS9954M1ZH | 30600 | 2333.87 | 2333.87 | 0.42 | 25931.84
2024-05-20 | Shri Gurudev Electricals | Purchase | 211 2024/25 | 27ATLPS9954M1ZH | 36239 | 2764.03 | 2764.03 | -0.4 | 30711.34
2024-05-23 | Bansari Steel Traders | Purchase | 016/24-25 | 27ABDPS0174K1ZG | 1625692 | 123993.45 | 123993.45 | 0.1 | 1377705
2024-05-23 | Naresh Plywood & Timber Mart | Purchase | 395/24-25 | 27ABKPJ4778P1ZQ | 5619 | 428.55 | 428.55 | 0.28 | 4761.62
2024-05-27 | JSW Cement Limited | Purchase | MH2403030403 | 27AABCJ6731B1ZW | 128375 | 3056.55 | 3056.55 |  | 122261.9
2024-05-27 | JSW Cement Limited | Purchase | MH2403030349 | 27AABCJ6731B1ZW | 128375 | 3056.55 | 3056.55 |  | 122261.9
2024-05-28 | Ritezone Chemcon India Limited | Purchase | 24-25/TI/0163 | 27AAHCR2348Q1ZQ | 30798 | 2349 | 2349 |  | 26100
2024-05-28 | Ritezone Chemcon India Limited | Purchase | 24-25/TI/0162 | 27AAHCR2348Q1ZQ | 30798 | 2349 | 2349 |  | 26100
2024-05-28 | Ashtech India Pvt Limited | Purchase | 272425MU12469 | 27AAECA4133B1ZA | 126798 | 6792.75 | 6792.75 |  | 113212.5
2024-05-29 | Bansari Steel Traders | Purchase | 019/24-25 | 27ABDPS0174K1ZG | 93810 | 7155 | 7155 |  | 79500
2024-05-29 | M.M. Transport | Purchase | 114 |  | 90720 |  |  |  | 90720
2024-05-29 | Shri Gurudev Electricals | Purchase | 265 2024/25 | 27ATLPS9954M1ZH | 3422 | 260.98 | 260.98 | 0.24 | 2899.8
2024-05-29 | Shri Gurudev Electricals | Purchase | 271 2024/25 | 27ATLPS9954M1ZH | 2218 | 169.2 | 169.2 | -0.4 | 1880
2024-05-31 | Maheshkumar Hasmukhlal & Co. | Purchase | 98/2024-25 | 27AAAFM4291P1ZS | 1603467 | 122298.3 | 122298.3 | 0.4 | 1358870
2024-05-31 | Patil Transport Co. | Purchase | 031/24-25 | 27ANQPP9895H2ZT | 24091 | 573.6 | 573.6 | -0.2 | 22944
2024-05-31 | Meera Corporation | Purchase | 791 | 27ACQPG6852L1ZY | 55716 | 1326.58 | 1326.58 | -0.16 | 53063
2024-05-31 | Meera Corporation | Purchase | 792 | 27ACQPG6852L1ZY | 49350 | 1175 | 1175 |  | 47000
2024-05-31 | Nilkanth Associate | Purchase | 34 | 27ALUPP8078Q1ZM | 43873 | 1044.6 | 1044.6 | -0.2 | 41784
2024-06-01 | Shri Gurudev Electricals | Purchase | 280 2024/25 | 27ATLPS9954M1ZH | 22190 | 1692.45 | 1692.45 | 0.1 | 18805
2024-06-04 | Jai Laxmi Trading | Purchase | JLT/24-25/122 | 27AHGPP5479B1Z5 | 1590109 | 121279.5 | 121279.5 | 0.07 | 1347549.93
2024-06-06 | S. S. Transport | Purchase | 004 |  | 264600 |  |  |  | 264600
2024-06-06 | Shri Gurudev Electricals | Purchase | 307 2024/25 | 27ATLPS9954M1ZH | 93803 | 7154.46 | 7154.46 | 0.08 | 79494
2024-06-07 | Ultratech Cement Limited | Purchase | 8310962569 | 27AAACL6442L1ZA | 94400 | 10325 | 10325 |  | 73750
2024-06-10 | Jai Laxmi Trading | Purchase | JLT/24-25/130 | 27AHGPP5479B1Z5 | 1279672 | 97602.12 | 97602.12 | -0.24 | 1084468
2024-06-10 | Shri Gurudev Electricals | Purchase | 328 2024/25 | 27ATLPS9954M1ZH | 31154 | 2334.86 | 2334.86 | -0.22 | 26484.5
2024-06-10 | Shri Gurudev Electricals | Purchase | 329 2024/25 | 27ATLPS9954M1ZH | 9324 | 711.18 | 711.18 | -0.36 | 7902
2024-06-10 | Hari Om Transport Co. | Purchase | 80 |  | 29050 |  |  |  | 29050
2024-06-10 | Hari Om Transport Co. | Purchase | 79 |  | 51750 |  |  |  | 51750
2024-06-11 | S. S. Transport | Purchase | 11 |  | 220500 |  |  |  | 220500
2024-06-12 | Shri Gurudev Electricals | Purchase | 341 2024/25 | 27ATLPS9954M1ZH | 76646 | 5845.87 | 5845.87 | 0.16 | 64954.1
2024-06-12 | Ultratech Cement Limited | Purchase | 8310963713 | 27AAACL6442L1ZA | 88000 | 9625 | 9625 |  | 68750
2024-06-14 | Vardhaman Enterprises | Purchase | 24-25/JUN/27 | 27AARFV6828L1Z7 | 88800 | 9712.5 | 9712.5 |  | 69375
2024-06-14 | Vardhaman Enterprises | Purchase | 24-25/JUN/26 | 27AARFV6828L1Z7 | 88800 | 9712.5 | 9712.5 |  | 69375
2024-06-15 | Jai Laxmi Trading | Purchase | JLT/24-25/137 | 27AHGPP5479B1Z5 | 1266795 | 96619.95 | 96619.95 | 0.1 | 1073555
2024-06-15 | Ultratech Cement Limited | Purchase | 8310964372 | 27AAACL6442L1ZA | 94400 | 10325 | 10325 |  | 73750
2024-06-15 | Ultratech Cement Limited | Purchase | 8310964370 | 27AAACL6442L1ZA | 94400 | 10325 | 10325 |  | 73750
2024-06-15 | Shri Gurudev Electricals | Purchase | 361 2024/25 | 27ATLPS9954M1ZH | 21433 | 1634.72 | 1634.72 | 0.06 | 18163.5
2024-06-15 | Shivam Stone | Purchase | SS/23-24/133 | 27ABPPM2467B1ZL | 67200 | 1600 | 1600 |  | 64000
2024-06-15 | Nilkanth Associate | Purchase | 49 | 27ALUPP8078Q1ZM | 88946 | 2117.76 | 2117.76 | 0.48 | 84710
2024-06-16 | Vardhaman Enterprises | Purchase | 24-25/JUN/40 | 27AARFV6828L1Z7 | 88800 | 9712.5 | 9712.5 |  | 69375
2024-06-16 | Vardhaman Enterprises | Purchase | 24-25/JUN/41 | 27AARFV6828L1Z7 | 88800 | 9712.5 | 9712.5 |  | 69375
2024-06-17 | Vardhaman Enterprises | Purchase | 24-25/JUN/43 | 27AARFV6828L1Z7 | 88800 | 9712.5 | 9712.5 |  | 69375
2024-06-17 | Vardhaman Enterprises | Purchase | 24-25/JUN/BLK/11 | 27AARFV6828L1Z7 | 18040 | 1375.92 | 1375.92 | 0.03 | 15288.13
2024-06-18 | Jai Laxmi Trading | Purchase | JLT/24-25/139 | 27AHGPP5479B1Z5 | 778977 | 59413.5 | 59413.5 |  | 660150
2024-06-18 | Shri Gurudev Electricals | Purchase | 376 2024/25 | 27ATLPS9954M1ZH | 10856 | 828 | 828 |  | 9200
2024-06-19 | Vardhaman Enterprises | Purchase | 24-25/JUN/48 | 27AARFV6828L1Z7 | 56000 | 6125 | 6125 |  | 43750
2024-06-22 | Shri Gurudev Electricals | Purchase | 402 2024/25 | 27ATLPS9954M1ZH | 3823 | 291.6 | 291.6 | -0.2 | 3240
2024-06-25 | Ultratech Cement Limited | Purchase | 8310966290 | 27AAACL6442L1ZA | 88000 | 9625 | 9625 |  | 68750
2024-06-27 | Ultratech Cement Limited | Purchase | 8310966747 | 27AAACL6442L1ZA | 94400 | 10325 | 10325 |  | 73750
2024-06-27 | National Marble & Granites | Purchase | 133 | 27AYBPM9767H1ZV | 6330 | 482.77 | 482.77 | 0.31 | 5364.15
2024-06-30 | M.M. Transport | Purchase | 120 |  | 30240 |  |  |  | 30240
2024-06-30 | M.M. Transport | Purchase | 121 |  | 60480 |  |  |  | 60480
2024-06-30 | Nilkanth Associate | Purchase | 051 | 27ALUPP8078Q1ZM | 82038 | 1953.28 | 1953.28 | 0.44 | 78131
2024-06-30 | Vardhaman Enterprises | Purchase | 24-25/JUN/BLK/20 | 27AARFV6828L1Z7 | 49970 | 3811.28 | 3811.28 | -0.02 | 42347.46
2024-06-30 | Vardhaman Enterprises | Purchase | 24-25/JUN/BLK/21 | 27AARFV6828L1Z7 | 127500 | 9724.58 | 9724.58 | -0.01 | 108050.85
2024-06-30 | Shivam Stone | Purchase | SS/24-25/157 | 27ABPPM2467B1ZL | 33600 | 800 | 800 |  | 32000
2024-06-30 | Patil Transport Co. | Purchase | 53/2024-25 | 27ANQPP9895H2ZT | 124677 | 2968.5 | 2968.5 |  | 118740
2024-06-30 | Hari Om Transport Co. | Purchase | 134 |  | 21500 |  |  |  | 21500
2024-07-02 | Jai Laxmi Trading | Purchase | JLT/24-25/157 | 27AHGPP5479B1Z5 | 1200067 | 91439.1 | 91439.1 | -0.07 | 1015990 | 1198.87
2024-07-02 | Shri Gurudev Electricals | Purchase | 451 2024/25 | 27ATLPS9954M1ZH | 9619 | 733.68 | 733.68 | -0.36 | 8152
2024-07-03 | Ultratech Cement Limited | Purchase | 8310967746 | 27AAACL6442L1ZA | 94400 | 10325 | 10325 |  | 73750
2024-07-03 | Jyoti India Kitchensink Pvt Ltd | Purchase | 4586/24-25 | 27AAECJ7000J1ZO | 5445 | 415.3 | 415.3 | -0.01 | 4614.41
2024-07-04 | BECS Coating | Purchase | 896/24-25 | 27AZFPS5857B1Z4 | 1726 | 131.61 | 131.61 | 0.48 | 762.3 | 700
2024-07-04 | BECS Coating | Purchase | 895/24-25 | 27AZFPS5857B1Z4 | 12495 | 297.5 | 297.5 |  | 11900
2024-07-04 | Shri Gurudev Electricals | Purchase | 461 2024/25 | 27ATLPS9954M1ZH | 76694 | 5849.55 | 5849.55 | -0.1 | 64995
2024-07-04 | Shri Gurudev Electricals | Purchase | 462 2024/25 | 27ATLPS9954M1ZH | 2866 | 218.61 | 218.61 | -0.22 | 2429
2024-07-05 | National Marble & Granites | Purchase | 148 | 27AYBPM9767H1ZV | 9346 | 712.8 | 712.8 | 0.4 | 7920
2024-07-05 | Vardhaman Enterprises | Purchase | 24-25/JUN/BLK/03 | 27AARFV6828L1Z7 | 142726 | 7646.02 | 7646.02 | 0.38 | 127433.58
2024-07-05 | Vardhaman Enterprises | Purchase | 24-25/JUL/BLK/02 | 27AARFV6828L1Z7 | 195500 | 14911.02 | 14911.02 | -0.01 | 165677.97
2024-07-06 | New Baaj Water Suppliers | Purchase | 143 |  | 46000 |  |  |  | 46000
2024-07-08 | JSW Cement Limited | Purchase | MH2403052925 | 27AABCJ6731B1ZW | 128375 | 3056.55 | 3056.55 |  | 122261.9
2024-07-08 | Ultratech Cement Limited | Purchase | 8310968764 | 27AAACL6442L1ZA | 91200 | 9975 | 9975 |  | 71250
2024-07-09 | Shri Gurudev Electricals | Purchase | 480 2024/25 | 27ATLPS9954M1ZH | 9593 | 731.7 | 731.7 | -0.4 | 8130
2024-07-09 | Hari Om Transport Co. | Purchase | 184 |  | 4350 |  |  |  | 4350
2024-07-10 | Bharti Electric & Hardware Stores | Purchase | 228 | 27AKQPM1737L1ZL | 2499 | 190.62 | 190.62 | -0.24 | 2118
2024-07-10 | UV Trading Corporation | Purchase | 2024-25/136 | 27AACFU6362P1ZI | 104076 | 7938 | 7938 |  | 85600 |  |  | 2600
2024-07-11 | Su-Dhara Sanitations Private Limited | Purchase | SSPL/24-25/466 | 09AAACS1782N1ZW | 154639 |  |  |  | 131050 |  | 23589
2024-07-12 | Shri Gurudev Electricals | Purchase | 505 2024/25 | 27ATLPS9954M1ZH | 16289 | 1242.36 | 1242.36 | 0.28 | 13804
2024-07-12 | Aqualuxe Bathware LLP | Purchase | 241 | 27ACEFA0372R1Z2 | 44418 | 3387.83 | 3387.83 | -0.24 | 37642.58
2024-07-12 | Aqualuxe Bathware LLP | Purchase | 242 | 27ACEFA0372R1Z2 | 36098 | 2753.21 | 2753.21 | 0.33 | 30591.25
2024-07-13 | Jai Laxmi Trading | Purchase | JLT/24-25/166 | 27AHGPP5479B1Z5 | 1190647 | 90721.35 | 90721.35 | -0.16 | 986015 | 1189.46 |  | 22000
2024-07-14 | Bharti Electric & Hardware Stores | Purchase | 225 | 27AKQPM1737L1ZL | 34668 | 2643.08 | 2643.08 | -0.16 | 29382
2024-07-15 | Shri Gurudev Electricals | Purchase | 516 2024/25 | 27ATLPS9954M1ZH | 69596 | 5308.2 | 5308.2 | -0.4 | 58980
2024-07-15 | Shivam Stone | Purchase | SS/24-25/195 | 27ABPPM2467B1ZL | 28728 | 684 | 684 |  | 27360
2024-07-15 | Nilkanth Associate | Purchase | 69 | 27ALUPP8078Q1ZM | 83028 | 1976.85 | 1976.85 | 0.3 | 79074
2024-07-16 | Ultratech Cement Limited | Purchase | 8310969899 | 27AAACL6442L1ZA | 84800 | 9275 | 9275 |  | 66250
2024-07-16 | UV Trading Corporation | Purchase | 2024-25/143 | 27AACFU6362P1ZI | 60711 | 4630.5 | 4630.5 |  | 48850 |  |  | 2600
2024-07-16 | Shri Gurudev Electricals | Purchase | 526 2024/25 | 27ATLPS9954M1ZH | 2183 | 166.5 | 166.5 |  | 1850
2024-07-16 | Aqualuxe Bathware LLP | Purchase | 251 | 27ACEFA0372R1Z2 | 7650 | 583.46 | 583.46 | 0.18 | 6032.9 |  |  | 450
2024-07-17 | Shri Nakoda Marble House | Purchase | 280 | 27AFUPJ9579E1ZM | 9752 | 743.79 | 743.79 | 0.02 | 8264.4
2024-07-17 | Bharti Electric & Hardware Stores | Purchase | 238 | 27AKQPM1737L1ZL | 11358 | 866.25 | 866.25 | 0.5 | 9625
2024-07-18 | Shri Gurudev Electricals | Purchase | 533 2024/25 | 27ATLPS9954M1ZH | 8921 | 680.4 | 680.4 | 0.2 | 7560
2024-07-18 | Pramanik Centre | Purchase | 56 | 27ABJPJ5084F1ZJ | 6040 | 322.38 | 322.38 |  | 5395.24
2024-07-19 | Aqualuxe Bathware LLP | Purchase | 262 | 27ACEFA0372R1Z2 | 951 | 72.54 | 72.54 | -0.05 | 705.97 |  |  | 100
2024-07-20 | Shri Gurudev Electricals | Purchase | 551 2024/25 | 27ATLPS9954M1ZH | 55471 | 4230.81 | 4230.81 | 0.38 | 47009
2024-07-20 | Jai Laxmi Trading | Purchase | JLT/24-25/173 | 27AHGPP5479B1Z5 | 1174524 | 89492.86 | 89492.86 | -0.07 | 976365 | 1173.35 |  | 18000
2024-07-22 | Shri Gurudev Electricals | Purchase | 572 2024/25 | 27ATLPS9954M1ZH | 9676 | 738 | 738 |  | 8200
2024-07-23 | Shri Nakoda Marble House | Purchase | 299 | 27AFUPJ9579E1ZM | 50917 | 3883.5 | 3883.5 |  | 43150
2024-07-25 | JSW Cement Limited | Purchase | MH2403062181 | 27AABCJ6731B1ZW | 128375 | 3056.55 | 3056.55 |  | 122261.9
2024-07-26 | Jai Laxmi Trading | Purchase | JLT/24-25/180 | 27AHGPP5479B1Z5 | 1137789 | 86693.86 | 86693.86 | -0.37 | 945490 | 1136.65 |  | 17775
2024-07-27 | Ultratech Cement Limited | Purchase | 8985696110 | 27AAACL6442L1ZA | 86400 | 9450 | 9450 |  | 67500
2024-07-28 | Ultratech Cement Limited | Purchase | 8985696249 | 27AAACL6442L1ZA | 172800 | 18900 | 18900 |  | 135000
2024-07-30 | Bansari Steel Traders | Purchase | 037/24-25 | 27ABDPS0174K1ZG | 1081725 | 82504.44 | 82504.44 | 0.12 | 916716
2024-07-30 | Pallavi Ceramic and Granite | Purchase | OT/0108/2024-25 | 27AAJFP4017D1ZH | 42132 | 3213.45 | 3213.45 | 0.1 | 33705 |  |  | 2000
2024-07-30 | Aqualuxe Bathware LLP | Purchase | 296 | 27ACEFA0372R1Z2 | 64873 | 4947.93 | 4947.93 | 0.14 | 53777 |  |  | 1200
2024-07-31 | Jai Laxmi Trading | Purchase | JLT/24-25/187 | 27AHGPP5479B1Z5 | 799238 | 60897.96 | 60897.96 | -0.36 | 664440 | 798.44 |  | 12204
2024-07-31 | Natural Granimarmo | Purchase | 402 | 27AAYPC4128R1ZX | 106908 | 8154 | 8154 |  | 90600
2024-07-31 | Ketan Engineering Co. | Purchase | 49 | 27ABTPP2842H1Z7 | 90909 | 2164.5 | 2164.5 |  | 86580
2024-07-31 | Ketan Engineering Co. | Purchase | 50 | 27ABTPP2842H1Z7 | 72608 | 1728.75 | 1728.75 | 0.5 | 69150
2024-07-31 | Ketan Engineering Co. | Purchase | 51 | 27ABTPP2842H1Z7 | 11738 | 628.8 | 628.8 | 0.4 | 10480
2024-07-31 | M.M. Transport | Purchase | 122 |  | 60480 |  |  |  | 60480
2024-07-31 | Nilkanth Associate | Purchase | 76 | 27ALUPP8078Q1ZM | 18963 | 451.5 | 451.5 |  | 18060
2024-07-31 | Hari Om Transport Co. | Purchase | 183 |  | 38150 |  |  |  | 38150
2024-08-01 | Shri Gurudev Electricals | Purchase | 628 2024/25 | 27ATLPS9954M1ZH | 4458 | 340.01 | 340.01 | 0.08 | 3777.9
2024-08-02 | Maheshkumar Hasmukhlal & Co. | Purchase | 171/2024-25 | 27AAAFM4291P1ZS | 1159203 | 88413.81 | 88413.81 | -0.22 | 982375.6
2024-08-02 | Shri Gurudev Electricals | Purchase | 629 2024/25 | 27ATLPS9954M1ZH | 1936 | 147.69 | 147.69 | -0.38 | 1641
2024-08-02 | Nilkanth Associate | Purchase | 81 | 27ALUPP8078Q1ZM | 84742 | 2017.68 | 2017.68 | -0.36 | 80707
2024-08-05 | UV Trading Corporation | Purchase | 2024-25/168 | 27AACFU6362P1ZI | 78765 | 6007.5 | 6007.5 |  | 64150 |  |  | 2600
2024-08-06 | Shri Gurudev Electricals | Purchase | 648 2024/25 | 27ATLPS9954M1ZH | 127369 | 9714.6 | 9714.6 | -0.2 | 107940
2024-08-06 | Vardhaman Enterprises | Purchase | 24-25/AUG/BLK/01 | 27AARFV6828L1Z7 | 144118 | 7720.58 | 7720.58 | 0.5 | 128676.34
2024-08-06 | Shri Gurudev Electricals | Purchase | 650 2024/25 | 27ATLPS9954M1ZH | 871 | 66.46 | 66.46 | -0.37 | 738.45
2024-08-06 | RK Aluminium | Purchase | 000504 | 27AAHFR0173J1Z3 | 39352 | 3001.4 | 3001.4 | 0.3 | 32948.9 |  |  | 400
2024-08-07 | Jai Laxmi Trading | Purchase | JLT/24-25/196 | 27AHGPP5479B1Z5 | 1175861 | 89594.73 | 89594.73 | -0.15 | 972980 | 1174.69 |  | 22517
2024-08-07 | Naresh Plywood & Timber Mart | Purchase | 1069/24-25 | 27ABKPJ4778P1ZQ | 4838 | 369 | 369 |  | 4000 |  |  | 100
2024-08-08 | JSW Cement Limited | Purchase | MH2403071452 | 27AABCJ6731B1ZW | 128375 | 3056.55 | 3056.55 |  | 122261.9
2024-08-08 | JSW Cement Limited | Purchase | MH2403071405 | 27AABCJ6731B1ZW | 128375 | 3056.55 | 3056.55 |  | 122261.9
2024-08-08 | Shri Nakoda Marble House | Purchase | 341 | 27AFUPJ9579E1ZM | 8526 | 650.25 | 650.25 | 0.5 | 7225
2024-08-09 | Ultratech Cement Limited | Purchase | 8310974384 | 27AAACL6442L1ZA | 172800 | 18900 | 18900 |  | 135000
2024-08-09 | Ultratech Cement Limited | Purchase | 8310974375 | 27AAACL6442L1ZA | 172800 | 18900 | 18900 |  | 135000
2024-08-09 | Shri Gurudev Electricals | Purchase | 668 2024/25 | 27ATLPS9954M1ZH | 4014 | 306.18 | 306.18 | -0.36 | 3402
2024-08-11 | UV Trading Corporation | Purchase | 2024-25/170 | 27AACFU6362P1ZI | 91922 | 7011 | 7011 |  | 75300 |  |  | 2600
2024-08-12 | Dubans Construction Chemical | Purchase | DC/2425/766 | 27AOCPD5951R1ZG | 23010 | 1755 | 1755 |  | 19500
2024-08-13 | Bharti Electric & Hardware Stores | Purchase | 294 | 27AKQPM1737L1ZL | 20314 | 1549.35 | 1549.35 | 0.3 | 17215
2024-08-14 | Shri Nakoda Marble House | Purchase | 367 | 27AFUPJ9579E1ZM | 17924 | 1367.1 | 1367.1 | -0.2 | 15190
2024-08-14 | Shri Gurudev Electricals | Purchase | 741 2024/25 | 27ATLPS9954M1ZH | 3847 | 293.4 | 293.4 | 0.2 | 3260
2024-08-15 | Nilkanth Associate | Purchase | 86 | 27ALUPP8078Q1ZM | 81530 | 1941.2 | 1941.2 | -0.4 | 77648
2024-08-15 | Nilkanth Associate | Purchase | 87 | 27ALUPP8078Q1ZM | 88946 | 2117.76 | 2117.76 | 0.48 | 84710
2024-08-15 | Shivam Stone | Purchase | SS/24-25/248 | 27ABPPM2467B1ZL | 28728 | 684 | 684 |  | 27360
2024-08-16 | Shri Gurudev Electricals | Purchase | 750 2024/25 | 27ATLPS9954M1ZH | 4366 | 333 | 333 |  | 3700
2024-08-16 | Shri Gurudev Electricals | Purchase | 748 2024/25 | 27ATLPS9954M1ZH | 2974 | 226.8 | 226.8 | 0.4 | 2520
2024-08-16 | Ultratech Cement Limited | Purchase | 8310975762 | 27AAACL6442L1ZA | 83200 | 9100 | 9100 |  | 65000
2024-08-16 | Shri Gurudev Electricals | Purchase | 746 2024/25 | 27ATLPS9954M1ZH | 6063 | 462.42 | 462.42 | 0.16 | 5138
2024-08-16 | Vardhaman Enterprises | Purchase | 24-25/AUG/BLK/03 | 27AARFV6828L1Z7 | 137873 | 7386.07 | 7386.07 | -0.39 | 123101.25
2024-08-17 | Bharti Electric & Hardware Stores | Purchase | 243 | 27AKQPM1737L1ZL | 590 | 45 | 45 |  | 500
2024-08-17 | Shri Gurudev Electricals | Purchase | 753 2024/25 | 27ATLPS9954M1ZH | 4130 | 315 | 315 |  | 3500
2024-08-17 | Shri Gurudev Electricals | Purchase | 712 2024/25 | 27ATLPS9954M1ZH | 2360 | 180 | 180 |  | 2000
2024-08-17 | Raj Steel Centre | Purchase | 468 | 27ALHPS0523Q1ZM | 8833 | 673.74 | 673.74 | -0.48 | 6586 |  |  | 900
2024-08-19 | Shiv Ply and Wood | Purchase | 162 | 27AAOFS4874J1ZF | 84362 | 6434.42 | 6434.42 | -0.44 | 71493.6
2024-08-20 | Naresh Plywood & Timber Mart | Purchase | 1164/24-25 | 27ABKPJ4778P1ZQ | 32450 | 2475 | 2475 |  | 27400 |  |  | 100
2024-08-20 | Shri Gurudev Electricals | Purchase | 777 2024/25 | 27ATLPS9954M1ZH | 2078 | 158.47 | 158.47 | 0.26 | 1760.8
2024-08-20 | RK Aluminium | Purchase | 000454 | 27AAHFR0173J1Z3 | 134006 | 10220.76 | 10220.76 | 0.48 | 112364 |  |  | 1200
2024-08-20 | Shiv Ply and Wood | Purchase | 164 | 27AAOFS4874J1ZF | 53808 | 4104 | 4104 |  | 45600
2024-08-20 | Vardhaman Enterprises | Purchase | 24-25/AUG/BLK/04 | 27AARFV6828L1Z7 | 154887 | 8297.52 | 8297.52 |  | 138291.96
2024-08-21 | Ultratech Cement Limited | Purchase | 8310977183 | 27AAACL6442L1ZA | 66560 | 7280 | 7280 |  | 52000
2024-08-21 | Sanjay Engineers | Purchase | SE/517/24-25 | 27ADLPR6941B1ZD | 847948 | 64674 | 64674 |  | 718600
2024-08-22 | Ultratech Cement Limited | Purchase | 8310977358 | 27AAACL6442L1ZA | 169600 | 18550 | 18550 |  | 132500
2024-08-22 | Ultratech Cement Limited | Purchase | 8310977360 | 27AAACL6442L1ZA | 169600 | 18550 | 18550 |  | 132500
2024-08-23 | Ultratech Cement Limited | Purchase | 8310977572 | 27AAACL6442L1ZA | 83200 | 9100 | 9100 |  | 65000
2024-08-23 | UV Trading Corporation | Purchase | 2024-25/2024 | 27AACFU6362P1ZI | 82636 | 6318 | 6318 |  | 67400 |  |  | 2600
2024-08-24 | Jai Laxmi Trading | Purchase | JLT/24-25/214 | 27AHGPP5479B1Z5 | 1122416 | 85522.5 | 85522.5 | -0.3 | 932160 | 1121.3 |  | 18090
2024-08-24 | National Marble & Granites | Purchase | 230 | 27AYBPM9767H1ZV | 6050 | 461.43 | 461.43 | 0.14 | 5127
2024-08-26 | Bansari Steel Traders | Purchase | 045/24-25 | 27ABDPS0174K1ZG | 1418466 | 108188.1 | 108188.1 | -0.2 | 1202090
2024-08-26 | Naresh Plywood & Timber Mart | Purchase | 1216/24-25 | 27ABKPJ4778P1ZQ | 15930 | 1215 | 1215 |  | 13500
2024-08-26 | Burhani Glass House | Purchase | 234 | 27ADAPT0607M1ZG | 40892 | 3118.86 | 3118.86 | 0.28 | 34654
2024-08-27 | Jai Laxmi Trading | Purchase | JLT/24-25/216 | 27AHGPP5479B1Z5 | 1111355 | 84679.65 | 84679.65 | 0.46 | 922885 | 1110.24 |  | 18000
2024-08-27 | Shri Gurudev Electricals | Purchase | 815 2024/25 | 27ATLPS9954M1ZH | 26629 | 1824.48 | 1824.48 | -0.24 | 22980.28
2024-08-29 | National Marble & Granites | Purchase | 235 | 27AYBPM9767H1ZV | 9086 | 693 | 693 |  | 7700
2024-08-30 | Shri Gurudev Electricals | Purchase | 841 2024/25 | 27ATLPS9954M1ZH | 6783 | 517.32 | 517.32 | 0.36 | 5748
2024-08-30 | Vardhaman Enterprises | Purchase | 24-25/AUG/BLK/09 | 27AARFV6828L1Z7 | 140133 | 7507.1 | 7507.1 | 0.32 | 125118.48
2024-08-31 | Jai Laxmi Trading | Purchase | JLT/24-25/225 | 27AHGPP5479B1Z5 | 711608 | 54220.95 | 54220.95 | 0.2 | 602455 | 710.9
2024-08-31 | M.M. Transport | Purchase | 123 |  | 106176 |  |  |  | 106176
2024-08-31 | M.M. Transport | Purchase | 124 |  | 60480 |  |  |  | 60480
2024-08-31 | Nilkanth Associate | Purchase | 91 | 27ALUPP8078Q1ZM | 71119 | 1693.3 | 1693.3 | 0.4 | 67732
2024-08-31 | Shivam Stone | Purchase | SS/24-25/275 | 27ABPPM2467B1ZL | 26880 | 640 | 640 |  | 25600
2024-08-31 | National Marble & Granites | Purchase | 237 | 27AYBPM9767H1ZV | 9670 | 737.55 | 737.55 | -0.1 | 8195
2024-08-31 | Patil Transport Co. | Purchase | 87/2024-25 | 27ANQPP9895H2ZT | 163565 | 3894.4 | 3894.4 | 0.2 | 155776
2024-08-31 | Hari Om Transport Co. | Purchase | 222 |  | 55100 |  |  |  | 55100
2024-08-31 | Hari Om Transport Co. | Purchase | 223 |  | 11850 |  |  |  | 11850
2024-04-16 | Kiran Jadhav (Ramdas) | EXPENSES | . |  | 35228 |  |  |  | 35228
2024-05-07 | Mohak Labour Contract (Nilesh Raut) | EXPENSES | 045 |  | 1020000 |  |  |  | 1020000
2024-05-08 | Samiksha Pawar (Ramdas) | EXPENSES | . |  | 500000 |  |  |  | 500000
2024-05-08 | Ashok Bhanubhai Kalena HUF | EXPENSES | . |  | 871000 |  |  |  | 871000
2024-05-11 | Samarjeet Singh | EXPENSES | . |  | 515000 |  |  |  | 515000
2024-05-24 | Om Sai Enterprises (Vishwanath) | EXPENSES | . |  | 500000 |  |  |  | 500000
2024-05-24 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 57368 |  | 5200 |  |  |  | 5200
2024-05-28 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 57384 |  | 3200 |  |  |  | 3200
2024-06-01 | Maharashtra Rajya General Kamgar Mathadi and Trans. | EXPENSES | . |  | 22875 |  |  |  | 22875
2024-06-02 | Karan Corporation | EXPENSES | 01/2024-2025 | 27AARFK5984A1ZY | 1180000 | 90000 | 90000 |  | 1000000
2024-06-06 | Girishbhai Chandubhai Akola HUF | EXPENSES | . |  | 929500 |  |  |  | 929500
2024-06-10 | Prakash K Patel HUF | EXPENSES | 01/2024-2025 |  | 1875000 |  |  |  | 1875000
2024-06-10 | Avdhesh Kumar Rajpati Yadav | EXPENSES | 01/2024-2025 |  | 1875000 |  |  |  | 1875000
2024-06-20 | Karan Corporation | EXPENSES | 02/2024-2025 | 27AARFK5984A1ZY | 1380001 | 105254.28 | 105254.28 | 0.44 | 1169492
2024-07-20 | Vijay Laxmi Furniture Mart | EXPENSES | . |  | 75000 |  |  |  | 75000
2024-08-05 | Hemang K Shah HUF | EXPENSES | . |  | 1150000 |  |  |  | 1150000
2024-08-05 | Komal Keval Modi | EXPENSES | . |  | 1875000 |  |  |  | 1875000
2024-08-05 | Rahul Hasmukhlal Shah (HUF) | EXPENSES | . |  | 525000 |  |  |  | 525000
2024-08-08 | Ketan Navalchand Shah HUF | EXPENSES | . |  | 1040000 |  |  |  | 1040000
2024-08-08 | Jayesh Navalchand Shah | EXPENSES | . |  | 1060000 |  |  |  | 1060000
2024-08-10 | Popat Namdev Jankar | EXPENSES | 120 |  | 7000 |  |  |  | 7000
2024-08-16 | Satinand Jata Ray | EXPENSES | . |  | 1790000 |  |  |  | 1790000
2024-08-25 | Karan Corporation | EXPENSES | 03/2024-2025 | 27AARFK5984A1ZY | 2950000 | 225000 | 225000 |  | 2500000
2024-08-31 | Shiv Shakti Furniture | EXPENSES | . |  | 50000 |  |  |  | 50000
2023-11-21 | JSW Cement Limited | Purchase | MH2303106056 | 27AABCJ6731B1ZW | 123125 | 2931.55 | 2931.55 | -0.1 | 117262
2023-11-21 | JSW Cement Limited | Purchase | MH2303106053 | 27AABCJ6731B1ZW | 123125 | 2931.55 | 2931.55 |  | 117261.9
2023-11-21 | Ultratech Cement Limited | Purchase | 8310911570 | 27AAACL6442L1ZA | 126720 | 13860 | 13860 |  | 99000
2023-11-21 | Ultratech Cement Limited | Purchase | 8310911571 | 27AAACL6442L1ZA | 84480 | 9240 | 9240 |  | 66000
2023-11-21 | Ultratech Cement Limited | Purchase | 8310911679 | 27AAACL6442L1ZA | 42240 | 4620 | 4620 |  | 33000
2023-11-21 | Ultratech Cement Limited | Purchase | 8310911678 | 27AAACL6442L1ZA | 126720 | 13860 | 13860 |  | 99000
2023-11-24 | Ultratech Cement Limited | Purchase | 8310912147 | 27AAACL6442L1ZA | 42240 | 4620 | 4620 |  | 33000
2023-11-25 | Ask Agro | Purchase | AA/2023-24/166 | 27ASZPS8800R1ZC | 1434714 | 109427.37 | 109427.37 | -0.24 | 1215859.5
2023-11-25 | Bansari Steel Traders | Purchase | 43/2023-24 | 27ABDPS0174K1ZG | 27654 | 2109.24 | 2109.24 | -0.48 | 23436
2023-11-29 | Bansari Steel Traders | Purchase | 44/2023-24 | 27ABDPS0174K1ZG | 74812 | 5706 | 5706 |  | 63400
2023-11-30 | M.M. Transport | Purchase | 77 |  | 53088 |  |  |  | 53088
2023-11-30 | M.M. Transport | Purchase | 76 |  | 117535 |  |  |  | 117535
2023-11-30 | Patil Transport Co. | Purchase | 136 | 27ANQPP9895H2ZT | 55881 | 1330.5 | 1330.5 |  | 53220
2023-12-01 | MD Azizul Haque Water Supply | Purchase | 101 |  | 26000 |  |  |  | 26000
2023-12-03 | Shri Gurudev Electricals | Purchase | 1077/2023-24 | 27ATLPS9954M1ZH | 6835 | 521.28 | 521.28 | 0.44 | 5792
2023-12-05 | Ritezone Chemcon India Limited | Purchase | 23-24/TI/0624 | 27AAHCR2348Q1ZQ | 30798 | 2349 | 2349 |  | 26100
2023-12-05 | Ritezone Chemcon India Limited | Purchase | 23-24/TI/0623 | 27AAHCR2348Q1ZQ | 30798 | 2349 | 2349 |  | 26100
2023-12-07 | Vardhaman Enterprises | Purchase | 23-24/DEC/BLK/01 | 27AARFV6828L1Z7 | 176227 | 9440.74 | 9440.74 | -0.2 | 157345.72
2023-12-07 | Ultratech Cement Limited | Purchase | 8303434140 | 27AAACL6442L1ZA | 96768 | 10584 | 10584 |  | 75600
2023-12-08 | Hari Om Transport Co. | Purchase | 371 |  | 14300 |  |  |  | 14300
2023-12-08 | Hari Om Transport Co. | Purchase | 372 |  | 5500 |  |  |  | 5500
2023-12-09 | Om Steels | Purchase | 1569/23-24 | 27AAAFO6340H1ZD | 2225504 | 169741.8 | 169741.8 | 0.4 | 1886020
2023-12-12 | JSW Cement Limited | Purchase | MH2303118804 | 27AABCJ6731B1ZW | 123125 | 2931.55 | 2931.55 |  | 117261.9
2023-12-14 | Ask Agro | Purchase | AA/2023-24/194 | 27ASZPS8800R1ZC | 724101 | 55228.05 | 55228.05 | -0.1 | 613645
2023-12-14 | Vardhaman Enterprises | Purchase | 23-24/DEC/19 | 27AARFV6828L1Z7 | 194000 | 21218.75 | 21218.75 |  | 151562.5
2023-12-15 | Shivam Stone | Purchase | SS/339 | 27ABPPM2467B1ZL | 12852 | 306 | 306 |  | 12240
2023-12-18 | Vardhaman Enterprises | Purchase | 23-24/DEC/BLK/10 | 27AARFV6828L1Z7 | 161482 | 8650.8 | 8650.8 | 0.4 | 144180
2023-12-20 | MG Corporation | Purchase | 623/2023-24 | 27AAKHS9817H1ZJ | 2065878 | 157566.96 | 157566.96 | 0.08 | 1750744
2023-12-21 | Shri Gurudev Electricals | Purchase | 1118/2023-24 | 27ATLPS9954M1ZH | 25908 | 1976.05 | 1976.05 | -0.2 | 21956.1
2023-12-22 | Om Steels | Purchase | 1688/23-24 | 27AAAFO6340H1ZD | 2453337 | 187118.91 | 187118.91 | 0.18 | 2079099
2023-12-23 | Vardhaman Enterprises | Purchase | 23-24/DEC/BLK/15 | 27AARFV6828L1Z7 | 31640 | 2413.22 | 2413.22 |  | 26813.56
2023-12-27 | Vardhaman Enterprises | Purchase | 23-24/DEC/BLK/16 | 27AARFV6828L1Z7 | 171216 | 9172.28 | 9172.28 | 0.02 | 152871.42
2023-12-28 | Ask Agro | Purchase | AA/2023-24/208 | 27ASZPS8800R1ZC | 1329379 | 101393.3 | 101393.3 | 0.4 | 1126592
2023-12-28 | Ultratech Cement Limited | Purchase | 8310919742 | 27AAACL6442L1ZA | 76800 | 8400 | 8400 |  | 60000
2023-12-28 | Ultratech Cement Limited | Purchase | 8310919743 | 27AAACL6442L1ZA | 76800 | 8400 | 8400 |  | 60000
2023-12-28 | Ultratech Cement Limited | Purchase | 8310919740 | 27AAACL6442L1ZA | 115200 | 12600 | 12600 |  | 90000
2023-12-28 | Ultratech Cement Limited | Purchase | 8310919741 | 27AAACL6442L1ZA | 115200 | 12600 | 12600 |  | 90000
2023-12-31 | M.M. Transport | Purchase | 83 |  | 30240 |  |  |  | 30240
2023-12-31 | M.M. Transport | Purchase | 82 |  | 129690 |  |  |  | 129690
2023-12-31 | Hari Om Transport Co. | Purchase | 404 |  | 25050 |  |  |  | 25050
2023-12-31 | Hari Om Transport Co. | Purchase | 405 |  | 17600 |  |  |  | 17600
2023-12-31 | Patil Transport Co. | Purchase | 152 | 27ANQPP9895H2ZT | 104063 | 2477.7 | 2477.7 | -0.4 | 99108
2023-12-31 | Shivam Stone | Purchase | SS/358 | 27ABPPM2467B1ZL | 34902 | 831 | 831 |  | 33240
2024-01-01 | Bharti Electric & Hardware Stores | Purchase | 541 | 27AKQPM1737L1ZL | 3436 | 262.08 | 262.08 | -0.16 | 2912
2024-01-05 | Shri Gurudev Electricals | Purchase | 1231 2023/24 | 27ATLPS9954M1ZH | 17090 | 1303.46 | 1303.46 | 0.33 | 14482.75
2024-01-07 | JSW Cement Limited | Purchase | MH2303132714 | 27AABCJ6731B1ZW | 123125 | 2931.55 | 2931.55 |  | 117261.9
2024-01-07 | Meera Corporation | Purchase | 524 | 27ACQPG6852L1ZY | 18428 | 438.75 | 438.75 | 0.5 | 17550
2024-01-11 | Ultratech Cement Limited | Purchase | 8303437240 | 27AAACL6442L1ZA | 79360 | 8680 | 8680 |  | 62000
2024-01-12 | JSW Cement Limited | Purchase | MH2303134864 | 27AABCJ6731B1ZW | 123125 | 2931.55 | 2931.55 |  | 117261.9
2024-01-12 | Ultratech Cement Limited | Purchase | 8303437264 | 27AAACL6442L1ZA | 79360 | 8680 | 8680 |  | 62000
2024-01-12 | Ultratech Cement Limited | Purchase | 8303437265 | 27AAACL6442L1ZA | 119040 | 13020 | 13020 |  | 93000
2024-01-12 | Ultratech Cement Limited | Purchase | 8303437331 | 27AAACL6442L1ZA | 79360 | 8680 | 8680 |  | 62000
2024-01-12 | MD Azizul Haque Water Supply | Purchase | 103 |  | 19000 |  |  |  | 19000
2024-01-13 | Ultratech Cement Limited | Purchase | 8303437404 | 27AAACL6442L1ZA | 39680 | 4340 | 4340 |  | 31000
2024-01-19 | Maheshkumar Hasmukhlal & Co. | Purchase | 409/2023-24 | 27AAAFM4291P1ZS | 1859708 | 141842.15 | 141842.15 | -0.2 | 1576023.9
2024-01-19 | Vardhaman Enterprises | Purchase | 23-24/JAN/BLK/12 | 27AARFV6828L1Z7 | 138134 | 7400.06 | 7400.06 | -0.4 | 123334.28
2024-01-19 | Shri Gurudev Electricals | Purchase | 1381 2023/24 | 27ATLPS9954M1ZH | 35900 | 2738.11 | 2738.11 | 0.33 | 30423.45
2024-01-19 | JSW Cement Limited | Purchase | MH2303138680 | 27AABCJ6731B1ZW | 123125 | 2931.55 | 2931.55 |  | 117261.9
2024-01-19 | Shri Gurudev Electricals | Purchase | 1395 2023/24 | 27ATLPS9954M1ZH | 1770 | 135 | 135 |  | 1500
2024-01-20 | Ultratech Cement Limited | Purchase | 8310926282 | 27AAACL6442L1ZA | 76800 | 8400 | 8400 |  | 60000
2024-01-20 | Ultratech Cement Limited | Purchase | 8310926281 | 27AAACL6442L1ZA | 115200 | 12600 | 12600 |  | 90000
2024-01-20 | Pramanik Centre | Purchase | 174 | 27ABJPJ5084F1ZJ | 17200 | 1311.87 | 1311.87 | -0.03 | 14576.29
2024-01-21 | Pramanik Centre | Purchase | 175 | 27ABJPJ5084F1ZJ | 61311 | 4676.28 | 4676.28 | -0.28 | 51958.72
2024-01-21 | Ritezone Chemcon India Limited | Purchase | 23-24/TI/0770 | 27AAHCR2348Q1ZQ | 30798 | 2349 | 2349 |  | 26100
2024-01-21 | Ritezone Chemcon India Limited | Purchase | 23-24/TI/0771 | 27AAHCR2348Q1ZQ | 30798 | 2349 | 2349 |  | 26100
2024-01-23 | JSW Cement Limited | Purchase | MH2303141025 | 27AABCJ6731B1ZW | 123125 | 2931.55 | 2931.55 |  | 117261.9
2024-01-29 | Vardhaman Enterprises | Purchase | 23-24/JAN/BLK/24 | 27AARFV6828L1Z7 | 177034 | 9483.94 | 9483.94 | 0.4 | 158065.72
2024-01-30 | Hari Om Transport Co. | Purchase | 450 |  | 29300 |  |  |  | 29300
2024-01-31 | JSW Cement Limited | Purchase | MH2303145064 | 27AABCJ6731B1ZW | 123125 | 2931.55 | 2931.55 |  | 117261.9
2024-01-31 | Ultratech Cement Limited | Purchase | 8303439012 | 27AAACL6442L1ZA | 92160 | 10080 | 10080 |  | 72000
2024-01-31 | M.M. Transport | Purchase | 85 |  | 75256 |  |  |  | 75256
2024-01-31 | M.M. Transport | Purchase | 84 |  | 106176 |  |  |  | 106176
2024-01-31 | Nilkanth Associate | Purchase | 226 | 27ALUPP8078Q1ZM | 68538 | 1631.86 | 1631.86 | 0.28 | 65274
2024-01-31 | Hari Om Transport Co. | Purchase | 451 |  | 22800 |  |  |  | 22800
2024-01-31 | Patil Transport Co. | Purchase | 172 | 27ANQPP9895H2ZT | 142027 | 3381.6 | 3381.6 | -0.2 | 135264
2024-02-01 | Ultratech Cement Limited | Purchase | 8303439106 | 27AAACL6442L1ZA | 92160 | 10080 | 10080 |  | 72000
2024-02-03 | Sanjay Engineers | Purchase | SE/1136/23-24 | 27ADLPR6941B1ZD | 2245 | 171.23 | 171.23 | -0.01 | 402.55 | 1500
2024-02-05 | BECS Coating | Purchase | 2890/23-24 | 27AZFPS5857B1Z4 | 4354 | 332.1 | 332.1 | -0.2 | 3390 |  |  | 300
2024-02-06 | Sanjay Engineers | Purchase | SE/1143/23-24 | 27ADLPR6941B1ZD | 20236 | 1543.43 | 1543.43 | -0.03 | 16949.17 |  |  | 200
2024-02-08 | MD Azizul Haque Water Supply | Purchase | 123 |  | 18000 |  |  |  | 18000
2024-02-09 | Maheshkumar Hasmukhlal & Co. | Purchase | 485/2023-24 | 27AAAFM4291P1ZS | 1788579 | 136417.03 | 136417.03 | 0.24 | 1515744.7
2024-02-13 | Vardhaman Enterprises | Purchase | 23-24/BLK/FEB/23 | 27AARFV6828L1Z7 | 137499 | 7588.48 | 7588.48 | -0.17 | 122322.21
2024-02-15 | Nilkanth Associate | Purchase | 241 | 27ALUPP8078Q1ZM | 43873 | 1044.6 | 1044.6 | -0.2 | 41784
2024-02-19 | Shri Gurudev Electricals | Purchase | 1567 2023/24 | 27ATLPS9954M1ZH | 1007 | 76.79 | 76.79 | 0.22 | 853.2
2024-02-19 | Shri Gurudev Electricals | Purchase | 1561 2023/24 | 27ATLPS9954M1ZH | 4661 | 355.5 | 355.5 |  | 3950
2024-02-20 | JSW Cement Limited | Purchase | MH2303156181 | 27AABCJ6731B1ZW | 125750 | 2994.05 | 2994.05 |  | 119761.9
2024-02-21 | Ultratech Cement Limited | Purchase | 8310935191 | 27AAACL6442L1ZA | 132160 | 14455 | 14455 |  | 103250
2024-02-21 | Ultratech Cement Limited | Purchase | 8310935124 | 27AAACL6442L1ZA | 151040 | 16520 | 16520 |  | 118000
2024-02-21 | M.M. Transport | Purchase | 96 |  | 79965 |  |  |  | 79965
2024-02-24 | Bharti Electric & Hardware Stores | Purchase | 641 | 27AKQPM1737L1ZL | 12860 | 980.82 | 980.82 | 0.36 | 10898
2024-02-24 | Bansari Steel Traders | Purchase | 061/23-24 | 27ABDPS0174K1ZG | 112248 | 8561.25 | 8561.25 | 0.5 | 95125
2024-02-28 | Shri Gurudev Electricals | Purchase | 1634/2023-24 | 27ATLPS9954M1ZH | 22939 | 1749.6 | 1749.6 | -0.2 | 19440
2024-02-29 | M.M. Transport | Purchase | 97 |  | 44962 |  |  |  | 44962
2024-02-29 | JSW Cement Limited | Purchase | MH2303161896 | 27AABCJ6731B1ZW | 125750 | 2994.05 | 2994.05 |  | 119761.9
2024-02-29 | Patil Transport Co. | Purchase | 191 | 27ANQPP9895H2ZT | 48182 | 1147.2 | 1147.2 | -0.4 | 45888
2024-02-29 | Hari Om Transport Co. | Purchase | 498 |  | 35600 |  |  |  | 35600
2024-02-29 | Hari Om Transport Co. | Purchase | 499 |  | 17450 |  |  |  | 17450
2024-02-29 | National Marble & Granites | Purchase | 405 | 27AYBPM9767H1ZV | 13434 | 1024.65 | 1024.65 | -0.3 | 11385
2024-02-29 | Nilkanth Associate | Purchase | 253 | 27ALUPP8078Q1ZM | 24098 | 573.75 | 573.75 | 0.5 | 22950
2024-02-29 | Shivam Stone | Purchase | SS/452 | 27ABPPM2467B1ZL | 55608 | 1324 | 1324 |  | 52960
2024-03-04 | Shri Gurudev Electricals | Purchase | 1651/202-24 | 27ATLPS9954M1ZH | 12827 | 978.37 | 978.37 | -0.38 | 10870.64
2024-03-04 | BECS Coating | Purchase | 3211/23-24 | 27AZFPS5857B1Z4 | 6248 | 148.75 | 148.75 | 0.5 | 5950
2024-03-04 | BECS Coating | Purchase | 3210/23-24 | 27AZFPS5857B1Z4 | 48920 | 3731.2 | 3731.2 | -0.1 | 41457.7
2024-03-04 | MD Azizul Haque Water Supply | Purchase | 145 |  | 11000 |  |  |  | 11000
2024-03-04 | Pramanik Centre | Purchase | 196 | 27ABJPJ5084F1ZJ | 5000 | 381.35 | 381.35 |  | 4237.3
2024-03-04 | Pramanik Centre | Purchase | 197 | 27ABJPJ5084F1ZJ | 5000 | 381.35 | 381.35 |  | 4237.3
2024-03-04 | Ashtech India Pvt Limited | Purchase | 272324MU22683 | 27AAECA4133B1ZA | 128646 | 6891.75 | 6891.75 |  | 114862.5
2024-03-05 | Meera Corporation | Purchase | 629 | 27ACQPG6852L1ZY | 4316 | 329.19 | 329.19 |  | 3657.62
2024-03-05 | Meera Corporation | Purchase | 628 | 27ACQPG6852L1ZY | 5828 | 138.75 | 138.75 | 0.5 | 5550
2024-03-07 | Ultratech Cement Limited | Purchase | 8310939127 | 27AAACL6442L1ZA | 151040 | 16520 | 16520 |  | 118000
2024-03-07 | Ultratech Cement Limited | Purchase | 8310939250 | 27AAACL6442L1ZA | 113280 | 12390 | 12390 |  | 88500
2024-03-07 | Pramanik Centre | Purchase | 198 | 27ABJPJ5084F1ZJ | 7020 | 237.98 | 237.98 | -0.39 | 6544.43
2024-03-07 | Meera Corporation | Purchase | 633 | 27ACQPG6852L1ZY | 104396 | 2485.61 | 2485.61 | 0.28 | 99424.5
2024-03-07 | Dubans Construction Chemical | Purchase | DC/2324/1624 | 27AOCPD5951R1ZG | 93010 | 7093.98 | 7093.98 | 0.04 | 78822
2024-03-08 | Ultratech Cement Limited | Purchase | 8310939403 | 27AAACL6442L1ZA | 113280 | 12390 | 12390 |  | 88500
2024-03-08 | Shri Gurudev Electricals | Purchase | 1678 2023/24 | 27ATLPS9954M1ZH | 2950 | 225 | 225 |  | 2500
2024-03-09 | JSW Cement Limited | Purchase | MH2303166806 | 27AABCJ6731B1ZW | 125750 | 2994.05 | 2994.05 |  | 119761.9
2024-03-09 | JSW Cement Limited | Purchase | MH2303166977 | 27AABCJ6731B1ZW | 125750 | 2994.05 | 2994.05 |  | 119761.9
2024-03-11 | BECS Coating | Purchase | 3283/23-24 | 27AZFPS5857B1Z4 | 13230 | 315 | 315 |  | 12600
2024-03-13 | Ultratech Cement Limited | Purchase | 8310940675 | 27AAACL6442L1ZA | 185600 | 20300 | 20300 |  | 145000
2024-03-14 | National Marble & Granites | Purchase | 427 | 27AYBPM9767H1ZV | 28670 | 2186.66 | 2186.66 | 0.43 | 24296.25
2024-03-15 | Shivam Stone | Purchase | SS/480 | 27ABPPM2467B1ZL | 40656 | 968 | 968 |  | 38720
2024-03-16 | Meera Corporation | Purchase | 654 | 27ACQPG6852L1ZY | 7036 | 536.64 | 536.64 | 0.02 | 5962.7
2024-03-16 | National Marble & Granites | Purchase | 431 | 27AYBPM9767H1ZV | 15965 | 1217.7 | 1217.7 | -0.4 | 13530
2024-03-16 | Manordas Gopalji & Co | Purchase | 833/2023-24 | 27AAAFM4290N1ZX | 1255389 | 95749.98 | 95749.98 | 0.44 | 1063888.6
2024-03-17 | Vardhaman Enterprises | Purchase | 23-24/BLK/MAR/05 | 27AARFV6828L1Z7 | 9310 | 710.08 | 710.08 | 0.01 | 7889.83
2024-03-27 | Manordas Gopalji & Co | Purchase | 867/2023-24 | 27AAAFM4290N1ZX | 1230989 | 93888.96 | 93888.96 | 0.48 | 1043210.6
2024-03-28 | Ashtech India Pvt Limited | Purchase | 272324MU22888 | 27AAECA4133B1ZA | 121422 | 6504.75 | 6504.75 |  | 108412.5
2024-03-30 | National Marble & Granites | Purchase | 447 | 27AYBPM9767H1ZV | 15138 | 1154.61 | 1154.61 | -0.22 | 12829
2024-03-31 | M.M. Transport | Purchase | 105 |  | 79965 |  |  |  | 79965
2024-03-31 | Nilkanth Associate | Purchase | 265 | 27ALUPP8078Q1ZM | 58637 | 1396.13 | 1396.13 | -0.26 | 55845
2024-03-31 | M.M. Transport | Purchase | 106 |  | 30240 |  |  |  | 30240
2024-03-31 | Patil Transport Co. | Purchase | 211 | 27ANQPP9895H2ZT | 72274 | 1720.8 | 1720.8 | 0.4 | 68832
2024-03-31 | Hari Om Transport Co. | Purchase | 544 |  | 35650 |  |  |  | 35650
2024-03-31 | Hari Om Transport Co. | Purchase | 545 |  | 23700 |  |  |  | 23700
2024-02-01 | Yogesh V Soparkar | EXPENSES |  |  | 18350 |  |  |  | 18350
2024-02-01 | Yogesh V Soparkar | EXPENSES |  |  | 11270 |  |  |  | 11270
2024-02-09 | Yogesh V Soparkar | EXPENSES |  |  | 46555 |  |  |  | 46555
2024-03-01 | Prakash K Patel HUF | EXPENSES | 01/2023-2024 |  | 500000 |  |  |  | 500000
2024-03-05 | Avdhesh Kumar Rajpati Yadav | EXPENSES | 01/2023-2024 |  | 600000 |  |  |  | 600000
2024-03-11 | Avdhesh Kumar Rajpati Yadav | EXPENSES | 02/2023-2024 |  | 575000 |  |  |  | 575000
2024-03-14 | Shri Ram Traders | EXPENSES | 028 |  | 16678 |  |  |  | 16678
2024-03-15 | Prakash K Patel HUF | EXPENSES | 02/2023-2024 |  | 775000 |  |  |  | 775000
2024-03-20 | Prakash K Patel HUF | EXPENSES | 03/2023-24 |  | 150000 |  |  |  | 150000
2024-03-21 | Yogesh V Soparkar | EXPENSES | . |  | 3500 |  |  |  | 3500
2024-03-27 | Avdhesh Kumar Rajpati Yadav | EXPENSES | 03/2023-2024 |  | 600000 |  |  |  | 600000
2024-02-05 | Sanjay Engineers | Purchase | SE/1139/23-24 | 27ADLPR6941B1ZD | 1239 | 94.5 | 94.5 | 750 |  | 300
2024-03-30 | Sanjay Engineers | EXPENSES | SE/1349/23-24 | 27ADLPR6941B1ZD | 1416 | 108 | 108 | 1200
TOTAL |  |  |  |  | 85214275 | 4721379.87 | 4721379.87 | 1957.66 | 75585318.7 | 12113.9 | 23589 | 148536

## Professional
Date | Particulars | Voucher Type | Supplier Invoice No. | GSTIN/UIN | Gross Total | Basic Amount | CGST | SGST | Round
2024-04-01 | Landmark Consultants & Engg. Technology | EXPENSES | L-1456 | 27AVBPP6929K1Z1 | 897 | 760 | 68.4 | 68.4 | 0.2
2024-04-11 | Landmark Consultants & Engg. Technology | EXPENSES | L-0039 | 27AVBPP6929K1Z1 | 897 | 760 | 68.4 | 68.4 | 0.2
2024-04-18 | SRSBM Lab Testing Pvt Ltd | EXPENSES | MRT-27215 | 27ABACS8249K1ZU | 826 | 700 | 63 | 63
2024-05-01 | Landmark Consultants & Engg. Technology | EXPENSES | L-0123 | 27AVBPP6929K1Z1 | 1794 | 1520 | 136.8 | 136.8 | 0.4
2024-05-13 | SRSBM Lab Testing Pvt Ltd | EXPENSES | MRT-27862 | 27ABACS8249K1ZU | 826 | 700 | 63 | 63
2024-05-24 | Landmark Consultants & Engg. Technology | EXPENSES | L-0253 | 27AVBPP6929K1Z1 | 897 | 760 | 68.4 | 68.4 | 0.2
2024-05-28 | Landmark Consultants & Engg. Technology | EXPENSES | L-0278 | 27AVBPP6929K1Z1 | 1794 | 1520 | 136.8 | 136.8 | 0.4
2024-06-19 | SRSBM Lab Testing Pvt Ltd | EXPENSES | MRT-29158 | 27ABACS8249K1ZU | 413 | 350 | 31.5 | 31.5
2024-07-01 | Landmark Consultants & Engg. Technology | EXPENSES | L-0415 | 27AVBPP6929K1Z1 | 897 | 760 | 68.4 | 68.4 | 0.2
2024-07-06 | Landmark Consultants & Engg. Technology | EXPENSES | L-0454 | 27AVBPP6929K1Z1 | 897 | 760 | 68.4 | 68.4 | 0.2
2024-07-12 | Landmark Consultants & Engg. Technology | EXPENSES | L-0486 | 27AVBPP6929K1Z1 | 897 | 760 | 68.4 | 68.4 | 0.2
2024-07-19 | SRSBM Lab Testing Pvt Ltd | EXPENSES | MRT-29735 | 27ABACS8249K1ZU | 826 | 700 | 63 | 63
2024-07-23 | Landmark Consultants & Engg. Technology | EXPENSES | L-0530 | 27AVBPP6929K1Z1 | 897 | 760 | 68.4 | 68.4 | 0.2
2024-08-01 | SRSBM Lab Testing Pvt Ltd | EXPENSES | MRT-30227 | 27ABACS8249K1ZU | 826 | 700 | 63 | 63
2024-08-01 | SRSBM Lab Testing Pvt Ltd | EXPENSES | MRT-30400 | 27ABACS8249K1ZU | 826 | 700 | 63 | 63
2024-08-14 | Landmark Consultants & Engg. Technology | EXPENSES | L-0611 | 27AVBPP6929K1Z1 | 897 | 760 | 68.4 | 68.4 | 0.2
2024-08-26 | Landmark Consultants & Engg. Technology | EXPENSES | L-0653 | 27AVBPP6929K1Z1 | 1794 | 1520 | 136.8 | 136.8 | 0.4
2024-05-06 | Landmark Consultants & Engg. Technology | EXPENSES | L-0156 | 27AVBPP6929K1Z1 | 897 | 760 | 68.4 | 68.4 | 0.2
2024-05-08 | The Legalist | EXPENSES | TL/SBI/1272A |  | 7500 | 7500
2024-05-16 | Protech Consultants | EXPENSES | 25/558/BLDG 6D/02/2024-25 | 27ADTPD6280F1ZB | 118000 | 100000 | 9000 | 9000
2023-12-15 | UBG & Compnay | EXPENSES | 4564 | 27AAGFU4027K1ZY | 70800 | 60000 | 5400 | 5400
2024-02-13 | Cubictree Technology Solutions Pvt Ltd | EXPENSES | 23-24/BPR/3343 | 27AADCC8997J1ZW | 5900 | 5000 | 450 | 450
2024-01-01 | SRSBM Lab Testing Pvt Ltd | EXPENSES | MRT-23802 | 27ABACS8249K1ZU | 826 | 700 | 63 | 63
2024-01-01 | SRSBM Lab Testing Pvt Ltd | EXPENSES | MRT-23803 | 27ABACS8249K1ZU | 826 | 700 | 63 | 63
2024-01-01 | Landmark Consultants & Engg. Technology | EXPENSES | L-0954 | 27AVBPP6929K1Z1 | 2690 | 2280 | 205.2 | 205.2 | -0.4
2024-01-01 | Landmark Consultants & Engg. Technology | EXPENSES | L-0980 | 27AVBPP6929K1Z1 | 897 | 760 | 68.4 | 68.4 | 0.2
2024-01-09 | SRSBM Lab Testing Pvt Ltd | EXPENSES | MRT-23092 | 27ABACS8249K1ZU | 354 | 300 | 27 | 27
2024-01-09 | SRSBM Lab Testing Pvt Ltd | EXPENSES | MRT-24079 | 27ABACS8249K1ZU | 826 | 700 | 63 | 63
2024-02-01 | Landmark Consultants & Engg. Technology | EXPENSES | L-1050 | 27AVBPP6929K1Z1 | 1794 | 1520 | 136.8 | 136.8 | 0.4
2024-02-01 | Landmark Consultants & Engg. Technology | EXPENSES | L-1129 | 27AVBPP6929K1Z1 | 897 | 760 | 68.4 | 68.4 | 0.2
2024-02-13 | SRSBM Lab Testing Pvt Ltd | EXPENSES | MRT-25066 | 27ABACS8249K1ZU | 826 | 700 | 63 | 63
2024-02-15 | Landmark Consultants & Engg. Technology | EXPENSES | L-1275 | 27AVBPP6929K1Z1 | 1794 | 1520 | 136.8 | 136.8 | 0.4
2024-02-17 | SRSBM Lab Testing Pvt Ltd | EXPENSES | MRT-25223 | 27ABACS8249K1ZU | 826 | 700 | 63 | 63
2024-02-21 | SRSBM Lab Testing Pvt Ltd | EXPENSES | MRT-25355 | 27ABACS8249K1ZU | 826 | 700 | 63 | 63
2024-03-20 | SRSBM Lab Testing Pvt Ltd | EXPENSES | MRT-26376 | 27ABACS8249K1ZU | 826 | 700 | 63 | 63
2024-03-20 | SRSBM Lab Testing Pvt Ltd | EXPENSES | MRT-25629 | 27ABACS8249K1ZU | 826 | 700 | 63 | 63
2024-01-01 | Arch Graphics | EXPENSES | . | 27ABQPH0195L1Z7 | 94400 | 80000 | 7200 | 7200
2024-02-02 | Eco Mep Consultants | EXPENSES | EMC/23-24/222 | 27ANRPR8651E1ZD | 110625 | 93750 | 8437.5 | 8437.5
2024-02-10 | Vastukala Consultants (I) Pvt Ltd | EXPENSES | MUM/2324/FEB/079 | 27AADCV4303R1ZX | 118000 | 100000 | 9000 | 9000
2024-02-10 | Yogesh R. Vankar | EXPENSES | . |  | 60000 | 60000
2024-03-01 | Protech Consultants | EXPENSES | 144/558/Bldg 6C/2023-24 | 27ADTPD6280F1ZB | 236000 | 200000 | 18000 | 18000
2024-03-01 | Landmark Consultants & Engg. Technology | EXPENSES | L-1360 | 27AVBPP6929K1Z1 | 897 | 760 | 68.4 | 68.4 | 0.2
2024-03-12 | Landmark Consultants & Engg. Technology | EXPENSES | L-1410 | 27AVBPP6929K1Z1 | 1794 | 1520 | 136.8 | 136.8 | 0.4
2024-01-12 | The Legalist | EXPENSES | TL/SBI/1272 |  | 60000 | 60000
2024-02-05 | Adv. Rachana Marwal | EXPENSES | 369 |  | 45000 | 45000
2024-01-24 | MAHARASHTRA CHAMBER OF HOUSING INDUSTRY | EXPENSES | Bill Not Available | 27AAATM0334K1ZP | 11800 | 10000 | 900 | 900
|  | TOTAL |  |  | 973748 | 851520 | 61111.8 | 61111.8 | 4.4

## Admin
Date | Particulars | Voucher Type | Supplier Invoice No. | GST NO. | Gross Total | Basic Amount | CGST | SGST | Round Off | Other Cost
2024-04-06 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 56713 |  | 3978 | 3978
2024-04-15 | Maharashtra Rajya General Kamgar Mathadi and Trans. | EXPENSES | 1706 |  | 10500 | 10500
2024-04-21 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 56786 |  | 4560 | 4560
2024-04-27 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 57024 |  | 4314 | 4314
2024-07-01 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 57999 |  | 1064 | 1064
2024-07-03 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 58000 |  | 3706 | 3706
2024-07-05 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 58201 |  | 460 | 460
2024-07-31 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 58202 |  | 6000 | 6000
2024-08-01 | Maharashtra Rajya General Kamgar Mathadi and Trans. | EXPENSES | 1656 |  | 8425 | 8425
2024-08-03 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 58231 |  | 4200 | 4200
2024-08-06 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 58241 |  | 4040 | 4040
2024-08-10 | Maharashtra Rajya General Kamgar Mathadi and Trans. | EXPENSES | 1657 |  | 8375 | 8375
2024-08-16 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 58280 |  | 3386 | 3386
2024-08-20 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 58294 |  | 4324 | 4324
2024-08-27 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 58533 |  | 5040 | 5040
2024-08-31 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 58557 |  | 3064 | 3064
2024-04-26 | State Bank of India | EXPENSES | RT0424270O315814 | 27AAACS8577K2ZO | 6372000 | 5400000 | 486000 | 486000
2024-05-11 | Sunil Motors | EXPENSES | 425 |  | 42600 | 42600
2024-06-07 | Sunil Motors | EXPENSES | 384 |  | 16100 | 16100
2024-05-27 | Ekdant Boradband | EXPENSES | 1880 |  | 3300 | 3300
2024-06-27 | Mukund Printers | EXPENSES | 0068 | 27ADYPS0140E1ZE | 885 | 750 | 67.5 | 67.5
2024-07-10 | SNA Infotech Pvt Ltd | EXPENSES | V/1339/24-25 | 27AAJCS7663P1ZD | 361 | 305.8 | 27.52 | 27.52 | 0.16
2024-08-01 | SNA Infotech Pvt Ltd | EXPENSES | V/1659/24-25 | 27AAJCS7663P1ZD | 940 | 796.4 | 71.68 | 71.68 | 0.24
2024-07-01 | Bassein Petrol Supply Co. | EXPENSES | 00553 | 27AABFB3084C1ZW | 31677 | 31307.95 | 28.18 | 28.18 | -0.39 | 313.08
2024-07-31 | Bassein Petrol Supply Co. | EXPENSES | 00738 | 27AABFB3084C1ZW | 25475 | 25177.47 | 22.66 | 22.66 | 0.44 | 251.77
2024-08-31 | Bassein Petrol Supply Co. | EXPENSES | 00930 | 27AABFB3084C1ZW | 35628 | 34833.1 | 60.62 | 60.62 | 0.08 | 673.58
2024-07-03 | Swapnam Enterprises | EXPENSES | 06-2024-2025 | 27AFIPP6228A1ZK | 113700 | 88828.12 | 12435.94 | 12435.94
2024-07-15 | Swapnam Enterprises | EXPENSES | 09-2024-2025 | 27AFIPP6228A1ZK | 48000 | 37500 | 5250 | 5250
2024-07-03 | Serene Transport | EXPENSES | 275 | 27AGLPA4743K1Z9 | 8653 | 7333 | 659.97 | 659.97 | 0.06
2024-07-27 | Mahavir Decor | EXPENSES | 586 | 27ACGPK4033P1ZB | 44840 | 38000 | 3420 | 3420
2024-08-03 | Keeran Decor | EXPENSES | K-87/24-25 | 27DFFPS9205L1ZV | 7700 | 6525.44 | 587.29 | 587.29 | -0.02
2024-08-05 | Keeran Decor | EXPENSES | LK-89/24-25 | 27DFFPS9205L1ZV | 3850 | 3262.72 | 293.64 | 293.64
2024-08-07 | Keeran Decor | EXPENSES | K-91/24-25 | 27DFFPS9205L1ZV | 1925 | 1631.36 | 146.82 | 146.82
2024-08-12 | Keeran Decor | EXPENSES | K-96/24-25 | 27DFFPS9205L1ZV | 15400 | 13050.88 | 1174.58 | 1174.58 | -0.04
2024-08-19 | Keeran Decor | EXPENSES | K-103/24-25 | 27DFFPS9205L1ZV | 5775 | 4894.08 | 440.47 | 440.47 | -0.02
2024-08-21 | Shri Gurudev Electricals | EXPENSES | 791 2024/25 | 27ATLPS9954M1ZH | 14695 | 12453.5 | 1120.82 | 1120.82 | -0.14
2024-08-22 | Poojan Colour Point | EXPENSES | 852/24-25 | 27AAJFP0517A1ZQ | 2260 | 1720.43 | 160.32 | 160.32 | -0.11 | 219.04
2024-08-23 | Poojan Colour Point | EXPENSES | 854/2-25 | 27AAJFP0517A1ZQ | 21671 | 18365.36 | 1652.88 | 1652.88 | -0.12
2024-08-04 | Mahaveer Enterprises & Personal Services | EXPENSES | 72/2024-25 | 27AECPY5912R2ZM | 19000 | 19000
2023-11-21 | Mukund Printers | EXPENSES | 0166 | 27ADYPS0140E1ZE | 944 | 800 | 72 | 72
2023-11-28 | Pratik Transport | EXPENSES | 039 |  | 13615 | 13615
2024-01-01 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 55141 |  | 4320 | 4320
2024-01-01 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 55199 |  | 3724 | 3724
2024-01-01 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 55340 |  | 2160 | 2160
2024-01-01 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 55362 |  | 4182 | 4182
2024-01-01 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 55416 |  | 3870 | 3870
2024-01-01 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 55421 |  | 3960 | 3960
2024-02-01 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 55612 |  | 3594 | 3594
2024-02-01 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 55700 |  | 3918 | 3918
2024-03-01 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 55987 |  | 3154 | 3154
2024-03-04 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 56325 |  | 3400 | 3400
2024-03-11 | Maharashtra Rajya General Kamgar Mathadi and Trans. | EXPENSES | 1643 |  | 9750 | 9750
2024-03-28 | Aadivasi Ekta Varai Mathadi Transport and General | EXPENSES | 56638 |  | 3232 | 3232
2024-01-09 | Rajshree Transport | EXPENSES | 25 |  | 5000 | 5000
TOTAL |  |  |  |  | 6980694 | 5951850.61 | 513692.89 | 513692.89 | 0.14 | 1457.47

## MArketing
Date | Particulars | Voucher Type | Supplier Invoice No. | GSTIN/UIN | Gross Total | CGST | SGST | Sales & Marketing Expenses
2024-07-01 | Wow Media Works | EXPENSES | 70 |  | 38500 |  |  | 38500
2024-07-01 | Vizon Solutions | EXPENSES | 009-2024 | 27AFLPC6650C1ZO | 8024 | 612 | 612 | 6800
2024-08-08 | 3D Studio | EXPENSES | . |  | 50000 |  |  | 50000
2024-08-24 | Sneha Enterprises | EXPENSES | 0347 | 27AABHT8679K1ZA | 448400 | 34200 | 34200 | 380000
2024-03-01 | Rikanimo | EXPENSES | 6 |  | 35000 |  | 35000
TOTAL |  |  |  |  | 579924 | 34812 | 69812 | 475300

## Interest
Sr. No. | Month | Interest Amount
1 | 2024-04-01 | 22201
| 2024-05-01 | 176365
| 2024-06-01 | 394267
| 2024-07-01 | 508574
| 2024-08-01 | 723937
2024-09-01
1825344

## Construction Area Statement
Sr. No. | Floor | Total Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | Percentage of work completed | Actual Expenditure till date in `
1 | Excavation Cost |  |  |  | 29168399 | 100% | 29168399
2 | Basement | 365.64 | 365.64 | 30000 | 10969200 | 50% | 5484600
3 | Ground Floor | 365.64 | 365.64 | 30000 | 10969200 | 50% | 5484600
4 | 1st Floor | 393.261 | 393.261 | 30000 | 11797830 | 50% | 5898915
5 | 2nd Floor | 391.881 | 391.881 | 30000 | 11756430 | 50% | 5878215
6 | 3rd Floor | 391.881 | 391.881 | 30000 | 11756430 | 50% | 5878215
7 | 4th Floor | 391.881 | 391.881 | 30000 | 11756430 | 40% | 4702572
8 | 5th Floor | 391.881 |  | 30000 | 11756430 |  | 0
9 | 6th Floor | 391.881 |  | 30000 | 11756430 |  | 0
10 | 7th Floor | 391.881 |  | 30000 | 11756430 |  | 0
11 | 8th Floor | 408.5235 |  | 30000 | 12255705 |  | 0
12 | 9th Floor | 408.5235 |  | 30000 | 12255705 |  | 0
13 | 10th Floor | 412.4735 |  | 30000 | 12374205 |  | 0
14 | 11th Floor | 415.5335 |  | 30000 | 12466005 |  | 0
15 | 12th Floor | 415.5335 |  | 30000 | 12466005 |  | 0
16 | 13th Floor | 415.5335 |  | 30000 | 12466005 |  | 0
17 | 14th Floor | 415.8335 |  | 30000 | 12475005 |  | 0
18 | 15th Floor | 422.2735 |  | 30000 | 12668205 |  | 0
19 | 16th Floor | 422.2535 |  | 30000 | 12667605 |  | 0
20 | 17th Floor | 411.1035 |  | 30000 | 12333105 |  | 0
21 | 18th Floor | 411.1035 |  | 30000 | 12333105 |  | 0
22 | 19th Floor | 411.1035 |  | 30000 | 12333105 |  | 0
23 | 20th Floor | 411.1035 |  | 30000 | 12333105 |  | 0
24 | 21st Floor | 411.1035 |  | 30000 | 12333105 |  | 0
25 | 22nd Floor | 411.1035 |  | 30000 | 12333105 |  | 0
26 | OHT / LMR | 43.87 |  | 30000 | 1316100 |  | 0
Sub - Total (A) |  | 9722.7995 | 2300.184 |  | 320852384 |  | 62495516
STACK PARKING Nos. |  | 49 |  | 350000 | 17150000 |  | 0
TOTAL COST OF CONSTRUCTION (A + B) |  |  |  |  | 338002384 | 18.49% | 62495516

## Construction Area Statement (2)
WING C
Sr. No. | Floor | Built Up Area in Sq. M. | Balcony Area in Sq. M. | Staircase / Lift Area in Sq. M. | EF Area in Sq. M. | Patio Area in Sq. M. | Refuge Area in Sq. M. | Other Area in Sq. M. | Total Construction Area in Sq. M. | Total Construction Area in Sq. Ft. | Rate of Construction | Value after Completion | % work completed | Actual Expenditure till date in `
1 | Basement Floor | 0 | 0 | 51.19 | 0 | 0 | 0 | 466.04 | 517.23 | 5567.4637 | 30000 | 15516900 | 50% | 7758450
2 | Ground Floor | 0 | 0 | 114.48 | 0 | 0 | 0 | 739.52 | 854 | 9192.456 | 30000 | 25620000 | 50% | 12810000
3 | 1st Floor (Pt. Podium) | 164.24 | 15.85 | 69.31 | 19.19 | 12.83 | 0 | 610.12 | 891.54 | 9596.5366 | 30000 | 26746200 | 50% | 13373100
4 | 2nd Floor (pt. Podium) | 225.09 | 21.86 | 71.53 | 27.58 | 13.95 | 0 | 91.42 | 451.43 | 4859.1925 | 30000 | 13542900 | 50% | 6771450
5 | 3rd Floor | 307.79 | 30.58 | 71.53 | 35.99 | 24.09 | 0 | 0 | 469.98 | 5058.8647 | 30000 | 14099400 | 40% | 5639760
6 | 4th Floor | 307.79 | 30.58 | 71.53 | 36.31 | 23.06 | 23.479 | 0 | 492.749 | 5303.9502 | 30000 | 14782470 | 0% | 0
7 | 5th Floor | 307.79 | 30.58 | 71.53 | 35.99 | 24.09 | 0 | 0 | 469.98 | 5058.8647 | 30000 | 14099400 | 0% | 0
8 | 6th Floor | 307.79 | 30.58 | 71.53 | 36.31 | 23.06 | 23.479 | 0 | 492.749 | 5303.9502 | 30000 | 14782470 | 0% | 0
9 | 7th Floor | 307.79 | 30.58 | 71.53 | 35.99 | 24.09 | 0 | 0 | 469.98 | 5058.8647 | 30000 | 14099400 | 0% | 0
10 | 8th Floor | 307.79 | 30.58 | 71.53 | 36.31 | 23.06 | 23.479 | 0 | 492.749 | 5303.9502 | 30000 | 14782470 | 0% | 0
11 | 9th Floor | 307.79 | 30.58 | 71.53 | 35.99 | 24.09 | 0 | 0 | 469.98 | 5058.8647 | 30000 | 14099400 | 0% | 0
12 | 10th Floor | 307.79 | 30.58 | 71.53 | 36.31 | 23.06 | 23.479 | 0 | 492.749 | 5303.9502 | 30000 | 14782470 | 0% | 0
13 | 11th Floor | 307.79 | 30.58 | 71.53 | 35.99 | 24.09 | 0 | 0 | 469.98 | 5058.8647 | 30000 | 14099400 | 0% | 0
14 | 12th Floor | 307.79 | 30.58 | 71.53 | 36.31 | 23.06 | 23.479 | 0 | 492.749 | 5303.9502 | 30000 | 14782470 | 0% | 0
15 | 13th Floor | 307.79 | 30.58 | 71.53 | 35.99 | 24.09 | 0 | 0 | 469.98 | 5058.8647 | 30000 | 14099400 | 0% | 0
16 | 14th Floor | 307.79 | 30.58 | 71.53 | 36.31 | 23.06 | 23.479 | 0 | 492.749 | 5303.9502 | 30000 | 14782470 | 0% | 0
17 | 15th Floor | 307.79 | 30.58 | 71.53 | 35.99 | 24.09 | 0 | 0 | 469.98 | 5058.8647 | 30000 | 14099400 | 0% | 0
18 | 16th Floor | 307.79 | 30.58 | 71.53 | 36.31 | 23.06 | 23.479 | 0 | 492.749 | 5303.9502 | 30000 | 14782470 | 0% | 0
19 | Terrace / OHT | 0 | 0 | 84.3 | 0 | 0 | 0 | 0 | 84.3 | 907.4052 | 30000 | 2529000 | 0% | 0
TOTAL |  | 4698.39 | 465.83 | 1392.23 | 552.87 | 356.83 | 164.353 | 1907.1 | 9537.603 | 102662.7587 |  | 286128090 | 16.2% | 46352760
Deep Excavation & Raft Footing Cost | [11 empty] | 28612809 | 100% | 28612809
TOTAL CONSTRUCTION COST OF WING C | [11 empty] | 314740899 | 23.82% | 74965569
WING D
Sr. No. | Floor | Built Up Area in Sq. M. | Balcony Area in Sq. M. | Staircase / Lift Area in Sq. M. | EF Area in Sq. M. | Patio Area in Sq. M. | Refuge Area in Sq. M. | Other Area in Sq. M. | Total Construction Area in Sq. M. | Total Construction Area in Sq. Ft. | Rate of Construction | Value after Completion | % work completed | Actual Expenditure till date in `
1 | Basement Floor | 0 | 0 | 55.41 | 0 | 0 | 0 | 617.937 | 673.347 | 7247.9071 | 30000 | 20200410 | 50% | 10100205
2 | Ground Floor | 0 | 0 | 110.82 | 0 | 0 | 0 | 639.432 | 750.252 | 8075.7125 | 30000 | 22507560 | 50% | 11253780
3 | 1st Floor (Pt. Podium) | 0 | 0 | 55.41 | 0 | 0 | 0 | 690.353 | 745.763 | 8027.3929 | 30000 | 22372890 | 60% | 13423734
4 | 2nd Floor (pt. Podium) | 126.67 | 8.26 | 55.41 | 16.31 | 9.6 | 0 | 105.2 | 321.45 | 3460.0878 | 30000 | 9643500 | 60% | 5786100
5 | 3rd Floor | 220.408 | 22.022 | 53.33 | 29.5 | 16.88 | 0 | 0 | 342.14 | 3682.795 | 30000 | 10264200 | 60% | 6158520
6 | 4th Floor | 220.408 | 22.022 | 53.33 | 28.65 | 18.53 | 17.285 | 0 | 360.225 | 3877.4619 | 30000 | 10806750 | 60% | 6484050
7 | 5th Floor | 220.408 | 22.022 | 53.33 | 29.5 | 16.88 | 0 | 0 | 342.14 | 3682.795 | 30000 | 10264200 | 60% | 6158520
8 | 6th Floor | 220.408 | 22.022 | 53.33 | 28.65 | 18.53 | 17.285 | 0 | 360.225 | 3877.4619 | 30000 | 10806750 | 60% | 6484050
9 | 7th Floor | 220.408 | 22.022 | 53.33 | 29.5 | 16.88 | 0 | 0 | 342.14 | 3682.795 | 30000 | 10264200 | 60% | 6158520
10 | 8th Floor | 220.408 | 22.022 | 53.33 | 28.65 | 18.53 | 17.285 | 0 | 360.225 | 3877.4619 | 30000 | 10806750 | 60% | 6484050
11 | 9th Floor | 220.408 | 22.022 | 53.33 | 29.5 | 16.88 | 0 | 0 | 342.14 | 3682.795 | 30000 | 10264200 | 50% | 5132100
12 | 10th Floor | 220.408 | 22.022 | 53.33 | 28.65 | 18.53 | 17.285 | 0 | 360.225 | 3877.4619 | 30000 | 10806750 | 50% | 5403375
13 | 11th Floor | 220.408 | 22.022 | 53.33 | 29.5 | 16.88 | 0 | 0 | 342.14 | 3682.795 | 30000 | 10264200 | 50% | 5132100
14 | 12th Floor | 220.408 | 22.022 | 53.33 | 28.65 | 18.53 | 17.285 | 0 | 360.225 | 3877.4619 | 30000 | 10806750 | 50% | 5403375
15 | 13th Floor | 220.408 | 22.022 | 53.33 | 29.5 | 16.88 | 0 | 0 | 342.14 | 3682.795 | 30000 | 10264200 | 40% | 4105680
16 | 14th Floor | 220.408 | 22.022 | 53.33 | 28.65 | 18.53 | 17.285 | 0 | 360.225 | 3877.4619 | 30000 | 10806750 | 0% | 0
17 | 15th Floor | 220.408 | 22.022 | 53.33 | 29.5 | 16.88 | 0 | 0 | 342.14 | 3682.795 | 30000 | 10264200 | 0% | 0
18 | 16th Floor | 220.408 | 22.022 | 53.33 | 28.65 | 18.53 | 17.285 | 0 | 360.225 | 3877.4619 | 30000 | 10806750 | 0% | 0
19 | Terrace / OHT | 0 | 0 | 67.69 | 0 | 0 | 0 | 0 | 67.69 | 728.6152 | 30000 | 2030700 | 0% | 0
TOTAL |  | 3212.382 | 316.568 | 1091.36 | 423.36 | 257.47 | 120.995 | 2052.922 | 7475.057 | 80461.5135 |  | 224251710 | 46.23% | 103668159
Deep Excavation & Raft Footing Cost | [11 empty] | 22425171 | 100% | 22425171
TOTAL CONSTRUCTION COST OF WING C | [11 empty] | 246676881 | 51.12% | 126093330
Sr. No. | Wing | Total Construction Area in Sq. M. | Total Construction Area in Sq. Ft. | Rate of Construction | Value after Completion | % work completed | Value as on Date
1 | Construction Cost of Wing C | 9537.603 | 102662.7587 | 30000 | 286128090 | 16.2% | 46352760
2 | Excavation Cost of Wing C | 10% of Cost of Construction of Wing C |  |  | 28612809 | 100% | 28612809
3 | Construction Cost of Wing D | 7475.057 | 80461.5135 | 30000 | 224251710 | 46.23% | 103668159
4 | Excavation Cost of Wing D | 10% of Cost of Construction of Wing D |  |  | 22425171 | 100% | 22425171
5 | Podium Joining Area | 2592.34 | 27903.9478 | 30000 | 77770200 | 0% | 0
TOTAL |  | 19605 | 211028.22 |  | 639187980 | 31.46% | 201058899
19605
0

## Sheet8
Date | Particulars | Voucher Type | Gross Total | FSI Purchase (Blossom C&D)
2024-01-05 | Ajmera Developers | Purchase | 249677750 | 249677750
29677750
Sr. No. | Wing | Total Construction Area in Sq. M. | Total Construction Area in Sq. Ft. | Value after Completion | % work completed | Value as on Date
1 | Podium Joining Area | 2592.34 | 27903.9478 | 77770200 | 0% | 0
2 | Construction Cost of Wing C | 9537.603 | 102662.7587 | 314740899 | 23.82% | 74965569
3 | Construction Cost of Wing D | 7475.057 | 80461.5135 | 246676881 | 51.12% | 126093330
TOTAL |  | 19605 | 211028.22 | 639187980 | 31.46% | 201058899
`