## Final Summary
Project expenses | Estimated Cost as per Cost Vetting | Incurred Cost as per Bill till 30.09.2024 | Incurred Cost as per CA till 30.09.2024 | Incurred Cost as per Bill till 30.06.2024 | Incurred Cost as per CA till 30.06.2024 | Difference between the Bills & CA | Difference between both the Bills | Difference between both CA | Remark
Land Cost | 0.81 | 0.81478 | 0.8146 | 0.81478 | 0.81 | 0.00018 | 0 | 0.0046
Rent Cost | 3.95 | 1.1335 | 1.1335 | 1.0398 | 1.03 | 0 | 0.093719 | 0.10353
Construction Cost of Sale Building | 15.44 | 1.2882 | 1.5105 | 1.2882 | 1.29 | -0.22234 | 0 | 0.22052
TDR Cost | 3.42 | 2.8412 | 2.8412 | 2.8412 | 2.84 | 0 | 0 | 0.0012136
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 13.63 | 2.991 | 2.991 | 2.8641 | 2.86 | 0 | 0.12688 | 0.13097
Architect Cost, RCC & other Professional fees | 0.77 | 0.72139 | 1.1127 | 0.43372 | 0.43 | -0.39135 | 0.28767 | 0.46274
On- site expenditure for development / Advance for Project / Administrative Cost / Fixed Assets | 0.93 | 0.63144 |  | 0.22293 | 0.22 | 0.63144 | 0.40852 |  | .
Marketing Expenses | 1.19 | 0.00225 |  | 0 | 0 | 0.00225 | 0.00225
Interest Cost | 4 | 0 | 0.28619 | 0 | 0 | -0.28619 | 0 | 0.28619
Contingency Cost | 0.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost | 44.6 | 10.4238 | 10.6898 | 9.5047 | 9.48 | -0.26601 | 0.91903 | 1.2098
|  | 34.1762 | 23.97%
Particulars | Revised Estimated Cost (in Cr.) | 30.09.2024 as per Bill Tally (inclusive of GST) | Cost incurred as %age total cost of that Component | Cost incurred as %age of cost incurred as on 30.09.2024
Land Cost | 0.81 | 0.81478 | 100.6% | 1.827%
Rent Cost | 3.95 | 1.1335 | 28.7% | 2.542%
Construction Cost of Sale Building | 15.44 | 1.2882 | 8.343% | 2.888%
TDR Cost | 3.42 | 2.8412 | 83.08% | 6.37%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 13.63 | 2.991 | 21.94% | 6.706%
Architect Cost, RCC & other Professional fees | 0.77 | 0.72139 | 93.69% | 1.617%
On- site expenditure for development / Advance for Project / Administrative Cost / Fixed Assets | 0.93 | 0.63144 | 67.9% | 1.416%
Marketing Expenses | 1.19 | 0.00225 | 0.1891% | 0.005045%
Interest Cost | 4 | 0 | 0% | 0%
Contingency Cost | 0.46 | 0 | 0% | 0%
Total | 44.6 | 10.4238 | 23.37% | 23.37%
Pariculars | 30.09.2024 as per Bill Tally (inclusive of GST) | 30.06.2024 as per Bill Tally (inclusive of GST) | Difference b/w bills of 30.09.2024 & 30.06.2024 | Difference of Cost incurred as %age of cost incurred as on 30.09.2024 & 30.06.2024
Land Cost | 0.81478 | 0.81478 | 0 | 0%
Rent Cost | 1.1335 | 1.0398 | 0.09 | 0.8634%
Construction Cost of Sale Building | 1.2882 | 1.2882 | 0 | 0%
TDR Cost | 2.8412 | 2.8412 | 0 | 0%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 2.991 | 2.8641 | 0.13 | 1.247%
Architect Cost, RCC & other Professional fees | 0.72139 | 0.43372 | 0.29 | 2.782%
On- site expenditure for development / Advance for Project / Administrative Cost / Fixed Assets | 0.63144 | 0.22293 | 0.41 | 3.933%
Marketing Expenses | 0.00225 | 0 | 0 | 0%
Interest Cost | 0 | 0 | 0 | 0%
Contingency Cost | 0 | 0 | 0 | 0%
Total | 10.4238 | 9.5047 | 0.92 | 8.826%

## Summary Sheet
Sr. No. | Particulars | Incurred Cost in ` till 30.09.2024 | Incurred Cost in ` Cr. Till 30.09.2022 | Incurred Cost in ` till 30.06.2024 | Incurred Cost in ` Cr. Till 30.06.2022 | Balance in ` | Balance in ` Cr.
1 | Land Cost | 8147800 | 0.81478 | 8147800 | 0.81478 | 0 | 0
2 | Rent Cost | 11335330 | 1.1335 | 10398140 | 1.0398 | 937190 | 0.093719
3 | Construction Cost | 12881839 | 1.2882 | 12881839 | 1.2882 | 0 | 0
4 | TDR Cost | 28412136 | 2.8412 | 28412136 | 2.8412 | 0 | 0
5 | Approval Cost & Stamp Duty | 29909667 | 2.991 | 28640910 | 2.8641 | 1268757 | 0.12688
6 | Professional Cost | 7213908 | 0.72139 | 4337240 | 0.43372 | 2876668 | 0.28767
7 | Admin Cost | 6314408 | 0.63144 | 2229254 | 0.22293 | 4085154 | 0.40852
8 | Marketing Cost | 22500 | 0.00225 | 0 | 0 | 22500 | 0.00225
9 | Interest Cost | 0 | 0 | 0 | 0 | 0 | 0
10 | Contingency Cost | 0 | 0 | 0 | 0 | 0 | 0
| Total | 104237588 | 10.4238 | 95047319 | 9.5047 | 9190269 | 0.91903
|  | 96089788 | 9.609 | 86899519 | 8.69 | 9190269 | 0.91903
40000000
40000000

## Land, Stamp Duty cost
Stamp Duty & Registration Fees
Sr. No. | Agreement Name | Date | Particulars | Amount | Incurred Amount
1 | Development Agreement | 2023-04-19 | Stamp Duty | 8116000 | 8116000
2 |  |  | Reg. Fees | 30000 | 30000
3 |  |  |  | 1800 | 1800
| TOTAL |  |  | 8147800 | 8147800
| Particulars | Rs. | Heading
| Stampduty & Registration Charges (Tdr) | 819507 | TDR
| Scrutiny Fees for TDR | 34065 | TDR
| Purchase of TDR-Aneesh | 27203564 | TDR
| Brokerage on Purchase of TDR | 355000 | TDR
| Total | 28412136
| Particulars | Rs. | Heading
| Compensation to Members ( Aneesh) | 5130600 | Corpus
| Society Corpus | 300000 | Corpus
| Shifting & Reshifting Charges ( Aneesh) | 350000 | Rent
| Alternate Accomodation( Aneesh) | 4617540 | Rent
| Alternate Accomodation( Aneesh) | 937190 | Rent
| TOTAL | 11335330

## Approval Cost
Particulars | Rs. | Heading
Stampduty & Registration Charges (BMC | 1235600 | Approval
Permission & Approval | 27405310 | Approval
Permission & Approval | 1268757 | Approval
Total | 29909667

## Construction Cost
Particulars | Rs. | Heading
Titan Ceramic and Cemet Centre | 20572 | Construction
Classic Infrastructuer | 2461527.2 | Construction
J.K Enterprise | 5275525.62 | Construction
Skyway Rmc Plants Pvt Ltd | 4114753.2 | Construction
Bharat Steel | 4720 | Construction
Crack Filling Work ( Asset) | 35000 | Construction
Electricity Charges (Aneesh Site) | 15327 | Construction
Exavation Work ( WIP) | 31000 | Construction
On Site Labour Charges( AA) | 4800 | Construction
Purchase of Meterials (WIP) | 913693.5 | Construction
Plumbing Work ( WIP) | 4920 | Construction
Total | 12881838.52

## Professional Cost
Particulars | Rs. | Heading
Vastukala Consultants (I) Pvt Ltd | 59000 | Professional
Rajan Pillai | 36500 | Professional
Architects/Engineers Fees | 712675 | Professional
Agami EngineeringConsultants | 62675 | Professional
Consultancy Charges | 153790 | Professional
Professional / Legal Expenses | 3312600 | Professional
Architects/Engineers Fees | 200000 | Professional
Professional / Legal Expenses | 2676668 | Professional
Total | 7213908

## Admin Cost
Particulars | Rs. | Heading
NeevConstruction | 416345 | Admin overheads
Bettle industries Pvt Ltd | 31624 | Admin overheads
A q Jilani | 98100 | Admin overheads
Kaushik Pitwa | 249465 | Admin overheads
Tejal Plumbing Work | 4920 | Admin overheads
Sudha.R | 31000 | Admin overheads
Saleem Hashmi | 35000 | Admin overheads
Pratik Electric | 10355 | Admin overheads
Megha Enterprises | 1029197 | Admin overheads
Mahavir Furnituer | 2832 | Admin overheads
Lotus Trading & Co | 56551 | Admin overheads
Lotus Borewell & Pumps | 69573 | Admin overheads
Lock & Key | 8300 | Admin overheads
Lawgical Consultants | 29500 | Admin overheads
Repairs & Maintenanace Aneesh Site | 2550 | Admin overheads
Ground Water Exploration Service | 11000 | Admin overheads
BILIMORIA MEHTA & COMPANY | 107380 | Admin overheads
Baltic India Private Limited | 15222 | Admin overheads
Alpha Enterprises | 850 | Admin overheads
Water Testing | 17490 | Admin overheads
Transportation Charges | 2000 | Admin overheads
Electricity Work | 57996
Fees & Royalities | 547003
Repairs & Maintenanace Aneesh Site | 4130
Stamp Duty & Reg. Charges | 928300
Documentation charges loan sbi | 25960
Processing Fees | 2124000
Security Charges | 13000
Insurance Charges | 341610
Postage and Courier | 600
Printing and Stationary | 7155
Inspection Charges loan SBI | 35400
Total | 6314408

## MArketing Cost
Particulars | Rs. | Heading
Advertising Expenses | 22500 | Ads
Total | 22500

## Interest
Sr. No. | Particulars | Amount | Amount in ` Cr. | Amount | Amount in ` Cr. | Balance | Balance in Cr.
| September secured interest | 0 | 0 |  |  | 0 | 0
| October |  |  |  |  | 0 | 0
| November |  |  |  |  | 0 | 0
| December |  |  |  |  | 0 | 0
| Jan to March |  |  |  |  | 0 | 0
| April to June |  |  |  |  | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0

## Construction Area of Sale Build
Summary of Cost of Construction
Plinth Area Calculation
Sr. No | Floor Nos. | Total Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | Percentage of work completed | Actual Expenditure till date in `
1 | Excavation |  |  |  | 12129600 | 100% | 12129600
2 | Part Basement | 249.09 | 249.09 | 35000 | 8718150 | 50% | 4359075
3 | Ground Floor | 297.62 | 297.62 | 35000 | 10416700 | 50% | 5208350
4 | 1st Floor | 297.62 |  | 35000 | 10416700 | 0% | 0
5 | 2nd Floor | 300.92 |  | 35000 | 10532200 | 0% | 0
6 | 3rd Floor | 310.74 |  | 35000 | 10875900 | 0% | 0
7 | 4th Floor | 310.74 |  | 35000 | 10875900 | 0% | 0
8 | 5th Floor | 327.92 |  | 35000 | 11477200 | 0% | 0
9 | 6th Floor | 327.92 |  | 35000 | 11477200 | 0% | 0
10 | 7th Floor | 327.92 |  | 35000 | 11477200 | 0% | 0
11 | 8th Floor | 327.92 |  | 35000 | 11477200 | 0% | 0
12 | 9th Floor | 327.92 |  | 35000 | 11477200 | 0% | 0
13 | Terrace / OHT | 59.27 |  | 35000 | 2074450 | 0% | 0
Total |  | 3465.6 | 546.71 |  | 133425600 | 16.26% | 21697025
| Parking | 42 |  | 500000 | 21000000 | 0 | 0
Total |  | 6426.49 | 546.71 |  | 154425600 | 14.05% | 21697025