## Project Cost
INR in Crore
Particulars | Total Project Cost | Cost incurred till | Balance Cost to be Incurred | Particulars | Total Project Cost | %tage of Total
Land & Stamp Duty | 30.15 | 21.26 | 8.89 | Land & Stamp Duty | 30.15 | 20.77% | 14.64%
Construction Cost | 95.51 | 12.68 | 82.83 | Construction Cost | 95.51 | 65.78% | 8.733%
Architect & Consultancy Expenses | 0.6 | 0 | 0.6 | Architect & Consultancy Expenses | 0.6 | 0.4133% | 0%
Administrative Expenses | 4.18 | 0.15 | 4.03 | Administrative Expenses | 4.18 | 2.879% | 0.1033%
Marketing Cost | 3.9 | 0.19 | 3.71 | Marketing Cost | 3.9 | 2.686% | 0.1309%
Contingency | 0 |  | 0 | Contingency | 0 | 0% | 0%
Interest to Bank Finance upto construction period | 10.85 | 0 | 10.85 | Interest to Bank Finance upto construction period | 10.85 | 7.473% | 0%
Total | 145.19 | 34.28 | 110.91 | Total | 145.19 | 100%
|  | (INR Crore) |  |  |  | (INR Crore)
Particulars | Total Fund | Fund raised | Pending to be Raised | Particulars | Total Funds to be Raised | %tage of Total
Promoters Contribution |  |  |  | Promoters Contribution
Promoters Contribution | 20.5 | 20.5 | 0 | Promoters Contribution | 20.5 | 14.12%
USL | 14.5 | 1.49 | 13.01 | USL | 14.5 | 9.987%
Bank Loan |  |  | 0 | Bank Loan
Term Loan | 48 | 0 | 48 | Term Loan | 48 | 33.06%
Customer Advances | 62.19 | 12.29 | 49.9 | Customer Advances | 62.19 | 42.83%
0
Total | 145.19 | 34.28 | 110.91 | Total | 145.19 | 100%
| 0 | 0 | [5 empty] | 0
| 824.04 | 13.46%
| 5.825% |  |  | 31.63%
|  | 362.9822 | 350.6922
| 102.69 | 13.22% | 0.13687

## Revenue Working (hidden)
#VALUE!
Particulars | Remaining | time axis 2023-07-31 to 2027-03-01
Sale Building
1BHK | 9 | [45 empty] | 1 | bar: 2024-04-01
1BHK | 145 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 129
1BHK | 13 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 52
1BHK | 22 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 16
Shop | 23 | [45 empty] | 24 | bar: 2023-07-31 to 2025-06-01
Price
1BHK |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1BHK |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1BHK |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1BHK |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Revenue
1BHK |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1BHK |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1BHK |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1BHK |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collection
Sale Building |  | 5% | 5% | 5% | 5% | 5% | 10% | 12% | 14% | 16% | 18% | 20% | 24% | 28% | 32% | 36% | 40% | 44% | 48% | 52% | 56% | 60% | 64% | 68% | 72% | 76% | 80% | 80% | 80% | 80% | 80% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
Collection |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | 10 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Existing Sales |  | 1.5197 | 0 | 0 | 0 | 0 | 0 | 16.2461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.2507 | 0 | 0 | 0 | 0 | 0 | 104.9527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.8253
R5 | Remaining | 2023-07-31 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01
1BHK | 102 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 2 | [7 empty] | 102
1BHK | 105 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | [7 empty] | 105
1BHK | 0 | 2024-01-01: 0; 2024-04-01: 0; 2024-07-01: 0; 2024-10-01: 0; 2025-01-01: 0; 2025-04-01: 0; 2025-07-01: 0; 2025-10-01: 0; 2026-01-01: 0; 2026-04-01: 0; 2026-07-01: 0; 2026-09-01: 0 | [5 empty] | 0
Revenue
1BHK | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1BHK | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1BHK | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collection | [6 empty] | 10% | 12% | 14% | 16% | 18% | 20% | 24% | 28% | 32% | 36% | 40% | 44% | 48% | 52% | 56% | 60% | 64% | 68% | 72% | 76% | 80% | 80% | 80% | 80% | 80% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
R5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Sales |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Collection |  | 1.5197 | 0 | 0 | 0 | 0 | 0 | 16.2461 | 0 | 0 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | 15.2507 | -1 | -1 | 10 | -2 | -2 | 102.9527 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | 24 | 0 | 0 | 10.8253 | 0 | 0 | 0
Sales and Marketing Expenses |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Particulars
Type | RERA Area | 2023-07-31: Total Units; 2023-09-01: Sold Units; 2023-11-01: Inventory
|  | R4 | R5 | R4 | R5 | R4 | R5
1BHK | 40.43 | 2023-07-31: 52; 2023-08-01: 106; 2023-09-01: 20; 2023-10-01: 0; 2023-11-01: 32; 2023-12-01: 106
2BHK | 59.72 | 2023-07-31: 163; 2023-08-01: 109; 2023-09-01: 145; 2023-10-01: 0; 2023-11-01: 18; 2023-12-01: 109
3++ BHK | 103.34 | 2023-07-31: 19; 2023-08-01: 39; 2023-09-01: 20; 2023-10-01: 0; 2023-11-01: -1; 2023-12-01: 39
4++BHK | 122.79 | 2023-07-31: 20; 2023-09-01: 23; 2023-10-01: 0; 2023-11-01: -3; 2023-12-01: 0
Total |  | 2023-07-31: 254; 2023-08-01: 254; 2023-09-01: 23; 2023-10-01: 0; 2023-11-01: 46; 2023-12-01: 254

## Sale Building Inv Sales (hidden)
[5 empty] | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-12-31 | 2023-12-31 | 2023-12-31 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2024-06-30 | 2024-06-30 | 2024-06-30 | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-12-31 | 2024-12-31 | 2024-12-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-09-30 | 2026-09-30 | 2026-09-30 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2027-03-31 | 2027-03-31 | 2027-03-31
 | time axis 2023-07-31 to 2027-03-31
| Construction Linked Plan |  | % Completion |  | 5% | 0% | 0% | 5% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 2% | 0% | 0% | 2% | 0% | 0% | 2% | 0% | 0%
|  |  | Cumulative |  | 5% | 5% | 5% | 10% | 10% | 10% | 11% | 11% | 11% | 12% | 12% | 12% | 13% | 13% | 13% | 14% | 14% | 14% | 15% | 15% | 15% | 16% | 16% | 16% | 17% | 17% | 17% | 18% | 18% | 18% | 19% | 19% | 19% | 20% | 20% | 20% | 22% | 22% | 22% | 24% | 24% | 24% | 26% | 26% | 26%
| Scheme |  |  | 1 | 2023-07-31: 5%; 2024-07-31: 10%; 2025-09-30: 10%; 2026-06-30: 75%
|  |  | Cumulative |  |  | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Sales Scheme 1 | SCH1 |  |  | 2023-07-31: 5%; 2023-09-30: 5%; 2023-12-31: 5%; 2024-03-31: 5%; 2024-06-30: 10%; 2024-09-30: 10%; 2024-12-31: 10%; 2025-03-31: 10%; 2025-06-30: 10%; 2025-09-30: 10%; 2025-12-31: 10%; 2026-03-31: 5%; 2026-06-30: 5%
[5 empty] | 5% | 5% | 10% | 10% | 10% | 15% | 15% | 15% | 20% | 20% | 20% | 30% | 30% | 30% | 40% | 40% | 40% | 50% | 50% | 50% | 60% | 60% | 60% | 70% | 70% | 70% | 80% | 80% | 80% | 90% | 90% | 90% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Sales Scheme 2 | SCH2 |  | 95% | 2023-09-30: 5%; 2024-01-31: 10%; 2024-07-31: 20%; 2025-01-31: 20%; 2025-07-31: 20%; 2026-01-31: 20%; 2026-06-30: 5%
[6 empty] | 0% | 5% | 5% | 5% | 5% | 15% | 15% | 15% | 15% | 15% | 15% | 35% | 35% | 35% | 35% | 35% | 35% | 55% | 55% | 55% | 55% | 55% | 55% | 75% | 75% | 75% | 75% | 75% | 75% | 95% | 95% | 95% | 95% | 95% | 100%
| Sales Scheme 3 | SCH3 |  | 1 | 2023-09-30: 5%; 2024-04-30: 25%; 2025-01-31: 25%; 2025-10-31: 25%; 2026-06-30: 20%
[6 empty] | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 100%
| Sales Scheme 4 | SCH4 |  | 1.05 | 2023-09-30: 5%; 2024-07-31: 50%; 2025-07-31: 35%; 2026-06-30: 15%
[6 empty] | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 105%
198
|  | 198 | 198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Month | Quantity | Units | Sale Value | time axis 2023-07-31 to 2027-03-31
0 | 2023-07-31 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2023-08-31 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2023-09-30 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2023-10-31 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2023-11-30 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2023-12-31 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-01-31 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-02-29 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-03-31 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-04-30 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-05-31 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-06-30 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-07-31 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-08-31 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-09-30 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-10-31 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-11-30 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-12-31 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-01-31 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-02-28 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-03-31 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-04-30 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-05-31 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-06-30 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-07-31 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-08-31 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-09-30 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-10-31 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-11-30 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-12-31 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-01-31 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-02-28 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-03-31 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-04-30 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-05-31 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-06-30 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-07-31 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-08-31 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-09-30 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-10-31 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-11-30 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-12-31 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2027-01-31 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2027-02-28 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2027-03-31 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Assumptions
Particulars | Till Date | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | Total
Revenue
Sale Building | 1.15 | 18.04 | 21.72 | 18.49 | 44.44 | 91.33 | 0 | 195.17
Total Revenue | 1.15 | 18.04 | 21.72 | 18.49 | 44.44 | 91.33 | 0 | 195.17
Construction Cost | Till date | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | Total
Land & Stamp Duty | 21.26 | 30.15 | 0 | 0 | 0 | 0 | 0 | 30.15
Construction Cost | 12.68 | 30.34 | 31.4 | 25.29 | 8.48 | 0 | 0 | 95.51
Administrative Expenses | 0.15 | 0.85 | 1.34 | 1.24 | 0.752 | 0 | 0 | 4.182
Marketing Expenses | 0.19 | 0.69 | 1.25 | 1.29 | 0.58 | 0 | 0 | 3.81
Professional Charges | 0 | 0.05 | 0.2 | 0.2 | 0.15 | 0 |  | 0.6
Contingous Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest during moratorium period | 0 | 0.43 | 2.38 | 4.05 | 1.96 | 0 | 0 | 8.82
Total Cost Incurred | 34.28 | 62.51 | 36.57 | 32.07 | 11.922 | 0 | 0 | 143.072
Work Completed |  | 40.19% | 72.57% | 101% | 111.5% |  |  | 100%
Sales Completed |  | 9.243% | 20.37% | 29.85% | 52.62% |  |  | 100%
Cost of Sales |  | 8.9465 | 18.2216 | 22.2058 | 43.9411 |  |  | 93.3149
Sales Recognised |  | 7.2497 | 21.605 | 29.9617 | 55.7138 |  |  | 114.5302
Closing WIP |  | 87.8435 | 106.1919 | 116.0561 | 84.0371
Cash Collection |  | 1.15 | 18.04 | 21.72 | 18.49 |  |  | 59.4
Debtors |  | 6.0997 | 9.6647 | 17.9064 | 55.1302

## Cashflow Statement (hidden)
Particulars | FY24 | FY25 | FY26 | FY27 | Particulars | Total | 2023-03-30 | 2023-06-30 | 2023-09-30 | 2023-12-31 | 2024-03-31 | 2024-06-30 | 2024-09-30 | 2024-12-31 | 2025-03-31 | 2025-06-30 | 2025-09-30 | 2025-12-31 | 2026-03-31 | 2026-06-30 | 2026-09-30 | 2026-12-30 | 2027-03-30
Sources of the fund |  |  |  |  | Construction Cost | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Cash Generation From Sale | 18.04 | 21.72 | 18.49 | 44.44 | Approval Cost (FSI charges)+DC+Stair case+PT+( BMC Premium) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Increase in term loan | 0 | 13 | 14 | 0 | Architect & Consultancy Expenses | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Increase in Promoter's Contribution | 0 | 0 | #REF! | 0 | Admin & Marketing Expenses
Increase in Promoter's Contribution Loan | #REF! | #REF! | #REF! | 0 | Contingency | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Sources | #REF! | #REF! | #REF! | 44.44 | Rent Cost | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | Interest to Bank Finance upto construction period | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Applications of the fund |  |  |  |  | Interest on Unsecured Loan | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Project cost | 62.51 | 36.57 | 32.07 | 11.922 | Contingous Cost | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | Repayment of Term Loan | #REF! | 2025-09-30: 0; 2025-12-31: 0; 2026-03-31: #REF!; 2026-06-30: #REF!; 2026-09-30: #REF!; 2026-12-30: #REF!; 2027-03-30: 75
Repayment of Term Loan |  |  | #REF! | #REF! | Tax Payment | #REF! |  | 0.405 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Taxation | 0.405 | 0.64 | 0.685 | 2.345 | Total Cash Outflow | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Applications of the fund | 62.915 | 37.21 | #REF! | #REF!
[5 empty] | Collection |  | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Opening | 0 | #REF! | #REF! | #REF! | Surplus/Deficit |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Surplus/Deficit of the year | #REF! | #REF! | #REF! | #REF! | Cumulative Defict |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Closing | #REF! | #REF! | #REF! | #REF! | Promoter's Contribution | 90 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | Project specific Term Loan | 90 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | Opening Balance |  | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | Closing Balance |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Promoter's Contribution
Term Loan
[5 empty] | Promoter's | 15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | Promoters Loan | 75 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | Term Loan | 90 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## CF (2)
| STATEMENT OF CASH FLOW | Trio Infrastructure Private Limited
| PROPOSED LIMIT | 60 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 50 | As per prayush |  |  |  |  | Summary
| Quarter ended | Q0 | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q16 | Q17 | TOTAL
S. No. | PARTICULARS | Upto Oct-24 | 2024-12-01 | 2025-03-01 | 2025-06-01 | 2025-09-01 | 2025-12-01 | 2026-03-01 | 2026-06-01 | 2026-09-01 | 2026-12-01 | 2027-03-01 | 2027-06-01 | 2027-09-01 | 2027-12-01 | 2028-03-01 | 2028-06-01 | 2028-09-01 | 2028-12-01 | Total | Till const |  |  |  |  | Till FY 25 | FY26 | FY27 | FY28 | FY29
1 | CASH INFLOW
2 | Sale of Residential Regular | 12.29 | 3.5 | 3.4 | 5.17 | 5.37 | 5.46 | 5.72 | 5.23 | 4.32 | 4.42 | 3.52 | 2.65 | 1.73 | 1.43 | 30 | 31 | 32 | 28.56 | 185.77
3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3.4 |  |  |  |  | 9.4
4 | TOTAL INFLOW | 12.29 | 3.5 | 3.4 | 5.17 | 5.37 | 5.46 | 5.72 | 5.23 | 4.32 | 4.42 | 4.52 | 4.65 | 4.73 | 4.83 | 30 | 31 | 32 | 28.56 | 195.17 |  | 195.17
5 | Less : Land Owner's Share | [18 empty] | 0 |  | 0
6 | TOTAL INFLOW | 12.29 | 3.5 | 3.4 | 5.17 | 5.37 | 5.46 | 5.72 | 5.23 | 4.32 | 4.42 | 4.52 | 4.65 | 4.73 | 4.83 | 30 | 31 | 32 | 28.56 | 195.17 | 0 | 195.17
7 | COMULATIVE INFLOW (A) | 12.29 | 15.79 | 19.19 | 24.36 | 29.73 | 35.19 | 40.91 | 46.14 | 50.46 | 54.88 | 59.4 | 64.05 | 68.78 | 73.61 | 103.61 | 134.61 | 166.61 | 195.17 |  |  | 0
[20 empty] | 0 |  | 0
8 | CASH OUTFLOW | [18 empty] | 0 |  | 0
9 | Acquisition cost of land | 21.26 | 8.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 30.15 | 30.15 | 0 | 30.15 | 0 | Acquisition cost of land | 30.15 | 0 | 0 | 0 | 0 | 30.15 | 0
10 | Cost of Permission | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | Cost of Permission | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Construction Cost | 12.68 | 9.81 | 7.85 | 7.85 | 7.85 | 7.85 | 7.85 | 7.16 | 6.37 | 6.37 | 5.39 | 3.43 | 2.94 | 2.11 |  |  |  |  | 95.51 | 95.51 | 0 | 95.51 | 0 | Construction Cost | 30.34 | 31.4 | 25.29 | 8.48 | 0 | 95.51 | 0
13 | Administrative Expenses | 0.15 | 0.35 | 0.35 | 0.35 | 0.35 | 0.32 | 0.32 | 0.32 | 0.32 | 0.3 | 0.3 | 0.25 | 0.25 | 0.25 | 0.132 | 0.1452 | 0.1452 | 0.1452 | 4.7476 | 4.18 | 0.5676 | 4.78 | 0.6 | Administrative Expenses | 0.85 | 1.34 | 1.24 | 0.882 | 0.4356 | 4.7476 | 0.5676
14 | Marketing Expenses | 0.19 | 0.25 | 0.25 | 0.3 | 0.31 | 0.32 | 0.32 | 0.32 | 0.33 | 0.34 | 0.3 | 0.25 | 0.25 | 0.17 | 0 | 0 | 0 | 0 | 3.9 | 3.9 | 0 | 3.9 | 0 | Marketing Expenses | 0.69 | 1.25 | 1.29 | 0.67 | 0 | 3.9 | 0
15 | Professional Charges | 0 | 0 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  |  |  |  | 0.6 | 0.6 | 0 | 0 | -0.6 | Professional Charges | 0.05 | 0.2 | 0.2 | 0.15 | 0 | 0.6 | 0
16 | Contingous Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | Contingous Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Interest during moratorium period | 0 | 0.12 | 0.31 | 0.44 | 0.54 | 0.65 | 0.75 | 0.86 | 0.96 | 1.06 | 1.17 | 1.26 | 1.33 | 1.4 | 1.31 | 1.07 | 0.71 | 0.24 | 14.18 | 10.85 | 3.33 | 10.85 | 0 | Interest during moratorium period | 0.43 | 2.38 | 4.05 | 5.3 | 2.02 | 14.18 | 3.33
18 | Payment of Income Tax | 0 | [17 empty] | 0 |  | 0 |  |  |  | 62.51 | 36.57 | 32.07 | 15.482 | 2.4556 | 149.0876
19 | Other Current Assets | 0 | 2027-03-01: 1; 2027-06-01: 2; 2027-09-01: 3; 2027-12-01: 3.4; 2028-12-01: -9.4 | 0 |  | 0 |  | 149.0876 |  |  | 5.17 | 6.78 | 7.002
20 | Advances to Suppliers / Investment | 0 | [17 empty] | 0 |  | 0 |  | 195.17
21 | TOTAL OUTFLOW | 34.28 | 19.42 | 8.81 | 8.99 | 9.1 | 9.19 | 9.29 | 8.71 | 8.03 | 8.12 | 8.21 | 7.24 | 7.82 | 7.38 | 1.442 | 1.2152 | 0.8552 | -9.0148 | 149.0876 |  | 149.0876 |  | 46.0824
22 | COMULATIVE OUTFLOW (B) | 34.28 | 53.7 | 62.51 | 71.5 | 80.6 | 89.79 | 99.08 | 107.79 | 115.82 | 123.94 | 132.15 | 139.39 | 147.21 | 154.59 | 156.032 | 157.2472 | 158.1024 | 149.0876 | 149.0876 |  | 149.0876
23 | NET FLOW ( B-A) IN DEBIT BALANCE (GAP) (C) | 21.99 | 37.91 | 43.32 | 47.14 | 50.87 | 54.6 | 58.17 | 61.65 | 65.36 | 69.06 | 72.75 | 75.34 | 78.43 | 80.98 | 52.422 | 22.6372 | -8.5076 | -46.0824 |  |  | 0
24 | PROMOTER CONTRIBUTION | 20.5 | [17 empty] | 20.5 |  | 20.5
25 | Unsecured Loans | 1.49 | 8 | 0.5 | 0.5 | 0.5 | 0.5 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.21 |  |  |  |  | 14.5 |  | 14.5
26 | CUMULATIVE PROMOTERS CONTRIBUTION (D) | 21.99 | 29.99 | 30.49 | 30.99 | 31.49 | 31.99 | 32.39 | 32.79 | 33.19 | 33.59 | 33.99 | 34.39 | 34.79 | 35 | 35 | 35 | 35 | 35 |  |  | 0
27 | Net Gap | 0 | 7.92 | 12.83 | 16.15 | 19.38 | 22.61 | 25.78 | 28.86 | 32.17 | 35.47 | 38.76 | 40.95 | 43.64 | 45.98 | 17.42 | -12.36 | -43.51 | -81.08 |  |  | 0
28 | BANK FUNDING (C-D) | 0 | 7.92 | 12.83 | 16.15 | 19.38 | 22.61 | 25.78 | 28.86 | 32.17 | 35.47 | 38.76 | 40.95 | 43.64 | 45.98 | 17.42 | -12.36 | -43.51 | -81.08 |  |  | 0
29 | Bank Funding During the Quarter |  | 7.92 | 4.91 | 3.32 | 3.23 | 3.23 | 3.17 | 3.08 | 3.31 | 3.3 | 3.29 | 2.19 | 2.69 | 2.34 | [6 empty] | 0
30 | REPAYMENT* |  | 2028-03-01: 8; 2028-06-01: 8; 2028-09-01: 16; 2028-12-01: 16 | 48 |  | 48
31 | LOAN BALANCE /OUTSTANDING* |  | 8 | 13 | 16.5 | 20 | 23.5 | 27 | 30.5 | 34 | 37.5 | 41 | 43.5 | 46 | 48 | 40 | 32 | 16 | 0 |  |  | 0
32 | BALANCE IN ESCROW AC OR CURRENT AC | 0 | -0.08 | -0.17 | -0.35 | -0.62 | -0.89 | -1.22 | -1.64 | -1.83 | -2.03 | -2.24 | -2.55 | -2.36 | -2.02 | -22.58 | -44.36 | -59.51 | -81.08 | 0
33 | BANK FUNDING/GAP (%) | 0 | 20.8916 | 29.6168 | 34.2597 | 38.0971 | 41.4103 | 44.3184 | 46.8127 | 49.2197 | 51.3611 | 53.2784 | 54.3536 | 55.642 | 56.7795 | 33.2303 | -54.6004 | 511.4251 | 175.9457
34 | BANK FUNDING / TOTAL COST (%) | 0 | 5.3123 | 8.6057 | 10.8326 | 12.9991 | 15.1656 | 17.2918 | 19.3577 | 21.5779 | 23.7914 | 25.9981 | 27.4671 | 29.2714 | 30.8409 | 11.6844 | -8.2904 | -29.1842 | -54.3841 | 0
|  | 0 | 7.92 | 4.91 | 3.32 | 3.23 | 3.23 | 3.17 | 3.08 | 3.31 | 3.3 | 3.29 | 2.19 | 2.69 | 2.34 | 45.98
|  |  | 8 | 5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 2.5 | 2.5 | 2 | 48 | 0
|  | 0 | -0.08 | -0.09 | -0.18 | -0.27 | -0.27 | -0.33 | -0.42 | -0.19 | -0.2 | -0.21 | -0.31 | 0.19 | 0.34
| Cumlative Capital | 21.99 | 29.99 | 30.49 | 30.99 | 31.49 | 31.99 | 32.39 | 32.79 | 33.19 | 33.59 | 33.99 | 34.39 | 34.79 | 35
| Cumlative Loan | 0 | 7.92 | 12.83 | 16.15 | 19.38 | 22.61 | 25.78 | 28.86 | 32.17 | 35.47 | 38.76 | 40.95 | 43.64 | 45.98
| Debt Equity |  | 0.26409 | 0.42079 | 0.52114 | 0.61543 | 0.70678 | 0.79592 | 0.88015 | 0.96927 | 1.056 | 1.1403 | 1.1908 | 1.2544 | 1.3137
| Cum Cons Cost | 12.68 | 22.49 | 30.34 | 38.19 | 46.04 | 53.89 | 61.74 | 68.9 | 75.27 | 81.64 | 87.03 | 90.46 | 93.4 | 95.51
| Comp % | 13.2761 | 23.5473 | 31.7663 | 39.9853 | 48.2044 | 56.4234 | 64.6424 | 72.139 | 78.8085 | 85.478 | 91.1213 | 94.7126 | 97.7908 | 100
| Cum Loan | 0 | 7.92 | 12.83 | 16.15 | 19.38 | 22.61 | 25.78 | 28.86 | 32.17 | 35.47 | 38.76 | 40.95 | 43.64 | 45.98
| Cum Loan % | 0 | 17.2249 | 27.9034 | 35.124 | 42.1488 | 49.1736 | 56.0679 | 62.7664 | 69.9652 | 77.1422 | 84.2975 | 89.0605 | 94.9108 | 100
|  |  | -6.3224 | -3.8629 | -4.8614 | -6.0556 | -7.2499 | -8.5746 | -9.3726 | -8.8433 | -8.3357 | -6.8238 | -5.6521 | -2.88 | 0
| Project Cost | 34.28 | 19.42 | 8.81 | 8.99 | 9.1 | 9.19 | 9.29 | 8.71 | 8.03 | 8.12 | 7.21 | 5.24 | 4.82 | 3.98 | 145.19 | -1.763
| Construction Cost | 12.68 | 9.81 | 7.85 | 7.85 | 7.85 | 7.85 | 7.85 | 7.16 | 6.37 | 6.37 | 5.39 | 3.43 | 2.94 | 2.11 | 95.51 | -2.633

## P&L
[5 empty] | 25% | 35% | 50%
Particulars | FY 23-24 | FY 24-25 | FY 25-26 | FY 26-27 | FY 27-28 | FY 28-29 | FY 29-30 | Total
Revenue | [10 empty] | 195.17 | 145.19
Sales | 1.15 | 18.04 | 21.72 | 18.49 | 44.44 | 91.33 | 0 | 195.17 | 1.15 |  | 18.04 | 13.4202
Closing WIP - | 32.79 | 45.79 | 63.2 | 79.52 | 59.942 | 0.8 | 0 |  |  |  | 18.49 | 13.755
Total Revenue | 33.94 | 63.83 | 84.92 | 98.01 | 104.382 | 92.13 | 0 | 0 |  |  | 44.44 | 33.0596
Expenses
Expenses incurred during the year | 33.09 | 29.42 | 36.57 | 32.07 | 15.482 | 2.4556 | 0 | 149.0876
Opening WIP - | 0.8 | 32.79 | 45.79 | 63.2 | 79.52 | 59.942 | 0 | 0
Operating Profit | 0.05 | 1.62 | 2.56 | 2.74 | 9.38 | 29.7324 | 0 | 46.0824 | 46.0824 | 0
PBT | 0.05 | 1.62 | 2.56 | 2.74 | 9.38 | 29.7324 | 0 | 46.0824
Tax | 0 | 0.405 | 0.64 | 0.685 | 2.345 | 7.4331 | 0 | 11.5081
PAT | 0.05 | 1.215 | 1.92 | 2.055 | 7.035 | 22.2993 | 0 | 34.5743

## Balance Sheet
INR in Crore
Particulars | FY 23-24 | FY 24-25 | FY 25-26 | FY 26-27 | FY 27-28 | FY 28-29
Shareholder Funds | 3.7 | 21.505 | 23.425 | 25.48 | 32.515 | 54.8143
Share capital | 3.91 | 20.5 | 20.5 | 20.5 | 20.5 | 20.5
Reserve & Surplus | -0.21 | 1.005 | 2.925 | 4.98 | 12.015 | 34.3143
Non current Liabilities | 12.82 | 25 | 40.9 | 56.5 | 56.51 | 16.51
Term Loan | 0 | 13 | 27 | 41 | 40 | 0
Promotors Loan | 12.82 | 12 | 13.9 | 15.5 | 16.51 | 16.51 | 0
Current Liabilities | 22.51 | 4.86 | 4.3 | 21.81 | 14.81 | 0.57
Unsecured loan
Advance received | 2.17 | 3.96 | 3.31 | 19.2 | 11.25 | 0
Sundry Creditors | 0.63 | 0.6 | 0.66 | 1.12 | 1.23 | 0.01
Provision | 0.34 | 0.3 | 0.33 | 0.56 | 0.62 | 0.01
Others | 19.37 | 0 | 0 | 0.93 | 1.71 | 0.55
0
Total Liabilities | 39.03 | 51.365 | 68.625 | 103.79 | 103.835 | 71.8943
Asset
Non Current Assets
Fixed Assets | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13
|  | 0 | 0
Project WIP | 32.79 | 45.79 | 63.2 | 79.52 | 59.942 | 0.8
Current Assets
Advance for Plots | 0 | 0 | 0 | 15 | 25 | 60
Sundry Debtors | FY 23-24: 0.49; FY 24-25: 0.22
other current assets |  | 0 | 0 | 1 | 9.4 | 0
Loans & Advances | 4.72 | 1.51 | 2.09 | 1.5 | 1.75 | 1.8
Cash & Cash Equivalent | 0.9 | 1.12 | 0.61 | 4.04 | 5.02 | 6.55
Total Current Assets | 38.9 | 48.64 | 65.9 | 101.06 | 101.112 | 69.15
Total | 39.03 | 48.77 | 66.03 | 101.19 | 101.242 | 69.28
| 0 | -2.595 | -2.595 | -2.6 | -2.593 | -2.6143
Differ | 0 | 2.595 | 2.595 | 2.6 | 2.593 | 2.6143

## Financial Analysis
DSCR Ratio
Particular | FY24 | FY25 | FY26 | FY27 | FY28 | FY29
EBITDA | 0.05 | 2.05 | 4.94 | 6.79 | 14.68 | 31.7524 |  | 60.2624
Interest on Term Loan | 0 | 0.43 | 2.38 | 4.05 | 5.3 | 2.02 |  | 14.18
Repayment of Term Loan | 0 | 0 | 0 | 0 | 8 | 40 |  | 46.0824
Coverage | 0.05 | 2.48 | 7.32 | 10.84 | 27.98 | 73.7724 |  | 46.0824
Debt Service | 0 | 0.43 | 2.38 | 4.05 | 13.3 | 42.02 |  | 0 |  |  | ROI | 11.9
DSCR | 0 | 5.7674 | 3.0756 | 2.6765 | 2.1038 | 1.7556
Average DSCR | FY24: 2.5632
Interest Coverage Ratio
Particular | FY24 | FY25 | FY26 | FY27 | FY28 | FY29
EBIT | 0.05 | 2.12 | 5.34 | 7.46 | 15.57 | 32.0924
Interest on Term Loan | 0 | 0.43 | 2.38 | 4.05 | 5.3 | 2.02
Interest Coverage Ratio | 0 | 4.9302 | 2.2437 | 1.842 | 2.9377 | 15.8873
Avergage Interest Coverage Ratio | FY24: 4.6402
[9 empty] | period | Expected CF | PV | IRR
Project IRR
Particular | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 |  |  | 1 | -31.94 | -2.476 | -2.476
Cash Inflow | [8 empty] | 2 | -11.38 | -0.88217 | -0.88217
Amount Received | 1.15 | 18.04 | 21.72 | 18.49 | 44.44 | 91.33 |  |  | 3 | -14.85 | -1.1512 | -1.1512
Cash Outfow | [8 empty] | 5 | -13.58 | -1.0527 | -1.0527
Cash outflow | 33.09 | 29.42 | 36.57 | 32.07 | 15.482 | 2.4556 |  |  | 5 | 28.958 | 2.2448 | 2.2448
Net Cashflow | -31.94 | -11.38 | -14.85 | -13.58 | 28.958 | 88.8744 |  |  | 6 | 88.8744 | 6.8895 | 6.8895
[11 empty] | 3.5723 | 3.5723
Internal Rate of Return | FY24: 14.38% |  | 14.38%
NPV
Sensitivity Analysis
Particulars | Average DSCR | Avg Interest Coverage ratio | Min. DSCR | Min.Int Cov.Ratio | IRR | Actual return of Project | NPV
Base Case | 2.5632 | 4.6402 | 1 | 1.5 | 14.38% | 17.71% | 3.5723
Sales reduce by 5% | 2.53 | 3.88 | 1 | 1.5 | 12.41% | 15.37% | 2.98
Price reduce by 5% | 2.53 | 3.89 | 1 | 1.5 | 12.48% | 15.45% | 3
Cost increase by 5% | 2.55 | 4.14 | 1 | 1.5 | 12.92% | 16.15% | 3.25
Interest cost increase by 2% | 2.42 | 3.81 | 1 | 1.5 | 13.65% | 16.8% | 3.39
Note : 1) Actual return of project is higher than IRR, accordingly project is feasible
2) NPV of the project is Positive , Accordingly the project is feasible
Note on L21: Author:

## Loan Schedule (hidden)
Rate of Interest | 12.15%
INR in Crore
Particulars | FY24 | FY25 | FY26 | FY27
Loan Disburement | 31.5 | 36 | 9 | 0
Interest Payment | 0 | 9.8643 | 3.5311 | 0
Loan Repayment | 0 | 22.5 | 67.5 | 0
Year | Month | Montly Disbursment | Outstanding Amount |  | Repayment | Monthly Interest | Yearly Interest | Yearly Reimbursment
|  |  | Start of Month | End of Month
FY24 | April |  | 0 | 0 | 0 | 0 | 0 | 0
| May | 0 | 0 | 0 | 0 | 0
| June | 0 | 0 | 0 | 0 | 0
| July | 13.5 | 0 | 13.5 | 0 | 0.068344
| August | 0 | 13.5 | 13.5 | 0 | 0.13669
| September | 13.5 | 13.5 | 27 | 0 | 0.20503
| October |  | 27 | 27 | 0 | 0.27337
| November |  | 27 | 27 | 0 | 0.27337
| December | 9 | 27 | 36 | 0 | 0.31894
| January |  | 36 | 36 | 0 | 0.3645
| February |  | 36 | 36 | 0 | 0.3645
| March | 9 | 36 | 45 | 0 | 0.41006
FY25 | April |  | 45 | 45 | 0 | 0.45563 | 9.8643 | 22.5
| May |  | 45 | 45 | 0 | 0.45563
| June | 13.5 | 45 | 58.5 | 0 | 0.52397
| July |  | 58.5 | 58.5 | 0 | 0.59231
| August |  | 58.5 | 58.5 | 0 | 0.59231
| September | 9 | 58.5 | 67.5 |  | 0.63787
| October |  | 67.5 | 67.5 | 0 | 0.68344
| November |  | 67.5 | 67.5 | 0 | 0.68344
| December | 4.5 | 67.5 | 72 |  | 0.70622
| January |  | 72 | 72 |  | 0.729
| February |  | 72 | 72 |  | 0.729
| March | 9 | 72 | 58.5 | 22.5 | 0.66066
FY26 | April |  | 58.5 | 58.5 |  | 0.59231 | 3.5311 | 67.5
| May |  | 58.5 | 58.5 |  | 0.59231
| June | 9 | 58.5 | 45 | 22.5 | 0.52397
| July |  | 45 | 45 |  | 0.45563
| August |  | 45 | 45 |  | 0.45563
| September |  | 45 | 22.5 | 22.5 | 0.34172
| October |  | 22.5 | 22.5 |  | 0.22781
| November |  | 22.5 | 22.5 |  | 0.22781
| December |  | 22.5 | 0 | 22.5 | 0.11391
| January |  | 0 | 0 |  | 0
| February |  | 0 | 0 |  | 0
| March |  | 0 | 0 |  | 0
FY27 | April |  | 0 | 0 |  | 0 | 0 | 0
| May |  | 0 | 0 |  | 0
| June |  | 0 | 0 | 0 | 0
| July |  | 0 | 0 |  | 0
| August |  | 0 | 0 |  | 0
| September |  | 0 | 0 | 0 | 0
| October |  | 0 | 0 |  | 0
| November |  | 0 | 0 |  | 0
| December |  | 0 | 0 | 0 | 0
| January |  | 0 | 0 |  | 0
| February |  | 0 | 0 |  | 0
| March |  | 0 | 0 | 0 | 0
Total |  |  |  |  | 90 | 13.3954 | 13.3954 | 90

## Assumption Sheet (hidden)
PROJECT:
Assumption
Cost Assumptions
Particulars |  |  | Rate |  |  | Type | RERA Area | Total Units |  |  | Sold Units |  |  | Inventory
Interest Rate construction funding |  |  | 11.75% |  |  |  | Sq. M | RB | RB | SB | AB | RB1 | SB | AB 2 | RB1 | SB
Sales, Marketing, Branding & Advertising Cost on Sales |  |  | 5% |  |  | 1BHK | 29.45 | 0 | 0 | 20 | 0 | 0 | 11 | 0 | 0 | 9
Contigencies on Total Cost |  |  | 1% |  |  | 1BHK | 30.01 | 0 | 0 | 145 | 0 | 0 | 0 | 0 | 0 | 145
Income Tax Rate |  |  | 30% |  |  | 1BHK | 39.76 | 0 | 0 | 20 | 0 | 0 | 7 | 0 | 0 | 13
[6 empty] | 1BHK | 41.43 | 0 | 0 | 23 | 0 | 0 | 1 | 0 | 0 | 22
[6 empty] | 1BHK | 41.53 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 23
[6 empty] | 1BHK | 41.81 | 0 | 0 | 22 | 0 | 0 | 3 | 0 | 0 | 19
[6 empty] | 1BHK | 42.08 | 0 | 0 | 23 | 0 | 0 | 1 | 0 | 0 | 22
[6 empty] | 1BHK | 42.46 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 21
[6 empty] | 1BHK | 43.57 | 0 | 0 | 21 | 0 | 0 | 11 | 0 | 0 | 10
Construction Schedule | [5 empty] | Total |  | 0 | 0 | 318 | 0 | 0 | 34 | 0 | 0 | 284
Building | Start Date | End Date | Duration |  |  | Sale Price
AB2 | 2023-03-31 | 2025-11-30 | 32 |  |  | Galleria Rent/Sq. ft./Month |  |  |  | 90
RB1 | 2023-03-31 | 2025-11-30 | 32 |  |  |  | Area in Sq. Ft | Rate per Sq. Ft | 2021-03-31 | 2022-03-31 | 2023-03-31 | 2024-03-31
SB | 2023-03-31 | 2025-11-30 | 32 |  |  | 1BHK | 302 | 0 | 0 | 0 | 0 | 0
[6 empty] | 2BHK | 803 | 0 | 0 | 0 | 0 | 0
[6 empty] | 3++ BHK | 1115 | 0 | 0 | 0 | 0 | 0
Construction Area & Cost of consultant | [5 empty] | 4++BHK | 1675 | 0 | 0 | 0 | 0 | 0
` | AB 2 | RB1 | SB |  | Total Cost (Rs. In Crore) | Shop & Office | 500 | 0 | 0 | 0 | 0 | 0
Construction Area (in Sq. ft) | 0 | 14424.73 | 27417.85 |  |  | Yearly Sales Increment
Cpnstruction Cost/Sq. Ft. |  |  |  | 41842.58
Construction Cost | #REF! | #REF! | #REF! |  | #REF! | Sales Receivable
Approval Cost (FSI charges)+DC+Stair case+PT+( BMC Premium) | #REF! | #REF! | #REF! |  | #REF! | Month | Milestone | % Completion | Cumulative
Architect & Consultancy Expenses | #REF! | #REF! | #REF! |  | #REF! | 2023-07-01 | Booking | 5% | 5%
Admin & Marketing Expenses | #REF! | #REF! | #REF! |  | #REF! | 2023-10-31 | Plinth | 5% | 10%
Contingency | #REF! | #REF! | #REF! |  | #REF! | 2024-01-31 | Slab 1 | 1% | 11%
Rent Cost | #REF! | #REF! | #REF! |  | #REF! | 2024-04-30 | Slab 2 | 1% | 12%
Interest to Bank Finance upto construction period | #REF! | #REF! | #REF! |  | #REF! | 2024-07-31 | Slab 3 | 1% | 13%
Interest on Unsecured Loan | #REF! | #REF! | #REF! |  | #REF! | 2024-10-31 | Slab 4 | 1% | 14%
[6 empty] | 2025-01-31 | Slab 5 | 1% | 15% |  | #VALUE!
Total Cost | #REF! | #REF! | #REF! |  | #REF! | 2025-04-30 | Slab 6 | 1% | 16%
[6 empty] | 2025-07-31 | Slab 7 | 1% | 17%
Land Cost | [5 empty] | 2025-10-31 | Slab 8 | 1% | 18%
Building | Const Land Area (sqm) | Land Cost |  |  |  | 2026-01-31 | Slab 9 | 1% | 19%
AB2 | 0 | 0 |  |  |  | 2026-04-30 | Slab 10 | 1% | 20%
RB1 | 14424.73 | 0.15168 |  |  |  | 2026-07-31 | Slab 11 | 2% | 22%
SB | 27417.85 | 0.28832 |  |  |  | 2026-10-31 | Slab 12 | 2% | 24%
Total | 41842.58 | 0.44 |  |  |  | 2027-01-31 | Slab 13 | 2% | 26%
[6 empty] | 2027-04-30 | Slab 14 | 2% | 28%
[6 empty] | 2027-07-31 | Slab 15 | 2% | 30%
[6 empty] | 2027-10-31 | Slab 16 | 2% | 32%
[6 empty] | 2028-01-31 | Slab 17 | 2% | 34%
[6 empty] | 2028-04-30 | Slab 18 | 2% | 36%
[6 empty] | 2028-07-31 | Slab 19 | 2% | 38%
[6 empty] | 2028-10-31 | Slab 20 | 2% | 40%
[6 empty] | 2029-01-31 | Slab 21 | 2% | 42%
[6 empty] | 2029-04-30 | Slab 22 | 2% | 44%
[6 empty] | 2029-07-31 | Slab 23 | 2% | 46%
[6 empty] | 2029-10-31 | Slab 24 | 2% | 48%
[6 empty] | 2030-01-31 | Slab 25 | 2% | 50%
[6 empty] | 2030-04-30 | Slab 26 | 2% | 52%
[6 empty] | 2030-07-31 | Slab 27 | 2% | 54%
[6 empty] | 2030-10-31 | Slab 28 | 2% | 56%
[6 empty] | 2031-01-31 | Slab 29 | 2% | 58%
[6 empty] | 2031-04-30 | Slab 30 | 2% | 60%
[6 empty] | 2031-07-31 | Slab 31 | 2% | 62%
[6 empty] | 2031-10-31 | Slab 32 | 2% | 64%
[6 empty] | 2032-01-31 | Slab 33 | 2% | 66%
[6 empty] | 2032-04-30 | Slab 34 | 2% | 68%
[6 empty] | 2032-07-31 | Slab 35 | 2% | 70%
[6 empty] | 2032-10-31 | Slab 36 | 2% | 72%
[6 empty] | 2033-01-31 | Slab 37 | 2% | 74%
[6 empty] | 2033-04-30 | Slab 38 | 2% | 76%
[6 empty] | 2033-07-31 | Slab 39 | 2% | 78%
[6 empty] | 2033-10-31 | Slab 40 | 2% | 80%
[6 empty] | 2034-01-31 | Possession | 15% | 95%
Formulas:
End Date = EOMONTH([Start Date],32)
Rate = DATEDIF([Start Date],[End Date],"m")+1
Start Date = [Start Date, row above]
Type = EOMONTH([Type, row above],3)

## Summary
PROJECT:
Summary
Sales Velocity
Value |  | 2024-03-31 | 2025-03-31 | 2026-03-31 | 2027-03-31 | 2028-03-31 | 2029-03-31 | Total
Sale Building |  | 1.15 | 18.04 | 21.72 | 18.49 | 44.44 | 91.33 | 195.17
Total Sale Value | in Cr. | 1.15 | 18.04 | 21.72 | 18.49 | 44.44 | 91.33 | 195.17
Cashflow
| Total | 2024-03-31 | 2025-03-31 | 2026-03-31 | 2027-03-31 | 2028-03-31 | 2029-03-31
Cash inflow
Sales Receivables
Sale Building | 195.17 | 1.15 | 18.04 | 21.72 | 18.49 | 44.44 | 91.33
Total Cash Receipts | 195.17 | 1.15 | 18.04 | 21.72 | 18.49 | 44.44 | 91.33
Cash out flow
Land Cost | 30.15 | 30.15 | 0 | 0 | 0 | 0 | 0
Construction Cost | 95.51 | 3.24 | 27.1 | 31.4 | 25.29 | 8.48 | 0
Administrative Expenses | 0 | 2028-03-31: 0; 2029-03-31: 0
SB | 4.4876 | 0.85 | 1.34 | 1.24 | 0.752 | 0.3056 | 0
Marketing Expenses | 0
SB | 3.9 | 0.69 | 1.25 | 1.29 | 0.58 | 0.09 | 0
Professional Charges |  | 2028-03-31: 0; 2029-03-31: 0
SB | 0.6 | 0.05 | 0.2 | 0.2 | 0.15 | 0 | 0
Interest to Bank Finance upto construction period | 0
SB | 14.18 | 0.43 | 2.38 | 4.05 | 5.3 | 2.02
Contingous Cost |  | 2028-03-31: 0; 2029-03-31: 0
SB | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost | 148.8276 | 35.41 | 32.27 | 38.18 | 32.072 | 10.8956 | 0
Profit Before Interest & Tax | 46.3424 | -34.26 | -14.23 | -16.46 | -13.582 | 33.5444 | 91.33
Interest Cost | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Loan principal payment | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Income Tax | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Profit after Interest & Tax | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Owners Fund | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Loan Drawdown | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Cash inflow | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Cumulative Cash Inflow |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
DSRA |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Means of Finance
PAT |  | #REF! | 0 | 0 | 0 | 0 | 0
Interest |  | #REF! | 0 | 0 | 0 | 0 | 0
Repayment Amount |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Total inflow |  | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Application of Funds
Interest |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Repayment Amount |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Total Outflow |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Budgeted Cost | 2027-03-31: Incurred Cost
Construction Cost Break up | AB | RB1 | SB | Total Cost | AB | AB | AB | RB1 | SB | Total Cost
Land Cost | 0 | 0 | 30.15 | 30.15 | 0 | 0 | 0 | 0 | 21.26 | 21.26
Construction Cost | 0 | 0 | 95.51 | 95.51 | 0 | 0 | 0 | 0 | 12.68 | 12.68
Approval Cost (FSI charges)+DC+Stair case+PT+( BMC Premium) | 0 | 0 | 4.182 | 4.182 | 0 | 0 | 0 | 0 | 0.15 | 0.15
Architect & Consultancy Expenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stamp duty cost |  |  | 3.81 | 3.81 | 0 | 0 | 0 | 0 | 0.19 | 0.19
Contingency |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rent Cost | 0 | 0 | 0.6 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0
Interest to Bank Finance upto construction period | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest on Unsecured Loan | 0 | 0 | 8.82 | 8.82 | 0 | 0 | 0 | 0 | 0 | 0
GST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Development Cost | 0 | 0 | 143.072 | 143.072 | 0 | 0 | 0 | 0 | 34.28 | 34.28
Contingencies | - | 2024-03-31: -; 2025-03-31: -; 2026-03-31: 0
Interest Cost | 0 | 2024-03-31: 0; 2025-03-31: 0; 2026-03-31: 0
Total Cost | 0 | 0 | 143.072 | 143.072 | 0 | 0 | 0 | 0 | 34.28 | 34.28

## Snap Shot (hidden)
PROJECT: Nicco Residency
Snapshot
PROJECT COST |  | TOTAL | Incurred | After Mar-23
Land Cost | Cr | #REF! | 21.26 | #REF!
Construction Cost | Cr | #REF! | #REF! | #REF!
Contingencies | Cr | #REF! | 0 | #REF!
Interest Expenses | Cr | #REF! | #REF! | #REF!
Total Project Cost | Cr | #REF! | #REF! | #REF!
MEANS OF FINANCE |  | TOTAL | Till June 23 | After June 23
Promoter Contribution | Cr | 90 | 70.19 | 19.81
Proposed Loan | Cr | 90 | 0 | 90
Advance Booking/Sales revenue | Cr | 147.75 | 3.2 | 88.59 | 35%
Balance Carried forward | Cr |  |  | #REF! | 65%
TOTAL | Cr | 327.75 | 73.39 | #REF!
|  | #REF! |  | #REF!

## Tax Working (hidden)
PROJECT: Nicco Residency
Tax Working
|  | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2022-03-31 | 2022-03-31 | 2022-03-31 | 2022-03-31 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2024-03-31
| Total | 2023-09-30 | 2023-12-31 | 2024-03-31 | 2024-06-30 | 2024-09-30 | 2024-12-31 | 2025-03-31 | 2025-06-30 | 2025-09-30 | 2025-12-31 | 2026-03-31 | 2026-06-30 | 2026-09-30 | 2026-12-31 | 2027-03-31 | Total
Sales Recognition |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | bar: 2027-03-31
Resi Cost of Sales |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | bar: 2027-03-31
PBDIT | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Interest Cost | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
PBT | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Tax | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
PAT | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Tax Rate | 30%
Income Tax Calculation
PBT |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Tax |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
PAT |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Working notes:
Actual Sales Value (AB, RB & SB) |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
% of Total Sale Value |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Cost Incurred (AB, RB & SB) |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
%of Cost |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Sales recognition |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Cost recognition |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## R4 Pre Sales-Recovery (hidden)
Possession date | 2023-12-31 |  | 1BHK | 38
|  |  | 2BHK-S | 7
|  |  | 2BHK-L | 64
|  |  | 3BHK | 14
|  |  | 4BHK | 6
|  |  |  | 129 |  |  |  |  | 0 | 2020-06-30 | 2020-09-30 | 2020-09-30 | 2020-09-30 | 2020-12-31 | 2020-12-31 | 2020-12-31 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 2021-09-30 | 2021-09-30 | 2021-09-30 | 2021-12-31 | 2021-12-31 | 2021-12-31 | 2022-03-31 | 2022-03-31 | 2022-03-31 | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-12-31 | 2022-12-31 | 2022-12-31 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-12-31 | 2023-12-31 | 2023-12-31 | 2024-03-31 | 2024-03-31 | 2024-03-31
[7 empty] | 1625072070.7568 | 127127852.25 | 1497944218.5068 | 0 | 0 | 0 | 0 | 0 | 0 | 15196837.6286 | 0 | 0 | 0 | 0 | 0 | 162460736.6618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162507207.0757 | 0 | 0 | 0 | 0 | 0 | 1049526575.7919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108252861.3488 |  |  |  | 19513154.3545 | 8894445.9701
Sr.no. | Building | Type | Registered/Unregistered | Date of booking | Plan | Scheme | Flat Cost | Net Collection | EMI Amount | 2020-06-30 | 2020-07-31 | 2020-08-31 | 2020-09-30 | 2020-10-31 | 2020-11-30 | 2020-12-31 | 2021-01-31 | 2021-02-28 | 2021-03-31 | 2021-04-30 | 2021-05-31 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30 | 2022-12-31 | 2023-01-31 | 2023-02-28 | 2023-03-31 | 2023-04-30 | 2023-05-31 | 2023-06-30 | 2023-07-31 | 2023-08-31 | 2023-09-30 | 2023-10-31 | 2023-11-30 | 2023-12-31 | 2024-03-31 | 2024-03-31 | 2024-03-31 | Due | Advance
1 | R4 | 1BHK | R | 2019-10-08 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7630630.6306 | 763062.8571 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 4959909.9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381531.7375 |  |  |  | 0.20592 | 0 | 0
2 | R4 | 1BHK | R | 2019-10-05 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7630630.6306 | 763062.8571 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 4959909.9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381531.7375 |  |  |  | 0.20592 | 0 | 0
3 | R4 | 1BHK | R | 2019-10-10 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7630630.6306 | 763062.8571 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 4959909.9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381531.7375 |  |  |  | 0.20592 | 0 | 0
4 | R4 | 2BHK-S | R | 2019-10-05 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1213513.3333 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606756.9369 |  |  |  | 0.18018 | 0 | 0
5 | R4 | 1BHK | R | 2019-10-06 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7630630.6306 | 759729.5238 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 4959909.9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384865.0708 |  |  |  | 3333.5393 | 0 | 0
6 | R4 | 1BHK | UR | 2019-10-14 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7630630.6306 | 809523.8095 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 716602.3166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 4959909.9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381531.5315 |  |  |  | 0 | 46460.7465 | 0
7 | R4 | 1BHK | R | 2019-10-02 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7630630.6306 | 763062.8571 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 4959909.9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381531.7375 |  |  |  | 0.20592 | 0 | 0
8 | R4 | 1BHK | R | 2019-10-14 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7630630.6306 | 529180.9762 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 4959909.9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 615413.6184 |  |  |  | 286872.5869 | 0 | 0
9 | R4 | 1BHK | R | 2019-10-08 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7630630.6306 | 761246.6381 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 4959909.9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383347.9565 |  |  |  | 1816.425 | 0 | 0
10 | R4 | 1BHK | R | 2019-09-23 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7630630.6306 | 757612.381 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 4959909.9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 386982.2136 |  |  |  | 5450.6821 | 0 | 0
11 | R4 | 2BHK-L | R | 2019-10-11 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1221940.5139 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 598329.7564 |  |  |  | 0.18018 | 0 | 0
12 | R4 | 2BHK-L | R | 2019-10-10 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 476190.4762 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344079.7941 |  |  |  | 0.18018 | 0 | 0
13 | R4 | 1BHK | R | 2019-09-29 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7630630.6306 | 763062.8571 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 4959909.9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381531.7375 |  |  |  | 0.20592 | 0 | 0
14 | R4 | 2BHK-L | R | 2019-09-26 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1213523.181 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213503.8461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606756.7568 |  |  |  | 0 | 9.6674 | 0
15 | R4 | 2BHK-L | R | 2019-10-08 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1213513.6643 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606756.606 |  |  |  | 0 | 0.15077 | 0
16 | R4 | 2BHK-L | R | 2019-10-14 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1213513.3333 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606756.9369 |  |  |  | 0.18018 | 0 | 0
17 | R4 | 2BHK-L | R | 2019-09-23 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1213513.3333 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606756.9369 |  |  |  | 0.18018 | 0 | 0
18 | R4 | 2BHK-L | R | 2019-10-08 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 866839.0476 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 953431.2227 |  |  |  | 346674.4659 | 0 | 0
19 | R4 | 1BHK | R | 2019-09-29 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7630630.6306 | 763062.8571 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 4959909.9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381531.7375 |  |  |  | 0.20592 | 0 | 0
20 | R4 | 2BHK-L | UR | 2019-10-14 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12315315.3153 | 476190.4762 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1231531.5315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1231531.5315 | 0 | 0 | 0 | 0 | 0 | 8004954.955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1371106.8211 |  |  |  | 755341.0553 | 0 | 0
21 | R4 | 2BHK-L | R | 2019-10-19 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1105718.0952 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 714552.175 |  |  |  | 107795.4183 | 0 | 0
22 | R4 | 2BHK-L | R | 2019-10-14 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12315315.3153 | 1231530.4762 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1231531.5315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1231531.5315 | 0 | 0 | 0 | 0 | 0 | 8004954.955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 615766.8211 |  |  |  | 1.0553 | 0 | 0
23 | R4 | 1BHK | R | 2019-10-14 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7810810.8108 | 781080.9524 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 781081.0811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 781081.0811 | 0 | 0 | 0 | 0 | 0 | 5077027.027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390540.6692 |  |  |  | 0.1287 | 0 | 0
24 | R4 | 2BHK-L | R | 2019-09-29 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12585586 | 1258559.0476 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1258558.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258558.6 | 0 | 0 | 0 | 0 | 0 | 8180630.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629278.8524 |  |  |  | 0 | 0.44762 | 0
25 | R4 | 2BHK-L | R | 2019-10-06 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1213513.3333 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606756.9369 |  |  |  | 0.18018 | 0 | 0
26 | R4 | 1BHK | R | 2019-12-12 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 8081081.0811 | 476190.4762 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 808108.1081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 808108.1081 | 0 | 0 | 0 | 0 | 0 | 5252702.7027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 735971.686 |  |  |  | 331917.6319 | 0 | 0
27 | R4 | 2BHK-L | UR | 2019-10-06 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1213513.3333 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606756.9369 |  |  |  | 0.18018 | 0 | 0
28 | R4 | 2BHK-S | R | 2019-10-13 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1213512.381 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606757.8893 |  |  |  | 1.1326 | 0 | 0
29 | R4 | 1BHK | R | 2019-09-13 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7630630.6306 | 768513.3071 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 4959909.9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376081.2875 |  |  |  | 0 | 5450.2441 | 0
30 | R4 | 1BHK | R | 2019-10-02 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7630630.6306 | 763062.8571 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 4959909.9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381531.7375 |  |  |  | 0.20592 | 0 | 0
31 | R4 | 2BHK-L | R | 2019-10-14 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12315315.3153 | 476190.4762 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1231531.5315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1231531.5315 | 0 | 0 | 0 | 0 | 0 | 8004954.955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1371106.8211 |  |  |  | 755341.0553 | 0 | 0
32 | R4 | 2BHK-L | R | 2019-10-14 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12315315.3153 | 476190.4762 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1231531.5315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1231531.5315 | 0 | 0 | 0 | 0 | 0 | 8004954.955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1371106.8211 |  |  |  | 755341.0553 | 0 | 0
33 | R4 | 1BHK | R | 2019-10-06 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7630630.6306 | 763062.8571 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 4959909.9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381531.7375 |  |  |  | 0.20592 | 0 | 0
34 | R4 | 2BHK-S | R | 2019-10-06 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1213513.3333 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606756.9369 |  |  |  | 0.18018 | 0 | 0
35 | R4 | 1BHK | UR | 2019-10-13 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7810810.8108 | 476190.4762 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 781081.0811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 781081.0811 | 0 | 0 | 0 | 0 | 0 | 5077027.027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 695431.1454 |  |  |  | 304890.6049 | 0 | 0
36 | R4 | 2BHK-L | R | 2019-09-23 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 476190.4762 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344079.7941 |  |  |  | 737323.0373 | 0 | 0
37 | R4 | 1BHK | R | 2019-10-14 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7810810.8108 | 780952.381 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 781081.0811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 781081.0811 | 0 | 0 | 0 | 0 | 0 | 5077027.027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390669.2407 |  |  |  | 128.7001 | 0 | 0
38 | R4 | 2BHK-L | R | 2019-10-08 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12315315.3153 | 1231531.4286 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1231531.5315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1231531.5315 | 0 | 0 | 0 | 0 | 0 | 8004954.955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 615765.8687 |  |  |  | 755341.0553 | 0 | 0
39 | R4 | 2BHK-L | R | 2019-10-14 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12315315.3153 | 476190.4762 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1231531.5315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1231531.5315 | 0 | 0 | 0 | 0 | 0 | 8004954.955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1371106.8211 |  |  |  | 755341.0553 | 0 | 0
40 | R4 | 2BHK-L | UR | 2019-09-29 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 476190.4762 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344079.7941 |  |  |  | 737323.0373 | 0 | 0
41 | R4 | 2BHK-L | R | 2019-10-01 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1213271.9286 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606998.3417 |  |  |  | 8668.7516 | 0 | 0
42 | R4 | 2BHK-L | R | 2019-10-01 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1213271.9286 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606998.3417 |  |  |  | 8668.7516 | 0 | 0
43 | R4 | 1BHK | R | 2019-10-12 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7810810.8108 | 776190.4762 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 781081.0811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 781081.0811 | 0 | 0 | 0 | 0 | 0 | 5077027.027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395431.1454 |  |  |  | 304890.6049 | 0 | 0
44 | R4 | 2BHK-S | R | 2019-09-10 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1213512.381 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606757.8893 |  |  |  | 1.1326 | 0 | 0
45 | R4 | 2BHK-S | UR | 2019-10-08 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12315315.3153 | 476190.4762 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1231531.5315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1231531.5315 | 0 | 0 | 0 | 0 | 0 | 8004954.955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1371106.8211 |  |  |  | 755341.0553 | 0 | 0
46 | R4 | 1BHK | UR | 2019-10-08 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7810810.8108 | 476190.4762 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 781081.0811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 781081.0811 | 0 | 0 | 0 | 0 | 0 | 5077027.027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 695431.1454 |  |  |  | 304890.6049 | 0 | 0
47 | R4 | 2BHK-L | R | 2019-10-01 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1213512.381 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606757.8893 |  |  |  | 1.1326 | 0 | 0
48 | R4 | 2BHK-L | R | 2019-10-01 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1213512.381 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606757.8893 |  |  |  | 1.1326 | 0 | 0
49 | R4 | 2BHK-L | R | 2019-10-08 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12315315.3153 | 1231531.4286 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1231531.5315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1231531.5315 | 0 | 0 | 0 | 0 | 0 | 8004954.955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 615765.8687 |  |  |  | 0.10296 | 0 | 0
50 | R4 | 2BHK-L | R | 2019-10-02 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1213512.381 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606757.8893 |  |  |  | 1.1326 | 0 | 0
51 | R4 | 1BHK | R | 2019-10-19 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 8081081.0811 | 808108.5714 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 808108.1081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 808108.1081 | 0 | 0 | 0 | 0 | 0 | 5252702.7027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404053.5907 |  |  |  | 331917.6319 | 0 | 0
52 | R4 | 2BHK-L | UR | 2020-01-15 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12585585.5856 | 476190.4762 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1258558.5586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258558.5586 | 0 | 0 | 0 | 0 | 0 | 8180630.6306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1411647.3616 |  |  |  | 782368.0824 | 0 | 0
53 | R4 | 2BHK-L | UR | 2019-10-14 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12585585.5856 | 476285.7143 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1258558.5586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258558.5586 | 0 | 0 | 0 | 0 | 0 | 8180630.6306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1411552.1236 |  |  |  | 782272.8443 | 0 | 0
54 | R4 | 2BHK-L | R | 2019-10-08 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12315315.3153 | 1047619.0476 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1231531.5315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1231531.5315 | 0 | 0 | 0 | 0 | 0 | 8004954.955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799678.2497 |  |  |  | 755341.0553 | 0 | 0
55 | R4 | 1BHK | R | 2019-10-08 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7810810.8108 | 781080.9524 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 781081.0811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 781081.0811 | 0 | 0 | 0 | 0 | 0 | 5077027.027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390540.6692 |  |  |  | 0.1287 | 0 | 0
56 | R4 | 1BHK | R | 2019-10-07 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7810810.8108 | 781080.9524 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 781081.0811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 781081.0811 | 0 | 0 | 0 | 0 | 0 | 5077027.027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390540.6692 |  |  |  | 0.1287 | 0 | 0
57 | R4 | 2BHK-L | UR | 2019-10-08 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12585586 | 1258559.0476 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1258558.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258558.6 | 0 | 0 | 0 | 0 | 0 | 8180630.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629278.8524 |  |  |  | 832561.1326 | 0 | 0
58 | R4 | 2BHK-L | UR | 2019-10-08 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12585586 | 1258559.0476 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1258558.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258558.6 | 0 | 0 | 0 | 0 | 0 | 8180630.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629278.8524 |  |  |  | 0 | 0.44762 | 0
59 | R4 | 1BHK | R | 2019-10-02 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7630630.6306 | 476190.4762 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 4959909.9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 668404.1184 |  |  |  | 0 | 0.44762 | 0
60 | R4 | 1BHK | R | 2019-10-06 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7630630.6306 | 757779.0476 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 4959909.9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 386815.547 |  |  |  | 286872.5869 | 0 | 0
61 | R4 | 2BHK-L | R | 2019-10-05 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1213512.381 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606757.8893 |  |  |  | 5284.0154 | 0 | 0
62 | R4 | 2BHK-L | R | 2019-09-29 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12585585.5856 | 1238095.2381 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1258558.5586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258558.5586 | 0 | 0 | 0 | 0 | 0 | 8180630.6306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649742.5997 |  |  |  | 368662.0849 | 0 | 0
63 | R4 | 2BHK-L | R | 2019-10-14 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12585585.5856 | 1249568.5714 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1258558.5586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258558.5586 | 0 | 0 | 0 | 0 | 0 | 8180630.6306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638269.2664 |  |  |  | 20463.3205 | 0 | 0
64 | R4 | 2BHK-S | R | 2019-10-07 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12495495.4955 | 1249550.4762 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1249549.5495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1249549.5495 | 0 | 0 | 0 | 0 | 0 | 8122072.0721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624773.8481 |  |  |  | 782368.0824 | 0 | 0
65 | R4 | 1BHK | UR | 2019-09-20 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7630630.6306 | 478190.4762 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 4959909.9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 666404.1184 |  |  |  | 0 | 0.92664 | 0
66 | R4 | 2BHK-L | R | 2019-10-05 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1213513.3333 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606756.9369 |  |  |  | 284872.5869 | 0 | 0
67 | R4 | 2BHK-L | R | 2019-10-14 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12585585.5856 | 1258558.0952 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1258558.5586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258558.5586 | 0 | 0 | 0 | 0 | 0 | 8180630.6306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629279.7426 |  |  |  | 0.18018 | 0 | 0
68 | R4 | 1BHK | R | 2019-09-17 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7630630.6306 | 763062.8571 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 4959909.9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381531.7375 |  |  |  | 782368.0824 | 0 | 0
69 | R4 | 2BHK-L | R | 2019-09-22 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1213513.3333 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606756.9369 |  |  |  | 0.20592 | 0 | 0
70 | R4 | 2BHK-L | R | 2019-09-21 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1213513.3333 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606756.9369 |  |  |  | 0.18018 | 0 | 0
71 | R4 | 2BHK-L | R | 2019-10-14 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 13036036.036 | 922651.4286 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1303603.6036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1303603.6036 | 0 | 0 | 0 | 0 | 0 | 8473423.4234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1032753.9768 |  |  |  | 0.18018 | 0 | 0
72 | R4 | 2BHK-L | R | 2019-10-02 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1213513.3333 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606756.9369 |  |  |  | 761904.556 | 0 | 0
73 | R4 | 2BHK-L | R | 2019-10-02 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 476190.4762 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344079.7941 |  |  |  | 0.18018 | 0 | 0
74 | R4 | 2BHK-L | R | 2019-09-23 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1213513.3333 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606756.9369 |  |  |  | 737323.0373 | 0 | 0
75 | R4 | 2BHK-L | R | 2019-10-04 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1218747.4381 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 601522.8322 |  |  |  | 0.18018 | 0 | 0
76 | R4 | 1BHK | R | 2019-09-15 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7630630.6306 | 763062.8571 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 4959909.9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381531.7375 |  |  |  | 0 | 5233.9246 | 0
77 | R4 | 2BHK-L | R | 2019-10-02 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12135135.1351 | 1213513.3333 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5135 | 0 | 0 | 0 | 0 | 0 | 7887837.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606756.9369 |  |  |  | 0.20592 | 0 | 0
78 | R4 | 1BHK | R | 2019-10-01 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 7630630.6306 | 756148.5714 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763063.0631 | 0 | 0 | 0 | 0 | 0 | 4959909.9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388446.0232 |  |  |  | 0.18018 | 0 | 0
79 | R4 | 1BHK | UR | 2019-10-21 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 8171171.1712 | 476190.4762 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 817117.1171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 817117.1171 | 0 | 0 | 0 | 0 | 0 | 5311261.2613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 749485.1995 |  |  |  | 6914.4916 | 0 | 0
80 | R4 | 3BHK | R | 2019-10-08 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 20693694 | 2069369.5238 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2069369.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2069369.4 | 0 | 0 | 0 | 0 | 0 | 13450901.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1034684.5762 |  |  |  | 340926.6409 | 0 | 0
81 | R4 | 3BHK | R | 2020-01-19 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 20243243.2432 | 2024324.7619 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2024324.3243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024324.3243 | 0 | 0 | 0 | 0 | 0 | 13158108.1081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012161.7246 |  |  |  | 952380.8286 | 0 | 0
82 | R4 | 4BHK | R | 2019-10-13 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 25198198 | 2519820 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2519819.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2519819.8 | 0 | 0 | 0 | 0 | 0 | 16378828.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1259909.7 |  |  |  | 0 | 0.43758 | 0
83 | R4 | 4BHK | R | 2020-01-07 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 25198198.1982 | 2519820 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2519819.8198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2519819.8198 | 0 | 0 | 0 | 0 | 0 | 16378828.8288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1259909.7297 |  |  |  | 0 | 0.2 | 0
84 | R4 | 3BHK | R | 2019-10-14 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 20243243.2432 | 2024324.7619 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2024324.3243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024324.3243 | 0 | 0 | 0 | 0 | 0 | 13158108.1081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012161.7246 |  |  |  | 0 | 0.18018 | 0
85 | R4 | 3BHK | R | 2019-10-06 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 20243243.2432 | 2024324.7619 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2024324.3243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024324.3243 | 0 | 0 | 0 | 0 | 0 | 13158108.1081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012161.7246 |  |  |  | 0 | 0.43758 | 0
86 | R4 | 3BHK | R | 2019-10-09 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 20243243.2432 | 2024323.8095 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2024324.3243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024324.3243 | 0 | 0 | 0 | 0 | 0 | 13158108.1081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012162.677 |  |  |  | 0 | 0.43758 | 0
87 | R4 | 4BHK | R | 2020-01-06 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 25198198.1982 | 2519820 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2519819.8198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2519819.8198 | 0 | 0 | 0 | 0 | 0 | 16378828.8288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1259909.7297 |  |  |  | 0.5148 | 0 | 0
88 | R4 | 4BHK | R | 2019-09-28 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 24747747.7477 | 2474774.6857 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2474774.7748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2474774.7748 | 0 | 0 | 0 | 0 | 0 | 16086036.036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1237387.4764 |  |  |  | 0 | 0.18018 | 0
89 | R4 | 3BHK | R | 2019-10-06 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 20243243.2432 | 2024324.7619 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2024324.3243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024324.3243 | 0 | 0 | 0 | 0 | 0 | 13158108.1081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012161.7246 |  |  |  | 0.08906 | 0 | 0
90 | R4 | 3BHK | R | 2020-01-20 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 20423423.4234 | 2053529.6571 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2042342.3423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2042342.3423 | 0 | 0 | 0 | 0 | 0 | 13275225.2252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1009983.8564 |  |  |  | 0 | 0.43758 | 0
91 | R4 | 4BHK | R | 2020-01-28 | Epay | 10% on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 55% Dec 22, 5% Possession | 26369369 | 2636934.2857 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2636936.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2636936.9 | 0 | 0 | 0 | 0 | 0 | 14503152.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3955407.9643 |  |  |  | 0 | 11187.3148 | 0
92 | R4 | 2BHK-L | R | 2020-02-14 | Epay | 10% on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 55% Dec 22, 5% Possession | 13486486 | 1348648.5714 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1348648.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1348648.6 | 0 | 0 | 0 | 0 | 0 | 7417567.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022972.9286 |  |  |  | 2.6143 | 0 | 0
93 | R4 | 1BHK | R | 2020-02-07 | Epay | 10% on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 55% Dec 22, 5% Possession | 7630631 | 476190.4762 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 763063.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763063.1 | 0 | 0 | 0 | 0 | 0 | 4196847.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1431467.2738 |  |  |  | 0.028571 | 0 | 0
94 | R4 | 2BHK-L | R | 2020-01-08 | Epay | 10% on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 55% Dec 22, 5% Possession | 12135135 | 462962.963 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213513.5 | 0 | 0 | 0 | 0 | 0 | 6674324.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2570820.787 |  |  |  | 286872.6238 | 0 | 0
95 | R4 | 1BHK | R | 2020-03-09 | Epay | 10% on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 55% Dec 22, 5% Possession | 8081081 | 1616217.1429 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 808108.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 808108.1 | 0 | 0 | 0 | 0 | 0 | 4444594.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404053.1071 |  |  |  | 750550.537 | 0 | 0
96 | R4 | 2BHK-L | R | 2020-01-31 | Epay | 5 lacs on booking, 10% in June 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12315315 | 1231532.381 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1231531.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1231531.5 | 0 | 0 | 0 | 0 | 0 | 8004954.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 615764.869 |  |  |  | 0 | 808109.0429 | 0
97 | R4 | 3BHK | UR | 2020-06-27 | Epay | 10% Aug 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 21144144 | 952380.9524 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2114414.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2114414.4 | 0 | 0 | 0 | 0 | 0 | 13743693.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2219240.6476 |  |  |  | 0 | 0.88095 | 0
98 | R4 | 2BHK-L | R | 2020-08-21 | Epay | 10% Nov 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12585586 | 638019.0384 | [13 empty] | 1258558.6 | [11 empty] | 1258558.6 | [5 empty] | 8180630.9 | [11 empty] | 1249818.8616 |  |  |  | 1638223.9238 | 0 | 0
99 | R4 | 2BHK-L | R | 2020-08-21 | Epay | 10% Nov 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12585586 | 638019.0384 | [13 empty] | 1258558.6 | [11 empty] | 1258558.6 | [5 empty] | 8180630.9 | [11 empty] | 1249818.8616 |  |  |  | 0 | 95238.0952 | 0
100 | R4 | 3BHK | UR | 2020-08-15 | Epay | 10% Nov 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 21144144 | 95238.0952 | [13 empty] | 2114414.4 | [11 empty] | 2114414.4 | [5 empty] | 13743693.6 | [11 empty] | 3076383.5048 |  |  |  | 0 | 95238.0952 | 0
101 | R4 | 3BHK | R | 2020-08-15 | Epay | 10% Oct 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 20693694 | 2068959.1964 | [13 empty] | 2069369.4 | [11 empty] | 2069369.4 | [5 empty] | 13450901.1 | [11 empty] | 1035094.9036 |  |  |  | 0 | 95238.0952 | 0
102 | R4 | 1BHK | UR | 2020-08-31 | Epay | 10% Nov 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 8081081 | 95238.0952 | [13 empty] | 808108.1 | [11 empty] | 808108.1 | [5 empty] | 5252702.65 | [11 empty] | 1116924.0548 |  |  |  | 0 | 95238.0952 | 0
103 | R4 | 2BHK-L | UR | 2020-09-03 | Epay | 10% Oct 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12675676 | 571428.5714 | [7 empty] | 0 | [5 empty] | 1267567.6 | [11 empty] | 1267567.6 | [5 empty] | 8239189.4 | [11 empty] | 1329922.8286 |  |  |  | 0 | 95238.0952 | 0
104 | R4 | 2BHK-L | UR | 2020-09-03 | Epay | 10% Oct 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 13036036 | 95238.0952 | [7 empty] | 0 | [5 empty] | 1303603.6 | [11 empty] | 1303603.6 | [5 empty] | 8473423.4 | [11 empty] | 1860167.3048 |  |  |  | 0 | 95238.0952 | 0
105 | R4 | 2BHK-L | R | 2020-09-09 | Epay | 10% Oct 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 13216216 | 1321620.9524 | [7 empty] | 0 | [5 empty] | 1321621.6 | [11 empty] | 1321621.6 | [5 empty] | 8590540.4 | [11 empty] | 660811.4476 |  |  |  | 0 | 95238.0952 | 0
106 | R4 | 2BHK-L | UR | 2020-09-19 | Epay | 10% Oct 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 13036036 | 95238.0952 | [7 empty] | 0 | [5 empty] | 1303603.6 | [11 empty] | 1303603.6 | [5 empty] | 8473423.4 | [11 empty] | 1860167.3048 |  |  |  | 0 | 0 | 0
107 | R4 | 2BHK-L | UR | 2020-09-19 | Epay | 10% Oct 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12855856 | 1285585.7143 | [7 empty] | 0 | [5 empty] | 1285585.6 | [11 empty] | 1285585.6 | [5 empty] | 8356306.4 | [11 empty] | 642792.6857 |  |  |  | 0 | 95238.0952 | 0
108 | R4 | 2BHK-L | R | 2020-09-30 | Epay | 10% Dec 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 13036036 | 1303602.8571 | [7 empty] | 0 | [5 empty] | 1303603.6 | [11 empty] | 1303603.6 | [5 empty] | 8473423.4 | [11 empty] | 651802.5429 |  |  |  | 0 | 95238.0952 | 0
109 | R4 | 1BHK | UR | 2020-09-07 | Epay | 10% Nov 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 8351351 | 95238.0952 | [13 empty] | 835135.1 | [11 empty] | 835135.1 | [5 empty] | 5428378.15 | [11 empty] | 1157464.5548 |  |  |  | 0 | 0 | 0
110 | R4 | 3BHK | UR | 2020-09-30 | Epay | 10% Oct 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 20243243 | 956190.4762 | [7 empty] | 0 | [5 empty] | 2024324.3 | [11 empty] | 2024324.3 | [5 empty] | 13158107.95 | [11 empty] | 2080295.9738 |  |  |  | 0 | 0 | 0
111 | R4 | 2BHK-L | R | 2020-10-10 | Epay | 10% Oct 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 13036036 | 1303602.8571 | [13 empty] | 1303603.6 | [11 empty] | 1303603.6 | [5 empty] | 8473423.4 | [11 empty] | 651802.5429 |  |  |  | 0 | 95238.0952 | 0
112 | R4 | 2BHK-L | R | 2020-10-17 | Epay | 10% Oct 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 13036036 | 1303603.8095 | [13 empty] | 1303603.6 | [11 empty] | 1303603.6 | [5 empty] | 8473423.4 | [11 empty] | 651801.5905 |  |  |  | 0 | 95238.0952 | 0
113 | R4 | 4BHK | UR | 2020-10-09 | Epay | 10% Oct 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 26099099 | 95238.0952 | [7 empty] | 2609909.9 | [5 empty] | 2609909.9 | [11 empty] | 2609909.9 | [5 empty] | 16964414.35 | [11 empty] | 1209716.8548 |  |  |  | 0 | 462962.963 | 0
114 | R4 | 3BHK | UR | 2020-10-23 | Epay | 10% Oct 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 21144143 | 2756628.5714 | [13 empty] | 2114414.3 | [11 empty] | 2114414.3 | [5 empty] | 13743692.95 | [11 empty] | 414992.8786 |  |  |  | 0 | 929629.6296 | 0
115 | R4 | 1BHK | UR | 2020-10-24 | Epay | 10% Oct 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 8261261 | 826125.7143 | [13 empty] | 826126.1 | [11 empty] | 826126.1 | [5 empty] | 5369819.65 | [11 empty] | 413063.4357 |  |  |  | 0 | 929629.6296 | 0
116 | R4 | 2BHK-L | UR | 2020-11-06 | Epay | 10% Nov 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 13306306 | 1321125.7143 | [13 empty] | 1330630.6 | [11 empty] | 1330630.6 | [5 empty] | 8649098.9 | [11 empty] | 674820.1857 |  |  |  | 0 | 929629.6296 | 0
117 | R4 | 3BHK | UR | 2020-11-08 | Epay | 10% Nov 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 21594595 | 95238.0952 | [7 empty] | 2159459.5 | [5 empty] | 2159459.5 | [11 empty] | 2159459.5 | [5 empty] | 14036486.75 | [11 empty] | 984491.6548
118 | R4 | 2BHK-L | UR | 2020-11-08 | Epay | 10% Dec 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12945946 | 285714.2857 | [7 empty] | 1294594.6 | [5 empty] | 1294594.6 | [11 empty] | 1294594.6 | [5 empty] | 8414864.9 | [11 empty] | 361583.0143
119 | R4 | 2BHK-L | UR | 2020-11-08 | Epay | 10% Nov 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 13216216 | 1333333.3333 | [13 empty] | 1321621.6 | [11 empty] | 1321621.6 | [5 empty] | 8590540.4 | [11 empty] | 649099.0667 |  |  |  | 0 | 929629.6296 | 0
120 | R4 | 1BHK | UR | 2020-11-08 | Epay | 10% Nov 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 8261261 | 95238.0952 | [7 empty] | 826126.1 | [5 empty] | 826126.1 | [11 empty] | 826126.1 | [5 empty] | 5369819.65 | [11 empty] | 317824.9548
121 | R4 | 2BHK-L | R | 2020-11-12 | Epay | 10% Dec 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 13441441 | 1334542.8571 | [13 empty] | 1344144.1 | [11 empty] | 1344144.1 | [5 empty] | 8736936.65 | [11 empty] | 681673.2929 |  |  |  | 0 | 929629.6296 | 0
122 | R4 | 2BHK-L | R | 2020-11-12 | Epay | 10% Dec 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 13261261 | 1316654.2857 | [13 empty] | 1326126.1 | [11 empty] | 1326126.1 | [5 empty] | 8619819.65 | [11 empty] | 672534.8643 |  |  |  | 0 | 929629.6296 | 0
123 | R4 | 2BHK-L | UR | 2020-11-16 | Epay | 10% Dec 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12945946 | 95238.0952 | [7 empty] | 1294594.6 | [5 empty] | 1294594.6 | [11 empty] | 1294594.6 | [5 empty] | 8414864.9 | [11 empty] | 552059.2048
124 | R4 | 1BHK | UR | 2020-11-18 | Epay | 10% Dec 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 8531532 | 95238.0952 | [7 empty] | 853153.2 | [5 empty] | 853153.2 | [11 empty] | 853153.2 | [5 empty] | 5545495.8 | [11 empty] | 331338.5048
125 | R4 | 2BHK-L | UR | 2020-11-18 | Epay | 10% Dec 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12675676 | 95238.0952 | [7 empty] | 1267567.6 | [5 empty] | 1267567.6 | [11 empty] | 1267567.6 | [5 empty] | 8239189.4 | [11 empty] | 538545.7048
126 | R4 | 2BHK-S | UR | 2020-11-19 | Epay | 10% Oct 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12585586 | 629288.5714 | [7 empty] | 629270.0286 | [5 empty] | 1258558.6 | [11 empty] | 1258558.6 | [5 empty] | 8180630.9 | [11 empty] | 629279.3 |  |  |  | 0 | 929629.6296 | 0
127 | R4 | 1BHK | UR | 2020-11-30 | Epay | 10% Dec 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 8441441 | 0 | [7 empty] | 844144.1 | [5 empty] | 844144.1 | [11 empty] | 844144.1 | [5 empty] | 5486936.65 | [11 empty] | 422072.05
128 | R4 | 2BHK-L | UR | 2020-11-30 | Epay | 10% Dec 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 12945946 | 0 | [7 empty] | 1294594.6 | [5 empty] | 1294594.6 | [11 empty] | 1294594.6 | [5 empty] | 8414864.9 | [11 empty] | 647297.3
129 | R4 | 3BHK | UR | 2020-11-30 | Epay | 10% Dec 2020, 10% June 2021, 10% June 2022, 65% Dec 22, 5% Possession | 21234234 | 0 | [7 empty] | 2123423.4 | [5 empty] | 2123423.4 | [11 empty] | 2123423.4 | [5 empty] | 13802252.1 | [11 empty] | 1061711.7

## Shops Inv S (3) (hidden)
[5 empty] | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-12-31 | 2023-12-31 | 2023-12-31 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2024-06-30 | 2024-06-30 | 2024-06-30 | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-12-31 | 2024-12-31 | 2024-12-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-09-30 | 2026-09-30 | 2026-09-30 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2027-03-31 | 2027-03-31 | 2027-03-31
 | time axis 2023-07-31 to 2027-03-31
| Construction Linked Plan |  | % Completion |  | 0% | 0% | 0% | 5% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 2% | 0% | 0% | 2% | 0% | 0% | 2% | 0% | 0%
|  |  | Cumulative |  |  | 0% | 0% | 5% | 5% | 5% | 6% | 6% | 6% | 7% | 7% | 7% | 8% | 8% | 8% | 9% | 9% | 9% | 10% | 10% | 10% | 11% | 11% | 11% | 12% | 12% | 12% | 13% | 13% | 13% | 14% | 14% | 14% | 15% | 15% | 15% | 17% | 17% | 17% | 19% | 19% | 19% | 21% | 21% | 21%
| Scheme |  |  | 1 | 2024-01-31: 5%; 2025-01-31: 10%; 2025-09-30: 15%; 2026-06-30: 70%
|  |  | Cumulative |  |  | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Sales Scheme 1 | SCH1 | 2020-07-31 | 1 | 2023-07-31: 5%; 2023-09-30: 5%; 2023-12-31: 5%; 2024-03-31: 5%; 2024-06-30: 10%; 2024-09-30: 10%; 2024-12-31: 10%; 2025-03-31: 10%; 2025-06-30: 10%; 2025-09-30: 10%; 2025-12-31: 10%; 2026-03-31: 5%; 2026-06-30: 5%
[5 empty] | 5% | 5% | 10% | 10% | 10% | 15% | 15% | 15% | 20% | 20% | 20% | 30% | 30% | 30% | 40% | 40% | 40% | 50% | 50% | 50% | 60% | 60% | 60% | 70% | 70% | 70% | 80% | 80% | 80% | 90% | 90% | 90% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Sales Scheme 2 | SCH2 |  | 1 | 2023-09-30: 5%; 2024-01-31: 10%; 2024-07-31: 20%; 2025-01-31: 20%; 2025-07-31: 20%; 2026-01-31: 20%; 2026-06-30: 5%
[6 empty] | 0% | 5% | 5% | 5% | 5% | 15% | 15% | 15% | 15% | 15% | 15% | 35% | 35% | 35% | 35% | 35% | 35% | 55% | 55% | 55% | 55% | 55% | 55% | 75% | 75% | 75% | 75% | 75% | 75% | 95% | 95% | 95% | 95% | 95% | 100%
| Sales Scheme 3 | SCH3 |  | 1 | 2023-09-30: 5%; 2024-04-30: 25%; 2025-01-31: 25%; 2025-10-31: 25%; 2026-06-30: 20%
[6 empty] | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 100%
| Sales Scheme 4 | SCH4 |  | 1 | 2023-09-30: 5%; 2024-07-31: 50%; 2025-07-31: 35%; 2026-06-30: 10%
[6 empty] | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 100%
|  | 925% | 24
|  | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Month | Quantity | Units | Sale Value | time axis 2023-07-31 to 2027-03-31
0 | 2023-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2023-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2023-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2023-10-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2023-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2023-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-01-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-02-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-04-30 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-05-31 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-06-30 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-07-31 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-08-31 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-09-30 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-10-31 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-11-30 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-12-31 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-01-31 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-02-28 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-03-31 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-04-30 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-05-31 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-06-30 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-07-31 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-08-31 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-09-30 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-10-31 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-11-30 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-12-31 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-01-31 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-02-28 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-03-31 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-09-30 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-10-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-11-30 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2027-01-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2027-02-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2027-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## REHAB BUILDING No. 1 Inv S (2) (hidden)
[5 empty] | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-12-31 | 2023-12-31 | 2023-12-31 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2024-06-30 | 2024-06-30 | 2024-06-30 | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-12-31 | 2024-12-31 | 2024-12-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-09-30 | 2026-09-30 | 2026-09-30 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2027-03-31 | 2027-03-31 | 2027-03-31
 | time axis 2023-07-31 to 2027-03-31
| Construction Linked Plan |  | % Completion |  | 0% | 0% | 0% | 5% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 2% | 0% | 0% | 2% | 0% | 0% | 2% | 0% | 0%
|  |  | Cumulative |  |  | 0% | 0% | 5% | 5% | 5% | 6% | 6% | 6% | 7% | 7% | 7% | 8% | 8% | 8% | 9% | 9% | 9% | 10% | 10% | 10% | 11% | 11% | 11% | 12% | 12% | 12% | 13% | 13% | 13% | 14% | 14% | 14% | 15% | 15% | 15% | 17% | 17% | 17% | 19% | 19% | 19% | 21% | 21% | 21%
| Scheme |  |  | 1 | 2024-01-31: 5%; 2025-01-31: 10%; 2025-09-30: 15%; 2026-06-30: 70%
|  |  | Cumulative |  |  | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Sales Scheme 1 | SCH1 | 2020-07-31 | 1 | 2023-07-31: 5%; 2023-09-30: 5%; 2023-12-31: 5%; 2024-03-31: 5%; 2024-06-30: 10%; 2024-09-30: 10%; 2024-12-31: 10%; 2025-03-31: 10%; 2025-06-30: 10%; 2025-09-30: 10%; 2025-12-31: 10%; 2026-03-31: 5%; 2026-06-30: 5%
[5 empty] | 5% | 5% | 10% | 10% | 10% | 15% | 15% | 15% | 20% | 20% | 20% | 30% | 30% | 30% | 40% | 40% | 40% | 50% | 50% | 50% | 60% | 60% | 60% | 70% | 70% | 70% | 80% | 80% | 80% | 90% | 90% | 90% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Sales Scheme 2 | SCH2 |  | 1 | 2023-09-30: 5%; 2024-01-31: 10%; 2024-07-31: 20%; 2025-01-31: 20%; 2025-07-31: 20%; 2026-01-31: 20%; 2026-06-30: 5%
[6 empty] | 0% | 5% | 5% | 5% | 5% | 15% | 15% | 15% | 15% | 15% | 15% | 35% | 35% | 35% | 35% | 35% | 35% | 55% | 55% | 55% | 55% | 55% | 55% | 75% | 75% | 75% | 75% | 75% | 75% | 95% | 95% | 95% | 95% | 95% | 100%
| Sales Scheme 3 | SCH3 |  | 1 | 2023-09-30: 5%; 2024-04-30: 25%; 2025-01-31: 25%; 2025-10-31: 25%; 2026-06-30: 20%
[6 empty] | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 100%
| Sales Scheme 4 | SCH4 |  | 1 | 2023-09-30: 5%; 2024-07-31: 50%; 2025-07-31: 35%; 2026-06-30: 10%
[6 empty] | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 100%
|  | #DIV/0! | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Month | Quantity | Units | Sale Value | time axis 2023-07-31 to 2027-03-31
0 | 2023-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2023-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2023-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2023-10-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2023-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2023-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-01-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-02-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-04-30 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-10-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-01-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-02-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-10-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-01-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-02-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-10-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-11-30 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2027-01-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2027-02-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2027-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## AMENITY BUILDING No. Inv Sales (hidden)
[5 empty] | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-12-31 | 2023-12-31 | 2023-12-31 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2024-06-30 | 2024-06-30 | 2024-06-30 | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-12-31 | 2024-12-31 | 2024-12-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-09-30 | 2026-09-30 | 2026-09-30 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2027-03-31 | 2027-03-31 | 2027-03-31
 | time axis 2023-07-31 to 2027-03-31
| Construction Linked Plan |  | % Completion |  | 0% | 0% | 0% | 5% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 1% | 0% | 0% | 2% | 0% | 0% | 2% | 0% | 0% | 2% | 0% | 0%
|  |  | Cumulative |  |  | 0% | 0% | 5% | 5% | 5% | 6% | 6% | 6% | 7% | 7% | 7% | 8% | 8% | 8% | 9% | 9% | 9% | 10% | 10% | 10% | 11% | 11% | 11% | 12% | 12% | 12% | 13% | 13% | 13% | 14% | 14% | 14% | 15% | 15% | 15% | 17% | 17% | 17% | 19% | 19% | 19% | 21% | 21% | 21%
| Scheme |  |  | 1 | 2024-01-31: 5%; 2025-01-31: 10%; 2025-09-30: 15%; 2026-06-30: 70%
|  |  | Cumulative |  |  | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Sales Scheme 1 | SCH1 | 2020-07-31 | 1 | 2023-07-31: 5%; 2023-09-30: 5%; 2023-12-31: 5%; 2024-03-31: 5%; 2024-06-30: 10%; 2024-09-30: 10%; 2024-12-31: 10%; 2025-03-31: 10%; 2025-06-30: 10%; 2025-09-30: 10%; 2025-12-31: 10%; 2026-03-31: 5%; 2026-06-30: 5%
[5 empty] | 5% | 5% | 10% | 10% | 10% | 15% | 15% | 15% | 20% | 20% | 20% | 30% | 30% | 30% | 40% | 40% | 40% | 50% | 50% | 50% | 60% | 60% | 60% | 70% | 70% | 70% | 80% | 80% | 80% | 90% | 90% | 90% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Sales Scheme 2 | SCH2 |  | 1 | 2023-09-30: 5%; 2024-01-31: 10%; 2024-07-31: 20%; 2025-01-31: 20%; 2025-07-31: 20%; 2026-01-31: 20%; 2026-06-30: 5%
[6 empty] | 0% | 5% | 5% | 5% | 5% | 15% | 15% | 15% | 15% | 15% | 15% | 35% | 35% | 35% | 35% | 35% | 35% | 55% | 55% | 55% | 55% | 55% | 55% | 75% | 75% | 75% | 75% | 75% | 75% | 95% | 95% | 95% | 95% | 95% | 100%
| Sales Scheme 3 | SCH3 |  | 1 | 2023-09-30: 5%; 2024-04-30: 25%; 2025-01-31: 25%; 2025-10-31: 25%; 2026-06-30: 20%
[6 empty] | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 100%
| Sales Scheme 4 | SCH4 |  | 1 | 2023-09-30: 5%; 2024-07-31: 50%; 2025-07-31: 35%; 2026-06-30: 10%
[6 empty] | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 100%
|  | #DIV/0! | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Month | Quantity | Units | Sale Value | time axis 2023-07-31 to 2027-03-31
0 | 2023-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2023-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2023-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2023-10-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2023-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2023-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-01-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-02-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-10-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2024-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-01-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-02-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-10-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2025-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-01-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-02-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-10-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2026-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2027-01-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2027-02-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 2027-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sale Building k (hidden)
[8 empty] | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-12-31 | 2023-12-31 | 2023-12-31 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2024-06-30 | 2024-06-30 | 2024-06-30 | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-12-31 | 2024-12-31 | 2024-12-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-12-01 | 2025-12-01
1 | Particulars | Budgeted | Incurred | Balance |  |  |  | 2023-04-01 | 2023-05-31 | 2023-06-30 | 2023-07-31 | 2023-08-31 | 2023-09-30 | 2023-10-31 | 2023-11-30 | 2023-12-31 | 2024-01-31 | 2024-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-31 | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30
1 | Construction Cost | 77.06 | 23.15 | 53.91 |  |  |  | 0 | 0 | 0 | 0 | 0 | 9.31 | 0 | 0 | 9.25 | 0 | 0 | 9.25 | 0 | 0 | 9.25 | 0 | 0 | 9.25 | 0 | 0 | 5.47 | 0 | 0 | 2.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Approval Cost (FSI charges)+DC+Stair case+PT+( BMC Premium) | 13 | 3.8 | 9.2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47 | 0 | 0 | 1.95 | 0 | 0 | 1.95 | 0 | 0 | 1.95 | 0 | 0 | 1.56 | 0 | 0 | 1.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Architect & Consultancy Expenses | 2 | 1.07 | 0.93 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0.104 | 0 | 0 | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0.2 | 0 | 0 | 0.2 | 0 | 0 | 0.126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Admin & Marketing Expenses | 5.5 | 2.16 | 3.34 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.17 | 0 | 0 | 0.17 | 0 | 0 | 0.17 | 0 | 0 | 0.55 | 0 | 0 | 0.64 | 0 | 0 | 0.83 | 0 | 0 | 0.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Contingency | 1.47 | 0 | 1.47 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0.21 | 0 | 0 | 0.11 | 0 | 0 | 0.1 | 0 | 0 | 0.11 | 0 | 0 | 0.1 | 0 | 0 | 0.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Rent Cost | 9.45 | 6.27 | 3.18 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.34 | 0 | 0 | 0.47 | 0 | 0 | 0.47 | 0 | 0 | 0.47 | 0 | 0 | 0.48 | 0 | 0 | 0.47 | 0 | 0 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Interest to Bank Finance upto construction period | 3.87 | 0 | 3.87 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0.36 | 0 | 0 | 0.47 | 0 | 0 | 0.57 | 0 | 0 | 0.68 | 0 | 0 | 0.78 | 0 | 0 | 0.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Interest on Unsecured Loan | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 112.35 | 36.45 | 75.9 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 10.22 | 0 | 0 | 11.034 | 0 | 0 | 12.52 | 0 | 0 | 12.99 | 0 | 0 | 13.31 | 0 | 0 | 9.41 | 0 | 0 | 6.416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Packages | Particulars | Budgeted | Incurred | Balance | Start Date | End Date | Months | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-12-31 | 2023-12-31 | 2023-12-31 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2024-06-30 | 2024-06-30 | 2024-06-30 | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-12-31 | 2024-12-31 | 2024-12-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-12-01 | 2025-12-01
Construction Cost | Construction Cost | 77.06 | 23.15 | 53.91 | 2023-08-01 | 2026-03-31 | 32 | 2023-06-30: 0; 2023-08-31: 0; 2023-09-30: 9.31; 2023-12-31: 9.25; 2024-03-31: 9.25; 2024-06-30: 9.25; 2024-09-30: 9.25; 2024-12-31: 5.47; 2025-03-31: 2.13; 2025-06-30: 0; 2025-09-30: 0; 2025-11-30: 0
| Approval Cost (FSI charges)+DC+Stair case+PT+( BMC Premium) | 13 | 3.8 | 9.2 | 2023-08-01 | 2026-03-31 | 32 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0.47 | 0 | 0 | 1.95 | 0 | 0 | 1.95 | 0 | 0 | 1.95 | 0 | 0 | 1.56 | 0 | 0 | 1.32 | 0 | 0
| Architect & Consultancy Expenses | 2 | 1.07 | 0.93 | 2023-08-01 | 2026-03-31 | 32 | 0 | 0 |  | 0 | 0 | 0.1 | 0 | 0 | 0.104 | 0 | 0 | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0.2 | 0 | 0 | 0.2 | 0 | 0 | 0.126 | 0 | 0
| Admin & Marketing Expenses | 5.5 | 2.16 | 3.34 | 2023-08-01 | 2026-03-31 | 32 | 0 | 0 |  | 0 | 0 | 0.17 | 0 | 0 | 0.17 | 0 | 0 | 0.17 | 0 | 0 | 0.55 | 0 | 0 | 0.64 | 0 | 0 | 0.83 | 0 | 0 | 0.81 | 0 | 0
| Contingency | 1.47 | 0 | 1.47 | 2023-08-01 | 2026-03-31 | 32 | 0 | 0 |  | 0 | 0 | 0.15 | 0 | 0 | 0.21 | 0 | 0 | 0.11 | 0 | 0 | 0.1 | 0 | 0 | 0.11 | 0 | 0 | 0.1 | 0 | 0 | 0.69 | 0 | 0
| Rent Cost | 9.45 | 6.27 | 3.18 | 2023-08-01 | 2026-03-31 | 32 | 2023-04-01: 0; 2023-05-31: 0; 2023-07-31: 0; 2023-08-31: 0; 2023-09-30: 0.34; 2023-10-31: 0; 2023-11-30: 0; 2023-12-31: 0.47; 2024-01-31: 0; 2024-02-29: 0; 2024-03-31: 0.47; 2024-06-30: 0.47; 2024-09-30: 0.48; 2024-12-31: 0.47; 2025-03-31: 0.48
| Interest to Bank Finance upto construction period | 3.87 | 0 | 3.87 | 2023-08-01 | 2026-03-31 | 32 | 2023-04-01: 0; 2023-05-31: 0; 2023-07-31: 0; 2023-08-31: 0; 2023-09-30: 0.15; 2023-10-31: 0; 2023-11-30: 0; 2023-12-31: 0.36; 2024-01-31: 0; 2024-02-29: 0; 2024-03-31: 0.47; 2024-06-30: 0.57; 2024-09-30: 0.68; 2024-12-31: 0.78; 2025-03-31: 0.86
| Interest on Unsecured Loan | 0 | 0 | 0 | 2023-08-01 | 2026-03-31 | 32 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Particulars | AMENITY BUILDING No. 2 | REHAB BUILDING No. 1 | SALE BUILDING | Total |  |  | 2023-05-31: Particulars; 2023-06-30: Construction area
| Construction area | 2057.05 | 12066.9356 | 30990.9475 | 45114.9331 |  |  | 2023-05-31: R4; 2023-06-30: 2057.05
1 | Construction Cost | 0 | 77.06 | #REF! | #REF! | #REF! |  | 2023-05-31: R5; 2023-06-30: 12066.9356
2 | Premium Cost | 0 | 13 | #REF! | #REF! | #REF! |  | 2023-05-31: Galleria; 2023-06-30: 30990.9475
3 | Consultants | 0 | 2 | #REF! | #REF! | #REF! |  | 2023-05-31: Total; 2023-06-30: 45114.9331
4 | Sales, Marketing, Branding & Advertising Cost | 0 | 5.5 | #REF! | #REF! | #REF!
5 | Salary & Admin Overheads | 0 | 1.47 |  | 1.47 | 325.8345
6 | GST | 0 | 0 | #REF! | #REF! | #REF!
|  | 0 | 99.03 | #REF! | #REF! | #REF!

## Sheet1 (hidden)
Particulars | Till Sept-23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | Total
Revenue
Sale Building | 11.48 | FY24: 13.13; FY25: 5.4; FY26: 7.1 | 96.68
24.85
[5 empty] | 15.11 | 31.09
Total Revenue | 11.48 | 13.13 | 5.4 | 7.1 | 15.11 | 31.09 | 24.85
96.68
Construction Cost | Till Sept 23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | Total
Land & Stamp Duty | 9.91 | FY24: 0; FY25: 0; FY26: 0 | 9.91
[5 empty] | 0 | 0 | 0
Construction Cost | 23.4 | FY24: 5; FY25: 10; FY26: 10 | 50
1.6
Approval Cost (FSI charges) + DC + Stair case + PT + (BMC Premium) | 7.48 | FY24: 0.44; FY25: 0; FY26: 0 | 8.25
[5 empty] | 0.33 | 0 | 0
Architect & Consultancy Expenses | 1.31 | FY24: 1.41; FY25: 0.12; FY26: 0.24 | 1.95
[5 empty] | 0.18 | 0 | 0
Admin & Marketing Expenses | 1.35 | FY24: 1.53; FY25: 0.2; FY26: 0.41 | 2.5
[5 empty] | 0.36 | 0 | 0
Contingency | 0.06 | FY24: 0.07; FY25: 0.05; FY26: 0.08 | 0.26
[5 empty] | 0.06 | 0 | 0
Interest to Bank Finance | - | FY24: 1.52; FY25: 3.65; FY26: 3.65 | 13.82
[5 empty] | 3.3 | 1.59 | 0.11
Total Cost Incurred | 43.51 | 9.97 | 14.02 | 14.38 | 5.83 | 1.59 | 0.11 | 86.69
Work Completed | 46.8% | 10% | 20% | 20% | 3.2% |  |  | 100%
Sales Completed | 11.1% | 1.7% | 5.22% | 6.86% | 14.61% | 30.06% | 24.02% | 100%
| 11.87% | 13.58% | 5.585% | 7.344% | 15.63% | 32.16% | 25.7% | 0%
Cost of Sales | 42.05 | FY24: 43.01; FY25: 48.17; FY26: 0 | 133.23
Sales Recognised | 0 | FY24: 0; FY25: 0; FY26: 232.1 | 232.1
Closing WIP | 45.28 | FY24: 89.1; FY25: 140.73; FY26: 0
Cash Collection | 10.8 | FY24: 26.23; FY25: 49.31; FY26: 145.76 | 232.1
Debtors | 0 | FY24: 0.09; FY25: 15.09; FY26: 0
| 11.87% | 1.707% | 5.585% | 7.344% | 15.63% | 32.16% | 25.7% | 0%

## REHAB BUILDING No. 1 Costing k (hidden)
[8 empty] | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-12-31 | 2023-12-31 | 2023-12-31 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2024-06-30 | 2024-06-30 | 2024-06-30 | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-12-31 | 2024-12-31 | 2024-12-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-12-01 | 2025-12-01
1 | Particulars | Budgeted | Incurred | Balance |  |  |  | 2023-04-01 | 2023-05-31 | 2023-06-30 | 2023-07-31 | 2023-08-31 | 2023-09-30 | 2023-10-31 | 2023-11-30 | 2023-12-31 | 2024-01-31 | 2024-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-31 | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30
1 | Construction Cost | 27.93 | 8.39 | 19.54 |  |  |  | 0 | 0 | 0 | 0 | 0 | 3.35 | 0 | 0 | 3.35 | 0 | 0 | 3.35 | 0 | 0 | 3.35 | 0 | 0 | 3.35 | 0 | 0 | 1.98 | 0 | 0 | 0.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Payment payable to Rehab Tenants Alter Accommodation | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Construction Cost for Rehab & Amenity Building | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Approval Cost Of Fungible Cost & Development cess premium | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Architect Cost, RCC & other Professional fees | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Administrative Expenses | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Marketing Expences | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Interest Cost | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Contingous Cost | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | GST | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 27.93 | 8.39 | 19.54 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 3.35 | 0 | 0 | 3.35 | 0 | 0 | 3.35 | 0 | 0 | 3.35 | 0 | 0 | 3.35 | 0 | 0 | 1.98 | 0 | 0 | 0.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Packages | Particulars | Budgeted | Incurred | Balance | Start Date | End Date | Months | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-12-31 | 2023-12-31 | 2023-12-31 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2024-06-30 | 2024-06-30 | 2024-06-30 | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-12-31 | 2024-12-31 | 2024-12-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-12-01 | 2025-12-01
Construction Cost | Construction Cost | 27.93 | 8.39 | 19.54 | 2023-08-01 | 2026-03-31 | 32 | 2023-06-30: 0; 2023-07-31: 0; 2023-09-30: 3.35; 2023-10-31: 0; 2023-12-31: 3.35; 2024-03-31: 3.35; 2024-06-30: 3.35; 2024-09-30: 3.35; 2024-12-31: 1.98; 2025-03-31: 0.81; 2025-06-30: 0; 2025-09-30: 0; 2025-11-30: 0
Construction Cost | Excavation Cost | 3.2581 |  | 3.2581 | 2023-08-01 | 2025-01-30 | 18 | 0.181 | 0.181 | 0.181 | 0.181 | 0.181 | 0.181 | 0.181 | 0.181 | 0.181 | 0.181 | 0.181 | 0.181 | 0.181 | 0.181 | 0.181 | 0.181 | 0.181 | 0.181 | 0.181 | 0.181 | 0.181 | 0.181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Cost | Stack Parking Cost | 6.55 |  | 6.55 | 2023-08-01 | 2025-01-30 | 18 | 0.36389 | 0.36389 | 0.36389 | 0.36389 | 0.36389 | 0.36389 | 0.36389 | 0.36389 | 0.36389 | 0.36389 | 0.36389 | 0.36389 | 0.36389 | 0.36389 | 0.36389 | 0.36389 | 0.36389 | 0.36389 | 0.36389 | 0.36389 | 0.36389 | 0.36389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Cost | Payment payable to Rehab Tenants Alter Accommodation |  |  | 0 | 2023-08-01 | 2025-01-30 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Cost | Construction Cost for Rehab & Amenity Building |  |  | 0 | 2023-08-01 | 2025-01-30 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Cost | Approval Cost Of Fungible Cost & Development cess premium |  |  | 0 | 2023-08-01 | 2025-01-30 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Cost | Architect Cost, RCC & other Professional fees |  |  | 0 | 2023-08-01 | 2025-01-30 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Cost | Administrative Expenses |  |  | 0 | 2023-08-01 | 2025-01-30 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Cost | Marketing Expences |  |  | 0 | 2023-08-01 | 2025-01-30 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Cost | Interest Cost |  |  | 0 | 2023-08-01 | 2025-01-30 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Cost | Contingous Cost |  |  | 0 | 2023-08-01 | 2025-01-30 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GST | GST |  |  | 0 | 2023-08-01 | 2025-01-30 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## AMENITY BUILDING No. 2 Costink (hidden)
[8 empty] | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-12-31 | 2023-12-31 | 2023-12-31 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2024-06-30 | 2024-06-30 | 2024-06-30 | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-12-31 | 2024-12-31 | 2024-12-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-12-01 | 2025-12-01
1 | Particulars | Budgeted | Incurred | Balance |  |  |  | 2023-04-01 | 2023-05-31 | 2023-06-30 | 2023-07-31 | 2023-08-31 | 2023-09-30 | 2023-10-31 | 2023-11-30 | 2023-12-31 | 2024-01-31 | 2024-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-31 | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30
1 | Construction Cost | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Payment payable to Rehab Tenants Alter Accommodation | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Construction Cost for Rehab & Amenity Building | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Approval Cost Of Fungible Cost & Development cess premium | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Architect Cost, RCC & other Professional fees | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Administrative Expenses | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Marketing Expences | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Interest Cost | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Contingous Cost | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | GST | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Packages | Particulars | Budgeted | Incurred | Balance | Start Date | End Date | Months | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-12-31 | 2023-12-31 | 2023-12-31 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2024-06-30 | 2024-06-30 | 2024-06-30 | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-12-31 | 2024-12-31 | 2024-12-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-12-01 | 2025-12-01
Construction Cost | Construction Cost | 0 | 0 | 0 | 2023-04-01 | 2025-11-30 | 32 | 2023-06-30: 0; 2023-09-30: 0; 2023-12-31: 0; 2024-03-31: 0; 2024-06-30: 0; 2024-09-30: 0; 2024-12-31: 0; 2025-03-31: 0; 2025-06-30: 0; 2025-09-30: 0; 2025-11-30: 0
Construction Cost | Excavation Cost | 0.5554 |  | 0.5554 | 2023-04-01 | 2025-11-30 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Stack Parking Cost |  |  | 0 | 2023-04-01 | 2025-11-30 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Payment payable to Rehab Tenants Alter Accommodation |  |  | 0 | 2023-04-01 | 2025-11-30 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction Cost for Rehab & Amenity Building |  |  | 0 | 2023-04-01 | 2025-11-30 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Approval Cost Of Fungible Cost & Development cess premium |  |  | 0 | 2023-04-01 | 2025-11-30 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Architect Cost, RCC & other Professional fees |  |  | 0 | 2023-04-01 | 2025-11-30 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Administrative Expenses |  |  | 0 | 2023-04-01 | 2025-11-30 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Marketing Expences |  |  | 0 | 2023-04-01 | 2025-11-30 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Interest Cost |  |  | 0 | 2023-04-01 | 2025-11-30 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Contingous Cost |  |  | 0 | 2023-04-01 | 2025-11-30 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GST | GST |  |  | 0 | 2023-04-01 | 2025-11-30 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Premium (hidden)
Premium Calculation for Resi
Premium Calculation |  |  | 2021
MIDC Rate | 21000 |  | Present rate 22825 about 8% escalation
Development charges | 343 | per m2 of FSI
Labour Cess | 250 | per m2 of (FSI+ free of FSI)
ScrutinyCharges | 7 | per m2 of FSI
in ₹
| R4 | R5 | Excess Lobby Area | Club house | Total
BUA | 16755.65 | 15247.53 | 543.45 | 1125.36 | 33671.99
Approval Obtained | 16755.65 | 7796.57 | 543.45 | 1125.36 | 26221.03
Free of FSI Area | 54636.48 | 4351.36 | 0 | 633.78 | 59621.62 | 107738.61
Balance Approval | 0 | 7450.96 | 0 | 0 | 7450.96
Free of FSI Area | 0 | 3962.94 | 0 | 0 | 3962.94
Calculation for Premium Paid
Approved Area | 16755.65 | 7796.57 | 514.42 | 1125.36 | 26192
MIDC Rate | 21000 | 21000 | 21000 | 21000
Multiplying factor | 30% | 30% | 30% | 30% | 30%
Premium Amount Paid | 105560595 | 49118391 | 3240846 | 7089768 | 165009600
Dev Charges | 5747187.95 | 2674223.51 | 186403.35 | 385998.48 | 8993813.29
Labour Cess | 17848032.5 | 3036982.5 | 135862.5 | 439785 | 21460662.5
Total | 129155815.45 | 54829597.01 | 3563111.85 | 7915551.48 | 195464075.79
Fire Charges | 7266602.8897 | 3381222.3394 |  | 488046.9709 | 11135872.2
Compound wall |  |  |  |  | 500
Scrutiny Charges | 70686.4037 | 32891.0842 |  | 4747.5121 | 108325
Total | 136493104.7434 | 58243710.4336 | 3563111.85 | 8408345.963 | 206708272.99
Lobby and Club House premium apportined
Excess Lobby | 4402290.711 | 4006055.2521
Club House | 1865510.0859 | 1697601.7641
Total Premium paid | 142760905.5402 | 63947367.4498
Balance Premium Payable for Pending Approvals : R5 |  | Present rate 22825 about 8% escalation |  |  | 22825
Balance Premium Amount | 0 | 51020448.6 | 0 | 0 | 51020448.6
Fire Charges |  | 3176914.3928 |  |  | 3176914.3928
Dev Charges | 0 | 2555679.28 | 0 | 0 | 2555679.28
Labour Cess | 0 | 2853475 | 0 | 0 | 2853475
Scrutiny Charges | 0 | 52156.72 | 0 | 0 | 52156.72
Total | 0 | 59658673.9928 | 0 | 0 | 59658673.9928
GST | 0 | 10738561.3187 | 0 | 0 | 10738561.3187
Total Premium Payable | 0 | 70397235.3115 | 0 | 0 | 70397235.3115
Total Premium for Resi R5 |  | 134344602.7613
Premium Calculation : Galleria | [6 empty] | 410194093.312
Current Rate per Sq.mtr. | 22825
Dev Charges per Sq.mtr. | 343
Labour Cess per Sq.mtr. | 250
BUA in Sq.mtr. | 14445
FSI Premium | 98912137.5
Dev Charges | 4954635
Labour Cess | 3611250
Total Premium | 107478022.5
GST on above @ 18% | 19346044.05
Total Premium + GST | 126824066.55
Fire Charges | 6264518.4604
Total Premium | 133088585.0104

## Schedule (hidden)
Project:
Sale Building -Detailed Implementation schedule A wing
Sr. No. | Particulars | Start Date | End Date
1 | Land Acquisition | 2020-12-01 | 2021-06-01
2 | Plan Approval | 2022-04-01 | 2022-04-01
3 | Execuation , plinit to 11th slab | 2022-04-01 | 2023-08-10
4 | 12th slab | 2023-08-11 | 2023-08-29
5 | 13th slab | 2023-08-30 | 2023-09-14
6 | 14th slab | 2023-09-15 | 2023-09-30
7 | 15th slab | 2023-10-01 | 2023-10-16
8 | 16th slab | 2023-10-17 | 2023-11-01
9 | 17th slab | 2023-11-02 | 2023-11-17
10 | 18th Slab | 2023-11-18 | 2023-12-03
11 | 19th slab | 2023-12-04 | 2023-12-19
12 | 20th slab | 2023-12-20 | 2024-01-04
13 | 21St slab | 2024-01-05 | 2024-01-20
14 | 22nd slab | 2024-01-21 | 2024-02-05
15 | 23rd slab | 2024-02-06 | 2024-02-21
16 | Brick Work | 2023-04-01 | 2024-03-31
17 | Flooring, Door & Window, electrical work | 2023-07-01 | 2024-06-30
18 | Plastering Internal/ External | 2023-12-01 | 2024-11-30
19 | Satir case lift wells flooring | 2024-01-01 | 2024-12-31
20 | external plumimg | 2024-01-01 | 2024-12-31
21 | completion of terrace | 2024-10-01 | 2025-01-29
22 | Painting Internal/ External | 2024-08-01 | 2025-01-28
23 | Finishing & Completion | Mar,-2025 | Mar,-2025
Project:
Sale Building -Detailed Implementation schedule B wing
Sr. No. | Particulars | Start Date | End Date
1 | Land Acquisition | 2020-12-01 | 2021-06-01
2 | 0 | 2022-04-01 | 2022-04-01
3 | Execuation , plinit to 7th slab | 2022-08-01 | 2023-08-10
4 | 8th slab | 2023-08-11 | 2023-08-27
5 | 9th slab | 2023-08-28 | 2023-09-13
6 | 10th slab | 2023-09-14 | 2023-09-30
7 | 11th slab | 2023-10-01 | 2023-10-17
8 | 12th slab | 2023-10-18 | 2023-11-03
9 | 13th slab | 2023-11-04 | 2023-11-20
10 | 14th slab | 2023-11-21 | 2023-12-07
11 | 15th slab | 2023-12-08 | 2023-12-24
12 | 16th slab | 2023-12-25 | 2024-01-10
13 | 17th slab | 2024-01-11 | 2024-01-27
14 | 18th Slab | 2024-01-28 | 2024-02-13
15 | 19th slab | 2024-02-14 | 2024-03-01
16 | 20th slab | 2024-03-02 | 2024-03-18
17 | 21St slab | 2024-03-19 | 2024-04-04
18 | 22nd slab | 2024-04-05 | 2024-04-21
19 | 23rd slab | 2024-04-22 | 2024-05-08
20 | Brick Work | 2023-04-01 | 2024-03-31
21 | Flooring, Door & Window, electrical work | 2023-07-01 | 2024-06-30
22 | Plastering Internal/ External | 2023-12-01 | 2024-11-30
23 | Satir case lift wells flooring | 2024-01-01 | 2024-12-31
24 | external plumimg | 2024-01-01 | 2024-12-31
25 | completion of terrace | 2024-10-01 | 2025-01-29
26 | Painting Internal/ External | 2024-08-01 | 2025-01-28
27 | Finishing & Completion | Mar,-2025 | Mar,-2025
Project:
Rehab Building -Detailed Implementation schedule C wing
Sr. No. | Particulars | Start Date | End Date
1 | Land Acquisition | 2020-12-01 | 2021-06-01
2 | Plan Approval | April,-22 | April,-22
3 | Execuation , plinit to 14th slab | 2022-04-01 | 2023-08-10
4 | 15th slab | 2023-08-11 | 2023-08-26
5 | 16th slab | 2023-08-27 | 2023-09-11
6 | 17th slab | 2023-09-12 | 2023-09-27
7 | 18th Slab | 2023-09-28 | 2023-10-13
8 | 19th slab | 2023-10-14 | 2023-10-29
9 | 20th slab | 2023-10-30 | 2023-11-14
10 | 21St slab | 2023-11-15 | 2023-11-30
11 | 22nd slab | 2023-12-01 | 2023-12-16
12 | 23rd slab | 2023-12-17 | 2024-01-01
13 | Brick Work | 2023-04-01 | 2024-03-31
14 | Flooring, Door & Window, electrical work | 2023-07-01 | 2024-06-30
15 | Plastering Internal/ External | 2023-12-01 | 2024-08-27
16 | Satir case lift wells flooring | 2024-03-01 | 2024-08-28
17 | external plumimg | 2024-02-01 | 2024-08-29
18 | completion of terrace | 2024-07-01 | 2024-10-29
19 | Painting Internal/ External | 2024-05-01 | 2024-10-28
20 | Finishing & Completion | Dec,-2024 | Dec,-2024
Formulas:
Start Date = [End Date, row above]+1
Start Date = +[End Date, row above]+1
End Date = [Start Date]+18
End Date = +[Start Date]+365

## Sales Milestone ok (hidden)
Sales Milestone working | [6 empty] | Avg Sale Rate for Comm. |  | 8180
[6 empty] | Rs. In crores | Avg Sale Rate for Resi. |  | 8180
Quarter | No of Units Estimated to be Sold | Estimated Cumulative Units to be Sold | Estimated Area to be Sold | Estimated Cumulative Area to be Sold | Estimated Amount to be received | Estimated Cumulative Amount to be received | O/s Loan Amount (i) | Sale value of booked units | Balance Revenue (ii) | FACR (ii/i) | Residential Area | Commercial Area | Total Saleable Area | cumulative sales | O/s rece
| 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
Till date | 118 | 118 |  | 0 | #REF! | #REF! | 0 | 0 | #REF! | 0 | 0 |  | 0 | 0 | #REF!
2023-24 Q4 | 0 | 118 |  | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 0 |  | 0 | 0 | #REF!
2024-25 Q1 | 0 | 118 |  | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 0 |  | 0 | 0 | #REF!
2024-25 Q2 | 0 | 118 |  | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 0 |  | 0 | 0 | #REF!
2024-25 Q3 |  | 118 |  | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF!
2024-25 Q4 |  | 118 |  | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF!
2025-26 Q1 |  | 118 |  | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF!
2025-26 Q2 |  | 118 |  | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF!
2025-26 Q3 |  | 118 |  | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF!
2025-26 Q4 |  | 118 |  | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF!
2026-27 Q1 |  | 118 |  | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF!
2026-27 Q2 |  | 118 |  | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF!
2026-27 Q3 |  | 118 |  | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF!
2026-27 Q4 |  | 118 |  | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF!
2027-28 Q1 |  | 118 |  | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF!
2027-28 Q2 |  | 118 |  | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF!
2027-28 Q3 |  | 118 |  | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF!
2027-28 Q4 |  | 118 |  | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF!
2028-29 Q1 |  | 118 |  | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF!
2028-29-Q2 |  | 118 |  | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF!
2028-29-Q3 |  | 118 |  | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF!
2028-29-Q4 |  | 118 |  | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF!
Total | 118 |  | 0 |  | #REF! |  | 0 | 0 |  |  | 0 | 0 | 0

## Velocity Input (hidden)
| Type | AMENITY BUILDING No. 2 | REHAB BUILDING No. 1 | SALE BUILDING | Total
| 1BHK | 0 | 0 | 1 | 1
| 2BHK | 0 | 0 | 129 | 129
| 3++ BHK | 0 | 0 | 52 | 52
| 4++BHK | 0 | 0 | 16 | 16
| Shop | 0 | 5 | 19 | 24
|  | 0 | 5 | 217 | 222
[15 empty] | 0 | 0 |  | 0 | 0 | 0
|  |  |  | 221 | 0 | 0 | 198 | 24 | 0 | 0 | 0 | 0 | 197 | 0 |  |  | Month
Quarter | FY | Month | Size | Qty | AMENITY BUILDING No. 2 | REHAB BUILDING No. 1 | SALE BUILDING | Shop | AMENITY BUILDING No. 2 Value | REHAB BUILDING No. 1 Value | SALE BUILDING Value | Shop Value | Total Units | Total Value | R4 | R5 | Month | R4 | R5
2023-09-30 | 2024-03-31 | 2023-07-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2023-07-31 | 0 | 0 | 0
2023-09-30 | 2024-03-31 | 2023-07-31 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2023-07-31 | 0 | 0 | 0
2023-09-30 | 2024-03-31 | 2023-07-31 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2023-07-31 | 0 | 0 | 0
2023-09-30 | 2024-03-31 | 2023-07-31 | 4++BHK | [9 empty] | 0 | 0 | 0 | 0 | 2023-07-31 | 0 | 0 | 0
2023-09-30 | 2024-03-31 | 2023-08-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2023-08-31 | 0 | 0 | 0
2023-09-30 | 2024-03-31 | 2023-08-31 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2023-08-31 | 0 | 0 | 0
2023-09-30 | 2024-03-31 | 2023-08-31 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2023-08-31 | 0 | 0 | 0
2023-09-30 | 2024-03-31 | 2023-08-31 | 4++BHK | [9 empty] | 0 | 0 | 0 | 0 | 2023-08-31 | 0 | 0 | 0
2023-09-30 | 2024-03-31 | 2023-09-30 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2023-09-30 | 0 | 0 | 0
2023-09-30 | 2024-03-31 | 2023-09-30 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2023-09-30 | 0 | 0 | 0
2023-09-30 | 2024-03-31 | 2023-09-30 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2023-09-30 | 0 | 0 | 0
2023-09-30 | 2024-03-31 | 2023-09-30 | 4++BHK | [9 empty] | 0 | 0 | 0 | 0 | 2023-09-30 | 0 | 0 | 0
2023-12-31 | 2024-03-31 | 2023-10-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2023-10-31 | 0 | 0 | 0
2023-12-31 | 2024-03-31 | 2023-10-31 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2023-10-31 | 0 | 0 | 0
2023-12-31 | 2024-03-31 | 2023-10-31 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2023-10-31 | 0 | 0 | 0
2023-12-31 | 2024-03-31 | 2023-10-31 | 4++BHK | [9 empty] | 0 | 0 | 0 | 0 | 2023-10-31 | 0 | 0 | 0
2023-12-31 | 2024-03-31 | 2023-11-30 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2023-11-30 | 0 | 0 | 0
2023-12-31 | 2024-03-31 | 2023-11-30 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2023-11-30 | 0 | 0 | 0
2023-12-31 | 2024-03-31 | 2023-11-30 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2023-11-30 | 0 | 0 | 0
2023-12-31 | 2024-03-31 | 2023-11-30 | 4++BHK | [9 empty] | 0 | 0 | 0 | 0 | 2023-11-30 | 0 | 0 | 0
2023-12-31 | 2024-03-31 | 2023-12-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2023-12-31 | 0 | 0 | 0
2023-12-31 | 2024-03-31 | 2023-12-31 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2023-12-31 | 0 | 0 | 0
2023-12-31 | 2024-03-31 | 2023-12-31 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2023-12-31 | 0 | 0 | 0
2023-12-31 | 2024-03-31 | 2023-12-31 | 4++BHK | [9 empty] | 0 | 0 | 0 | 0 | 2023-12-31 | 0 | 0 | 0
2024-03-31 | 2024-03-31 | 2024-01-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2024-01-31 | 0 | 0 | 0
2024-03-31 | 2024-03-31 | 2024-01-31 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2024-01-31 | 0 | 0 | 0
2024-03-31 | 2024-03-31 | 2024-01-31 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2024-01-31 | 0 | 0 | 0
2024-03-31 | 2024-03-31 | 2024-01-31 | 4++BHK | [9 empty] | 0 | 0 | 0 | 0 | 2024-01-31 | 0 | 0 | 0
2024-03-31 | 2024-03-31 | 2024-02-29 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2024-02-29 | 0 | 0 | 0
2024-03-31 | 2024-03-31 | 2024-02-29 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2024-02-29 | 0 | 0 | 0
2024-03-31 | 2024-03-31 | 2024-02-29 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2024-02-29 | 0 | 0 | 0
2024-03-31 | 2024-03-31 | 2024-02-29 | 4++BHK | [9 empty] | 0 | 0 | 0 | 0 | 2024-02-29 | 0 | 0 | 0
2024-03-31 | 2024-03-31 | 2024-03-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2024-03-31 | 0 | 0 | 0
2024-03-31 | 2024-03-31 | 2024-03-31 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2024-03-31 | 0 | 0 | 0
2024-03-31 | 2024-03-31 | 2024-03-31 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2024-03-31 | 0 | 0 | 0
2024-03-31 | 2024-03-31 | 2024-03-31 | 4++BHK | [9 empty] | 0 | 0 | 0 | 0 | 2024-03-31 | 0 | 0 | 0
2024-06-30 | 2025-03-31 | 2024-04-30 | 1BHK |  |  |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2024-04-30 | 0 | 0 | 0
2024-06-30 | 2025-03-31 | 2024-04-30 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2024-04-30 | 0 | 0 | 0
2024-06-30 | 2025-03-31 | 2024-04-30 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2024-04-30 | 0 | 0 | 0
2024-06-30 | 2025-03-31 | 2024-04-30 | 4++BHK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2024-04-30 | 0 | 0 | 0
| 2025-03-31 | 2024-04-30 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2024-04-30 | 0 | 0 | 0
2024-06-30 | 2025-03-31 | 2024-05-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2024-05-31 | 0 | 0 | 0
2024-06-30 | 2025-03-31 | 2024-05-31 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2024-05-31 | 0 | 0 | 0
2024-06-30 | 2025-03-31 | 2024-05-31 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2024-05-31 | 0 | 0 | 0
2024-06-30 | 2025-03-31 | 2024-05-31 | 4++BHK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2024-05-31 | 0 | 0 | 0
| 2025-03-31 | 2024-05-31 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2024-05-31 | 0 | 0 | 0
2024-06-30 | 2025-03-31 | 2024-06-30 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2024-06-30 | 0 | 0 | 0
2024-06-30 | 2025-03-31 | 2024-06-30 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2024-06-30 | 0 | 0 | 0
2024-06-30 | 2025-03-31 | 2024-06-30 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2024-06-30 | 0 | 0 | 0
2024-06-30 | 2025-03-31 | 2024-06-30 | 4++BHK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2024-06-30 | 0 | 0 | 0
| 2025-03-31 | 2024-06-30 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2024-06-30 | 0 | 0 | 0
2024-09-30 | 2025-03-31 | 2024-07-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2024-07-31 | 0 | 0 | 0
2024-09-30 | 2025-03-31 | 2024-07-31 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2024-07-31 | 0 | 0 | 0
2024-09-30 | 2025-03-31 | 2024-07-31 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2024-07-31 | 0 | 0 | 0
2024-09-30 | 2025-03-31 | 2024-07-31 | 4++BHK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2024-07-31 | 0 | 0 | 0
| 2025-03-31 | 2024-07-31 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2024-07-31 | 0 | 0 | 0
2024-09-30 | 2025-03-31 | 2024-08-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2024-08-31 | 0 | 0 | 0
2024-09-30 | 2025-03-31 | 2024-08-31 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2024-08-31 | 0 | 0 | 0
2024-09-30 | 2025-03-31 | 2024-08-31 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2024-08-31 | 0 | 0 | 0
2024-09-30 | 2025-03-31 | 2024-08-31 | 4++BHK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2024-08-31 | 0 | 0 | 0
| 2025-03-31 | 2024-08-31 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2024-08-31 | 0 | 0 | 0
2024-09-30 | 2025-03-31 | 2024-09-30 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2024-09-30 | 0 | 0 | 0
2024-09-30 | 2025-03-31 | 2024-09-30 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2024-09-30 | 0 | 0 | 0
2024-09-30 | 2025-03-31 | 2024-09-30 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2024-09-30 | 0 | 0 | 0
2024-09-30 | 2025-03-31 | 2024-09-30 | 4++BHK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2024-09-30 | 0 | 0 | 0
| 2025-03-31 | 2024-09-30 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2024-09-30 | 0 | 0 | 0
2024-12-31 | 2025-03-31 | 2024-10-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2024-10-31 | 0 | 0 | 0
2024-12-31 | 2025-03-31 | 2024-10-31 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2024-10-31 | 0 | 0 | 0
2024-12-31 | 2025-03-31 | 2024-10-31 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2024-10-31 | 0 | 0 | 0
2024-12-31 | 2025-03-31 | 2024-10-31 | 4++BHK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2024-10-31 | 0 | 0 | 0
| 2025-03-31 | 2024-10-31 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2024-10-31 | 0 | 0 | 0
2024-12-31 | 2025-03-31 | 2024-11-30 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2024-11-30 | 0 | 0 | 0
2024-12-31 | 2025-03-31 | 2024-11-30 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2024-11-30 | 0 | 0 | 0
2024-12-31 | 2025-03-31 | 2024-11-30 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2024-11-30 | 0 | 0 | 0
2024-12-31 | 2025-03-31 | 2024-11-30 | 4++BHK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2024-11-30 | 0 | 0 | 0
| 2025-03-31 | 2024-11-30 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2024-11-30 | 0 | 0 | 0
2024-12-31 | 2025-03-31 | 2024-12-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2024-12-31 | 0 | 0 | 0
2024-12-31 | 2025-03-31 | 2024-12-31 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2024-12-31 | 0 | 0 | 0
2024-12-31 | 2025-03-31 | 2024-12-31 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2024-12-31 | 0 | 0 | 0
2024-12-31 | 2025-03-31 | 2024-12-31 | 4++BHK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2024-12-31 | 0 | 0 | 0
| 2025-03-31 | 2024-12-31 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2024-12-31 | 0 | 0 | 0
2025-03-31 | 2025-03-31 | 2025-01-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2025-01-31 | 0 | 0 | 0
2025-03-31 | 2025-03-31 | 2025-01-31 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2025-01-31 | 0 | 0 | 0
2025-03-31 | 2025-03-31 | 2025-01-31 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2025-01-31 | 0 | 0 | 0
2025-03-31 | 2025-03-31 | 2025-01-31 | 4++BHK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2025-01-31 | 0 | 0 | 0
| 2025-03-31 | 2025-01-31 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2025-01-31 | 0 | 0 | 0
2025-03-31 | 2025-03-31 | 2025-02-28 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2025-02-28 | 0 | 0 | 0
2025-03-31 | 2025-03-31 | 2025-02-28 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2025-02-28 | 0 | 0 | 0
2025-03-31 | 2025-03-31 | 2025-02-28 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2025-02-28 | 0 | 0 | 0
2025-03-31 | 2025-03-31 | 2025-02-28 | 4++BHK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2025-02-28 | 0 | 0 | 0
| 2025-03-31 | 2025-02-28 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2025-02-28 | 0 | 0 | 0
2025-03-31 | 2025-03-31 | 2025-03-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2025-03-31 | 0 | 0 | 0
2025-03-31 | 2025-03-31 | 2025-03-31 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2025-03-31 | 0 | 0 | 0
2025-03-31 | 2025-03-31 | 2025-03-31 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2025-03-31 | 0 | 0 | 0
2025-03-31 | 2025-03-31 | 2025-03-31 | 4++BHK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2025-03-31 | 0 | 0 | 0
| 2025-03-31 | 2025-03-31 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2025-03-31 | 0 | 0 | 0
2025-06-30 | 2026-03-31 | 2025-04-30 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2025-04-30 | 0 | 0 | 0
2025-06-30 | 2026-03-31 | 2025-04-30 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2025-04-30 | 0 | 0 | 0
2025-06-30 | 2026-03-31 | 2025-04-30 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2025-04-30 | 0 | 0 | 0
2025-06-30 | 2026-03-31 | 2025-04-30 | 4++BHK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2025-04-30 | 0 | 0 | 0
| 2026-03-31 | 2025-04-30 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2025-04-30 | 0 | 0 | 0
2025-06-30 | 2026-03-31 | 2025-05-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2025-05-31 | 0 | 0 | 0
2025-06-30 | 2026-03-31 | 2025-05-31 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2025-05-31 | 0 | 0 | 0
2025-06-30 | 2026-03-31 | 2025-05-31 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2025-05-31 | 0 | 0 | 0
2025-06-30 | 2026-03-31 | 2025-05-31 | 4++BHK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2025-05-31 | 0 | 0 | 0
| 2026-03-31 | 2025-05-31 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2025-05-31 | 0 | 0 | 0
2025-06-30 | 2026-03-31 | 2025-06-30 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2025-06-30 | 0 | 0 | 0
2025-06-30 | 2026-03-31 | 2025-06-30 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2025-06-30 | 0 | 0 | 0
2025-06-30 | 2026-03-31 | 2025-06-30 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2025-06-30 | 0 | 0 | 0
2025-06-30 | 2026-03-31 | 2025-06-30 | 4++BHK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2025-06-30 | 0 | 0 | 0
| 2026-03-31 | 2025-06-30 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2025-06-30 | 0 | 0 | 0
2025-09-30 | 2026-03-31 | 2025-07-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2025-07-31 | 0 | 0 | 0
2025-09-30 | 2026-03-31 | 2025-07-31 | 2BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2025-07-31 | 0 | 0 | 0
2025-09-30 | 2026-03-31 | 2025-07-31 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2025-07-31 | 0 | 0 | 0
2025-09-30 | 2026-03-31 | 2025-07-31 | 4++BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2025-07-31 | 0 | 0 | 0
| 2026-03-31 | 2025-07-31 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2025-07-31 | 0 | 0 | 0
2025-09-30 | 2026-03-31 | 2025-08-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2025-08-31 | 0 | 0 | 0
2025-09-30 | 2026-03-31 | 2025-08-31 | 2BHK | 3 |  |  | 3 |  |  |  | 0 |  | 3 | 0 | 0 | 0 | 2025-08-31 | 0 | 0 | 0
2025-09-30 | 2026-03-31 | 2025-08-31 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2025-08-31 | 0 | 0 | 0
2025-09-30 | 2026-03-31 | 2025-08-31 | 4++BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2025-08-31 | 0 | 0 | 0
| 2026-03-31 | 2025-08-31 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2025-08-31 | 0 | 0 | 0
2025-09-30 | 2026-03-31 | 2025-09-30 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2025-09-30 | 0 | 0 | 0
2025-09-30 | 2026-03-31 | 2025-09-30 | 2BHK | 4 |  |  | 4 |  |  |  | 0 |  | 4 | 0 | 0 | 0 | 2025-09-30 | 0 | 0 | 0
2025-09-30 | 2026-03-31 | 2025-09-30 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2025-09-30 | 0 | 0 | 0
2025-09-30 | 2026-03-31 | 2025-09-30 | 4++BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2025-09-30 | 0 | 0 | 0
| 2026-03-31 | 2025-09-30 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2025-09-30 | 0 | 0 | 0
2025-12-31 | 2026-03-31 | 2025-10-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2025-10-31 | 0 | 0 | 0
2025-12-31 | 2026-03-31 | 2025-10-31 | 2BHK | 4 |  |  | 4 |  |  |  | 0 |  | 4 | 0 | 0 | 0 | 2025-10-31 | 0 | 0 | 0
2025-12-31 | 2026-03-31 | 2025-10-31 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2025-10-31 | 0 | 0 | 0
2025-12-31 | 2026-03-31 | 2025-10-31 | 4++BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2025-10-31 | 0 | 0 | 0
| 2026-03-31 | 2025-10-31 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2025-10-31 | 0 | 0 | 0
2025-12-31 | 2026-03-31 | 2025-11-30 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2025-11-30 | 0 | 0 | 0
2025-12-31 | 2026-03-31 | 2025-11-30 | 2BHK | 4 |  |  | 4 |  |  |  | 0 |  | 4 | 0 | 0 | 0 | 2025-11-30 | 0 | 0 | 0
2025-12-31 | 2026-03-31 | 2025-11-30 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2025-11-30 | 0 | 0 | 0
2025-12-31 | 2026-03-31 | 2025-11-30 | 4++BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2025-11-30 | 0 | 0 | 0
| 2026-03-31 | 2025-11-30 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2025-11-30 | 0 | 0 | 0
2025-12-31 | 2026-03-31 | 2025-12-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2025-12-31 | 0 | 0 | 0
2025-12-31 | 2026-03-31 | 2025-12-31 | 2BHK | 4 |  |  | 4 |  |  |  | 0 |  | 4 | 0 | 0 | 0 | 2025-12-31 | 0 | 0 | 0
2025-12-31 | 2026-03-31 | 2025-12-31 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2025-12-31 | 0 | 0 | 0
2025-12-31 | 2026-03-31 | 2025-12-31 | 4++BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2025-12-31 | 0 | 0 | 0
| 2026-03-31 | 2025-12-31 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2025-12-31 | 0 | 0 | 0
2026-03-31 | 2026-03-31 | 2026-01-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2026-01-31 | 0 | 0 | 0
2026-03-31 | 2026-03-31 | 2026-01-31 | 2BHK | 4 |  |  | 4 |  |  |  | 0 |  | 4 | 0 | 0 | 0 | 2026-01-31 | 0 | 0 | 0
2026-03-31 | 2026-03-31 | 2026-01-31 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2026-01-31 | 0 | 0 | 0
2026-03-31 | 2026-03-31 | 2026-01-31 | 4++BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2026-01-31 | 0 | 0 | 0
| 2026-03-31 | 2026-01-31 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2026-01-31 | 0 | 0 | 0
2026-03-31 | 2026-03-31 | 2026-02-28 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2026-02-28 | 0 | 0 | 0
2026-03-31 | 2026-03-31 | 2026-02-28 | 2BHK | 4 |  |  | 4 |  |  |  | 0 |  | 4 | 0 | 0 | 0 | 2026-02-28 | 0 | 0 | 0
2026-03-31 | 2026-03-31 | 2026-02-28 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2026-02-28 | 0 | 0 | 0
2026-03-31 | 2026-03-31 | 2026-02-28 | 4++BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2026-02-28 | 0 | 0 | 0
| 2026-03-31 | 2026-02-28 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2026-02-28 | 0 | 0 | 0
2026-03-31 | 2026-03-31 | 2026-03-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2026-03-31 | 0 | 0 | 0
2026-03-31 | 2026-03-31 | 2026-03-31 | 2BHK | 4 |  |  | 4 |  |  |  | 0 |  | 4 | 0 | 0 | 0 | 2026-03-31 | 0 | 0 | 0
2026-03-31 | 2026-03-31 | 2026-03-31 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2026-03-31 | 0 | 0 | 0
2026-03-31 | 2026-03-31 | 2026-03-31 | 4++BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2026-03-31 | 0 | 0 | 0
| 2026-03-31 | 2026-03-31 | Shop | 1 |  |  |  | 1 |  |  |  | 0 |  | 0 | 0 | 0 | 2026-03-31 | 0 | 0 | 0
2026-06-30 | 2027-03-31 | 2026-04-30 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2026-04-30 | 0 | 0 | 0
2026-06-30 | 2027-03-31 | 2026-04-30 | 2BHK | 4 |  |  | 4 |  |  |  | 0 |  | 4 | 0 | 0 | 0 | 2026-04-30 | 0 | 0 | 0
2026-06-30 | 2027-03-31 | 2026-04-30 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2026-04-30 | 0 | 0 | 0
2026-06-30 | 2027-03-31 | 2026-04-30 | 4++BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2026-04-30 | 0 | 0 | 0
| 2027-03-31 | 2026-04-30 | Shop | [8 empty] | 0 |  | 0
2026-06-30 | 2027-03-31 | 2026-05-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2026-05-31 | 0 | 0 | 0
2026-06-30 | 2027-03-31 | 2026-05-31 | 2BHK | 4 |  |  | 4 |  |  |  | 0 |  | 4 | 0 | 0 | 0 | 2026-05-31 | 0 | 0 | 0
2026-06-30 | 2027-03-31 | 2026-05-31 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2026-05-31 | 0 | 0 | 0
2026-06-30 | 2027-03-31 | 2026-05-31 | 4++BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2026-05-31 | 0 | 0 | 0
| 2027-03-31 | 2026-05-31 | Shop | [8 empty] | 0 |  | 0
2026-06-30 | 2027-03-31 | 2026-06-30 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2026-06-30 | 0 | 0 | 0
2026-06-30 | 2027-03-31 | 2026-06-30 | 2BHK | 4 |  |  | 4 |  |  |  | 0 |  | 4 | 0 | 0 | 0 | 2026-06-30 | 0 | 0 | 0
2026-06-30 | 2027-03-31 | 2026-06-30 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2026-06-30 | 0 | 0 | 0
2026-06-30 | 2027-03-31 | 2026-06-30 | 4++BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2026-06-30 | 0 | 0 | 0
| 2027-03-31 | 2026-06-30 | Shop | [8 empty] | 0 |  | 0
2026-09-30 | 2027-03-31 | 2026-07-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2026-07-31 | 0 | 0 | 0
2026-09-30 | 2027-03-31 | 2026-07-31 | 2BHK | 4 |  |  | 4 |  |  |  | 0 |  | 4 | 0 | 0 | 0 | 2026-07-31 | 0 | 0 | 0
2026-09-30 | 2027-03-31 | 2026-07-31 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2026-07-31 | 0 | 0 | 0
2026-09-30 | 2027-03-31 | 2026-07-31 | 4++BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2026-07-31 | 0 | 0 | 0
| 2027-03-31 | 2026-07-31 | Shop | [8 empty] | 0 |  | 0
2026-09-30 | 2027-03-31 | 2026-08-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2026-08-31 | 0 | 0 | 0
2026-09-30 | 2027-03-31 | 2026-08-31 | 2BHK | 4 |  |  | 4 |  |  |  | 0 |  | 4 | 0 | 0 | 0 | 2026-08-31 | 0 | 0 | 0
2026-09-30 | 2027-03-31 | 2026-08-31 | 3++ BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2026-08-31 | 0 | 0 | 0
2026-09-30 | 2027-03-31 | 2026-08-31 | 4++BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2026-08-31 | 0 | 0 | 0
| 2027-03-31 | 2026-08-31 | shop | [8 empty] | 0 |  | 0
2026-09-30 | 2027-03-31 | 2026-09-30 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2026-09-30 | 0 | 0 | 0
2026-09-30 | 2027-03-31 | 2026-09-30 | 2BHK | 4 |  |  | 4 |  |  |  | 0 |  | 4 | 0 | 0 | 0 | 2026-09-30 | 0 | 0 | 0
2026-09-30 | 2027-03-31 | 2026-09-30 | 3++ BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0 | 0 | 0 | 2026-09-30 | 0 | 0 | 0
2026-09-30 | 2027-03-31 | 2026-09-30 | 4++BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0 | 0 | 0 | 2026-09-30 | 0 | 0 | 0
2026-12-31 | 2027-03-31 | 2026-10-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0
2026-12-31 | 2027-03-31 | 2026-10-31 | 2BHK | 4 |  |  | 4 |  |  |  | 0 |  | 4 | 0
2026-12-31 | 2027-03-31 | 2026-10-31 | 3++ BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0
2026-12-31 | 2027-03-31 | 2026-10-31 | 4++BHK | 1 |  |  | 1 |  |  |  | 0 |  | 1 | 0
2026-12-31 | 2027-03-31 | 2026-11-30 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0
2026-12-31 | 2027-03-31 | 2026-11-30 | 2BHK | 4 |  |  | 4 |  |  |  | 0 |  | 4 | 0
2026-12-31 | 2027-03-31 | 2026-11-30 | 3++ BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0
2026-12-31 | 2027-03-31 | 2026-11-30 | 4++BHK | [9 empty] | 0 | 0
2026-12-31 | 2027-03-31 | 2026-12-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0
2026-12-31 | 2027-03-31 | 2026-12-31 | 2BHK | 4 |  |  | 4 |  |  |  | 0 |  | 4 | 0
2026-12-31 | 2027-03-31 | 2026-12-31 | 3++ BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0
2026-12-31 | 2027-03-31 | 2026-12-31 | 4++BHK | [9 empty] | 0 | 0
2027-03-31 | 2027-03-31 | 2027-01-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0
2027-03-31 | 2027-03-31 | 2027-01-31 | 2BHK | 4 |  |  | 4 |  |  |  | 0 |  | 4 | 0
2027-03-31 | 2027-03-31 | 2027-01-31 | 3++ BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0
2027-03-31 | 2027-03-31 | 2027-01-31 | 4++BHK | [9 empty] | 0 | 0
2027-03-31 | 2027-03-31 | 2027-02-28 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0
2027-03-31 | 2027-03-31 | 2027-02-28 | 2BHK | 4 |  |  | 4 |  |  |  | 0 |  | 4 | 0
2027-03-31 | 2027-03-31 | 2027-02-28 | 3++ BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0
2027-03-31 | 2027-03-31 | 2027-02-28 | 4++BHK | [9 empty] | 0 | 0
2027-03-31 | 2027-03-31 | 2027-03-31 | 1BHK | [5 empty] | 0 | 0 | 0 |  | 0 | 0
2027-03-31 | 2027-03-31 | 2027-03-31 | 2BHK | 4 |  |  | 4 |  |  |  | 0 |  | 4 | 0
2027-03-31 | 2027-03-31 | 2027-03-31 | 3++ BHK | 2 |  |  | 2 |  |  |  | 0 |  | 2 | 0
2027-03-31 | 2027-03-31 | 2027-03-31 | 4++BHK | [9 empty] | 0 | 0
Formulas:
Month = [AMENITY BUILDING No. 2]
Quarter = [Quarter, row above]
Quarter = EOMONTH([Quarter, row above],3)
Type = [Type, row above]
Type = EOMONTH([Type, row above],12)
AMENITY BUILDING No. 2 = [AMENITY BUILDING No. 2, row above]
Note on E2: Author: Taken from Sale Buinding MIS