## Final Summary
Project expenses | Estimated Cost as per Cost Vetting | Incurred Cost as per Bill till 31.12.2024 | Incurred Cost as per CA till 31.12.2024 | Incurred Cost as per Bill till 30.11.2024 | Incurred Cost as per CA till 30.11.2024 | Difference between the Bills & CA | Difference between both the Bills | Difference between both CA | Remark
Land Cost | 0.51 | 0.51339 | 0.51 | 0.51339 | 0.51 | 0.0033885 | 0 | 0
Rent Cost | 3.49 | 0.83269 | 0.83 | 0.76818 | 0.8 | 0.0026882 | 0.064504 | 0.03
Construction Cost of Sale Building | 12.3 | 2.9323 | 3.09 | 0.83402 | 0.81 | -0.15771 | 2.0983 | 2.28
TDR Cost | 2.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Approval Cost | 6.44 | 0.47822 | 0.5 | 0.47722 | 0.47 | -0.021777 | 0.001 | 0.03
Professional Charges | 0.62 | 0.11804 | 0.08 | 0.085741 | 0.05 | 0.038044 | 0.032303 | 0.03
Admin Cost | 0.49 | 0.55236 | 0.47 | 0.27921 | 0.34 | 0.082356 | 0.27314 | 0.13 | .
Marketing Expenses | 0.74 | 0.020084 | 0 | 0.020084 | 0 | 0.020084 | 0 | 0
Interest Cost | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contingency Cost | 0.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost | 29.34 | 5.4471 | 5.48 | 2.9778 | 2.98 | -0.032932 | 2.4692 | 2.5
|  | 23.8929 | 18.68%
Particulars | Revised Estimated Cost (in Cr.) | 31.12.2024 as per Bill Tally (inclusive of GST) | Cost incurred as %age total cost of that Component | Cost incurred as %age of cost incurred as on 31.12.2024
Land Cost | 0.51 | 0.51339 | 100.7% | 1.75%
Rent Cost | 3.49 | 0.83269 | 23.86% | 2.838%
Construction Cost of Sale Building | 12.3 | 2.9323 | 23.84% | 9.994%
TDR Cost | 2.62 | 0 | 0% | 0%
Approval Cost | 6.44 | 0.47822 | 7.426% | 1.63%
Professional Charges | 0.62 | 0.11804 | 19.04% | 0.4023%
Admin Cost | 0.49 | 0.55236 | 112.7% | 1.883%
Marketing Expenses | 0.74 | 0.020084 | 2.714% | 0.06845%
Interest Cost | 1.76 | 0 | 0% | 0%
Contingency Cost | 0.37 | 0 | 0% | 0%
Total | 29.34 | 5.4471 | 18.57% | 18.57%
Pariculars | 31.12.2024 as per Bill Tally (inclusive of GST) | 30.11.2024 as per Bill Tally (inclusive of GST) | Difference b/w bills of 30.11..2024 & 31.12.2024 | Difference of Cost incurred as %age of cost incurred as on 30.11.2024 & 31.12.2024
Land Cost | 0.51339 | 0.51339 | 0 | 0.51339
Rent Cost | 0.83269 | 0.76818 | 0.06 | 1.102%
Construction Cost of Sale Building | 2.9323 | 0.83402 | 2.1 | 38.55%
TDR Cost | 0 | 0 | 0 | 0%
Approval Cost | 0.47822 | 0.47722 | 0 | 0%
Professional Charges | 0.11804 | 0.085741 | 0.03 | 0.5508%
Admin Cost | 0.55236 | 0.27921 | 0.27 | 4.957%
Marketing Expenses | 0.020084 | 0.020084 | 0 | 0%
Interest Cost | 0 | 0 | 0 | 0%
Contingency Cost | 0 | 0 | 0 | 0%
Total | 5.4471 | 2.9778 | 2.47 | 45.35%

## Summary Sheet
Sr. No. | Particulars | Incurred Cost in ` till 30.11.2024 | Incurred Cost in ` Cr. Till 30.11.2024 | Incurred Cost in ` till 30.11.2024 | Incurred Cost in ` Cr. Till 30.11.2024 | Balance in ` | Balance in ` Cr.
1 | Land Cost | 5133885 | 0.51339 | 5133885 | 0.51339 | 0 | 0
2 | Rent Cost | 8326882 | 0.83269 | 7681841 | 0.76818 | 645041 | 0.064504
3 | Construction Cost | 29322857.86 | 2.9323 | 8340155.86 | 0.83402 | 20982702 | 2.0983
4 | TDR Cost | 0 | 0 | 0 | 0 | 0 | 0
5 | Approval Cost & Stamp Duty | 4782225.2 | 0.47822 | 4772225.2 | 0.47722 | 10000 | 0.001
6 | Professional Cost | 1180439.6 | 0.11804 | 857411.6 | 0.085741 | 323028 | 0.032303
7 | Admin Cost | 5523557.58 | 0.55236 | 2792119.58 | 0.27921 | 2731438 | 0.27314
8 | Marketing Cost | 200836 | 0.020084 | 200836 | 0.020084 | 0 | 0
9 | Interest Cost | 0 | 0 | 0 | 0 | 0 | 0
10 | Contingency Cost | 0 | 0 | 0 | 0 | 0 | 0
| Total | 54470683.24 | 5.4471 | 29778474.24 | 2.9778 | 24692209 | 2.4692
|  | 49336798.24 | 4.9337 | 24644589.24 | 2.4645 | 24692209 | 2.4692
17600000
17600000

## Land, Rent, TDR, Approval
Land Cost Description | [5 empty] | TDR Cost
Sr. No. | Date | Document Name | Description | Total Cost | Incurred Cost | Sr. No. | Date | Description | Area in Sq. M. | Total Cost | Incurred Cost
1 | 2023-04-28 | Developer Agreement | Stamp Duty | 5100045 | 5100045 | 1 |  | Stamp Duty |  | 0 | 0
2 |  |  | Reg. Fees | 30000 | 30000 | 2 |  | Reg. Fees |  | 0 | 0
3 |  |  |  | 2600 | 2600 | 3 |  | Stamp Duty | 0 | 0 | 0
4 | 2023-04-28 | General Power of Attorney | Stamp Duty | 500 | 500 | 4 |  | Purchase Price |  | 0 | 0
5 |  |  | Reg. Fees | 100 | 100 | Total |  |  | 0 | 0 | 0
6 |  |  |  | 640 | 640
Total |  |  |  | 5133885 | 5133885
| Rent Calulation |  |  |  | Paid Amount
| Sr. No. | Particulars |  | Unit | 1/4/23 to 31/12/24
| 1 | No. of Tenants | 14 | Nos | 8326882
| 2 | No. of Existing Carpet Area | 7248.41 | Sq. Ft.
| 3 | Rate per Sq. Ft. on Carpet Area for Dec 23 to Nov 24 | 100 | Rupees
| 4 | Rent per month per tenant for Dec 23 to Nov 24 | 724841 | Rupees
| 5 | Rent per year for Dec 23 to Nov 24 | 8698092 | Rupees
| 6 | Rate per Sq. Ft. on Carpet Area for Dec 25 to Dec 26 | 110 | Rupees
| 7 | Rent per month per tenant for Dec 25 to Dec 26 | 797325.1 | Rupees
| 8 | Rent per year for Dec 25 to Dec 26 | 10365226 | Rupees
| 9 | Shifting Charges per tenant | 20000 | Rupees
| 10 | Total Shifting Charges | 280000 | Rupees
| 11 | Brokerage Charges | 724841 | Rupees
| 12 | Rate per Sq. Ft. on Carpet Area for Hardship Compesation | 2000 | Rupees
| 13 | Hardship Compesation Cost | 14496820 | Rupees
| 14 | Sinking Fund per Tenant | 25000 | Rupees
| 15 | Total Sinking Fund Cost | 350000 | Rupees
| Total rent paid to tenants |  | 34914979 | Rupees | 8326882
Approval Cost
| Sr. No. | Particulars | Amount in ` | Incurred Amount till 30/11/2024
| 1 | Scrutiny Fees | 520600 | 4782225.2
| 2 | IOD Deposit | 16000
| 3 | Debris Deposit | 30150
| 4 | Staircase Premium | 9604000
| 5 | Development Charges | 7768000
| 6 | Development Cess | 1865000
| 7 | Labour Welfare Charges | 826226
| 8 | Fungible Compensatory | 16932750
| 9 | Open Space Deficiency Premium | 17334000
| Total |  | 54896726 | 4782225.2

## Construction Cost
Date | Particulars | Supplier Invoice No. | Supplier Invoice Date | GSTIN/UIN | Narration | Gross Total | Purchase Net GST @18% Shanti Sadan | CGST @ 9% - Shanti Sadan | SGST @9% - Shanti Sadan | Round Off | Purchase Net GST @28% - Shanti Sadan | CGST @ 14% - Shanti Sadan | SGST @ 14% - Shanti Sadan | Transportation - Shanti Sadan | RD Purchase No Set Off-Shanti Sadan
2024-04-25 | Brijeshkumar & Co-Shanti Sadan | 250/24-25 | 2024-04-25 | 27ADOPR7271D1Z5 | Ultratech Cement 2 BAGS @ 335.94/- | 860 |  |  |  |  | 671.88 | 94.06 | 94.06
2024-04-26 | Swastik Sales - Shanti Sadan | 106 | 2024-04-26 | 27CNWPS2429C1ZL | DRP FWRRULEISI 1/2, GI UNION 1/2, GI SOCKET 1/2, GI BEND 1/2 | 1785 | 1512.4 | 136.11 | 136.11 | 0.38
2024-04-29 | P5 Industries - Shanti Sadan | P5/24-25/314 | 2024-04-29 | 27ASRPB3828L1ZB | ELECTRICAL MATERIAL | 42780 | 35654.15 | 3262.87 | 3262.87 | 0.11 |  |  |  | 600
2024-05-19 | Arton Global (Steel) Shanti Sadan | AG/M/031/24-25 | 2024-05-19 | 27ABOFA7024M1Z1 | STEEL | 2921184.8 | 2475580 | 222802.2 | 222802.2 | 0.4
2024-05-23 | RSS Infra Co - Shanti Sadan | RSS/MAY24-25/020 | 2024-05-23 | 27EQDPS3153M1ZC | PUMPING CHARGES QTY.53 @339.62/- CUM | 21240 | 18000 | 1620 | 1620
2024-05-23 | RSS Infra Co - Shanti Sadan | RSS/MAY24-25/019 | 2024-05-23 | 27EQDPS3153M1ZC | READY MIX CONCRETE M-15 QTY 14 @5338.98/- CUM | 88200 | 74745.72 | 6727.11 | 6727.11 | 0.06
2024-05-23 | RSS Infra Co - Shanti Sadan | RSS/MAY24-25/018 | 2024-05-23 | 27EQDPS3153M1ZC | READY MIX CONCRETE M-15 QTY 14 @5338.98/- CUM | 88200 | 74745.72 | 6727.11 | 6727.11 | 0.06
2024-05-23 | RSS Infra Co - Shanti Sadan | RSS/MAY24-25/017 | 2024-05-23 | 27EQDPS3153M1ZC | READY MIX CONCRETE M-15 QTY 12 @5338.98/- CUM | 75600 | 64067.76 | 5766.1 | 5766.1 | 0.04
2024-05-23 | RSS Infra Co - Shanti Sadan | RSS/MAY24-25/016 | 2024-05-23 | 27EQDPS3153M1ZC | READY MIX CONCRETE M-15 QTY 13 @5338.98/- CUM | 81900 | 69406.74 | 6246.61 | 6246.61 | 0.04
2024-05-25 | Jai Bharat Trading Co. - Shanti Sadan | 53 | 2024-05-25 | 27BJDPS3850F1Z4 | G.I. CUTTING WIRE QTY 828 @60/- | 58622.8 | 49680 | 4471.2 | 4471.2 | 0.4
2024-05-27 | Ramkishan Prajapati - Shanti Sadan | 749 | 2024-05-27 |  | RCC COVER 75MM FOOTING, 40MM ROUND, TRIP | 9300 | [8 empty] | 9300
2024-05-29 | RSS Infra Co - Shanti Sadan | RSS/MAY 24-25/031 | 2024-05-29 | 27EQDPS3153M1ZC | READY MIX CONCRETE M-30 QTY.7 @5338.98/- CUM | 44100 | 37372.86 | 3363.56 | 3363.56 | 0.02
2024-06-02 | RSS Infra Co - Shanti Sadan | RSS/JUN 24-25/042 | 2024-06-02 | 27EQDPS3153M1ZC | PUMPING CHARGES QTY 133 @ 211.86/- CUM | 33250.02 | 28177.97 | 2536.02 | 2536.02 | 0.01
2024-06-02 | RSS Infra Co - Shanti Sadan | RSS/JUN 24-25/032 | 2024-06-02 | 27EQDPS3153M1ZC | READY MIX CONCRETE M-30 QTY.14 @6228.81/- CUM | 102900 | 87203.34 | 7848.3 | 7848.3 | 0.06
2024-06-02 | RSS Infra Co - Shanti Sadan | RSS/JUN 24-25/033 | 2024-06-02 | 27EQDPS3153M1ZC | READY MIX CONCRETE M-30 QTY.13 @6228.81/- CUM | 95550 | 80974.53 | 7287.71 | 7287.71 | 0.05
2024-06-02 | RSS Infra Co - Shanti Sadan | RSS/JUN 24-25/034 | 2024-06-02 | 27EQDPS3153M1ZC | READY MIX CONCRETE M-30 QTY.13 @6228.81/- CUM | 95550 | 80974.53 | 7287.71 | 7287.71 | 0.05
2024-06-02 | RSS Infra Co - Shanti Sadan | RSS/JUN 24-25/035 | 2024-06-02 | 27EQDPS3153M1ZC | READY MIX CONCRETE M-30 QTY.13 @6228.81/- CUM | 95550 | 80974.53 | 7287.71 | 7287.71 | 0.05
2024-06-02 | RSS Infra Co - Shanti Sadan | RSS/JUN 24-25/036 | 2024-06-02 | 27EQDPS3153M1ZC | READY MIX CONCRETE M-30 QTY.13 @6228.81/- CUM | 95550 | 80974.53 | 7287.71 | 7287.71 | 0.05
2024-06-02 | RSS Infra Co - Shanti Sadan | RSS/JUN 24-25/037 | 2024-06-02 | 27EQDPS3153M1ZC | READY MIX CONCRETE M-30 QTY.13 @6228.81/- CUM | 95550 | 80974.53 | 7287.71 | 7287.71 | 0.05
2024-06-02 | RSS Infra Co - Shanti Sadan | RSS/JUN 24-25/038 | 2024-06-02 | 27EQDPS3153M1ZC | READY MIX CONCRETE M-30 QTY.13 @6228.81/- CUM | 95550 | 80974.53 | 7287.71 | 7287.71 | 0.05
2024-06-02 | RSS Infra Co - Shanti Sadan | RSS/JUN 24-25/039 | 2024-06-02 | 27EQDPS3153M1ZC | READY MIX CONCRETE M-30 QTY.14 @6228.81/- CUM | 102900 | 87203.34 | 7848.3 | 7848.3 | 0.06
2024-06-02 | RSS Infra Co - Shanti Sadan | RSS/JUN 24-25/040 | 2024-06-02 | 27EQDPS3153M1ZC | READY MIX CONCRETE M-30 QTY.13 @6228.81/- CUM | 95550 | 80974.53 | 7287.71 | 7287.71 | 0.05
2024-06-02 | RSS Infra Co - Shanti Sadan | RSS/JUN 24-25/041 | 2024-06-02 | 27EQDPS3153M1ZC | READY MIX CONCRETE M-30 QTY.14 @6228.81/- CUM | 102900 | 87203.34 | 7848.3 | 7848.3 | 0.06
2024-06-09 | RSS Infra Co - Shanti Sadan | RSS/JUNE/043 | 2024-06-09 | 27EQDPS3153M1ZC | RMC M-30 | 88200 | 74745.72 | 6727.11 | 6727.11 | 0.06
2024-06-09 | RSS Infra Co - Shanti Sadan | RSS/JUNE/044 | 2024-06-09 | 27EQDPS3153M1ZC | RMC M-30 | 88200 | 74745.72 | 6727.11 | 6727.11 | 0.06
2024-06-09 | RSS Infra Co - Shanti Sadan | RSS/JUNE/045 | 2024-06-09 | 27EQDPS3153M1ZC | RMC M-30 | 88200 | 74745.72 | 6727.11 | 6727.11 | 0.06
2024-06-09 | RSS Infra Co - Shanti Sadan | RSS/JUNE/046 | 2024-06-09 | 27EQDPS3153M1ZC | RMC M-30 | 88200 | 74745.72 | 6727.11 | 6727.11 | 0.06
2024-06-09 | RSS Infra Co - Shanti Sadan | RSS/JUNE/047 | 2024-06-09 | 27EQDPS3153M1ZC | RMC M-30 | 88200 | 74745.72 | 6727.11 | 6727.11 | 0.06
2024-06-09 | RSS Infra Co - Shanti Sadan | RSS/JUNE/048 | 2024-06-09 | 27EQDPS3153M1ZC | RMC M-30 | 88200 | 74745.72 | 6727.11 | 6727.11 | 0.06
2024-06-09 | RSS Infra Co - Shanti Sadan | RSS/JUNE/049 | 2024-06-09 | 27EQDPS3153M1ZC | RMC M-30 | 88200 | 74745.72 | 6727.11 | 6727.11 | 0.06
2024-06-09 | RSS Infra Co - Shanti Sadan | RSS/JUNE/050 | 2024-06-09 | 27EQDPS3153M1ZC | RMC M-30 | 88200 | 74745.72 | 6727.11 | 6727.11 | 0.06
2024-06-09 | RSS Infra Co - Shanti Sadan | RSS/JUNE/051 | 2024-06-09 | 27EQDPS3153M1ZC | RMC M-30 | 88200 | 74745.72 | 6727.11 | 6727.11 | 0.06
2024-06-09 | RSS Infra Co - Shanti Sadan | RSS/JUNE/052 | 2024-06-09 | 27EQDPS3153M1ZC | RMC M-30 | 88200 | 74745.72 | 6727.11 | 6727.11 | 0.06
2024-06-09 | RSS Infra Co - Shanti Sadan | RSS/JUNE/053 | 2024-06-09 | 27EQDPS3153M1ZC | RMC M-30 | 88200 | 74745.72 | 6727.11 | 6727.11 | 0.06
2024-06-09 | RSS Infra Co - Shanti Sadan | RSS/JUNE/054 | 2024-06-09 | 27EQDPS3153M1ZC | RMC M-30 | 80850 | 68516.91 | 6166.52 | 6166.52 | 0.05
2024-06-09 | RSS Infra Co - Shanti Sadan | RSS/JUNE/055 | 2024-06-09 | 27EQDPS3153M1ZC | RMC M-30 | 88200 | 74745.72 | 6727.11 | 6727.11 | 0.06
2024-06-09 | RSS Infra Co - Shanti Sadan | RSS/JUNE/056 | 2024-06-09 | 27EQDPS3153M1ZC | RMC M-30 | 88200 | 74745.72 | 6727.11 | 6727.11 | 0.06
2024-06-09 | RSS Infra Co - Shanti Sadan | RSS/JUNE/057 | 2024-06-09 | 27EQDPS3153M1ZC | PUMPING CHARGES | 41999.24 | 35592.48 | 3203.32 | 3203.32 | 0.12
2024-06-15 | RSS Infra Co - Shanti Sadan | RSS/JUNE/058 | 2024-06-15 | 27EQDPS3153M1ZC | RMC M-30 | 88200 | 74745.72 | 6727.11 | 6727.11 | 0.06
2024-06-15 | RSS Infra Co - Shanti Sadan | RSS/JUNE/059 | 2024-06-15 | 27EQDPS3153M1ZC | RMC M-30 | 88200 | 74745.72 | 6727.11 | 6727.11 | 0.06
2024-06-15 | RSS Infra Co - Shanti Sadan | RSS/JUNE/060 | 2024-06-15 | 27EQDPS3153M1ZC | RMC M-30 | 73500 | 62288.1 | 5605.93 | 5605.93 | 0.04
2024-06-17 | RSS Infra Co - Shanti Sadan | RSS/JUNE/062 | 2024-06-17 | 27EQDPS3153M1ZC | PUMPING CHARGES | 23600 | 20000 | 1800 | 1800
2024-06-22 | RSS Infra Co - Shanti Sadan | RSS/JUN 24-25/063 | 2024-06-22 | 27EQDPS3153M1ZC | READY MIX CONCRETE M-30 QTY.14 @6228.81/- CUM | 102900 | 87203.34 | 7848.3 | 7848.3 | 0.06
2024-06-22 | RSS Infra Co - Shanti Sadan | RSS/JUN 24-25/064 | 2024-06-22 | 27EQDPS3153M1ZC | READY MIX CONCRETE M-30 QTY.14 @6228.81/- CUM | 102900 | 87203.34 | 7848.3 | 7848.3 | 0.06
2024-06-22 | RSS Infra Co - Shanti Sadan | RSS/JUN 24-25/065 | 2024-06-22 | 27EQDPS3153M1ZC | RMC M-30 | 51450 | 43601.67 | 3924.15 | 3924.15 | 0.03
2024-06-22 | RSS Infra Co - Shanti Sadan | RSS/JUNE/066 | 2024-06-22 | 27EQDPS3153M1ZC | PUMPING CHARGES | 23600 | 20000 | 1800 | 1800
2024-06-25 | RSS Infra Co - Shanti Sadan | RSS/JUNE/067 | 2024-06-25 | 27EQDPS3153M1ZC | RMC M-30 | 88200 | 74745.72 | 6727.11 | 6727.11 | 0.06
2024-06-25 | RSS Infra Co - Shanti Sadan | RSS/JUNE/068 | 2024-06-25 | 27EQDPS3153M1ZC | RMC M-30 | 88200 | 74745.72 | 6727.11 | 6727.11 | 0.06
2024-06-25 | RSS Infra Co - Shanti Sadan | RSS/JUNE/069 | 2024-06-25 | 27EQDPS3153M1ZC | RMC M-30 | 33075 | 28029.65 | 2522.67 | 2522.67 | 0.01
2024-06-25 | RSS Infra Co - Shanti Sadan | RSS/JUNE/070 | 2024-06-25 | 27EQDPS3153M1ZC | PUMPING CHARGES | 23600 | 20000 | 1800 | 1800
2024-06-29 | RSS Infra Co - Shanti Sadan | RSS/JUNE/075 | 2024-06-29 | 27EQDPS3153M1ZC | RMC M-30 | 88200 | 74745.72 | 6727.11 | 6727.11 | 0.06
2024-06-29 | RSS Infra Co - Shanti Sadan | RSS/JUNE/076 | 2024-06-29 | 27EQDPS3153M1ZC | RMC M-30 | 88200 | 74745.72 | 6727.11 | 6727.11 | 0.06
2024-06-29 | RSS Infra Co - Shanti Sadan | RSS/JUNE/077 | 2024-06-29 | 27EQDPS3153M1ZC | RMC M-30 | 33075 | 28029.65 | 2522.67 | 2522.67 | 0.01
2024-06-29 | RSS Infra Co - Shanti Sadan | RSS/JUNE/078 | 2024-06-29 | 27EQDPS3153M1ZC | PUMPING CHARGES | 23600 | 20000 | 1800 | 1800
2024-07-10 | Deepak Kumar Sharma - Shanti Sadan | 01 | 2024-07-10 |  | PUMPING CHARGES | 20000 | [8 empty] | 20000
2024-07-10 | Steel Centre- Shanti Sadan | SC-GS-154/24-25 | 2024-07-10 | 27AAAFS5359Q1ZH | RMC-30 QTY 6.5 CUM @6300/- | 48321 | 40950 | 3685.5 | 3685.5
2024-07-10 | Steel Centre- Shanti Sadan | SC-GS-155/24-25 | 2024-07-10 | 27AAAFS5359Q1ZH | RMC-30 QTY.7 CUM @6300/- | 52038 | 44100 | 3969 | 3969
2024-07-10 | Steel Centre- Shanti Sadan | SC-GS-156/24-25 | 2024-07-10 | 27AAAFS5359Q1ZH | RMC-30 QTY.7 CUM @6300/- | 52038 | 44100 | 3969 | 3969
2024-07-10 | Steel Centre- Shanti Sadan | SC-GS-157/24-25 | 2024-07-10 | 27AAAFS5359Q1ZH | RMC-30 QTY 6.5 CUM @6300/- | 48321 | 40950 | 3685.5 | 3685.5
2024-07-10 | Steel Centre- Shanti Sadan | SC-GS-158/24-25 | 2024-07-10 | 27AAAFS5359Q1ZH | RMC-30 QTY.11 CUM @6300/- | 81774 | 69300 | 6237 | 6237
2024-07-10 | Steel Centre- Shanti Sadan | SC-GS-159/24-25 | 2024-07-10 | 27AAAFS5359Q1ZH | RMC-30 QTY.6 CUM @6300/- | 44604 | 37800 | 3402 | 3402
2024-07-17 | Steel Centre- Shanti Sadan | SC-DN-09/24-25 | 2024-07-17 | 27AAAFS5359Q1ZH | PUMPING CHARGES | 21240 | 18000 | 1620 | 1620
2024-07-17 | Steel Centre- Shanti Sadan | SC-GS-168/24-25 | 2024-07-17 | 27AAAFS5359Q1ZH | RMC-30 QTY.7.5 CUM @6300/- | 55755 | 47250 | 4252.5 | 4252.5
2024-07-17 | Steel Centre- Shanti Sadan | SC-GS-167/24-25 | 2024-07-17 | 27AAAFS5359Q1ZH | RMC-30 QTY.7 CUM @6300/- | 52038 | 44100 | 3969 | 3969
2024-07-17 | Steel Centre- Shanti Sadan | SC-GS-166/24-25 | 2024-07-17 | 27AAAFS5359Q1ZH | RMC-30 QTY.7 CUM @6300/- | 52038 | 44100 | 3969 | 3969
2024-07-17 | Steel Centre- Shanti Sadan | SC-GS/165/24-25 | 2024-07-17 | 27AAAFS5359Q1ZH | RMC-30 QTY.7 CUM @6300/- | 52038 | 44100 | 3969 | 3969
2024-07-20 | Steel Centre- Shanti Sadan | SC-GS-178/24-25 | 2024-07-20 | 27AAAFS5359Q1ZH | RMC-15 QTY. 5CUM @5350/- | 31565 | 26750 | 2407.5 | 2407.5
2024-08-06 | Sunshine Infra - Shanti Sadan | SI/RMC/0053/24-25 | 2024-08-06 | 27AFTH3733F1ZB | PUMPING CHARGE | 21240 | 18000 | 1620 | 1620
2024-08-10 | Steel Centre- Shanti Sadan | SC-GS-236/24-25 | 2024-08-10 | 27AAAFS5359Q1ZH | RMC -30 | 55755 | 47250 | 4252.5 | 4252.5
2024-08-10 | Steel Centre- Shanti Sadan | SC-GS-237/24-25 | 2024-08-10 | 27AAAFS5359Q1ZH | RMC -30 | 29736 | 25200 | 2268 | 2268
2024-08-10 | Steel Centre- Shanti Sadan | SC-GS-238/24-25 | 2024-08-10 | 27AAAFS5359Q1ZH | RMC -30 | 48321 | 40950 | 3685.5 | 3685.5
2024-08-10 | Steel Centre- Shanti Sadan | SC-GS-239/24-25 | 2024-08-10 | 27AAAFS5359Q1ZH | RMC -30 | 59472 | 50400 | 4536 | 4536
2024-08-10 | Steel Centre- Shanti Sadan | SC-GS-240/24-25 | 2024-08-10 | 27AAAFS5359Q1ZH | RMC -30 | 29736 | 25200 | 2268 | 2268
2024-08-14 | Steel Centre- Shanti Sadan | SC-GS-253/24-25 | 2024-08-14 | 27AAAFS5359Q1ZH | RMC -30 | 92925 | 78750 | 7087.5 | 7087.5
2024-08-14 | Steel Centre- Shanti Sadan | SC-GS-254/24-25 | 2024-08-14 | 27AAAFS5359Q1ZH | RMC -30 | 96642 | 81900 | 7371 | 7371
2024-08-14 | Steel Centre- Shanti Sadan | SC-GS-255/24-25 | 2024-08-14 | 27AAAFS5359Q1ZH | RMC -30 | 96642 | 81900 | 7371 | 7371
2024-08-14 | Steel Centre- Shanti Sadan | SC-GS-256/24-25 | 2024-08-14 | 27AAAFS5359Q1ZH | RMC -30 | 66906 | 56700 | 5103 | 5103
2024-08-14 | Steel Centre- Shanti Sadan | SC-DN-14/24-25 | 2024-08-14 | 27AAAFS5359Q1ZH | PUMPING CHARGES | 21240 | 18000 | 1620 | 1620
2024-08-24 | Steel Centre- Shanti Sadan | SC-GS-265/24-25 | 2024-08-24 | 27AAAFS5359Q1ZH | RMC M-30 QTY 8.5 CUM @6300/- PER CUM | 63189 | 53550 | 4819.5 | 4819.5
2024-09-01 | Jai Durga Transport-Shanti Sadan | 4709 | 2024-09-01 |  | WATER SUPPLY | 8400 | [8 empty] | 8400
2024-09-02 | Steel Centre- Shanti Sadan | SC-GS-344/24-25 | 2024-09-02 | 27AAAFS5359Q1ZH | RMC M-30 QTY.9.5 CUM @6300/- PER CUM | 70623 | 59850 | 5386.5 | 5386.5
2024-09-02 | Steel Centre- Shanti Sadan | SC-DN-18/24-25 | 2024-09-02 | 27AAAFS5359Q1ZH | PUMPING CHARGES | 21240 | 18000 | 1620 | 1620
2024-09-02 | Steel Centre- Shanti Sadan | SC-GS-345/24-25 | 2024-09-02 | 27AAAFS5359Q1ZH | RMC M-30 QTY.4 CUM @6300/- PER CUM | 29736 | 25200 | 2268 | 2268
2024-09-02 | Steel Centre- Shanti Sadan | SC-GS-343/24-25 | 2024-09-02 | 27AAAFS5359Q1ZH | RMC M-30 QTY.12.500 CUM @6300/- PER CUM | 92925 | 78750 | 7087.5 | 7087.5
2024-09-20 | Steel Centre- Shanti Sadan | SC-GS-397/24-25 | 2024-09-20 | 27AAAFS5359Q1ZH | M-30 QTY.4 CUM @6300/- | 29736 | 25200 | 2268 | 2268
2024-10-01 | Jai Durga Transport-Shanti Sadan | 4776 | 2024-10-01 |  | WATER SUPPLY | 15600 | [8 empty] | 15600
2024-04-23 | Omkar Santosh Velhal - Shanti Sadan | OV:02-702-24/25 | 2024-04-23 |  | BEING INV. NO. 02-702-24/25 SERVICE CHARGES CAMERA FITTING, SETTING, SERVICE CHARGES NVR, BASE, TREE IP CONFIGURATION, SERVICE CHARGES 12 MONTHS SERVICE SUPPORT | 10200 | 10200
2024-05-20 | Shivprerana Maharashtra Rajya Mathadi Transport & G |  |  |  | MATHADI PAVTI NO. 887 | 19125 | 19125
2024-06-28 | Water Pump Hire Service - Shanti Sadan |  |  |  | WATER PUMP SERVICE BILL NO. 1067 | 7500 | 7500
2024-11-09 | Shivprerana Maharashtra Rajya Mathadi Transport & G |  |  |  | MATHADI PAVTI NO. 1233 | 6975 | 6975
2024-12-07 | K.V. Steel Traders LLP | GST-179/24-25 | 2024-12-07 | 27AARFK0919K1ZW | BEING STEEL PURCHASE | 601955 | 510131 | 45911.79 | 45911.79 | 0.42
2024-12-12 | RSS Infra Co - Shanti Sadan | RSS/DEC24-25/105 | 2024-12-12 | 27EQDPS3153M1ZC | RMC M-30 | 29400 | 24915.24 | 2242.37 | 2242.37 | 0.02
2024-12-15 | RSS Infra Co - Shanti Sadan | RSS/DEC/24-24/114 | 2024-12-15 | 27EQDPS3153M1ZC | PUMPING CHARGES | 23600 | 20000 | 1800 | 1800
2024-12-24 | K.V. Steel Traders LLP | GST-179/24-25 | 2024-12-07 | 27AARFK0919K1ZW | BEING STEEL PURCHASE | 660484 | 559732 | 50375.88 | 50375.88 | 0.24
2024-12-08 | Shivprerana Maharashtra Rajya Mathadi Transport |  |  |  | MATHADI PAVTI NO. 1254 | 4500 | 4500
2024-12-11 | Uday Radhakrishna Sinari |  |  |  | CONTRACT FOR LABOUR MANAGEMENT CHARGES INV. NO. 01 | 1075000 | 1075000
2024-12-13 | S.S. Construction - Shanti Sadan |  |  | 27BMSPS2570J3Z9 | CIVIL WORK OF RESIDENTIAL BUILDING ON LABOUR BASIS | 944000 | 800000 | 72000 | 72000
2024-12-27 | Haroon Hasan Rindani - Shanti Sadan |  |  |  | EXCAVATION WORK SHANTI SADAN CHSL, DADABHAI ROAD, NAVPADA, VILE PARLE (W) | 60000 | 60000
| Urban India |  |  |  |  | 14900000
17/-Dec-24 | Vikram Steel |  |  |  |  | 2683763
| Grand Total |  |  |  |  | 29322857.86 | 10082387.11 | 800971.75 | 800971.75 | 4.25 | 671.88 | 94.06 | 94.06 | 600 | 53300

## Professional Cost
Date | Particulars | GSTIN/UIN | Gross Total | Professional Charges - Shanti Sadan | CGST @ 9% - Shanti Sadan | SGST @9% - Shanti Sadan | CGST @2.5% - Shanti Sadan | SGST @2.5% - Shanti Sadan | IGST @18% Shanti Sadan
2023-11-17 | Sincrono Solutions Pvt Ltd | 27AAZCS2917G1ZT | 32450 | 27500 | 2475 | 2475
2023-12-14 | Vikas Yadav - Shanti Sadan |  | 6750 | 6750
2024-01-15 | J K ADVERTISING | 27AUDPD2428A3ZA | 19530 | 18600 |  |  | 465 | 465
2024-02-03 | Advance Geo Tech Solutions-Shanti Sadan |  | 86140 | 73000 | 6570 | 6570
2024-03-11 | Rajan Pillai - Shanti Sadan |  | 12500 | 12500
2024-04-01 | Sincrono Solutions Pvt Ltd | 27AAZCS2917G1ZT | 32450 | 27500 | 2475 | 2475
2024-04-30 | Kalpesh Kaner - Shanti Sadan |  | 20000 | 20000
2024-05-31 | Kalpesh Kaner - Shanti Sadan |  | 20000 | 20000
2024-06-11 | Ambest Media (Prop. Sachin Kanji Chheda) Shanti | 27AAAPC9435D1Z2 | 206500 | 175000 | 15750 | 15750
2024-06-12 | Shyam Prajapati & Associates |  | 3500 | 3500
2024-06-25 | Vastukala Consultants (I) Pvt Ltd-Shanti | 27AADCV4303R1ZX | 17700 | 15000 | 1350 | 1350
2024-06-30 | Kalpesh Kaner - Shanti Sadan |  | 20000 | 20000
2024-07-31 | Kalpesh Kaner - Shanti Sadan |  | 20000 | 20000
2024-08-31 | Kalpesh Kaner - Shanti Sadan |  | 20000 | 20000
2024-09-03 | Padiyar & Co - Shanti Sadan |  | 17250 | 17250
2024-09-20 | Rekha Nair & Associates |  | 30000 | 30000
2024-09-30 | Kalpesh Kaner - Shanti Sadan |  | 20000 | 20000
2024-09-30 | Padiyar & Co - Shanti Sadan |  | 20000 | 20000
2024-10-03 | Vastukala Consultants (I) Pvt Ltd-Shanti | 27AADCV4303R1ZX | 41300 | 35000 | 3150 | 3150
2024-10-08 | Nagulapati & Co - Shanti Sadan | 27AACFN8756A1ZA | 31152 | 26400 | 2376 | 2376
2024-10-14 | Cubictree Technology Solutions Pvt Ltd | 27AADCC8997J1ZW | 5900 | 5000 | 450 | 450
2024-10-17 | LEI Register India Pvt Ltd | 19AADCL9323M1Z0 | 15043.8 | 12748.98 |  |  |  |  | 2294.82
2024-10-31 | Kalpesh Kaner - Shanti Sadan |  | 20000 | 20000
2024-11-14 | Mukesh Solani - Shanti Sadan |  | 30000 | 30000
2024-11-30 | Kalpesh Kaner - Shanti Sadan |  | 20000 | 20000
| RERA Registration |  | 61250.8
| Survey Expenses |  | 10000
2024-06-01 | Global Lab - Shanti Sadan | 27AAICG1385R1ZV | 7375 | 6250 | 562.5 | 562.5
2024-06-23 | F.M. Testing Lab - Shanti Sadan | 27AOMPP6000R1ZC | 1416 | 1200 | 108 | 108
2024-07-21 | F.M. Testing Lab - Shanti Sadan | 27AOMPP6000R1ZC | 4602 | 3900 | 351 | 351
2024-08-25 | F.M. Testing Lab - Shanti Sadan | 27AOMPP6000R1ZC | 2124 | 1800 | 162 | 162
2024-09-22 | F.M. Testing Lab - Shanti Sadan | 27AOMPP6000R1ZC | 1770 | 1500 | 135 | 135
2024-10-20 | F.M. Testing Lab - Shanti Sadan | 27AOMPP6000R1ZC | 708 | 600 | 54 | 54
2024-12-22 | F.M. Testing Lab - Shanti Sadan | 27AOMPP6000R1ZC | 2478 | 2100 | 189 | 189
2024-12-01 | Rekha Nair & Associates |  | 10000 | 10000
2024-12-04 | New Wave Solutions |  | 7350 | 7350
2024-12-07 | Vastukala Consultants (I) Pvt Ltd-Shanti |  | 47200 | 40000 | 3600 | 3600
2024-12-09 | Facilis (Architecture & Interior)-Shanti Sadan |  | 236000 | 200000 | 18000 | 18000
2024-12-31 | Kalpesh Kaner - Shanti Sadan |  | 20000 | 20000
0
TOTAL |  |  | 1180439.6 | 990448.98 | 57757.5 | 57757.5 | 465 | 465 | 2294.82

## Admin Cost
Date | Particulars | Voucher Ref. No. | Voucher Ref. Date | GSTIN/UIN | Gross Total | Purchase Net GST @18% Shanti Sadan | Transportation - Shanti Sadan | CGST @ 9% - Shanti Sadan | SGST @9% - Shanti Sadan | Round Off | Marketing Exp.
2024-04-29 | P5 Industries - Shanti Sadan | P5/24-25/314 | 2024-04-29 | 27ASRPB3828L1ZB | 42780 | 35654.15 | 600 | 3262.87 | 3262.87 | 0.11
2024-05-01 | Pro Talk System - Shanti Sadan |  |  | 27BDEPC2755A1Z4 | 33600 | 33600
2024-06-01 | Pro Talk System - Shanti Sadan |  |  | 27BDEPC2755A1Z4 | 32516 | 32516
2024-07-01 | Pro Talk System - Shanti Sadan |  |  | 27BDEPC2755A1Z4 | 33600 | 33600
2024-08-01 | Pro Talk System - Shanti Sadan |  |  | 27BDEPC2755A1Z4 | 32000 | 32000
2024-09-01 | Pro Talk System - Shanti Sadan |  |  | 27BDEPC2755A1Z4 | 32000 | 32000
2024-10-01 | Pro Talk System - Shanti Sadan |  |  | 27BDEPC2755A1Z4 | 48000 | 48000
2024-11-01 | Pro Talk System - Shanti Sadan |  |  | 27BDEPC2755A1Z4 | 48000 | 48000
| Bank Charges |  |  |  | 1238.6
| BG Commission Charges - Shanti Sadan |  |  |  | 9912
| BMC Property Tax |  |  |  | 408322
| Computer Exp |  |  |  | 13192.38
| Diwali Bonus |  |  |  | 122000
| Electricity Charges - Office |  |  |  | 34310
| Electricity Charges - Site |  |  |  | 108063
| Franking Challan |  |  |  | 3700
| Office Rent |  |  |  | 520000
| Salary & Wages FY 2024 - 25 |  |  |  | 1169200
| Site Insurances |  |  |  | 9016
| ROC Fees - |  |  |  | 2600
2024-04-23 | Velhal Telecom - Shanti Sadan | GST/24-25/VT:005 | 2024-04-23 | 27ABWPV3284E1ZY | 88069.6 | 74635 | 6717.15 | 6717.15 | 0.3
2024-12-01 | Pro Talk System - Shanti Sadan | 27BDEPC2755A1Z4 |  |  | 48000 | 48000
| Bank Charges |  |  |  | 531
| Electricity Charges - Office |  |  |  | 3880
| Electricity Charges - Site |  |  |  | 29300
| Franking Challan |  |  |  | 10900
| Office Rent |  |  |  | 65000
| Salary & Wages FY 2024 - 25 |  |  |  | 152400
| SBI Car Policy |  |  |  | 199731
| SBI Loan Process Charges |  |  |  | 1560196
| Stamp Duty & registration |  |  |  | 661500
TOTAL |  |  |  |  | 5523557.58 | 418005.15 | 7317.15 | 9980.02 | 3263.17 | 0.11 | 0

## MArketing Cost
Date | Particulars | Voucher Type | Voucher No. | Voucher Ref. No. | Voucher Ref. Date | GSTIN/UIN | Gross Total | Transportation - Shanti Sadan | CGST @ 9% - Shanti Sadan | SGST @9% - Shanti Sadan | Round Off | Marketing Exp.
2024-07-11 | Signage AD. India-Shanti Sadan | Journal | 604 |  |  | 27ADVPD2012R1Z6 | 63720 |  | 4860 | 4860 |  | 54000
2024-07-12 | Signage AD. India-Shanti Sadan | Journal | 602 |  |  | 27ADVPD2012R1Z6 | 66080 | 2000 | 5040 | 5040 |  | 54000
2024-07-13 | Signage AD. India-Shanti Sadan | Journal | 603 |  |  | 27ADVPD2012R1Z6 | 71036 | 2000 | 5418 | 5418 |  | 58200
| Grand Total | [5 empty] | 200836 | 4000 | 15318 | 15318 | 0 | 166200

## Interest
Sr. No. | Particulars | Amount | Amount in ` Cr. | Amount | Amount in ` Cr. | Balance | Balance in Cr.
| September secured interest |  |  |  |  | 0 | 0
| October |  |  |  |  | 0 | 0
| November |  |  |  |  | 0 | 0
| December |  |  |  |  | 0 | 0
| Jan to March |  |  |  |  | 0 | 0
| April to June |  |  |  |  | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0

## Construction Area of Sale Build
Summary of Cost of Construction
Plinth Area Calculation
Sr. No | Floor Nos. | Total Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | % of work completed | Actual Expenditure till date in `
1 | Excavation |  |  |  | 9439501 | 100% | 9439501
2 | Ground Floor | 2583.7906 | 2583.7906 | 3000 | 7751372 | 50% | 3875686
3 | 1st Floor | 2583.7906 | 2583.7906 | 3000 | 7751372 | 50% | 3875686
4 | 2nd Floor | 2583.7906 | 2583.7906 | 3000 | 7751372 | 40% | 3100548.8
5 | 3rd Floor | 2583.7906 |  | 3000 | 7751372 | 0% | 0
6 | 4th Floor | 2583.7906 |  | 3000 | 7751372 | 0% | 0
7 | 5th Floor | 2583.7906 |  | 3000 | 7751372 | 0% | 0
8 | 6th Floor | 2583.7906 |  | 3000 | 7751372 | 0% | 0
9 | 7th Floor | 2660.8608 |  | 3000 | 7982582 | 0% | 0
10 | 8th Floor | 2583.7906 |  | 3000 | 7751372 | 0% | 0
11 | 9th Floor | 2583.7906 |  | 3000 | 7751372 | 0% | 0
12 | 10th Floor | 2583.7906 |  | 3000 | 7751372 | 0% | 0
13 | 11th Floor | 2583.7906 |  | 3000 | 7751372 | 0% | 0
14 | Terrace / OHT | 382.4449 |  | 3000 | 1147335 | 0% | 0
Sub - Total |  | 31465.0019 | 7751.3717 |  | 103834510 | 19.54% | 20291421.8
15 | Parking | 32 |  | 600000 | 19200000 | 0% | 0
Total |  |  |  |  | 123034510 | 16.49% | 20291421.8