## Final Summary
Project expenses | Estimated Cost as per Cost Vetting | Incurred Cost as per Bill till 31.12.2024 | Incurred Cost as per CA till 31.12.2024 | Incurred Cost as per Bill till 30.09.2024 | Incurred Cost as per CA till 30.09.2024 | Difference between the Bills & CA | Difference between both the Bills | Difference between both CA | Remark
Land Cost | 0.81 | 0.81478 | 0.8146 | 0.81478 | 0.8146 | 0.00018 | 0 | 0
Rent Cost | 3.95 | 1.371 | 1.37 | 1.1335 | 1.1335 | 0.00098 | 0.23745 | 0.23647
Construction Cost of Sale Building | 15.44 | 9.1399 | 2.45 | 1.2882 | 1.5105 | 6.6899 | 7.8517 | 0.93948
TDR Cost | 3.42 | 2.8412 | 2.8412 | 2.8412 | 2.8412 | 0 | 0 | 0
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 13.63 | 3.0123 | 3.04 | 2.991 | 2.991 | -0.027739 | 0.021295 | 0.049033
Architect Cost, RCC & other Professional fees | 0.77 | 0.75132 | 0.47 | 0.72139 | 1.1127 | 0.28132 | 0.029931 | 0.037257
On- site expenditure for development / Advance for Project / Administrative Cost / Fixed Assets | 0.93 | 0.63803 | 0.58 | 0.63144 |  | 0.058028 | 0.0065867 |  | .
Marketing Expenses | 1.19 | 0.10225 | 0.1 | 0.00225 |  | 0.00225 | 0.1
Interest Cost | 4 | 0 | 0 | 0 | 0.28619 | 0 | 0 | -0.28619
Contingency Cost | 0.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost | 44.6 | 18.6707 | 11.6658 | 10.4238 | 10.6898 | 7.0049 | 8.247 | 0.97604
|  | 25.9293 | 26.16%
Particulars | Revised Estimated Cost (in Cr.) | 31.12.2024 as per Bill Tally (inclusive of GST) | Cost incurred as %age total cost of that Component | Cost incurred as %age of cost incurred as on 31.12.2024
Land Cost | 0.81 | 0.81478 | 100.6% | 1.827%
Rent Cost | 3.95 | 1.371 | 34.71% | 3.074%
Construction Cost of Sale Building | 15.44 | 9.1399 | 59.2% | 20.49%
TDR Cost | 3.42 | 2.8412 | 83.08% | 6.37%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 13.63 | 3.0123 | 22.1% | 6.754%
Architect Cost, RCC & other Professional fees | 0.77 | 0.75132 | 97.57% | 1.685%
On- site expenditure for development / Advance for Project / Administrative Cost / Fixed Assets | 0.93 | 0.63803 | 68.61% | 1.431%
Marketing Expenses | 1.19 | 0.10225 | 8.592% | 0.2293%
Interest Cost | 4 | 0 | 0% | 0%
Contingency Cost | 0.46 | 0 | 0% | 0%
Total | 44.6 | 18.6707 | 41.86% | 41.86%
Pariculars | 31.12.2024 as per Bill Tally (inclusive of GST) | 30.09.2024 as per Bill Tally (inclusive of GST) | Difference b/w bills of 30.09.2024 & 31.12.2024 | Difference of Cost incurred as %age of cost incurred as on 30.09.2024 & 31.12.2024
Land Cost | 0.81478 | 0.81478 | 0 | 0%
Rent Cost | 1.371 | 1.1335 | 0.24 | 1.285%
Construction Cost of Sale Building | 9.1399 | 1.2882 | 7.85 | 42.04%
TDR Cost | 2.8412 | 2.8412 | 0 | 0%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 3.0123 | 2.991 | 0.02 | 0.1071%
Architect Cost, RCC & other Professional fees | 0.75132 | 0.72139 | 0.03 | 0.1607%
On- site expenditure for development / Advance for Project / Administrative Cost / Fixed Assets | 0.63803 | 0.63144 | 0.01 | 0.05356%
Marketing Expenses | 0.10225 | 0.00225 | 0.1 | 0.5356%
Interest Cost | 0 | 0 | 0 | 0%
Contingency Cost | 0 | 0 | 0 | 0%
Total | 18.6707 | 10.4238 | 8.25 | 44.19%

## Summary Sheet
Sr. No. | Particulars | Incurred Cost in ` till 31.12.2024 | Incurred Cost in ` Cr. Till 31.12.2024 | Incurred Cost in ` till 30.09.2024 | Incurred Cost in ` Cr. Till 30.09.2024 | Balance in ` | Balance in ` Cr.
1 | Land Cost | 8147800 | 0.81478 | 8147800 | 0.81478 | 0 | 0
2 | Rent Cost | 13709800 | 1.371 | 11335330 | 1.1335 | 2374470 | 0.23745
3 | Construction Cost | 91399039 | 9.1399 | 12881839 | 1.2882 | 78517200 | 7.8517
4 | TDR Cost | 28412136 | 2.8412 | 28412136 | 2.8412 | 0 | 0
5 | Approval Cost & Stamp Duty | 30122614 | 3.0123 | 29909667 | 2.991 | 212947 | 0.021295
6 | Professional Cost | 7513222 | 0.75132 | 7213908 | 0.72139 | 299314 | 0.029931
7 | Admin Cost | 6380275 | 0.63803 | 6314408 | 0.63144 | 65867 | 0.0065867
8 | Marketing Cost | 1022500 | 0.10225 | 22500 | 0.00225 | 1000000 | 0.1
9 | Interest Cost | 0 | 0 | 0 | 0 | 0 | 0
10 | Contingency Cost | 0 | 0 | 0 | 0 | 0 | 0
| Total | 186707386 | 18.6707 | 104237588 | 10.4238 | 82469798 | 8.247
|  | 178559586 | 17.856 | 96089788 | 9.609 | 82469798 | 8.247
40000000
40000000

## Land, Stamp Duty cost
Stamp Duty & Registration Fees
Sr. No. | Agreement Name | Date | Particulars | Amount | Incurred Amount
1 | Development Agreement | 2023-04-19 | Stamp Duty | 8116000 | 8116000
2 |  |  | Reg. Fees | 30000 | 30000
3 |  |  |  | 1800 | 1800
| TOTAL |  |  | 8147800 | 8147800
| Particulars | Rs. | Heading
| Stampduty & Registration Charges (Tdr) | 819507 | TDR
| Scrutiny Fees for TDR | 34065 | TDR
| Purchase of TDR-Aneesh | 27203564 | TDR
| Brokerage on Purchase of TDR | 355000 | TDR
| Total | 28412136
| Particulars | Rs. | Heading
| Compensation to Members ( Aneesh) | 5130600 | Corpus
| Society Corpus | 300000 | Corpus
| Shifting & Reshifting Charges ( Aneesh) | 350000 | Rent
| Alternate Accomodation( Aneesh) | 4617540 | Rent
| Alternate Accomodation( Aneesh) | 937190 | Rent
| Alternate Accomodation( Aneesh) | 2374470 | Rent
| TOTAL | 13709800

## Approval Cost
Particulars | Rs. | Heading
Stampduty & Registration Charges (BMC | 1235600 | Approval
Permission & Approval | 27405310 | Approval
Permission & Approval | 1268757 | Approval
BMC Challan | 195247
Airport NOC | 17700
Total | 30122614

## Construction Cost
Particulars | Rs. | Heading
Titan Ceramic and Cemet Centre | 20572 | Construction
Classic Infrastructuer | 2461527.2 | Construction
J.K Enterprise | 5275525.62 | Construction
Skyway Rmc Plants Pvt Ltd | 4114753.2 | Construction
Bharat Steel | 4720 | Construction
Crack Filling Work ( Asset) | 35000 | Construction
Electricity Charges (Aneesh Site) | 15327 | Construction
Exavation Work ( WIP) | 31000 | Construction
On Site Labour Charges( AA) | 4800 | Construction
Purchase of Meterials (WIP) | 913693.5 | Construction
Plumbing Work ( WIP) | 4920 | Construction
Work Contract | 5310000 | Construction
Zaar Line | 9605200
Zaar Line | 12036000 | PI dated 30.12.2024
Zaar Line | 15753000 | PI dated 23.12.2024
Zaar Line | 17405000 | PI dated 16.12.2024
Zaar Line | 18408000 | PI dated 09.12.2024
Total | 91399038.52

## Professional Cost
Particulars | Rs. | Heading
Vastukala Consultants (I) Pvt Ltd | 59000 | Professional
Rajan Pillai | 36500 | Professional
Architects/Engineers Fees | 712675 | Professional
Agami EngineeringConsultants | 62675 | Professional
Consultancy Charges | 153790 | Professional
Professional / Legal Expenses | 3312600 | Professional
Architects/Engineers Fees | 200000 | Professional
Professional / Legal Expenses | 2676668 | Professional
Architects/Engineers Fees | 236000 | Professional
Consultancy Charges | 53100
Shyam Prajapati | 7500
Chopra & Associates | 2714
Total | 7513222

## Admin Cost
Particulars | Rs. | Heading
NeevConstruction | 416345 | Admin overheads
Bettle industries Pvt Ltd | 31624 | Admin overheads
A q Jilani | 98100 | Admin overheads
Kaushik Pitwa | 249465 | Admin overheads
Tejal Plumbing Work | 4920 | Admin overheads
Sudha.R | 31000 | Admin overheads
Saleem Hashmi | 35000 | Admin overheads
Pratik Electric | 10355 | Admin overheads
Megha Enterprises | 1029197 | Admin overheads
Mahavir Furnituer | 2832 | Admin overheads
Lotus Trading & Co | 56551 | Admin overheads
Lotus Borewell & Pumps | 69573 | Admin overheads
Lock & Key | 8300 | Admin overheads
Lawgical Consultants | 29500 | Admin overheads
Repairs & Maintenanace Aneesh Site | 2550 | Admin overheads
Ground Water Exploration Service | 11000 | Admin overheads
BILIMORIA MEHTA & COMPANY | 107380 | Admin overheads
Baltic India Private Limited | 15222 | Admin overheads
Alpha Enterprises | 850 | Admin overheads
Water Testing | 17490 | Admin overheads
Transportation Charges | 2000 | Admin overheads
Electricity Work | 57996
Fees & Royalities | 547003
Repairs & Maintenanace Aneesh Site | 4130
Stamp Duty & Reg. Charges | 928300
Documentation charges loan sbi | 25960
Processing Fees | 2124000
Security Charges | 13000
Insurance Charges | 341610
Postage and Courier | 600
Printing and Stationary | 7155
Inspection Charges loan SBI | 35400
Electricity Work | 52837
Vouncher | 300
Stamppaper charges | 200
Stamppaper charges | 500
Vocher | 130
Water Charges | 11900
Total | 6380275

## MArketing Cost
Particulars | Rs. | Heading
Advertising Expenses | 22500 | Ads
Aurum Analytica Pvt Ltd | 1000000
Total | 1022500

## Interest
Sr. No. | Particulars | Amount | Amount in ` Cr. | Amount | Amount in ` Cr. | Balance | Balance in Cr.
| September secured interest | 0 | 0 |  |  | 0 | 0
| October |  |  |  |  | 0 | 0
| November |  |  |  |  | 0 | 0
| December |  |  |  |  | 0 | 0
| Jan to March |  |  |  |  | 0 | 0
| April to June |  |  |  |  | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0

## Construction Area of Sale Build
Summary of Cost of Construction
Plinth Area Calculation
Sr. No | Floor Nos. | Total Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | Percentage of work completed | Actual Expenditure till date in `
1 | Excavation |  |  |  | 12129600 | 100% | 12129600
2 | Part Basement | 249.09 | 249.09 | 35000 | 8718150 | 50% | 4359075
3 | Ground Floor | 297.62 | 297.62 | 35000 | 10416700 | 50% | 5208350
4 | 1st Floor | 297.62 | 297.62 | 35000 | 10416700 | 50% | 5208350
5 | 2nd Floor | 300.92 | 300.92 | 35000 | 10532200 | 50% | 5266100
6 | 3rd Floor | 310.74 | 310.74 | 35000 | 10875900 | 50% | 5437950
7 | 4th Floor | 310.74 | 310.74 | 35000 | 10875900 | 50% | 5437950
8 | 5th Floor | 327.92 | 327.92 | 35000 | 11477200 | 50% | 5738600
9 | 6th Floor | 327.92 | 327.92 | 35000 | 11477200 | 50% | 5738600
10 | 7th Floor | 327.92 |  | 35000 | 11477200 | 0% | 0
11 | 8th Floor | 327.92 |  | 35000 | 11477200 | 0% | 0
12 | 9th Floor | 327.92 |  | 35000 | 11477200 | 0% | 0
13 | Terrace / OHT | 59.27 |  | 35000 | 2074450 | 0% | 0
Total |  | 3465.6 | 2422.57 |  | 133425600 | 40.87% | 54524575
| Parking | 42 |  | 500000 | 21000000 | 0 | 0
Total |  | 6426.49 | 4298.43 |  | 154425600 | 35.31% | 54524575