## Final Summary
Project expenses | Estimated Cost as per Cost Vetting | Incurred Cost as per Bill till 31.12.2024 | Incurred Cost as per CA till 31.12.2024 | Incurred Cost as per Bill till 30.09.2024 | Incurred Cost as per CA till 30.09.2024 | Difference between the Bills & CA | Difference between both the Bills | Difference between both CA | Remark
Land Cost | 1.56 | 1.5647 | 1.56 | 1.5647 | 1.56 | 0.004742 | 0 | 0
Rent Cost | 14.71 | 12.0705 | 12.07 | 11.3201 | 11.32 | 0.0005 | 0.75037 | 0.75
Construction Cost of Rehab cum Sale Building | 57.23 | 44.4215 | 44.6 | 32.0848 | 33.57 | -0.17852 | 12.3366 | 11.03
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 27.73 | 28.2003 | 28.2 | 28.2003 | 28.2 | 0.0003 | 5e-05 | 0
Architect Cost, RCC & other Professional fees | 1.14 | 0.97005 | 0.97 | 0.87294 | 0.87 | 5e-05 | 0.097115 | 0.1
Administrative Expenses | 2.86 | 2.18 | 2.18 | 1.7459 | 1.71 | 2e-05 | 0.43415 | 0.47
Marketing Expences | 2.75 | 2.27 | 2.27 | 1.3702 | 1.37 | 1e-05 | 0.89986 | 0.9
Interest Cost | 8.49 | 1.87 | 1.87 | 1.11 | 1.11 | 5e-05 | 0.76005 | 0.76
Total Cost | 116.47 | 93.5472 | 93.72 | 78.2689 | 79.71 | -0.17285 | 15.2782 | 14.01 | DSRA Amount is not accounted in LIE Report
|  | 22.9228 | 22.75 | 80.47%
Particulars | Revised Estimated Cost (in Cr.) | Incurred Cost as per Bill till 31.12.2024 | Cost incurred as %age total cost of that Component | Cost incurred as %age of cost incurred as 31.12.2024
Land Cost | 1.56 | 1.5647 | 100.3% | 1.343%
Rent Cost | 14.71 | 12.0705 | 82.06% | 10.36%
Construction Cost of Sale Building | 57.23 | 44.4215 | 77.62% | 38.14%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 27.73 | 28.2003 | 101.7% | 24.21%
Architect Cost, RCC & other Professional fees | 1.14 | 0.97005 | 85.09% | 0.8329%
Administrative Expenses | 2.86 | 2.18 | 76.22% | 1.872%
Marketing Expences | 2.75 | 2.27 | 82.55% | 1.949%
Interest Cost | 8.49 | 1.87 | 22.03% | 1.606%
Total | 116.47 | 93.5471 | 80.32% | 80.32%
Pariculars | 31.12.2024 as per bill | 30.09.2024 as per bill | Difference b/w bills of 30.09.2024 & 31.12.2024 | Difference of Cost incurred as %age of cost incurred as on 30.09.2024 & 31.12.2024
Land Cost | 1.5647 | 1.5647 | 0 | 0%
Rent Cost | 12.0705 | 11.3201 | 0.75 | 0.8017%
Construction Cost of Sale Building | 44.4215 | 32.0848 | 12.34 | 13.19%
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 28.2003 | 28.2003 | 0 | 0%
Architect Cost, RCC & other Professional fees | 0.97005 | 0.87294 | 0.1 | 0.1069%
Administrative Expenses | 2.18 | 1.7459 | 0.43 | 0.4597%
Marketing Expences | 2.27 | 1.3702 | 0.9 | 0.9621%
Interest Cost | 1.87 | 1.11 | 0.76 | 0.8124%
Total | 93.5472 | 78.2689 | 15.28 | 16.33%

## Summary Sheet
Sr. No. | Particulars | Incurred Cost in ` till 31.12.2024 | Incurred Cost in ` Cr. Till 31.12.2024 | Incurred Cost in ` till 30.09.2024 | Incurred Cost in ` Cr. Till 30.09.2024 | Balance | Balance in Cr.
1 | Land Cost | 15647420 | 1.5647 | 15647420 | 1.5647 | 0 | 0
2 | Rent Cost | 120705000 | 12.0705 | 113201250 | 11.3201 | 7503750 | 0.75038
4 | Construction Cost of Sale Building | 444214826.8 | 44.4215 | 320848447 | 32.0848 | 123366379.8 | 12.3366
5 | Approval Cost & Stamp Duty | 282003000 | 28.2003 | 282002500 | 28.2003 | 500 | 5e-05
6 | Professional Cost | 9700500 | 0.97005 | 8729352 | 0.87294 | 971148 | 0.097115
7 | Admin Cost | 21800200 | 2.18 | 17458706 | 1.7459 | 4341494 | 0.43415
8 | Marketing Cost | 22700100 | 2.27 | 13701550 | 1.3702 | 8998550 | 0.89985
9 | Interest Cost | 18700500 | 1.87 | 11100000 | 1.11 | 7600500 | 0.76005
| Total | 935471546.8 | 93.5472 | 782689225 | 78.2689 | 152782321.8 | 15.2782
|  | 901123626.8 |  |  |  |  | 14.5182
84900000
66199500
|  | 901123626.8 | 90.1124 | 755941805 | 75.5942 | 145181821.8 | 14.5182

## Land, Stamp Duty and rent cost
Stamp Duty & Registration Fees
Sr. No. | Agreement Name | Date | Particulars | Amount | Incurred Amount |  | August 21 - July22 | 12
1 | Development Agreement | 2019-03-27 | Stamp Duty | 14497980 | 14497980 |  | August 22 - June 23 | 10
2 |  |  | Reg. Fees | 30000 | 30000 |  | July 23 - August 24 | 14
3 |  |  |  | 2000 | 2000 |  | Sept 24 - July 25 | 11
4 | Rectification Cum Supplementary Deed | 2022-04-29 | Stamp Duty | 1086200 | 1086200 |  | August 25 - June 26 | 11
5 |  |  | Reg. Fees | 30000 | 30000
6 | Special Power of Attorney | 2021-03-27 | Stamp Duty | 500 | 500
7 |  |  | Reg. Fees | 740 | 740 |  | July 26 - Sept 26 | 3
| TOTAL |  |  | 15647420 | 15647420
Sr. No. | Particulars | Commercial Shops | Commercial Offices | Residental Flat | Total | Units
1 | No. of Tenants | 4 | 9 | 48 | 61 | Nos.
2 | Rent per tenant per month for April 23 to Feb 24 | 110000 | 50000 | 40000 |  | Rupees
3 | Rent per year for April 23 to Feb 24 | 4840000 | 4950000 | 21120000 | 30910000 | Rupees
4 | Rent per tenants per month for March 24 to Jan 25 | 121000 | 55000 | 44000 |  | Rupees
5 | Rent per year for March 24 to Jan 25 | 5324000 | 5445000 | 23232000 | 34001000 | Rupees
6 | Rent per tenants per month for Feb 25 to March 25 | 133100 | 60500 | 0 |  | Rupees
7 | Rent per year for Feb 25 to March 25 | 1064800 | 1089000 | 0 | 2153800 | Rupees
8 | Rent per tenants per month for Feb 25 to Dec 25 | 0 | 0 | 48400 |  | Rupees
9 | Rent per year for Feb 25 to Dec 25 | 0 | 0 | 25555200 | 25555200 | Rupees
10 | Rent per tenants per month for Jan 26 to Mar 26 | 0 | 0 | 53240 |  | Rupees
11 | Rent per year for Jan 26 to Mar 26 | 0 | 0 | 7666560 | 7666560 | Rupees
12 | Corpus Fund per Tenant | 800000 | 700000 | 700000 |  | Rupees
13 | Total Corpus Fund | 3200000 | 6300000 | 33600000 | 43100000 | Rupees
14 | Shifting Charges per Tenant | 15000 | 15000 | 15000 |  | Rupees
15 | Total Shifting Charges | 60000 | 135000 | 720000 | 915000 | Rupees
16 | Brokerage Cost | 440000 | 450000 | 1920000 | 2810000 | Rupees
17 | Total Rent Cost (3 + 5 + 7 + 9 + 11 + 13 + 15 + 16) | 14928800 | 18369000 | 113813760 | 147111560 | Rupees

## Sheetal Ekta_Tax Invoices
M/s. DGS Township Private Limited
Sheetal Ekta
Sr. No. | Vendor Name | Customer Name | Invoice Date | Invoice Number | Invoice Amount | Project Name | Description of Material
1 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2023-08-13 | ASC302/23-24 | 1765445 | Sheetal Ekta | T.M.T. Bars 10mm, 12mm, 20mm, 32mm,M.S Wire
2 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2023-09-23 | ASC409/23-24 | 1752115 | Sheetal Ekta | T.M.T. Bars 08mm, 12mm,16mm, 20mm, 32mm, TCS on Sales
3 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2023-10-19 | ASC482/23-24 | 1806562 | Sheetal Ekta | T.M.T. Bars 08mm, 10mm,12mm, 16mm, 20mm, 25mm, TCS on Sales
4 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-02-16 | ASC991/23-24 | 1647889 | Sheetal Ekta | T.M.T. Bars 25mm, 32mm
5 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-02-10 | ASC963/23-24 | 144727 | Sheetal Ekta | M.S Pipe
6 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-01-11 | ASC828/23-24 | 195314 | Sheetal Ekta | M.S Plate
7 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-03-27 | PI/ASC1227/23-24 | 47241294 | Sheetal Ekta | 08mm, 10mm, 12mm, 16mm, 20mm, 25mm & 32mm TMT Bars
8 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-02-27 | ASC1046/23-24 | 1551254 | Sheetal Ekta | T.M.T. Bars 08mm, 10mm,16mm, 20mm,
9 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-01-11 | ASC826/23-24 | 121490 | Sheetal Ekta | M.S Structure,M.S Pipe
10 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-02-07 | ASC951/23-24 | 1777556 | Sheetal Ekta | T.M.T. Bars 08mm, 10mm,12mm, 16mm, 20mm, 25mm
11 | B. Mittal & Co. | DGS Township Pvt Ltd | 2023-11-23 | BM23240206 | 1788957 | Sheetal Ekta | TMT Rebar 08mm,10mm,25mm,32mm,MS Binding wire
12 | B. Mittal & Co. | DGS Township Pvt Ltd | 2023-12-25 | BM23240248 | 1820517 | Sheetal Ekta | TMT Rebar 08mm,12mm,16mm,25mm,32mm,MS Binding wire
13 | B. Mittal & Co. | DGS Township Pvt Ltd | 2024-03-07 | BM23240344 | 1745973 | Sheetal Ekta | TMT Rebar 16mm,20mm,25mm,32mm
14 | B. Mittal & Co. | DGS Township Pvt Ltd | 2023-11-01 | BM23240178 | 1928057 | Sheetal Ekta | TMT Rebar 08mm,12mm,16mm,20mm,25mm,32mm
15 | B. Mittal & Co. | DGS Township Pvt Ltd | 2023-11-09 | BM23240188 | 1860010 | Sheetal Ekta | TMT Rebar 08mm,12mm,16mm,20mm,25mm,32mm
16 | Fine Steel corporation | DGS Township Pvt Ltd | 2023-07-01 | FSC/23-24/25 | 1731227 | Sheetal Ekta | Thermex,TMT Bar 08mm,10mm,12mm,20mm
17 | Fine Steel corporation | DGS Township Pvt Ltd | 2023-06-21 | FSC/23-24/20 | 1819704 | Sheetal Ekta | Thermex,TMT Bar 25mm,G.M.S Wire
18 | Fine Steel corporation | DGS Township Pvt Ltd | 2023-06-24 | FSC/23-24/21 | 1776767 | Sheetal Ekta | Thermex,TMT Bar 25mm
19 | Fine Steel corporation | DGS Township Pvt Ltd | 2023-07-07 | FSC/23-24/27 | 1685839 | Sheetal Ekta | Thermex,TMT Bar 08mm,12mm,32mm
20 | Fine Steel corporation | DGS Township Pvt Ltd | 2023-09-18 | FSC/23-24/46 | 1817448 | Sheetal Ekta | Thermex,TMT Bar 08mm,25mm,32mm
21 | Fine Steel corporation | DGS Township Pvt Ltd | 2023-11-28 | FSC/23-24/74 | 337008 | Sheetal Ekta | PPGI Sheets,MS pipe
22 | Fine Steel corporation | DGS Township Pvt Ltd | 2023-08-04 | FSC/23-24/29 | 1692594 | Sheetal Ekta | Thermex,TMT Bar 12mm,16mm,20mm,25mm
23 | Kratos Concrete | DGS Township Pvt Ltd | 2023-08-31 | 381 | 1244039 | Sheetal Ekta | M 40
24 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-08-24 | AC/23-24/0830 | 2080779 | Sheetal Ekta | M40,M60
25 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-01-29 | AC/23-24/1899 | 92556 | Sheetal Ekta | OPC Without Pump Tax Rate
26 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-07-17 | AC/23-24/0347 | 355416 | Sheetal Ekta | M40 Fiber
27 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-06-30 | AC/23-24/0669 | 233434 | Sheetal Ekta | M 15
28 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-07-17 | AC/23-24/0709 | 2528032 | Sheetal Ekta | M 40 Fiber, Pumping Charges
29 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-07-29 | AC/23-24/0743 | 154025 | Sheetal Ekta | M40,M60
30 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-07-31 | AC/23-24/0760 | 158680 | Sheetal Ekta | M60
31 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-10-20 | AC/23-24/1092 | 411968 | Sheetal Ekta | RMC M-60 OPC,Under load
32 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-02-14 | AC/23-24/2016 | 79709 | Sheetal Ekta | RMC M-15
33 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-12-22 | AC/23-24/1552 | 748061 | Sheetal Ekta | RMC M-60,RMC M-40,Pumping Charges
34 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-01-08 | AC/23-24/1709 | 123576 | Sheetal Ekta | RMC M-60,RMC M-40,RMC M-15
35 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-01-10 | AC/23-24/1737 | 111068 | Sheetal Ekta | RMC M-40
36 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-01-20 | AC/23-24/1842 | 74045 | Sheetal Ekta | RMC M-40
37 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-01-15 | AC/23-24/1779 | 213182 | Sheetal Ekta | RMC M-40, RMC M-20
38 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-01-19 | AC/23-24/1820 | 252933 | Sheetal Ekta | RMC M-40, RMC M-20,Under Load
39 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-08-24 | AC/23-24/0409 | 439279 | Sheetal Ekta | M40
40 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-08-16 | AC/23-24/0791 | 556977 | Sheetal Ekta | M40,M60
41 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-08-16 | AC/23-24/0792 | 221950 | Sheetal Ekta | M 15
42 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-08-29 | AC/23-24/0845 | 464667 | Sheetal Ekta | M60, Pumping Charges
43 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-08-31 | AC/23-24/0863 | 117000 | Sheetal Ekta | M60
44 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-08-31 | AC/23-24/0871 | 144000 | Sheetal Ekta | M60
45 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-09-10 | AC/23-24/0895 | 581022 | Sheetal Ekta | M40, M60
46 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-11-05 | AC/23-24/1210 | 229436 | Sheetal Ekta | RMC M-60 OPC
47 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-10-26 | AC/23-24/1123 | 898260 | Sheetal Ekta | RMC M-60 & M-40 OPC, RMC M4O OPC, Pumping Charges, Under load
48 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-10-11 | AC/23-24/1030 | 625488 | Sheetal Ekta | RMC M-60 & M-40 OPC, RMC M4O OPC, Pumping Charges, Under load
49 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-09-30 | AC/23-24/0971 | 44430 | Sheetal Ekta | M40
50 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-09-30 | AC/23-24/0971 | 333246 | Sheetal Ekta | M40, M60
51 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-09-20 | AC/23-24/0932 | 442589 | Sheetal Ekta | M40, M60
52 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-10-07 | AC/23-24/1003 | 372976 | Sheetal Ekta | RMC M-60 & M-40 OPC
53 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-10-31 | AC/23-24/1155 | 511692 | Sheetal Ekta | RMC M-60 & M-40 OPC, Under load
54 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-10-17 | AC/23-24/1063 | 787856 | Sheetal Ekta | RMC M-60 & M-40 OPC, RMC M4O OPC, Pumping Charges
55 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-12-08 | AC/23-24/1399 | 264099 | Sheetal Ekta | RMC M-60 OPC, Under Road
56 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-11-30 | AC/23-24/1355 | 193668 | Sheetal Ekta | RMC M-60 OPC, Under Road
57 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-11-25 | AC/23-24/1328 | 74045 | Sheetal Ekta | RMC M-60 OPC
58 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-11-25 | AC/23-24/1316 | 238434 | Sheetal Ekta | RMC M-60 OPC
59 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-11-20 | AC/23-24/1282 | 195069 | Sheetal Ekta | RMC M-60 & M-20 OPC, RMC M4O OPC, Under Road
60 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-11-15 | AC/23-24/1267 | 37170 | Sheetal Ekta | RMC M-60 OPC, Under Road
61 | Aetreum Concrete | DGS Township Pvt Ltd | 2023-11-10 | AC/23-24/1252 | 1022145 | Sheetal Ekta | RMC M-60 & M-40 OPC, RMC M4O OPC, Pumping Charges, Under load
62 | S K Traders | DGS Township Pvt Ltd | 2023-06-13 | SK/137/23-24 | 26437 | Sheetal Ekta | Ind Wire 4 Sqmm x 4 core, MCB 63 Amp ABB, MCB Box 2-4 Way
63 | S K Traders | DGS Township Pvt Ltd | 2023-06-29 | SK/138/23-24 | 42000 | Sheetal Ekta | Safety Net
64 | S K Traders | DGS Township Pvt Ltd | 2023-07-07 | SK/211/23-24 | 16048 | Sheetal Ekta | Led Light Fitting
65 | S K Traders | DGS Township Pvt Ltd | 2023-12-04 | SK/578/23-24 | 174182 | Sheetal Ekta | AAC Fly Ash Block
66 | S K Traders | DGS Township Pvt Ltd | 2023-09-12 | SK/378/23-24 | 65021 | Sheetal Ekta | Aluminium Arm Cable, SFU 400 amp Enclouser, Busbar 200 amp, 200 & 100 Amp Main Switch Kew, Aluminium Lugs 120, 70 & 50 spmm, HRC Fuse 400 A
67 | S K Traders | DGS Township Pvt Ltd | 2023-12-09 | SK/5898/23-24 | 89088 | Sheetal Ekta | PPC
68 | S K Traders | DGS Township Pvt Ltd | 2023-12-10 | SK/590/23-24 | 179021 | Sheetal Ekta | AAC Fly Ash Block
69 | S K Traders | DGS Township Pvt Ltd | 2023-10-15 | SK/609/23-24 | 69521 | Sheetal Ekta | 200mm Foamlit 3mtr Pipe SN4, 110 & 75mm Swr Pipe l0', 75mm Swr Nahani Trap WO Jali, Pvc Solvent 500m1
70 | S K Traders | DGS Township Pvt Ltd | 2024-01-21 | SK/697/23-24 | 5458 | Sheetal Ekta | C I Plate 1x1, Gi Pipe, C I Funnel, Bentonite Powder, Copper Wires 8 swg
71 | S K Traders | DGS Township Pvt Ltd | 2023-11-19 | SK/551/23-24 | 79360 | Sheetal Ekta | PPC
72 | S K Traders | DGS Township Pvt Ltd | 2023-09-21 | SK/412/23-24 | 2354 | Sheetal Ekta | 23" Orrisa Pan White, P-Trap Sada
73 | S K Traders | DGS Township Pvt Ltd | 2023-11-16 | SK/545/23-24 | 147168 | Sheetal Ekta | AAC Fly Ash Block
74 | S K Traders | DGS Township Pvt Ltd | 2023-11-01 | SK/507/23-24 | 150460 | Sheetal Ekta | AAC Fly Ash Block, Magic Bond Joint Mortar
75 | S K Traders | DGS Township Pvt Ltd | 2023-11-14 | SK/540/23-24 | 24938 | Sheetal Ekta | Wrap Knit Fabrics
76 | S K Traders | DGS Township Pvt Ltd | 2023-12-21 | SK/618/23-24 | 10266 | Sheetal Ekta | JQR (069) Concealed Body
77 | S K Traders | DGS Township Pvt Ltd | 2023-12-18 | SK/612/23-24 | 111360 | Sheetal Ekta | PPC
78 | S K Traders | DGS Township Pvt Ltd | 2023-12-21 | SK/620/23-24 | 23697 | Sheetal Ekta | 40mm Swr Plpe 10"'B" Type,40mm Agri Elbow, 75mm Swr Pipe 2', Pvc Solvent 250m1, 3/4" Gpvc Elbow 90, 3/4" Cpvc Tee, l/2" Gpvc Threaded End Plug, 3/4"x1/2" Cpvc Brass Elbow 90, 3/4" x l/2" Cpvc Brass MTA, 314'xll2" Cpvc Brass Tee, Cpvc Solvent Coment 473m1
79 | S K Traders | DGS Township Pvt Ltd | 2023-12-25 | SK/634/23-24 | 87552 | Sheetal Ekta | PPC
80 | S K Traders | DGS Township Pvt Ltd | 2023-12-27 | SK/636/23-24 | 75630 | Sheetal Ekta | AAG Fly Ash Block
81 | S K Traders | DGS Township Pvt Ltd | 2024-01-05 | SK/656/23-24 | 109440 | Sheetal Ekta | PPC
82 | S K Traders | DGS Township Pvt Ltd | 2024-01-07 | SK/666/23-24 | 11139 | Sheetal Ekta | Cascade Chair Bracket
83 | S K Traders | DGS Township Pvt Ltd | 2024-01-14 | SK/683/23-24 | 87552 | Sheetal Ekta | PPC
84 | S K Traders | DGS Township Pvt Ltd | 2024-01-21 | SK/696/23-24 | 22050 | Sheetal Ekta | Copper Arm Cable, Bulkhead Metal, Led Bulb 9w, ABB Switch 6A, Gang Box 3w, ABB MCB 16AMP 2 POLE, ABB Mcb 25A4P
85 | S K Traders | DGS Township Pvt Ltd | 2024-01-21 | SK/699/23-24 | 8909 | Sheetal Ekta | SW x BSP Elbow 2000 PSI, Forge Socket Ext Hvy Bsp M.S 15mm, Spc Erw C Class Elbow 80,65,50,40,32,25 mm
86 | S K Traders | DGS Township Pvt Ltd | 2024-01-23 | SK/705/23-24 | 49376 | Sheetal Ekta | 110 & 75mm Swr Pipe 10' , 110 & 75mm Swr Pipe 4' , 110 & 75mm Swr Single Y Plain , 110&75 mm Swr Door Bend , 110&75 mm Swr Plain Bend 90, 110&75 mm Swr Plain Bend 45, 75mm Swr Plain Tee, Rubber Lubricant 500 Gm, G.I.U Bracket , G.I.U Bolt
87 | S K Traders | DGS Township Pvt Ltd | 2024-01-30 | SK/719/23-24 | 109440 | Sheetal Ekta | PPC
88 | S K Traders | DGS Township Pvt Ltd | 2024-01-10 | SK/678/23-24 | 149282 | Sheetal Ekta | AAC Fly Ash Btock, Magic Bond Joint Mortar
89 | S K Traders | DGS Township Pvt Ltd | 2024-01-31 | SK/728/23-24 | 67984 | Sheetal Ekta | TUFF AAC Block
90 | S K Traders | DGS Township Pvt Ltd | 2023-06-03 | SK/114/23-24 | 25404 | Sheetal Ekta | Mcb Four Pole 100A, Mcb Box 2-4 way, Busbar 63amp, 100amp Main switch Kew, 100/200 Amp Neutal
91 | S K Traders | DGS Township Pvt Ltd | 2023-06-16 | SK/227/23-24 | 16992 | Sheetal Ekta | Round water Tank 2000 Ltr
92 | S K Traders | DGS Township Pvt Ltd | 2023-08-06 | SK/259/23-24 | 33276 | Sheetal Ekta | ISI Cube Mould 150mm
93 | S K Traders | DGS Township Pvt Ltd | 2023-08-09 | SK/275/23-24 | 24397 | Sheetal Ekta | 2HP 1ph sub Pump, stator
94 | S K Traders | DGS Township Pvt Ltd | 2023-10-04 | SK/443/23-24 | 15582 | Sheetal Ekta | Hessian Cloth
95 | S K Traders | DGS Township Pvt Ltd | 2023-11-21 | SK/552/23-24 | 150458 | Sheetal Ekta | AAC Fly Ash Btock, Magic Bond Joint Mortar
96 | Neeraj Steel Sales | DGS Township Pvt Ltd | 2023-08-16 | 361/23-24 | 1776884 | Sheetal Ekta | TMT BARS
97 | Neeraj Steel Sales | DGS Township Pvt Ltd | 2023-10-08 | 529/23-24 | 1947976 | Sheetal Ekta | TMT BARS
98 | Neeraj Steel Sales | DGS Township Pvt Ltd | 2023-10-05 | 710/23-24 | 1752482 | Sheetal Ekta | TMT BARS
99 | Neeraj Steel Sales | DGS Township Pvt Ltd | 2023-10-25 | 603/23-24 | 1885754 | Sheetal Ekta | TMT BARS
100 | Vastu RMC LLP | DGS Township Pvt Ltd | 2024-02-18 | VRMCG/2324/00149 | 1929964 | Sheetal Ekta | M-60 Pumpable
101 | Malik Steels Corporation | DGS Township Pvt Ltd | 2023-07-12 | MSC/23-24/49 | 2087205 | Sheetal Ekta | 08 mm, 25mm,32ms TMT Bar
102 | Umika Enterprises | DGS Township Pvt Ltd | 2024-03-04 | 28 | 64994 | Sheetal Ekta | 32mm, 25mm & 20mm dia Coupler
103 | Umika Enterprises | DGS Township Pvt Ltd | 2024-03-05 | 29 | 59660 | Sheetal Ekta | 32mm & 25mm dia Coupler, 32/25mm dia Reducer Coupler
104 | Umika Enterprises | DGS Township Pvt Ltd | 2024-03-06 | 30 | 69242 | Sheetal Ekta | 32mm dia cold forged coupler, 32/25 mm dia cold forged coupler reducer
105 | Umika Enterprises | DGS Township Pvt Ltd | 2024-03-07 | 31 | 76855 | Sheetal Ekta | 25mm & 22mm dia Coupler, 25/20mm dia Cold forged Reducer Coupler
106 | Umika Enterprises | DGS Township Pvt Ltd | 2024-03-07 | 32 | 53451 | Sheetal Ekta | 32mm, 25mm & 20mm dia cold forged threading both side
107 | A-1 Fabrication | DGS Township Pvt Ltd | 2024-03-12 |  | 3227412 | Sheetal Ekta | Glazing, Opnable, Louvers, ACP Chajja Column, ACP Board, Sliding, Sliding Openable, Bathroom Louvers, Scaffolding
108 | A-1 Fabrication | DGS Township Pvt Ltd | 2024-03-12 |  | 1955856 | Sheetal Ekta | Platform, Top Chajja, Borad, Shutter, MS Channel, MS Plate, Labour Charges, L Frame 2x2 Angle, MS Tappa 10" Deep, SS Railing, M.S.Sheet, Tempo Bhada, Platform Repairing, Platform & Bucckel Roof Wire with Labour, Tank Sidi
109 | Avenue Imperial Construction LLP | DGS Township Pvt Ltd | 2024-03-27 | DGS/AE/06/2023-24 | 35400000 | Sheetal Ekta | RCC Work of Building
110 | Evolve Construction | DGS Township Pvt Ltd | 2023-10-16 | DGS/01/WO/Sheetal Ekta/2023 | 15000000 | Sheetal Ekta | Aluminium Form Work
111 | Evolve Construction | DGS Township Pvt Ltd | 2023-10-24 | 30/2023-24 | 975000 | Sheetal Ekta | Construction of Residential Complex
112 | Evolve Construction | DGS Township Pvt Ltd | 2023-12-22 | 41/2023-24 | 781541 | Sheetal Ekta | Construction of Residential Complex
113 | Evolve Construction | DGS Township Pvt Ltd | 2024-03-22 | 57/2023-24 | 11100000 | Sheetal Ekta | Construction of Residential Complex
114 | Mahakal Enterprises | DGS Township Pvt Ltd | 2024-03-28 | PERFORMA/01/23-24 | 11682590 | Sheetal Ekta | 08mm, 10mm, 12mm, 16mm & 20mm TMT Bars
115 | Saurabh Steel Corporation | DGS Township Pvt Ltd | 2024-03-28 | PRO/001/2023-24 | 12301500 | Sheetal Ekta | 08mm, 12mm, 16mm & 20mm TMT Bars
116 | Shree Ganesh Electricals | DGS Township Pvt Ltd | 2024-02-26 | 7 | 205544 | Sheetal Ekta | Electrical Work
117 | SK Kawsar Ali Civil Contractor | DGS Township Pvt Ltd | 2024-03-20 | 2 | 564385 | Sheetal Ekta | Window Framing Work, Border Patti Fixing, Tappa Fixing, Raizer Cutting With Fixing, Grove Making For Tappa, Champering Work, Wall Tiles Fixing, Umbra Patti Fixing, Dhar Polish Work, Passage Flooring Tiles, 2nd Floor (6 Room) Flooring Tiles (1600*800), Tiles Skirting Work, Granite Fixing, Nali Traf Cutting, Pavor Flooring, Department Supply,
118 | Saurabh Enterprise | DGS Township Pvt Ltd | 2024-04-01 | 5 | 14444 | Sheetal Ekta | Sika Microcrete 4 & AP Apcocrete
119 | Umika Enterprises | DGS Township Pvt Ltd | 2024-04-02 | 2 | 54006 | Sheetal Ekta | 25 mm dia Coupler & 20 mm dia Coupler
120 | Umika Enterprises | DGS Township Pvt Ltd | 2024-04-03 | 4 | 129084 | Sheetal Ekta | Cold Forged Threading Both Side 20 mm dia, 25 mm dia, 32 mm dia & 20 mm dia oneside
121 | Umika Enterprises | DGS Township Pvt Ltd | 2024-04-03 | 3 | 84062 | Sheetal Ekta | 32 mm dia Cold Forged Coupler & 25 mm dia Cold Forged Coupler
122 | Saurabh Enterprise | DGS Township Pvt Ltd | 2024-04-08 | 15 | 21158 | Sheetal Ekta | Ap Cemcrete
123 | BMCC Enterprise | DGS Township Pvt Ltd | 2024-04-22 | 1278 | 61425 | Sheetal Ekta | Crush Sand, Metal Mix & Plaster Sand
124 | M R Pigeon Net | DGS Township Pvt Ltd | 2024-04-22 | 8 | 47381 | Sheetal Ekta | Agro Shade Net 75% BDL
125 | BMCC Enterprise | DGS Township Pvt Ltd | 2024-04-30 | 1295 | 45675 | Sheetal Ekta | C Sand, P Sand & Metal Mix
126 | Umika Enterprises | DGS Township Pvt Ltd | 2024-05-05 | 12 | 84039 | Sheetal Ekta | 20 mm dia Cold Forged Coupler, 25 mm dia Cold Forged Coupler, 32/25 mm dia reducer & 25/20 mm dia reducer
127 | Umika Enterprises | DGS Township Pvt Ltd | 2024-05-06 | 14 | 32096 | Sheetal Ekta | 25 mm dia Cold Forged Coupler
128 | Vintage Traders | DGS Township Pvt Ltd | 2024-05-06 | 047 | 148425 | Sheetal Ekta | Flyash Blocks & Joint Morter
129 | Umika Enterprises | DGS Township Pvt Ltd | 2024-05-10 | 16 | 48144 | Sheetal Ekta | 25 mm dia Cold Forged Coupler
130 | Anupam Hardware | DGS Township Pvt Ltd | 2024-05-13 | 01746 | 9947 | Sheetal Ekta | LED Flat Light & PVC Green Breded Pipe
131 | S. V. & Co. | DGS Township Pvt Ltd | 2024-05-14 | 83/24-25 | 3474 | Sheetal Ekta | Flexo Board
132 | B. Mittal & Co. | DGS Township Pvt Ltd | 2024-05-20 | BM24250082 | 2055284 | Sheetal Ekta | TMT Rebar
133 | BMCC Enterprise | DGS Township Pvt Ltd | 2024-05-24 | 1335 | 23310 | Sheetal Ekta | C Sand, P Sand & Metal Mix
134 | Anupam Hardware | DGS Township Pvt Ltd | 2024-05-25 | 02311 | 11862 | Sheetal Ekta | Pipe Easyfit SCH- 80 & others
135 | S K Traders | DGS Township Pvt Ltd | 2024-05-28 | SK/114/24-25 | 216742 | Sheetal Ekta | Aluminium Arm Cable & others
136 | B. Mittal & Co. | DGS Township Pvt Ltd | 2024-05-28 | BM24250104 | 1993876 | Sheetal Ekta | TMT Rebar
137 | Anupam Hardware | DGS Township Pvt Ltd | 2024-05-22 | 02158 | 20432 | Sheetal Ekta | Earthing Strip & others
138 | Salim Timber Corporation | DGS Township Pvt Ltd | 2024-05-16 | 82/2024-2025 | 8095 | Sheetal Ekta | Timbers Frame
139 | S K Traders | DGS Township Pvt Ltd | 2024-05-30 | SK/121/24-25 | 135828 | Sheetal Ekta | TUFF AAC Block
140 | S K Traders | DGS Township Pvt Ltd | 2024-05-27 | SK/115/24-25 | 41008 | Sheetal Ekta | Aluminium Lugs & others
141 | S K Traders | DGS Township Pvt Ltd | 2024-05-31 | SK/123/24-25 | 17464 | Sheetal Ekta | Mortar Tuff Easyfix
142 | Ramkishan Prajapati | DGS Township Pvt Ltd | 2024-06-01 | 755 | 27350 | Sheetal Ekta | 40 mm round & others
143 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-747 | 53808 | Sheetal Ekta | M60- Supercrete
144 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-748 | 53808 | Sheetal Ekta | M60- Supercrete
145 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-749 | 53808 | Sheetal Ekta | M60- Supercrete
146 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-750 | 53808 | Sheetal Ekta | M60- Supercrete
147 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-762 | 53808 | Sheetal Ekta | M60- Supercrete
148 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP1-783 | 53808 | Sheetal Ekta | M60- Supercrete
149 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-789 | 53808 | Sheetal Ekta | M60- Supercrete
150 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP1-786 | 53808 | Sheetal Ekta | M60- Supercrete
151 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-765 | 53808 | Sheetal Ekta | M60- Supercrete
152 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-764 | 53808 | Sheetal Ekta | M60- Supercrete
153 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-763 | 53808 | Sheetal Ekta | M60- Supercrete
154 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-746 | 53808 | Sheetal Ekta | M60- Supercrete
155 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-767 | 53808 | Sheetal Ekta | M60- Supercrete
156 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-768 | 53808 | Sheetal Ekta | M60- Supercrete
157 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-790 | 53808 | Sheetal Ekta | M60- Supercrete
158 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-794 | 53808 | Sheetal Ekta | M60- Supercrete
159 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-793 | 53808 | Sheetal Ekta | M60- Supercrete
160 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-769 | 53808 | Sheetal Ekta | M60- Supercrete
161 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-795 | 53808 | Sheetal Ekta | M60- Supercrete
162 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-770 | 53808 | Sheetal Ekta | M60- Supercrete
163 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-796 | 49324 | Sheetal Ekta | M60- Supercrete
164 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-797 | 53808 | Sheetal Ekta | M60- Supercrete
165 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-799 | 53808 | Sheetal Ekta | M60- Supercrete
166 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-771 | 53808 | Sheetal Ekta | M60- Supercrete
167 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-798 | 53808 | Sheetal Ekta | M60- Supercrete
168 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-772 | 53808 | Sheetal Ekta | M60- Supercrete
169 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-773 | 53808 | Sheetal Ekta | M60- Supercrete
170 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-800 | 53808 | Sheetal Ekta | M60- Supercrete
171 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-801 | 53808 | Sheetal Ekta | M60- Supercrete
172 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-802 | 53808 | Sheetal Ekta | M60- Supercrete
173 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-803 | 53808 | Sheetal Ekta | M60- Supercrete
174 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-806 | 53808 | Sheetal Ekta | M60- Supercrete
175 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-780 | 53808 | Sheetal Ekta | M60- Supercrete
176 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-807 | 53808 | Sheetal Ekta | M60- Supercrete
177 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-810 | 58292 | Sheetal Ekta | M60- Supercrete
178 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP1-787 | 53808 | Sheetal Ekta | M60- Supercrete
179 | Umika Enterprises | DGS Township Pvt Ltd | 2024-06-02 | 22 | 59354 | Sheetal Ekta | Cold Forged Coupler 20 mm dia, 25 mm dia & 32 mm dia
180 | Umika Enterprises | DGS Township Pvt Ltd | 2024-06-03 | 24 | 35140 | Sheetal Ekta | Cold Forged Coupler 25 mm dia & 32/25 mm dia
181 | Umika Enterprises | DGS Township Pvt Ltd | 2024-06-04 | 26 | 70179 | Sheetal Ekta | Cold Forged Coupler 20 mm dia, 25 mm dia & 25/20 mm dia
182 | Mahadev Traders | DGS Township Pvt Ltd | 2024-06-06 | 68 | 85054 | Sheetal Ekta | M. S. Binding Wire
183 | S. V. & Co. | DGS Township Pvt Ltd | 2024-06-10 | 187/24-25 | 10547 | Sheetal Ekta | Flexo Board & other
184 | Jai Durga Transport | DGS Township Pvt Ltd | 2024-04-01 | 4451 | 11800 | Sheetal Ekta | Boring Water
185 | Vinod Yadav | DGS Township Pvt Ltd | 2024-04-02 | 1010 | 14500 | Sheetal Ekta | Steel Shifting
186 | Evolve Construction | DGS Township Pvt Ltd | 2024-04-08 | 2/2024-25 | 11800000 | Sheetal Ekta | RA Bill 03
187 | Brahmadev | DGS Township Pvt Ltd | 2024-04-07 | 003 | 6720 | Sheetal Ekta | Meter room cement sheet
188 | Shravan Sahani | DGS Township Pvt Ltd | 2024-04-07 |  | 14400 | Sheetal Ekta | 12 Frame and others
189 | Rukmani G.Chouhan | DGS Township Pvt Ltd | 2024-04-16 |  | 4200 | Sheetal Ekta | Labour
190 | SRSBM Lab Testing Pvt.Ltd. | DGS Township Pvt Ltd | 2024-04-16 | MRT-27006 | 3304 | Sheetal Ekta | Concrete Cube ( Compressive Strength)
191 | Jai Durga Transport | DGS Township Pvt Ltd | 2024-05-01 | 4501 | 18000 | Sheetal Ekta | Boring Water, Drinking Water
192 | Poonam D. Jha | DGS Township Pvt Ltd | 2024-04-30 | 423 | 18000 | Sheetal Ekta | Rabbit
193 | Umika Enterprises | DGS Township Pvt Ltd | 2024-05-04 | 10 | 44259 | Sheetal Ekta | 25 mm dia cold forged one side , 25 mm dia forged both side, 20 mm dia forged
194 | Vinod Yadav | DGS Township Pvt Ltd | 2024-05-05 | 1012 | 14500 | Sheetal Ekta | Steel Shifting, Block
195 | Rajesh Singh Water pump hiring | DGS Township Pvt Ltd | 2024-05-14 | 598 | 5000 | Sheetal Ekta | HP Pump
196 | Rajesh Singh Water pump hiring | DGS Township Pvt Ltd | 2024-05-14 | 465 | 10000 | Sheetal Ekta | HP Pump
197 | Abhay Facility Service | DGS Township Pvt Ltd | 2024-06-01 | AFS/867/2024 | 92040 | Sheetal Ekta | Secuirty head guars, Liftman
198 | Jai Durga Transport | DGS Township Pvt Ltd | 2024-06-01 | 4551 | 42200 | Sheetal Ekta | Boring Water, Drinking Water
199 | Maharaja Enterprises | DGS Township Pvt Ltd | 2024-05-31 | 8330 | 7830 | Sheetal Ekta | Bottles
200 | Vinod Yadav | DGS Township Pvt Ltd | 2024-06-03 | 1013 | 29000 | Sheetal Ekta | Steel Shifting, Block
201 | Umika Enterprises | DGS Township Pvt Ltd | 2024-06-04 | 27 | 123715 | Sheetal Ekta | 25 mm dia cold forged one side , 25 mm dia forged both side, 20 mm dia forged, 32 mm dia forged
202 | Rajesh Singh Water pump hiring | DGS Township Pvt Ltd | 2024-06-16 | 630 | 5000 | Sheetal Ekta | HP Pump
203 | Janki Devi Prajapati | DGS Township Pvt Ltd | 2024-06-16 | 473 | 10100 | Sheetal Ekta | 40 mm round block, 25 mm square block, Transport charges
204 | Om Infrastrcuture | DGS Township Pvt Ltd | 2024-06-19 | OM/008/2024-25 | 15000000 | Sheetal Ekta | Labour Work
205 | Avenue Imperial Construction LLP | DGS Township Pvt Ltd | 2024-05-05 | DGS/AE/04/2024-25 | 15000000 | Sheetal Ekta | RCC Work of Building
206 | Mahibuddin | DGS Township Pvt Ltd | 2024-06-05 |  | 36235 | Sheetal Ekta | Labour Charges
207 | Saikat Mondal | DGS Township Pvt Ltd | 2024-06-05 | 790 | 7200 | Sheetal Ekta | glass sticker with pasting
208 | Saikat Mondal | DGS Township Pvt Ltd | 2024-06-05 | 785 | 81200 | Sheetal Ekta | Acrylic letter, Logo 2 pic
209 | Anupam Hardware | DGS Township Pvt Ltd | 2024-04-02 | 00059 | 6348 | Sheetal Ekta | Wires House Flex 1.5 SQ MM & others
210 | Shree Krushna Electrical & Hardware | DGS Township Pvt Ltd | 2024-04-10 | 370 | 13800 | Sheetal Ekta | Water Tank 2000 L & Tampo
211 | S K Traders | DGS Township Pvt Ltd | 2024-04-14 | SK/033/24-25 | 87552 | Sheetal Ekta | PPC Birla Shakti
212 | Maatangi Enterprises | DGS Township Pvt Ltd | 2024-04-15 | 385 | 10561 | Sheetal Ekta | Black Granite
213 | S K Traders | DGS Township Pvt Ltd | 2024-04-17 | SK/035/24-25 | 150866 | Sheetal Ekta | AAC Fly Ash Block & Magic Bond Joint Mortar
214 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-04-19 | ASC066/24-25 | 1945990 | Sheetal Ekta | TMT BARS 8 mm, 12 mm, 16 mm, 20 mm & 25 mm
215 | S K Traders | DGS Township Pvt Ltd | 2024-04-19 | SK/041/24-25 | 16184 | Sheetal Ekta | Reducer Socket MS ERW 80*40 mm & others
216 | S K Traders | DGS Township Pvt Ltd | 2024-04-22 | SK/047/24-25 | 36657 | Sheetal Ekta | Butterfly Valve & others
217 | Shree Krushna Electrical & Hardware | DGS Township Pvt Ltd | 2024-04-22 | 378 | 3580 | Sheetal Ekta | P Draw, 110 mm Albow & others
218 | Anupam Hardware | DGS Township Pvt Ltd | 2024-04-25 | 01036 | 19612 | Sheetal Ekta | Vertical Tank Black 2000 ltr & Others
219 | Saurabh Enterprise | DGS Township Pvt Ltd | 2024-04-27 | 51 | 24485 | Sheetal Ekta | AP Antihack
220 | Anupam Hardware | DGS Township Pvt Ltd | 2024-04-28 | 01136 | 24619 | Sheetal Ekta | Pump Mono Mik-22-18 2HP & Other
221 | Schindler India Pvt Ltd | DGS Township Pvt Ltd | 2024-04-29 | CI2700413089 | 147500 | Sheetal Ekta | Installation, Repair & Maintenance of Elevators & Escalators
222 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-04-09 | AC/24-25/0011 | 1995734 | Sheetal Ekta | M-60 Mivan & others
223 | Shree Krushna Electrical & Hardware | DGS Township Pvt Ltd | 2024-06-25 | 006 | 20300 | Sheetal Ekta | Tube Light, Flood light, Ploycab core, Metal Socket single phase
224 | Neeraj Steel Sales | DGS Township Pvt Ltd | 2024-06-08 | 203/24-25 | 2066752 | Sheetal Ekta | TMT BARS- 8mm, 10mm, 12mm, 16mm, 20mm, 25mm, 32mm
225 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-05-21 | 24-25/0011 | 5808 | Sheetal Ekta | Pumping Charges
226 | M R Pigeon Net | DGS Township Pvt Ltd | 2024-06-01 |  | 145 | Sheetal Ekta | TDS on Labour
227 | City Elevators Private Limited | DGS Township Pvt Ltd | 2024-06-05 |  | 86580 | Sheetal Ekta
228 | Anupam Hardware | DGS Township Pvt Ltd | 2024-06-21 |  | 46360 | Sheetal Ekta
229 | Anupam Hardware | DGS Township Pvt Ltd | 2024-05-23 |  | 46460 | Sheetal Ekta
230 | B S Fire Protection | DGS Township Pvt Ltd | 2024-05-10 |  | 590000 | Sheetal Ekta | Labour Charges
231 | Seema Dipak Alaskar | DGS Township Pvt Ltd | 2024-04-30 |  | 57842 | Sheetal Ekta | 08mm, 10mm, 12mm, 16mm & 20mm TMT Bars
232 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-04-30 |  | 492061 | Sheetal Ekta
233 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-04-30 |  | 467460 | Sheetal Ekta
234 | Saurabh Steel Corporation | DGS Township Pvt Ltd | 2024-04-30 |  | 615075 | Sheetal Ekta
235 | Shree Krushna Electrical & Hardware | DGS Township Pvt Ltd | 2024-04-09 |  | 14650 | Sheetal Ekta
236 | Mahakal Enterprises | DGS Township Pvt Ltd | 2024-04-30 |  | 584130 | Sheetal Ekta
237 | Bajarang Drilling | DGS Township Pvt Ltd | 2024-06-07 | 06 | 18337 | Sheetal Ekta | Bill for Core cutting, Drilling hole in RCC along with electric portable machine
238 | Poonam D. Jha | DGS Township Pvt Ltd | 2024-06-30 | 515 | 13500 | Sheetal Ekta | Rabbit
239 | Shri Krihsna Electrical & Hardware | DGS Township Pvt Ltd | 2024-06-30 | 014 | 695 | Sheetal Ekta | L Hall Pass & Anchor Faszar
240 | Aayush Enterprises | DGS Township Pvt Ltd | 2024-06-28 | 188 | 1392 | Sheetal Ekta | FAIBER MESH (HSN7019)
241 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-06-10 | AC/24-25/0514 | 1951631 | Sheetal Ekta | M-60 MIVAN OPC Without Pump, M-60 MIVAN OPC With Pump, Pumping Charges
242 | BMCC Enterprise | DGS Township Pvt Ltd | 2024-06-28 | 1409 | 33075 | Sheetal Ekta | Plaster Sand, Metal Mix, Crush Sand
243 | R.R Enterprises | DGS Township Pvt Ltd | 2024-06-16 | 12 | 1997834 | Sheetal Ekta | RMC M-60 FREE FLOW, SLURRY
244 | Salim Timber Corporation | DGS Township Pvt Ltd | 2024-06-22 | 136/2024-2025 | 52510 | Sheetal Ekta | Timbers Frame
245 | R.R Enterprises | DGS Township Pvt Ltd | 2024-06-30 | 16 | 2027235 | Sheetal Ekta | RMC M-60 FREE FLOW, SLURRY
246 | Ramkishan Prajapati | DGS Township Pvt Ltd | 2024-06-15 | 770 | 40000 | Sheetal Ekta | RCC Chember cover with frame, 600x900, Transport
247 | Shabbir Pipe Fitting | DGS Township Pvt Ltd | 2024-06-15 | SPF/064/24-25 | 43176 | Sheetal Ekta | Steelman 6" G.I C Class
248 | Vintage Traders | DGS Township Pvt Ltd | 2024-06-18 | VT/24-25/36 | 143847 | Sheetal Ekta | Fly Ash Block, Joining Mortor
249 | Ramkishan Prajapati |  | 2024-07-01 | 770 | 40000
250 | Aarti Steel Corporation |  | 2024-07-01 | ASC320/24-25 | 2139240
251 | Aetreum Concrete |  | 2024-07-01 | AC/24-25/0514 | 1951603
252 | Shabbir Pipe Fitting |  | 2024-07-01 | SPF/064/24-25 | 43176
253 | BMCC Enterprises |  | 2024-07-01 | 1409 | 33075
254 | VINTAGE TRADERS |  | 2024-07-01 | VT/24-25/36 | 143847
255 | M.R. Pigeon Net |  | 2024-07-01 | 26 | 48951
256 | Aayush Enterprises |  | 2024-07-01 | 188 | 1392
257 | R.R. Enterprises |  | 2024-07-01 | 16 | 2027235
258 | Salim Timber Corporation |  | 2024-07-01 | 136/2024-2025 | 52510
259 | B Mittal & Co. |  | 2024-07-02 | BM24250158 | 2275158
260 | Mahadev Traders |  | 2024-07-04 | 99 | 39318
261 | Umika Enterprises |  | 2024-07-08 | 33 | 90659
262 | Umika Enterprises |  | 2024-07-09 | 40 | 101930
263 | Salim Timber Corporation |  | 2024-07-09 | 153/2024-2025 | 97090
264 | Salim Timber Corporation |  | 2024-07-11 | 162/2024-2025 | 101209
265 | VINTAGE TRADERS |  | 2024-07-15 | VT/24-25/57 | 155396
266 | B Mittal & Co. |  | 2024-07-16 | BM24250179 | 1907832
267 | R.R. Enterprises |  | 2024-08-01 | 24 | 1983835
268 | R.R. Enterprises |  | 2024-08-01 | 12 | 1997834
269 | R.R. Enterprises |  | 2024-08-01 | 19 | 1863432
270 | R.R. Enterprises |  | 2024-08-01 | 20 | 21740
271 | Aarti Steel Corporation |  | 2024-08-01 | ASC/408/24-25 | 81076
272 | Aarti Steel Corporation |  | 2024-08-01 | ASC407/24-25 | 1806201
273 | S.K TRADERS |  | 2024-08-01 | SK/180/24-25 | 72960
274 | Shabbir Pipe Fitting |  | 2024-08-01 | SPF/089/24-25 | 3965
275 | Ramkishan Prajapati |  | 2024-08-01 | 792 | 9650
276 | Maatangi Enterprises |  | 2024-08-01 | 407 | 11890
277 | BMCC Enterprises |  | 2024-08-01 | 1483 | 161700
278 | Umika Enterprises |  | 2024-08-02 | 42 | 57112
279 | Shabbir Pipe Fitting |  | 2024-08-02 | SPF/093/24-25 | 21559
280 | Umika Enterprises |  | 2024-08-03 | 43 | 89444
281 | Umika Enterprises |  | 2024-08-04 | 44 | 88854
282 | S.V& Co, |  | 2024-08-05 | 363/24-25 | 82128
283 | Aayush Enterprises |  | 2024-08-07 | 259 | 16201
284 | Ramkishan Prajapati |  | 2024-08-09 | 812 | 20450
285 | Aarti Steel Corporation |  | 2024-08-09 | ASC447/24-25 | 1958375
286 | S.K TRADERS |  | 2024-08-19 | SK/276/24-25 | 15812
287 | S.K TRADERS |  | 2024-08-19 | SK/275/24-25 | 114211
288 | S.K TRADERS |  | 2024-08-20 | SK/279/24-25 | 70400
289 | S.K TRADERS |  | 2024-08-24 | SK/291/24-25 | 15812
290 | S.K TRADERS |  | 2024-08-24 | SK/290/24-25 | 120316
291 | Aarti Steel Corporation |  | 2024-09-01 | ASC521/24-25 | 2197867
292 | Aayush Enterprises |  | 2024-09-01 | 298 | 19435
293 | S.K TRADERS |  | 2024-09-01 | SK/308/24-25 | 11859
294 | S.K TRADERS |  | 2024-09-01 | SK/307/24-25 | 119280
295 | RDC Concrete India Pvt Ltd |  | 2024-09-01 | 11MU23BP1-4846 | 50298
296 | RDC Concrete India Pvt Ltd |  | 2024-09-01 | 11MU23BP2-583 | 54870
297 | RDC Concrete India Pvt Ltd |  | 2024-09-01 | 11MU23BP1-3367 | 27435
298 | RDC Concrete India Pvt Ltd |  | 2024-09-01 | 11MU23BP1-4840 | 27435
299 | RDC Concrete India Pvt Ltd |  | 2024-09-01 | 11MU23BP2-578 | 45725
300 | RDC Concrete India Pvt Ltd |  | 2024-09-01 | 11MU23BP2-591 | 41152
301 | RDC Concrete India Pvt Ltd |  | 2024-09-01 | 11MU23BP2-563 | 54870
302 | BMCC Enterprises |  | 2024-09-01 | 1539 | 85050
303 | R.R. Enterprises |  | 2024-09-01 | 26 | 1938334
304 | R.R. Enterprises |  | 2024-09-01 | 29 | 1749751
305 | R.R. Enterprises |  | 2024-09-01 | 34 | 1708147
306 | ANUPAM HARDWARE |  | 2024-09-03 | 07263 | 72669
307 | S.K TRADERS |  | 2024-09-04 | SK/324/24-25 | 118564
308 | S.K TRADERS |  | 2024-09-04 | SK/325/24-25 | 15812
309 | Rushabh Trading Co, |  | 2024-09-05 | 113 | 9656
310 | Salim Timber Corporation |  | 2024-09-05 | 268/2024-2025 | 37760
311 | Aarti Steel Corporation |  | 2024-09-09 | ASC532/24-25 | 7139
312 | Swati Industries |  | 2024-09-16 | SI/531/2024-25 | 2767
313 | S.K TRADERS |  | 2024-09-16 | SK/363/24-25 | 15812
314 | Saurabh Enterprise |  | 2024-09-19 | 211 | 28828
315 | Saurabh Enterprise |  | 2024-09-21 | 213 | 15517
316 | ANUPAM HARDWARE |  | 2024-09-22 | 08028 | 21236
317 | Sudha Sales Corporation |  | 2024-09-23 | SSC/084 | 75520
318 | MAHARAJA ENTERPRISES |  | 2024-07-01 | 8290 | 5220
319 | Shree Krishna Electrical & Hardware |  | 2024-07-01 | 014 | 695
320 | Poonam D.Jha |  | 2024-07-01 | 515 | 13500
321 | Jai Durga Transports |  | 2024-07-01 | 4608 | 34800
322 | R.R. Enterprises- Pumping Charges |  | 2024-07-01 | 13 | 70800
323 | R.R. Enterprises- Pumping Charges |  | 2024-07-01 | 17 | 71390
324 | Vinod Yadav ( Mathadi) |  | 2024-07-02 | 1014 | 28030
325 | Retaintion Money (Evolve Construction) |  | 2024-07-05 | 18/2024-25 | 256256
326 | A-1 Fabrication |  | 2024-07-05 | 05.07.24 | 1001602
327 | Umika Enterprises |  | 2024-07-08 | 37 | 173275
328 | Shree Krishna Electrical & Hardware |  | 2024-07-21 | 025 | 5340
329 | Shree Krishna Electrical & Hardware |  | 2024-07-25 | 030 | 2162
330 | Shree Krishna Electrical & Hardware |  | 2024-07-27 | 032 | 3400
331 | Gayatri Water Supplier & Co. |  | 2024-08-01 | 814 | 1400
332 | Gayatri Water Supplier & Co. |  | 2024-08-01 | 815 | 14400
333 | R.R. Enterprises- Pumping Charges |  | 2024-08-01 | 21 | 11800
334 | R.R. Enterprises- Pumping Charges |  | 2024-08-01 | 25 | 94990
335 | R.R. Enterprises- Pumping Charges |  | 2024-08-01 | 18 | 75048
336 | Poonam D.Jha |  | 2024-08-01 | 554 | 27000
337 | Abhay Facility Services |  | 2024-08-01 | AFS/892/2024 | 78000
338 | Ahsan Shaikh |  | 2024-08-01 | 065 | 8000
339 | MAHARAJA ENTERPRISES |  | 2024-08-01 | 8447 | 7250
340 | MAHARAJA ENTERPRISES |  | 2024-08-01 | 8375 | 9570
341 | Rajesh Singh Water Pump Hiring |  | 2024-08-01 | 898 | 2500
342 | Vinod Yadav ( Mathadi) |  | 2024-08-03 | 1015 | 36575
343 | Umika Enterprises |  | 2024-08-04 | 45 | 132254
344 | Sagar Lifts |  | 2024-08-06 | SL/462/24-25 | 121540
345 | Vruddhi Engineering Works Ltd |  | 2024-08-07 | VSL/23-24/458 | 40184
346 | City Elevators Private Limited |  | 2024-08-13 | CEPL/08/25/E/10 | 5108220
347 | Shree Krishna Electrical & Hardware |  | 2024-08-13 | 043 | 41770
348 | Evolve Construction |  | 2024-08-21 | 29/2024-25 | 11800000
349 | Shree Krishna Electrical & Hardware |  | 2024-08-21 | 056 | 4000
350 | Poonam D.Jha |  | 2024-09-01 | A000005 | 39800
351 | Abhay Facility Services |  | 2024-09-01 | AFS/608/2024 | 78000
352 | Kalesh L. Kamat |  | 2024-09-01 | 075 | 15084
353 | Poonam D.Jha |  | 2024-09-01 | A000021 | 22500
354 | Gayatri Water Supplier & Co. |  | 2024-09-01 | 844 | 33600
355 | Mihir Water Suppliers |  | 2024-09-01 | 006 | 27000
356 | T.H. CONSTRUCTION |  | 2024-09-01 | 159 | 19629
357 | T.H. CONSTRUCTION |  | 2024-09-01 | 158 | 29040
358 | R.R. Enterprises- Pumping Charges |  | 2024-09-01 | 28 | 69310
359 | R.R. Enterprises- Pumping Charges |  | 2024-09-01 | 33 | 84100
360 | The All Inside Decorators |  | 2024-09-03 | 001/ RA- 1 Bill | 698590
361 | Vinod Yadav ( Mathadi) |  | 2024-09-03 | 1016 | 38750
362 | Bajarang Drilling |  | 2024-09-03 | 49 | 23803
363 | A-1 Fabrication |  | 2024-09-06 | 06.09.24 | 229200
364 | Firoz Khan |  | 2024-09-07 | 164 | 34200
365 | Rajesh Singh Water Pump Hiring |  | 2024-09-10 | 1074 | 3780
366 | Sagar Lifts |  | 2024-09-13 | SL/622/24-25 | 607700
367 | Sagar Lifts |  | 2024-09-20 | SL/646/24-25 | 364620
368 | Shravan Sahan |  | 2024-09-24 | 24.09.24 | 6000
369 | Oracle Granito Ltd. |  | 2024-10-01 | OGL/24-25/1048 | 66670
370 | Ramkishan Prajapati |  | 2024-10-01 | 833 | 22950
371 | Aayush Enterprises |  | 2024-10-01 | 331 | 14750
372 | Shabbir Pipe Fitting |  | 2024-10-04 | SPF/137/24-25 | 55820
373 | MITC Rolling Mills Pvt Ltd |  | 2024-10-05 | 2024-25/4194 | 2133860
374 | S K Traders |  | 2024-10-08 | SK/415/24-25 | 17789
375 | Anupam Hardware |  | 2024-10-10 | 08982 | 17044
376 | A Cube Stone World |  | 2024-10-14 | 17/2024-25 | 134909
377 | Salim Timber Corporation |  | 2024-10-14 | 319/2024-2025 | 182251
378 | Anupam Hardware |  | 2024-10-16 | 09221 | 30877
379 | Adarsh Enterprises |  | 2024-10-16 | 13 | 90034
380 | S K Traders |  | 2024-10-17 | SK/442/24-25 | 136038
381 | Ramkishan Prajapati |  | 2024-10-17 | 871 | 28050
382 | Aayush Enterprises |  | 2024-10-18 | 387 | 91863
383 | Saurabh Enterprise |  | 2024-10-20 | 260 | 5310
384 | MITC Rolling Mills Pvt Ltd |  | 2024-10-22 | 2024-25/4652 | 2268969
385 | Aayush Enterprises |  | 2024-10-22 | 395 | 18856
386 | Sudha Sales Corporation |  | 2024-10-22 | SSC/116 | 94400
387 | Anupam Hardware |  | 2024-10-22 | 09558 | 6817
388 | A Cube Stone World |  | 2024-10-22 | 20/2024-25 | 188414
389 | Ankit Plastic |  | 2024-10-25 | 029 | 28750
390 | Aetreum Concrete |  | 2024-11-01 | AC/24-25/0994 | 1848955
391 | Aetreum Concrete |  | 2024-11-01 | AC/24-25/1075 | 1775733
392 | Aetreum Concrete |  | 2024-11-01 | AC/24-25/1124 | 1703205
393 | Salim Timber Corporation |  | 2024-11-01 | 315/2024-2025 | 146037
394 | S K Traders |  | 2024-11-01 | SK/470/24-25 | 158981
395 | BMCC Enterprises |  | 2024-11-01 | 1670 | 172462
396 | S K Traders |  | 2024-11-01 | SK/489/24-25 | 15812
397 | Aetreum Concrete |  | 2024-11-01 | AC/24-25/1171 | 1792888
398 | Shabbir Pipe Fitting |  | 2024-11-01 | SPF/146/24-25 | 6107
399 | Shabbir Pipe Fitting |  | 2024-11-01 | SPF/145/24-25 | 67496
400 | Sudha Sales Corporation |  | 2024-11-02 | SSC/129 | 140020
401 | Sudha Sales Corporation |  | 2024-11-02 | SSC/130 | 17789
402 | Ankit Plastic |  | 2024-11-10 | 079 | 14400
403 | Aetreum Concrete |  | 2024-11-10 | AC/24-25/1245 | 98058
404 | Ramkishan Prajapati |  | 2024-11-11 | 901 | 6000
405 | Ankit Plastic |  | 2024-11-12 | 083 | 6600
406 | M R Pigeon Net |  | 2024-11-12 | 92 | 98490
407 | MITC Rolling Mills Pvt Ltd |  | 2024-11-13 | 2024-25/5141 | 1897859
408 | Maatangi Enterprises |  | 2024-11-15 | 434 | 126175
409 | S K Traders |  | 2024-11-17 | SK/523/24-25 | 173730
410 | Saurabh Enterprise |  | 2024-11-19 | 321 | 63838
411 | Oracle Granito Ltd. |  | 2024-11-19 | OGL/24-25/2544 | 25320
412 | Saurabh Enterprise |  | 2024-11-19 | 320 | 262.8
413 | Aayush Enterprises |  | 2024-11-21 | 450 | 14809
414 | Aayush Enterprises |  | 2024-11-24 | 460 | 91200
415 | Anupam Hardware |  | 2024-11-25 | 10889 | 4800
416 | S K Traders |  | 2024-11-26 | SK/540/24-25 | 4366
417 | S K Traders |  | 2024-11-26 | SK/542/24-25 | 104784
418 | Natural Stone Studio |  | 2024-12-01 | NSS/250/24-25 | 53865
419 | Aayush Enterprises |  | 2024-12-01 | 462 | 27494
420 | Aetreum Concrete |  | 2024-12-01 | AC/24-25/1306 | 1793718
421 | Aayush Enterprises |  | 2024-12-01 | 463 | 11623
422 | Ramkishan Prajapati |  | 2024-12-01 | 922 | 31650
423 | Oracle Granito Ltd. |  | 2024-12-01 | OGL/24-25/2679 | 614676
424 | Saurabh Enterprise |  | 2024-12-01 | 343 | 29677
425 | S K Traders |  | 2024-12-01 | SK/551/24-25 | 92630
426 | BMCC Enterprises |  | 2024-12-01 | 1720 | 169312
427 | Vintage Traders |  | 2024-12-01 | VT/24-25/257 | 148129
428 | Aetreum Concrete |  | 2024-12-01 | AC/24-25/1387 | 1399360
429 | Natural Stone Studio |  | 2024-12-01 | NSS/259/24-25 | 60861
430 | Anupam Hardware |  | 2024-12-02 | 11253 | 11399
431 | Anupam Hardware |  | 2024-12-02 | 11256 | 19920
432 | S V & CO |  | 2024-12-02 | 880/24-25 | 44604
433 | M R Pigeon Net |  | 2024-12-05 | 102 | 46271
434 | Aayush Enterprises |  | 2024-12-06 | 507 | 47790
435 | Neeraj Steel Sales |  | 2024-12-07 | 710/24-25 | 1985616
436 | Saurabh Enterprise |  | 2024-12-08 | 362 | 32273
437 | Aetreum Concrete |  | 2024-12-10 | AC/24-25/1458 | 300192
438 | S K Traders |  | 2024-12-10 | SK/580/24-25 | 300511
439 | Natural Stone Studio |  | 2024-12-10 | NSS/270/24-25 | 71709
440 | Anupam Hardware |  | 2024-12-11 | 11660 | 8354
441 | Aayush Enterprises |  | 2024-12-11 | 523 | 34539
442 | S K Traders |  | 2024-12-11 | SK/582/24-25 | 156038
443 | Natural Stone Studio |  | 2024-12-13 | NSS/273/24-25 | 96871
444 | S K Traders |  | 2024-12-14 | SK/603/24-25 | 15812
445 | Anupam Hardware |  | 2024-12-15 | 11836 | 17427
446 | Oracle Granito Ltd. |  | 2024-12-16 | OGL/24-25/2851 | 373143
447 | Oracle Granito Ltd. |  | 2024-12-18 | OGL/24-25/2868 | 690529
448 | A Cube Stone World |  | 2024-12-26 | 65/2024-25 | 765429
449 | Anupam Hardware |  | 2024-12-27 | 12384 | 10586
450 | Natural Stone Studio |  | 2024-12-28 | NSS/293/24-25 | 36558
451 | ANUPAM HARDWARE |  | 2024-12-31 | 12581 | 2755
452 | AETREUM CONCRETE |  | 2024-12-20 | AC/24-25/1559 | 707374
453 | AETREUM CONCRETE |  | 2024-12-31 | AC/24-25/1653 | 494966
454 | Aayush Enterprises |  | 2024-12-25 | 554 | 79803
455 | BMCC Enterprises |  | 2024-12-31 | 1789 | 141750
456 | Kone Elevator India Private Limited |  | 2024-10-01 |  | 626000
457 | Kone Elevator India Private Limited |  | 2024-10-01 |  | 625000
458 | Kone Elevator India Private Limited |  | 2024-10-01 |  | 661000
459 | RDC Concrete India Pvt Ltd |  | 2024-10-01 |  | 35960
460 | RDC Concrete India Pvt Ltd |  | 2024-10-01 |  | 8700
461 | R.R. Enterprises- Pumping Charges |  | 2024-10-01 |  | 73080
462 | Vinod Yadav ( Mathadi) |  | 2024-10-02 |  | 28363
463 | M R Pigeon Net |  | 2024-10-08 |  | 28326
464 | M K Power |  | 2024-10-09 |  | 113724
465 | Mahibuddin |  | 2024-10-14 |  | 11088
466 | Ganesh Enterprises |  | 2024-10-15 |  | 135630
467 | Riddhi P Shah |  | 2024-10-28 |  | 232650
468 | Poonam D Jha |  | 2024-11-01 |  | 40095
469 | Evolve Construction |  | 2024-11-01 |  | 5650000
470 | Evolve Construction |  | 2024-11-01 |  | 4204010
471 | Evolve Construction |  | 2024-11-01 |  | 3073998
472 | Vinod Yadav ( Mathadi) |  | 2024-11-05 |  | 33343
473 | Evolve Construction |  | 2024-11-21 |  | 5550000
474 | Umika Enterprises |  | 2024-12-01 |  | 26554
475 | Poonam D Jha |  | 2024-12-01 |  | 31185
476 | Vinod Yadav ( Mathadi) |  | 2024-12-03 |  | 16320
477 | Sagar Lift |  | 2024-12-11 |  | 121540
478 | Evolve Construction |  | 2024-12-26 |  | 10396000
479 | Firoz Khan |  | 31-Dec-24 |  | 15048
480 | Kone Elevator India Private Limited |  | 2024-12-07 | KEI/202423/6781511 | 27970720
481 | City Elevator Private Limited |  | 2024-12-07 | CEPL-RET-01826 | 25265034
482 | City Elevator Private Limited |  | 2024-12-07 | CEPL-RET-01830 | 11257200
483
484
485
486
487
488
489
490
491
492
493
| Total |  |  |  | 444214826.8

## Construction Area sale building
Sr. | Floor | Total Construction Area in Sq. M. | Completed Area in Sq. Ft. | Rate per Sq. Ft. | Full Value after completion | % of work completed | Actual Expenditure till date in `
1 | Exacavation Cost |  |  |  | 24608686 | 100% | 24608686
2 | Basement Floor | 438.7364 | 438.7364 | 30000 | 13162092 | 98% | 12898850.16
3 | Ground Floor | 486.0664 | 486.0664 | 30000 | 14581992 | 98% | 14290352.16
4 | 1st Floor | 514.0664 | 514.0664 | 30000 | 15421992 | 98% | 15113552.16
5 | 2nd Floor | 514.0664 | 514.0664 | 30000 | 15421992 | 98% | 15113552.16
6 | 3rd Floor | 514.0664 | 514.0664 | 30000 | 15421992 | 98% | 15113552.16
7 | 4th Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 65% | 8951989.8
8 | 5th Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 65% | 8951989.8
9 | 6th Floor | 465.64 | 465.64 | 30000 | 13969200 | 65% | 9079980
10 | 7th Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 69% | 9502881.48
11 | 8th Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 69% | 9502881.48
12 | 9th Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 69% | 9502881.48
13 | 10th Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 69% | 9502881.48
14 | 11th Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 68% | 9365158.56
15 | 12th Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 68% | 9365158.56
16 | 13th Floor | 465.64 | 465.64 | 30000 | 13969200 | 68% | 9499056
17 | 14th Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 68% | 9365158.56
18 | 15th Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 68% | 9365158.56
19 | 16th Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 60% | 8263375.2
20 | 17th Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 65% | 8951989.8
21 | 18th Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 60% | 8263375.2
22 | 19th Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 50% | 6886146
23 | 20th Floor | 468.19 | 468.19 | 30000 | 14045700 | 50% | 7022850
24 | 21st Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 50% | 6886146
25 | 22nd Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 50% | 6886146
26 | 23rd Floor | 459.0764 | 459.0764 | 30000 | 13772292 | 50% | 6886146
27 | 24th Floor | 460.45 | 230.225 | 30000 | 13813500 | 25% | 3453375
28 | 25th Floor | 460.45 |  | 30000 | 13813500
29 | 26th Floor | 460.45 |  | 30000 | 13813500
30 | 27th Floor | 467.98 |  | 30000 | 14039400
31 | 28th Floor | 462.33 |  | 30000 | 13869900
32 | 29th Floor | 462.33 |  | 30000 | 13869900
33 | 30th Floor | 462.33 |  | 30000 | 13869900
34 | 31st Floor | 462.33 |  | 30000 | 13869900
35 | 32nd Floor | 462.33 |  | 30000 | 13869900
36 | 33rd Floor | 459.65 |  | 30000 | 13789500
37 | Terrace / OHT | 114.39 |  | 30000 | 3431700
38 | Sub Total | 16405.7908 |  |  | 516782410 | 52.75% | 272593270
39 | Parking | 111 |  | 500000 | 55500000
TOTAL |  |  | 11900.9958 |  | 572282410 | 47.63% | 272593270
[6 empty] | 50.01% | 13625143 | MIVAN
[7 empty] | 40000000 | Material At Site
[6 empty] | 57% | 326218413
[7 empty] | 64492954 | Advance Payment
[6 empty] | 68.27% | 390711367

## Sheet1
Sr. No. | Vendor Name | Customer Name | Invoice Date | Invoice Number | Invoice Amount | Project Name | Description of Material
118 | Saurabh Enterprise | DGS Township Pvt Ltd | 2024-04-01 | 5 | 14444 | Sheetal Ekta | Sika Microcrete 4 & AP Apcocrete
119 | Umika Enterprises | DGS Township Pvt Ltd | 2024-04-02 | 2 | 54006 | Sheetal Ekta | 25 mm dia Coupler & 20 mm dia Coupler
120 | Umika Enterprises | DGS Township Pvt Ltd | 2024-04-03 | 4 | 129084 | Sheetal Ekta | Cold Forged Threading Both Side 20 mm dia, 25 mm dia, 32 mm dia & 20 mm dia oneside
121 | Umika Enterprises | DGS Township Pvt Ltd | 2024-04-03 | 3 | 84062 | Sheetal Ekta | 32 mm dia Cold Forged Coupler & 25 mm dia Cold Forged Coupler
122 | Saurabh Enterprise | DGS Township Pvt Ltd | 2024-04-08 | 15 | 21158 | Sheetal Ekta | Ap Cemcrete
123 | BMCC Enterprise | DGS Township Pvt Ltd | 2024-04-22 | 1278 | 61425 | Sheetal Ekta | Crush Sand, Metal Mix & Plaster Sand
124 | M R Pigeon Net | DGS Township Pvt Ltd | 2024-04-22 | 8 | 47381 | Sheetal Ekta | Agro Shade Net 75% BDL
125 | BMCC Enterprise | DGS Township Pvt Ltd | 2024-04-30 | 1295 | 45675 | Sheetal Ekta | C Sand, P Sand & Metal Mix
126 | Umika Enterprises | DGS Township Pvt Ltd | 2024-05-05 | 12 | 84039 | Sheetal Ekta | 20 mm dia Cold Forged Coupler, 25 mm dia Cold Forged Coupler, 32/25 mm dia reducer & 25/20 mm dia reducer
127 | Umika Enterprises | DGS Township Pvt Ltd | 2024-05-06 | 14 | 32096 | Sheetal Ekta | 25 mm dia Cold Forged Coupler
128 | Vintage Traders | DGS Township Pvt Ltd | 2024-05-06 | 047 | 148425 | Sheetal Ekta | Flyash Blocks & Joint Morter
129 | Umika Enterprises | DGS Township Pvt Ltd | 2024-05-10 | 16 | 48144 | Sheetal Ekta | 25 mm dia Cold Forged Coupler
130 | Anupam Hardware | DGS Township Pvt Ltd | 2024-05-13 | 01746 | 9947 | Sheetal Ekta | LED Flat Light & PVC Green Breded Pipe
131 | S. V. & Co. | DGS Township Pvt Ltd | 2024-05-14 | 83/24-25 | 3474 | Sheetal Ekta | Flexo Board
132 | B. Mittal & Co. | DGS Township Pvt Ltd | 2024-05-20 | BM24250082 | 2055284 | Sheetal Ekta | TMT Rebar
133 | BMCC Enterprise | DGS Township Pvt Ltd | 2024-05-24 | 1335 | 23310 | Sheetal Ekta | C Sand, P Sand & Metal Mix
134 | Anupam Hardware | DGS Township Pvt Ltd | 2024-05-25 | 02311 | 11862 | Sheetal Ekta | Pipe Easyfit SCH- 80 & others
135 | S K Traders | DGS Township Pvt Ltd | 2024-05-28 | SK/114/24-25 | 216742 | Sheetal Ekta | Aluminium Arm Cable & others
136 | B. Mittal & Co. | DGS Township Pvt Ltd | 2024-05-28 | BM24250104 | 1993876 | Sheetal Ekta | TMT Rebar
137 | Anupam Hardware | DGS Township Pvt Ltd | 2024-05-22 | 02158 | 20432 | Sheetal Ekta | Earthing Strip & others
138 | Salim Timber Corporation | DGS Township Pvt Ltd | 2024-05-16 | 82/2024-2025 | 8095 | Sheetal Ekta | Timbers Frame
139 | S K Traders | DGS Township Pvt Ltd | 2024-05-30 | SK/121/24-25 | 135828 | Sheetal Ekta | TUFF AAC Block
140 | S K Traders | DGS Township Pvt Ltd | 2024-05-27 | SK/115/24-25 | 41008 | Sheetal Ekta | Aluminium Lugs & others
141 | S K Traders | DGS Township Pvt Ltd | 2024-05-31 | SK/123/24-25 | 17464 | Sheetal Ekta | Mortar Tuff Easyfix
142 | Ramkishan Prajapati | DGS Township Pvt Ltd | 2024-06-01 | 755 | 27350 | Sheetal Ekta | 40 mm round & others
143 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-747 | 53808 | Sheetal Ekta | M60- Supercrete
144 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-748 | 53808 | Sheetal Ekta | M60- Supercrete
145 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-749 | 53808 | Sheetal Ekta | M60- Supercrete
146 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-750 | 53808 | Sheetal Ekta | M60- Supercrete
147 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-762 | 53808 | Sheetal Ekta | M60- Supercrete
148 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP1-783 | 53808 | Sheetal Ekta | M60- Supercrete
149 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-789 | 53808 | Sheetal Ekta | M60- Supercrete
150 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP1-786 | 53808 | Sheetal Ekta | M60- Supercrete
151 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-765 | 53808 | Sheetal Ekta | M60- Supercrete
152 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-764 | 53808 | Sheetal Ekta | M60- Supercrete
153 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-763 | 53808 | Sheetal Ekta | M60- Supercrete
154 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP2-746 | 53808 | Sheetal Ekta | M60- Supercrete
155 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-767 | 53808 | Sheetal Ekta | M60- Supercrete
156 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-768 | 53808 | Sheetal Ekta | M60- Supercrete
157 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-790 | 53808 | Sheetal Ekta | M60- Supercrete
158 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-794 | 53808 | Sheetal Ekta | M60- Supercrete
159 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-793 | 53808 | Sheetal Ekta | M60- Supercrete
160 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-769 | 53808 | Sheetal Ekta | M60- Supercrete
161 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-795 | 53808 | Sheetal Ekta | M60- Supercrete
162 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-770 | 53808 | Sheetal Ekta | M60- Supercrete
163 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-796 | 49324 | Sheetal Ekta | M60- Supercrete
164 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-797 | 53808 | Sheetal Ekta | M60- Supercrete
165 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-799 | 53808 | Sheetal Ekta | M60- Supercrete
166 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-771 | 53808 | Sheetal Ekta | M60- Supercrete
167 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-798 | 53808 | Sheetal Ekta | M60- Supercrete
168 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-772 | 53808 | Sheetal Ekta | M60- Supercrete
169 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-773 | 53808 | Sheetal Ekta | M60- Supercrete
170 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-800 | 53808 | Sheetal Ekta | M60- Supercrete
171 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-801 | 53808 | Sheetal Ekta | M60- Supercrete
172 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-802 | 53808 | Sheetal Ekta | M60- Supercrete
173 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-803 | 53808 | Sheetal Ekta | M60- Supercrete
174 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-806 | 53808 | Sheetal Ekta | M60- Supercrete
175 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP2-780 | 53808 | Sheetal Ekta | M60- Supercrete
176 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-807 | 53808 | Sheetal Ekta | M60- Supercrete
177 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-19 | 11MU24BP1-810 | 58292 | Sheetal Ekta | M60- Supercrete
178 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-05-18 | 11MU24BP1-787 | 53808 | Sheetal Ekta | M60- Supercrete
179 | Umika Enterprises | DGS Township Pvt Ltd | 2024-06-02 | 22 | 59354 | Sheetal Ekta | Cold Forged Coupler 20 mm dia, 25 mm dia & 32 mm dia
180 | Umika Enterprises | DGS Township Pvt Ltd | 2024-06-03 | 24 | 35140 | Sheetal Ekta | Cold Forged Coupler 25 mm dia & 32/25 mm dia
181 | Umika Enterprises | DGS Township Pvt Ltd | 2024-06-04 | 26 | 70179 | Sheetal Ekta | Cold Forged Coupler 20 mm dia, 25 mm dia & 25/20 mm dia
182 | Mahadev Traders | DGS Township Pvt Ltd | 2024-06-06 | 68 | 85054 | Sheetal Ekta | M. S. Binding Wire
183 | S. V. & Co. | DGS Township Pvt Ltd | 2024-06-10 | 187/24-25 | 10547 | Sheetal Ekta | Flexo Board & other
185 | Jai Durga Transport | DGS Township Pvt Ltd | 2024-04-01 | 4451 | 11800 | Sheetal Ekta | Boring Water
186 | Vinod Yadav | DGS Township Pvt Ltd | 2024-04-02 | 1010 | 14500 | Sheetal Ekta | Steel Shifting
187 | Evolve Construction | DGS Township Pvt Ltd | 2024-04-08 | 2/2024-25 | 11800000 | Sheetal Ekta | RA Bill 03
188 | Brahmadev | DGS Township Pvt Ltd | 2024-04-07 | 003 | 6720 | Sheetal Ekta | Meter room cement sheet
189 | Shravan Sahani | DGS Township Pvt Ltd | 2024-04-07 |  | 14400 | Sheetal Ekta | 12 Frame and others
190 | Rukmani G.Chouhan | DGS Township Pvt Ltd | 2024-04-16 |  | 4200 | Sheetal Ekta | Labour
191 | SRSBM Lab Testing Pvt.Ltd. | DGS Township Pvt Ltd | 2024-04-16 | MRT-27006 | 3304 | Sheetal Ekta | Concrete Cube ( Compressive Strength)
193 | Jai Durga Transport | DGS Township Pvt Ltd | 2024-05-01 | 4501 | 18000 | Sheetal Ekta | Boring Water, Drinking Water
194 | Poonam D. Jha | DGS Township Pvt Ltd | 2024-04-30 | 423 | 18000 | Sheetal Ekta | Rabbit
195 | Umika Enterprises | DGS Township Pvt Ltd | 2024-05-04 | 10 | 44259 | Sheetal Ekta | 25 mm dia cold forged one side , 25 mm dia forged both side, 20 mm dia forged
196 | Vinod Yadav | DGS Township Pvt Ltd | 2024-05-05 | 1012 | 14500 | Sheetal Ekta | Steel Shifting, Block
197 | Rajesh Singh Water pump hiring | DGS Township Pvt Ltd | 2024-05-14 | 598 | 5000 | Sheetal Ekta | HP Pump
198 | Rajesh Singh Water pump hiring | DGS Township Pvt Ltd | 2024-05-14 | 465 | 10000 | Sheetal Ekta | HP Pump
199 | Abhay Facility Service | DGS Township Pvt Ltd | 2024-06-01 | AFS/867/2024 | 92040 | Sheetal Ekta | Secuirty head guars, Liftman
202 | Jai Durga Transport | DGS Township Pvt Ltd | 2024-06-01 | 4551 | 42200 | Sheetal Ekta | Boring Water, Drinking Water
203 | Maharaja Enterprises | DGS Township Pvt Ltd | 2024-05-31 | 8330 | 7830 | Sheetal Ekta | Bottles
204 | Vinod Yadav | DGS Township Pvt Ltd | 2024-06-03 | 1013 | 29000 | Sheetal Ekta | Steel Shifting, Block
205 | Umika Enterprises | DGS Township Pvt Ltd | 2024-06-04 | 27 | 123715 | Sheetal Ekta | 25 mm dia cold forged one side , 25 mm dia forged both side, 20 mm dia forged, 32 mm dia forged
206 | Rajesh Singh Water pump hiring | DGS Township Pvt Ltd | 2024-06-16 | 630 | 5000 | Sheetal Ekta | HP Pump
207 | Janki Devi Prajapati | DGS Township Pvt Ltd | 2024-06-16 | 473 | 10100 | Sheetal Ekta | 40 mm round block, 25 mm square block, Transport charges
208 | Om Infrastrcuture | DGS Township Pvt Ltd | 2024-06-19 | OM/008/2024-25 | 15000000 | Sheetal Ekta | Labour Work
209 | Avenue Imperial Construction LLP | DGS Township Pvt Ltd | 2024-05-05 | DGS/AE/04/2024-25 | 15000000 | Sheetal Ekta | RCC Work of Building
210 | Mahibuddin | DGS Township Pvt Ltd | 2024-06-05 |  | 36235 | Sheetal Ekta | Labour Charges
211 | Saikat Mondal | DGS Township Pvt Ltd | 2024-06-05 | 790 | 7200 | Sheetal Ekta | glass sticker with pasting
212 | Saikat Mondal | DGS Township Pvt Ltd | 2024-06-05 | 785 | 81200 | Sheetal Ekta | Acrylic letter, Logo 2 pic
213 | Anupam Hardware | DGS Township Pvt Ltd | 2024-04-02 | 00059 | 6348 | Sheetal Ekta | Wires House Flex 1.5 SQ MM & others
214 | Shree Krushna Electrical & Hardware | DGS Township Pvt Ltd | 2024-04-10 | 370 | 13800 | Sheetal Ekta | Water Tank 2000 L & Tampo
215 | S K Traders | DGS Township Pvt Ltd | 2024-04-14 | SK/033/24-25 | 87552 | Sheetal Ekta | PPC Birla Shakti
216 | Maatangi Enterprises | DGS Township Pvt Ltd | 2024-04-15 | 385 | 10561 | Sheetal Ekta | Black Granite
217 | S K Traders | DGS Township Pvt Ltd | 2024-04-17 | SK/035/24-25 | 150866 | Sheetal Ekta | AAC Fly Ash Block & Magic Bond Joint Mortar
218 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-04-19 | ASC066/24-25 | 1945990 | Sheetal Ekta | TMT BARS 8 mm, 12 mm, 16 mm, 20 mm & 25 mm
219 | S K Traders | DGS Township Pvt Ltd | 2024-04-19 | SK/041/24-25 | 16184 | Sheetal Ekta | Reducer Socket MS ERW 80*40 mm & others
220 | S K Traders | DGS Township Pvt Ltd | 2024-04-22 | SK/047/24-25 | 36657 | Sheetal Ekta | Butterfly Valve & others
221 | Shree Krushna Electrical & Hardware | DGS Township Pvt Ltd | 2024-04-22 | 378 | 3580 | Sheetal Ekta | P Draw, 110 mm Albow & others
222 | Anupam Hardware | DGS Township Pvt Ltd | 2024-04-25 | 01036 | 19612 | Sheetal Ekta | Vertical Tank Black 2000 ltr & Others
223 | Saurabh Enterprise | DGS Township Pvt Ltd | 2024-04-27 | 51 | 24485 | Sheetal Ekta | AP Antihack
224 | Anupam Hardware | DGS Township Pvt Ltd | 2024-04-28 | 01136 | 24619 | Sheetal Ekta | Pump Mono Mik-22-18 2HP & Other
225 | Schindler India Pvt Ltd | DGS Township Pvt Ltd | 2024-04-29 | CI2700413089 | 147500 | Sheetal Ekta | Installation, Repair & Maintenance of Elevators & Escalators
226 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-04-09 | AC/24-25/0011 | 1995734 | Sheetal Ekta | M-60 Mivan & others
227 | Shree Krushna Electrical & Hardware | DGS Township Pvt Ltd | 2024-06-25 | 006 | 20300 | Sheetal Ekta | Tube Light, Flood light, Ploycab core, Metal Socket single phase
228 | Neeraj Steel Sales | DGS Township Pvt Ltd | 2024-06-08 | 203/24-25 | 2066752 | Sheetal Ekta | TMT BARS- 8mm, 10mm, 12mm, 16mm, 20mm, 25mm, 32mm
229 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-05-21 | 24-25/0011 | 5808 | Sheetal Ekta | Pumping Charges
233 | M R Pigeon Net | DGS Township Pvt Ltd | 2024-06-01 |  | 145 | Sheetal Ekta | TDS on Labour
239 | City Elevators Private Limited | DGS Township Pvt Ltd | 2024-06-05 |  | 86580 | Sheetal Ekta
241 | Anupam Hardware | DGS Township Pvt Ltd | 2024-06-21 |  | 46360 | Sheetal Ekta
244 | Anupam Hardware | DGS Township Pvt Ltd | 2024-05-23 |  | 46460 | Sheetal Ekta
247 | B S Fire Protection | DGS Township Pvt Ltd | 2024-05-10 |  | 590000 | Sheetal Ekta | Labour Charges
251 | Seema Dipak Alaskar | DGS Township Pvt Ltd | 2024-04-30 |  | 57842 | Sheetal Ekta | 08mm, 10mm, 12mm, 16mm & 20mm TMT Bars
252 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-04-30 |  | 492061 | Sheetal Ekta
253 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-04-30 |  | 467460 | Sheetal Ekta
254 | Saurabh Steel Corporation | DGS Township Pvt Ltd | 2024-04-30 |  | 615075 | Sheetal Ekta
258 | Shree Krushna Electrical & Hardware | DGS Township Pvt Ltd | 2024-04-09 |  | 14650 | Sheetal Ekta
259 | Mahakal Enterprises | DGS Township Pvt Ltd | 2024-04-30 |  | 584130 | Sheetal Ekta
267 | Bajarang Drilling | DGS Township Pvt Ltd | 2024-06-07 | 06 | 18337 | Sheetal Ekta | Bill for Core cutting, Drilling hole in RCC along with electric portable machine
292 | Poonam D. Jha | DGS Township Pvt Ltd | 2024-06-30 | 515 | 13500 | Sheetal Ekta | Rabbit
303 | Shri Krihsna Electrical & Hardware | DGS Township Pvt Ltd | 2024-06-30 | 014 | 695 | Sheetal Ekta | L Hall Pass & Anchor Faszar
307 | Aayush Enterprises | DGS Township Pvt Ltd | 2024-06-28 | 188 | 1392 | Sheetal Ekta | FAIBER MESH (HSN7019)
308 | Aetreum Concrete | DGS Township Pvt Ltd | 2024-06-10 | AC/24-25/0514 | 1951631 | Sheetal Ekta | M-60 MIVAN OPC Without Pump, M-60 MIVAN OPC With Pump, Pumping Charges
311 | BMCC Enterprise | DGS Township Pvt Ltd | 2024-06-28 | 1409 | 33075 | Sheetal Ekta | Plaster Sand, Metal Mix, Crush Sand
323 | R.R Enterprises | DGS Township Pvt Ltd | 2024-06-16 | 12 | 1997834 | Sheetal Ekta | RMC M-60 FREE FLOW, SLURRY
327 | Salim Timber Corporation | DGS Township Pvt Ltd | 2024-06-22 | 136/2024-2025 | 52510 | Sheetal Ekta | Timbers Frame
347 | R.R Enterprises | DGS Township Pvt Ltd | 2024-06-30 | 16 | 2027235 | Sheetal Ekta | RMC M-60 FREE FLOW, SLURRY
348 | Ramkishan Prajapati | DGS Township Pvt Ltd | 2024-06-15 | 770 | 40000 | Sheetal Ekta | RCC Chember cover with frame, 600x900, Transport
362 | Shabbir Pipe Fitting | DGS Township Pvt Ltd | 2024-06-15 | SPF/064/24-25 | 43176 | Sheetal Ekta | Steelman 6" G.I C Class
368 | Vintage Traders | DGS Township Pvt Ltd | 2024-06-18 | VT/24-25/36 | 143847 | Sheetal Ekta | Fly Ash Block, Joining Mortor
65831519

## Sheet2
Sr. No. | Vendor Name | Customer Name | Invoice Date | Invoice Number | Invoice Amount | Project Name | Description of Material
262 | A-1 Fabrication | DGS Township Pvt Ltd | 2024-09-06 | 0 | 229200 | Sheetal Ekta | Bill for Fabrication Work
263 | A-1 Fabrication | DGS Township Pvt Ltd | 2024-07-05 | 0 | 1001602 | Sheetal Ekta | Bill for Rolling Shutter
264 | Abhay Facility Service | DGS Township Pvt Ltd | 2024-07-01 | AFS/880/2024 | 78000 | Sheetal Ekta | 3 Guards & 3 Liftman
265 | Abhay Facility Service | DGS Township Pvt Ltd | 2024-08-01 | AFS/892/2024 | 78000 | Sheetal Ekta | 3 Guards & 3 Liftman
266 | Ahsan Shaikh | DGS Township Pvt Ltd | 2024-07-27 | 065 | 8000 | Sheetal Ekta | ACP Sheet White Colour With Red Pasting Size 18*18 inch
268 | Dr. Brijesh Singh | DGS Township Pvt Ltd | 2024-09-05 | RA-9 | 24000 | Sheetal Ekta | Periodic medical service for workers at site
269 | Abhay Facility Service | DGS Township Pvt Ltd | 2024-09-01 | AFS/608/2024 | 78000 | Sheetal Ekta | 3 Guards & 3 Liftman
270 | Bajarang Drilling | DGS Township Pvt Ltd | 2024-09-03 | 49 | 23803 | Sheetal Ekta | Bill for Drilling Grouting, Core cutting in RCC.
271 | Firoz Khan | DGS Township Pvt Ltd | 2024-09-07 | 164 | 34200 | Sheetal Ekta | Scafolding work in lift shaft from ground flr to 17th flr
272 | Gayatri Water Supplier & Co. | DGS Township Pvt Ltd | 2024-07-31 | 815 | 14400 | Sheetal Ekta | Bill for water supply
273 | Gayatri Water Supplier & Co. | DGS Township Pvt Ltd | 2024-07-31 | 814 | 1400 | Sheetal Ekta | Bill for water supply
274 | Kalesh L. Kamat | DGS Township Pvt Ltd | 2024-08-22 | 075 | 15084 | Sheetal Ekta | Main Door, Toilet Door & Moulding Cover Patti
275 | Mihir Water Suppliers | DGS Township Pvt Ltd | 2024-08-31 | 006 | 27000 | Sheetal Ekta | Boring Water
276 | Poonam D. Jha | DGS Township Pvt Ltd | 2024-08-22 | A000005 | 39800 | Sheetal Ekta | Rabbit
277 | Poonam D. Jha | DGS Township Pvt Ltd | 2024-08-31 | A000021 | 22500 | Sheetal Ekta | Rabbit
278 | Poonam D. Jha | DGS Township Pvt Ltd | 2024-07-31 | 554 | 27000 | Sheetal Ekta | Rabbit
279 | Rajesh Singh Water pump hiring | DGS Township Pvt Ltd | 2024-07-20 | 898 | 2500 | Sheetal Ekta | Dewatering Charges
280 | Rajesh Singh Water pump hiring | DGS Township Pvt Ltd | 2024-09-10 | 1074 | 3780 | Sheetal Ekta | Dewatering Charges
281 | R.R. Enterprises | DGS Township Pvt Ltd | 2024-07-15 | 18 | 75048 | Sheetal Ekta | Pipeline Fitting Charges
282 | R.R. Enterprises | DGS Township Pvt Ltd | 2024-08-07 | 21 | 11800 | Sheetal Ekta | Ideal Charges
283 | Sagar Lifts | DGS Township Pvt Ltd | 2024-08-06 | SL/462/24-25 | 121540 | Sheetal Ekta | Supply, installation, testing & commissioning of Man & Material lift
284 | T. H. Construction | DGS Township Pvt Ltd | 2024-08-19 | 158 | 29040 | Sheetal Ekta | Bill for Gate- 2 fixing, Chapra fixing at sales office, Gate fixing at 6th flr, Side parking staireareas
285 | T. H. Construction | DGS Township Pvt Ltd | 2024-08-19 | 159 | 19629 | Sheetal Ekta | 5 room entrance door fixing, 5 penel room door fixing
286 | The All Inside Decorators | DGS Township Pvt Ltd | 2024-09-03 | RA-1 | 698590 | Sheetal Ekta | Bill for Gypsum work with material and labour charge.
287 | Umika Enterprises | DGS Township Pvt Ltd | 2024-08-04 | 45 | 132254 | Sheetal Ekta | Labour Work
288 | Vinod Yadav | DGS Township Pvt Ltd | 2024-09-03 | 1016 | 38750 | Sheetal Ekta | Steel shifting & Block
289 | Evolve Construction | DGS Township Pvt Ltd | 2024-08-21 | 122422727543748 | 11800000 | Sheetal Ekta | RA Bill 07
290 | Gayatri Water Supplier & Co. | DGS Township Pvt Ltd | 2024-08-31 | 844 | 33600 | Sheetal Ekta | Bill for water supply
291 | Jai Durga Transport | DGS Township Pvt Ltd | 2024-07-01 | 4608 | 34800 | Sheetal Ekta | Bill for 10000 Ltrs Boring Water & 2000 Ltrs Drinking Water
293 | R.R. Enterprises | DGS Township Pvt Ltd | 2024-07-01 | 13 | 70800 | Sheetal Ekta | Ideal Charges, RMC Pump Charges & Extra Qty Pumping Charges
294 | Sagar Lifts | DGS Township Pvt Ltd | 2024-09-20 | SL/646/24-25 | 364620 | Sheetal Ekta | Supply, installation & commissioning of construction purpose Man & Material lift
295 | Sagar Lifts | DGS Township Pvt Ltd | 2024-09-13 | SL/622/24-25 | 607700 | Sheetal Ekta | Supply, installation & commissioning of construction purpose Man & Material lift
296 | Shri Krihsna Electrical & Hardware | DGS Township Pvt Ltd | 2024-07-25 | 030 | 2162 | Sheetal Ekta | CSK 38*8
297 | Shri Krihsna Electrical & Hardware | DGS Township Pvt Ltd | 2024-07-27 | 032 | 3400 | Sheetal Ekta | Aral dite & Fevikwik
298 | Shri Krihsna Electrical & Hardware | DGS Township Pvt Ltd | 2024-07-21 | 025 | 5340 | Sheetal Ekta | 12*30 Tad Patry Transport
299 | R.R. Enterprises | DGS Township Pvt Ltd | 2024-07-31 | 25 | 94990 | Sheetal Ekta | Ideal Charges, RMC Pump Charges & Extra Qty Pumping Charges
300 | R.R. Enterprises | DGS Township Pvt Ltd | 2024-07-01 | 17 | 71390 | Sheetal Ekta | Ideal Charges, RMC Pump Charges & Extra Qty Pumping Charges
301 | Umika Enterprises | DGS Township Pvt Ltd | 2024-07-08 | 37 | 173275 | Sheetal Ekta | Labour Work
302 | Shravan Sahani | DGS Township Pvt Ltd | 2024-09-24 | 0 | 6000 | Sheetal Ekta | Bill for Material Purpose
304 | SRSBM Lab Testing Pvt.Ltd. | DGS Township Pvt Ltd | 2024-09-18 | MRT-27962/1 | 1652 | Sheetal Ekta | Concrete Cube ( Compressive Strength)
305 | Vinod Yadav | DGS Township Pvt Ltd | 2024-07-02 | 1014 | 28030 | Sheetal Ekta | Steel Shifting, Block, Cement & Pipe Shifting
306 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-09-09 | ASC532/24-25 | 7146 | Sheetal Ekta | M.S Pipe (73066100)
309 | Anupam Hardware | DGS Township Pvt Ltd | 2024-09-22 | 08028 | 21236 | Sheetal Ekta | Nylon frame screw 10x120MM, Roofing Nails 2.5 KG 1.1/2", Pump Dewatering STPM(I)-15 2HP^Cropmtion
310 | B. Mittal & Co. | DGS Township Pvt Ltd | 2024-07-02 | BM24250158 | 2275158 | Sheetal Ekta | TMT REBAR- 8MM, 10MM, 12MM, 16MM, 20MM, 25MM
312 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-07-29 | ASC407/24-25 | 1806201 | Sheetal Ekta | TMT BARS- 8MM, 10MM, 12MM, 16MM, 20MM, 25MM
313 | Aarti Steel Corporation | DGS Township Pvt Ltd | 2024-07-29 | ASC408/24-26 | 81076 | Sheetal Ekta | M.S. Wire
315 | Aayush Enterprises | DGS Township Pvt Ltd | 2024-08-07 | 259 | 16201 | Sheetal Ekta | MAGNI GROUT
317 | Anupam Hardware | DGS Township Pvt Ltd | 2024-09-03 | 07263 | 72669 | Sheetal Ekta | Electronics Items, Transport Charges
318 | BMCC Enterprise | DGS Township Pvt Ltd | 2024-07-31 | 1483 | 161700 | Sheetal Ekta | Plaster Sand, Metal Mix, Crush Sand
319 | Maatangi Enterprises | DGS Township Pvt Ltd | 2024-07-31 | 407 | 11890 | Sheetal Ekta | Black Granite
320 | Ramkishan Prajapati | DGS Township Pvt Ltd | 2024-07-15 | 792 | 9650 | Sheetal Ekta | 40 mm round, 30 mm round, Transport Charges
321 | R.R Enterprises | DGS Township Pvt Ltd | 2024-07-31 | 25 | 11800 | Sheetal Ekta | Ideal Charges ( Pump)
322 | R.R Enterprises | DGS Township Pvt Ltd | 2024-07-31 | 24 | 1983835 | Sheetal Ekta | RMC M-60 FREE FLOW
324 | R.R Enterprises | DGS Township Pvt Ltd | 2024-07-15 | 19 | 1863432 | Sheetal Ekta | RMC M-60 FREE FLOW, SLURRY
325 | R.R Enterprises | DGS Township Pvt Ltd | 2024-07-15 | 20 | 21740 | Sheetal Ekta | RMC M-60 FREE FLOW, SLURRY, Under Loading Charges
326 | Rushabh Trading Co. | DGS Township Pvt Ltd | 2024-08-31 | 113 | 9656 | Sheetal Ekta | Rubble
328 | Salim Timber Corporation | DGS Township Pvt Ltd | 2024-07-09 | 153/2024-2025 | 97090 | Sheetal Ekta | Timbers Frame & Timbers Frame
329 | Salim Timber Corporation | DGS Township Pvt Ltd | 2024-07-11 | 162/2024-2025 | 101209 | Sheetal Ekta | Timbers Frame & Timbers Frame
330 | Shabbir Pipe Fitting | DGS Township Pvt Ltd | 2024-07-28 | SPF/089/24-25 | 3965 | Sheetal Ekta | Chair Bracket
331 | Shabbir Pipe Fitting | DGS Township Pvt Ltd | 2024-08-02 | SPF/093/24-25 | 21559 | Sheetal Ekta | Metropole Flush Value, Concealed Stopcock
332 | S K Traders | DGS Township Pvt Ltd | 2024-08-19 | SK/276/24-25 | 15812 | Sheetal Ekta | Block Joining Mortor
333 | S K Traders | DGS Township Pvt Ltd | 2024-08-20 | SK/279/24-25 | 70400 | Sheetal Ekta | PPC Birla Shakti
334 | S K Traders | DGS Township Pvt Ltd | 2024-08-24 | SK/290/24-25 | 120316 | Sheetal Ekta | AAC Fly Ash Block
335 | S K Traders | DGS Township Pvt Ltd | 2024-08-24 | SK/291/24-25 | 15812 | Sheetal Ekta | Block Joining Mortor
336 | S K Traders | DGS Township Pvt Ltd | 2024-08-29 | SK/307/24-25 | 119280 | Sheetal Ekta | AAC Fly Ash Block
337 | S K Traders | DGS Township Pvt Ltd | 2024-08-29 | SK/308/24-25 | 11859 | Sheetal Ekta | Block Joining Mortor
338 | S K Traders | DGS Township Pvt Ltd | 2024-09-04 | SK/324/24-25 | 118564 | Sheetal Ekta | AAC Fly Ash Block
339 | S K Traders | DGS Township Pvt Ltd | 2024-09-04 | SK/325/24-25 | 15812 | Sheetal Ekta | Block Joining Mortor
340 | Umika Enterprises | DGS Township Pvt Ltd | 2024-08-02 | 42 | 57112 | Sheetal Ekta | Cold Forged Coupler- 20 mm, 25 mm, 32 mm
341 | Umika Enterprises | DGS Township Pvt Ltd | 2024-08-03 | 43 | 89444 | Sheetal Ekta | Cold Forged Coupler- 20 mm, 25 mm, 32 mm , 32 & 25 mm reducer, 20 & 25 mm reducer
342 | Umika Enterprises | DGS Township Pvt Ltd | 2024-08-04 | 44 | 88854 | Sheetal Ekta | Cold Forged Coupler- 20 mm, 25 mm, 20/25 mm
343 | Vintage Traders | DGS Township Pvt Ltd | 2024-07-15 | VT/24-25/57 | 155396 | Sheetal Ekta | Flaysh blocks, Joint Morter
344 | Swati Industries | DGS Township Pvt Ltd | 2024-09-16 | SI/531/2024-25 | 2767 | Sheetal Ekta | Udyogi Ventilation White Helmet, Grey Udyogi Vent helmet HD, Safety Green Jacket 2" Pati
345 | M.R Pigeon Net | DGS Township Pvt Ltd | 2024-07-01 | 26 | 48951 | Sheetal Ekta | Agro Shade Net 75% BDL, Labour Charges
346 | Mahadev Traders | DGS Township Pvt Ltd | 2024-07-04 | 99 | 39318 | Sheetal Ekta | M.S Binding Wire
349 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-09-01 | 11MU23BP1-3367 | 27435 | Sheetal Ekta | M60- Supercrete
350 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-09-01 | 11MU23BP1-4840 | 27435 | Sheetal Ekta | M60-Mivan
351 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-09-01 | 11MU23BP1-4846 | 50298 | Sheetal Ekta | M60-Mivan
352 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-09-01 | 11MU23BP2-563 | 54870 | Sheetal Ekta | M60- Supercrete
353 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-09-01 | 11MU23BP2-578 | 45725 | Sheetal Ekta | M60- Supercrete
354 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-09-01 | 11MU23BP2-583 | 54870 | Sheetal Ekta | M60- Supercrete
355 | RDC Concrete (India) Pvt Ltd | DGS Township Pvt Ltd | 2024-09-01 | 11MU23BP2-591 | 41152 | Sheetal Ekta | M60- Supercrete
357 | S K Traders | DGS Township Pvt Ltd | 2024-07-04 | SK/180/24-25 | 72960 | Sheetal Ekta | PPC Birla Shakti
358 | S. V. & Co. | DGS Township Pvt Ltd | 2024-08-05 | 363/24-25 | 82128 | Sheetal Ekta | Doors, Teakwood Sawn sizes
359 | Salim Timber Corporation | DGS Township Pvt Ltd | 2024-09-05 | 268/2024-25 | 37760 | Sheetal Ekta | Timbers Frame
360 | Saurabh Enterprise | DGS Township Pvt Ltd | 2024-09-19 | 211 | 28828 | Sheetal Ekta | Ap Cemcrete, Faiber Mesh
361 | Saurabh Enterprise | DGS Township Pvt Ltd | 2024-09-21 | 213 | 15517 | Sheetal Ekta | Faimate Flowgrout 60, 25 kg pack
363 | B. Mittal & Co. | DGS Township Pvt Ltd | 2024-07-16 | BM24250179 | 1907832 | Sheetal Ekta | TMT REBAR- 8MM, 10MM, 12MM, 16MM, 20MM, 25MM
364 | BMCC Enterprise | DGS Township Pvt Ltd | 2024-08-31 | 1539 | 85050 | Sheetal Ekta | C. Sand, Mix Metal, River Sand
365 | S K Traders | DGS Township Pvt Ltd | 2024-09-16 | SK/363/24-25 | 15812 | Sheetal Ekta | Block Fix Mortar
366 | Sudha Sales Corporation | DGS Township Pvt Ltd | 2024-09-23 | SSC/084 | 75520 | Sheetal Ekta | M. P Birla Shakti Cement
367 | Umika Enterprises | DGS Township Pvt Ltd | 2024-07-09 | 40 | 101930 | Sheetal Ekta | Cold Forged Coupler- 32/25 mm, 20 mm, 25 mm, 20/25 mm
373 | Evolve Construction | DGS Township Pvt Ltd | 2024-07-05 | 18/2024-25 | 256256 | Sheetal Ekta | Retaintion Money
374 | Maharaja Enterprises | DGS Township Pvt Ltd | 2024-08-01 | 8447 | 7250 | Sheetal Ekta | Water Charges
375 | Maharaja Enterprises | DGS Township Pvt Ltd | 2024-08-01 | 8375 | 9570 | Sheetal Ekta | Water Charges
376 | Vinod Yadav | DGS Township Pvt Ltd | 2024-08-03 | 1015 | 36575 | Sheetal Ekta | Mathadi
377 | Vruddhi Engineering Works Ltd | DGS Township Pvt Ltd | 2024-08-07 | VSL/23-24/458 | 40184 | Sheetal Ekta | Steel bar threading charges
378 | City Elevators Private Limited | DGS Township Pvt Ltd | 2024-08-13 | CEPL/08/25/E/10 | 5108220 | Sheetal Ekta | Installation charges Parking Supply, Installation, Testing & Commissioning of tower parking system
33862766