## Final Summary
Project expenses | Estimated Cost as per Cost Vetting | Incurred Cost as per Bill till 31.12.2024 | Incurred Cost as per CA till 31.12.2024 | Incurred Cost as per Bill till 30.09.2024 | Incurred Cost as per CA till 30.09.2024 | Difference between the Bills & CA | Difference between both the Bills | Difference between both CA | Remark
Land Cost | 36.8 | 36.7957 | 36.8 | 36.7957 | 36.8 | -0.00431 | 0 | 0
Rent Cost | 3.85 | 5.2959 | 5.15 | 5.2959 | 5.15 | 0.14589 | 0 | 0
Construction Cost of Rehab & Amenity Building | 48.5 | 47.083 | 46.85 | 38.836 | 38.97 | 0.23304 | 8.2471 | 7.88
Construction Cost of Sale Building | 117.27
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 32.43 | 29.57 | 30.06 | 29.5474 | 30.04 | -0.48996 | 0.022608 | 0.02
Architect Cost, RCC & other Professional fees | 8.29 | 2.7344 | 2.65 | 2.7131 | 2.65 | 0.084364 | 0.021254 | 0
Administrative Expenses | 6.63 | 5.1492 | 14.32 | 4.6056 | 11.96 | 3.9199 | 0.54358 | 2.36
Marketing Expences | 16.77 | 13.0907 |  | 11.0568 |  |  | 2.0339
Interest Cost | 50 | 4.2778 | 4.26 | 3.2519 | 3.23 | 0.017803 | 1.0259 | 1.03
Contingency Cost | 4.97 | 0 | 4.36 | 0 | 0 | -4.36 | 0 | 4.36
Total Cost | 325.51 | 143.9967 | 144.45 | 132.1024 | 128.8 | -0.45326 | 11.8943 | 15.65
|  | 181.5133 | -0.45326 | 44.38% | 3.3024
Particulars | Revised Estimated Cost (in Cr.) | 31.12.2024 as per Bill Tally (inclusive of GST) | Cost incurred as %age total cost of that Component | Cost incurred as %age of cost incurred as on 31.12.2024
Land Cost | 36.8 | 36.7957 | 99.99% | 11.3%
Rent Cost | 3.85 | 5.2959 | 137.6% | 1.627%
Construction Cost of Rehab & Amenity Building | 48.5 | 47.083 | 28.4% | 14.46%
Construction Cost of Sale Building | 117.27
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 32.43 | 29.57 | 91.18% | 9.084%
Architect Cost, RCC & other Professional fees | 8.29 | 2.7344 | 32.98% | 0.84%
Administrative Expenses | 6.63 | 5.1492 | 77.67% | 1.582%
Marketing Expences | 16.77 | 13.0907 | 78.06% | 4.022%
Interest Cost | 50 | 4.2778 | 8.556% | 1.314%
Contingency Cost | 4.97 | 0 | 0% | 0%
Total | 325.51 | 143.9967 | 44.24% | 44.24%
Pariculars | 31.12.2024 as per Bill Tally (inclusive of GST) | 30.09.2024 as per Bill Tally (inclusive of GST) | Difference b/w bills of 30.09.2024 & 31.12.2024 | Difference of Cost incurred as %age of cost incurred as on 30.09.2024 & 31.12.2024
Land Cost | 36.7957 | 36.7957 | 0 | 0%
Rent Cost | 5.2959 | 5.2959 | 0 | 0%
Construction Cost of Rehab & Amenity Building | 47.083 | 38.836 | 8.25 | 5.729%
Construction Cost of Sale Building
Approval Cost Of Fungible Cost & Development cess premium & Stamp Duty | 29.57 | 29.5474 | 0.02 | 0.01389%
Architect Cost, RCC & other Professional fees | 2.7344 | 2.7131 | 0.02 | 0.01389%
Administrative Expenses | 5.1492 | 4.6056 | 0.54 | 0.375%
Marketing Expences | 13.0907 | 11.0568 | 2.03 | 1.41%
Interest Cost | 4.2778 | 3.2519 | 1.03 | 0.7153%
Contingency Cost | 0 | 4.36 | -4.36 | -3.028%
Total | 143.9967 | 136.4624 | 7.53 | 5.229%

## Summary Sheet
Sr. No. | Particulars | Incurred Cost in ` till 31.12.2024 | Incurred Cost in ` Cr. Till 31.12.2024 | Incurred Cost in ` till 30.09.2024 | Incurred Cost in ` Cr. Till 30.09.2024 | Balance in ` | Balance in ` Cr.
1 | Land Cost | 367956900 | 36.7957 | 367956900 | 36.7957 | 0 | 0
2 | Rent Cost | 52958946 | 5.2959 | 52958946 | 5.2959 | 0 | 0
3 | Construction Cost of Rehab & Amenity Building | 470830354 | 47.083 | 388359536 | 38.836 | 82470818 | 8.2471
4 | Construction Cost of Sale Building
5 | Approval Cost & Stamp Duty | 295700360 | 29.57 | 295474280 | 29.5474 | 226080 | 0.022608
6 | Professional Cost | 27343641 | 2.7344 | 27131105 | 2.7131 | 212536 | 0.021254
7 | Admin Cost | 51492263.97 | 5.1492 | 46056475 | 4.6056 | 5435788.97 | 0.54358
8 | Marketing Cost | 130906933.06 | 13.0907 | 110568115 | 11.0568 | 20338818.06 | 2.0339
9 | Interest Cost | 42778031 | 4.2778 | 32518577 | 3.2519 | 10259454 | 1.0259
| Total | 1439967429.03 | 143.9967 | 1321023934 | 132.1024 | 118943495.03 | 11.8943
500000000
457221969
|  | 1029232498.03 | 102.9232 | 920548457 | 92.0548 | 108684041.03 | 10.8684

## Land, Stamp Duty and rent c (2)
Stamp Duty & Registration Fees
Sr. No. | Agreement Name | Date | Particulars | Amount | Incurred Amount
1 | Conveyance Deed | 21.12.2018 | Purchase Cost | 350400000 | 350400000
2 |  |  | Stamp Duty | 17520000 | 17520000 | Sr. No. | Particulars
3 |  |  | Reg. Fees | 30000 | 30000 | 1 | No. of Tenants | 58 | Nos
4 |  |  |  | 1900 | 1900 | 2 | No. of Half Loft Tenant | 38 | Nos
5 | Confirmation Deed | 03.04.2019 | Stamp Duty | 500 | 500 | 3 | No. of Full Loft Tenant | 6 | Nos
6 |  |  | Reg. Fees | 1900 | 1900 | 4 | Rent Per Month (Jan 22 to Dec 22) Per Tenant | 16000 | Rupees
7 |  |  |  | 100 | 100 | 5 | Rent per Year (Jan to Dec 22) | 11136000 | Rupees
5 | Rectification Deed | 22.06.2019 | Stamp Duty | 500 | 500 | 6 | Rent per Month (Jan 23 to Dec 23) | 17000 | Rupees
6 |  |  | Reg. Fees | 1900 | 1900 | 7 | Rent per Year (Jan to Dec 23) | 11832000 | Rupees
7 |  |  |  | 100 | 100 | 8 | Rent per Month (Jan 24 to Jun 24) | 18000 | Rupees
| TOTAL |  |  | 367956900 | 367956900 | 9 | Rent per Year (Jan to Jun 24) | 12528000 | Rupees
[6 empty] | 10 | Rent for Full Loft per Tenant | 60000 | Rupees
[6 empty] | 11 | Rent for Full Loft | 360000 | Rupees
[6 empty] | 12 | Rent for Half Loft per tenant | 15000 | Rupees
[6 empty] | 13 | Rent for Half Loft | 570000 | Rupees
[6 empty] | 14 | Shifting Cost per Tenant | 20000 | Rupees
[6 empty] | 15 | Shifting Cost | 1160000 | Rupees
[6 empty] | 16 | Brokerage Cost | 928000 | Rupees
[6 empty] | 17 | TOTAL RENT COST | 38514000 | Rupees

## Rent Cost
|  |  | TOTAL | Till July 2023 | 2023-08-01 | 2023-09-01 | Oct - Dec 23 | Jan - Mar 24 | April - May 24 | 2024-06-01
1 | ANANDI SHANTARAM GAWADE | COMPENSATION | 925000 | 322000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
2 | Anant Shivram Surve | COMPENSATION | 865000 | 262000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
3 | Ankush Shivram Parab | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
4 | Ashadevi Sudama Prasad Mourya | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
5 | Ashok Sakharam Mulik | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
6 | Awadhraj Majadhar Pal | COMPENSATION | 925000 | 322000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
7 | Babbuprasad Amrutlal Gupta | COMPENSATION | 1140000 | 243000 | 17000 | 328000 | 34000 | 51000 | 53000 | 414000
8 | Babulal Jagnarayan Pal | COMPENSATION | 892921 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 426921
9 | Balaram Dagdu Pawar | COMPENSATION | 865000 | 262000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
10 | Bansh Bahadur Dayaram Singh | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
11 | Bhanupratap Ramnaresh Mishra | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
12 | Brahmacharya Dayashankar Shukla | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
13 | Chotelal Tapashi Goud | COMPENSATION | 771000 | 277000 | 17000 | 34000 | 34000 | 97000 | 36000 | 276000
14 | Dattaram Harischandra Dicholkar | COMPENSATION | 880075 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414075
15 | Dhondu Sahdev Katkar | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
16 | DILIP MANOHAR PISE | COMPENSATION | 865000 | 262000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
17 | Dinanath Chandan Prasad Dubey | COMPENSATION | 846000 | 243000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
18 | Doodhnath Awadhnarayan Singh | COMPENSATION | 451028 | 262000 | 17000 | 34000 | 34000 | 51000 | 53000 | 28
19 | Fayaram Baliraj Yadav | COMPENSATION | 928030 | 322000 | 17000 | 34000 | 34000 | 51000 | 53000 | 417030
20 | Ganpat Vishnu Sonar | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
21 | Hargovind Lalbahadur Singh | COMPENSATION | 846000 | 243000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
22 | Harinath Chandanprasad Dubey | COMPENSATION | 511002 | 322000 | 17000 | 34000 | 34000 | 51000 | 53000 | 2
23 | Jahraji Devi Yadav | COMPENSATION | 865000 | 262000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
24 | Kashiram Tukaram Dhumal | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
25 | Kewala Prasad Mishra | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
26 | Manojkumar Awadhraj Pal | COMPENSATION | 925000 | 322000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
27 | Matru Jangee Yadav | COMPENSATION | 930945 | 322000 | 17000 | 34000 | 34000 | 51000 | 53000 | 419945
28 | Mukesh Ganpat Sonar | COMPENSATION | 865000 | 262000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
29 | MURARI FAYARAM YADAV | COMPENSATION | 928129.62 | 322000 | 17000 | 34000 | 34000 | 51000 | 53000 | 417129.62
30 | Parvati Shilajeet Thakur | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
31 | Pawan Kumar Ojha | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
32 | Phulavatidevi | COMPENSATION | 846000 | 243000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
33 | Pradeep Manohar Pise | COMPENSATION | 1271000 | 668000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
34 | Pragati Prakash Shiringarpure | COMPENSATION | 1271000 | 668000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
35 | Prashant Vasant Gawde | COMPENSATION | 1042000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 576000
36 | Prathmesh Shankar Juwale | COMPENSATION | 1027000 | 262000 | 17000 | 34000 | 34000 | 51000 | 53000 | 576000
37 | Pruthvi Sahadev Pal | COMPENSATION | 831000 | 228000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
38 | Rajbali Sahadev Pal | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
39 | Rajkumari Gulabchand Shukla | COMPENSATION | 846000 | 243000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
40 | Rajpati Shivprasad Varma | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
41 | Ramadevi Amrutlal Gupta | COMPENSATION | 865000 | 262000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
42 | Ramadhar Dalmal Yadav | COMPENSATION | 883030.23 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 417030.23
43 | Ramesh Anant Kulkarni | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
44 | Ramkumar Rammurat Yadav | COMPENSATION | 925000 | 322000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
45 | RAMRAJ RAMJIVAN PAL | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
46 | Ravinath Santaram More | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
47 | Sanjay Atma Prasad Mishra | COMPENSATION | 884200 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 418200
48 | Santosh Chintaman Juwale | COMPENSATION | 897083 | 277000 | 34000 | 34000 | 34000 | 51000 | 53000 | 414083
49 | Satyendra Dharmdev Pal | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
50 | Shankar Chintaman Juwale | COMPENSATION | 914000 | 277000 | 51000 | 34000 | 34000 | 51000 | 53000 | 414000
51 | Shivprasad Sitlaprasad Dubey | COMPENSATION | 880000 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
52 | SHUBHANGI D. TULASKAR | COMPENSATION | 863000 | 260000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
53 | Shubhangi Sahdev Kande | COMPENSATION | 880502 | 277000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414502
54 | SRAVAN RAM | COMPENSATION | 891000 | 288000 | 17000 | 34000 | 34000 | 51000 | 53000 | 414000
55 | Sulochana Suryakant Devalkar | COMPENSATION | 863000 | 277000 |  | 34000 | 34000 | 51000 | 53000 | 414000
56 | SUSHILA AMRESH YADAV | COMPENSATION | 840000 | 322000 |  |  |  | 51000 | 53000 | 414000
57 | Vasant Bhaskar Naik | COMPENSATION | 1105000 | 277000 | [5 empty] | 828000
58 | Vasanti Santaram Ghag | COMPENSATION | 691000 | 277000 | [5 empty] | 414000
59 | GULAB CHAND SHUKLA | COMPENSATION | 448000 | 34000 | [5 empty] | 414000
60 | KALINDRI HARIGOVIND SINGH | COMPENSATION | 448000 | 34000 | [5 empty] | 414000
61 | PHULAVATI DAYARAM MOURY | COMPENSATION | 448000 | 34000 | [5 empty] | 414000
62 | Prathvi Sehdev Pal | COMPENSATION | 34000 | 34000
0
0
0
|  |  | 52958945.85 | 17044000 | 969000 | 2164000 | 1870000 | 2902000 | 2951000 | 25058945.85

## TDR & Approval
SR.NO | PARTICULARS | NATURE | DATE | TOTAL AMOUNT
1 | MUNICIPAL TAXES & OTHER CHARGES | CFO SCRUNITY FEES | 2018-12-28 | 1522992
2 | MUNICIPAL TAXES & OTHER CHARGES | REIMBURSEMENT OF FEES | 2020-01-29 | 2420
3 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2020-10-09 | 4000
4 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2020-10-15 | 220000
5 | MUNICIPAL TAXES & OTHER CHARGES | SCRUNITY FEES | 2020-12-14 | 1028581
6 | MUNICIPAL TAXES & OTHER CHARGES | RBI FUND MUMBAI | 2021-03-31 | 280000
7 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-07-21 | 1710000
8 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-08-12 | 36500
9 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-08-12 | 59000
10 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-08-12 | 9000
11 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-08-12 | 19000
12 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-08-12 | 199000
13 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-08-12 | 210100
14 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-08-12 | 20393670
15 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-08-12 | 6742725
16 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-08-12 | 750000
17 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-08-12 | 5000
18 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2021-08-12 | 4425
19 | MUNICIPAL TAXES & OTHER CHARGES | PAY ORDER REHAB 1 POONAM NAGAR | 2021-09-28 | 2874800
20 | MUNICIPAL TAXES & OTHER CHARGES | PAY ORDER POONAM NAGAR | 2021-10-01 | 564800
21 | MUNICIPAL TAXES & OTHER CHARGES | PAYORDER FOR DEMARCATION | 2021-10-29 | 9420
22 | MUNICIPAL TAXES & OTHER CHARGES | PAY ORDER FOR SRA POONAM NAGAR | 2021-12-04 | 55095105
23 | MUNICIPAL TAXES & OTHER CHARGES | PAY ORDER FOR SRA POONAM NAGAR | 2022-04-19 | 200000
24 | MUNICIPAL TAXES & OTHER CHARGES | PAID TO SCRUTINY FEES | 2022-06-17 | 700000
25 | MUNICIPAL TAXES & OTHER CHARGES | CREDIT CARD FOR AIRPORT AUTHORITY OF INDIA. | 2022-08-06 | 236000
26 | MUNICIPAL TAXES & OTHER CHARGES | ONLINE PAYMENT MADE TO GRASS | 2022-08-20 | 30000
27 | MUNICIPAL TAXES & OTHER CHARGES | CH.NO 450920 | 2022-09-05 | 677520
30 | MUNICIPAL TAXES & OTHER CHARGES | CFO SCRUTINY FEES | 2022-09-07 | 157522
31 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2022-09-23 | 4000
32 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2022-09-30 | 9000
33 | MUNICIPAL TAXES & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2022-09-30 | 32000
34 | MUNICIPAL TAXES & OTHER CHARGES | BMC PAY ORDER | 2022-11-24 | 42900
35 | MUNICIPAL TAXES & OTHER CHARGES | BMC PAY ORDER | 2022-11-24 | 13900
36 | MUNICIPAL TAXES & OTHER CHARGES | BMC PAY ORDER | 2022-11-24 | 56700
37 | MUNICIPAL TAXES & OTHER CHARGES | TREE CUTING CHARGES | 2022-12-14 | 10000
38 | MUNICIPAL TAXES & OTHER CHARGES | TREE CUTING CHARGES | 2022-12-14 | 255000
39 | MUNICIPAL TAXES & OTHER CHARGES | TREE CUTING CHARGES | 2022-12-14 | 150000
40 | MUNICIPAL TAXES & OTHER CHARGES | PAID AIRPORT AUTHORITY OF INDIA | 2022-12-14 | 2360000
41 | MUNICIPAL TAXES & OTHER CHARGES | PAY ORDER TO SRA AG REHAB | 2023-01-12 | 3015000
42 | MUNICIPAL TAXES & OTHER CHARGES | PAY ORDER TO SRA AG REHAB | 2023-01-12 | 594500
43 | MUNICIPAL TAXES & OTHER CHARGES | PAID TO SRA AG MRTP CHARGES | 2023-01-12 | 3756000
44 | MUNICIPAL TAXES & OTHER CHARGES | PAID TO SRA AG LABOUR CESS FOR POONAM NAGAR | 2023-01-12 | 7713500
45 | MUNICIPAL TAXES & OTHER CHARGES | PAYMENT MADE TO MAHAKANJI | 2023-02-27 | 45912
46 | MUNICIPAL TAXES & OTHER CHARGES | PAYMENT MADE TO GRASS | 2023-02-27 | 366138
47 | MUNICIPAL TAXES & OTHER CHARGES | PAYMENT MADE TO MAHAKANJI | 2023-02-27 | 54329
48 | MUNICIPAL TAXES & OTHER CHARGES | PAYMENT MADE TO GRASS | 2023-02-27 | 433770
49 | MUNICIPAL TAXES & OTHER CHARGES | PAYMENT MADE TO MAHAKANJI | 2023-02-27 | 177526
50 | MUNICIPAL TAXES & OTHER CHARGES | PAYMENT MADE TO GRASS | 2023-02-27 | 1417486
51 | MUNICIPAL TAXES & OTHER CHARGES | CH.NO 450572 AG POONAM NAGAR | 2023-05-15 | 71775
52 | MUNICIPAL TAXES & OTHER CHARGES | CH.NO 450573 POONAM NAGAR CARRIAGE AMOUNT | 2023-05-17 | 31235
53 | MUNICIPAL TAXES & OTHER CHARGES | CH.NO 071903 AG PCO CHARGES NEELKAMAL AMINITIES | 2023-07-05 | 64831
|  | LEGAL CHARGES FOR VERIFICATION | 2023-07-31 | 44522
| MRTP DEVELOPMENT CHARGES | SLUM REHABILITATION AUTHORITY | 2023-04-08 | 4675625
| MRTP DEVELOPMENT CHARGES | SLUM REHABILITATION AUTHORITY | 2023-04-08 | 13935500
| MRTP DEVELOPMENT CHARGES | SLUM REHABILITATION AUTHORITY | 2023-04-08 | 2007750
| MRTP DEVELOPMENT CHARGES | SLUM REHABILITATION AUTHORITY | 2023-04-08 | 2000400
| MRTP DEVELOPMENT CHARGES | SLUM REHABILITATION AUTHORITY | 22/8/23 | 3545500
| MRTP DEVELOPMENT CHARGES | SLUM REHABILITATION AUTHORITY |  | 8000
| MUNICIPAL TAX & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2023-11-22 | 81910
| MUNICIPAL TAX & OTHER CHARGES | SLUM REHABILITATION AUTHORITY | 2023-12-03 | 64831
|  | SLUM REHABILITATION AUTHORITY | 2023-12-26 | 2000
|  | SLUM REHABILITATION AUTHORITY | 2023-12-26 | 2000
|  | SLUM REHABILITATION AUTHORITY | 2023-12-26 | 4000
| COST OF T.D.R. |  | 2024-02-26 | 2074315
| COST OF T.D.R. |  | 2024-02-29 | 14426207
| COST OF T.D.R. |  | 2024-02-29 | 5822040
| COST OF T.D.R. |  | 2024-03-04 | 63000
| COST OF T.D.R. |  | 2024-03-04 | 433400
| COST OF T.D.R. |  | 2024-03-04 | 175300
| COST OF T.D.R. |  | 2024-03-07 | 24800000
| COST OF T.D.R. |  | 2024-03-14 | 744600
| MUNICIPAL TAX & OTHER CHARGES |  | 2024-02-16 | 21500
| MUNICIPAL TAX & OTHER CHARGES |  | 2024-03-21 | 368749
| MUNICIPAL TAX & OTHER CHARGES |  | 2024-03-21 | 45912
| SLUM REHABILITATION AUTHORITY | CHEQ.NO.071022 INTEREST PAID | 2024-02-28 | 841613
| SLUM REHABILITATION AUTHORITY | CH.NO 071045 | 2024-02-28 | 2000400
| SLUM REHABILITATION AUTHORITY | CH.NO 071039 | 2024-02-28 | 13935500
| SLUM REHABILITATION AUTHORITY | CH.NO 071042 | 2024-02-28 | 2007750
| SLUM REHABILITATION AUTHORITY | CH.NO 071036 | 2024-02-28 | 4675625
| SLUM REHABILITATION AUTHORITY | CHEQ.NO.071025 INTEREST PAID | 2024-02-28 | 2508390
| SLUM REHABILITATION AUTHORITY | CHEQ.NO.071028 INTEREST PAID | 2024-02-28 | 361395
| SLUM REHABILITATION AUTHORITY | CHEQ.NO.071031 INTEREST PAID | 2024-02-28 | 360072
| SLUM REHABILITATION AUTHORITY |  | 2024-06-01 | 51000
| SLUM REHABILITATION AUTHORITY |  | 2024-06-01 | 16322500
| SLUM REHABILITATION AUTHORITY |  | 2024-06-01 | 23000
| MUNICIPAL TAX & OTHER CHARGES |  |  | 90243
| MUNICIPAL TAX & OTHER CHARGES |  |  | 75656
| MUNICIPAL TAX & OTHER CHARGES |  |  | 186829
| MUNICIPAL TAX & OTHER CHARGES |  |  | 23262
| SHIVALIK VENTURES PRIVATE LIMITED- TDR | COST OF TDR |  | 24457472
| SBI A/C NO.41853900460 RERA 30% | Approval | 2024-08-31 | 561075
| SBI A/C NO.41853900460 RERA 30% | Approval | 2024-08-31 | 1672260
| SBI A/C NO.41853900460 RERA 30% | Approval | 2024-08-31 | 240930
| SBI A/C NO.41853900460 RERA 30% | Approval | 2024-08-31 | 240048
| SBI A/C NO.41853900460 RERA 30% | Approval | 2024-08-31 | 4675625
| SBI A/C NO.41853900460 RERA 30% | Approval | 2024-08-31 | 13935500
| SBI A/C NO.41853900460 RERA 30% | Approval | 2024-08-31 | 2007750
| SBI A/C NO.41853900460 RERA 30% | Approval | 2024-08-31 | 2000400
| SBI A/C NO.41853900460 RERA 30% | Approval | 2024-09-12 | 2095500
| SBI A/C NO.41853900460 RERA 30% | Approval | 2024-09-12 | 5629000
| SBI A/C NO.41853900460 RERA 30% | Approval | 2024-09-12 | 804000
| MUNICIPAL TAX & OTHER CHARGES | Approval | 2024-07-24 | 390000
| MUNICIPAL TAX & OTHER CHARGES | Approval | 2024-08-14 | 240197
| MUNICIPAL TAX & OTHER CHARGES | Approval | 2024-08-28 | 64070
| STAMPDUTY & REGISTRATION - TDR | Approval | 2024-07-03 | 94800
| RUPVALULA PROPERTIES PRIVATE LIMITED -TDR | Approval | 2024-07-03 | 3138275
| SBI A/C NO.41853900460 RERA 30% | CH.NO 072138 PAID TO SRA FOR C C REVALIDATION FEE FOR REHAB BUILDING 1 | 2024-12-21 | 2000
| SBI A/C NO.41853900460 RERA 30% | CH.NO 072139 PAID C/C REVALIDATION FEE FOR REHAB BUILDING 2 | 2024-12-21 | 2000
| SBI A/C NO.41853900460 RERA 30% | CH.NO 072140 PAID C/C REVALIDATION FEE FOR REHAB BUILDING 3 | 2024-12-21 | 4000
| MUNICIPAL TAX & OTHER CHARGES |  |  | 218080
|  | TOTAL MUNICIPAL TAX CHARGES |  | 295700360

## Construction Cost
PURCHASE- NEELKAMAL REALTY & CONTRUCTION LLP
1/4/18 - 31/7/23
Date | Particular |  | Total Amount
2022-07-15 | D.R LINKS |  | 71456
2022-10-10 | SHARADA ENTERPRISES |  | 65408
2023-03-14 | R.K.TRADERS |  | 6720
2023-03-31 | OM ENTERPRISES |  | 64774.08
2023-04-30 | OM ENTERPRISES |  | 61377.12
2023-05-27 | AMIT CORPORATION |  | 54880
2023-05-31 | S. H. ENTERPRISES |  | 61936
2023-06-03 | R.K.TRADING CO. |  | 3743.6
2023-06-15 | S. H. ENTERPRISES |  | 64960
2023-07-27 | RECONS BUILDING PRODUCTS PVT.LTD. |  | 59448
2022-04-18 | SHREEJI WATER PUMPS & BOREWELL |  | 132460.9
2022-06-18 | ANUPAM ELECTRICALS |  | 16756
2022-06-23 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 77864.66
2022-06-25 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 17792.64
2022-06-25 | ANUPAM ELECTRICALS |  | 4678.7
2022-07-07 | ANUPAM ELECTRICALS |  | 1060.82
2022-07-18 | SKY TELECOM |  | 73396
2022-08-03 | ANUPAM ELECTRICALS |  | 46621.8
2022-08-22 | KRISHNA TRADING CORPORATION |  | 13266.74
2022-08-29 | ANUPAM ELECTRICALS |  | 25649.66
2022-08-31 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 10521.58
2022-09-01 | KRISHNA TRADING CORPORATION |  | 4010.77
2022-09-03 | SHREEJI WATER PUMPS & BOREWELL |  | 65431
2022-09-03 | SHREEJI WATER PUMPS & BOREWELL |  | 59885
2022-09-03 | SHREEJI WATER PUMPS & BOREWELL |  | 65431
2022-11-09 | MEHTA PLYWOOD |  | 4720
2023-02-20 | D.R LINKS |  | 45593.44
2023-02-25 | ANUPAM ELECTRICALS |  | 1062
2023-03-09 | ANUPAM ELECTRICALS |  | 63519.4
2023-03-14 | R.K.TRADERS |  | 7269.98
2023-03-16 | ANUPAM ELECTRICALS |  | 47837.2
2023-03-20 | MEHTA PLYWOOD |  | 4908.8
2023-03-22 | R.K.TRADERS |  | 7198
2023-03-23 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2148160.5
2023-03-24 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 82052.48
2023-03-29 | ANUPAM ELECTRICALS |  | 47613
2023-03-30 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2171703.86
2023-03-30 | ANUPAM ELECTRICALS |  | 86022
2023-03-31 | OM SWASTIK ENTERPRISES |  | 33250.01
2023-04-03 | R.K.TRADERS |  | 7186.2
2023-04-03 | ANUPAM ELECTRICALS |  | 31425.76
2023-04-04 | ANUPAM ELECTRICALS |  | 38899.88
2023-04-04 | D.R LINKS |  | 22838.9
2023-04-05 | ANUPAM ELECTRICALS |  | 79281.84
2023-04-05 | KRISHNA CERAMICS |  | 49600.14
2023-04-06 | ANUPAM ELECTRICALS |  | 85404.28
2023-04-06 | KRISHNA TRADING CORPORATION |  | 31388
2023-04-07 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2165595
2023-04-07 | ANUPAM ELECTRICALS |  | 98810.26
2023-04-07 | KRISHNA TRADING CORPORATION |  | 11298.5
2023-04-08 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2190731.36
2023-04-10 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2026465.92
2023-04-10 | YESKAY INDUSTRIES |  | 36580
2023-04-11 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 81608.8
2023-04-12 | SKY TELECOM |  | 29618
2023-04-14 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2220017.78
2023-04-15 | WEATHER COOL SERVICES |  | 9451.8
2023-04-17 | ANUPAM ELECTRICALS |  | 51079.84
2023-04-19 | VEDANT MARKETING |  | 54516
2023-04-20 | TEJAS CERAMICS |  | 5960.18
2023-04-24 | ANUPAM ELECTRICALS |  | 13776.74
2023-04-24 | VEDANT MARKETING |  | 89090
2023-04-25 | ANUPAM ELECTRICALS |  | 24724.54
2023-04-27 | KRISHNA TRADING CORPORATION |  | 62000.09
2023-05-02 | ANUPAM ELECTRICALS |  | 29665.2
2023-05-03 | VEDANT MARKETING |  | 53454
2023-05-04 | R.K.TRADING CO. |  | 3793.7
2023-05-05 | VEDANT MARKETING |  | 89090
2023-05-05 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2132342.6
2023-05-06 | VEDANT MARKETING |  | 178180
2023-05-08 | MEHTA PLYWOOD |  | 339.84
2023-05-10 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2138807.82
2023-05-12 | KRISHNA TRADING CORPORATION |  | 6903
2023-05-14 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2182202.32
2023-05-17 | VEDANT MARKETING |  | 142780
2023-05-18 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2170598.2
2023-05-19 | VEDANT MARKETING |  | 5982.6
2023-05-20 | R.K.TRADING CO. |  | 3894
2023-05-21 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 81427.08
2023-05-23 | OM SWASTIK ENTERPRISES |  | 275400.08
2023-05-30 | SHREE DEV STEEL WORKS |  | 156940
2023-05-30 | VEDANT MARKETING |  | 178180
2023-05-31 | SEACOM SERVICES |  | 27376
2023-06-01 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2175891.68
2023-06-01 | ANUPAM ELECTRICALS |  | 73768.88
2023-06-01 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2187199.62
2023-06-02 | SAROVAR TRADING CO |  | 45312
2023-06-02 | SAROVAR TRADING CO |  | 45312
2023-06-02 | SAROVAR TRADING CO |  | 45312
2023-06-02 | SAROVAR TRADING CO |  | 45312
2023-06-02 | SAROVAR TRADING CO |  | 45312
2023-06-02 | SAROVAR TRADING CO |  | 45312
2023-06-02 | SAROVAR TRADING CO |  | 45312
2023-06-02 | SAROVAR TRADING CO |  | 45312
2023-06-02 | SAROVAR TRADING CO |  | 52864
2023-06-02 | SAROVAR TRADING CO |  | 52864
2023-06-02 | SAROVAR TRADING CO |  | 45312
2023-06-02 | SAROVAR TRADING CO |  | 45312
2023-06-02 | SAROVAR TRADING CO |  | 45312
2023-06-02 | SAROVAR TRADING CO |  | 45312
2023-06-02 | SAROVAR TRADING CO |  | 45312
2023-06-02 | SAROVAR TRADING CO |  | 45312
2023-06-02 | SAROVAR TRADING CO |  | 45312
2023-06-02 | SAROVAR TRADING CO |  | 45312
2023-06-02 | SAROVAR TRADING CO |  | 45312
2023-06-02 | SAROVAR TRADING CO |  | 45312
2023-06-02 | SAROVAR TRADING CO |  | 45312
2023-06-02 | SAROVAR TRADING CO |  | 45312
2023-06-02 | SAROVAR TRADING CO |  | 45312
2023-06-02 | SAROVAR TRADING CO |  | 45312
2023-06-02 | SAROVAR TRADING CO |  | 45312
2023-06-02 | ANUPAM ELECTRICALS |  | 80474.12
2023-06-03 | ANUPAM ELECTRICALS |  | 83872.74
2023-06-05 | FIRETRONICS SAFETY SYSTEMS |  | 88500
2023-06-10 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2141110
2023-06-12 | R.K.TRADERS |  | 4956
2023-06-14 | GENIUS TRACTOR COMPANY |  | 6643.45
2023-06-14 | UMA SERVICES |  | 15458
2023-06-15 | ANUPAM ELECTRICALS |  | 9617
2023-06-16 | SRK ENGINEERING SERVICES |  | 25346.4
2023-06-16 | SKY TELECOM |  | 51212
2023-06-20 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 6955.04
2023-06-20 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 96737.82
2023-06-20 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 38646.32
2023-06-27 | UMA SERVICES |  | 2360
2023-06-29 | MAHIMA ENTERPRISES |  | 1326403.78
2023-07-03 | UMA SERVICES |  | 2360
2023-07-10 | SHREE TECHNOCHEM |  | 59000
2023-07-12 | KRISHNA TRADING CORPORATION |  | 4606.6
2023-07-15 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 1796916.98
2023-07-17 | ANUPAM ELECTRICALS |  | 32855.92
2023-07-25 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 70325.64
2023-07-27 | RECONS BUILDING PRODUCTS PVT.LTD. |  | 4200
2023-07-28 | ANUPAM ELECTRICALS |  | 35016.5
2020-01-13 | KIRIT TRADING COMPANY |  | 13888
2023-03-18 | SUNTREK CORPORATION |  | 115200
2023-03-24 | SUNTREK CORPORATION |  | 114048
2023-03-26 | SUNTREK CORPORATION |  | 114048
2023-03-27 | SUNTREK CORPORATION |  | 188800
2023-03-31 | SUNTREK CORPORATION |  | 151040
2023-03-31 | SUNTREK CORPORATION |  | 37760
2023-04-04 | J.K.LAKSHMI CEMENT (KETANBHAI) |  | 115200
2023-04-04 | J.K.LAKSHMI CEMENT (KETANBHAI) |  | 76800
2023-04-09 | THE INDIA CEMENTS LIMITED |  | 94400
2023-04-09 | THE INDIA CEMENTS LIMITED |  | 94400
2023-04-15 | WEATHER COOL SERVICES |  | 32000
2023-04-17 | J.K.LAKSHMI CEMENT (KETANBHAI) |  | 115200
2023-04-22 | THE INDIA CEMENTS LIMITED |  | 111360
2023-04-22 | THE INDIA CEMENTS LIMITED |  | 111360
2023-04-22 | THE INDIA CEMENTS LIMITED |  | 111360
2023-04-22 | THE INDIA CEMENTS LIMITED |  | 111360
2023-04-22 | THE INDIA CEMENTS LIMITED |  | 111360
2023-04-26 | THE INDIA CEMENTS LIMITED |  | 92800
2023-04-26 | THE INDIA CEMENTS LIMITED |  | 92800
2023-04-29 | THE INDIA CEMENTS LIMITED |  | 111360
2023-04-29 | THE INDIA CEMENTS LIMITED |  | 111360
2023-04-29 | THE INDIA CEMENTS LIMITED |  | 111360
2023-04-29 | THE INDIA CEMENTS LIMITED |  | 111360
2023-04-29 | THE INDIA CEMENTS LIMITED |  | 111360
2023-05-06 | THE INDIA CEMENTS LIMITED |  | 111360
2023-05-06 | THE INDIA CEMENTS LIMITED |  | 111360
2023-05-06 | THE INDIA CEMENTS LIMITED |  | 111360
2023-05-06 | THE INDIA CEMENTS LIMITED |  | 111360
2023-05-06 | THE INDIA CEMENTS LIMITED |  | 111360
2023-05-06 | THE INDIA CEMENTS LIMITED |  | 111360
2023-05-06 | THE INDIA CEMENTS LIMITED |  | 111360
2023-05-06 | THE INDIA CEMENTS LIMITED |  | 111360
2023-05-08 | THE INDIA CEMENTS LIMITED |  | 92800
2023-05-08 | THE INDIA CEMENTS LIMITED |  | 92800
2023-05-08 | THE INDIA CEMENTS LIMITED |  | 111360
2023-05-08 | THE INDIA CEMENTS LIMITED |  | 111360
2023-05-13 | KARAN ENTERPRISES |  | 74240
2023-05-16 | KARAN ENTERPRISES |  | 148480
2023-05-16 | KARAN ENTERPRISES |  | 148480
2023-05-16 | KARAN ENTERPRISES |  | 148480
2023-05-16 | KARAN ENTERPRISES |  | 185600
2023-05-16 | KARAN ENTERPRISES |  | 148480
2023-05-16 | KARAN ENTERPRISES |  | 92800
2023-05-17 | KARAN ENTERPRISES |  | 185600
2023-05-17 | KARAN ENTERPRISES |  | 148480
2023-05-17 | KARAN ENTERPRISES |  | 185600
2023-05-17 | KARAN ENTERPRISES |  | 185600
2023-05-20 | KARAN ENTERPRISES |  | 74240
2023-05-21 | THE INDIA CEMENTS LIMITED |  | 92800
2023-05-21 | THE INDIA CEMENTS LIMITED |  | 92800
2023-05-27 | THE INDIA CEMENTS LIMITED |  | 222720
2023-05-29 | J.K.LAKSHMI CEMENT (KETANBHAI) |  | 74240
2023-05-29 | J.K.LAKSHMI CEMENT (KETANBHAI) |  | 148480
2023-05-29 | J.K.LAKSHMI CEMENT (KETANBHAI) |  | 148480
2023-05-29 | J.K.LAKSHMI CEMENT (KETANBHAI) |  | 148480
2023-05-29 | J.K.LAKSHMI CEMENT (KETANBHAI) |  | 148480
2023-05-29 | J.K.LAKSHMI CEMENT (KETANBHAI) |  | 74240
2023-05-29 | J.K.LAKSHMI CEMENT (KETANBHAI) |  | 111360
2023-05-30 | J.K.LAKSHMI CEMENT (KETANBHAI) |  | 185600
2023-05-31 | J.K.LAKSHMI CEMENT (KETANBHAI) |  | 74240
2023-06-01 | THE INDIA CEMENTS LIMITED |  | 185600
2023-06-01 | THE INDIA CEMENTS LIMITED |  | 185600
2023-06-17 | J.K.LAKSHMI CEMENT (KETANBHAI) |  | 93440
2023-06-17 | J.K.LAKSHMI CEMENT (KETANBHAI) |  | 93440
2023-06-20 | THE INDIA CEMENTS LIMITED |  | 224256
2023-06-24 | THE INDIA CEMENTS LIMITED |  | 112128
2023-06-24 | THE INDIA CEMENTS LIMITED |  | 112128
2023-07-01 | THE INDIA CEMENTS LIMITED |  | 93440
2023-07-01 | THE INDIA CEMENTS LIMITED |  | 93440
2023-07-08 | THE INDIA CEMENTS LIMITED |  | 92800
2023-07-08 | THE INDIA CEMENTS LIMITED |  | 92800
2023-07-11 | THE INDIA CEMENTS LIMITED |  | 111360
2023-07-12 | THE INDIA CEMENTS LIMITED |  | 111360
2023-07-12 | THE INDIA CEMENTS LIMITED |  | 111360
2023-07-12 | THE INDIA CEMENTS LIMITED |  | 111360
2023-07-15 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 185600
2023-07-28 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 91840
2023-07-28 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 183680
2023-07-28 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 183680
2023-07-28 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 91840
2019-08-31 | PANCHANKUR STONE QUARY |  | 8531.26
2019-12-31 | GAURAV TRADING CO. |  | 12311.26
2019-12-31 | SHARADA ENTERPRISES |  | 25552.8
2020-01-15 | SHARADA ENTERPRISES |  | 55666.8
2020-01-31 | GAURAV TRADING CO. |  | 7185
2020-02-29 | OM ENTERPRISES |  | 24024
2020-11-30 | OM ENTERPRISES |  | 33075
2020-11-30 | SHARADA ENTERPRISES |  | 26082
2020-12-31 | OM ENTERPRISES |  | 21117.6
2020-12-31 | OM ENTERPRISES |  | 70978.96
2020-12-31 | S. H. ENTERPRISES |  | 26460
2021-01-31 | OM ENTERPRISES |  | 33075
2022-10-31 | DHANAAJI ENTERPRISES |  | 4357.5
2022-11-15 | DHANAAJI ENTERPRISES |  | 4147.5
2023-03-13 | RAJLAXMI CORPORATION |  | 27540.46
2023-03-27 | AMIT CORPORATION |  | 89838
2023-03-30 | AMIT CORPORATION |  | 26068.36
2023-03-31 | S. H. ENTERPRISES |  | 48567.76
2023-03-31 | SHARADA ENTERPRISES |  | 52409.7
2023-03-31 | RAJLAXMI CORPORATION |  | 52943.1
2023-03-31 | ADINATH ENTERPRISES |  | 72377.56
2023-04-05 | AMIT CORPORATION |  | 28182
2023-04-08 | JSW CEMENT LIMITED |  | 59625
2023-04-09 | RAJLAXMI CORPORATION |  | 32263.88
2023-04-15 | NEER TRADING CO. |  | 24210.9
2023-04-15 | RAJ TRANSIT INFRA PVT LTD |  | 127554
2023-04-24 | ADINATH ENTERPRISES |  | 17321.86
2023-04-24 | AMIT CORPORATION |  | 87387.3
2023-04-25 | HARMAN ENGINEERING WORKS |  | 13393.28
2023-04-25 | RAJLAXMI CORPORATION |  | 100641.98
2023-04-26 | AMIT CORPORATION |  | 87845.62
2023-04-29 | SHIV ENTERPRISES |  | 50652.52
2023-04-30 | S. H. ENTERPRISES |  | 101164.36
2023-04-30 | S. H. ENTERPRISES |  | 78788.32
2023-04-30 | S. H. ENTERPRISES |  | 80890.42
2023-04-30 | S. H. ENTERPRISES |  | 36948.46
2023-04-30 | OM ENTERPRISES |  | 43942.5
2023-04-30 | NEER TRADING CO. |  | 43489.96
2023-04-30 | AMIT CORPORATION |  | 75929.18
2023-04-30 | AMIT CORPORATION |  | 28059.68
2023-04-30 | ADINATH ENTERPRISES |  | 30723
2023-04-30 | RAJ TRANSIT INFRA PVT LTD |  | 103592.48
2023-05-02 | JSW CEMENT LIMITED |  | 119250
2023-05-03 | JSW CEMENT LIMITED |  | 119250
2023-05-04 | R.K.TRADING CO. |  | 7245
2023-05-05 | HARMAN ENGINEERING WORKS |  | 65336.26
2023-05-05 | S.S.ENTERPRISES |  | 33075
2023-05-06 | AMIT CORPORATION |  | 87081.76
2023-05-07 | AMIT CORPORATION |  | 98096.26
2023-05-10 | JSW CEMENT LIMITED |  | 119250
2023-05-10 | AMIT CORPORATION |  | 83771.62
2023-05-13 | AMIT CORPORATION |  | 94975.12
2023-05-15 | JSW CEMENT LIMITED |  | 119250
2023-05-15 | RAJ TRANSIT INFRA PVT LTD |  | 109620
2023-05-15 | ADINATH ENTERPRISES |  | 31161.9
2023-05-15 | OM ENTERPRISES |  | 26884.2
2023-05-15 | S. H. ENTERPRISES |  | 103447.58
2023-05-15 | S. H. ENTERPRISES |  | 91764.76
2023-05-15 | S. H. ENTERPRISES |  | 97456.8
2023-05-15 | S. H. ENTERPRISES |  | 85943.56
2023-05-15 | S. H. ENTERPRISES |  | 101749.72
2023-05-15 | S. H. ENTERPRISES |  | 96827.86
2023-05-15 | S. H. ENTERPRISES |  | 99954.22
2023-05-15 | S. H. ENTERPRISES |  | 99165.68
2023-05-15 | S. H. ENTERPRISES |  | 103002.9
2023-05-15 | AMIT CORPORATION |  | 64036.88
2023-05-20 | R.K.TRADING CO. |  | 7245
2023-05-20 | JSW CEMENT LIMITED |  | 119250
2023-05-23 | SHIV ENTERPRISES |  | 24578.4
2023-05-24 | HARMAN ENGINEERING WORKS |  | 59990.7
2023-05-28 | AMIT CORPORATION |  | 95382.52
2023-05-28 | AMIT CORPORATION |  | 79513.88
2023-05-29 | JSW CEMENT LIMITED |  | 119250
2023-05-30 | M/S.SHRIYAA ENTERPRISES |  | 65417.1
2023-05-31 | S. H. ENTERPRISES |  | 98118.3
2023-05-31 | S. H. ENTERPRISES |  | 95925.38
2023-05-31 | S. H. ENTERPRISES |  | 102937.8
2023-05-31 | S. H. ENTERPRISES |  | 99768.9
2023-05-31 | S. H. ENTERPRISES |  | 92427.82
2023-05-31 | S. H. ENTERPRISES |  | 37582.64
2023-05-31 | S. H. ENTERPRISES |  | 33086.02
2023-05-31 | OM ENTERPRISES |  | 54195.76
2023-05-31 | RAJLAXMI CORPORATION |  | 157754.1
2023-05-31 | RAJ TRANSIT INFRA PVT LTD |  | 116887.58
2023-06-02 | JSW CEMENT LIMITED |  | 119250
2023-06-14 | ADINATH ENTERPRISES |  | 69244.36
2023-06-14 | HARMAN ENGINEERING WORKS |  | 35494.72
2023-06-15 | S. H. ENTERPRISES |  | 94271.1
2023-06-15 | S. H. ENTERPRISES |  | 98313.6
2023-06-15 | S. H. ENTERPRISES |  | 32744.26
2023-06-15 | S. H. ENTERPRISES |  | 94166.62
2023-06-21 | AMIT CORPORATION |  | 94813.42
2023-06-23 | JSW CEMENT LIMITED |  | 119250
2023-06-24 | HARMAN ENGINEERING WORKS |  | 27771.98
2023-06-25 | AMIT CORPORATION |  | 95472.3
2023-06-28 | RAJLAXMI CORPORATION |  | 96299.18
2023-06-30 | NEER TRADING CO. |  | 31329.9
2023-06-30 | S. H. ENTERPRISES |  | 94905.3
2023-06-30 | S. H. ENTERPRISES |  | 73671.16
2023-06-30 | S. H. ENTERPRISES |  | 37582.66
2023-06-30 | M/S.SHRIYAA ENTERPRISES |  | 44251.2
2023-07-08 | AMIT CORPORATION |  | 96625.72
2023-07-13 | AMIT CORPORATION |  | 92168.48
2023-07-15 | ADINATH ENTERPRISES |  | 23580.9
2023-07-15 | RAJ TRANSIT INFRA PVT LTD |  | 30605.92
2023-07-18 | M/S.SHRIYAA ENTERPRISES |  | 87998.4
2023-07-22 | RAJLAXMI CORPORATION |  | 50571.68
2023-07-23 | AMIT CORPORATION |  | 97215.82
2023-07-31 | AMIT CORPORATION |  | 52202.32
2023-04-30 | THE INDIA CEMENTS LIMITED |  | 489241.6
2022-04-01 | K.S.HIRING |  | 18600
2022-06-20 | Thakkar Electrical Works |  | 18000
2022-12-28 | H. A. NADAR |  | 674925
2023-03-04 | Thakkar Electrical Works |  | 15000
2023-03-09 | ROHIT SHUKLA |  | 100000
2023-03-16 | PREET DESAI |  | 29000
2023-03-16 | SADHANA MISHRA |  | 29000
2023-03-16 | NITIN SHENGDE |  | 29000
2023-03-16 | SUFIYAN JAMADAR |  | 29000
2023-03-16 | AMIT KUMAR |  | 29000
2023-03-20 | ANIL MANI HUF |  | 29000
2023-03-25 | G C CREATION |  | 1500000
2023-03-25 | SHAMBHO GROUPS OF COMPANYS |  | 1500000
2023-04-01 | VANDANA RAJARAM POL |  | 25000
2023-04-02 | REHAN ENTERPRISES |  | 178480
2023-04-03 | SADHANA MISHRA |  | 29000
2023-04-03 | SUFIYAN JAMADAR |  | 29000
2023-04-03 | PREET DESAI |  | 29000
2023-04-03 | NITIN SHENGDE |  | 29000
2023-04-03 | AMIT KUMAR |  | 29000
2023-04-03 | ROHIT SHUKLA |  | 500000
2023-04-03 | ROHIT SHUKLA |  | 29250
2023-04-03 | ROHIT SHUKLA |  | 175000
2023-04-06 | HARMAN ENGINEERING WORKS |  | 30723
2023-04-10 | INDIAN FABRICATORS |  | 250000
2023-04-21 | RAMASHREY PRAJAPATI |  | 15136
2023-04-28 | AKAR CONSTRUCTION COMPANY |  | 2950000
2023-04-29 | INDIAN FABRICATORS |  | 355440.5
2023-05-05 | WATER PUMP HIRE SERVICE |  | 16565
2023-05-15 | Thakkar Electrical Works |  | 15000
2023-05-22 | AKAR CONSTRUCTION COMPANY |  | 2360000
2023-05-26 | ADITYA CRANE SERVICE |  | 79562
2023-06-08 | WATER PUMP HIRE SERVICE |  | 23366
2023-06-17 | AKAR CONSTRUCTION COMPANY |  | 2950000
2023-06-24 | WELCOME ENTERPRIESES |  | 150000
2023-06-30 | WATER PUMP HIRE SERVICE |  | 21000
2023-07-07 | YOGENDRA PANDEY |  | 1000000
2023-07-07 | AKAR CONSTRUCTION COMPANY |  | 944000
2023-07-07 | MOHAMMAD ABUL HAYAT |  | 500000
2023-07-11 | MUNNI TAUFIK SHAIKH |  | 700000
2023-07-24 | ROHIT SHUKLA |  | 145000
2023-07-24 | ROHIT SHUKLA |  | 145000
2023-08-01 | VIDHI CONSTRUCTIONS |  | 830661
2023-08-05 | VIDHI CONSTRUCTIONS |  | 1900980
2023-08-14 | VIDHI CONSTRUCTIONS |  | 4195301
2023-08-22 | AKAR CONSTRUCTION COMPANY |  | 10030000
2023-09-01 | HEMANT B. AMANAG |  | 700000
2023-09-01 | SULABAI AMANAGE |  | 700000
2023-09-01 | KAMLADEVI CHAMPALAL GOWANI |  | 700000
2023-09-01 | YOGESH B.SAHU |  | 1125000
2023-09-02 | INDIAN FABRICATORS |  | 13100
2023-09-02 | INDIAN FABRICATORS |  | 230915
2023-09-02 | REHAN ENTERPRISES |  | 111734
2023-09-18 | RAMASHREY PRAJAPATI |  | 13224
2023-09-30 | WATER PUMP HIRE SERVICE |  | 23250
2023-09-30 | GUNVANTRAI M SONI |  | 82600
2023-08-14 | RECONS BUILDING PRODUCTS PVT.LTD. |  | 67485.6
2023-08-14 | RECONS BUILDING PRODUCTS PVT.LTD. |  | 60060
2023-08-18 | RECONS BUILDING PRODUCTS PVT.LTD. |  | 67616.64
2023-08-21 | RECONS BUILDING PRODUCTS PVT.LTD. |  | 72727
2023-08-22 | RECONS BUILDING PRODUCTS PVT.LTD. |  | 20249.6
2023-08-29 | RECONS BUILDING PRODUCTS PVT.LTD. |  | 53857
2023-08-31 | RECONS BUILDING PRODUCTS PVT.LTD. |  | 53511.01
2023-08-05 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 1924329.84
2023-08-08 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2164195.52
2023-08-08 | SHREEJI WATER PUMPS & BOREWELL |  | 24603
2023-08-08 | SHREE TECHNOCHEM |  | 53100
2023-08-08 | SHREE TECHNOCHEM |  | 53100
2023-08-09 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 1598162.5
2023-08-12 | ANUPAM ELECTRICALS |  | 4277.5
2023-08-14 | RECONS BUILDING PRODUCTS PVT.LTD. |  | 5669.9
2023-08-14 | RECONS BUILDING PRODUCTS PVT.LTD. |  | 6074.64
2023-08-16 | ANUPAM ELECTRICALS |  | 25606
2023-08-16 | SHREE TECHNOCHEM |  | 66375
2023-08-16 | ANUPAM ELECTRICALS |  | 26172.4
2023-08-17 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 1700265.54
2023-08-17 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 78064.08
2023-08-21 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 1971592.38
2023-08-23 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 1987354.82
2023-08-26 | R.K.TRADERS |  | 5310
2023-08-27 | SHREE TECHNOCHEM |  | 132750
2023-08-28 | ANUPAM ELECTRICALS |  | 22462.48
2023-08-31 | RECONS BUILDING PRODUCTS PVT.LTD. |  | 10181.04
2023-08-04 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 183680
2023-08-12 | KARAN ENTERPRISES |  | 93440
2023-08-16 | KARAN ENTERPRISES |  | 93440
2023-08-16 | KARAN ENTERPRISES |  | 93440
2023-08-16 | KARAN ENTERPRISES |  | 74752
2023-08-16 | KARAN ENTERPRISES |  | 93440
2023-08-16 | KARAN ENTERPRISES |  | 93440
2023-08-18 | KARAN ENTERPRISES |  | 93440
2023-08-18 | KARAN ENTERPRISES |  | 93440
2023-08-22 | SUNTREK CORPORATION |  | 75008
2023-08-22 | SUNTREK CORPORATION |  | 44254.72
2023-08-22 | SUNTREK CORPORATION |  | 75008
2023-08-22 | SUNTREK CORPORATION |  | 37504
2023-08-26 | THE INDIA CEMENTS LIMITED |  | 228774.4
2023-08-26 | THE INDIA CEMENTS LIMITED |  | 228774.4
2023-08-31 | THE INDIA CEMENTS LIMITED |  | 232524.8
2023-08-31 | THE INDIA CEMENTS LIMITED |  | 232524.8
2023-08-04 | JSW CEMENT LIMITED |  | 119250
2023-08-06 | AMIT CORPORATION |  | 59465.18
2023-08-15 | ADINATH ENTERPRISES |  | 24019.8
2023-08-15 | SHARADA ENTERPRISES |  | 90493.72
2023-08-15 | SHARADA ENTERPRISES |  | 94759.88
2023-08-15 | SHARADA ENTERPRISES |  | 93270.46
2023-08-15 | SHARADA ENTERPRISES |  | 83058.68
2023-08-16 | AMIT CORPORATION |  | 67605.3
2023-08-21 | HARMAN ENGINEERING WORKS |  | 90349.88
2023-08-21 | SHARADA ENTERPRISES |  | 96490.28
2023-08-21 | SHARADA ENTERPRISES |  | 83048.18
2023-08-21 | SHARADA ENTERPRISES |  | 63143.86
2023-08-23 | JSW CEMENT LIMITED |  | 119250
2023-08-25 | R.K.TRADING CO. |  | 11550
2023-08-29 | AMIT CORPORATION |  | 95130
2023-08-31 | SHARADA ENTERPRISES |  | 84003.16
2023-08-31 | SHARADA ENTERPRISES |  | 95755.8
2023-08-31 | SHARADA ENTERPRISES |  | 83160.52
2023-08-31 | SHARADA ENTERPRISES |  | 73896.9
2023-08-31 | SHARADA ENTERPRISES |  | 73896.9
2023-08-31 | SHARADA ENTERPRISES |  | 41198.32
2023-08-31 | RAJ TRANSIT INFRA PVT LTD |  | 25589.02
2023-08-31 | RAJLAXMI CORPORATION |  | 92159.56
2023-09-04 | RECONS BUILDING PRODUCTS PVT.LTD. |  | 54206.88
2023-09-07 | RECONS BUILDING PRODUCTS PVT.LTD. |  | 62506.08
2023-09-08 | RECONS BUILDING PRODUCTS PVT.LTD. |  | 57788.64
2023-09-12 | RECONS BUILDING PRODUCTS PVT.LTD. |  | 128419.08
2023-09-16 | SNEH ENTERPRISE |  | 82869.48
2023-09-16 | SNEH ENTERPRISE |  | 82043.88
2023-09-04 | RECONS BUILDING PRODUCTS PVT.LTD. |  | 6075.01
2023-09-07 | RECONS BUILDING PRODUCTS PVT.LTD. |  | 6075.01
2023-09-08 | RECONS BUILDING PRODUCTS PVT.LTD. |  | 6075.01
2023-09-12 | RECONS BUILDING PRODUCTS PVT.LTD. |  | 2025.01
2023-09-13 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 76691.74
2023-09-16 | SNEH ENTERPRISE |  | 21249.44
2023-09-24 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2153671.1
2023-09-30 | LANDMARK CONSULTANTS & ENGG. TECHNOLOGY |  | 13098
2023-09-08 | THE INDIA CEMENTS LIMITED |  | 232524.8
2023-09-13 | SUNTREK CORPORATION |  | 74240
2023-09-13 | SUNTREK CORPORATION |  | 18560
2023-09-13 | SUNTREK CORPORATION |  | 74240
2023-09-13 | SUNTREK CORPORATION |  | 31923.2
2023-09-13 | THE INDIA CEMENTS LIMITED |  | 222720
2023-09-16 | SUNTREK CORPORATION |  | 74240
2023-09-16 | SUNTREK CORPORATION |  | 31923.2
2023-09-16 | SUNTREK CORPORATION |  | 74240
2023-09-16 | SUNTREK CORPORATION |  | 18560
2023-09-16 | SUNTREK CORPORATION |  | 74240
2023-09-16 | SUNTREK CORPORATION |  | 18560
2023-09-16 | SUNTREK CORPORATION |  | 74240
2023-09-16 | SUNTREK CORPORATION |  | 18560
2023-09-06 | M/S.SHRIYAA ENTERPRISES |  | 43540.88
2023-09-07 | JSW CEMENT LIMITED |  | 119250
2023-09-15 | ADINATH ENTERPRISES |  | 48318.9
2023-09-15 | M/S.SHRIYAA ENTERPRISES |  | 71549.62
2023-09-15 | CHIRAG ENTERPRISES |  | 55500.9
2023-10-02 | SAKSHI CORPORATION |  | 142829
2023-10-15 | SAKSHI CORPORATION |  | 135703.8
2023-10-18 | SAKSHI CORPORATION |  | 138739.1
2023-10-19 | SAKSHI CORPORATION |  | 139927.2
2023-11-07 | SAKSHI CORPORATION |  | 171607.52
2023-11-25 | SAKSHI CORPORATION |  | 163944.7
2023-12-05 | SHARADA ENTERPRISES |  | 65408
2023-12-07 | UN CORPORATION |  | 181602
2023-12-15 | UN CORPORATION |  | 150052.5
2023-10-02 | SAKSHI CORPORATION |  | 10624.72
2023-10-07 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2095621
2023-10-07 | SHREE TECHNOCHEM |  | 66375
2023-10-09 | CHANDRAKANT ELECTRICAL & CONTRACTOR |  | 41944.76
2023-10-10 | KRISHNA TRADING CORPORATION |  | 4860.91
2023-10-10 | KRISHNA CERAMICS |  | 8024
2023-10-15 | SAKSHI CORPORATION |  | 21249.44
2023-10-16 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2129374.9
2023-10-17 | ANUPAM ELECTRICALS |  | 9221.7
2023-10-18 | SAKSHI CORPORATION |  | 16999.56
2023-10-18 | SHREE TECHNOCHEM |  | 132750
2023-10-19 | SAKSHI CORPORATION |  | 16999.56
2023-10-20 | GLOBAL GYPSUM PVT LTD |  | 28320
2023-10-26 | KRISHNA TRADING CORPORATION |  | 12272
2023-10-31 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2021151.2
2023-11-03 | R.K.TRADING CO. |  | 5959
2023-11-06 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 70540.4
2023-11-06 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2039045.9
2023-11-06 | SHREE TECHNOCHEM |  | 66375
2023-11-07 | SAKSHI CORPORATION |  | 12749.66
2023-11-07 | HITECH CONSTRUCTIONS AND REPAIRS |  | 17464
2023-11-17 | VEDANT MARKETING |  | 51566
2023-11-18 | HITECH CONSTRUCTIONS AND REPAIRS |  | 26196
2023-11-20 | CHANDRAKANT ELECTRICAL & CONTRACTOR |  | 544179.42
2023-11-20 | GLOBAL GYPSUM PVT LTD |  | 14160
2023-11-22 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2056705.78
2023-11-25 | SAKSHI CORPORATION |  | 38249
2023-11-29 | VEDANT MARKETING |  | 51566
2023-11-30 | KRISHNA TRADING CORPORATION |  | 19045.37
2023-12-03 | R.K.TRADING CO. |  | 9735
2023-12-05 | VEDANT MARKETING |  | 72251.4
2023-12-06 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2085384.5
2023-12-07 | UN CORPORATION |  | 17550
2023-12-08 | GLOBAL GYPSUM PVT LTD |  | 28320
2023-12-09 | HITECH CONSTRUCTIONS AND REPAIRS |  | 5782
2023-12-11 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2042485.6
2023-12-15 | UN CORPORATION |  | 17550.09
2023-12-15 | VEDANT MARKETING |  | 53159
2023-12-19 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2040102
2023-12-24 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 1961732.3
2023-12-30 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2073134.92
2023-10-05 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 185600
2023-10-06 | KIRIT TRADING COMPANY |  | 78080
2023-10-06 | KIRIT TRADING COMPANY |  | 78080
2023-10-06 | KIRIT TRADING COMPANY |  | 78080
2023-10-06 | KIRIT TRADING COMPANY |  | 78080
2023-10-06 | KIRIT TRADING COMPANY |  | 78080
2023-10-06 | KIRIT TRADING COMPANY |  | 242048
2023-10-08 | THE INDIA CEMENTS LIMITED |  | 225024
2023-10-13 | KIRIT TRADING COMPANY |  | 78080
2023-10-18 | SNEH ENTERPRISE |  | 111360
2023-10-20 | KIRIT TRADING COMPANY |  | 201600
2023-10-21 | KIRIT TRADING COMPANY |  | 201600
2023-10-24 | KIRIT TRADING COMPANY |  | 201600
2023-10-24 | KIRIT TRADING COMPANY |  | 201600
2023-10-28 | KIRIT TRADING COMPANY |  | 100800
2023-10-31 | KIRIT TRADING COMPANY |  | 201600
2023-10-31 | KIRIT TRADING COMPANY |  | 120960
2023-11-01 | KIRIT TRADING COMPANY |  | 72576
2023-11-06 | SUNTREK CORPORATION |  | 120960
2023-11-06 | SUNTREK CORPORATION |  | 120960
2023-11-06 | SUNTREK CORPORATION |  | 120960
2023-11-06 | SUNTREK CORPORATION |  | 120960
2023-11-08 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 91200
2023-11-08 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 18240
2023-11-08 | THE INDIA CEMENTS LIMITED |  | 100800
2023-11-08 | THE INDIA CEMENTS LIMITED |  | 100800
2023-11-09 | THE INDIA CEMENTS LIMITED |  | 249984
2023-11-16 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 117120
2023-11-16 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 117120
2023-11-17 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 156160
2023-11-17 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 195200
2023-11-23 | KIRIT TRADING COMPANY |  | 195200
2023-11-23 | KIRIT TRADING COMPANY |  | 195200
2023-11-24 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 188800
2023-11-24 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 188800
2023-11-26 | KIRIT TRADING COMPANY |  | 88640
2023-12-01 | KIRIT TRADING COMPANY |  | 106368
2023-12-04 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 94400
2023-12-04 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 94400
2023-12-04 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 94400
2023-12-04 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 94400
2023-12-04 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 94400
2023-12-04 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 94400
2023-12-05 | THE INDIA CEMENTS LIMITED |  | 96000
2023-12-05 | THE INDIA CEMENTS LIMITED |  | 96000
2023-12-05 | THE INDIA CEMENTS LIMITED |  | 115200
2023-12-06 | THE INDIA CEMENTS LIMITED |  | 76800
2023-12-12 | KIRIT TRADING COMPANY |  | 188800
2023-12-12 | KIRIT TRADING COMPANY |  | 188800
2023-12-12 | KIRIT TRADING COMPANY |  | 188800
2023-12-13 | THE INDIA CEMENTS LIMITED |  | 105600
2023-12-17 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 92800
2023-12-17 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 92800
2023-12-19 | KIRIT TRADING COMPANY |  | 104832
2023-10-02 | AMIT CORPORATION |  | 90888
2023-10-02 | AMIT CORPORATION |  | 60471.08
2023-10-02 | AMIT CORPORATION |  | 31531.5
2023-10-07 | HARMAN ENGINEERING WORKS |  | 55301.4
2023-10-09 | M/S.SHRIYAA ENTERPRISES |  | 31288.96
2023-10-11 | HARMAN ENGINEERING WORKS |  | 38601.16
2023-10-13 | RAJLAXMI CORPORATION |  | 82709.56
2023-10-15 | RAJ TRANSIT INFRA PVT LTD |  | 23850.76
2023-10-15 | SHARADA ENTERPRISES |  | 77355.08
2023-10-15 | ADINATH ENTERPRISES |  | 33795.3
2023-10-16 | M/S.SHRIYAA ENTERPRISES |  | 116366.26
2023-10-17 | JSW CEMENT LIMITED |  | 119249.56
2023-10-19 | M/S.SHRIYAA ENTERPRISES |  | 78435
2023-10-20 | HARMAN ENGINEERING WORKS |  | 94545.68
2023-10-21 | GLOBAL GYPSUM PVT LTD |  | 231000
2023-10-24 | M/S.SHRIYAA ENTERPRISES |  | 82956.82
2023-10-30 | RAJLAXMI CORPORATION |  | 38703
2023-10-31 | HARMAN ENGINEERING WORKS |  | 77040.08
2023-10-31 | SHARADA ENTERPRISES |  | 96575.32
2023-10-31 | SHARADA ENTERPRISES |  | 78664.96
2023-10-31 | RAJ TRANSIT INFRA PVT LTD |  | 32501.7
2023-10-31 | CHIRAG ENTERPRISES |  | 34673.1
2023-10-31 | OM ENTERPRISES |  | 27449.62
2023-11-01 | M/S.SHRIYAA ENTERPRISES |  | 38346.52
2023-11-03 | R.K.TRADING CO. |  | 27300
2023-11-04 | JSW CEMENT LIMITED |  | 119249.56
2023-11-06 | HARMAN ENGINEERING WORKS |  | 77791.36
2023-11-10 | RAJLAXMI CORPORATION |  | 85216.42
2023-11-15 | ADINATH ENTERPRISES |  | 33715.5
2023-11-15 | RAJ TRANSIT INFRA PVT LTD |  | 23446.5
2023-11-20 | M/S.SHRIYAA ENTERPRISES |  | 30844.28
2023-11-20 | M/S.SHRIYAA ENTERPRISES |  | 58581.6
2023-11-21 | JSW CEMENT LIMITED |  | 121875
2023-11-22 | M/S.SHRIYAA ENTERPRISES |  | 62443.5
2023-11-22 | GLOBAL GYPSUM PVT LTD |  | 231000
2023-11-23 | RAJ TRANSIT INFRA PVT LTD |  | 48752.56
2023-11-24 | M/S.SHRIYAA ENTERPRISES |  | 75623.62
2023-11-25 | HARMAN ENGINEERING WORKS |  | 80254.12
2023-11-28 | RAJLAXMI CORPORATION |  | 68109.3
2023-11-30 | M/S.SHRIYAA ENTERPRISES |  | 61316.86
2023-11-30 | ADINATH ENTERPRISES |  | 31920
2023-12-03 | R.K.TRADING CO. |  | 27300
2023-12-05 | GLOBAL GYPSUM PVT LTD |  | 249480
2023-12-05 | JSW CEMENT LIMITED |  | 121875
2023-12-05 | M/S.SHRIYAA ENTERPRISES |  | 58396.8
2023-12-05 | SHARADA ENTERPRISES |  | 35533.58
2023-12-05 | SHARADA ENTERPRISES |  | 63399
2023-12-05 | SHARADA ENTERPRISES |  | 87318
2023-12-05 | SHARADA ENTERPRISES |  | 84841.06
2023-12-05 | SHARADA ENTERPRISES |  | 38550.22
2023-12-07 | M/S.SHRIYAA ENTERPRISES |  | 76692
2023-12-11 | JSW CEMENT LIMITED |  | 121875
2023-12-12 | M/S.SHRIYAA ENTERPRISES |  | 78909.6
2023-12-14 | HARMAN ENGINEERING WORKS |  | 37937.02
2023-12-15 | M/S.SHRIYAA ENTERPRISES |  | 109033.58
2023-12-15 | RAJ TRANSIT INFRA PVT LTD |  | 22611.76
2023-12-18 | M/S.SHRIYAA ENTERPRISES |  | 57103
2023-12-18 | M/S.SHRIYAA ENTERPRISES |  | 64167.08
2023-10-10 | WATER PUMP HIRE SERVICE |  | 10000
2023-10-16 | RAMASHREY PRAJAPATI |  | 16584
2023-10-16 | RAMASHREY PRAJAPATI |  | 2064
2023-10-21 | PRABHAKAR C.DUDHBHATE |  | 200000
2023-11-06 | WATER PUMP HIRE SERVICE |  | 5000
2023-11-20 | PRABHAKAR C.DUDHBHATE |  | 300000
2023-12-04 | CHANDULAL GOVIND PATEL |  | 1000000
2023-12-04 | SHIV PUJAN |  | 600000
2023-12-04 | RAM BHARAT |  | 400000
2023-12-04 | SHAMSER KHAN |  | 700000
2023-12-04 | NIDA MUJEEB SHAIKH |  | 800000
2023-12-04 | MANOJ KUMAR |  | 500000
2023-12-05 | WATER PUMP HIRE SERVICE |  | 5000
2023-12-19 | BHAVANI ENTERPRISES |  | 200000
2023-10-18 | SHREEJI WATER PUMPS & BOREWELL |  | 61500
2023-11-09 | AKAR CONSTRUCTION COMPANY |  | 2500000
2023-12-04 | AKAR CONSTRUCTION COMPANY |  | 847458
2023-08-31 | AKAR CONSTRUCTION COMPANY |  | 23600000
2023-08-01 | AJIT KUMAR BOIPAL |  | 291060
2023-08-02 | DHRUVALAL GAURI PRASAD |  | 181440
2023-08-03 | GUNARAM BOIPAL |  | 295680
2023-08-04 | DIPESH GOHIL |  | 97650
2023-08-05 | SADHU CHARAN BOIPAI |  | 291060
2023-08-06 | DEVILAL PURTY |  | 100800
2023-08-07 | ABHINAY KUMAR |  | 253260
2023-08-09 | ANSARI ATIQ SHAKEEL |  | 76800
2023-08-10 | SK ANUWAR |  | 31200
2023-08-11 | RUPAL DILIP TANK |  | 25200
2023-08-11 | UDAY KUMAR |  | 151680
2023-08-12 | WATER PUMP HIRE SERVICE |  | 4332
2023-08-12 | BEHRA GUIYA |  | 109800
2023-08-16 | RAMASHREY PRAJAPATI |  | 5976
2023-08-22 | MOHAMMED SHOAIB BHATI |  | 1250000
2023-08-22 | BHAVESH M SENGHANI |  | 1250000
2023-09-30 | SAKSHI CORPORATION |  | 178471.88
2023-09-26 | THE INDIA CEMENTS LIMITED |  | 111360
2023-09-06 | M/S.SHRIYAA ENTERPRISES |  | 43540.88
2023-09-15 | SHARADA ENTERPRISES |  | 97585.96
2023-09-15 | SHARADA ENTERPRISES |  | 79525.96
2023-09-15 | SHARADA ENTERPRISES |  | 79206.22
2023-09-15 | SHARADA ENTERPRISES |  | 81307.8
2023-09-21 | RAJLAXMI CORPORATION |  | 90147.76
2023-09-28 | M/S.SHRIYAA ENTERPRISES |  | 56758.28
2023-09-29 | JSW CEMENT LIMITED |  | 119250
2023-09-30 | ADINATH ENTERPRISES |  | 23940
2023-09-30 | M/S.SHRIYAA ENTERPRISES |  | 34934.56
2023-09-30 | RAJLAXMI CORPORATION |  | 86832.9
2023-09-30 | SHARADA ENTERPRISES |  | 83197.28
2023-09-30 | SHARADA ENTERPRISES |  | 89389.66
2023-09-30 | SHARADA ENTERPRISES |  | 53573.1
2023-09-08 | ANUPAM ELECTRICALS |  | 10804.08
2023-09-17 | SHREE TECHNOCHEM |  | 106200
2023-09-23 | ANUPAM ELECTRICALS |  | 1198.88
2023-09-28 | THE INDIA CEMENTS LIMITED |  | 489241.6
2024-01-02 | WATER PUMP HIRE SERVICE |  | 5000
2024-01-10 | ADITYA CRANE SERVICE |  | 2500
2024-01-15 | WELCOME ENTERPRIESES |  | 250000
2024-01-15 | PRABHAKAR C.DUDHBHATE |  | 250000
2024-01-16 | BHAVANI ENTERPRISES |  | 400000
2024-01-29 | RUDRA PLUMPBING SYSTEM |  | 500000
2024-02-01 | WATER PUMP HIRE SERVICE |  | 5000
2024-02-10 | RAMASHREY PRAJAPATI |  | 14616
2024-02-12 | NIDA MUJEEB SHAIKH |  | 220800
2024-02-12 | MD ABRAR AHAMAD |  | 223250
2024-02-12 | KAJAL DAS |  | 957000
2024-02-12 | FATIMA JAVED SHAIKH |  | 225000
2024-02-12 | JAVED KATHALU SHAIKH |  | 220000
2024-02-12 | MUJEEB KHATALU SHAIKH |  | 250200
2024-02-12 | MD AALIM |  | 210200
2024-02-12 | MD NIYAZ |  | 225500
2024-02-12 | CHHOTAN RAY |  | 234050
2024-02-12 | SABROJ MAUSAM ALI AHMAD |  | 200500
2024-02-12 | GAURAV BHARAT JABUANI |  | 500000
2024-02-12 | DHARMENDRAKUMAR BHIMANI |  | 957000
2024-02-15 | BHAVANI ENTERPRISES |  | 500000
2024-02-18 | S D ENTERPRISES |  | 469865
2024-02-19 | HEMANI BHARAT JABUANI |  | 650000
2024-02-19 | BHAVESH M SENGHANI HUF |  | 850000
2024-02-19 | MANISHA JITENDRA RAMJIYANI |  | 650000
2024-03-01 | WATER PUMP HIRE SERVICE |  | 5000
2024-03-02 | RAMASHREY PRAJAPATI |  | 7800
2024-03-04 | PANKAJ PAYARCHAND JAIN |  | 200693
2024-03-13 | SHAIKH MUSHTAQ SHAIKH ISAQ |  | 220800
2024-03-13 | PREMILABEN VIJAY RAMJIYANI |  | 576500
2024-03-13 | POOJA D VISHWAKARMA |  | 216211
2024-03-15 | WELCOME ENTERPRIESES |  | 400000
2024-03-15 | PRABHAKAR C.DUDHBHATE |  | 600000
2024-03-15 | S D ENTERPRISES |  | 499000
2024-03-15 | MD KAMRUL HAK |  | 292043
2024-03-15 | CHHOTAN RAY |  | 292043
2024-03-15 | PRAVIND ASHOK KUMAR |  | 322493
2024-03-15 | ANGAD YADAV |  | 322493
2024-03-15 | RAVEENDRA KUMAR PRAJAPATI |  | 322493
2024-03-15 | VISHWANATH RAJKUMAR GUPTA |  | 322493
2024-03-15 | MANOJ KUMAR |  | 322493
2024-03-15 | KAJAL DAS |  | 202467
2024-03-15 | MD NIYAZ |  | 292043
2024-03-15 | HEMANI BHARAT JABUANI |  | 600000
2024-03-15 | MUJEEB KHATALU SHAIKH |  | 508848
2024-03-15 | FATIMA JAVED SHAIKH |  | 508848
2024-03-15 | BHARAT SOMJI PATEL |  | 500000
2024-03-15 | SABROJ MAUSAM ALI AHMAD |  | 200000
2024-03-15 | BHAVANI ENTERPRISES |  | 500000
2024-03-15 | DHARMENDRAKUMAR BHIMANI |  | 322493
2024-03-26 | MD AALIM |  | 223250
2024-03-26 | NIKHIL SHASHIKANT WAGHMARE |  | 850000
2024-03-31 | HARI OM INTERIOR |  | 36200
2024-03-31 | MANISHA V PATEL |  | 35185
2024-03-31 | MANISHA V PATEL |  | 64569
2024-03-31 | MANISHA V PATEL |  | 43852
2024-01-15 | AKAR CONSTRUCTION COMPANY |  | 1271186
2024-02-13 | AKAR CONSTRUCTION COMPANY |  | 2118644
2024-02-15 | UNITEDONE CONSTRUCTION |  | 3805084.75
2024-02-22 | TEJVEER ENTERPRISE |  | 1000000
2024-02-24 | SAMAYPRA INFRA PROJECT PVT LTD |  | 200693
2024-03-01 | SIDDHIVINAYAKCREATIONS FACADE PVT LTD |  | 296133.89
2024-03-01 | AVINASH ENTERPRISE |  | 500000
2024-03-15 | AKAR CONSTRUCTION COMPANY |  | 4240000
2024-03-15 | UNITEDONE CONSTRUCTION |  | 8450136
2024-03-21 | AVINASH VISWANATH MENON |  | 500000
2024-01-01 | SHARADA ENTERPRISES |  | 64601.6
2024-01-01 | SHARADA ENTERPRISES |  | 61936
2024-01-08 | UN CORPORATION |  | 182371.5
2024-01-08 | UN CORPORATION |  | 169301.44
2024-01-08 | AL-BURHAN SAFETY PRODUCTS |  | 5040
2024-01-12 | AL-BURHAN SAFETY PRODUCTS |  | 6440
2024-01-23 | UN CORPORATION |  | 157106.26
2024-01-25 | M/S.SHRIYAA ENTERPRISES |  | 61824
2024-02-14 | UN CORPORATION |  | 146301.18
2024-02-14 | UN CORPORATION |  | 138270.59
2024-02-15 | UN CORPORATION |  | 134662.49
2024-02-15 | SHARADA ENTERPRISES |  | 62720
2024-02-15 | SHARADA ENTERPRISES |  | 61936
2024-02-22 | UN CORPORATION |  | 144272.69
2024-03-06 | UN CORPORATION |  | 183141.01
2024-03-08 | UN CORPORATION |  | 122607
2024-03-13 | UN CORPORATION |  | 184680
2024-03-13 | SHARADA ENTERPRISES |  | 61936
2024-03-13 | R.K.TRADERS |  | 1680
2024-03-26 | SHARADA ENTERPRISES |  | 62720
2024-03-26 | SHARADA ENTERPRISES |  | 31360
2024-03-30 | UN CORPORATION |  | 164160.01
2024-03-30 | UN CORPORATION |  | 158388.75
2024-01-11 | UN CORPORATION |  | 156208.5
2024-01-15 | SHARADA ENTERPRISES |  | 62596.8
2024-01-22 | UN CORPORATION |  | 151334.99
2024-01-01 | THE INDIA CEMENTS LIMITED |  | 75520
2024-01-01 | THE INDIA CEMENTS LIMITED |  | 113280
2024-01-01 | JANATA SAND SUPPLYING CO. |  | 1799.94
2024-01-01 | KIRIT TRADING COMPANY |  | 104832
2024-01-01 | THE INDIA CEMENTS LIMITED |  | 111360
2024-01-01 | THE INDIA CEMENTS LIMITED |  | 111360
2024-01-01 | THE INDIA CEMENTS LIMITED |  | 111360
2024-01-01 | THE INDIA CEMENTS LIMITED |  | 96512
2024-01-01 | THE INDIA CEMENTS LIMITED |  | 89088
2024-01-01 | THE INDIA CEMENTS LIMITED |  | 37120
2024-01-01 | THE INDIA CEMENTS LIMITED |  | 259840
2024-01-01 | THE INDIA CEMENTS LIMITED |  | 111360
2024-01-03 | KIRIT TRADING COMPANY |  | 183680
2024-01-03 | KIRIT TRADING COMPANY |  | 227763.2
2024-01-04 | KIRIT TRADING COMPANY |  | 183680
2024-01-07 | KIRIT TRADING COMPANY |  | 103680
2024-01-07 | KIRIT TRADING COMPANY |  | 183680
2024-01-09 | SAKSHI CORPORATION |  | 84800
2024-01-11 | KIRIT TRADING COMPANY |  | 227763.2
2024-01-11 | KIRIT TRADING COMPANY |  | 183680
2024-01-11 | KIRIT TRADING COMPANY |  | 73472
2024-01-12 | KIRIT TRADING COMPANY |  | 183680
2024-01-12 | KIRIT TRADING COMPANY |  | 73472
2024-01-17 | JANATA SAND SUPPLYING CO. |  | 1799.94
2024-01-22 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 91840
2024-01-22 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 91840
2024-01-22 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 91840
2024-01-22 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 91840
2024-02-01 | KARAN ENTERPRISES |  | 73472
2024-02-05 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 16960
2024-02-05 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 84800
2024-02-06 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 42681.6
2024-02-08 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 145920
2024-02-08 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 145920
2024-02-08 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 91200
2024-02-08 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 91200
2024-02-08 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 91200
2024-02-09 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 91200
2024-02-09 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 18240
2024-02-13 | THE INDIA CEMENTS LIMITED |  | 99840
2024-02-15 | THE INDIA CEMENTS LIMITED |  | 101760
2024-02-15 | THE INDIA CEMENTS LIMITED |  | 111360
2024-02-15 | THE INDIA CEMENTS LIMITED |  | 111360
2024-02-15 | THE INDIA CEMENTS LIMITED |  | 111360
2024-02-15 | THE INDIA CEMENTS LIMITED |  | 111360
2024-02-15 | THE INDIA CEMENTS LIMITED |  | 111360
2024-02-15 | THE INDIA CEMENTS LIMITED |  | 111360
2024-02-15 | THE INDIA CEMENTS LIMITED |  | 74240
2024-02-15 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 16960
2024-02-15 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 84800
2024-02-15 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 91200
2024-02-15 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 91200
2024-02-15 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 91200
2024-02-15 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 91200
2024-02-15 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 91200
2024-02-15 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 91200
2024-02-15 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 91200
2024-02-15 | KIRIT TRADING COMPANY |  | 72960
2024-02-15 | KIRIT TRADING COMPANY |  | 72960
2024-02-15 | KIRIT TRADING COMPANY |  | 72960
2024-02-15 | KIRIT TRADING COMPANY |  | 145920
2024-02-15 | KIRIT TRADING COMPANY |  | 72960
2024-02-15 | KIRIT TRADING COMPANY |  | 109440
2024-02-15 | KIRIT TRADING COMPANY |  | 109440
2024-02-17 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 54720
2024-02-17 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 18240
2024-02-20 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 16960
2024-02-20 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 84800
2024-02-25 | KIRIT TRADING COMPANY |  | 72704
2024-02-25 | KIRIT TRADING COMPANY |  | 72704
2024-02-25 | KIRIT TRADING COMPANY |  | 72704
2024-02-25 | KIRIT TRADING COMPANY |  | 72704
2024-02-26 | KIRIT TRADING COMPANY |  | 159948.8
2024-02-26 | KIRIT TRADING COMPANY |  | 109056
2024-02-26 | KIRIT TRADING COMPANY |  | 145408
2024-03-06 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 18112
2024-03-06 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 90560
2024-03-06 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 90560
2024-03-06 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 90560
2024-03-06 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 90560
2024-03-06 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 90560
2024-03-06 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 90560
2024-03-06 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 90560
2024-03-13 | KIRIT TRADING COMPANY |  | 101760
2024-03-14 | KIRIT TRADING COMPANY |  | 181120
2024-03-14 | KIRIT TRADING COMPANY |  | 181120
2024-03-22 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 90560
2024-03-22 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 90560
2024-03-22 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 39846.4
2024-03-23 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 90560
2024-03-23 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 90560
2024-03-23 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 90560
2024-03-23 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 90560
2024-03-23 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 90560
2024-03-23 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 50713.6
2024-03-26 | KARAN ENTERPRISES |  | 72448
2024-03-30 | THE INDIA CEMENTS LIMITED |  | 99840
2024-01-01 | JSW CEMENT LIMITED |  | 121875
2024-01-01 | JANATA SAND SUPPLYING CO. |  | 7087.5
2024-01-01 | GLOBAL GYPSUM PVT LTD |  | 231000
2024-01-01 | RAJLAXMI CORPORATION |  | 90873.3
2024-01-01 | RAJLAXMI CORPORATION |  | 72066.76
2024-01-01 | RAJLAXMI CORPORATION |  | 69976.2
2024-01-01 | RAJLAXMI CORPORATION |  | 72309.82
2024-01-01 | RAJ TRANSIT INFRA PVT LTD |  | 45760.06
2024-01-01 | SHARADA ENTERPRISES |  | 97795.96
2024-01-01 | SHARADA ENTERPRISES |  | 34147.58
2024-01-01 | SHARADA ENTERPRISES |  | 93750.82
2024-01-01 | SHARADA ENTERPRISES |  | 92391.08
2024-01-01 | SHARADA ENTERPRISES |  | 36696.46
2024-01-01 | SHARADA ENTERPRISES |  | 99740.02
2024-01-01 | SHARADA ENTERPRISES |  | 79564.28
2024-01-01 | ADINATH ENTERPRISES |  | 128080.06
2024-01-01 | M/S.SHRIYAA ENTERPRISES |  | 98621.26
2024-01-02 | H P CORPORATION |  | 84495.6
2024-01-03 | JSW CEMENT LIMITED |  | 121875
2024-01-04 | HARMAN ENGINEERING WORKS |  | 21845.26
2024-01-08 | JSW CEMENT LIMITED |  | 121875
2024-01-08 | OM ENTERPRISES |  | 100846.2
2024-01-08 | AL-BURHAN SAFETY PRODUCTS |  | 71177.4
2024-01-08 | M/S.SHRIYAA ENTERPRISES |  | 34492.5
2024-01-09 | S.S.ENTERPRISES |  | 71979.6
2024-01-09 | JANATA SAND SUPPLYING CO. |  | 9450
2024-01-11 | GLOBAL GYPSUM PVT LTD |  | 249480
2024-01-12 | AL-BURHAN SAFETY PRODUCTS |  | 59314.5
2024-01-15 | RAJ TRANSIT INFRA PVT LTD |  | 23850.76
2024-01-15 | SHARADA ENTERPRISES |  | 36066.46
2024-01-15 | SHARADA ENTERPRISES |  | 92373.76
2024-01-15 | SHARADA ENTERPRISES |  | 26055.76
2024-01-15 | SHARADA ENTERPRISES |  | 94608.16
2024-01-15 | SHARADA ENTERPRISES |  | 96256.66
2024-01-15 | ADINATH ENTERPRISES |  | 98843.86
2024-01-16 | JSW CEMENT LIMITED |  | 121875
2024-01-18 | M/S.SHRIYAA ENTERPRISES |  | 100080.76
2024-01-20 | S.S.ENTERPRISES |  | 33075
2024-01-22 | H P CORPORATION |  | 93051
2024-01-24 | JSW CEMENT LIMITED |  | 119250
2024-01-25 | OM ENTERPRISES |  | 29142.76
2024-01-28 | JSW CEMENT LIMITED |  | 121875
2024-01-30 | M/S.SHRIYAA ENTERPRISES |  | 123238.5
2024-02-03 | R.K.TRADING CO. |  | 20475
2024-02-04 | JANATA SAND SUPPLYING CO. |  | 9450
2024-02-05 | GLOBAL GYPSUM PVT LTD |  | 249480
2024-02-09 | JSW CEMENT LIMITED |  | 124500
2024-02-12 | M/S.SHRIYAA ENTERPRISES |  | 65394
2024-02-14 | H P CORPORATION |  | 90669.6
2024-02-15 | H P CORPORATION |  | 82966.8
2024-02-15 | OM ENTERPRISES |  | 57918
2024-02-15 | ADINATH ENTERPRISES |  | 29694
2024-02-15 | SHARADA ENTERPRISES |  | 91775.26
2024-02-15 | SHARADA ENTERPRISES |  | 28040.26
2024-02-15 | SHARADA ENTERPRISES |  | 89286.76
2024-02-15 | SHARADA ENTERPRISES |  | 92384.26
2024-02-15 | SHARADA ENTERPRISES |  | 98385
2024-02-15 | SHARADA ENTERPRISES |  | 81348.76
2024-02-15 | S.S.ENTERPRISES |  | 85995
2024-02-15 | M/S.SHRIYAA ENTERPRISES |  | 35059.5
2024-02-15 | M/S.SHRIYAA ENTERPRISES |  | 22197
2024-02-15 | SHIV ENTERPRISES |  | 61661.26
2024-02-15 | SHIV ENTERPRISES |  | 63504
2024-02-15 | SHIV ENTERPRISES |  | 91966.88
2024-02-15 | RAJLAXMI CORPORATION |  | 85821.76
2024-02-15 | OM ENTERPRISES |  | 56358.76
2024-02-15 | M/S.SHRIYAA ENTERPRISES |  | 26827.5
2024-02-15 | SHARADA ENTERPRISES |  | 23997.76
2024-02-15 | SHARADA ENTERPRISES |  | 95828.26
2024-02-15 | SHARADA ENTERPRISES |  | 29547
2024-02-15 | SHARADA ENTERPRISES |  | 26643.76
2024-02-17 | S.S.ENTERPRISES |  | 71376.9
2024-02-18 | M/S.SHRIYAA ENTERPRISES |  | 37185.76
2024-02-19 | JSW CEMENT LIMITED |  | 124500
2024-02-21 | JANATA SAND SUPPLYING CO. |  | 7087.5
2024-02-21 | M/S.SHRIYAA ENTERPRISES |  | 27268.5
2024-02-29 | SHIV ENTERPRISES |  | 89822.26
2024-03-03 | JSW CEMENT LIMITED |  | 124500
2024-03-05 | GLOBAL GYPSUM PVT LTD |  | 249480
2024-03-06 | H P CORPORATION |  | 84054.6
2024-03-13 | SHARADA ENTERPRISES |  | 33831
2024-03-13 | SHARADA ENTERPRISES |  | 93812.26
2024-03-13 | SHARADA ENTERPRISES |  | 69363
2024-03-13 | SHARADA ENTERPRISES |  | 72812.26
2024-03-13 | SHARADA ENTERPRISES |  | 84259.36
2024-03-13 | H P CORPORATION |  | 95167.8
2024-03-13 | OM ENTERPRISES |  | 28995.76
2024-03-13 | SHIV ENTERPRISES |  | 98610.76
2024-03-13 | SHIV ENTERPRISES |  | 92510.26
2024-03-13 | SHIV ENTERPRISES |  | 69977.26
2024-03-13 | SHIV ENTERPRISES |  | 22895.26
2024-03-13 | CHIRAG ENTERPRISES |  | 28628.26
2024-03-13 | ADINATH ENTERPRISES |  | 58763.26
2024-03-15 | ADINATH ENTERPRISES |  | 29032.5
2024-03-18 | M/S.SHRIYAA ENTERPRISES |  | 22197
2024-03-26 | SHARADA ENTERPRISES |  | 91518
2024-03-26 | SHARADA ENTERPRISES |  | 29988
2024-03-26 | SHARADA ENTERPRISES |  | 95371.52
2024-03-26 | SHARADA ENTERPRISES |  | 64149.76
2024-03-26 | SHARADA ENTERPRISES |  | 51228.46
2024-03-27 | M/S.SHRIYAA ENTERPRISES |  | 83223
2024-03-30 | GLOBAL GYPSUM PVT LTD |  | 249480
2024-03-30 | JSW CEMENT LIMITED |  | 124500
2024-03-30 | M/S.SHRIYAA ENTERPRISES |  | 63598.5
2024-03-30 | OM ENTERPRISES |  | 69205.5
2024-03-31 | OM ENTERPRISES |  | 70434
2024-03-30 | SHREEJI WOODCRAFT PVT LTD |  | 866812.07
2024-03-30 | SHREEJI WOODCRAFT PVT LTD |  | 79501.32
2024-03-30 | SHREEJI WOODCRAFT PVT LTD |  | 398335.1
2024-03-30 | SHREEJI WOODCRAFT PVT LTD |  | 664797.84
2024-01-01 | ANUPAM ELECTRICALS |  | 7611
2024-01-01 | VEDANT MARKETING |  | 102837
2024-01-01 | VEDANT MARKETING |  | 32284.8
2024-01-01 | HITECH CONSTRUCTIONS AND REPAIRS |  | 43660
2024-01-01 | R.K.TRADING CO. |  | 7080
2024-01-03 | KARRMANYA ENTERPRISE |  | 761241.6
2024-01-03 | KARRMANYA ENTERPRISE |  | 45916.16
2024-01-05 | VEDANT MARKETING |  | 32284.8
2024-01-06 | KARRMANYA ENTERPRISE |  | 370829.16
2024-01-08 | UN CORPORATION |  | 19500
2024-01-08 | AL-BURHAN SAFETY PRODUCTS |  | 22854.24
2024-01-08 | ANUPAM ELECTRICALS |  | 10856
2024-01-08 | AQUA ENVIRONMENTAL ENGINEERS |  | 212400
2024-01-09 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 1945447.12
2024-01-09 | KRISHNA TRADING CORPORATION |  | 62955.36
2024-01-09 | VEDANT MARKETING |  | 82446.6
2024-01-09 | KARRMANYA ENTERPRISE |  | 339915.52
2024-01-11 | UN CORPORATION |  | 19500
2024-01-11 | KRISHNA TRADING CORPORATION |  | 79591
2024-01-12 | KARRMANYA ENTERPRISE |  | 15406.08
2024-01-12 | AL-BURHAN SAFETY PRODUCTS |  | 48406.56
2024-01-13 | KARRMANYA ENTERPRISE |  | 86099.88
2024-01-15 | CHANDRAKANT ELECTRICAL & CONTRACTOR |  | 984903.04
2024-01-15 | CHANDRAKANT ELECTRICAL & CONTRACTOR |  | 742085.48
2024-01-16 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2011810.32
2024-01-16 | VEDANT MARKETING |  | 61879.2
2024-01-18 | BAADSHAH STEEL |  | 419372
2024-01-18 | R.K.TRADERS |  | 7646.4
2024-01-20 | S.S.ENTERPRISES |  | 56050
2024-01-21 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2002948.52
2024-01-22 | UN CORPORATION |  | 19500
2024-01-22 | KARRMANYA ENTERPRISE |  | 3600
2024-01-22 | KARRMANYA ENTERPRISE |  | 397991.58
2024-01-23 | KARRMANYA ENTERPRISE |  | 13520
2024-01-23 | UN CORPORATION |  | 19500
2024-01-23 | VEDANT MARKETING |  | 82446.6
2024-01-24 | KARRMANYA ENTERPRISE |  | 875071.48
2024-01-27 | BAADSHAH STEEL |  | 801220
2024-02-03 | S.S.ENTERPRISES |  | 56050
2024-02-05 | TEJAS CERAMICS |  | 20699.56
2024-02-06 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2007155.22
2024-02-10 | KARRMANYA ENTERPRISE |  | 66890.66
2024-02-13 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2077451.36
2024-02-14 | UN CORPORATION |  | 19500
2024-02-14 | UN CORPORATION |  | 19500
2024-02-15 | VEDANT MARKETING |  | 108465.6
2024-02-15 | KRISHNA TRADING CORPORATION |  | 91119.6
2024-02-15 | KRISHNA CERAMICS |  | 18054
2024-02-15 | MEHTA PLYWOOD |  | 26998.4
2024-02-15 | BAADSHAH STEEL |  | 1183540
2024-02-15 | GLOBAL GYPSUM PVT LTD |  | 14160
2024-02-19 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 65914.8
2024-02-19 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2003229.36
2024-02-20 | VEDANT MARKETING |  | 102837
2024-02-20 | KARRMANYA ENTERPRISE |  | 19420.44
2024-02-22 | UN CORPORATION |  | 19500
2024-02-26 | KRISHNA TRADING CORPORATION |  | 64696.46
2024-02-28 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2106618.6
2024-03-04 | TEJAS CERAMICS |  | 90999.53
2024-03-04 | VEDANT MARKETING |  | 102837
2024-03-06 | UN CORPORATION |  | 19500
2024-03-08 | UN CORPORATION |  | 19500
2024-03-09 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2072080
2024-03-13 | UN CORPORATION |  | 19500
2024-03-13 | S.S.ENTERPRISES |  | 56050
2024-03-13 | BECS COATING |  | 8354.4
2024-03-13 | KARRMANYA ENTERPRISE |  | 15360.06
2024-03-13 | KARRMANYA ENTERPRISE |  | -1593
2024-03-13 | KARRMANYA ENTERPRISE |  | -69241.22
2024-03-13 | SKY TELECOM |  | 19765
2024-03-13 | SKY TELECOM |  | 26756.5
2024-03-13 | SKY TELECOM |  | 4484
2024-03-13 | KARRMANYA ENTERPRISE |  | 21594
2024-03-14 | D.R LINKS |  | 111598.5
2024-03-15 | CHANDRAKANT ELECTRICAL & CONTRACTOR |  | 880939.72
2024-03-15 | CHANDRAKANT ELECTRICAL & CONTRACTOR |  | 934228
2024-03-15 | KARRMANYA ENTERPRISE |  | 7767.94
2024-03-15 | TEJAS CERAMICS |  | 12600
2024-03-15 | KARRMANYA ENTERPRISE |  | 74525.26
2024-03-17 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2122142.68
2024-03-19 | KARRMANYA ENTERPRISE |  | 315151.34
2024-03-26 | VEDANT MARKETING |  | 123227.4
2024-03-30 | KRISHNA TRADING CORPORATION |  | 159300
2024-03-30 | UN CORPORATION |  | 9749.99
2024-03-30 | UN CORPORATION |  | 9749.99
2024-03-30 | GLOBAL GYPSUM PVT LTD |  | 33984
2024-03-30 | KRISHNA TRADING CORPORATION |  | 42214.5
2024-03-31 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2080349.44
2024-03-31 | H V ENTERPRISE |  | 185257.06
2024-03-31 | DILIP PAINT & HARDWARE STORES |  | 72134.58
2024-04-04 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 179200
2024-04-13 | JANATA SAND SUPPLYING CO. |  | 1799.94
2024-04-14 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 16832
2024-04-14 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 84160
2024-04-14 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 181120
2024-04-20 | THE INDIA CEMENTS LIMITED |  | 65664
2024-04-21 | THE INDIA CEMENTS LIMITED |  | 102144
2024-04-21 | THE INDIA CEMENTS LIMITED |  | 102144
2024-04-21 | THE INDIA CEMENTS LIMITED |  | 102144
2024-04-21 | THE INDIA CEMENTS LIMITED |  | 109440
2024-04-21 | THE INDIA CEMENTS LIMITED |  | 109440
2024-04-21 | THE INDIA CEMENTS LIMITED |  | 109440
2024-04-21 | THE INDIA CEMENTS LIMITED |  | 102144
2024-05-07 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 89600
2024-05-07 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 89600
2024-05-07 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 89600
2024-05-07 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 89600
2024-05-12 | KIRIT TRADING COMPANY |  | 250880
2024-05-12 | KIRIT TRADING COMPANY |  | 179200
2024-05-13 | WEATHER COOL SERVICES |  | 210000.02
2024-05-15 | KIRIT TRADING COMPANY |  | 176000
2024-05-15 | KIRIT TRADING COMPANY |  | 176000
2024-05-16 | ZEE ELECTRONICS |  | 41499.12
2024-05-16 | KARAN ENTERPRISES |  | 97920
2024-05-21 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 176000
2024-05-21 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 176000
2024-05-21 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 176000
2024-05-24 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 176000
2024-05-24 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 176000
2024-05-25 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 176000
2024-05-26 | SUNTREK CORPORATION |  | 35200
2024-05-26 | SUNTREK CORPORATION |  | 70400
2024-05-28 | THE INDIA CEMENTS LIMITED |  | 105600
2024-05-31 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 87040
2024-05-31 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 87040
2024-05-31 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 87040
2024-05-31 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 87040
2024-04-02 | JSW CEMENT LIMITED |  | 124500
2024-04-03 | R.K.TRADING CO. |  | 37170
2024-04-08 | M/S.SHRIYAA ENTERPRISES |  | 36842.4
2024-04-10 | SHIV ENTERPRISES |  | 76826.4
2024-04-15 | M/S.SHRIYAA ENTERPRISES |  | 57173.56
2024-04-15 | CHIRAG ENTERPRISES |  | 26739.3
2024-04-15 | NEER TRADING CO. |  | 64921.5
2024-04-15 | S. H. ENTERPRISES |  | 92628.38
2024-04-15 | S. H. ENTERPRISES |  | 74457.6
2024-04-15 | S. H. ENTERPRISES |  | 32886
2024-04-16 | AL-BURHAN SAFETY PRODUCTS |  | 2850.06
2024-04-17 | M/S.SHRIYAA ENTERPRISES |  | 27239.1
2024-04-25 | SHIV ENTERPRISES |  | 29400
2024-04-25 | SHIV ENTERPRISES |  | 79468.2
2024-04-27 | SHIV ENTERPRISES |  | 25168.5
2024-04-28 | GLOBAL GYPSUM PVT LTD |  | 249480
2024-04-30 | NEER TRADING CO. |  | 35945.7
2024-04-30 | SHARADA ENTERPRISES |  | 59103.46
2024-04-30 | S. H. ENTERPRISES |  | 95241.82
2024-04-30 | S. H. ENTERPRISES |  | 57959.48
2024-04-30 | S. H. ENTERPRISES |  | 81312
2024-05-11 | M/S.SHRIYAA ENTERPRISES |  | 33824.7
2024-05-11 | NEER TRADING CO. |  | 115483.2
2024-05-14 | JSW CEMENT LIMITED |  | 127125
2024-05-15 | NEER TRADING CO. |  | 62781.6
2024-05-15 | S. H. ENTERPRISES |  | 85564.5
2024-05-15 | S. H. ENTERPRISES |  | 88384.8
2024-05-15 | S. H. ENTERPRISES |  | 91030.8
2024-05-15 | S. H. ENTERPRISES |  | 53904.9
2024-05-15 | OM ENTERPRISES |  | 144391.8
2024-05-18 | M/S.SHRIYAA ENTERPRISES |  | 57460.2
2024-05-20 | JSW CEMENT LIMITED |  | 127125
2024-05-25 | NEER TRADING CO. |  | 121371.6
2024-05-29 | GLOBAL GYPSUM PVT LTD |  | 249480
2024-05-31 | NEER TRADING CO. |  | 62178.9
2024-05-31 | SHARADA ENTERPRISES |  | 80797.5
2024-05-31 | SHARADA ENTERPRISES |  | 88580.1
2024-05-31 | SHARADA ENTERPRISES |  | 83382.6
2024-05-31 | SHARADA ENTERPRISES |  | 78409.8
2024-05-31 | SHARADA ENTERPRISES |  | 80864.7
2024-05-31 | SHARADA ENTERPRISES |  | 98548.8
2024-05-31 | SHARADA ENTERPRISES |  | 22041.6
2024-05-31 | OM ENTERPRISES |  | 126774.9
2024-04-15 | UN CORPORATION |  | 191092.49
2024-04-15 | S. H. ENTERPRISES |  | 62720
2024-04-15 | S. H. ENTERPRISES |  | 62328
2024-04-16 | UN CORPORATION |  | 164160.01
2024-04-16 | AL-BURHAN SAFETY PRODUCTS |  | 12019.84
2024-04-24 | R.K.TRADING CO. |  | 3360
2024-05-11 | UN CORPORATION |  | 152360.4
2024-05-24 | UN CORPORATION |  | 166724.4
2024-05-27 | UN CORPORATION |  | 169290
2024-04-01 | DILIP PAINT & HARDWARE STORES |  | 73949.42
2024-04-01 | SMT POOJA C. SHAH |  | 5900
2024-04-02 | KRISHNA TRADING CORPORATION |  | 94164
2024-04-03 | KARRMANYA ENTERPRISE |  | 125438.72
2024-04-03 | KARRMANYA ENTERPRISE |  | 8500.72
2024-04-04 | HEM ENTERPRISE |  | 188800
2024-04-05 | KRISHNA CERAMICS |  | 212400
2024-04-06 | KRISHNA TRADING CORPORATION |  | 93810
2024-04-06 | VEDANT MARKETING |  | 123227.4
2024-04-12 | D.R LINKS |  | 38444.4
2024-04-12 | D.R LINKS |  | 15222
2024-04-12 | D.R LINKS |  | 3026.7
2024-04-12 | Siddhivinayak Electrical & Hardware |  | 126006.3
2024-04-15 | DINESH ENTERPRISES |  | 408971.43
2024-04-15 | UN CORPORATION |  | 9749.99
2024-04-15 | S.S.ENTERPRISES |  | 28320
2024-04-16 | UN CORPORATION |  | 9749.99
2024-04-16 | AL-BURHAN SAFETY PRODUCTS |  | 67293.04
2024-04-18 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2210999.04
2024-04-22 | KARRMANYA ENTERPRISE |  | 23348.66
2024-04-23 | UNIQUE SPACE INTERIOR |  | 590000
2024-04-23 | KRISHNA TRADING CORPORATION |  | 125888.3
2024-04-24 | JONES LANG LASALLE PROPERTY CONSULTANTS INDIA PVT |  | 759299.32
2024-04-24 | R.K.TRADING CO. |  | 118
2024-04-25 | KARRMANYA ENTERPRISE |  | 2024.88
2024-04-25 | KRISHNA CERAMICS |  | 3658
2024-04-27 | SAMAYPRA INFRA PROJECT PVT LTD |  | 531817.74
2024-04-30 | D.R LINKS |  | 55412.8
2024-04-30 | D.R LINKS |  | 2076.8
2024-05-01 | AVINASH ENTERPRISE |  | 590000
2024-05-01 | SMT POOJA C. SHAH |  | 5900
2024-05-03 | NAVBHARAT HARDWARE STORES |  | 75661.6
2024-05-04 | TEJAS CERAMICS |  | 4200.22
2024-05-04 | SKY TELECOM |  | 65136
2024-05-07 | LANDMARK CONSULTANTS & ENGG. TECHNOLOGY |  | 9912
2024-05-07 | D.R LINKS |  | 34043
2024-05-08 | SKY TELECOM |  | 37406
2024-05-10 | WEATHER COOL SERVICES |  | 20698
2024-05-11 | VEDANT MARKETING |  | 51684
2024-05-11 | UN CORPORATION |  | 19500
2024-05-12 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2222237.36
2024-05-13 | CHANDRAKANT ELECTRICAL & CONTRACTOR |  | 481419.36
2024-05-13 | D.R LINKS |  | 9227.6
2024-05-15 | AKAR CONSTRUCTION COMPANY |  | 4999999.84
2024-05-15 | ROYAL GLASS HOUSE |  | 160000.16
2024-05-15 | HITECH CONSTRUCTIONS AND REPAIRS |  | 98884
2024-05-15 | KRISHNA TRADING CORPORATION |  | 34302.6
2024-05-15 | KRISHNA TRADING CORPORATION |  | 56864.2
2024-05-16 | ZEE ELECTRONICS |  | 15000.01
2024-05-16 | RAJ ALUMINIUM |  | 295944
2024-05-16 | KRISHNA TRADING CORPORATION |  | 18755.8
2024-05-16 | D.R LINKS |  | 83308
2024-05-17 | GYPSO INDIA |  | 708000.04
2024-05-18 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2336154.56
2024-05-18 | D.R LINKS |  | 56647.08
2024-05-18 | R.K.TRADERS |  | 4012
2024-05-20 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2185280.94
2024-05-21 | VEDANT MARKETING |  | 123227.4
2024-05-23 | NAVBHARAT HARDWARE STORES |  | 8466.5
2024-05-24 | S.S.ENTERPRISES |  | 28320
2024-05-24 | UN CORPORATION |  | 19500
2024-05-27 | UN CORPORATION |  | 19500
2024-05-30 | KRISHNA TRADING CORPORATION |  | 9442.36
2024-05-30 | KRISHNA TRADING CORPORATION |  | 140869
2024-05-31 | AXLER WOODWORKS LLP |  | 224206.99
2024-06-02 | SUNTREK CORPORATION |  | 70400
2024-06-02 | SUNTREK CORPORATION |  | 26048
2024-06-02 | SUNTREK CORPORATION |  | 26048
2024-06-02 | SUNTREK CORPORATION |  | 24640
2024-06-02 | SUNTREK CORPORATION |  | 70400
2024-06-02 | SUNTREK CORPORATION |  | 70400
2024-06-02 | SUNTREK CORPORATION |  | 1408
2024-06-09 | SUNTREK CORPORATION |  | 23674.88
2024-06-09 | SUNTREK CORPORATION |  | 69632
2024-06-09 | SUNTREK CORPORATION |  | 69632
2024-06-09 | SUNTREK CORPORATION |  | 34816
2024-06-09 | SUNTREK CORPORATION |  | 69632
2024-06-09 | SUNTREK CORPORATION |  | 34816
2024-06-10 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 172800
2024-06-10 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 172800
2024-06-10 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 172800
2024-06-11 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 17280
2024-06-11 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) |  | 86400
2024-06-22 | THE INDIA CEMENTS LIMITED |  | 103680
2024-06-22 | THE INDIA CEMENTS LIMITED |  | 86400
2024-06-22 | THE INDIA CEMENTS LIMITED |  | 79488
2024-06-22 | THE INDIA CEMENTS LIMITED |  | 76032
2024-06-02 | JSW CEMENT LIMITED |  | 127125
2024-06-08 | JSW CEMENT LIMITED |  | 127125
2024-06-13 | NEER TRADING CO. |  | 53726.4
2024-06-15 | S. H. ENTERPRISES |  | 78733.2
2024-06-15 | S. H. ENTERPRISES |  | 88993.8
2024-06-15 | S. H. ENTERPRISES |  | 85457.4
2024-06-15 | S. H. ENTERPRISES |  | 81471.6
2024-06-15 | S. H. ENTERPRISES |  | 80973.9
2024-06-15 | S. H. ENTERPRISES |  | 92366.4
2024-06-15 | S. H. ENTERPRISES |  | 95904.9
2024-06-15 | S. H. ENTERPRISES |  | 90098.4
2024-06-15 | S. H. ENTERPRISES |  | 25872
2024-06-15 | JSW CEMENT LIMITED |  | 127125
2024-06-15 | S.S.ENTERPRISES |  | 84577.5
2024-06-29 | JSW CEMENT LIMITED |  | 127125
2024-06-29 | R.K.TRADING CO. |  | 25725
2024-06-30 | SHARADA ENTERPRISES |  | 76251
2024-06-30 | SHARADA ENTERPRISES |  | 25200
2024-06-05 | UN CORPORATION |  | 126711
2024-06-30 | SHARADA ENTERPRISES |  | 62720
2024-06-01 | VEDANT MARKETING |  | 123227.4
2024-06-01 | SMT POOJA C. SHAH |  | 5900
2024-06-03 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2162524.64
2024-06-04 | R.R. ENTERPRISES |  | 1982.4
2024-06-05 | UN CORPORATION |  | 11699.99
2024-06-07 | P.R.CRAFT AND DESIGN |  | 143770.31
2024-06-08 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2239055.9
2024-06-08 | P.R.CRAFT AND DESIGN |  | 258271.6
2024-06-10 | D.R LINKS |  | 83072
2024-06-10 | P.R.CRAFT AND DESIGN |  | 235585.58
2024-06-11 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2062134.96
2024-06-11 | P.R.CRAFT AND DESIGN |  | 117400.85
2024-06-11 | H V ENTERPRISE |  | 9345.6
2024-06-13 | VEDANT MARKETING |  | 61879.2
2024-06-15 | D.R LINKS |  | 11682
2024-06-15 | KARRMANYA ENTERPRISE |  | 71732.99
2024-06-16 | KRISHNA TRADING CORPORATION |  | 41111.2
2024-06-18 | ANUPAM ELECTRICALS |  | 1121
2024-06-19 | SHREEJI WATER PUMPS & BOREWELL |  | 100300
2024-06-19 | JONES LANG LASALLE PROPERTY CONSULTANTS INDIA PVT |  | 1938138.2
2024-06-19 | DILIP PAINT & HARDWARE STORES |  | 61776.54
2024-06-21 | S.S.ENTERPRISES |  | 28320
2024-06-23 | SUSHMA CONTRUCTION STEEL SALES LLP |  | 2028381.06
2024-06-23 | KRISHNA TRADING CORPORATION |  | 18691.2
2024-06-25 | KRISHNA TRADING CORPORATION |  | 3635.58
2024-06-29 | KRISHNA TRADING CORPORATION |  | 36698
2024-06-30 | NAVBHARAT HARDWARE STORES |  | 37099.2
2024-07-01 | WEATHER COOL SERVICES | 339 | 95403
2024-07-01 | RAJAN MENDA | 181 | 2000
2024-07-01 | NIRMALA TAMBEWAGH | 01/2024 | 577182
2024-07-01 | BABURAM SAHANI |  | 14850
2024-07-01 | DIGIPACE CONSULTING (OPC) PRIVATE LIMITED | 84 | 386304
2024-07-01 | SATWANT SINGH BHAMBRA | 001 | 380100
2024-07-01 | VAISHALI P.DUDHBHATE | 023 | 150000
2024-07-01 | JONES LANG LASALLE PROPERTY CONSULTANTS INDIA PVT | PC/MH/2425/00220 | 564796
2024-07-01 | S.R.INDUSTRIES | 29 | 67840
2024-07-03 | KARRMANYA ENTERPRISE | 231/2024/2025 | 691786
2024-07-03 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/1165/24-25 | 2112914
2024-07-03 | KOMAL ENTERPRISES | 039 | 90300
2024-07-04 | VEDANT MARKETING | VM/24-25/0939 | 123227
2024-07-04 | SUNTREK CORPORATION | SC/JULY/2425/07 | 67840
2024-07-04 | SUNTREK CORPORATION | SC/JULY/2425/08 | 33920
2024-07-04 | SUNTREK CORPORATION | SC/JULY/2425/09 | 67840
2024-07-04 | SUNTREK CORPORATION | SC/JULY/2425/10 | 16960
2024-07-04 | SUNTREK CORPORATION | SC/JULY/2425/11 | 67840
2024-07-04 | SUNTREK CORPORATION | SC/JULY/2425/12 | 16960
2024-07-04 | KRISHNA TRADING CORPORATION | 391 | 145400
2024-07-05 | U N CORPORATION | UNC/1054/24-25 | 19500
2024-07-05 | U N CORPORATION | UNC/1053/24-25 | 116708
2024-07-05 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360133972 | 16128
2024-07-05 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360133971 | 80640
2024-07-07 | M/S.SHRIYAA ENTERPRISES | 5192 | 79834
2024-07-09 | R.K.TRADERS | RKT/279/24-25 | 5016
2024-07-10 | Thakkar Electrical Works | 208 | 28500
2024-07-10 | Thakkar Electrical Works | 209 | 61000
2024-07-10 | WATER PUMP HIRE SERVICE | 1102 | 10000
2024-07-10 | DIPESH BHARWAD |  | 42905
2024-07-11 | AQUA ENVIRONMENTAL ENGINEERS | AEE/24/25/017 | 318600
2024-07-11 | HITECH CONSTRUCTIONS AND REPAIRS | MH/48/24-25 | 58882
2024-07-13 | KARRMANYA ENTERPRISE | 258/2024/2025 | 4102
2024-07-14 | BHAVANI ENTERPRISES |  | 433005
2024-07-15 | BHAVESH M SENGHANI | 001/24-25 | 1000000
2024-07-15 | MD NIYAZ | 001/24-25 | 300000
2024-07-15 | SHAIKH MUSHTAQ SHAIKH ISAQ | 001/24-24 | 485000
2024-07-15 | MUJEEB KHATALU SHAIKH | 001/24-25 | 485000
2024-07-15 | SABROJ MAUSAM ALI AHMAD | 001/24-25 | 84000
2024-07-15 | PRAVIND ASHOK KUMAR | 001/24-25 | 318850
2024-07-15 | CHHOTAN RAY | 001/24-25 | 300000
2024-07-15 | MD HAFIJUL ISLAM |  | 70000
2024-07-15 | HEMANI BHARAT JABUANI | 001/24-25 | 637700
2024-07-15 | GAURAV BHARAT JABUANI | 001/24-25 | 889500
2024-07-15 | JSW CEMENT LIMITED | MH2403056770 | 127125
2024-07-15 | NEER TRADING CO. | NT/47/24-25 | 28739
2024-07-15 | SHARADA ENTERPRISES | 121 | 90029
2024-07-15 | SHARADA ENTERPRISES | 122 | 72400
2024-07-15 | SHARADA ENTERPRISES | 123 | 95788
2024-07-15 | SHARADA ENTERPRISES | 124 | 95796
2024-07-15 | SHARADA ENTERPRISES | 125 | 92471
2024-07-15 | SHARADA ENTERPRISES | 126 | 87343
2024-07-15 | SHARADA ENTERPRISES | 127 | 51337
2024-07-16 | UNIQUE SPACE INTERIOR | USI-25 | 76842
2024-07-16 | U N CORPORATION | UNC/1190/24-25 | 9750
2024-07-16 | U N CORPORATION | UNC/1189/24-25 | 179306
2024-07-16 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360134604 | 83200
2024-07-16 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360134605 | 83200
2024-07-16 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360134606 | 83200
2024-07-16 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360134607 | 83200
2024-07-17 | GLOBAL GYPSUM PVT LTD | 217 | 249480
2024-07-18 | VEDANT MARKETING | VM/24-25/1048 | 123227
2024-07-18 | KRISHNA TRADING CORPORATION | 432 | 15092
2024-07-19 | SUNTREK CORPORATION | SC/JULY/2425/43 | 16640
2024-07-19 | SUNTREK CORPORATION | SC/JULY/2425/42 | 66560
2024-07-19 | SUNTREK CORPORATION | SC/JULY/2425/41 | 16640
2024-07-19 | SUNTREK CORPORATION | SC/JULY/2425/40 | 66560
2024-07-19 | SUNTREK CORPORATION | SC/JULY/2425/39 | 22630
2024-07-19 | SUNTREK CORPORATION | SC/JULY/2425/38 | 66560
2024-07-19 | SUNTREK CORPORATION | SC/JULY/2425/37 | 33280
2024-07-19 | SUNTREK CORPORATION | SC/JULY/2425/36 | 66560
2024-07-20 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/1356/24-25 | 1998774
2024-07-20 | SHREE RAM ENTERPRISES | 6 | 1240000
2024-07-22 | STAR WINDOWS | 083 | 629250
2024-07-22 | KARRMANYA ENTERPRISE | 278/2024/2025 | 1044569
2024-07-22 | MODELS FOV | 24-25/MF/NLK/12 | 604750
2024-07-23 | KRISHNA CERAMICS | 33 | 50150
2024-07-24 | VISHAL CHAVAN | 002 | 533263
2024-07-24 | S. S. ENTERPRISES | 247/24-25 | 28320
2024-07-25 | JONES LANG LASALLE PROPERTY CONSULTANTS INDIA PVT | PC/MH/2425/00332 | 187686
2024-07-25 | HITECH CONSTRUCTIONS AND REPAIRS | MH/51/24-25 | 93220
2024-07-25 | R.K.TRADERS | RKT/325/24-25 | 6018
2024-07-27 | U N CORPORATION | UNC/1308/24-25 | 11700
2024-07-27 | U N CORPORATION | UNC/1307/24-25 | 139608
2024-07-29 | S. S. ENTERPRISES | 255/24-25 | 72198
2024-07-29 | S. S. ENTERPRISES | 262/24-25 | 75684
2024-07-29 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360135347 | 15680
2024-07-29 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360135346 | 78400
2024-07-30 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/1432/24-25 | 1431500
2024-07-30 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/1433/24-25 | 381426
2024-07-30 | MEHTA PLYWOOD | 340-24-25 | 7363
2024-07-30 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360135425 | 81600
2024-07-30 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360135427 | 81600
2024-07-30 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360135432 | 81600
2024-07-30 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360135449 | 81600
2024-07-30 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360135455 | 81600
2024-07-30 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360135466 | 81600
2024-07-30 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360135484 | 81600
2024-07-30 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360135485 | 81600
2024-07-30 | U N CORPORATION | UNC/1346/24-25 | 11700
2024-07-30 | U N CORPORATION | UNC/1345/24-25 | 156240
2024-07-31 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/1454/24-25 | 70651
2024-07-31 | MEELI RAI SHARMA | 1 | 168113
2024-07-31 | KRISHNA TRADING CORPORATION | 28 | 12744
2024-07-31 | MEHTA PLYWOOD | 311-24-25 | 19635
2024-07-31 | MEHTA PLYWOOD | 293-24-25 | 4909
2024-07-31 | MEHTA PLYWOOD | 279-24-25 | 14726
2024-07-31 | SHARADA ENTERPRISES | 164 | 90836
2024-07-31 | SHARADA ENTERPRISES | 165 | 85662
2024-07-31 | SHARADA ENTERPRISES | 166 | 87343
2024-07-31 | SHARADA ENTERPRISES | 167 | 91252
2024-07-31 | SHARADA ENTERPRISES | 168 | 61824
2024-08-01 | SMT. POOJA C. SHAH |  | 5900
2024-08-02 | MEHTA PLYWOOD | 352-24-25 | 2454
2024-08-02 | KARRMANYA ENTERPRISE | 333/2024/2025 | 261856
2024-08-03 | MARKETING CHANAKYA | PR-37-24 | 8850
2024-08-03 | S. S. ENTERPRISES | 277/24-25 | 27730
2024-08-06 | S. S. ENTERPRISES | 286/24-25 | 54870
2024-08-07 | SM INTEGRATED SERVICES | SMIS-019 | 131100
2024-08-07 | DILIP PAINT& HARDWARE STORES | 287 | 59242
2024-08-08 | U N CORPORATION | UNC/1469/24-25 | 141036
2024-08-08 | U N CORPORATION | UNC/1470/24-25 | 11700
2024-08-08 | MK MAT | 24-25/16 | 39782
2024-08-11 | JSW CEMENT LIMITED | MH2403073538 | 127125
2024-08-12 | VEDANT MARKETING | VM/24-25/1246 | 123227
2024-08-12 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360136384 | 30720
2024-08-12 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360136383 | 61440
2024-08-13 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/1580/24-25 | 762087
2024-08-13 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/1579/24-25 | 1111383
2024-08-13 | S. S. ENTERPRISES | 312/24-25 | 54870
2024-08-14 | SANTOSH J. SAROJ | 026 | 50000
2024-08-14 | PRABHAKAR C.DUDHBHATE | 027 | 50000
2024-08-14 | CHANDRAKANT T. DUDHBHATE | 025 | 150000
2024-08-14 | VAISHALI P.DUDHBHATE | 024 | 100000
2024-08-14 | GLOBAL GYPSUM PVT LTD | 259 | 323400
2024-08-15 | SHARADA ENTERPRISES | 181 | 89930
2024-08-15 | SHARADA ENTERPRISES | 182 | 82975
2024-08-15 | SHARADA ENTERPRISES | 183 | 34474
2024-08-15 | SHARADA ENTERPRISES | 179 | 86720
2024-08-15 | SHARADA ENTERPRISES | 180 | 93859
2024-08-15 | SHARADA ENTERPRISES | 178 | 76078
2024-08-15 | SHARADA ENTERPRISES | 177 | 87879
2024-08-16 | AKAR CONSTRUCTION COMPANY | 011/24-25 | 6000000
2024-08-20 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/1633/24-25 | 1898415
2024-08-20 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360137032 | 80000
2024-08-20 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360137033 | 80000
2024-08-20 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360137054 | 80000
2024-08-20 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360137070 | 80000
2024-08-20 | KRISHNA CERAMICS | 44 | 100300
2024-08-21 | AVINASH ENTERPRISE | 187 | 634014
2024-08-21 | REKHA TRADING |  | 537300
2024-08-21 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/1646/24-25 | 73313
2024-08-21 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360137145 | 80024
2024-08-21 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360137362 | 80080
2024-08-21 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360137184 | 80080
2024-08-21 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360137185 | 80080
2024-08-21 | U N CORPORATION | UNC/1674/24-25 | 19500
2024-08-21 | LA CERAMICA | 810/24-25 | 32000
2024-08-22 | SKY TELECOM | ST/2024-25/219 | 58292
2024-08-23 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360137361 | 15376
2024-08-23 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360137360 | 76877
2024-08-23 | U N CORPORATION | UNC/1698/24-25 | 142262
2024-08-23 | U N CORPORATION | UNC/1699/24-25 | 11700
2024-08-24 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/1688/24-25 | 1943958
2024-08-24 | HITECH CONSTRUCTIONS AND REPAIRS | MH/61/24-25 | 93220
2024-08-25 | JANATASAND SUPPLYING CO. | 1299 | 10688
2024-08-26 | MD HAFIJUL ISLAM |  | 150000
2024-08-26 | H.P.CORPORATION | HPC/0640/24-25 | 6375
2024-08-26 | H.P.CORPORATION | HPC/0635/24-25 | 145200
2024-08-28 | JANATASAND SUPPLYING CO. | 1302 | 2363
2024-08-28 | MEHTA PLYWOOD | 438-24-25 | 7500
2024-08-28 | VEDANT MARKETING | VM/24-25/1397 | 123227
2024-08-28 | JSW CEMENT LIMITED | MH2403084628 | 127125
2024-08-28 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360137774 | 81682
2024-08-28 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360137775 | 81682
2024-08-29 | KARRMANYA ENTERPRISE | 392/2024-2025 | 788268
2024-08-29 | U N CORPORATION | UNC/1786/24-25 | 162989
2024-08-29 | U N CORPORATION | UNC/1787/24-25 | 15600
2024-08-29 | KRISHNA TRADING CORPORATION | 584 | 253110
2024-08-31 | SHREEJI WOODCRAFT PVT LTD | SS/PSI/2425/0134 | 36698
2024-08-31 | SKY TELECOM | ST/2024-25/113 | 4484
2024-08-31 | SHARADA ENTERPRISES | 203 | 87343
2024-08-31 | SHARADA ENTERPRISES | 204 | 87879
2024-08-31 | SHARADA ENTERPRISES | 205 | 83811
2024-08-31 | SHARADA ENTERPRISES | 206 | 81644
2024-08-31 | SHARADA ENTERPRISES | 207 | 79218
2024-08-31 | SHARADA ENTERPRISES | 208 | 75823
2024-08-31 | SHARADA ENTERPRISES | 229 | 78540
2024-08-31 | SHARADA ENTERPRISES | 230 | 85661
2024-08-31 | SHARADA ENTERPRISES | 231 | 85661
2024-08-31 | SHARADA ENTERPRISES | 232 | 59993
2024-08-31 | SHARADA ENTERPRISES | 209 | 95042
2024-08-31 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360138069 | 80721
2024-08-31 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360138072 | 80721
2024-08-31 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360138068 | 80721
2024-08-31 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360138067 | 80721
2024-08-31 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360138073 | 64577
2024-08-31 | NEER TRADING CO. | NT/67/24-25 | 132710
2024-08-31 | AXLER WOODWORKS LLP | AW/24-25/15 | 140420
2024-09-01 | JONES LANG LASALLE PROPERTY CONSULTANTS INDIA PVT | PC/MH/2425/00409 | 1569029
2024-09-01 | WIZFX COMMUNICATIONS PRIVATE LIMITED | REF-M-34/02/2023-24 | 35400
2024-09-01 | KAILASH ENTERPRISES | 02/01 | 17330
2024-09-01 | RAMASHREY PRAJAPATI | 626 | 14676
2024-09-01 | WATER PUMP HIRE SERVICE | 1164 | 23000
2024-09-01 | ALLARAKHA ABDUL SALAM SHAIKH | 02/24-25 | 386304
2024-09-01 | KAN INDIA REALTORS PRIVATE LIMITED | IN2024MH250 | 447216
2024-09-01 | REAL ESTATE CORNER |  | 289462
2024-09-01 | KARAN POOJARI | 81 | 212700
2024-09-01 | K.R.ENTERPRISES | 751 | 4300
2024-09-01 | K.R.ENTERPRISES | 734 | 64500
2024-09-01 | NEER TRADING CO. | NT/68/24-25 | 30845
2024-09-01 | AVINASH ENTERPRISE |  | 330404
2024-09-01 | SB ENTERPRISES-TRANSPORT | 092 | 73100
2024-09-01 | THE INDIA CEMENTS LIMITED | 198/25103136 | 32256
2024-09-01 | THE INDIA CEMENTS LIMITED | 198/25103125 | 96768
2024-09-01 | THE INDIA CEMENTS LIMITED | 198/25103126 | 96768
2024-09-01 | THE INDIA CEMENTS LIMITED | 198/25103112 | 96768
2024-09-01 | SHREEJI WATER PUMPS & BOREWELL | 050/2024-25 | 61242
2024-09-01 | SHREEJI WATER PUMPS & BOREWELL | 046/2024-25 | 60770
2024-09-02 | DIGITECH MOBILE MEDIA | DMM/08/09/24 | 147500
2024-09-02 | MD PRINT SOLUTION | INV-0086 | 170000
2024-09-02 | MD PRINT SOLUTION | INV-0087 | 92500
2024-09-02 | ALGORHYTHM INNOVATION | PI-1415 | 240000
2024-09-02 | KARRMANYA ENTERPRISE | 409/2024-2025 | 825801
2024-09-02 | KRISHNA TRADING CORPORATION | 604 | 31907
2024-09-03 | WINNYTINE EVENTS & MARKETING | AP583 | 25000
2024-09-03 | AARAMBH PROPERTIES | 01 | 374366
2024-09-03 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360138316 | 15376
2024-09-03 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360138315 | 76877
2024-09-03 | KOMAL ENTERPRISES | 049 | 47300
2024-09-03 | R.K.TRADING CO. | RK455 | 2832
2024-09-03 | HAMIDA ENTERPRISES |  | 22380
2024-09-04 | DILIP PAINT& HARDWARE STORES | 355 | 5369
2024-09-07 | BELLE VIEW ESTATE AGENCY |  | 400874
2024-09-09 | AVENUE REALTY | 10 | 330637
2024-09-09 | S. S. ENTERPRISES | 400/24-25 | 50150
2024-09-10 | U N CORPORATION | UNC/1998/24-25 | 15600
2024-09-10 | U N CORPORATION | UNC/1997/24-25 | 169243
2024-09-11 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/1916/24-25 | 1892930
2024-09-11 | S. S. ENTERPRISES | 411/24-25 | 50150
2024-09-11 | U N CORPORATION | UNC/2024/24-25 | 142017
2024-09-11 | U N CORPORATION | UNC/2025/24-25 | 15600
2024-09-11 | PROFESSIONAL BUILDING CONTRACTOR | NIC-NK-0924-01 | 98293
2024-09-12 | RAMASHREY PRAJAPATI | 653 | 4332
2024-09-12 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360139031 | 88088
2024-09-12 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360139034 | 88088
2024-09-12 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360139038 | 176176
2024-09-12 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360139045 | 176176
2024-09-13 | S. S. ENTERPRISES | 415/24-25 | 82593
2024-09-13 | GLOBAL GYPSUM PVT LTD | 318 | 260337
2024-09-14 | GANESH SHANKAR J. MISTRY |  | 78000
2024-09-15 | NEER TRADING CO. | NT/71/24-25 | 60797
2024-09-15 | SHARADA ENTERPRISES | 238 | 77175
2024-09-15 | SHARADA ENTERPRISES | 237 | 94232
2024-09-15 | SHARADA ENTERPRISES | 239 | 84790
2024-09-15 | SHARADA ENTERPRISES | 240 | 90235
2024-09-15 | SHARADA ENTERPRISES | 241 | 61507
2024-09-15 | SHARADA ENTERPRISES | 242 | 61824
2024-09-15 | JAGRUT RAMESH JADHAV | RA-1 | 400000
2024-09-16 | U N CORPORATION | UNC/2083/24-25 | 11700
2024-09-16 | U N CORPORATION | UNC/2082/24-25 | 122885
2024-09-16 | KARRMANYA ENTERPRISE | 445/2024-2025 | 50176
2024-09-16 | KARRMANYA ENTERPRISE | 442/2024-2025 | 286941
2024-09-16 | KRISHNA TRADING CORPORATION | 649 | 93810
2024-09-16 | KRISHNA TRADING CORPORATION | 646 | 159300
2024-09-18 | NAVBHARAT HARDWARE STORES | 4591 | 2218
2024-09-18 | KRISHNA TRADING CORPORATION | 658 | 281430
2024-09-18 | MEHTA PLYWOOD | 497-24-25 | 7751
2024-09-19 | S. S. ENTERPRISES | 437/24-25 | 50150
2024-09-19 | KRISHNA TRADING CORPORATION | 662 | 477900
2024-09-21 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/2037/24-25 | 1957467
2024-09-21 | VEDANT MARKETING | VM/24-25/1631 | 51684
2024-09-22 | USHA PLUMBING SYSTEM | NR-RA03 | 519000
2024-09-22 | S. S. ENTERPRISES | 447/24-25 | 50150
2024-09-23 | S. S. ENTERPRISES | 451/24-25 | 50150
2024-09-23 | SUNTREK CORPORATION | SC/SEPT/2425/33 | 70400
2024-09-23 | SUNTREK CORPORATION | SC/SEPT/2425/34 | 35200
2024-09-23 | SUNTREK CORPORATION | SC/SEPT/2425/31 | 70400
2024-09-23 | SUNTREK CORPORATION | SC/SEPT/2425/32 | 35200
2024-09-23 | SUNTREK CORPORATION | SC/SEPT/2425/35 | 70400
2024-09-23 | SUNTREK CORPORATION | SC/SEPT/2425/36 | 35200
2024-09-23 | SUNTREK CORPORATION | SC/SEPT/2425/37 | 70400
2024-09-23 | SUNTREK CORPORATION | SC/SEPT/2425/38 | 35200
2024-09-23 | KARRMANYA ENTERPRISE | 463/2024-2025 | 141743
2024-09-24 | RECONS BUILDING PRODUCTS PVT.LTD. | G242048 | 129231
2024-09-24 | RECONS BUILDING PRODUCTS PVT.LTD. | G242046 | 127131
2024-09-25 | JSW CEMENT LIMITED | MH2403102393 | 127125
2024-09-27 | M/S.SHRIYAA ENTERPRISES | 3692 | 61845
2024-09-27 | MD HAFIJUL ISLAM | 3 | 225000
2024-09-27 | RAJLAXMI CORPORATION | 88 | 69577
2024-09-27 | GLOBAL GYPSUM PVT LTD | 357 | 259644
2024-09-28 | RAJLAXMI CORPORATION | 89 | 58334
2024-09-29 | SUNTREK CORPORATION | SC/SEPT/2425/53 | 83072
2024-09-29 | SUNTREK CORPORATION | SC/SEPT/2425/52 | 70400
2024-09-29 | RAJLAXMI CORPORATION | 90 | 73437
2024-09-30 | VEDANT MARKETING | VM/24-25/1715 | 123227
2024-09-30 | RECONS BUILDING PRODUCTS PVT.LTD. | G242160 | 122917
2024-09-30 | SHARADA ENTERPRISES | 286 | 88318
2024-09-30 | SHARADA ENTERPRISES | 287 | 85861
2024-09-30 | SHARADA ENTERPRISES | 288 | 91907
2024-09-30 | SHARADA ENTERPRISES | 290 | 82811
2024-09-30 | SHARADA ENTERPRISES | 291 | 63941
2024-10-01 | WATER PUMP HIRE SERVICE | 1219 | 23000
2024-10-05 | RAMASHREY PRAJAPATI | 698 | 4872
2024-10-10 | ABHISHEK VISHWANATH MENON |  | 400000
2024-10-10 | MD HAFIJUL ISLAM |  | 150000
2024-10-10 | SABROJ MAUSAM ALI AHMAD | 002/24-25 | 165460
2024-10-10 | MD NIYAZ | 002/24-25 | 300000
2024-10-10 | MD AALIM | 001/24-25 | 300000
2024-10-10 | MUJEEB KHATALU SHAIKH | 002/24-25 | 366666
2024-10-10 | SHAIKH MUSHTAQ SHAIKH ISAQ | 002/24-25 | 366667
2024-10-10 | DHARMENDRAKUMAR BHIMANI | 001/24-25 | 900000
2024-10-10 | MONU KUMAR | 001/24-25 | 483635
2024-10-10 | MANOJ KUMAR HKZPK9753A | 001/24-25 | 483635
2024-10-10 | RAVEENDRA KUMAR PRAJAPATI | 001/24-25 | 483635
2024-10-10 | FATIMA JAVED SHAIKH | 001/23-24 | 366667
2024-10-10 | JAGRUT RAMESH JADHAV | RA-2 | 500000
2024-10-10 | MD ABRAR AHAMAD | 001/24-25 | 300000
2024-10-10 | PRAVIND ASHOK KUMAR | 002/24-25 | 483635
2024-10-14 | SUMEET SANJAY DAGADE | 005 | 518461
2024-10-15 | WATER PUMP HIRE SERVICE | 1237 | 18000
2024-11-14 | CHANDRAKANT T. DUDHBHATE | 032 | 200000
2024-11-14 | PRABHAKAR C.DUDHBHATE | 033 | 50000
2024-11-14 | VINAY KUMAR CHAURASIYA | 035 | 50000
2024-11-14 | CHETANA D. RANGASWAMI | 034 | 50000
2024-11-15 | WATER PUMP HIRE SERVICE | 1306 | 8000
2024-12-01 | PANKAJ PAYARCHAND JAIN | 03/24-25 | 450693
2024-12-01 | PANKAJ PAYARCHAND JAIN | 04/24-25 | 303862
2024-12-01 | VARSHA M. KAWA |  | 35000
2024-12-01 | RAMASHREY PRAJAPATI | 752 | 13992
2024-12-10 | RAMASHRE DUBEY | 001/24-25 | 1000000
2024-12-10 | DHARMENDRAKUMAR BHIMANI | 002/24-25 | 500000
2024-12-10 | MANOJ KUMAR HKZPK9753A | 002/24-25 | 600000
2024-12-10 | MONU KUMAR | 002/24-25 | 700000
2024-12-10 | RAVEENDRA KUMAR PRAJAPATI | 002/24-25 | 700000
2024-12-10 | SABROJ MAUSAM ALI AHMAD | 003/24-25 | 200000
2024-12-10 | MD AALIM | 002/24-25 | 550000
2024-12-10 | SHAIKH MUSHTAQ SHAIKH ISAQ | 003/24-25 | 600000
2024-12-10 | FATIMA JAVED SHAIKH | 002/24-25 | 600000
2024-12-10 | WATER PUMP HIRE SERVICE | 1352 | 8000
2024-12-10 | MD ABRAR AHAMAD | 002/24-25 | 550000
2024-12-10 | PANKAJ PAYARCHAND JAIN | 05/24-25 | 513933
2024-12-14 | VAISHALI P.DUDHBHATE | 037 | 92000
2024-12-14 | PRABHAKAR C.DUDHBHATE | 038 | 100000
2024-12-14 | CHANDRAKANT T. DUDHBHATE | 036 | 250000
2024-12-14 | SUNITA S. SANCHETI | 039 | 50000
2024-12-15 | MD HAFIJUL ISLAM |  | 135000
2024-10-11 | AKAR CONSTRUCTION COMPANY | 019/24-25 | 2499999.92
2024-10-14 | STAR WINDOWS | 152 | 2211967.16
2024-11-14 | AKAR CONSTRUCTION COMPANY | 032/24-25 | 3338982.98
2024-12-01 | SAMAYPRA INFRA PROJECT PVT LTD | SIPPL/107/24-25 | 2199768.74
2024-12-01 | SAMAYPRA INFRA PROJECT PVT LTD | SIPPL/108/24-25 | 2173339.16
2024-12-01 | R.R. ENTERPRISES | 196 | 2125135.7
2024-12-10 | AKAR CONSTRUCTION COMPANY | 035/24-25 | 2423728.74
2024-12-10 | SAMAYPRA INFRA PROJECT PVT LTD | SIPPL/122/24-25 | 2211152.12
2024-10-01 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/2142/24-25 | 1949924.04
2024-10-01 | R.K.TRADING CO. | RK506 | 14160
2024-10-01 | KRISHNA CERAMICS | 52 | 120360
2024-10-01 | SHARADA ENTERPRISES | 289 | 87141.6
2024-10-02 | SNEH ENTERPRISE | G/99/24-25G/99/24-25 | 33920
2024-10-02 | SNEH ENTERPRISE | G/98/24-25 | 67840
2024-10-03 | S.S.ENTERPRISES | 488/24-25 | 50150
2024-10-03 | S.S.ENTERPRISES | 489/24-25 | 50150
2024-10-03 | SNEH ENTERPRISE | G/108/24-25 | 33920
2024-10-03 | SNEH ENTERPRISE | G/107/24-25 | 67840
2024-10-03 | SNEH ENTERPRISE | G/103/24-25 | 33920
2024-10-03 | SNEH ENTERPRISE | G/102/24-25 | 67840
2024-10-03 | SNEH ENTERPRISE | G/101/24-25 | 33920
2024-10-03 | SNEH ENTERPRISE | G/100/24-25 | 67840
2024-10-04 | UN CORPORATION | UNC/2370/24-25 | 141793.34
2024-10-04 | UN CORPORATION | UNC/2371/24-25 | 11700.06
2024-10-06 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/2212/24-25 | 1991127.28
2024-10-06 | S.S.ENTERPRISES | 503/24-25 | 85585.5
2024-10-07 | JANATA SAND SUPPLYING CO. | 1320 | 4755.84
2024-10-07 | S.S.ENTERPRISES | 508/24-25 | 50150
2024-10-07 | KARRMANYA ENTERPRISE | 493/2024-2025 | 777424.68
2024-10-07 | KARRMANYA ENTERPRISE | 494/2024-2025 | 855262.5
2024-10-09 | NEER TRADING CO. | NT/85/24-25 | 28524.3
2024-10-09 | JSW CEMENT LIMITED | MH2403111428 | 127125
2024-10-10 | AVINASH ENTERPRISE | 198 | 472000
2024-10-10 | KIRIT TRADING COMPANY | 511-KTC/24-25 | 88000
2024-10-10 | KIRIT TRADING COMPANY | 512-KTC/24-25 | 88000
2024-10-10 | KIRIT TRADING COMPANY | 513-KTC/24-25 | 88000
2024-10-10 | KIRIT TRADING COMPANY | 514-KTC/24-25 | 88000
2024-10-10 | M/S.SHRIYAA ENTERPRISES | 5464 | 57162
2024-10-11 | KRISHNA TRADING CORPORATION | 763 | 3245
2024-10-11 | KIRIT TRADING COMPANY | 519-KTC/24-25 | 35200
2024-10-11 | S.S.ENTERPRISES | 526/24-25 | 50150
2024-10-12 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/2293/24-25 | 2182918.58
2024-10-14 | KIRIT TRADING COMPANY | 527-KTC/24-25 | 70400
2024-10-14 | KIRIT TRADING COMPANY | 528-KTC/24-25 | 70400
2024-10-14 | GLOBAL GYPSUM PVT LTD | 403 | 231000
2024-10-14 | KARRMANYA ENTERPRISE | 513/2024-2025 | 338684.99
2024-10-15 | UN CORPORATION | UNC/2555/24-25 | 140634.14
2024-10-15 | UN CORPORATION | UNC/2562/24-25 | 19500.1
2024-10-15 | KIRIT TRADING COMPANY | 540-KTC/24-25 | 97920
2024-10-15 | SHARADA ENTERPRISES | 317 | 33310.2
2024-10-15 | SHARADA ENTERPRISES | 315 | 85860.6
2024-10-15 | SHARADA ENTERPRISES | 314 | 94506.3
2024-10-15 | SHARADA ENTERPRISES | 312 | 79361.1
2024-10-15 | SHARADA ENTERPRISES | 313 | 88615.8
2024-10-15 | NEER TRADING CO. | NT/92/24-25 | 32130
2024-10-15 | RAJLAXMI CORPORATION | 96 | 100205.7
2024-10-16 | KIRIT TRADING COMPANY | 542-KTC/24-25 | 69120
2024-10-16 | S.S.ENTERPRISES | 544/24-25 | 153400
2024-10-16 | VEDANT MARKETING | VM/24-25/1867 | 180363
2024-10-17 | JSW CEMENT LIMITED | MH2403116086 | 127125
2024-10-17 | UN CORPORATION | UNC/2594/24-25 | 138640.32
2024-10-17 | UN CORPORATION | UNC/2595/24-25 | 19500.1
2024-10-17 | KIRIT TRADING COMPANY | 548-KTC/24-25 | 103680
2024-10-17 | KIRIT TRADING COMPANY | 549-KTC/24-25 | 86400
2024-10-18 | KIRIT TRADING COMPANY | 562-KTC/24-25 | 108518.4
2024-10-18 | KIRIT TRADING COMPANY | 561-KTC/24-25 | 86400
2024-10-19 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/2364/24-25 | 2043752.92
2024-10-20 | KIRIT TRADING COMPANY | 570-KTC/24-25 | 51840
2024-10-20 | KIRIT TRADING COMPANY | 569-KTC/24-25 | 98841.6
2024-10-20 | KIRIT TRADING COMPANY | 572-KTC/24-25 | 86400
2024-10-23 | HITECH CONSTRUCTIONS AND REPAIRS | MH/97/24-25 | 93220
2024-10-23 | M/S.SHRIYAA ENTERPRISES | 5499 | 111428.1
2024-10-24 | R.K.TRADING CO. | RK555 | 21240
2024-10-24 | UN CORPORATION | UNC/2732/24-25 | 118933.92
2024-10-24 | UN CORPORATION | UNC/2733/24-25 | 11700.06
2024-10-24 | S.S.ENTERPRISES | 572/24-25 | 93762.9
2024-10-25 | M/S.SHRIYAA ENTERPRISES | 5508 | 75860.4
2024-10-26 | S.S.ENTERPRISES | 582/24-25 | 153400
2024-10-26 | S.S.ENTERPRISES | 584/24-25 | 87480.76
2024-10-26 | VEDANT MARKETING | VM/24-25/1942 | 123227.4
2024-10-27 | KIRIT TRADING COMPANY | 631-KTC/24-25 | 86807.04
2024-10-27 | KIRIT TRADING COMPANY | 630-KTC/24-25 | 85440
2024-10-27 | KIRIT TRADING COMPANY | 629-KTC/24-25 | 85440
2024-10-27 | KIRIT TRADING COMPANY | 627-KTC/24-25 | 102528
2024-10-27 | KIRIT TRADING COMPANY | 628-KTC/24-25 | 68352
2024-10-27 | KIRIT TRADING COMPANY | 626-KTC/24-25 | 102528
2024-10-27 | KIRIT TRADING COMPANY | 623-KTC/24-25 | 68352
2024-10-28 | GLOBAL GYPSUM PVT LTD | 438 | 231000
2024-10-28 | SAKSHI CORPORATION | G/115/24-25 | 81600
2024-10-28 | RAJLAXMI CORPORATION | 102 | 98096.26
2024-10-28 | RAJLAXMI CORPORATION | 103 | 98786.1
2024-10-29 | GLOBAL GYPSUM PVT LTD | 439 | 42480
2024-10-29 | RAJLAXMI CORPORATION | 106 | 82538.4
2024-10-29 | KIRIT TRADING COMPANY | 647-KTC/24-25 | 85440
2024-10-30 | R.K.TRADING CO. | RK567 | 22417.5
2024-10-30 | RAJLAXMI CORPORATION | 107 | 91179.9
2024-10-31 | KRISHNA TRADING CORPORATION | 683 | 363499
2024-10-31 | NEER TRADING CO. | NT/99/24-25 | 105676
2024-10-31 | SHARADA ENTERPRISES | 349 | 87492.3
2024-10-31 | SHARADA ENTERPRISES | 350 | 83882.4
2024-10-31 | SHARADA ENTERPRISES | 351 | 86904.3
2024-10-31 | SHARADA ENTERPRISES | 352 | 86175.6
2024-10-31 | SHARADA ENTERPRISES | 353 | 88334.4
2024-11-01 | SUNTREK CORPORATION | SC/SEPT/2425/44 | 70400
2024-11-01 | SUNTREK CORPORATION | SC/SEPT/2425/45 | 14080
2024-11-01 | SUNTREK CORPORATION | SC/SEPT/2425/46 | 70400
2024-11-01 | SUNTREK CORPORATION | SC/SEPT/2425/51 | 17600
2024-11-01 | SUNTREK CORPORATION | SC/SEPT/2425/48 | 70400
2024-11-01 | SUNTREK CORPORATION | SC/SEPT/2425/47 | 21120
2024-11-01 | SUNTREK CORPORATION | SC/SEPT/2425/50 | 70400
2024-11-01 | SUNTREK CORPORATION | SC/SEPT/2425/49 | 17600
2024-11-01 | R.K.TRADERS | RKT/562/24-25 | 3274.5
2024-11-02 | SNEH ENTERPRISE | G/189/24-25 | 33920
2024-11-02 | SNEH ENTERPRISE | G/188/24-25 | 67840
2024-11-03 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/2547/24-25 | 1960376.48
2024-11-04 | KIRIT TRADING COMPANY | 674-KTC/24-25 | 102528
2024-11-06 | KIRIT TRADING COMPANY | 688-KTC/24-25 | 100992
2024-11-06 | KIRIT TRADING COMPANY | 689-KTC/24-25 | 100992
2024-11-06 | KIRIT TRADING COMPANY | 690-KTC/24-25 | 100992
2024-11-06 | DILIP PAINT & HARDWARE STORES | 509 | 9204
2024-11-07 | KIRIT TRADING COMPANY | 699-KTC/24-25 | 33664
2024-11-08 | JSW CEMENT LIMITED | MH2403130821 | 127125
2024-11-09 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/2638/24-25 | 2033391.34
2024-11-09 | S.S.ENTERPRISES | 622/24-25 | 86483.26
2024-11-12 | TEJAS CERAMICS | 340 | 31999.87
2024-11-12 | UN CORPORATION | UNC/3004/24-25 | 11700.06
2024-11-12 | UN CORPORATION | UNC/3003/24-25 | 144042.2
2024-11-13 | KARRMANYA ENTERPRISE | 571/2024-2025 | 917899.72
2024-11-13 | KIRIT TRADING COMPANY | 737-KTC/24-25 | 80793.6
2024-11-13 | KIRIT TRADING COMPANY | 738-KTC/24-25 | 80793.6
2024-11-13 | SAKSHI CORPORATION | G/128/24-25 | 80000
2024-11-14 | S.S.ENTERPRISES | 636/24-25 | 73185
2024-11-14 | KIRIT TRADING COMPANY | 750-KTC/24-25 | 84160
2024-11-14 | KIRIT TRADING COMPANY | 749-KTC/24-25 | 100992
2024-11-14 | KIRIT TRADING COMPANY | 748-KTC/24-25 | 100992
2024-11-14 | KIRIT TRADING COMPANY | 746-KTC/24-25 | 89546.24
2024-11-14 | KIRIT TRADING COMPANY | 747-KTC/24-25 | 100992
2024-11-15 | NEER TRADING CO. | NT/106/24-25 | 166105.8
2024-11-15 | SHARADA ENTERPRISES | 368 | 23847.6
2024-11-15 | SHARADA ENTERPRISES | 367 | 23490.6
2024-11-15 | SHARADA ENTERPRISES | 366 | 85354.5
2024-11-15 | VEDANT MARKETING | VM/24-25/2130 | 123227.4
2024-11-16 | S.S.ENTERPRISES | 644/24-25 | 151040
2024-11-17 | KIRIT TRADING COMPANY | 765-KTC/24-25 | 67328
2024-11-18 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/2752/24-25 | 2041341
2024-11-18 | GLOBAL GYPSUM PVT LTD | 475 | 249480
2024-11-18 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360145018 | 15999.72
2024-11-18 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360145017 | 80000.36
2024-11-19 | VEDANT MARKETING | VM/24-25/2177 | 17121.8
2024-11-20 | S.S.ENTERPRISES | 659/24-25 | 83606.26
2024-11-21 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/2796/24-25 | 59463.79
2024-11-21 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/2797/24-25 | 37229.1
2024-11-21 | JSW CEMENT LIMITED | MH2403140798 | 127125
2024-11-21 | KIRIT TRADING COMPANY | 780-KTC/24-25 | 84160
2024-11-21 | KIRIT TRADING COMPANY | 781-KTC/24-25 | 93585.92
2024-11-22 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/2798/24-25 | 5660.46
2024-11-22 | KIRIT TRADING COMPANY | 796-KTC/24-25 | 96279.04
2024-11-22 | KIRIT TRADING COMPANY | 795-KTC/24-25 | 84160
2024-11-22 | KIRIT TRADING COMPANY | 794-KTC/24-25 | 84160
2024-11-27 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/2854/24-25 | 74170.08
2024-11-29 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/2884/24-25 | 1979933.8
2024-12-01 | S.S.ENTERPRISES | 694/24-25 | 86090.56
2024-12-01 | S.S.ENTERPRISES | 665/24-25 | 84179.56
2024-12-01 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360146128 | 84245
2024-12-01 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360146129 | 84245
2024-12-01 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360146130 | 84245
2024-12-01 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360145750 | 84159.99
2024-12-01 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360145745 | 84159.99
2024-12-01 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360145795 | 84159.99
2024-12-01 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360145838 | 84159.99
2024-12-01 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360146131 | 84245
2024-12-01 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360146270 | 84245
2024-12-01 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360145846 | 134656.01
2024-12-01 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360145971 | 33663.99
2024-12-01 | RAJLAXMI CORPORATION | 123 | 86108.4
2024-12-01 | RAJLAXMI CORPORATION | 115 | 76230
2024-12-01 | RAJLAXMI CORPORATION | 114 | 67567.5
2024-12-01 | RAJLAXMI CORPORATION | 113 | 88437.3
2024-12-01 | RAJLAXMI CORPORATION | 126 | 71510.26
2024-12-01 | JSW CEMENT LIMITED | MH2403145599 | 127125
2024-12-01 | NEER TRADING CO. | NT/118/24-25 | 321528.9
2024-12-01 | SHARADA ENTERPRISES | 378 | 97101.9
2024-12-01 | SHARADA ENTERPRISES | 379 | 94254.3
2024-12-01 | SHARADA ENTERPRISES | 380 | 85314.6
2024-12-01 | SHARADA ENTERPRISES | 381 | 93431.1
2024-12-01 | SHARADA ENTERPRISES | 382 | 83611.5
2024-12-01 | VEDANT MARKETING | VM/24-25/2287 | 123227.4
2024-12-01 | KIRIT TRADING COMPANY | 807-KTC/24-25 | 95232
2024-12-01 | R.K.TRADING CO. | RK629 | 22417.5
2024-12-01 | MEHTA PLYWOOD | 528-24-25 | 7574.71
2024-12-01 | MEHTA PLYWOOD |  | -7574.71
2024-12-03 | UN CORPORATION | UNC/3363/24-25 | 113926.18
2024-12-03 | UN CORPORATION | UNC/3365/24-25 | 19500.1
2024-12-04 | S.S.ENTERPRISES | 707/24-25 | 84848.4
2024-12-05 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/2938/24-25 | 1946522.1
2024-12-05 | NUVOCO VISTAS CORP LTD | 241311017952 | 375677.54
2024-12-05 | S.S.ENTERPRISES | 713/24-25 | 84752.86
2024-12-05 | KIRIT TRADING COMPANY | 873-KTC/24-25 | 91200
2024-12-05 | KIRIT TRADING COMPANY | 874-KTC/24-25 | 91200
2024-12-05 | GLOBAL GYPSUM PVT LTD | 505 | 249480
2024-12-05 | JSW CEMENT LIMITED | MH2403150581 | 127125
2024-12-05 | JK LAKSHMI CEMENT LTD ( KITIT TRADING) | 7360146416 | 84245
2024-12-07 | JANATA SAND SUPPLYING CO. | 1335 | 14175
2024-12-08 | KIRIT TRADING COMPANY | 883-KTC/24-25 | 109440
2024-12-08 | KIRIT TRADING COMPANY | 884-KTC/24-25 | 109440
2024-12-08 | KIRIT TRADING COMPANY | 885-KTC/24-25 | 109440
2024-12-08 | KIRIT TRADING COMPANY | 886-KTC/24-25 | 109440
2024-12-08 | KIRIT TRADING COMPANY | 887-KTC/24-25 | 109440
2024-12-09 | S.S.ENTERPRISES | 733/24-25 | 84943.96
2024-12-10 | S.S.ENTERPRISES | 734/24-25 | 75423.6
2024-12-10 | DILIP PAINT & HARDWARE STORES | 582 | 13806
2024-12-10 | KARRMANYA ENTERPRISE | 632/2024-2025 | 41291.44
2024-12-10 | AXLER WOODWORKS LLP | AW/24-25/52 | 260072
2024-12-11 | S.S.ENTERPRISES | 737/24-25 | 84561.76
2024-12-12 | SAKSHI CORPORATION | G/160/24-25 | 97920
2024-12-13 | VEDANT MARKETING | VM/24-25/2449 | 60604.8
2024-12-13 | KARAN ENTERPRISES | 715-KE/24-25 | 182400
2024-12-13 | NAVBHARAT HARDWARE STORES | 4723 | 128930.34
2024-12-13 | NAVBHARAT HARDWARE STORES |  | -3469.2
2024-12-14 | CHANDRAKANT ELECTRICAL & CONTRACTOR | 023 | 628051.55
2024-12-14 | CHANDRAKANT ELECTRICAL & CONTRACTOR | 024 | 179395.24
2024-12-14 | KIRIT TRADING COMPANY | 912-KTC/24-25 | 45760
2024-12-15 | S.S.ENTERPRISES | 748/24-25 | 84561.76
2024-12-15 | JSW CEMENT LIMITED | MH240158065 | 127125
2024-12-15 | SHARADA ENTERPRISES | 417 | 91274.4
2024-12-15 | SHARADA ENTERPRISES | 418 | 87954.3
2024-12-15 | SHARADA ENTERPRISES | 419 | 86421.3
2024-12-15 | SHARADA ENTERPRISES | 420 | 86790.9
2024-12-15 | SHARADA ENTERPRISES | 421 | 84997.5
2024-12-15 | SHARADA ENTERPRISES | 422 | 33310.2
2024-12-15 | HSA INFRA PROJECTS | HSA/94/24-25 | 135063.6
2024-12-16 | GLOBAL GYPSUM PVT LTD | 537 | 249480
2024-12-16 | KARAN ENTERPRISES | 732-KE/24-25 | 182400
2024-12-16 | M/S.SHRIYAA ENTERPRISES | 5640 | 28381.5
2024-12-16 | S.S.ENTERPRISES | 755/24-25 | 153400
2024-12-17 | ANUPAM ELECTRICALS | GST/24-25/371 | 30638.7
2024-12-17 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/3075/24-25 | 69243.58
2024-12-17 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/3076/24-25 | 1905210.3
2024-12-17 | KIRIT TRADING COMPANY | 919-KTC/24-25 | 105600
2024-12-19 | KARAN ENTERPRISES | 740-KE/24-25 | 88000
2024-12-20 | AXLER WOODWORKS LLP | AW/24-25/53 | 1811418
2024-12-20 | HITECH CONSTRUCTIONS AND REPAIRS | MH/130/24-25 | 15930
2024-12-22 | S.S.ENTERPRISES | 779/24-25 | 85995
2024-12-23 | JANATA SAND SUPPLYING CO. | 1338 | 5655.8
2024-12-23 | SAKSHI CORPORATION | G/179/24-25 | 182400
2024-12-23 | SAKSHI CORPORATION | G/180/24-25 | 145920
2024-12-23 | SAKSHI CORPORATION | G/181/24-25 | 145920
2024-12-23 | SAKSHI CORPORATION | G/182/24-25 | 145920
2024-12-23 | UN CORPORATION | UNC/3655/24-25 | 11700.06
2024-12-23 | UN CORPORATION | UNC/3654/24-25 | 140726.88
2024-12-23 | VEDANT MARKETING | VM/24-25/2562 | 123227.4
2024-12-24 | JANATA SAND SUPPLYING CO. | 1340 | 14175
2024-12-25 | M/S.SHRIYAA ENTERPRISES | 5667 | 25882.5
2024-12-26 | R.K.TRADING CO. | RK714 | 76922
2024-12-26 | SAKSHI CORPORATION | G/186/24-25 | 109440
2024-12-26 | SAKSHI CORPORATION | G/193/24-25 | 164160
2024-12-26 | SAKSHI CORPORATION | G/194/24-25 | 84800
2024-12-27 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/3184/24-25 | 1973900.46
2024-12-27 | S.S.ENTERPRISES | 793/24-25 | 85995
2024-12-28 | SUSHMA CONTRUCTION STEEL SALES LLP | SCSS/3195/24-25 | 71985.9
2024-12-30 | KIRIT TRADING COMPANY | 786-KTC/24-25 | 67328
2024-12-30 | R.K.TRADING CO. | RK702 | 37065
2024-06-12 | NUVOCO VISTAS CORP LTD |  | 36001.8
470830353.84

## Professional
SR.NO | PARTICULARS | NATURE | DATE | TOTAL AMOUNT
| MEHTA & CO. | LEGAL AND PROFESSIONAL FEES | 2020-01-10 | 2000000
| S.J.ASSOCIATES | LEGAL AND PROFESSIONAL FEES | 2020-01-23 | 44800
| S.J.ASSOCIATES | LEGAL AND PROFESSIONAL FEES | 2021-03-19 | 37800
| S.J.ASSOCIATES | LEGAL AND PROFESSIONAL FEES | 2021-04-08 | 8850
| GEOTECH ENTERPRISES | LEGAL AND PROFESSIONAL FEES | 2021-10-22 | 115640
| ROHAN ENVIRO ASSOSIATES | LEGAL AND PROFESSIONAL FEES | 2022-03-17 | 796500
| Manish Kumar V.Bagsariya | LEGAL AND PROFESSIONAL FEES | 2022-03-30 | 900000
| Nidhin Narayan Pillai | LEGAL AND PROFESSIONAL FEES | 2022-03-30 | 1400000
| Abdulla M.Baig | LEGAL AND PROFESSIONAL FEES | 2022-03-30 | 900000
| S.J.ASSOCIATES | LEGAL AND PROFESSIONAL FEES | 2022-07-09 | 10030
| ENGARC ASSOCIATS | LEGAL AND PROFESSIONAL FEES | 2022-08-24 | 88500
| RAGHOBA BHAGWAN GOVEKAR | LEGAL AND PROFESSIONAL FEES | 2022-10-10 | 60000
| ROHAN ENVIRO ASSOSIATES | LEGAL AND PROFESSIONAL FEES | 2022-12-01 | 177000
| ROHAN ENVIRO ASSOSIATES | LEGAL AND PROFESSIONAL FEES | 2022-12-01 | 708000
| ENVIRO ENGINEERING SERVICES | LEGAL AND PROFESSIONAL FEES | 2022-12-01 | 59000
| RAGHOBA BHAGWAN GOVEKAR | LEGAL AND PROFESSIONAL FEES | 2023-01-12 | 104000
| RAGHOBA BHAGWAN GOVEKAR | LEGAL AND PROFESSIONAL FEES | 2023-01-16 | 100000
| DARSHANA INDULKAR | LEGAL AND PROFESSIONAL FEES | 2023-02-02 | 230000
| SHIVMOHAN B.JHA | LEGAL AND PROFESSIONAL FEES | 2023-02-06 | 118000
| SHALAKA D.SATHE | LEGAL AND PROFESSIONAL FEES | 2023-03-03 | 1000000
| NILOFER ABDULLA BAIG | LEGAL AND PROFESSIONAL FEES | 2023-03-03 | 1000000
| RAGHOBA BHAGWAN GOVEKAR | LEGAL AND PROFESSIONAL FEES | 2023-03-20 | 170000
| SWATI RAGHOBA GOVEKAR | LEGAL AND PROFESSIONAL FEES | 2023-03-20 | 360000
| ROHAN ENVIRO ASSOSIATES | LEGAL AND PROFESSIONAL FEES | 2023-03-28 | 177000
| VASTUKAL CONSULTANTS (I) PVT LTD | LEGAL AND PROFESSIONAL FEES | 2023-05-18 | 413000
| VASTUKAL CONSULTANTS (I) PVT LTD | LEGAL AND PROFESSIONAL FEES | 2023-05-18 | 135700
| CRISIL Ratings Ltd. | LEGAL AND PROFESSIONAL FEES | 2023-05-23 | 318600
| AJIT SURVEYORS | LEGAL AND PROFESSIONAL FEES | 2023-07-18 | 24000
| Professional fees |  |  | 285965
| PROFESSIONAL CHARGES - WITH GST | OTHER EXPENSES |  | 5900
| VASTUKAL CONSULTANTS (I) PVT LTD | LEGAL AND PROFESSIONAL FEES- WITH GST | 2023-05-09 | 88500
| PROFESSIONAL FEES OF C.A. |  | 2023-12-01 | 5900
| PROFESSIONAL FEES OF C.A. |  | 2023-12-01 | 29500
| TESTING CHARGES |  | 2023-10-01 | 11100
| TESTING CHARGES |  | 2023-11-09 | 6300
| TESTING CHARGES |  | 2023-04-12 | 49800
| TESTING CHARGES |  | 2023-05-09 | 1350
| TESTING CHARGES |  | 2023-09-08 | 10800
| TESTING CHARGES |  | 2023-09-08 | 5400
| PROFESSIONAL FEES OF C.A. | OTHER EXPENSES |  | 104000
| KASHMIRA K PATEL | LEGAL AND PROFESSIONAL FEES | 2024-03-20 | 1000000
| Abdulla M.Baig | LEGAL AND PROFESSIONAL FEES | 2024-03-20 | 1900000
| SHAILESH C AKBARI | LEGAL AND PROFESSIONAL FEES | 2024-03-20 | 1900000
| SHALAKA D.SATHE | LEGAL AND PROFESSIONAL FEES | 2024-03-20 | 1000000
| PRAGNA J PATEL | LEGAL AND PROFESSIONAL FEES | 2024-03-20 | 1000000
| NILOFER ABDULLA BAIG | LEGAL AND PROFESSIONAL FEES | 2024-03-20 | 1000000
| MIT J PATEL | LEGAL AND PROFESSIONAL FEES | 2024-03-20 | 1000000
| Manish Kumar V.Bagsariya | LEGAL AND PROFESSIONAL FEES | 2024-03-20 | 1900000
| Nidhin Narayan Pillai | LEGAL AND PROFESSIONAL FEES | 2024-03-20 | 1900000
| KAUSHIK B PATEL | LEGAL AND PROFESSIONAL FEES | 2024-03-20 | 1900000
| VASTUKAL CONSULTANTS (I) PVT LTD | LEGAL AND PROFESSIONAL FEES | 2024-06-06 | 41300
| VASTUKAL CONSULTANTS (I) PVT LTD | LEGAL AND PROFESSIONAL FEES | 2024-06-06 | 41300
| CRISIL Ratings Ltd. | LEGAL AND PROFESSIONAL FEES | 2024-06-06 | 207680
| LANDMARK CONSULTANTS & ENGG. TECHNOLOGY | TESTING CHARGES |  | 8400
| VASTUKALA CONSULTANTS (I) PVT LTD | MUM/2425/JULY/200 | 2024-08-01 | 41300
| PROFESSIONAL FEES OF C.A. | PROFESSIONAL FEES OF C.A. |  | 53000
| AJIT SURVEYORS | AS/15/24-25 | 2024-07-04 | 16000
| BALMUKUND DOKANIA | 003/24-25 | 2024-07-09 | 49200
| BALMUKUND DOKANIA | 004/24-25 | 2024-08-12 | 70800
| BALMUKUND DOKANIA | 005/24-25 | 2024-09-01 | 28800
| LANDMARK CONSULTANTS & ENGG.TECHNOLOGY | L-0655 | 2024-09-01 | 12390
| ROHAN ENVIRO ASSOSIATES | REA/027/2024-25 | 2024-11-04 | 88500
| BALMUKUND DOKANIA | 009/24-25 | 2024-11-05 | 13200
| BALMUKUND DOKANIA | 011/24-25 | 2024-12-01 | 37800
| LANDMARK CONSULTANTS & ENGG. TECHNOLOGY | L-1026 | 2024-12-01 | 4956
| J.J.SANGANEE & CO | CO/11-24/02 | 2024-11-04 | 11800
| H. RAJEN & CO. | RC/11/002 | 2024-11-13 | 41300
| J.J.SANGANEE & CO | CO/12-24/05 | 2024-12-03 | 7080
| RAJAN MENDA | 203 | 2024-12-04 | 2000
| J.J.SANGANEE & CO | CO/12-24/25 | 2024-12-10 | 5900
TOTAL |  |  |  | 27343641

## MArketing
SR.NO | PARTICULARS | NATURE | DATE | TOTAL AMOUNT
| MINESH N. SHAH (LOAN) |  | 2021-08-03 | 500
| STAMP DUTY | OTHER EXPENSES |  | 2518200
| COMMISSION AND BROKERAGE | OTHER EXPENSES |  | 552100
| STAMP DUTY | OTHER EXPENSES |  | 6110500
| COMMISSION AND BROKERAGE | OTHER EXPENSES |  | 1016728
| STAMP DUTY |  | 2023-05-29 | 493000
| STAMP DUTY |  | 2023-05-29 | 330800
| STAMP DUTY |  | 2023-05-29 | 334000
| STAMP DUTY |  | 2023-05-29 | 330800
| STAMP DUTY |  | 2023-06-28 | 1284600
| STAMP DUTY |  | 2023-06-28 | 1267200
| STAMP DUTY |  | 2023-06-28 | 469100
| STAMP DUTY |  | 2023-06-28 | 1491200
| STAMP DUTY |  | 2023-06-28 | 1008400
| STAMP DUTY |  | 2023-07-06 | 1238100
| STAMP DUTY |  | 2023-07-06 | 1291700
| STAMP DUTY |  | 2023-07-13 | 1104900
| STAMP DUTY |  | 2023-07-27 | 1018400
| STAMP DUTY |  | 2023-07-31 | 30000
| STAMP DUTY |  | 2023-08-19 | 1794000
| STAMP DUTY |  | 2023-08-21 | 2301500
| STAMP DUTY |  | 2023-08-21 | 2015000
| STAMP DUTY |  | 2023-09-08 | 1066300
| STAMP DUTY |  | 2023-09-08 | 1451900
| STAMP DUTY |  | 2023-10-10 | 1736200
| STAMP DUTY |  | 2023-10-10 | 1277100
| STAMP DUTY |  | 2023-10-10 | 698100
| STAMP DUTY |  | 2023-10-16 | 30000
| STAMP DUTY |  | 2023-10-19 | 30000
| STAMP DUTY |  | 2023-11-01 | 1068300
| STAMP DUTY |  | 2023-11-09 | 1277100
| STAMP DUTY |  | 2023-11-09 | 1282200
| STAMP DUTY |  | 2023-11-10 | 1262600
| STAMP DUTY |  | 2023-11-16 | 1220600
| STAMP DUTY |  | 2023-11-16 | 1245500
| STAMP DUTY |  | 2023-12-04 | 1773000
| STAMP DUTY |  | 2023-12-21 | 1311500
| COMMISSION AND BROKERAGE |  |  | 3661666
| STAMP DUTY & REGISTRATION FEE | OTHER EXPENSES |  | 10480860
| COMMISSION AND BROKERAGE | OTHER EXPENSES |  | 3297796
| COMMISSION AND BROKERAGE |  |  | 1642490
| STAMP DUTY & REGISTRATION FEE |  |  | 1874000
| ADVERTISEMENT EXPENSES |  |  | 202500
| COMMISSION AND BROKERAGE |  |  | 583140
| COMMISSION AND BROKERAGE |  |  | 643474
| COMMISSION AND BROKERAGE |  |  | 475800
| COMMISSION AND BROKERAGE |  |  | 400000
| COMMISSION AND BROKERAGE |  |  | 382020
| COMMISSION AND BROKERAGE |  |  | 390970
| COMMISSION AND BROKERAGE |  |  | 636400
| STAMP DUTY & REGISTRATION FEE |  |  | 1893000
| STAMP DUTY & REGISTRATION FEE |  |  | 1279700
| STAMP DUTY & REGISTRATION FEE |  |  | 1550500
| STAMP DUTY & REGISTRATION FEE |  |  | 1251130
| STAMP DUTY & REGISTRATION FEE |  |  | 1298300
| STAMP DUTY & REGISTRATION FEE |  |  | 1800000
| STAMP DUTY & REGISTRATION FEE |  |  | 1264800
| STAMP DUTY & REGISTRATION FEE |  |  | 1442300
| STAMP DUTY & REGISTRATION FEE |  |  | 1245000
| STAMP DUTY & REGISTRATION FEE |  |  | 21793000
| COMMISSION AND BROKERAGE | COMMISSION AND BROKERAGE |  | 5920641
| ADVERTISEMENT EXPENSES | ADVERTISEMENT EXPENSES |  | 427500
| SBI A/C NO.41853900460 RERA 30% | CH.NO. 072379 AG STAMPDUTY FOR 1102/B WING NICCO RESIDENCY | 2024-10-10 | 1297000
| SBI A/C NO.41853900460 RERA 30% | CH.NO. 072380 AG STAMPDUTY FOR 2103/A WING NICCO RESIDENCY | 2024-10-10 | 1626000
| SBI A/C NO.41853900460 RERA 30% | CH.NO. 072381 AG STAMPDUTY FOR 1801/A WING NICCO RESIDENCY | 2024-10-11 | 1324500
| SBI A/C NO.41853900460 RERA 30% | CH.NO. 072393 AG STAMPDUTY FOR 2001/A WING NICCO RESIDENCY | 2024-10-23 | 1327000
| SBI A/C NO.41853900460 RERA 30% | CH.NO. 072396 AG STAMPDUTY FOR 1604/C WING NICCO RESIDENCY | 2024-10-28 | 1965500
| SBI A/C NO.41853900460 RERA 30% | CH.NO. 072212 AG STAMPDUTY FOR 1701/C WING NICCO RESIDENCY | 2024-11-18 | 2570000
| SBI A/C NO.41853900460 RERA 30% | CH.NO. 072108 AG STAMPDUTY FOR 402/C WING NICCO RESIDENCY | 2024-11-21 | 1257000
| SBI A/C NO.41853900460 RERA 30% | CH.NO. 072108 AG STAMPDUTY FOR 1403/C WING NICCO RESIDENCY | 2024-12-02 | 977500
| SBI A/C NO.41853900460 RERA 30% | CH.NO. 072141 AG STAMPDUTY FOR 2001/C WING NICCO RESIDENCY | 2024-12-23 | 1688000
| MARKETING CHANAKYA | MC-94-24 | 2024-10-03 | 8850
| DIGITECH MOBILE MEDIA | DMM/131/10/24 | 2024-10-11 | 295000
| WIZFX COMMUNICATIONS PRIVATE LIMITED | 15/10/2024-25 | 2024-10-11 | 35400
| MARKETING CHANAKYA | MC-111-24 | 2024-11-01 | 8850
| ALGORHYTHM INNOVATION | PI-1429 | 2024-11-07 | 120000
| DIGITECH MOBILE MEDIA | DMM/155/11/24 | 2024-11-09 | 442500
| MARKETING CHANAKYA | MC-132-24 | 2024-12-01 | 17646.9
| DILIP RAVESHIA HUF | HUF-005-24 | 2024-12-12 | 50000
| JONES LANG LASALLE PROPERTY CONSULTANTS INDIA PVT | PC/MH/2425/00584 | 2024-10-01 | 679808.62
| MACVIN MENDONZA | 2/24-25 | 2024-10-04 | 531500
| PRAKHAR SHRIVASTAVA | 01 | 2024-10-09 | 499480
| AVENUE REALTY |  | 2024-10-09 | 681560
| AVENUE REALTY |  | 2024-10-09 | 328697
| A.S. CONSULTANCY |  | 2024-10-10 | 404916
| SUVARNA MUKADAM | 1/24-25 | 2024-10-11 | 530700
| JONES LANG LASALLE PROPERTY CONSULTANTS INDIA PVT | PC/MH/2425/00683 | 2024-11-01 | 1571409.54
| MACVIN MENDONZA | 3/24-25 | 2024-11-15 | 100000
TOTAL |  |  |  | 130906933.06

## Admin
SR.NO | PARTICULARS | NATURE | INVOICE NO | DATE | TOTAL AMOUNT
| WATER CHARGES |  |  | 2023-01-03 | 27500
| WATER CHARGES |  |  | 2023-01-03 | 27500
| WATER CHARGES |  |  | 2023-01-03 | 27500
| A1 STAR TRANSPORT | TRANSPORT CHARGES |  | 2021-01-09 | 4200
| A1 STAR TRANSPORT | TRANSPORT CHARGES |  | 2021-12-15 | 2400
| SGST OUTWARD REVERSE CHARGE | TRANSPORT CHARGES |  | 2022-03-31 | 120
| SWASTIK ENTERPRISES | TRANSPORT CHARGES |  | 2023-03-21 | 12000
| NEW NATIONAL MOTOR TRANSPORT CO. | TRANSPORT CHARGES |  | 2023-03-24 | 18000
| SWASTIK ENTERPRISES | TRANSPORT CHARGES |  | 2023-03-31 | 10000
| CGST INPUT REVERSE CHARGE | TRANSPORT CHARGES |  | 2023-03-31 | 2000
| SHREE KRISHNA TRANSPORT | TRANSPORT CHARGES |  | 2023-04-04 | 130800
| ANUPAM ELECTRICALS | TRANSPORT CHARGES |  | 2023-04-06 | 6300
| GAURI TRANSPORT | TRANSPORT CHARGES |  | 2023-05-15 | 20978
| A1 STAR TRANSPORT | TRANSPORT CHARGES |  | 2023-06-06 | 11000
| A1 STAR TRANSPORT | TRANSPORT CHARGES |  | 2023-07-08 | 20000
| ADANI ELECTRICITY | ELECTRICITY CHARGES |  | 2022-06-09 | 5470
| ADANI ELECTRICITY | ELECTRICITY CHARGES |  | 2022-09-23 | 27390
| ADANI ELECTRICITY | ELECTRICITY CHARGES |  | 2022-09-28 | 7500
| ADANI ELECTRICITY | ELECTRICITY CHARGES |  | 2022-11-02 | 2430
| ADANI ELECTRICITY | ELECTRICITY CHARGES |  | 2022-12-19 | 2730
| ADANI ELECTRICITY | ELECTRICITY CHARGES |  | 2023-02-02 | 3450
| ADANI ELECTRICITY | ELECTRICITY CHARGES |  | 2023-03-13 | 29190
| ADANI ELECTRICITY | ELECTRICITY CHARGES |  | 2023-04-07 | 4960
| ADANI ELECTRICITY | ELECTRICITY CHARGES |  | 2023-05-19 | 144700
| ADANI ELECTRICITY | ELECTRICITY CHARGES |  | 2023-05-19 | 22660
| ADANI ELECTRICITY | ELECTRICITY CHARGES |  | 2023-07-27 | 114850
| K.L.PATHAK | SECURITY SERVICES | KLP/23/08 | 2023-04-13 | 40000
| K.L.PATHAK | SECURITY SERVICES | KLP/23/039 | 2023-06-06 | 40000
| K.L.PATHAK | SECURITY SERVICES | KLP/23/068 | 2023-06-08 | 40000
| COOLIE & CARTAGE EXP |  |  |  | 240500
| LATE FILING FEES |  |  |  | 200
| MOTORCAR EXPENSES |  |  |  | 56532
| REOAIR & MAINTENANCE CHARGES |  |  |  | 2520
| REPAIR AND MAINTENACE CHARGES |  |  |  | 4500
| SALARY |  |  |  | 779879
| TESTING CHARGES |  |  |  | 51150
| WELFARE EXPENSES |  |  | 2023-04-02 | 5150
| office Rent expenses |  |  |  | 265000
| Gernal expenses |  |  |  | 85743
| others |  |  |  | 148571
| ELECTRICITY CHARGES |  |  | 2023-08-07 | 238640
| ELECTRICITY CHARGES |  |  | 2023-08-07 | 47300
| K.L.PATHAK | SECURITY CHARGES |  | 2023-04-08 | 44333
| PUJARI TRANSPORT | TRANSPORT CHARGES |  | 2023-07-08 | 20792
| PUJARI TRANSPORT | TRANSPORT CHARGES |  | 2023-11-08 | 17186
| BANK CHARGES | OTHER EXPENSES |  |  | 1010660.8
| COOLIE & CARTAGE EXP | OTHER EXPENSES |  |  | 176772
| Labour Charges | OTHER EXPENSES |  |  | 4415938
| LOAN PROCESING CHARGES | OTHER EXPENSES |  |  | 10976596
| OFFICE RENT EXPENSES | OTHER EXPENSES |  |  | 5000
| REPAIR & MAINTENANCE CHARGES | OTHER EXPENSES |  |  | 8850
| ELECTRICITY CHARGES |  |  | 2023-09-21 | 82350
| ELECTRICITY CHARGES |  |  | 2023-09-21 | 61990
| ELECTRICITY CHARGES |  |  | 2023-09-27 | 24820
| ELECTRICITY CHARGES |  |  | 2023-09-27 | 143508
| A1 STAR TRANSPORT | TRANSPORT CHARGES |  | 2023-01-09 | 1000
| A1 STAR TRANSPORT | TRANSPORT CHARGES |  | 2023-01-09 | 26000
| K.L.PATHAK | SECURITY SERVICES |  | 2023-01-09 | 49032
| BANK CHARGES | OTHER EXPENSES |  |  | 25101
| COOLIE AND CARTAGE | OTHER EXPENSES |  |  | 25101
| OFFICE RENT CHARGES | OTHER EXPENSES |  |  | 5000
| WELFARE EXPENSES | OTHER EXPENSES |  | 2023-09-01 | 3600
| DONATION |  |  |  | 15000
| BANK CHARGES | OTHER EXPENSES |  |  | 2594.16
| COMMISSION AND BROKERAGE | OTHER EXPENSES |  |  | 2092838
| MOTOR CAR EXPENSES | OTHER EXPENSES |  |  | 18844
| OFFICE RENT EXPENSES | OTHER EXPENSES |  |  | 5000
| FILLING FEES | OTHER EXPENSES |  |  | 400
| LATE FILING FEES | OTHER EXPENSES |  |  | 8450
| RERA APPLICATION FEES | OTHER EXPENSES |  |  | 8386.6
| PROPERTY TAX |  |  | 2023-10-25 | 773667
| PROPERTY TAX |  |  | 2023-10-25 | 29597
| WELFARE EXPENSES |  |  | 2023-10-01 | 4500
| WELFARE EXPENSES |  |  | 2023-11-01 | 2700
| SECURITY SERVICES |  | KLP/23/0127 | 2023-10-16 | 52333
| SECURITY SERVICES |  | KLP/23/0152 | 2023-11-01 | 52258
| SECURITY SERVICES |  | KLP/23/0172 | 2023-12-01 | 50000
| CHANDRAKANT ELECTRICAL & CONTRACTOR | TRANSPORT CHARGES | 05 | 2023-10-09 | 480
| A1 STAR TRANSPORT | TRANSPORT CHARGES | 573 | 2023-10-16 | 1000
| NAIDU TRANSPORT | TRANSPORT CHARGES | 99 | 2023-11-07 | 700000
| VAISHALI ENTERPRISES | TRANSPORT CHARGES | 12 | 2023-11-08 | 700000
| SHREE KRISHNA TRANSPORT | TRANSPORT CHARGES | 101 | 2023-11-08 | 700000
| A1 STAR TRANSPORT | TRANSPORT CHARGES | 585 | 2023-11-08 | 1000
| ELECTRICITY CHARGES |  |  | 2023-10-23 | 64580
| ELECTRICITY CHARGES |  |  | 2023-10-23 | 83200
| ELECTRICITY CHARGES |  |  | 2023-12-26 | 188300
| COOLIE & CARTAGE EXP |  |  | 2023-10-10 | 60209
| COOLIE & CARTAGE EXP |  |  | 2023-10-10 | 115800
| COOLIE & CARTAGE EXP |  |  | 2023-11-08 | 107241
| COOLIE & CARTAGE EXP |  |  | 2023-12-20 | 129300
| BANK CHARGES | OTHER EXPENSES |  |  | 2594.16
| COMMISSION AND BROKERAGE | OTHER EXPENSES |  |  | 2092838
| MOTOR CAR EXPENSES | OTHER EXPENSES |  |  | 18844
| OFFICE RENT EXPENSES | OTHER EXPENSES |  |  | 5000
| FILLING FEES | OTHER EXPENSES |  |  | 400
| LATE FILING FEES | OTHER EXPENSES |  |  | 8450
| RERA APPLICATION FEES | OTHER EXPENSES |  |  | 8386.6
| SALARY |  |  | 2023-05-08 | 44700
| SALARY |  |  | 2023-05-08 | 37900
| SALARY |  |  | 2023-05-08 | 83150
| SALARY |  |  | 2023-05-11 | 4060
| SALARY |  |  | 2023-05-11 | 34493
| SALARY |  |  | 2023-05-11 | 23550
| SALARY |  |  | 2023-06-01 | 44700
| SALARY |  |  | 2023-06-01 | 37900
| SALARY |  |  | 2023-06-01 | 83150
| SALARY |  |  | 2023-06-01 | 20300
| SALARY |  |  | 2023-06-01 | 39800
| SALARY |  |  | 2023-06-01 | 23550
| SALARY |  |  | 2023-06-01 | 23226
| SALARY |  |  | 2023-07-01 | 44700
| SALARY |  |  | 2023-07-01 | 37900
| SALARY |  |  | 2023-07-01 | 83150
| SALARY |  |  | 2023-07-01 | 20300
| SALARY |  |  | 2023-07-01 | 39800
| SALARY |  |  | 2023-07-01 | 23550
| SALARY |  |  | 2023-07-01 | 30000
| SALARY |  |  | 2023-08-01 | 44700
| SALARY |  |  | 2023-08-01 | 37900
| SALARY |  |  | 2023-08-01 | 83150
| SALARY |  |  | 2023-08-01 | 20300
| SALARY |  |  | 2023-08-01 | 39800
| SALARY |  |  | 2023-08-01 | 23550
| SALARY |  |  | 2023-08-01 | 30000
| SALARY |  |  | 2023-08-17 | 65000
| SALARY |  |  | 2023-09-01 | 65000
| SALARY |  |  | 2023-09-01 | 44700
| SALARY |  |  | 2023-09-01 | 83150
| SALARY |  |  | 2023-09-01 | 20300
| SALARY |  |  | 2023-09-01 | 39800
| SALARY |  |  | 2023-09-01 | 23550
| SALARY |  |  | 2023-09-18 | 37900
| SALARY |  |  | 2023-10-03 | 65000
| SALARY |  |  | 2023-10-03 | 44700
| SALARY |  |  | 2023-10-03 | 37900
| SALARY |  |  | 2023-10-03 | 83150
| SALARY |  |  | 2023-10-03 | 20300
| SALARY |  |  | 2023-10-03 | 39800
| SALARY |  |  | 2023-10-03 | 23550
| SALARY |  |  | 2023-11-01 | 65000
| SALARY |  |  | 2023-11-01 | 44700
| SALARY |  |  | 2023-11-01 | 37900
| SALARY |  |  | 2023-11-01 | 83150
| SALARY |  |  | 2023-11-01 | 39800
| SALARY |  |  | 2023-11-01 | 23550
| SALARY |  |  | 2023-11-01 | 5323
| SALARY |  |  | 2023-12-01 | 37900
| SALARY |  |  | 2023-12-01 | 23550
| SALARY |  |  | 2023-12-01 | 65000
| SALARY |  |  | 2023-12-01 | 44700
| SALARY |  |  | 2023-12-01 | 83150
| SALARY |  |  | 2023-12-01 | 39800
| SALARY |  |  | 2023-12-01 | 15000
| BANK CHARGES |  |  |  | 35810
| General Expenses |  |  |  | 17700
| MOTOR CAR EXPENSES |  |  |  | 113064
| OFFICE RENT EXPENSES |  |  |  | 35000
| Printing & Stationary |  |  |  | 6240
| WELFARE EXPENSES |  |  | 2023-07-01 | 5890
| WELFARE EXPENSES |  |  | 2023-05-01 | 23360
| K.L.PATHAK | SECURITY SERVICES |  | 2023-10-16 | 52333
| K.L.PATHAK | SECURITY SERVICES |  | 2023-11-01 | 52258
| K.L.PATHAK | SECURITY SERVICES |  | 2023-12-01 | 50000
| Insurance Charges |  |  |  | 912207
| CGST FEES | SALES & ADMINISTRATIVE EXPENSES |  |  | 375
| Company Professional Tax -PTEC | SALES & ADMINISTRATIVE EXPENSES |  |  | 5000
| INTERNET CHARGES | SALES & ADMINISTRATIVE EXPENSES |  |  | 9200
| RERA APPLICATION FEES | SALES & ADMINISTRATIVE EXPENSES |  |  | 50082.6
| SALARY | SALES & ADMINISTRATIVE EXPENSES |  |  | 1403980
| SGST FEES | SALES & ADMINISTRATIVE EXPENSES |  |  | 375
| SUNDRY BALANCE W/OFF (NET) | SALES & ADMINISTRATIVE EXPENSES |  |  | 10.45
| GENERAL EXPENSES | OTHER EXPENSES |  |  | 7300
| MOTOR CAR EXPENSES | OTHER EXPENSES |  |  | 37688
| OFFICE RENT EXPENSES | OTHER EXPENSES |  |  | 15000
| BANK CHARGES | OTHER EXPENSES |  |  | 1989.11
| M.P.WATER SUPPLIER | WELFARE EXPENSES |  | 2024-03-27 | 11700
| K.L.PATHAK | SECURITY SERVICES |  | 2024-01-08 | 50000
| K.L.PATHAK | SECURITY SERVICES |  | 2024-02-15 | 50000
| K.L.PATHAK | SECURITY SERVICES |  | 2024-03-13 | 50000
| A1 STAR TRANSPORT | TRANSPORT CHARGES |  | 2024-01-01 | 6000
| A1 STAR TRANSPORT | TRANSPORT CHARGES |  | 2024-01-08 | 4000
| CHANDRAKANT ELECTRICAL & CONTRACTOR | TRANSPORT CHARGES |  | 2024-01-15 | 3200
| CHANDRAKANT ELECTRICAL & CONTRACTOR | TRANSPORT CHARGES |  | 2024-01-15 | 1850
| K R ENTERPRISES | TRANSPORT CHARGES |  | 2024-02-01 | 120400
| K R ENTERPRISES | TRANSPORT CHARGES |  | 2024-02-01 | 94600
| A1 STAR TRANSPORT | TRANSPORT CHARGES |  | 2024-02-15 | 21200
| VAISHALI ENTERPRISES | TRANSPORT CHARGES |  | 2024-02-15 | 234000
| K R ENTERPRISES | TRANSPORT CHARGES |  | 2024-03-01 | 47300
| K R ENTERPRISES | TRANSPORT CHARGES |  | 2024-03-01 | 94600
| CHANDRAKANT ELECTRICAL & CONTRACTOR | TRANSPORT CHARGES |  | 2024-03-15 | 1850
| CHANDRAKANT ELECTRICAL & CONTRACTOR | TRANSPORT CHARGES |  | 2024-03-15 | 1850
| A1 STAR TRANSPORT | TRANSPORT CHARGES |  | 2024-03-27 | 5000
| SANKET TRANSPORT | TRANSPORT CHARGES |  | 2024-03-28 | 29800
| SANKET TRANSPORT | TRANSPORT CHARGES |  | 2024-03-28 | 29000
| SHREE KRISHNA ENTERPRISES | TRANSPORT CHARGES |  | 2024-03-30 | 221100
| A1 STAR TRANSPORT | TRANSPORT CHARGES |  | 2024-03-31 | 3000
| ELECTRICITY CHARGES |  |  | 2024-01-05 | 27832
| ELECTRICITY CHARGES |  |  | 2024-01-05 | 38965
| ELECTRICITY CHARGES |  |  | 2024-01-05 | 38965
| ELECTRICITY CHARGES |  |  | 2024-01-11 | 300190
| ELECTRICITY CHARGES |  |  | 2024-01-16 | 94880
| ELECTRICITY CHARGES |  |  | 2024-03-11 | 265530
| ELECTRICITY CHARGES |  |  | 2024-03-22 | 266630
| ELECTRICITY CHARGES |  |  | 2024-03-22 | 175500
| VAIBHAV KISAN SUTAR | COOLIE & CARTAGE EXP |  | 2024-01-24 | 233307
| VAIBHAV KISAN SUTAR | COOLIE & CARTAGE EXP |  | 2024-02-29 | 207860
| VAIBHAV KISAN SUTAR | COOLIE & CARTAGE EXP |  | 2024-03-27 | 175858
| INSURANCE CHARGES |  |  | 2024-01-04 | 20390
| CH.NO 071475 AMOUNT PAID RAHUL V KANOJIYA FOR SALARY MONTH OF MAY 2024 |  |  |  | 51000
| CH.NO 071476 SALARY PAID AJAYKUMAR JIVANBHAI PATEL FOR SALARY MONTH OF MAY 2024 |  |  |  | 75750
| CH.NO 071476 AMOUNT PAID SAIFALIKHAN ANEES FOR SALARY MONTH OF MAY 2024 |  |  |  | 51500
| CH.NO 071476 AMOUNT PAID GANESH G.KAMBLE FOR SALARY MONTH OF MAY 2024 |  |  |  | 84500
| CH.NO 071476 AMOUNT PAID ANIKET BANSHRAJ SINGH FOR SALARY MONTH OF MAY 2024 |  |  |  | 51500
| CH.NO 071476 AMOUNT PAID DIPESH R DHAKAL FOR SALARY MONTH OF MAY 2024 |  |  |  | 27250
| CH.NO 071476 AMOUNT PAID NEERAJ YADAV FOR SALARY MONTH OF MAY 2024 |  |  |  | 20500
| CH.NO 071476 AMOUNT PAID MOHAMMED ISRAN RAR FOR SALARY MONTH OF MAY 2024 |  |  |  | 31000
| CH.NO 071476 AMOUNT PAID SACHIN ASHOK PIWHAL FOR SALARY MONTH OF MAY 2024 |  |  |  | 17000
| PTEC |  |  |  | 2500
| BANK CHARGES |  |  |  | 460.2
| OFFICE RENT EXPENSES |  |  |  | 5000
| ELECTRICITY CHARGES |  |  |  | 215630
| ELECTRICITY CHARGES |  |  |  | 90950
| ELECTRICITY CHARGES |  |  |  | 7610
| COOLIE & CARTAGE EXP |  |  |  | 105615
| WELFARE EXPENSES |  |  |  | 17400
| CH.NO 071468 AMOUNT PAID RAHUL V KANOJIYA FOR SALARY MONTH OF APRIL 2024 |  |  | 2024-05-04 | 51000
| CH.NO 071469 SALARY PAID AJAYKUMAR JIVANBHAI PATEL FOR SALARY MONTH OF APRIL 2024 |  |  | 2024-05-04 | 75750
| CH.NO 071469 AMOUNT PAID SAIFALIKHAN ANEES FOR SALARY MONTH OF APRIL 2024 |  |  | 2024-05-04 | 51500
| CH.NO 071469 AMOUNT PAID GANESH G.KAMBLE FOR SALARY MONTH OF APRIL 2024 |  |  | 2024-05-04 | 84500
| CH.NO 071469 AMOUNT PAID ANIKET BANSHRAJ SINGH FOR SALARY MONTH OF APRIL 2024 |  |  | 2024-05-04 | 51500
| CH.NO 071469 AMOUNT PAID DIPESH R DHAKAL FOR SALARY MONTH OF APRIL 2024 |  |  | 2024-05-04 | 27250
| CH.NO 071469 AMOUNT PAID NEERAJ YADAV FOR SALARY MONTH OF APRIL 2024 |  |  | 2024-05-04 | 20500
| CH.NO 071469 AMOUNT PAID MOHAMMED ISRAN RAR FOR SALARY MONTH OF APRIL 2024 |  |  | 2024-05-04 | 31000
| CH.NO 071218 AMOUNT PAID SACHIN ASHOK PIWHAL FOR SALARY MONTH OF APRIL 2024 |  |  | 2024-05-08 | 17000
| BANK CHARGES | OTHER EXPENSES |  |  | 1420.72
| GENERAL EXPENSES | OTHER EXPENSES |  |  | 12900
| MOTOR CAR EXPENSES | OTHER EXPENSES |  |  | 18844
| OFFICE RENT EXPENSES | OTHER EXPENSES |  |  | 10000
| PROPERTY TAX |  |  |  | 145988
| PROPERTY TAX |  |  |  | 3816066
| WELFARE EXPENSES |  |  |  | 10440
| VAIBHAV KISAN SUTAR | COOLIE & CARTAGE EXP |  |  | 99482
| K.L.PATHAK | SECURITY SERVICES |  |  | 77000
| ELECTRICITY CHARGES |  |  |  | 504270
| COOLIE & CARTAGE EXP |  |  |  | 413683
| Insurance Charges |  |  |  | 787813
| M.P.WATER SUPPLIER | WELFARE EXPENSES |  |  | 73120
| K.L.PATHAK | SECURITY SERVICES |  |  | 296667
| BANK CHARGES | BANK CHARGES |  |  | 1970.6
| GENERAL EXPENSES | GENERAL EXPENSES |  |  | 10000
| LATE FILING FEES | LATE FILING FEES |  |  | 400
| OFFICE RENT EXPENSES | OFFICE RENT EXPENSES |  |  | 15000
| PRINTING & STATIONERY EXPENSES | PRINTING & STATIONERY EXPENSES |  |  | 262500
| REPAIR & MAINTENANCE CHARGES | REPAIR & MAINTENANCE CHARGES |  |  | 80850
| SUNDRY BALANCE W/OFF (NET) | SUNDRY BALANCE W/OFF (NET) |  |  | 5
| CH.NO 071495 AMOUNT PAID RAHUL V KANOJIYA FOR SALARY MONTH OF JUNE 2024 | SALARY |  | 2024-07-01 | 51000
| CH.NO 071494 SALARY PAID AJAYKUMAR JIVANBHAI PATEL FOR SALARY MONTH OF JUNE 2024 | SALARY |  | 2024-07-01 | 75750
| CH.NO 071494 AMOUNT PAID SAIFALIKHAN ANEES FOR SALARY MONTH OF JUNE 2024 | SALARY |  | 2024-07-01 | 51500
| CH.NO 071494 AMOUNT PAID GANESH G.KAMBLE FOR SALARY MONTH OF JUNE 2024 | SALARY |  | 2024-07-01 | 84500
| CH.NO 071494 AMOUNT PAID ANIKET BANSHRAJ SINGH FOR SALARY MONTH OF JUNE 2024 | SALARY |  | 2024-07-01 | 51500
| CH.NO 071494 AMOUNT PAID DIPESH R DHAKAL FOR SALARY MONTH OF JUNE 2024 | SALARY |  | 2024-07-01 | 27250
| CH.NO 071494 AMOUNT PAID NEERAJ YADAV FOR SALARY MONTH OF JUNE 2024 | SALARY |  | 2024-07-01 | 20500
| CH.NO 071494 AMOUNT PAID SACHIN ASHOK PIWHAL FOR SALARY MONTH OF JUNE 2024 | SALARY |  | 2024-07-01 | 17000
| CH.NO 071494 AMOUNT PAID MOHAMMED ISRAN RAR FOR SALARY MONTH OF JUNE 2024 | SALARY |  | 2024-07-01 | 31000
| CH.NO 071502 AMOUNT PAID RAHUL V KANOJIYA FOR SALARY MONTH OF JULY 2024 | SALARY |  | 2024-08-01 | 51000
| CH.NO 071501 SALARY PAID AJAYKUMAR JIVANBHAI PATEL FOR SALARY MONTH OF JULY 2024 | SALARY |  | 2024-08-01 | 75750
| CH.NO 071501 AMOUNT PAID SAIFALIKHAN ANEES FOR SALARY MONTH OF JULY 2024 | SALARY |  | 2024-08-01 | 51500
| CH.NO 071501 AMOUNT PAID GANESH G.KAMBLE FOR SALARY MONTH OF JULY 2024 | SALARY |  | 2024-08-01 | 84500
| CH.NO 071501 AMOUNT PAID ANIKET BANSHRAJ SINGH FOR SALARY MONTH OF JULY 2024.(LAST MONTH RS.2500 PAID) (54000-51500=2500). | SALARY |  | 2024-08-01 | 56500
| CH.NO 071501 AMOUNT PAID DIPESH R DHAKAL FOR SALARY MONTH OF JULY 2024 | SALARY |  | 2024-08-01 | 27250
| CH.NO 071501 AMOUNT PAID NEERAJ YADAV FOR SALARY MONTH OF JULY 2024 | SALARY |  | 2024-08-01 | 20500
| CH.NO 071501 AMOUNT PAID SACHIN ASHOK PIWHAL FOR SALARY MONTH OF JULY 2024 | SALARY |  | 2024-08-01 | 17000
| CH.NO 071501 AMOUNT PAID MOHAMMED ISRAN RAR FOR SALARY MONTH OF JULY 2024 | SALARY |  | 2024-08-01 | 31000
| CH.NO 071504 AMOUNT PAID RAHUL V KANOJIYA FOR SALARY MONTH OF AUG 2024 | SALARY |  | 2024-09-02 | 51000
| CH.NO 071503 SALARY PAID AJAYKUMAR JIVANBHAI PATEL FOR SALARY MONTH OF AUG 2024 | SALARY |  | 2024-09-02 | 75750
| CH.NO 071503 AMOUNT PAID SAIFALIKHAN ANEES FOR SALARY MONTH OF AUG 2024 | SALARY |  | 2024-09-02 | 51500
| CH.NO 071503 AMOUNT PAID GANESH G.KAMBLE FOR SALARY MONTH OF AUG 2024 | SALARY |  | 2024-09-02 | 84500
| CH.NO 071503 AMOUNT PAID ANIKET BANSHRAJ SINGH FOR SALARY MONTH OF AUG 2024 | SALARY |  | 2024-09-02 | 54000
| CH.NO 071503 AMOUNT PAID DIPESH R DHAKAL FOR SALARY MONTH OF AUG 2024 | SALARY |  | 2024-09-02 | 27250
| CH.NO 071503 AMOUNT PAID NEERAJ YADAV FOR SALARY MONTH OF AUG 2024 | SALARY |  | 2024-09-02 | 20500
| CH.NO 071503 AMOUNT PAID SACHIN ASHOK PIWHAL FOR SALARY MONTH OF AUG 2024 | SALARY |  | 2024-09-02 | 17000
| CH.NO 071503 AMOUNT PAID MOHAMMED ISRAN RAR FOR SALARY MONTH OF AUG 2024 | SALARY |  | 2024-09-02 | 31000
| D.R LINKS |  |  | 2024-07-01 | 24922
| D.R LINKS |  |  | 2024-07-31 | 27400
| D.R LINKS |  |  | 2024-08-29 | 11942
| A1 STAR TRANSPORT |  |  | 2024-09-01 | 1000
| SWASTIK ENTERPRISES (AOSPB1807N) |  | SE/2024-25/012 | 2024-07-01 | 19000
| CHANDRAKANT ELECTRICAL & CONTRACTOR | 014 |  | 2024-07-13 | 205225
| SANKET TRANSPORT | 1752 |  | 2024-07-31 | 57600
| CHANDRAKANT ELECTRICAL & CONTRACTOR | 017 |  | 2024-08-14 | 37918
| CHANDRAKANT ELECTRICAL & CONTRACTOR | 016 |  | 2024-08-14 | 54049
| CHANDRAKANT ELECTRICAL & CONTRACTOR | 015 |  | 2024-08-14 | 394380
| VAIBHAV KISAN SUTAR | CH NO-072399 BILL NO-1343, 1344, 1345, 1346, 1347, 1348, 1351, 1350, 1349, 1352, 12551, 12552, 12553, 12554, 12555, 12556 |  | 2024-11-01 | 159833
| VAIBHAV KISAN SUTAR | CH NO-072105 BILL NO-12557, 12558, 12559, 12560, 12561, 12562, 12563, 12564, 12565, 12566, 12567, 12568, 12569, 12570, 12571 |  | 2024-11-12 | 181636
| VAIBHAV KISAN SUTAR | CH NO-072129 BILL NO-12572, 12573, 12574, 12575, 12576, 12577, 12578, 12579, 12580, 12581, 12582, 12583 |  | 2024-12-01 | 164051
| ELECTRICITY CHARGES |  |  |  | 1180090
| M.P.WATER SUPPLIER |  | 101 | 2024-10-01 | 20030
| M.P.WATER SUPPLIER |  | 351 | 2024-11-01 | 10900
| M.P.WATER SUPPLIER |  | 381 | 2024-12-01 | 19700
| OM VEDANT PETROLEUM | CH NO-072392 BILL NO-31/734 | 31/734 | 2024-10-01 | 54824
| OM VEDANT PETROLEUM | CH NO-072392 BILL NO-31/312 | 31/312 | 2024-10-01 | 74528
| OM VEDANT PETROLEUM | CH NO-072392 BILL NO-31/100 | 31/100 | 2024-10-01 | 56108
| OM VEDANT PETROLEUM | CH NO-072392 BILL NO-31/978 | 31/978 | 2024-10-01 | 72808
| K.L.PATHAK | CH NO-072386 BILL NO-KLP/24/098 SEPT 2024 | KLP/24/098 | 2024-10-01 | 70000
| K.L.PATHAK | CH NO-072399 BILL NO-KLP/24/0115 OCT 2024 | KLP/24/0115 | 2024-11-01 | 70000
| K.L.PATHAK | CH NO-072129 BILL NO-KLP/24-25/0141 NOV 2024 | KLP/24-25/0141 | 2024-12-01 | 70000
| SBI A/C NO.41853900460 RERA 30% |  |  | 2024-11-25 | 2055
| SBI A/C NO.41853900460 RERA 30% |  |  | 2024-11-25 | 30830
| SBI A/C NO.41853900460 RERA 30% | BEING ONLINE TDS PAID FOR THE YEAR F.Y. 2022-2023 4TH QRT AS PER TDS DEMAND NOTICE |  | 2024-10-10 | 230
| SBI A/C NO.41853900460 RERA 30% | BEING ONLINE TDS PAID FOR THE YEAR F.Y. 2021-2022 4TH QRT AS PER TDS DEMAND NOTICE |  | 2024-10-11 | 4842
| SBI A/C NO.41853900460 RERA 30% | BEING ONLINE TDS PAID FOR THE YEAR F.Y. 2019-2020 4TH QRT AS PER TDS DEMAND NOTICE |  | 2024-10-11 | 2090
| SBI A/C NO.41853900460 RERA 30% | BEING ONLINE TDS PAID FOR THE YEAR F.Y. 2023-2024 1ST QRT AS PER TDS DEMAND NOTICE |  | 2024-10-11 | 7400
| SBI A/C NO.41853900460 RERA 30% | BEING ONLINE TDS PAID FOR THE YEAR F.Y. 2018-2019 4TH QRT AS PER TDS DEMAND NOTICE |  | 2024-10-14 | 64960
| SBI A/C NO.41853900460 RERA 30% | BEING GST PAID FOR THE MONTH OF SEPTEMBER 2024 |  | 2024-10-26 | 22074
| SBI A/C NO.41853900460 RERA 30% | BEING GST PAID FOR THE MONTH OF OCTOBER 2024 |  | 2024-11-26 | 3296
| SBI A/C NO.41853900460 RERA 30% | BEING GST PAID FOR THE MONTH OF OCTOBER 2024 |  | 2024-11-26 | 3296
| SBI A/C NO.41853900460 RERA 30% | BEING GST PAID FOR THE MONTH OF NOVEMBER 2024 |  | 2024-12-21 | 16660
| BANK CHARGES |  |  |  | 3353.08
| DONATION |  |  |  | 900
| FILLING FEES |  |  |  | 200
| GENERAL EXPENSES |  |  |  | 12372.89
| LATE FILING FEES |  |  |  | 1750
| LOAN PROCESING CHARGES |  |  |  | 1120000
| PRINTING & STATIONERY EXPENSES | CH NO-072386 BILL NO-INV-0101 | INV-0101 | 2024-10-10 | 297500
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071506 AMOUNT PAID RAHUL V KANOJIYA FOR SALARY MONTH OF SEPT 2024 |  | 2024-10-01 | 51000
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071505 SALARY PAID AJAYKUMAR JIVANBHAI PATEL FOR SALARY MONTH OF SEPT 2024 |  | 2024-10-01 | 75750
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071505 AMOUNT PAID SAIFALIKHAN ANEES FOR SALARY MONTH OF SEPT 2024 |  | 2024-10-01 | 51500
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071505 AMOUNT PAID GANESH G.KAMBLE FOR SALARY MONTH OF SEPT 2024 |  | 2024-10-01 | 84500
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071505 AMOUNT PAID ANIKET BANSHRAJ SINGH FOR SALARY MONTH OF SEPT 2024 |  | 2024-10-01 | 54000
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071505 AMOUNT PAID DIPESH R DHAKAL FOR SALARY MONTH OF SEPT 2024 |  | 2024-10-01 | 27250
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071505 AMOUNT PAID NEERAJ YADAV FOR SALARY MONTH OF SEPT 2024 |  | 2024-10-01 | 20500
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071505 AMOUNT PAID SACHIN ASHOK PIWHAL FOR SALARY MONTH OF SEPT 2024 |  | 2024-10-01 | 17000
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071505 AMOUNT PAID MOHAMMED ISRAN RAR FOR SALARY MONTH OF SEPT 2024 |  | 2024-10-01 | 31000
| SBI A/C NO.41853900460 RERA 30% | CH.NO. 071190 AG SALARY PAID FOR SEPT 2024 FOR 15TH DAY IN FAVOUR MD GHOLAM HASNAINE |  | 2024-10-04 | 18672
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071508 AMOUNT PAID RAHUL V KANOJIYA FOR SALARY MONTH OF OCT 2024 |  | 2024-10-25 | 51000
| SBI A/C NO.41853900460 RERA 30% | CH.NO. 071508 AG SALARY PAID FOR OCT 2024 FOR 15TH DAY IN FAVOUR MD GHOLAM HASNAINE |  | 2024-10-25 | 35000
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071507 SALARY PAID AJAYKUMAR JIVANBHAI PATEL FOR SALARY MONTH OF OCT 2024 |  | 2024-10-25 | 75750
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071507 AMOUNT PAID SAIFALIKHAN ANEES FOR SALARY MONTH OF OCT 2024 |  | 2024-10-25 | 51500
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071507 AMOUNT PAID GANESH G.KAMBLE FOR SALARY MONTH OF OCT 2024 |  | 2024-10-25 | 84500
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071507 AMOUNT PAID ANIKET BANSHRAJ SINGH FOR SALARY MONTH OF OCT 2024 |  | 2024-10-25 | 54000
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071507 AMOUNT PAID DIPESH R DHAKAL FOR SALARY MONTH OF OCT 2024 |  | 2024-10-25 | 27250
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071507 AMOUNT PAID NEERAJ YADAV FOR SALARY MONTH OF OCT 2024 |  | 2024-10-25 | 20500
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071507 AMOUNT PAID SACHIN ASHOK PIWHAL FOR SALARY MONTH OF OCT 2024 |  | 2024-10-25 | 17000
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071507 AMOUNT PAID MOHAMMED ISRAN RAR FOR SALARY MONTH OF OCT 2024 |  | 2024-10-25 | 31000
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071510 AMOUNT PAID RAHUL V KANOJIYA FOR SALARY MONTH OF NOV 2024 |  | 2024-12-02 | 51000
| SBI A/C NO.41853900460 RERA 30% | CH.NO. 071510 AG SALARY PAID FOR NOV 2024 MD GHOLAM HASNAIN |  | 2024-12-02 | 35000
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071509 SALARY PAID AJAYKUMAR JIVANBHAI PATEL FOR SALARY MONTH OF NOV 2024 |  | 2024-12-02 | 75750
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071509 AMOUNT PAID SAIFALIKHAN ANEES FOR SALARY MONTH OF NOV 2024 |  | 2024-12-02 | 51500
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071509 AMOUNT PAID GANESH G.KAMBLE FOR SALARY MONTH OF NOV 2024 |  | 2024-12-02 | 84500
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071509 AMOUNT PAID ANIKET BANSHRAJ SINGH FOR SALARY MONTH OF NOV 2024 |  | 2024-12-02 | 54000
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071509 AMOUNT PAID DIPESH R DHAKAL FOR SALARY MONTH OF NOV 2024 |  | 2024-12-02 | 27250
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071509 AMOUNT PAID NEERAJ YADAV FOR SALARY MONTH OF NOV 2024 |  | 2024-12-02 | 20500
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071509 AMOUNT PAID SACHIN ASHOK PIWHAL FOR SALARY MONTH OF NOV 2024 |  | 2024-12-02 | 17000
| SBI A/C NO.41853900460 RERA 30% | CH.NO 071509 AMOUNT PAID MOHAMMED ISRAN RAR FOR SALARY MONTH OF NOV 2024 |  | 2024-12-02 | 31000
| A1 STAR TRANSPORT |  | 902 | 2024-10-01 | 3000
| R K ENTERPRISES |  | 013 | 2024-10-04 | 73100
| SB ENTERPRISES-TRANSPORT |  | 094 | 2024-10-07 | 47300
| A1 STAR TRANSPORT |  | 923 | 2024-10-31 | 3000
| SB ENTERPRISES-TRANSPORT |  | 091 | 2024-11-05 | 34400
| K R ENTERPRISES |  | 778 | 2024-12-01 | 47300
| R K ENTERPRISES |  | 020 | 2024-12-03 | 103200
TOTAL |  |  |  |  | 51492263.97

## Interest
Sr. No. | Month | Interest Amount
| 31/-8/23 | 326663
| 30/09/23 | 1614621
1 | 2023-10-01 | 1771561
| 2023-11-01 | 1820958
| 2023-12-01 | 1965871
| 2024-01-01 | 2065940
| 2024-02-01 | 2178946
| 2024-03-01 | 2675909
| 2024-04-01 | 2861346
| 2024-05-01 | 3047941
| 2024-06-01 | 2950811
| 2024-07-01 | 3049171
| 2024-08-01 | 3127067
| 2024-09-01 | 3061772
| 2024-10-01 | 3266707
| 2024-11-01 | 3346624
| 2024-12-01 | 3646123
2025-01-01
2025-02-01
2025-03-01
42778031

## Construction Area Statement (4)
AMENITY BUILDING No. 2
Sr. No. | Floor | Total Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | Percentage of work completed | Actual Expenditure till date in ` | Sr. No. | Building | Total Construction Area in Sq. M. | Cost of Construction | % of work completed | Actual Expenditure till date in `
1 | Excavation & Piling Work | 10% of Construction Cost of Building |  |  | 5554035 | 100% | 5554035 | 1 | Amenity Building No. 2 | 2057.05 | 61094385 | 100% | 61094385
2 | Ground | 476.44 | 476.44 | 27000 | 12863880 | 100% | 12863880 | 2 | Rehab Building No. 1 | 12066.9356 | 358387987.2 | 27.86% | 99853072.476
3 | 1st | 508.48 | 508.48 | 27000 | 13728960 | 100% | 13728960 | 3 | Sale Building | 30990.9475 | 1022701268 | 57.03% | 583269866.5
4 | 2nd | 508.48 | 508.48 | 27000 | 13728960 | 100% | 13728960 |  | Sub Total (A) | 45114.9331 | 1442183640.2 | 51.6% | 744217323.976
5 | 3rd | 508.48 | 508.48 | 27000 | 13728960 | 100% | 13728960 | 4 | Puzzle Parking of Rehab Building in No. | 131 | 65500000 | 0% | 0
6 | OHT / LMR | 55.17 | 55.17 | 27000 | 1489590 | 100% | 1489590 | 5 | Puzzle Parking of Sale Building in No. | 300 | 150000000 | 0% | 0
TOTAL COST OF CONSTRUCTION |  | 2057.05 | 2057.05 |  | 61094385 | 100% | 61094385 |  | Sub Total (B) | 431 | 215500000 | 0% | 0
[8 empty] | Total Cost of Construction (A + B) |  |  | 1657683640.2 | 44.9% | 744217323.976
REHAB BUILDING No. 1
Sr. No. | Floor | Total Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | Percentage of work completed | Actual Expenditure till date in `
| Excavation & Piling Work | 10% of Construction Cost of Building |  |  | 32580726 | 100% | 32580726
1 | Ground | 464.4694 | 464.4694 | 27000 | 12540673.8 | 50% | 6270336.9
2 | 1st | 478.0194 | 478.0194 | 27000 | 12906523.8 | 52% | 6711392.376
3 | 2nd | 486.6394 | 486.6394 | 27000 | 13139263.8 | 52% | 6832417.176
4 | 3rd | 505.0894 | 505.0894 | 27000 | 13637413.8 | 52% | 7091455.176
5 | 4th | 505.0894 | 505.0894 | 27000 | 13637413.8 | 52% | 7091455.176
6 | 5th | 505.0894 | 505.0894 | 27000 | 13637413.8 | 52% | 7091455.176
7 | 6th | 505.0894 | 505.0894 | 27000 | 13637413.8 | 52% | 7091455.176
8 | 7th | 505.0894 | 505.0894 | 27000 | 13637413.8 | 50% | 6818706.9
9 | 8th | 505.0894 | 505.0894 | 27000 | 13637413.8 | 50% | 6818706.9
10 | 9th | 505.0894 | 505.0894 | 27000 | 13637413.8 | 40% | 5454965.52
11 | 10th | 505.0894 |  | 27000 | 13637413.8 |  | 0
12 | 11th | 505.0894 |  | 27000 | 13637413.8 |  | 0
13 | 12th | 505.0894 |  | 27000 | 13637413.8
14 | 13th | 505.0894 |  | 27000 | 13637413.8 |  | 0
15 | 14th | 505.0894 |  | 27000 | 13637413.8 |  | 0
16 | 15th | 505.0894 |  | 27000 | 13637413.8 |  | 0
17 | 16th | 505.0894 |  | 27000 | 13637413.8 |  | 0
18 | 17th | 505.0894 |  | 27000 | 13637413.8 |  | 0
19 | 18th | 505.0894 |  | 27000 | 13637413.8 |  | 0
20 | 19th | 505.0894 |  | 27000 | 13637413.8 |  | 0
21 | 20th | 505.0894 |  | 27000 | 13637413.8 |  | 0
22 | 21st | 505.0894 |  | 27000 | 13637413.8 |  | 0
23 | 22nd | 505.0894 |  | 27000 | 13637413.8 |  | 0
24 | 23rd | 505.0894 |  | 27000 | 13637413.8 |  | 0
25 | OHT / LMR | 30.93 |  | 27000 | 835110 |  | 0
Sub - Total (A) |  | 12066.9356 | 4964.754 |  | 358387987.2 | 27.86% | 99853072.476
PUZZLE PARKING Nos. (B) |  | 131 |  | 500000 | 65500000 |  | 0
TOTAL COST OF CONSTRUCTION (A + B) |  |  |  |  | 423887987.2 | 23.56% | 99853072.476
SALE BUILDING
Sr. No. | Floor | Total Construction Area in Sq. M. | Completed Area in Sq. M. | Rate per Sq. M. | Full Value after completion | Percentage of work completed | Actual Expenditure till date in `
| Excavation & Piling Work | 10% of Construction Cost of Building |  |  | 92972843 | 50% | 46486421.5
1 | Ground | 1877.0625 | 1877.0625 | 30000 | 56311875 | 90% | 50680687.5
2 | 1st | 1877.0587 | 938.5294 | 30000 | 56311762.5 | 80% | 45049410
3 | 2nd | 1877.0587 | 938.5294 | 30000 | 56311762.5 | 80% | 45049410
4 | 3rd | 1771.1225 | 885.5612 | 30000 | 53133675 | 80% | 42506940
5 | 4th | 1654.655 | 827.3275 | 30000 | 49639650 | 80% | 39711720
6 | 5th | 1484.685 | 1484.685 | 30000 | 44540550 | 80% | 35632440
7 | 6th | 1484.685 | 1484.685 | 30000 | 44540550 | 80% | 35632440
8 | 7th | 1484.685 | 1484.685 | 30000 | 44540550 | 80% | 35632440
9 | 8th | 1468.395 | 1468.395 | 30000 | 44051850 | 80% | 35241480
10 | 9th | 1484.685 | 1484.685 | 30000 | 44540550 | 80% | 35632440
11 | 10th | 1484.685 | 1484.685 | 30000 | 44540550 | 60% | 26724330
12 | 11th | 1484.685 | 1484.685 | 30000 | 44540550 | 55% | 24497302.5
13 | 12th | 1484.685 | 1484.685 | 30000 | 44540550 | 50% | 22270275
14 | 13th | 1484.685 | 1484.685 | 30000 | 44540550 | 50% | 22270275
15 | 14th | 1484.685 | 1484.685 | 30000 | 44540550 | 50% | 22270275
16 | 15th | 1498.465 | 1498.465 | 30000 | 44953950 | 40% | 17981580
17 | 16th | 1484.685 |  | 30000 | 44540550 |  | 0
18 | 17th | 1484.685 |  | 30000 | 44540550 |  | 0
19 | 18th | 1484.685 |  | 30000 | 44540550 |  | 0
20 | 19th | 990.59 |  | 30000 | 29717700 |  | 0
21 | OHT / LMR | 160.32 |  | 30000 | 4809600 |  | 0
Sub - Total (A) |  | 30990.9475 | 21796.035 |  | 1022701268 | 57.03% | 583269866.5
PUZZLE PARKING Nos. (B) |  | 300 |  | 500000 | 150000000 |  | 0
TOTAL COST OF CONSTRUCTION (A + B) |  |  |  |  | 1172701268 | 49.74% | 583269866.5